Minutes of a meeting of the

Oxfordshire Growth Board

on Thursday 1 February 2018

Voting members of the Committee present:

| Councillor Bob Price | Chair - Executive Member of Oxford City Council |
| --- | --- |
| Councillor John Cotton | Vice- Chairman - Leader of South Oxfordshire District Council |
| Councillor Barry Wood | Leader of Cherwell District Council |
| Councillor Ian Hudspeth | Leader of Oxfordshire County Council |
| Councillor Matthew Barber | Leader of Vale of White Horse District Council |
| Councillor James Mills | Leader of West Oxfordshire District Council |

Non-Voting members of the Committee present:

| Adrian Lockwood | Vice Chairman and Skills Board Representative |
| --- | --- |
| Professor Alistair Fitt | Universities Representative |
| Kevin Bourner | Homes England Representative |
| Lesley Tims | Environment Agency Representative |

Officers:

| Paul Staines | Oxfordshire Growth Board Partnership Programme Manager |
| --- | --- |
| Patsy Dell | Head of Planning, Sustainable Development & Regulatory Services, Oxford City Council |
| Caroline Green | Assistant Chief Executive, Oxford City Council |
| Gordon Mitchell | Chief Executive, Oxford City Council |
| Peter Clark | Chief Executive, Oxfordshire County Council |
| Christine Gore | Executive Director, West Oxfordshire District Council |
| Bev Hindle | Strategic Director, Oxfordshire County Council |
| Andrew Down | Head of Partnership and Insight, South Oxfordshire and Vale of White Horse District Councils |
| Adrian Colwell | Executive Director for Place and Growth Cherwell and South Northamptonshire Councils |
| Nigel Tipple | Chief Executive, OXLEP |
| Jennifer Thompson | Committee and Members Services Officer, Oxford City Council |

Apologies received from:

Jeremy Long 	Chairman of OXLEP

Phil Shadbolt 	OXLEP Business Representative – Bicester

Andrew Harrison 	OXLEP Business Representative – Science Vale

Richard Venables	OXLEP Business Representative – Oxford City

Louise Patten	Oxfordshire CCG Representative

Attending as observers:

Councillor Susan Brown 	Leader of Oxford City Council

Councillor Judith Heathcoat	Executive Member of Oxfordshire County Council

<AI1>

- Declarations of interest

There were no declarations of interest.

</AI1>

<AI2>

- Minutes of the last meeting

The Board confirmed as a correct record the minutes of the meeting of the Oxfordshire Growth Board held on 30 November 2017.

</AI2>

<AI3>

- Chair's Announcements

The Chair announced that the local authorities in Oxfordshire had been awarded £36m from the Government’s Housing Infrastructure Fund (HIF) Marginal Viability Fund for specific development projects.

</AI3>

<AI4>

- Public Participation

In accordance with the public participation scheme the Chair invited those who had submitted questions to speak to the Board.

The Board had before them:

- written questions submitted by

Colin Thomas on behalf of CPRE Oxfordshire

Charles Mathew, Oxfordshire County Councillor for the division of Eynsham

- and written responses from the Chair.

Colin Thomas asked a supplementary question and the Chair responded.

Councillor Mathew asked a supplementary question and Councillor Hudspeth responded.

Full details of the written and supplementary questions and responses are in the supplement to these minutes.

</AI4>

<AI5>

- Housing and Growth Deal - delivery plan update

Caroline Green reported that Government’s feedback on the final draft of the Delivery Plan was expected shortly and then each council would be asked to consider and decide whether to approve the Deal and Delivery Plan at a series of special co-ordinated council meetings in February.

In approving the Deal councils would be cognisant of the fact that the proposed draft revised NPPF (National Planning Policy Framework) could impact the planning freedoms and the arrangements for the JSSP agreed within the Deal , The Deal brings significant investment in several work strands supporting housing and infrastructure , productivity including skills.

Kevin Bourner, Homes England, outlined the ongoing work on the HIF bids and noted that the Deal puts Oxfordshire in a relatively advantageous position with regard to the HIF Forward Funding Bids. A decision on shortlisting for these bids was expected in March

Board members commented that:

- The Deal was a good start, if with limited funding, and a credit to the work by officers, and was ready to put to each council for consideration.

- The funds should be seen as a down-payment.

- There were concerns over potential changes resulting from the revised NPPF including the impact of any new flexibility.

- The Board needed to ensure that there was no penalty for failure to meet targets due to uncontrollable factors and officers were asked to ensure appropriate wording in the Deal to this effect

- Considerable progress had been made since the announcement in November but the detail and delivery mechanism was not certain yet. Methods for calculating successful delivery were key. The Board welcomed the fact that there was potential for further funding since the Deal whilst significant was only  a small percentage of the requirements and did not for example address the costs of non-transport infrastructure.

The Growth Board resolved:

- to note the ongoing conversations around the Oxfordshire Housing and Growth Deal and delivery plan and the comments at this meeting

- to endorse the progress made on the Oxfordshire Housing and Growth Deal and recommend this to the Oxfordshire Partners subject to satisfactory completion of the Delivery Plan.

</AI5>

<AI6>

- City and Growth Deal Programme reports

Nigel Tipple gave an update on the progress on projects within the City and Growth Deal; and reported that the Environment Agency and partners were still confident the flood alleviation channel could be delivered as planned.

The Growth Board noted the report and the operating plan update.

</AI6>

<AI7>

- Matters arising from OXLEP

Nigel Tipple gave an update on the work of OxLEP.

In summary he outlined:

- Work on funded projects in the Local Growth Fund 3 programme was progressing at a good pace

- There was good progress on remaining Local Growth Fund 1 and Local Growth Fund  2 projects and on City Deal projects as highlighted in the programme reports,

- BEIS (Department for Business, Energy & Industrial Strategy) had confirmed 2 years of funding from BEIS for extended support for the Business Growth Hub

- EU funds running to 2020 were in place including EU social fund programme for developing apprenticeships and working with those far from the workplace: in Oxfordshire about 19,000 people were not working while 16,000 of those were not registered as seeking work.

- OxLEP was piloting The Local Industrial Strategy response, and was starting work towards an agreed delivery-focussed plan to mutually reinforce the Growth Deal over the summer, aiming to submit for funding to start 1 March 2019.

Councillor Price reported that the Local Government Association were putting pressure on the government to set out how the EU funded programmes would continue after 2020.

The Growth Board noted the update.

</AI7>

<AI8>

- Growth Board Forward Plan

The Growth Board considered the updated Forward Plan setting out reports and decisions arising from the draft delivery plan for the Oxfordshire Housing and Growth Deal.

Members noted that the timetable for the Joint Statutory Spatial Plan was very ambitious and depended in part on the contents of the as-yet unpublished new National Planning Policy Framework (NPPF). The Forward Plan may therefore need to be amended in light of the NPPF.

The Growth Board noted the report setting out their Forward Plan, noting that this would be updated to reflect changes arising from the awaited NNPF and delivery of the planning functions of the Deal.

</AI8>

<AI9>

- Oxfordshire Local Plans progress report - January 2018

The Board considered the report setting out the progress towards adoption of Local Plans and noted that South Oxfordshire District Council had delayed submission of their plan until it could be assessed against the new NPPF, and that the statutory 6-week notice period for submission had not been given.

The Growth Board noted the report.

</AI9>

<AI10>

- Oxford to Cambridge corridor - update on progress

Corridor

Members and officers had given evidence to the newly established Oxford-Milton Keynes-Cambridge all-party parliamentary group, and saw this as a useful way of overseeing the processes and decision making.

The consultation on the expressway was set out and would run in parallel with the technical studies. The plans showed he stretch from the M40 to Cambridge but the Board was emphasising the need to connect to Oxford and beyond, and the need for sub-corridor connectivity. The corridor route would be decided in Sumer 2018, public consultation on the route within the corridor would be in Autumn 2019 in two phases, with construction starting in 2025.

Councillor Cotton, who is chairman of a group of leaders of local authorities in the corridor area; Councillor Price; and Nigel Tipple reported on the work on the corridor:

- Corridor leaders had sent a letter welcoming the NIC report and setting out options for on governance and management of the corridor, and received a clear message from NIC that they want to see progress that local authorities can be creative in tackling issues.

- Work on the corridor would be taken forward by the MHCHLG who were seeking a meeting with LA leaders.

- In the budget statement there was a request for LEPs to prepare a collective industrial strategy. LEPS were commissioning work building on Central Bedfordshire’s work on the corridor; a brief was ready to circulate; and requisite meetings set up.

- There was a commitment to fund rail improvements between Bedfordshire and Cambridge by mid-2020s.

The Board noted that a collective vision of the possibilities, ambition for, and potential of this project should be developed by local authorities and managing boards.

Rail connectivity

The Board considered a late report and recommendations submitted by Bev Hindle (Strategic Director for Communities Oxfordshire County Council) setting out information about the Government’s proposed Rail Connectivity Study for Oxfordshire as a result of a meeting held a few days earlier.

Bev Hindle reported that meeting had agreed that a sub-group of the Growth Board and an appropriate governance mechanism may be the most appropriate mechanism to support the Oxfordshire Rail Connectivity Study. The final decision lay with the Department of Transport.

The Growth Board noted proposals in the report to:

- Work with Department for Transport, Network Rail and Oxfordshire train operators to develop a brief and complete the Government’s announced Rail Connectivity Study for Oxfordshire; and

- Provide the governance framework and accountable body role (via Oxfordshire County Council) for the project from conception to completion, including establishing an Oxfordshire Growth Board Rail Sub-Group; and

- Agree to consider providing some element of local match funding in the form of officer capacity to support the completion of this project.

</AI10>

<AI11>

- Sub-national Transport Body (STB) - update

Bev Hindle (Strategic Director for Communities Oxfordshire County Council) reported on discussions about wider infrastructure including superfast cable networks and internet access.

Members of the Board:

- Reported that a consultation about major roads not controlled by Highways England was underway and asked for all councils to consider and respond, as there needed to be serious investment in the major roads such as the A40 and A420 that local authorities could not provide alone.

- Commented that ICT network and broadband infrastructure were crucial for successful businesses but an investment in hardware was not accompanied by an appraisal of its use.  The STB would be able to drive this and give consistency in approach across the corridor

The Growth Board noted the discussion and updates.

</AI11>

<AI12>

- Updates on matters relevant to the Growth Board

There were no updates.

</AI12>

<AI13>

- Dates of next meetings

The Board noted the meeting dates.

</AI13>

<TRAILER_SECTION>

The meeting started at 2.00 pm and ended at 3.15 pm

Chair …………………………..			Date:  Tuesday 27 March 2018

##### </TRAILER_SECTION>

<LAYOUT_SECTION>

- FIELD_TITLE

FIELD_SUMMARY

</LAYOUT_SECTION>

<TITLE_ONLY_LAYOUT_SECTION>

- FIELD_TITLE

</TITLE_ONLY_LAYOUT_SECTION>

<HEADING_LAYOUT_SECTION>

FIELD_TITLE

</HEADING_LAYOUT_SECTION>

<TITLED_COMMENT_LAYOUT_SECTION>

- FIELD_TITLE

FIELD_SUMMARY

</TITLED_COMMENT_LAYOUT_SECTION>

<COMMENT_LAYOUT_SECTION>

FIELD_SUMMARY

</COMMENT_LAYOUT_SECTION>

<SUBNUMBER_LAYOUT_SECTION>

  - field_title

FIELD_SUMMARY

</SUBNUMBER_LAYOUT_SECTION>

<TITLE_ONLY_SUBNUMBER_LAYOUT_SECTION>

  - field_title

</TITLE_ONLY_SUBNUMBER_LAYOUT_SECTION>