# Tenancy Strategy and Policy  City Executive Board 12th September 2012) Appendix B

# Risk Register

| No. | Risk Description Link to Corporate Obj | Gross Risk | Cause of Risk | Mitigation | Net Risk | Further Management of Risk: Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Current Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Score Impact Score: 1 =Insignificant; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Catastrophic Probability Score: 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost Certain |
|  |  | I | P |  | Mitigating Control: Level of Effectiveness: (HML) | I | P | Action: Action Owner: Mitigating Control: Control Owner: | Outcome required: Milestone Date: | Q 1 ((( | Q 2((( | Q 3((( | Q4((( | I | P |
| 1. | Failure to meet statutory deadline for adoption of Strategy and Policy` | 3 | 3 | Inability to meet statutory deadline | Ensure consultation draft approved by CEB in September, consultation deadlines met and final approval by CEB and Council in December 2012 | 2 | 2 | Ensure deadlines met Executive Director | Report to CEB in September Consultation Sept and October 2012 CEB/Council in December 2012 |  |  |  |  |  |  |
| 2. | Failure to consult effectively – specifically with Registered Providers and Tenants | 4 | 3 | Lack of consultation and targeting of consultation | Establish clear consultation plan specifically targeted at Registered Providers and Council Tenants | 2 | 2 | Ensure consultation plan implemented and deadline achieved Housing Strategy and Enabling Manager | Consultation achieved by 31 October 2012 |  |  |  |  |  |  |
| .3. | Negative public and stakeholder understanding / perceptions of tenancy strategy objectives. | 3 | 3 | Failure to communicate objectives and impacts of Tenancy Strategy in Oxford. | Establish clear communication strategy when it is adopted. | 2 | 3 | Publicise on website, in tenant’s newsletters and other publications. Direct notification to Registered Providers in the City . Housing Strategy & Enabling Manager | Publicity and communications in place by March 2013. – |  |  |  |  |  |  |