## Sheet1
COMMUNITY CENTRES ~ High Level Programme of Works (Provisional)
Property | UPRN | Building Type | Work required / Condition | Remedial Date | Budget Cost | Repairing liability | Cost ~ Council | Cost ~ Tenant | Original Building Condition classification | Current Building Condition classification | 2013~14 | 2014~15 | 2015~16 | 2016~17 | 2017~18 |  | TOTAL AMOUNT OF OUTSTANDING MAINTENANCE BACKLOG
0
Asian Cultural Centre | R098 | CC | External repairs and refurbishment | 2013 | 29790 | C | 29790 | 0 | B | B | 29790 | 0 | 0 | 0 | 0 | 29790
Asian Cultural Centre | R098 | CC | Upgrading to building services installation | 2013 | 44800 | C | 44800 | 0 |  |  | 44800 | 0 | 0 | 0 | 0 | 44800
Asian Cultural Centre | R098 | CC | Internal repairs and refurbishment | 2013 | 25810 | C | 25810 | 0 |  |  | 25810 | 0 | 0 | 0 | 0 | 25810
Asian Cultural Centre | R098 | CC | Upgrading to roof and rainwater goods | 2013 | 870 | C | 870 | 0 |  |  | 870 | 0 | 0 | 0 | 0 | 870 | 101270
0
Barton Centre | R098 | CC | External repairs and refurbishment | 2017 | 16500 | C | 16500 | 0 | B | B | 0 | 0 | 0 | 0 | 16500 | 16500
Barton Centre | R098 | CC | Upgrading to building services installation |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Barton Centre | R098 | CC | Internal repairs and refurbishment | 2017 | 18000 | C | 18000 | 0 |  |  | 0 | 0 | 0 | 0 | 18000 | 18000
Barton Centre | R098 | CC | Upgrading to roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34500
0
Blackbird Leys Community Centre |  |  | External repairs and refurbishment | 2017 | 52430 | C | 52430 |  | B | B | 0 | 0 | 0 | 0 | 52430
Blackbird Leys Community Centre |  |  | Upgrading to building services installation | 2017 | 52700 | C | 52700 |  |  |  | 0 | 0 | 0 | 0 | 52700
Blackbird Leys Community Centre |  |  | Internal repairs and refurbishment | 2017 | 20800 | C | 20800 |  |  |  | 0 | 0 | 0 | 0 | 20800
Blackbird Leys Community Centre |  |  | Upgrading to roof and rainwater goods | 2017 | 164100 | C | 164100 |  |  |  | 0 | 0 | 0 | 0 | 164100
[7 empty] | 0 | [8 empty] | 0 | 290030
Bullingdon Community Centre | 09/00179/OWN | CC | External repair and refurbishment | 2015 | 14860 | C | 14860 | 0 | B | B | 0 | 0 | 14860 | 0 | 0 | 14860
Bullingdon Community Centre | 09/00179/OWN | CC | Upgrading to building services installation | 2014 | 17040 | C | 17040 | 0 |  |  | 0 | 17040 | 0 | 0 | 0 | 17040
Bullingdon Community Centre | 09/00179/OWN | CC | Internal repair and refurbishment | 2015 | 22620 | C | 22620 | 0 |  |  | 0 | 0 | 22620 | 0 | 0 | 22620
Bullingdon Community Centre | 09/00179/OWN | CC | Upgrading to roof and rainwater goods | 2015 | 11400 | C | 11400 | 0 |  |  | 0 | 0 | 11400 | 0 | 0 | 11400 | 65920
0
Cheney Community Centre | 09/00622/OWN | CC | No repairing responsibility | 2015 |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cutteslowe Community Centre | 09/00485/OWN | CC | External repair and refurbishment | 2014 |  | C | 0 | 0 | B | B | 25000 | 0 | 0 | 0 | 0 | 25000
Cutteslowe Community Centre | 09/00485/OWN | CC | Upgrading to building services installation | 2013 | 46800 | C | 46800 | 0 |  |  | 46800 | 0 | 0 | 0 | 0 | 46800
Cutteslowe Community Centre | 09/00485/OWN | CC | Internal repair and refurbishment | 2015 |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cutteslowe Community Centre | 09/00485/OWN | CC | Upgrading to roof and rainwater goods | 2014 |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 71800
0
Cutteslowe Pavilion Community Centre |  | CC | External repair and refurbishment | 2013 | 5830 | C | 5830 | 0 | B | B | 5830 | 0 | 0 | 0 | 0 | 5830
Cutteslowe Pavilion Community Centre |  | CC | Upgrading to building services installation | 2015 | 11100 | C | 11100 | 0 |  |  | 0 | 0 | 11100 | 0 | 0 | 11100
Cutteslowe Pavilion Community Centre |  | CC | Internal repair and refurbishment | 2014 | 7110 | C | 7110 | 0 |  |  | 0 | 7110 | 0 | 0 | 0 | 7110
Cutteslowe Pavilion Community Centre |  | CC | Upgrading to roof and rainwater goods | 2013 | 200 | C | 200 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 200 | 24240
0
Donnington Community Centre | 09/00444/OWN | CC | External repair and refurbishment | 2015 | 10000 | C | 10000 | 0 | C | C | 0 | 0 | 10000 | 0 | 0 | 10000
Donnington Community Centre | 09/00444/OWN | CC | Internal repair and refurbishment |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Donnington Community Centre | 09/00444/OWN | CC | Upgrading of building services installation | 2015 | 16200 | C | 16200 | 0 |  |  | 0 | 0 | 16200 | 0 | 0 | 16200
Donnington Community Centre | 09/00444/OWN | CC | Renew roof coverings | 2015 | 75000 | C | 75000 | 0 |  |  | 0 | 0 | 75000 | 0 | 0 | 75000 | 101200
[7 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
East Oxford Community Centre |  | CC | External repair and refurbishment | 2016 |  | C | 125000 | 0 | B | B | 0 | 0 | 0 | 125000 | 0 | 125000
East Oxford Community Centre |  | CC | Internal repair and refurbishment |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
East Oxford Community Centre |  | CC | Upgrading of building services installation | 2015 | 32300 | C | 100000 | 0 |  |  | 0 | 0 | 100000 | 0 | 0 | 100000
East Oxford Community Centre |  | CC | Renew roof coverings |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 225000
[7 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
East Oxford Games Hall | 09/00396/OWN | CC | External repair and refurbishment | 2017 | 17130 | C | 17130 | 0 | C | C | 0 | 0 | 0 | 0 | 17130 | 17130
East Oxford Games Hall | 09/00396/OWN | CC | Internal repair and refurbishment | 2017 | 9440 | C | 9440 | 0 |  |  | 0 | 0 | 0 | 0 | 9440 | 9440
East Oxford Games Hall | 09/00396/OWN | CC | Upgrading of building services installation | 2014 | 5000 | C | 5000 | 0 |  |  | 0 | 5000 | 0 | 0 | 0 | 5000
East Oxford Games Hall | 09/00396/OWN | CC | Replacement roof and rainwater goods | 2017 | 100990 | C | 100990 | 0 |  |  | 0 | 0 | 0 | 0 | 100990 | 100990 | 132560
0
Ferry Community Centre |  | CC | External repair and refurbishment |  |  | C | 0 | 0 | A | A | 0 | 0 | 0 | 0 | 0 | 0
Ferry Community Centre |  | CC | Internal repair and refurbishment |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ferry Community Centre |  | CC | Upgrading of building services installation | 2014 | 5400 | C | 5400 | 0 |  |  | 0 | 5400 | 0 | 0 | 0 | 5400
Ferry Community Centre |  | CC | Replacement roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5400
0
Florence Park Community Centre (& pevious Bowls Club area) |  | CC | External repair and refurbishment | 2015 | 9000 | C | 9000 | 0 | B/C | B/D | 0 | 0 | 9000 | 0 | 0 | 9000
Florence Park Community Centre (& pevious Bowls Club area) |  | CC | Internal repair and refurbishment | 2015 | 53000 | C | 53000 | 0 |  |  | 0 | 0 | 53000 | 0 | 0 | 53000
Florence Park Community Centre (& pevious Bowls Club area) |  | CC | Upgrading of building services installation |  |  | C | 0 | 0 |  |  | 0 | 0 | inc. above | 0 | 0 | 0
Florence Park Community Centre (& pevious Bowls Club area) |  | CC | Replacement roof and rainwater goods | 2015 | 125000 | C | 125000 | 0 |  |  | 0 | 0 | 125000 | 0 | 0 | 125000 | 187000
0
Headington Community Centre | 09/00623/OWN | CC | External repair and refurbishment | 2014 | 15000 | C | 15000 | 0 | B | B | 0 | 15000 | 0 | 0 | 0 | 15000
Headington Community Centre | 09/00623/OWN | CC | Internal repair and refurbishment |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Headington Community Centre | 09/00623/OWN | CC | Upgrading of building services installation | 2013 | 16900 | C | 16900 | 0 |  |  | 16900 | 0 | 0 | 0 | 0 | 16900
Headington Community Centre | 09/00623/OWN | CC | Replacement roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 31900
0
Jericho Community Centre | 09/01044/OWN | CC | External repair and refurbishment | 2017 | 17190 | C | 17190 | 0 | C | C | 0 | 0 | 0 | 0 | 17190 | 17190
Jericho Community Centre | 09/01044/OWN | CC | Internal repair and refurbishment | 2017 | 18762 | C | 18762 | 0 |  |  | 0 | 0 | 0 | 0 | 18762 | 18762
Jericho Community Centre | 09/01044/OWN | CC | Upgrading of building services installation | 2017 | 18050 | C | 18050 | 0 |  |  | 0 | 0 | 0 | 0 | 18050 | 18050
Jericho Community Centre | 09/01044/OWN | CC | Replacement roof and rainwater goods | 2015 | 600 | C | 600 | 0 |  |  | 0 | 0 | 600 | 0 | 0 | 600 | 54602
0
Jubilee 77 Community Centre | 09/00807/OWN | CC | External repair and refurbishment | 2014 | 12890 | C | 12890 | 0 | B | B | 0 | 12890 | 0 | 0 | 0 | 12890
Jubilee 77 Community Centre | 09/00807/OWN | CC | Internal repair and refurbishment | 2016 | 5480 | C | 5480 | 0 |  |  | 0 | 0 | 0 | 5480 | 0 | 5480
Jubilee 77 Community Centre | 09/00807/OWN | CC | Upgrading of building services installation | 2016 | 12200 | C | 12200 | 0 |  |  | 0 | 0 | 0 | 12200 | 0 | 12200
Jubilee 77 Community Centre | 09/00807/OWN | CC | Replacement roof and rainwater goods | 2016 | 57130 | C | 57130 | 0 |  |  | 0 | 0 | 0 | 57130 | 0 | 57130 | 87700
0
Littlemore Community Centre | 09/00806/OWN | CC | External repair and refurbishment | 2017 | 3050 | C | 3050 | 0 | B | B | 0 | 0 | 0 | 0 | 3050 | 3050
Littlemore Community Centre | 09/00806/OWN | CC | Internal repair and refurbishment | 2013 | 20875 | C | 20875 | 0 |  |  | 20875 | 0 | 0 | 0 | 0 | 20875
Littlemore Community Centre | 09/00806/OWN | CC | Upgrading of building services installation | 2017 | 6800 | C | 6800 | 0 |  |  | 0 | 0 | 0 | 0 | 6800 | 6800
Littlemore Community Centre | 09/00806/OWN | CC | Replacement roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30725
0
Northway Community Centre | 09/00625/OWN | CC | Site to be redeveloped |  |  | C | 0 | 0 | B | D | 0 | 0 | 0 | 0 | 0 | 0
0
Regal Community Centre | 09/00180/OWN | CC | External repair and refurbishment | 2014 | 15390 | C | 15390 | 0 | B | B | 0 | 15390 | 0 | 0 | 0 | 15390
Regal Community Centre | 09/00180/OWN | CC | Internal repair and refurbishment | 2014 | 27170 | C | 27170 | 0 |  |  | 0 | 27170 | 0 | 0 | 0 | 27170
Regal Community Centre | 09/00180/OWN | CC | Upgrading of building services installation | 2017 | 15500 | C | 15500 | 0 |  |  | 0 | 0 | 0 | 0 | 15500 | 15500
Regal Community Centre | 09/00180/OWN | CC | Replacement roof and rainwater goods | 2014 | 100547 | C | 100547 | 0 |  |  | 0 | 100547 | 0 | 0 | 0 | 100547 | 158607
0
Risinghurst Community Centre | 09/00624/OWN | CC | External repair and refurbishment | 2017 | 37780 | C | 37780 | 0 | B | A/B | 0 | 0 | 0 | 0 | 37780 | 37780
Risinghurst Community Centre | 09/00624/OWN | CC | Internal repair and refurbishment | 2017 | 12150 | C | 12150 | 0 |  |  | 0 | 0 | 0 | 0 | 12150 | 12150
Risinghurst Community Centre | 09/00624/OWN | CC | Upgrading of building services installation | 2017 | 14020 | C | 14020 | 0 |  |  | 0 | 0 | 0 | 0 | 14020 | 14020
Risinghurst Community Centre | 09/00624/OWN | CC | Replacement roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63950
0
Rose Hill Community Centre | 09/00808/OWN | CC | Health and Safety works only pending redevelopment | 2013 | 40000 | C | 40000 | 0 | C | D | 10000 | 0 | 0 | 0 | 0 | 10000 | 10000
0
South Oxford Community Centre | 09/00381/OWN | CC | External repair and refurbishment | 2014 | 90000 | C | 90000 | 0 | B | B | 0 | 90000 | 0 | 0 | 0 | 90000
South Oxford Community Centre | 09/00381/OWN | CC | Internal repair and refurbishment |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
South Oxford Community Centre | 09/00381/OWN | CC | Upgrading of building services installation | 2014 | 13300 | C | 13300 | 0 |  |  | 0 | 13300 | 0 | 0 | 0 | 13300
South Oxford Community Centre | 09/00381/OWN | CC | Replacement roof and rainwater goods | 2014 | 16900 | C | 16900 | 0 |  |  | 0 | 16900 | 0 | 0 | 0 | 16900 | 120200
0
West Oxford Community Centre | 09/00287/OWN | CC | External repair and refurbishment | 2013 | 1290 | C | 1290 | 0 | A | A | 1290 | 0 | 0 | 0 | 0 | 1290
West Oxford Community Centre | 09/00287/OWN | CC | Internal repair and refurbishment | 2017 | 12225 | C | 12225 | 0 |  |  | 0 | 0 | 0 | 0 | 12225 | 12225
West Oxford Community Centre | 09/00287/OWN | CC | Upgrading of building services installation | 2017 | 3080 | C | 3080 | 0 |  |  | 0 | 0 | 0 | 0 | 3080 | 3080
West Oxford Community Centre | 09/00287/OWN | CC | Replacement roof and rainwater goods |  |  | C | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16595
0
|  |  | Proposed (draft) future years spending | [7 empty] | 228165 | 325747 | 448780 | 199810 | 610697 |  | 1813199
NOTE:~ In addition to these proposed capital budget allocations there is also an annual revenue budget for reactive and planned building services maintenance across all community centres of circa £130,000 per annum.