## cvhtmsrv
Appendix A - Housing Strategy Action Plan - Update to end June 2013 (Sept 2013 CEB)
This plan shows all projects/ tasks that should have been started by this date, including completed projects.
Key Action | Outcomes | Milestone | Due Date | RAG | Comments
Strategic Objective One: Provide More Affordable Housing in the City to Meet Housing Needs
Bring forward new housing schemes and develop a post 2015 programme. | New developments and a post 2015 programme are brought forward. | Working with developers and landowners, identify and bring forward potential sites as funding and economic circumstances allow | Mar 2015 | G | Planning in discussion with landowners on major DPD sites
|  | Bring forward new affordable housing opportunities in any new transformational projects in the City e.g. West End sites, Grenoble Road and new allocated sites | Sep 2014 | G | Ongoing discussion with RPs on redveloping outdated housing stock
|  | Development of a post 2015 affordable housing programme | Sep 2014 | G | In development - As above
Deliver 3 year affordable housing programme: A) provided by Oxford City Council. | 112 new Council homes. | 20 homes at Barton by March 2015 46 homes at Bradlands 46 homes on miscellaneous City sites | Mar 2015 | G | Bradlands scheme approved by Planning Committtee. Planning applications submitted on all other programme sites. CEB approval to let build contract
Deliver 3 year affordable housing programme: B) through partnership with Housing Associations. | 184 affordable homes by March 2015. | New homes at Shotover View (55), Lake St (8) , Lamarsh Road (4), Manor Ground (27), Lanham Way (8), Balfour Rd (9), Luther Court (42), Butler House (14), Lawn Upton House (8), Leiden Rd (9) | Mar 2015 | G | 94 units completed 2012/13 4 units on site - expected to complete August 2013
Deliver 3 year affordable housing programme: C) through physical regeneration projects at Cowley Northway, to deliver new housing and jobs. | 76 affordable homes by March 2015. | Barns Rd (18), Westland Drive (28), Dora Carr Close (30) | Mar 2015 | A | Programme slippage due to planning issues. Consent now given for 75 affordable units - 20 at Barns Road; 21 at Westlands Drive; & 34 at Dora Carr Close. All due to complete by end of 2015.
Develop a Tenancy Strategy to set out the Council’s Policy incorporating tenure and rent policy for affordable housing in the City. | Tenancy Strategy adopted. | Consultation Draft Tenancy Strategy approved – July 12 | Dec 2012 | Completed | Completed
|  | Consultation on Draft Tenancy Strategy completed- Summer 12 | Dec 2012 | Completed | Completed
|  | Tenancy Strategy adopted by end 2012 | Dec 2012 | Completed | Completed
Develop physical regeneration projects at Blackbird Leys to deliver new housing and jobs. | New physical regeneration projects developed at Blackbird Leys. | BBL: Consultation and involvement with Neighbourhood Management Groups and Area Forums to shape Regeneration Strategy by Autumn 2012 | Dec 2012 | Completed | Consultation workshops completed Dec 2012 and reports issued February 2013
|  | BBL: Develop Leys Area Project Plan by December 2012 | Dec 2012 | Completed | Completed.
|  | BBL: Bring forward new sites for development by April 2013 | Apr 2013 | Completed | Minchery Farm site identified - Now part of the Affordable Housing Programme delivering 42 of the 112 units
|  | BBL: Review results of maisonettes options appraisals by December 2012 | Dec 2012 | R | Appraisal will now be undertaken citywide as part of the Asset Mant Strategy. BBL maisonettes to be considered within BBL Regeneration project
|  | BBL: Undertake feasibility analysis and develop schemes by April 2013 | Apr 2013 | A | Preparation of a neighbourhood wide regeneration programme by Dec 2013. Programme plan is now underway due to be completed in draft by end December.
Ensure robust planning policy exists to drive new social housing including via s106 agreements and deliver sustainable homes. | New Sites Plan document. New affordable Housing SPD adopted. Policies adopted requiring financial contribution to affordable housing. | Submission following consultation by May 2012 for examination Sept/Oct 2012 Adopt and implement the Sites and Housing Development Plan Document building on SHLAA by Feb 2013 | Feb 2013 | Completed | Completed
|  | Refresh Local Investment Plan for adoption in June 2012 | Jun 2012 | Completed | Completed
|  | New Affordable Housing SPD: Review consultation by Dec 12, adopt April 2013 | Apr 2013 | A | Consultation completed and final version due to be considerd by CEB in Sept 2013
|  | Adopt policies requiring a financial contribution to support affordable housing (4-9 dwellings, student accommodation) by Dec 12, adopt April 2013 | Apr 2013 | Completed | Completed
Ensure understanding of current and future housing needs is kept up to date and is fit for purpose. | Up to date housing needs and market information. | Analyse and provide data from Oxford Housing Register to inform needs data including demand and availability of specialist accommodation and to ensure new housing meets the aspirations of home seekers by Sept 2012 | Sep 2012 | Completed | Analysis of housing register completed, and data on mobility needs provided to Planning. An updated analysis will be done for 2013. Data on housing register and lettings provided in June 2013 for Strategic Housing Market Assessment.
|  | Review current housing market data by Sept 2012 | Sep 2012 | Completed | Housing market data included in the Homelessness Strategy evidence base. Housing market data for Strategy evidence bases will be updated in 2013.
|  | Review census data as it becomes available | Sep 2013 | Completed | Initial census data reviewed and included in draft Strategy evidence bases. Additional census data will be included in Strategy evidence bases in 2013.
|  | Explore opportunities for commissioning research, including joint commissioning to improve housing needs and market information: and update by April 2013 | Apr 2013 | A | GL Hearn appointed to carry out SHMA for Oxfordshire SPIP (Lead authority West Oxon DC). Interim report due Aug 2013
Preparation for delivery of the new housing development at Barton. | Delivery programme and agreements in place to develop c.800 new homes, including 320 new affordable. | Barton Area Action Plan adopted Dec 2012 | Dec 2012 | Completed | Completed
|  | Barton: Outline planning permission by early 2013 | Mar 2013 | G | Planning application submitted in May 2013. On target for detemination in Sept 2013. Phase 1 marketing on target to start Autumn 2013
Review new delivery models to bring forward new affordable housing to meet needs. | New models evaluated and introduced where feasible. New Council building house programme evaluated and produced. Bring empty property back into use as affordable housing. | Review new opportunities and best practice models with partners and communities including Revitalised Right to Buy, Buy Back, Temporary to permanent social housing project, use of New Homes Bonus, new private sector rented property, Community Land Trusts, Community Infrastructure Levy, Community Right to Acquire by Sept 2013 | Sep 2013 | Completed | Report on homeless accommodation prepared for Sept 13 CEB. 14/15 budget preparation will include consideration of funding for enabling role, including recycling RTB receipts
|  | Review the role of Oxford City Council in developing new homes by reviewing funding opportunities and flexibilities allowed under new HRA funding regime by September 2012 | Sep 2012 | G | Funding in place for 112 new council properties. CEB July 2013 agreed purchase of social rented units at Barton and other properties in open market.
|  | Develop a Council building programme and development process by April 2013 | Apr 2013 | Completed | Completed
|  | Evaluate potential for schemes to bring empty property back into use as affordable housing | Mar 2013 | Completed | One Landlord with 3 empty dwellings has agreed to let his property through the Home Choice Scheme. Surveys sent out each June asking owners what their intentions are for their empty property are collated and those advising that they intend to rent are sent information on the Council's Home Choice Scheme. Currently there is the potential to work with a registered social landlord through the compulsory purchase of an empty dwelling for the purposes of developing the site.
Strategic Objective Two: Prevent Homelessness
Develop services to tackle rough sleeping | No Second Night Out for rough sleepers | Implement new working arrangements for street services for more presence out hours – linked to supported provision. | Jul 2012 | Completed | Oxford City Outreach on 3 year contract until March 2015 with longer and more flexible hours. Any new arrangements will be influenced by Supporting People's remodelling of the pathway.
Develop the role of private rented sector housing in meeting housing needs including homeless households or those threatened with homelessness | Annual meeting of landlord forum Undertake landlord/lettings agencies consultations Undertake consultations with current and prospective private tenants Homelessness Policy reviewed | Undertake a landlord/lettings agencies survey consultation to understand expectations of private landlords by Sept 2012 | Sep 2012 | Completed | All consultation is now complete. The survey was delayed by data protection difficulties which were later resolved.
|  | Develop information and incentives to encourage private landlords to offer accommodation to homeless households or those threatened with homelessness by April 2013 | Apr 2013 | G | On-going work - but full range of incentives provided. Recently signed up to a new insurance related scheme for landlords. Landlord survey completed. Next LL Forum being prepared with Env Devt. New marketing campaign (countywide) planned for Sept 2013
|  | Undertake consultation with prospective and current private sector tenants to undertake their expectations and barriers to investment and attaining a settled home in the private rented sector by Dec 2012 | Dec 2012 | Completed | Consultation complete. Evaluation and analysis now underway.
|  | Consider introducing a private tenants forum by April 2013 | Apr 2013 | Completed | This has been considered and there is currently no appetite or budget for developing a private tenants forum.
|  | Develop information and education current and prospective tenants and Investigate the use of Tenant Ready Schemes by November 2013 | Nov 2013 | G | Tenant Ready schemes in other areas being reseached. Initial discussions with Crisis re providing some training to support such a programme.
|  | Review homeless policy in relation to re-housing in private sector and discharge of duty following legislative change and new guidance by September 2012 | Sep 2012 | Completed | New policy approved by CEB on 13th Feb 2013. To go live from 1st April 2013
Ensure effective debt and welfare advice services are available to the public | Effective debt, welfare advice, services are provided and taken up | Review need and provision of debt and welfare advice/training by April 2013 | Apr 2013 | Completed | Completed
|  | Develop action plan for debt and welfare advice/training to address any gaps, unmet needs and maximise take up by Sept 2012 | Sep 2012 | Completed | Complete
Reduce the number of households in temporary accommodation | Households in temporary accommodation reduced to 120 by 2012/13, 100 by 2013/14, 87 by 2014/15 | Prepare planning and implementation of new forms of temporary accommodation by June 2012 | Jun 2012 | R | Report on new models of Homeless Accommodation Supply to go to CEB on 11th Sept 2013. Number of households in temporary accommodation target was achieved (120 as at 31 Mar 2013). Corporate Targets revised to 120 for 3 yrs due to potential pressures on h'lessness.
Research, consult and adopt a new Homelessness Strategy and Action Plan | New Homelessness Strategy, targets and Action Plan | Review progress since last Homelessness Strategy – May 2012 | May 2012 | Completed | Completed
|  | Produce Homelessness Strategy evidence base and issues by July 2012 | Jul 2012 | Completed | Completed
|  | Undertake consultation on Homelessness Strategy – July - Sept 2012. | Sep 2012 | Completed | Completed
|  | Adopt Homelessness Strategy Dec 2012 | Dec 2012 | Completed | Completed
|  | Publish homelessness Strategy – by end of March 2013 | Mar 2013 | Completed | Completed
Review of allocations policy | New Allocations Policy approved and implemented | Allocations policy review to commence April 2012 | Apr 2012 | Completed | Allocations Reviw underway
|  | Consultations on draft Allocations policy planned to be completed by Sept 2012 (subject to Government Guidance issued) | Sep 2012 | Completed | Delayed (Govt Guidance also delayed), but consultation period on draft Allocations Scheme (approved by CEB on 13th Feb 2013) open from 8th April to 19th May 2013
|  | New Allocations Policy completed by December 2012 | Dec 2012 | R | Timescales revised following delayed Govt Guidance. Draft Allocations Scheme approved for consultation at CEB in Feb 2013. Consultation completed. New proposed Scheme for CEB to recommend to full Council in Sept 2013, with the scheme due to go live in late Autumn 2013.
Strategic Objective Three: Address the Housing Needs of Vulnerable People and Communities
Develop housing strategies for specific vulnerable groups. | New Housing Strategy incorporates needs of young people, older people, BME households and families in difficulty. | Develop evidence base and housing strategy objectives for specialist needs groups – Young people | Sep 2013 | Completed | An evidence base has been produced to feed into cross Council plans and the development of the new Housing Strategy.
|  | Develop evidence base and housing strategy objectives for specialist needs groups - BME | Sep 2013 | G | A draft evidence base is in progress to inform the development of the new Housing Strategy.
|  | Develop evidence base and housing strategy objectives for specialist needs groups – Older people | Sep 2013 | G | This is being re-scheduled to ensure co-ordination and synergy within wider specific strategies being developed across Oxfordshire and City Councils. A draft evidence base is in progress.
|  | Develop evidence base and housing strategy objectives for specialist needs groups – Families in difficulty | Sep 2013 | Completed | Milestone reconsidered and specific work undertaken instead to assist with targeting suitable families for the Thriving Families initiative
Ensure commissioning of services for vulnerable people is co-ordinated across agencies and partnerships to ensure the preservation and most effective use of resources and meets identified need. | Retain or remodel hostel accommodation that provides sufficient bedspaces to meet needs and meaningful activity for clients. Successful re-commissioned services. | Review and implement Supporting People Financial Strategy by March 2013 | Mar 2013 | Completed | Oxford City Council have worked in partnership with Oxfordshire County Council to meet financial targets.
|  | Engage in County Council review for SP services – Single homelessness | Sep 2013 | G | on-going work - progressing well
|  | Engage in re-commissioning of SP funded services – DV | Dec 2013 | G | Successful re-commissioned services.
Ensure hospital discharge is facilitated to reduce ‘bed blocking’. | Effective hospital discharge mechanisms in place. | Review existing hospital discharge protocols, systems and promote awareness – including early warning | Mar 2015 | G | Operational meetings being developed (inc Broadway and Oxford City Housing Options staff) to consider changes to policies (Mental Health and Physical Health discharges). Strategic meeting to be convened by County Council (Adult Social Care) in Aug 13
Ensure housing options are available for people moving through and from supported housing. | Supported housing is available for people who need it and clients are enabled to attain independent living. | Review Move on Plan Protocol, identify barriers and actions to deal annually | Mar 2015 | Completed | New MOPPS process and forms agreed at meeting with providers and all stakeholders on 14th May 2013. Base data and Q1 and Q2 data now received. New approach to now continue with admin support from Oxford City Council on a quarterly basis.
Ensure supply of wheelchair adapted housing to meet needs. | Wheelchair accessible housing is available for households that need it. | Improved knowledge, analysis of need for and provision of fully wheelchair adapted social housing by Sept 2013 | Sep 2013 | G | A report presented to Housing Strategy Delivery Board in June 13. Further assessment of current stock information underway and will be reported on later in 2013
Produce housing guides for older and young people. | Older persons and young persons housing guides published. | Review existing Older persons guide with service users and partners by Dec 2012 | Dec 2012 | R | Item progressing following reorganisation of project. New guide expected in Autumn 2013
|  | Review existing Young persons guide with service users and partners by Dec 2012 | Dec 2012 | Completed | Project reviewed and decision taken that we don't need a separate guide as much of the information is already available elsewhere such as in the Survival Guide.
Re-model hostel to incorporate assessment centre, new referral and move on pathways. | New pathways for rough sleepers implemented. | Work with Supporting People Team to review existing provision with providers with the aim of remodelling services within diminished budgets whilst retaining sufficient bedspaces to meet needs and meaningful activity for clients throughout 2012-14 | Mar 2014 | G | On track. Needs analysis completed. Pathway framework developed and being populated. Districts at officer and member level consulted. A significant project, so new contract start date negotiated (after re-commissioning/ re-modelling) of March 2015
Strategic Objective Four: Improve Housing Conditions
Ensure knowledge of private housing stock and conditions is fit for purpose, enabling strategies and investment to be effective. | Fit for Purpose knowledge of housing stock and standards. | Review existing private housing stock data and gaps by Dec 2012 | Dec 2012 | Completed | BRE stock modelling procured.
|  | Review available census data for private housing stock by Dec 2012 | Dec 2012 | Completed | Reviewed and included in BRE stock modelling methodology.
|  | Recommend methodology to improve knowledge of private housing stock and condition by April 2013 | Apr 2013 | G | Feasibility study for second stage of BRE stock modelling complete. Over 150,000 lines of data to be included in improved data set to inform strategy changes.
Improve energy efficiency and reduce carbon emissions in homes in Oxford and address fuel poverty for households. | Develop integrated Home Energy/Fuel Poverty/Retrofitting strategy/ies. Improved energy ratings, lower carbon emissions in housing in the City. Retro-fitting strategy and implementation for council housing stock. Including external cladding for 5 tower blocks. Zero carbon new build council homes. | Fuel poverty etc: Develop officer group and assess current standards, baselines and issues by Sept 2012 | Sep 2012 | Completed | Completed
|  | Fuel poverty strategy: Consult with partners, residents, energy companies etc by Dec 2012 | Dec 2012 | R | A Government announcement was made in Sep 2012 that the definition of fuel poverty was to change and a refreshed national policy would be developed in 2013. Hence further development work on a Fuel Poverty Strategy and consultations were awaiting government clarification of new fuel poverty agenda. Project now being re-started with new timescales developed to feed into Asset Mant Strategy.
|  | Develop a Strategy to cover issues of home energy, carbon emissions, fuel poverty & retrofitting of homes by April 13 | Apr 2013 | R | See above
|  | Publicity and awareness Promote Green Deal | Mar 2015 | G | The Council is working on projects that will attract ECO funding to improve the energy efficiency of its own housing stock. The 'Green Deal Plus' approach for the city is focussing on working with deprived areas and hard-to-treat homes which can't be easily insulated. This work, in conjunction with the Low Carbon Hub, is drawing into Oxford funds from energy companies under the Energy Company Obligations (ECO) part of the Green Deal. Oxford City Council was recently awarded £310,000 from DECC's Green Deal Pioneer Places fund to develop its approach. This is anticipated to upgrade some of the private sector homes with the lowest energy efficiency rating in Oxford - steel system builds in Barton –with external wall insulation funded by ECO. The Council is also working on projects and developing databases of housing stock information that will inform ECO funding bids to improve the energy efficiency of its own housing stock and thermally poor properties in the private sector in other parts of the city. The city has seven areas in the lowest 15% nationally by Index of Multiple Deprivation – this open the door to another –area based - strand of ECO funding. Discussion are on-going with utility companies on how ECO funds might be drawn down to improve energy efficiency of local houses. A pilot has started in the private rented sector to inspect poor private rented properties based on a very low Energy Performance Certificate rating. This leads to advice on how to thermally upgrade the property and details of how the Green Deal may help fund upgrades, and could lead on to enforcement action against the landlord if they do not upgrade the property. The Green Deal Plus approach links in with the new requirement on the Authority under the Home Energy Conservation Act, and its intentions around fuel poverty reduction across the city, as declared by the council signing up to the End Fuel Poverty Coalition. For more detail see Oxford’s HECA report from March 2013.
|  | Develop specific retrofitting element and programmes for Council stock including external cladding for 5 tower blocks (400 homes) | Dec 2013 | A | This will form part of the Housing Asset Management Strategy to be adopted in April 2014. Project managers for the tower block cladding were commissioned in March 2013.
|  | Set zero carbon target for all new council homes | Mar 2013 | Completed | New council homes will be built to Code for Sustainable Homes Level 4. This is considered to be as close to a zero carbon target that is economically feasible
Improve the quality of individual private rented properties including those used via the Homechoice scheme. | Improvements are made to the quality and management of individual private rented properties. | Review landlord and lettings agencies accreditation schemes by December 2012 | Dec 2012 | Completed | The accreditation scheme was reviewed by December 2012. Increased discounts on HMO licensing fees were introduced and consideration is currently being given to how the scheme could be expanded, possibly using external providers.
|  | Implement new landlord and lettings agencies accreditation schemes from April 2013 | Apr 2013 | A | Consultation exercise not carried out yet. Planned for Q2.
|  | Private rented housing: Consider targeted interventions to tackle specific problems e.g. Hit Squad activities by November 2012 | Nov 2012 | Completed | £150k agreed in reserve for unlawful dwellings. Proactive targeting of landlords underway. Full HHSRS inspections of properties being carried out in reactive cases instead of just dealing with issue being raised by tenant.
Increase the number of individual HMOs subject to agreed licence provisions Baseline = 1100 (2011/12). | Every HMO in the City is inspected and accredited. | 2180 licensed HMOs in 2012/13 | Mar 2013 | Completed | The figure of 2180 licensed HMOs was achieved by 12/13
|  | 2950 Licensed HMOs in 2013/14 | Mar 2014 | G | 2880 licensed so far in 13/14. Target on track to be achieved.
Maximise take up and impact of Home Improvement Loans. | Home Improvement Loans made available to improve standards in private housing. | Ongoing publicity and promotion of Home Improvement Loans including partner organisations e.g. social services, health | Mar 2015 | G | Publicity agreed for Health Watch Guide.
Sustain improvements in the condition of council homes. | Condition of council housing is continually improved. | Evaluate progress made following attainment of Decent Homes Standard, considering aspirations of tenants & availability of funds | Mar 2013 | Completed | Significant investment in Council stock, with additional new kitchens and bathrooms included in the captial programme. A stock condition survey has been commissioned to measure progress. This starts in Sept 13.
|  | Consider setting a Local Oxford Standard for Council homes | Mar 2013 | R | To form part of Housing Asset Management Strategy to be adopted in April 2014.
Work with owners and communities to bring long term empty homes back into use. | New Empty Homes Strategy adopted. 10 long term empty homes returned to use annually. | Empty homes: Review progress to date and barriers/opportunities to increase success by Sept 2012 | Sep 2012 | Completed | Financial support provided through the DCLG Preventing Homelesness grant. The money is to facilitate the carrying out of works in default following the service of a notice and failure to comply. Changes within Env Devt have increased level of support for empty property work. Ongoing support from planning in respect of development of empty dwellings and empty commercial sites.
|  | Empty homes: Investigate procedures and if necessary implement the use of Compulsory Purchase Orders by Nov 2012 | Nov 2012 | G | Working with Planning, Corporate Assets, Legal and Environmental Health to assess potential to CPO a property with a view to partnering an RSL throughout the process.
|  | Empty homes: Undertake consultation and surveys by December 2012 | Dec 2012 | Completed | Talkback survey carried out September 2012 and completed November 2012. Responses commented upon in refreshed Empty Property Strategy 2013-2018. Further consultation in December 2012 using Councils E consult. Responses received for both consultation evaluated and reported upon within the refreshed Empty Property Strategy 2013-2018.
|  | Empty homes: Development of new Empty Homes Strategy by April 2013 | Apr 2013 | Completed | CEB endorsment and approval March 2013.
Strategic Objective Five: Improve Quality, Cost Effectiveness and Efficiency of Housing Services.
Deliver the Demonstration Project for direct payment of benefits to council tenants. | Direct payment of housing benefit to council tenants project successfully completed and lessons learnt. | Direct payments: Scoping of project with DWP and partners by May 2012 | May 2012 | Completed | Complete
|  | Direct payments: Tenants contacted and supported with information and assistance Spring 2012 and beyond | Mar 2015 | G | We continue to derive learning from the project. In particular the arrears process and support provided to tenants is being further developed. Project extended to remaining tenants on HB subject to suitability assessment.
|  | Direct payments: ICT issues resolved and system live by June 2012 | Jun 2012 | Completed | Complete
Develop and improve opportunities for tenants and leaseholders to get involved in managing the delivery of the council’s housing services. | Tenant and Leaseholder Involvement Strategy adopted. Local Offer agreed and implemented. Co-regulation with tenants implemented. | Develop Tenant and Leaseholder Involvement Strategy by September 2012 | Sep 2012 | Completed | Completed
|  | Draft Local Offer prepared with tenants representatives including Local Offer Planning Day to define services and set standards by May 2012 | May 2012 | Completed | Completed
|  | Consultations on Local Offer with all tenants during Spring 2012 | May 2012 | Completed | Completed
|  | Local Offer adopted by September 2012, implemented and reviewed annually in September | Sep 2012 | Completed | Completed
|  | Tenants trained in co-regulation by Summer 2012 | Aug 2012 | Completed | Completed
|  | Detailed implementation of co-regulation including role of member and tenant scrutiny by September 2012 | Sep 2012 | R | External consultants (TPAS) engaged, who recommended more extensive consultation. Strategy agreed Dec 12. Project timescales then revised. Tenant Scrutiny Steering group has been set up & is meeting regularly. The final recruitment & selection of tenants for the panel will take place in Aug 2013 with the first meetings to be held end Sept/early Oct 13.
Develop detailed Landlord Operational Plan to support HRA Business Plan. | A detailed Operational Action Plan exists for Council housing. | A Landlord Operational Action Plan is prepared by Sept 2012 and adopted by Dec 2012 | Dec 2012 | Completed | This has been incorporated into Housing Board structure and Housing Service Plan.
Improve performance in tenancy services. | Improve rent and income collection performance. Reduce rent arrears. Achieve greater VFM for repairs (cost and quality). | Review rent and income collection by November 2012 | Nov 2012 | Completed | Completed
|  | Undertake fundamental review of repairs service by Dec 2012 | Dec 2012 | A | The review is under way - 4 out of 5 workstreams are complete. Final workstream to be delivered in 2013.
Improve the percentage of council tenants satisfied with our landlord services. | 82% tenants satisfied 2012/13. 84% tenants satisfied 2013/14. 86% tenants satisfied 2014/15. | Undertake annual tenant satisfaction survey | Mar 2015 | G | The 2013 STAR survey has been carried out. The final report is due to be released 22 July 2013. Satisfaction at 88% (up 1% from last year)
Manage council housing to ensure it best meets the needs of individual households and tenants and the community as a whole. | Reduce underoccupation freeing up homes for larger households. Overcrowding is reduced in council homes. Actions to tackle and minimise Tenancy Fraud are up to date and effective. | Review under-occupation policies and incentive schemes by December 2012 | Dec 2012 | Completed | Under-occupation Scheme reviewed. Only minor tweaks to payments and publicity suggested - to streamline the way these are presented. Implemented (without need to further sign-off). Further work on under-occupation (of households not on the Housing Register) to be taken forward by Tenancy Mant in 13/14, with Allocations Officer and REMS Officer involved
|  | Review over-crowding and allocations/ transfer policies by October 2012 | Oct 2012 | Completed | Transfer policies and overcrowding considered as part of the overall Allocations Scheme review. Proposed new scheme being reported to CEB in Sept 13.
|  | Review use of pods/extensions to provide enlarged homes for larger households for tenants and prospective tenants by June 2013 | Jun 2013 | A | Review of Overcrowding and Options undertaken. Limited extentions to voids being piloted in 13/14 within existing budgets. Cost estimates to be used to help inform budget decisions (esp HRA Capital budgets) for 14/15 on, and to inform Asset Management Strategy.
|  | Review the implications of new Government guidance or legislation on the policies and work of Tenancy Fraud Team within 4 months of release Publicise | Mar 2015 | G | Awaiting the Statatory Instrument due in the Autumn enabling the Council to obtain data and evidence through the legal gateway. Housing Fraud and the intro of the new criminal offence for subletting social housing included in the July issue Tenants in Touch. Newly appoited p/t specialist housing lawyer appointed.
Review Housing Strategy targets mid term to ensure they are being delivered and refreshed in light of changing circumstances. | Housing Strategy targets are monitored and refreshed. | Housing strategy refresh: Review performance at end of financial year by July 2013 | Jul 2013 | Completed | See main body of report
|  | Housing strategy refresh: Consider policy, performance, trends and wider changes by July 2013 | Jul 2013 | Completed | See main body of report
|  | Housing strategy refresh: Produce progress information, any proposed revisions and consult with partners April to September 2013 | Sep 2013 | A | Consultation to take place after Sept CEB - see main body of report.
|  | Housing strategy refresh: Adopt September 2013 | Sep 2013 | A | To be reported to CEB in Dec 13.
Review policies and services to reduce administration to secure VFM efficiency savings in housing services. | Lower administration costs for low priority housing applications. | Online housing applications by April 2013 | Apr 2013 | R | Project cannot proceed until after the upgrade of the Housing ICT application. Awaiting prioritisation of this upgrade in the City ICT Strategy.
|  | Reduced validation processes for applicants in low housing need by April 2013 | Apr 2013 | Completed | Largely dependant on on-line apps. Validiation process already minimised as far as possible for cases likley to be Band 5 (within existing system)
Review, update and improve housing communications provided by the council. | Housing Communications Plan in place. High quality and relevant housing information is available. New style tenants newsletters produced annually. New Tenants Handbook is produced. Information and on-line reporting of repairs is reviewed. | A housing communications plan is developed by July 2012 | Mar 2013 | Completed | Completed.
|  | Housing publications, publicity and website reviewed on rolling programme | Mar 2015 | Completed | on-going work - 'business as usual'
|  | New tenants and leaseholders newsletter trailed and reviewed with tenants by June 2012 | Jun 2012 | Completed | Newletter issued quarterly in 2012/13. Format to continue in 2013/14. Tenants and leaseholders to be involved in content, design and production as new involvement structure is rolled out.
|  | Tenants Handbooks reviewed with tenants and new version/s published by April 2013 | Apr 2013 | R | The tenant handbook consultation took place in April 2013. The tenancy agreement review project PID is being drawn up to start in Aug 13 with an intended completion date of June 2014. Potential changes required to the tenancy handbook will be tracked alongside the new agreement with a decision on delivery of updates to follow.
|  | Review use and production of Repairs Handbook, information on website and on line reporting of repairs following fundamental review of repairs | Mar 2014 | G | Review will follow on from the Fundamental Review of Repairs.