## cvhtmsrv
Audit Tracker
Ref | Review | Review Date | Issue Noted | Risk Rating | Recommendation | Updater | Owner | Due Date | Forecast Completion Date | % Complete | Comments
EA002 | Certification of Claims and Returns | 23-Mar-2010 | All PC and Laptop Assets recorded with user and location details. All infrastructure Assets to be documented (with photographic evidence where possible) with location details | Medium | The Council should obtain a record of the laptop allocations and confirm their location | Fiona Colcutt | Jane Lubbock | 31-Jan-2011 |  | 99 | As part of the Windows 7 project, all patops have been reallocated and an up-to-date list of asset numbers and their owners/locations prepared. The remaining 5 staff are being updated to Windows 7 in January. Members are due to be upgraded in mid February but most have iPads.
IA506 | BCP | 1-Aug-2013 | Unless the information in BCPs is reviewed and kept up-to-date, the risk is that the plans will be ineffective during a disruption, leading to inability to deliver critical business services. | High | Business Continuity Plans should be reviewed and updated as a minimum on an annual basis or during organisational change. Our review confirmed that this control was not operating effectively. It was noted that version control tables were not consistently used across all Service Area BCPs or were incomplete. It was also noted that nine of the twelve Business Continuity Plans (BCP) had not been reviewed in line with their scheduled review dates. Seven BCPs had not been reviewed for at least 12 months and in four cases the last review took place in excess of two years ago. | LDS Support | Jeremy Thomas | 30-Nov-2013 |  | 50 | Service heads asked to update plans in November 2013 taking account of audit findings and recommendations (email to service heads 29th November 2013). This is in progress and should be complete by the end of March
IA507 | BCP | 1-Aug-2013 | Failure to identify all dependencies of Service Area critical activities could result in unforeseen | High | It was noted that dependencies on third party providers for delivery of critical activities are not mapped or considered should the Service Area be disrupted. It was noted that dependencies on third party providers for delivery of critical activities are not mapped or considered should the Service Area be disrupted. Within Service Area BCPs listings are provided of vital documents and equipment (such as keys, photocopiers and personal protective equipment) that would be required to recover to business as usual (BAU) levels. However, currently insufficient and incomplete details are provided in respect of: ? Document’s location, document owner and the availability of soft or hardcopy backups, and recovery priorities, ? Location of keys critical to Direct Services, Housing and Environmental Health, ? Details of how mail is to be re-directed. | LDS Support | Jeremy Thomas | 31-Dec-2013 |  | 50 | Recovery requirements to be reviewed by service heads as part of the respective BCP reviews, this is in progress and should be complete by the end of March
IA509 | BCP | 1-Aug-2013 | Inconsistent plans could result in key information required for successfully service recovery being omitted. | Medium | Review of the Service Area BCPs established that a common template was used for the plans with some customisation in the case of Law and Governance, Customer Services and Direct Services. Business Impact Analysis used in the Customer Services template showed elements of good practice in defining in more detail resource requirements for recovery. In the case of the Corporate Property plan a unique template was used which did not conform with good practice requirements in several areas: ? Defining critical activities and recovery times ? Defining the roles and responsibilities for initiating and managing service recovery ? Plan owners and maintainers ? Insufficent details on action to take for initial response and staged recovery ? Detailed resource requirements covering IT systems, equipment and documents and how they will be made available ? Defining key service dependencies | LDS Support | Jeremy Thomas | 31-Mar-2014 |  | 50 | Customer Services BCP circulated to all services as an example of good practice (November 2013). This has been used as part of the update process
IA510 | Asset Management | 1-Dec-2013 | Some areas were unclear with regard to the linkage between actions and objectives and to the Corporate Plan. | Medium | Future iterations should ensure that objectives are linked to those in the Corporate Plan, and that objectives, actions, targets and measures are linked together. With an executive summary included for the key messages and conclusions. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA511 | Asset Management | 1-Dec-2013 | The strategy includes a risk register,however this should include the the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Medium | Risk register to include the the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA512 | Asset Management | 1-Dec-2013 | The plan whilst strategic and policy driven in some instances is not specific. The general approach to management is included but this does not include an asset by asset breakdown or details of the future holding strategy. Reference should be included to how the Council manages assets on a day to day basis. | Medium | Plan to include reference to how the Council manages assets on a day to day basis. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA513 | Asset Management | 1-Dec-2013 | A section should be included on the review proces which is undertaken on completion of key projects and the capital programmes. | Medium | A section should be included on the review proces which is undertaken on completion of key projects and the capital programmes. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA514 | Asset Management | 1-Dec-2013 | The document is vague on the portfolio strategy, this hsould be expanded beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Medium | Expand portfolio strategy beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA515 | Asset Management | 1-Dec-2013 | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets whicha re identified as problems/low return. | Medium | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets whicha re identified as problems/low return. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA516 | Asset Management | 1-Dec-2013 | There needs to be a definition included of the levels of the strategy, sub-geographices and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Medium | There needs to be a definition included of the levels of the strategy, sub-geographices and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA517 | Asset Management | 1-Dec-2013 | There needs to be challenge on the curent use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Medium | There needs to be challenge on the curent use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA518 | Asset Management | 1-Dec-2013 | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Medium | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA519 | Asset Management | 1-Dec-2013 | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Medium | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Richard Hawkes | Richard Hawkes | 31-Mar-2014 |  | 0 | recommendation agreed
IA521 | Cash and Card Receipts Review | 7-Feb-2014 | Our review identified items in the suspense account which are dated back to 2010. The Council has not identified where these items should be allocated and therefore they have remained in the suspense account for a length of time. The status of all items in the suspense account was discussed with the total amount unallocated being £28,097.85. | Medium | Items are not cleared on a timely basis, and failure to allocate payments to an account can lead to errors in customer accounts. | Pete Johnson | Pete Johnson | 28/2/14 |  | 75 | Current balance has been reviewed and cleared. Going forward a process has been set up to clear down untraceable cash income to a cash reserve, we will review current suspense balance and allocated accordingly in a timely manner. Remaining balances will be cleared on a 6 monthly cycle.
IA508 | BCP | 1-Aug-2013 | A lack of information contained within BCPs which is necessary for recovery could result in unforeseen delays and ineffective co-ordination of recovery activities. | Medium | The Overarching Corporate BCP provides the strategic approach to recovery of critical activities, however the requirements have not been met within Service Area BCPs including: ? Defining the person/role responsible for invoking the BCP. ? Guidance within Service Area BCPs on the process for incurring expenditure as part of the recovery, including defining who has authority to approve spend. ? The stand-down process to be adopted should recovery arrangements need to be stopped altogether or transitioned to ‘business as usual’. ? The Corporate Plan, Direct Services, Leisure and Parks had key staff contact details missing or incomplete | LDS Support | Jeremy Thomas | 31-Dec-2013 |  | 50 | Critical activities list reviewed at CMT January 2014 (6th January) and links made to system disaster recovery arrangements. Service area BCP reviews to reflect audit requirements.
IA396 | HR Policy Review | 1-Mar-2013 | Performance Improvement Policy- The staff expectations section within the policy is limited and there is little information on how staff can maintain or improve performance. | Medium | A section is added in the policy for staff on how they can maintain or improve their own performance | Simon Howick | Simon Howick | 1-Apr-2013 |  | 70 | First draft was expected by 30/09/13 for consultation with trade unions thereafter. Delay in producing paper due to other priorities. First draft now seen and revisions being made, going to TU's early 2014
IA172 | ICT | 27-Apr-2010 | We were informed that no user access reviews have been performed recently, to determine who has access to particular network shared drives and if the access rights granted are appropriate. Similarly no formal reviews have been performed to determine and validate the level of access available to users in the applications such as CRM and Iworld. | Medium | The user access rights to network shares should be reviewed, to ensure that only authorised City Council staff can access the specific network shares they are entitled to access. Formal reviews covering user access rights within applications in the system should be performed to identify any remove any excess privileges available to users. | Fiona Colcutt | Jane Lubbock | 30-Apr-2010 |  | 99 | All admin rights have been removed for Windows 7 ysers. Approximately 5 staff left to upgrade in January. (This figure does not include Members who are scheduled for upgrade in mid Febraury). Staff are no longer able to download any software onto their laptops, giving the Council control of the applications used.
IA523 | Cash and Card Receipts Review | 7-Feb-2014 | Whilst the Council are moving towards becoming cash free there is no regular monitoring of the cash payments which are being received. | Low | The increase in cash intake during the year to date is not in line with the Council?s objective of reducing cash payments; failure to monitor and identify the reasons for increases could result in the Council not being able to put in place appropriate actions to reduce cash payments. | Pete Johnson | Pete Johnson | 31/4/14 |  | 30 | A report is being generated within PARIS to faciliate further investigation.
IA401 | Health and Safety:Housing Stock and Corporate Assets | 1/8/13 | The data on Uniform system is not upto date | Low | The electrical inspections data is uploaded to ensure the Uniform system is upto date and a key performance indicator is introduced that all repairs data is communicated to the Corporate Property Team within 14 days | Steve Stansfield | Steve Stansfield | 2013-12-31 |  | 100 | Information is now upto date on Uniform
IA402 | Health and Safety:Housing Stock and Corporate Assets | 1/8/13 | The reports currently being run for monitoring purposes are not as effective as they could be due to the electrical data on Uniform not being up to date | Low | The electrical inspections data is uploaded to ensure the Uniform system is up todate | Steve Stansfield | Steve Stansfield | 2013-12-31 |  | 75 | Further work is being carried out on the reporting and communication of the repair data to ensure Uniform is updated timely
IA520 | General Ledger | 1-Jan-2014 | Reconciliations for Accounts Receivable and Housing Benefits are reviewed but no date is added so unable to tell if review was timely. =- No evidence of review of Payroll Reconciliations. | Low | Reconciliations are not reviewed in a timely manner | Anna Winship | Anna Winship | 31-Jan-2014 |  | 100 | These reconciliations were reviewed in a timely manner, however were not evidienced, this has now been amended and all reviews are now dated
IA522 | Cash and Card Receipts Review | 7-Feb-2014 | A review of the listing of members of staff with access to Paris system identified a member of staff who had left the Council on the 31 August 2013 who still had access to the system at the time of our review. | Low | Risk of unauthorised access to the system and changes to data. | Pete Johnson | Pete Johnson | 31/4/14 |  | 100 | Review undertaken as part of the PARIS upgrade, and going forward ICT will pick up as part of the leavers process
IA524 | Risk Management & Performance Improvement | 7-Feb-2014 | For two of the five service areas tested, the risk registers were incomplete for one of the months. In both cases the current and residual risk score were not completed. | Low | Risks are not being recorded which means they cannot be monitored. | Anna Winship | Anna Winship | 31/4/14 |  | 100 | Monthly reviews are now carried out to ensure Risks are updated on Corvu in a timely manner.
IA525 | Risk Management & Performance Improvement | 7-Feb-2014 | For one of the five service areas tested, the full summary of the risk portfolio did not contain any controls information for one of the risks. | Low | The risk is not mitigated with controls. | Anna Winship | Anna Winship | 31/4/14 |  | 85 | Training is to be carried out so that all updaters are aware of the information that needs to be provided in Corvu
IA526 | Risk Management & Performance Improvement | 7-Feb-2014 | For the month of December, four out of five Corporate risks on Corvu had not been updated with a current score, and five out of five risks had not been updated with a residual score prior to reports being run. These risks were subsequently updated through manual intervention but the corporate risk register should be updated on a quarterly basis from complete and accurate data held on Corvu. | Low | Risks are not being monitored in a timely manner. | Anna Winship | Anna Winship |  |  | 100 | Monthly reviews are now carried out to ensure Risks are updated on Corvu in a timely manner.
IA527 | Risk Management & Performance Improvement | 7-Feb-2014 | In quarter 1, risk management information was not reported to the Audit and Governance Committee. | Low | Risks are not being reported in a timely manner. | Anna Winship | Anna Winship |  |  | 100 | Risks will be reported to A&G on a quarterly basis.
IA528 | Risk Management & Performance Improvement | 7-Feb-2014 | Council?s Operating Framework contains a template to be followed for the documentation of all risks (para 4.6).However, from viewing the risk registers on CorVu, they are not all consistent with this template. There is no Corporate Objective section on CorVu, and the required template does not include control information, which is included in the ?Formal Summary? on CorVu. | Low | Staff do not understand fully the requirements of the CorVu system. | Anna Winship | Anna Winship |  |  | 85 | Training is to be carried out so that all updaters are aware of the information that needs to be provided in Corvu
IA529 | Housing Benefits | 7-Feb-2014 | Each month random checks are performed on claims processed. Once the checks have been performed the feedback and errors are recorded on a checking form which is returned to the assessor for them to make the amendments on the system (Academy). A sample of 25 were tested to confirm that the check sheet has been appropriately completed and that any errors were subsequently addressed. 1/25 tested we found that the quality reviewer noted that an amendment was required, this had not been made. The error identified did not have a financial impact. | Low | Overpayments from uncorrected errors. | Sharon Warner | Sharon Warner |  |  | 100 | A monthly review is undertaken by the Benefits manager to ensure that these are all picked up at the end of every month
IA530 | Housing Benefits | 10-Feb-2014 | The total overpayments as at November 2013 were œ4.75m which is approximately 3.8% greater than the total at the same time last year. While an increased amount has been written off, that is œ0.21m compared to œ0.1m in 2012/13, a further review of the amounts is required. | Low | Increase in overpayments leading to losses to the council. | Sharon Warner | Sharon Warner |  |  | 100 | We continue to monitor the level of overpayments and continually consider those for write off where appropriate
IA531 | Housing Benefits | 31-Mar-2014 | The target for processing new claims and changes of circumstances has not been achieved in 2012/13. The time taken to process changes of circumstances has decreased from an average of 12.31 days in 2011/12 to 12.10 days in 2012/13; this is higher than the Council?s 10 day target. The time taken to process new claims has increased from an average of 17.95 days in 2011/12 to 23.17 days in 2012/13 this is over the target of 14 days. | Low | The target for processing new claims and changes of circumstances has not been achieved in 2013/14. There has been an improvement in the performance in this area; targets have still not been met. The average time taken to process a change of circumstance is 10.67 (target 10 days) and the time to process a new claim is 18.76 (target 14 days). The service provided to customers in 2013/14 is now 54% faster than in 2012/13 and this shows that the performance is improving. | Sharon Warner | Sharon Warner |  |  | 75% | The service provided to customers in 2013/14 is now 54% faster than in 2012/13 and this shows that the performance is improving. This is monitored on a weekly basis by the Revenues Manager
IA532 | Housing Benefits | 10-Feb-2014 | During the 2012/13 review we found issues with performing quality checks on a consistent basis, we found: ? Quality checks in 2012/13 only started in mid-October following a restructure during which time checks were suspended. ? Our review showed that the target for quality checking was not met during the two months which we tested (November and December). The following was agreed: Checks will be carried out consistently on a monthly basis throughout the remainder of the year and the new target will be achieved on a monthly basis. | Low | We found that the 10% quality checking target was not met in 1 of the 5 months tested. | Sharon Warner | Sharon Warner |  |  | 75% | A 10% check is carried out most days, The team are committed to meeting this target and expect to achieve this by the end of March.
Mon Feb 10 10:57:52 2014 |  | 1