## cvhtmsrv
Audit Tracker
Ref | Review | Review Date | Issue Noted | Risk Rating | Recommendation | Updater | Owner | Due Date | Forecast Completion Date | % Complete | Comments
EA050 | Certification of Claims and Returns | Nov 2013 | Ensure sufficient staff are available to complete Housing Benefit workbooks and respond to audit queries | High | Agreed - Additional team member in place and for 2013/14 there will be on less workbook as CT Benefit will no longer be part of the claim | Pauline Hull | Helen Bishop | 31/3/14 |  | 100 | Actions agreed and completed
EA052 | Certification of Claims and Returns | Nov 2013 | Review housing benefit assessments completed in 2013/14 to identify impact of errors identified in 2012/13. If necessary take action to reduce the impact | High | as 100% check of student income claims, more testing has taken place across the range of claims | Pauline Hull | Helen Bishop | 31/3/14 |  | 100 | Actions agreed and completed
EA053 | Certification of Claims and Returns | Nov 2013 | Improve training for all temporary staff employed by the Council assessing Housing Benefit Claims | High | The use of temporary staff has been reduced. The only temporary staff used are those who have been used before and produce good work. They are only used when there is a specific need | Sharon Warner | Helen Bishop | 31/3/14 |  | 100 | Actions agreed and completed
EA054 | Certification of Claims and Returns | Nov 2013 | Review work of temporary assessors as soon as possible to ensure that they are making accurate assessments | High | this is less likely to be an issue as fewer temporary staff are being used. | Sharon Warner | Helen Bishop | 31/3/14 |  | 100 | Actions agreed and completed
EA002 | Certification of Claims and Returns | 23-Mar-2010 | All PC and Laptop Assets recorded with user and location details. All infrastructure Assets to be documented (with photographic evidence where possible) with location details | Medium | The Council should obtain a record of the laptop allocations and confirm their location | Fiona Colcutt | Jane Lubbock | 31-Jan-2011 |  | 100 | As part of the Windows 7 project, all laptops have been reallocated and an up-to-date list of asset numbers and their owners/locations is now available. We are also exploring as a separate project, inputting this information into Support Works. There are a few XP laptops left to be upgraded, however we know the locations of these.
EA051 | Certification of Claims and Returns | Nov 2013 | Student Income: provide training on the correct treatment of student grant and loan income | Medium | 100% check undertaken to identify any errors and inform training programme. Training delivered | Pauline Hull |  | 31/3/14 |  | 100 | Actions agreed and completed
EA055 | Certification of Claims and Returns | Nov 2013 | Child Care Disregard: provide training to standardise the approach and how to record the calculation | Medium | These claims will be subject to a 100% check. Doing this will help us develop a consistent approach to these claims | Pauline Hull |  | 30/5/14 |  | 50 | Agreed and in progress
EA056 | Certification of Claims and Returns | Nov 2013 | Complete reconciliation of subsidy to software balancing report to resolve differences between the two | Medium | The aim is to balance direct payments claims earlier to identify potential problems | Pauline Hull |  | 30/5/14 |  | 50 | Agreed and in progress
EA057 | Certification of Claims and Returns | Nov 2013 | For the three cases where the Council was unable to recalculate the amount of subsidy, complete additional work to complete the recalculation so that the Council understands how the benefit paid was calculated | Medium | recalculate to understand how the benefit paid was calculated | Pauline Hull |  | 30/5/14 |  | 50 | Agreed and in progress
IA506 | BCP | 1-Aug-2013 | Unless the information in BCPs is reviewed and kept up-to-date, the risk is that the plans will be ineffective during a disruption, leading to inability to deliver critical business services. | High | As part of the requirements of the British Standard 25999-1 (2006) Business Continuity Plans should be reviewed and updated as a minimum on an annual basis or during organisational change. Our review confirmed that this control was not operating effectively. The Council has experienced changes in organisational structure, office locations, changes in management and an increase in home working, subsequently the plans had not been updated to reflect these changes. It was noted that version control tables were not consistently used across all Service Area BCPs or were incomplete. It was also noted that nine of the twelve Business Continuity Plans (BCP) had not been reviewed in line with their scheduled review dates. Seven BCPs had not been reviewed for at least 12 months and in four cases the last review took place in excess of two years ago. | LDS Support | Jeremy Thomas | 30-Nov-2013 | 30/5/14 | 50 | Service heads asked to update plans November 2013 taking account of audit findings and recommendations , some revised versions now received. A reminder has been send out in April with a revised deadline of completion of end of May
IA507 | BCP | 1-Aug-2013 | Failure to identify all dependencies of Service Area critical activities could result in unforeseen | High | It was noted that dependencies on third party providers for delivery of critical activities are not mapped or considered should the Service Area be disrupted. It was noted that dependencies on third party providers for delivery of critical activities are not mapped or considered should the Service Area be disrupted. Furthermore, resource requirements in Service Areas Business Continuity Plans (BCPs) provide numbers of workspaces required at the recovery site but do not provide guidance as to which Service Area roles/officers would be required to work from the recovery site. Within Service Area BCPs listings are provided of vital documents and equipment (such as keys, photocopiers and personal protective equipment) that would be required to recover to business as usual (BAU) levels. However, currently insufficient and incomplete details are provided in respect of: ? Document’s location, document owner and the availability of soft or hardcopy backups, and recovery priorities, ? Location of keys critical to Direct Services, Housing and Environmental Health, ? Details of how mail is to be re-directed. | LDS Support | Jeremy Thomas | 31-Dec-2013 | 30/5/14 | 50 | Service heads asked to update plans November 2013 taking account of audit findings and recommendations , some revised versions now received. A reminder has been send out in April with a revised deadline of completion of end of May
IA521 | Cash and Card Receipts Review | 7-Feb-2014 | Our review identified items in the suspense account which are dated back to 2010. The Council has not identified where these items should be allocated and therefore they have remained in the suspense account for a length of time. The status of all items in the suspense account was discussed with the total amount unallocated being œ28,097.85. | Medium | Items are not cleared on a timely basis, and failure to allocate payments to an account can lead to errors in customer accounts. | Pete Johnson | Pete Johnson |  |  | 100 | All balances over 6 months old have been cleared to a cash reserve. Daily reconciliation and review is done on this account and any balances over 6 months old will be cleared out on a monthly basis
IA172 | ICT | 27-Apr-2010 | We were informed that no user access reviews have been performed recently, to determine who has access to particular network shared drives and if the access rights granted are appropriate. Similarly no formal reviews have been performed to determine and validate the level of access available to users in the applications such as CRM and Iworld. | Medium | The user access rights to network shares should be reviewed, to ensure that only authorised City Council staff can access the specific network shares they are entitled to access. Formal reviews covering user access rights within applications in the system should be performed to identify any remove any excess privileges available to users. | Fiona Colcutt | Jane Lubbock | 30-Apr-2010 |  | 100 | All admin rights have been removed for Windows 7 users. Approximately 3 staff left to upgrade. Members have been upgraded. Staff are no longer able to download any software onto their laptops, giving the Council control of the applications used.
| Town Hall Income Review | March 2014 | Cash received at the Town Hall is physically taken to the Finance team, there is no record or signature retained to confirm that the cash has been passed onto Finance | Medium | A process should be put in place to ensure that each time cash is taken to finance documentation is retained showing the amount and what it relates to, this will also be signed by the recipient of the cash to confirm they have accepted it | Richard Clements | Simon Howick | immediately |  | 100 | Process now in place that all cash taken to finance is signed for and the documentation for this is retained
IA396 | HR Policy Review | 1-Mar-2013 | Performance Improvement Policy- The staff expectations section within the policy is limited and there is little information on how staff can maintain or improve performance. | Medium | A section is added in the policy for staff on how they can maintain or improve their own performance | Simon Howick | Simon Howick | 1-Apr-2013 |  | 100 | policy now updated and awaiting Council approval
IA510 | Asset Management | 1-Dec-2013 | Some areas were unclear with regard to the linkage between actions and objectives and to the Corporate Plan. | Medium | Future iterations should ensure that objectives are linked to those in the Corporate Plan, and that objectives, actions, targets and measures are linked together. With an executive summary included for the key messages and conclusions. | Lorraine Newman-Robson | Richard Hawkes | 31-Oct-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA511 | Asset Management | 1-Dec-2013 | The strategy includes a risk register, however this should include the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Medium | Risk register to include the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA512 | Asset Management | 1-Dec-2013 | The plan whilst strategic and policy driven in some instances is not specific. The general approach to management is included but this does not include an asset by asset breakdown or details of the future holding strategy. Reference should be included to how the Council manages assets on a day to day basis. | Medium | Plan to include reference to how the Council manages assets on a day to day basis. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA513 | Asset Management | 1-Dec-2013 | A section should be included on the review process which is undertaken on completion of key projects and the capital programmes. | Medium | A section should be included on the review process which is undertaken on completion of key projects and the capital programmes. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA514 | Asset Management | 1-Dec-2013 | The document is vague on the portfolio strategy, this should be expanded beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Medium | Expand portfolio strategy beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA515 | Asset Management | 1-Dec-2013 | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets which re identified as problems/low return. | Medium | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets which a re identified as problems/low return. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA516 | Asset Management | 1-Dec-2013 | There needs to be a definition included of the levels of the strategy, sub-geographies and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Medium | There needs to be a definition included of the levels of the strategy, sub-geographies and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA517 | Asset Management | 1-Dec-2013 | There needs to be challenge on the current use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Medium | There needs to be challenge on the current use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA518 | Asset Management | 1-Dec-2013 | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Medium | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA519 | Asset Management | 1-Dec-2013 | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Medium | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Richard Hawkes | 31-Mar-2014 | 31/10/14 | 50 | Actions will be addressed in new Asset Management Plan scheduled to be issues to CEB October 2014.
IA508 | BCP | 1-Aug-2013 | A lack of information contained within BCPs which is necessary for recovery could result in unforeseen delays and ineffective co-ordination of recovery activities. | Medium | The Overarching Corporate BCP provides the strategic approach to recovery of critical activities, however the requirements have not been met within Service Area BCPs including: ? Defining the person/role responsible for invoking the BCP. ? Guidance within Service Area BCPs on the process for incurring expenditure as part of the recovery, including defining who has authority to approve spend. ? The stand-down process to be adopted should recovery arrangements need to be stopped altogether or transitioned to ‘business as usual’. ? The Corporate Plan, Direct Services, Leisure and Parks had key staff contact details missing or incomplete | LDS Support | Jeremy Thomas | 31-Dec-2013 | 30/5/14 | 25 | Service heads asked to update plans November 2013 taking account of audit findings and recommendations , some revised versions now received. A reminder has been send out in April with a revised deadline of completion of end of May
| Community centres and associations | April 2014 | 1 of 19 community centres has a signed lease agreement. The remaining community centres have less formal agreements in place | Medium | Agree with each centre to get a lease agreement signed | Angela Cristofoli | Ian Brooke | immediately |  | 25 | Federation meeting with lead Councillors planned for June. Key documentation agreed internally
IA509 | BCP | 1-Aug-2013 | Inconsistent plans could result in key information required for successfully service recovery being omitted. | Medium | Review of the Service Area BCPs established that a common template was used for the plans with some customisation in the case of Law and Governance, Customer Services and Direct Services. Business Impact Analysis used in the Customer Services template showed elements of good practice in defining in more detail resource requirements for recovery. In the case of the Corporate Property plan a unique template was used which did not conform with good practice requirements in several areas: ? Defining critical activities and recovery times ? Defining the roles and responsibilities for initiating and managing service recovery ? Plan owners and maintainers ? Insufficient details on action to take for initial response and staged recovery ? Detailed resource requirements covering IT systems, equipment and documents and how they will be made available ? Defining key service dependencies | LDS Support | Jeremy Thomas | 31-Mar-2014 | 30/5/14 | 50 | Service heads asked to update plans November 2013 taking account of audit findings and recommendations , some revised versions now received. A reminder has been send out in April with a revised deadline of completion of end of May
IA531 | Housing Benefits | 31-Mar-2014 | The target for processing new claims and changes of circumstances has not been achieved in 2012/13. The time taken to process changes of circumstances has decreased from an average of 12.31 days in 2011/12 to 12.10 days in 2012/13; this is higher than the Councils 10 day target. The time taken to process new claims has increased from an average of 17.95 days in 2011/12 to 23.17 days in 2012/13 this is over the target of 14 days. | Low | The target for processing new claims and changes of circumstances has not been achieved in 2013/14. There has been an improvement in the performance in this area; targets have still not been met. The average time taken to process a change of circumstance is 10.67 (target 10 days) and the time to process a new claim is 18.76 (target 14 days). The service provided to customers in 2013/14 is now 54% faster than in 2012/13 and this shows that the performance is improving. | Sharon Warner | Sharon Warner |  |  | 75 | The final year results for 2013/14 were the best for over 3 years. Processing times for Change in circumstances came in under target and new claims were only slightly over target. Following refinements of proccesses, the first week of 2014/15 has shown that the work done over the past 18 months will enable both targets to be met in 2014/15. Stats are reviewed on a weekly basis and any patterns or areas of concern are identified and work plans drawn up.
IA525 | Risk Management & Performance Improvement | 7-Feb-2014 | For one of the five service areas tested, the full summary of the risk portfolio did not contain any controls information for one of the risks. | Low | The risk is not mitigated with controls. | Anna Winship | Anna Winship |  |  | 100 | Training has been carried out to ensure all key updaters in all service areas are aware of the information that needs to be provided in Corvu
IA528 | Risk Management & Performance Improvement | 7-Feb-2014 | Councils Operating Framework contains a template to be followed for the documentation of all risks (para 4.6).However, from viewing the risk registers on CorVu, they are not all consistent with this template. There is no Corporate Objective section on CorVu, and the required template does not include control information, which is included in the ?Formal Summary? on CorVu. | Low | Staff do not understand fully the requirements of the CorVu system. | Anna Winship | Anna Winship |  |  | 100 | Training has been carried out to ensure all key updaters in all service areas are aware of the information that needs to be provided in Corvu
IA532 | Housing Benefits | 10-Feb-2014 | During the 2012/13 review we found issues with performing quality checks on a consistent basis, we found: ? Quality checks in 2012/13 only started in mid-October following a restructure during which time checks were suspended. ? Our review showed that the target for quality checking was not met during the two months which we tested (November and December). The following was agreed: Checks will be carried out consistently on a monthly basis throughout the remainder of the year and the new target will be achieved on a monthly basis. | Low | We found that the 10% quality checking target was not met in 1 of the 5 months tested. | Sharon Warner | Sharon Warner |  |  | 100 | The process has been refined since we missed the target and since October, we have hit the 10% each month and in some months, exceeded the checking.
| Town Hall Income Review | March 2014 | Details are manually entered into Agresso from an invoice generated in Artifax. No reconciliation is performed between the two - our findings did no find any instances where the figures were different | Low | Team leader authorises and reviews the input into Agresso | Richard Clements | Simon Howick | 31/12/13 |  | 100 | Process in place for invoices to be authorised and checked when appropriate
| Town Hall Income Review | March 2014 | There are no controls in place for identifying all bookings in Artifax where an invoice has not been raised. All bookings may no be invoiced resulting in loss of income | Low | The authority will enquire with the providers of Artifax whether the system can produce reports highlighting bookings which have no been invoiced | Richard Clements | Simon Howick | immediately |  | 100 | Artifax does not provide this information. However, we now have increased the number of checks we have to ensure that invoices are not missed
| Town Hall Income Review | March 2014 | A sample of 25 invoices raised in artifax during the year was tested and it was found that 2 of the 25 had not been authorised | Low | Staff will be reminded of the need to appropriately carry out authorisation | Richard Clements | Simon Howick | 31/12/13 |  | 100 | Staff have been reminded of this and authorisation is done when appropriate
| Town Hall Income Review | March 2014 | A sample of 25 invoices raised in artifax during the year was tested and it was found that 2 of the 25 had not been authorised | Low | The process for retaining invoices will be reviewed and action will be taken to ensure that a record of all invoices is appropriately kept and consideration will be given to storing the invoices electronically. | Richard Clements | Simon Howick | immediately |  | 100 | The process has been reviewed and an appropriate record is now kept of invoices
| Grants | March 2014 | From testing performed there was no date on the payment authorisation forms signed by the Neighbourhood and Communities manager meaning there is no evidence that the terms and conditions were signed before payment | Low | A date stamp is used on payment authorisation forms | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 100 | Date stamp being used to show when creditor payment forms are authorised
| Grants | March 2014 | Grants and external funding officer does not receive documentation or meeting minutes from the decisions made by councillors to increase,decresase,include and exclude applications from receiving the grant | Low | Grants and external funding officer should receive backing documentation for any changes made to grant funding at Councillor level | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 100 | Process in place for this to happen in future
| Grants | March 2014 | The same organisation often receive the same grant income every year with 14 grant applications being from the same people in 2012/13, 2013/14 and 2014/15 and the number of successful applicants dropping from 57 to 30 between 2012/13 and 2014/15. | Low | Increase advertisement of the scheme including use of social media | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 100 | Being done through twitter and Facebook
| Grants | March 2014 | Proposals are due midday on the due date in 2014/15 2 applications came in on the due date but after the deadline. | Low | Deadline for the proposals should be midnight on deadline day | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 100 | amendments to grant application forms done
| Community centres and associations | April 2014 | 1 out of 5 audits tested had the documentation in a different format than the template. This was in less detail and was only ticks rather than providing a commentary for each risk. | Low | All audits and follow up work will be documented on the audit templates | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 100 | Template is now in place
| Collection Fund | March 2014 | A daily reconciliation between Paris and Academy is performed. When testing this there was one reconciliation item (£600) which was a difference for over 6 months without being cleared | Low | Differences are investigated and cleared within one month of discovery | Pete Johnson | Nigel Kennedy | immediately |  | 100 | This procedure is now in place
IA402 | Health and Safety: Housing Stock and Corporate Assets | 1/8/13 | The reports currently being run for monitoring purposes are not as effective as they could be due to the electrical data on Uniform not being up to date | Low | The electrical inspections data is uploaded to ensure the Uniform system is up to date | Steve Stansfield | Steve Stansfield | 2013-12-31 |  | 75 | Further work is being carried out on the reporting and communication of the repair data to ensure Uniform is updated timely
| Grants | March 2014 | 2 of 22 successful grants tested had no evidence backing up expenditure and 1 of 22 successful grants was missing an invoice for an item of expenditure. | Low | Introduction of a training programme for the successful applicants, and more regular monitoring of non compliant organisations will be introduced | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 50 | Training to focus on monitoring requirements from funded groups, meeting with OCVA on 9/4/14 to discuss requirements. Publish details of training by the end of June. In work programme of Grants Officer will target those with non-compliant history.
| Grants | March 2014 | 1 of 5 year end monitoring forms tested no evidence was received from organisations but the grant was still given in full | Low | Organisations that do not provide supporting documents are not able to apply for grants in future years | Angela Cristofoli | Ian Brooke | 30-06-2014 |  | 50 | This will be a recommendation in the annual monitoring report going to CEB July 2014 - monitoring information currently being collected
IA523 | Cash and Card Receipts Review | 7-Feb-2014 | Whilst the Council are moving towards becoming cash free there is no regular monitoring of the cash payments which are being received. | Low | The increase in cash intake during the year to date is not in line with the Councils objective of reducing cash payments; failure to monitor and identify the reasons for increases could result in the Council not being able to put in place appropriate actions to reduce cash payments. | Pete Johnson | Pete Johnson |  |  | 30 | A report is being generated within PARIS to facilitate further investigation
| Community centres and associations | April 2014 | Some community centres contact the repairs and maintenance team directly and have jobs raised on the Uniform system | Low | All repairs has to go through the community development team to authorise. All direct requests to the repairs team are rejected | Angela Cristofoli | Ian Brooke | immediately |  | 25 | Review process and management with Property to ensure budgets, management and repairs can go through CAN
| Town Hall Income Review | March 2014 | There are no procedure notes in place for cash payments, this may lead to staff not being fully aware of the controls and processes | Low | Procedure notes will be written for cash payments | Richard Clements | Simon Howick | 31/12/13 |  | 0 | These procedures are being revised and will be circulated across all services
| Debtors | April 2014 | A list of late invoice requests is not being taken to the management accountant meetings, 3 invoices tested had taken over a month from service delivery to raising the request | Low | An agenda item is added to the Management Accountant meeting to ensure this list is reviewed, and a reminder is sent to all officers to ensure invoices are issued timely | Pete Johnson | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Debtors | April 2014 | 8 out of 25 sundry debts tested did not have a separate preparer and authoriser | Low | Staff are to be reminded that separate people need to input and run sales orders | Nicki Peirce | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Debtors | April 2014 | 8 out of 25 debts tested had been raised by individuals not on the authorised signatory list | Low | ensure authorised signatory list is updated and staff are to be reminded that only individuals on the authorised signatory list can approve debts | Nicki Peirce | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Debtors | April 2014 | The aged debt report includes 366 uncoded balances over 56 days old | Low | The aged debt list is monitored on a weekly basis and debts over 30 days are chased with debts which are not likely to be recovered written off | Nicki Peirce | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Debtors | April 2014 | Exception reports are not produced for amendments to standing data on a frequent basis | Low | Use of amendment reports will be investigate | Nicki Peirce | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Creditors | April 2014 | 1 of 25 invoices (Servitor) were authorised and had a signature to show this, however it was not possible to verify the signature as the authoriser did not print or date the invoice | Low | Authorisers will include the date and their initials to identify who has signed the invoice for payment | Ivana Ilic | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Creditors | April 2014 | 2 out of 25 supplier invoices were not date stamped by the finance department upon arrival (1 Fleetplan and 1 P2P). PWC were unable to verify that these invoices were received after a purchase order | Low | All invoices are to be date stamped when received | Ivana Ilic | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014
| Creditors | April 2014 | Creditor payment forms should be stamped | Low | Procedures for stamping all supplier invoices will be reiterated to all departments concerned | Pete Johnson | Nigel Kennedy | immediately |  | 0 | Recommendation agreed and in progress to implement by end of April 2014