## cvhtmsrv
Audit Tracker
Ref | Review | Review Date | Issue Noted | Risk Rating | Recommendation | Updater | Owner | Due Date | Forecast Completion Date | % Complete | Comments
External Audit
| Financial Statements Audit | Sept 2014 | Service expenditure and income include Direct Services costs and recharges which grosses up the reported expenditure and income | Medium | The Council needs to establish effective accounting arrangements that eliminate internal recharges from reported expenditure and income | Anna Winship | Anna Winship | 31/3/15 |  | 50 | Discussion on the process have been started and work is progressing on putting these in place, which will be finalised ahead of the start of the next statement of accounts
| Financial Statements Audit | Sept 2014 | The Council has been incorrectly accounting for impairments and revaluations of dwellings | Medium | The Council needs to improve its arrangements for documenting and accounting for changes in the value of council dwellings | Anna Winship | Anna Winship | 31/3/15 |  | 100 | A full review of the process for documenting and accounting for impairments and revaluations of fixed assets has been undertaken and changes are now effective.
Internal Audit
IA510 | Asset Management | 1-Dec-2013 | Some areas were unclear with regard to the linkage between actions and objectives and to the Corporate Plan. | Medium | Future iterations should ensure that objectives are linked to those in the Corporate Plan, and that objectives, actions, targets and measures are linked together. With an executive summary included for the key messages and conclusions. | Lorraine Newman-Robson | Mike Scott | 31-Oct-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA511 | Asset Management | 1-Dec-2013 | The strategy includes a risk register,however this should include the the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Medium | Risk register to include the the key risks to the individual objectives, and include details of the actions and assurance sources to address the risks. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA512 | Asset Management | 1-Dec-2013 | The plan whilst strategic and policy driven in some instances is not specific. The general approach to management is included but this does not include an asset by asset breakdown or details of the future holding strategy. Reference should be included to how the Council manages assets on a day to day basis. | Medium | Plan to include reference to how the Council manages assets on a day to day basis. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA513 | Asset Management | 1-Dec-2013 | A section should be included on the review proces which is undertaken on completion of key projects and the capital programmes. | Medium | A section should be included on the review proces which is undertaken on completion of key projects and the capital programmes. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA514 | Asset Management | 1-Dec-2013 | The document is vague on the portfolio strategy, this hsould be expanded beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Medium | Expand portfolio strategy beyond the overview and objectives to be more specific and structured with consideration given to: How the objectives will be met rather than targets being given What the current and future business needs are and how well the existing estate is accommodation the requirements More detailed asset class strategies included with actions to how these will be achieved and performance measured A fit for purpose assessment of the main elements of the estate and The portfolio overview including more geographical references | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA515 | Asset Management | 1-Dec-2013 | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets whicha re identified as problems/low return. | Medium | Within the General Fund Assets, an investment fund strategy should be included which details objectives, commentary on the portfolio and any assets whicha re identified as problems/low return. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA516 | Asset Management | 1-Dec-2013 | There needs to be a definition included of the levels of the strategy, sub-geographices and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Medium | There needs to be a definition included of the levels of the strategy, sub-geographices and assets, with details of how these are layered and refreshed in the Housing Revenue Account assets list. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA517 | Asset Management | 1-Dec-2013 | There needs to be challenge on the curent use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Medium | There needs to be challenge on the curent use of assets and an assessment included of the benefit and suitability within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA518 | Asset Management | 1-Dec-2013 | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Medium | Details are required over the source of finance and/or consideration to other models of financing within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA519 | Asset Management | 1-Dec-2013 | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Medium | A summary should be included of tenant satisfaction within the Housing Revenue Account Asset list. | Lorraine Newman-Robson | Mike Scott | 31-Mar-2014 |  | 100 | The Asset Management Plan has been refreshed and as part of this refresh all the recommendation were considered. This refresh has been approved by CEB and Council
IA545 | Community Dev, Centres & Associations Audit | 1-Mar-2014 | 1 of 19 community centres currently has a signed lease agreement. The remaining centres have less formal agreements in place. | Medium | Legally the Council are not covered from liabilities. Lack of clarity over responsibilities. | Angela Cristofoli | Angela Cristofoli | 29-Apr-2014 |  | 95 | Nearly all CCs have an existing agreement in place, awaiting final confirmation on 1.
| Car Parks | November 2014 | There is no process in place for performing a reconciliaiton between the actual payments on Credit Call and what is uploaded into Agresso | Medium | Procedures will be established for a reconciliaiton to be performed between actual credit card payments and what has been accounted for in Agresso | Lyn Barker | Angie Anderson | 15/12/14 |  | 100 | The reconciliations between credit call and Agresso are now in place and a new process is in place from 1st December to make this process more efficient
| Collection Fund | November 2014 | From a sample of 25 cases being reviewed for debt recover procedures 7 of the cases had not been any action for long periods of time, in most cases this was over 2 years | Medium | All cases with long periods of inactivity will be identified and procedures for recovery will restart, and the recovery team will ensure that going forward cases are reviewed regularly to avoid similar issues occurring | Nick Gibb | Nick Gibb | 31/12/14 |  | 0 | All cases with long periods of inactivity will be identified and procedures for recovery will restart, and the recovery team will ensure that going forward cases are reviewed regularly to avoid similar issues occurring
| Collection Fund | November 2014 | No regular reconciliation is performed between NNDR data held on Academy and the Valuation Office reports | Medium | This is currently completed annually, but will now be completed on a weekly basis | Anne Harvey-Lynch | Anne Harvey-Lynch | 31/12/14 |  | 100 | This is currently completed annually, but will now be completed on a weekly basis
IA547 | Community Dev, Centres & Associations Audit | 1-Mar-2014 | Some of the community centres contact the repairs and maintenance team directly and have jobs raised on the Uniform system. | Low | Work in which the Council is not responsible is performed. Repairs and maintenance may not be monitored. | Mark Spriggs | Mark Spriggs | 1-May-2014 |  | 50 | A division of responsibility between the Council and Community Associations has been established and also attached to the proposed lease. Monthly meetings between CAN and Property have been organised to help monitor projects, performance and outcomes. Dialogue about the transfer of budget to CAN to increase monitoring and control is on-going
IA605 | Fraud Risk Assessment | 1-Jun-2014 | Internal fraud cases are not currently recorded on a system unless they relate to housing benefits or council tax. The investigations team are deemed to have sufficient knowledge to perform risk assessments to enable cases to be prioritised. The detail of the cases is maintained locally by the team. | Low | Internal reported cases will be documented on a centralised system. The existing Northgate system has the functionality to perform this.Timeline for delivery will be agreed with the Head of ICT and prioritised within the Council?s corporate ICT work plan. | Scott Warner | Scott Warner | 31-Dec-2014 |  | 70 | The proposed new system is incorporated in the Council's ICT work plan. Team restructure proposal about to go for consultation, the results of which will better inform resource planning for the new system. DCLG bid funding announcement recently received, adjustemnt to system specification required prior to contract tendering process.
IA523 | Cash and Card Receipts Review | 7-Feb-2014 | Whilst the Council are moving towards becoming cash free there is no regular monitoring of the cash payments which are being received. | Low | The increase in cash intake during the year to date is not in line with the Council?s objective of reducing cash payments; failure to monitor and identify the reasons for increases could result in the Council not being able to put in place appropriate actions to reduce cash payments. | Wendy Edwards | Wendy Edwards | 31/3/15 |  | 80 | A report is being compiled outlining and identifying the areas of cash intake with a view to decide on action to reduce. Direct Debits are being promoted in respect of Sundry Debtors
IA606 | Fraud Risk Assessment | 1-Jun-2014 | The investigations team do not report the success they are having in repossessing houses as part of the housing tenancy fraud work through all publication methods. | Low | The Council should increase publication of successful repossession of houses. For example putting posters onto reclaimed properties. This will provide positive publicity for the Council, whilst also acting as a deterrent. | Scott Warner | Scott Warner | 1-Aug-2014 |  | 100 | Publicity was increased during the Tenancy Amnesty period. Flyers were produced and sent to Registered Providers who included them in mailshots to all of their properties in the area. Posters were displayed in all Council office and depot locations, as well as communal areas in council owned housing blocks. An article regarding the outcome of the Amnesty Campaign is being devised for the next edition of the Tenants in Touch magazine.
| Car Parks | November 2014 | The documentation kept when issuing shopmobility vehicles is not always clear and accuratley updated | Low | ensure all staff are aware of the procedures and requirements in this area | Jason Munro | Jason Munro | 31/12/14 |  | 100 | This has now been completed.
| Collection Fund | November 2014 | Collection rates for NDR and Council Tax are not being met | Low | The Council will continue to monitor collection rates and ensure that any continued fall in rates against the profiled target is looked into and acitoned. The impact of the increased instalments will be incorporated into cash flow planning and the potential impact on treasury management will be monitored. any issues will be flagged up to ensure appropriate aciton can be taken | Nick Gibb | Nick Gibb | 31/3/15 |  | 100 | The collection rates and cash flow have been updated to take into account the impact of the increased instalments. The Council will continue to monitor colleciton rates and ensure that any continued fall in rates against the profiled target is looked into and acitoned.
| Collection Fund | November 2014 | The target ratesbeing used to monitor Council Tax and NNDR collection rates were marginally incorrect to those publicaly available | Low | Target rates will be updated to ensure the correct rates are used | Adrian Wood | Adrian Wood | 28/11/14 |  | 100 | All month end profile targets have been re-calculated based on the Council's actual targeted collection rate.
| Collection Fund | November 2014 | A sample of 25 reconciliations between Academy and Paris were reviewed, and one of these the reviewed date was not entered | Low | staff involved will be reminded of the need to complete all details clearly to ensure a clear audit trail is maintained | Ivana Ilic | Ivana Ilic | 28/11/14 |  | 100 | The process has been reviewed and all staff are aware of the process