## Cap programme with financing
APPENDIX B
Capital Budget and Spend as at 30th September, 2011
Capital Scheme | Approved Budget 2011/12 | Latest Budget 2011/12 | Spend as at 30 Sept 2011 | % Spend Against Latest Budget | Projected Outturn | Outturn Variance to Latest Budget | Outurn Variance due to Slippage | Outtrun variance due to Over/ Underspend | Officer Responsible | Comments
A1500 Paradise Street - work of art | 661 | 661 | 294 | 44.48% | 294 | -367 | -367 |  | L Freeman | S106 Funding - Work commissioned | pp
F0010 Gloucester Green Safety Measures | 0 | 0 | 1950 | 0% | 0 | 0 | 0 |  | To be closed | Likely coding error - Cost centre to be closed | pp
F1323 Bridge Over Fiddlers Stream | -0.38 | -0.38 | 0 | 0% | 0 | 0.38 | 0.38 |  | L Freeman | Scheme to be moved to 2012/13 | pp
F1330 Work at Donnington Middle School | 1662 | 1662 | 84 | 5.054% | 1662 | 0 | 0 |  | L Freeman | S106 Funding | pp
F1332 West End Contributions | 172271 | 172271 | 0 | 0% | 172271 | 0 | 0 |  | L Freeman | S106 To be held until project commences | pp
F6015 Slade Area Public Work of Art | 5993 | 5993 | 114 | 1.902% | 5993 | 0 | 0 |  | L Freeman | S106 Funding - Work commissioned | pp
F7005 Oxford Road /Littlemore improvement | 17624 | 17624 | 0 | 0% | 17624 | 0 | 0 |  | L Freeman | S106 Funding | pp
F7006 Work of art littlemore | 17850 | 17850 | 133 | 0.7451% | 17850 | 0 | 0 |  | L Freeman | S106 Funding | pp
NEW Landscaping Work Lamarsh Road | 0 | 12500 | 0 | 0% | 12500 | 0 | 0 |  | L Freeman | New S106 Funded Scheme to be Approved
NEW Landscaping Work Lamarsh Road | 0 | 3229 | 0 | 0% | 3229 | 0 | 0 |  | L Freeman | New S106 Funded Scheme to be Approved
NEW CCTV Gipsy Lane Campus | 0 | 60000 | 0 | 0% | 60000 | 0 | 0 |  | Karen Crossan | New S106 Funded Scheme to be Approved
M5002 Refurbishment of Bonn Square | 859 | 859 | 131 | 15.25% | 859 | 0 | 0 |  | M Crofton-Briggs | Project Completed - Accrual from 2010/11 | pp
M5014 West End Partnership (Growth Points Grant) | 162091 | 162091 | 19125 | 11.8% | 162091 | 0 | 0 |  | M Crofton-Briggs |  | pp
M5016 Housing Delivery (Funded via New Growth Points) | 184671 | 184671 | 35500 | 19.22% | 184671 | 0 | 0 |  | M Crofton-Briggs |  | pp
NEW Land at Barton (Funded via New Growth Points) | 500000 | 500000 | 0 | 0% | 0 | -500000 | 0 | -500000 | Steve Sprason | NGP funding will be diverted to other Capital Projects to allow reserves to fund the revenue cost of Barton project for 2011/12 | pp
City Development | 1063681.62 | 1139410.62 | 57331 | 5.032% | 639044 | -500366.62 | -366.62 | -500000 |  |  | pp
E3511 Renovation Grants | 84449 | 84449 | 3153.77 | 3.735% | 84449 | 0 | 0 |  | J Exeley | Additional budget is 10/11 slippage - however still project to spend to budget | pp
E3521 Disabled Facilities Grants | 640000 | 695000 | 241612.67 | 34.76% | 695000 | 0 |  | 0 | J Exeley | Additional budget is increase in funding from DCLG by £55k - project to spend to budget | pp
Environmental Development | 724449 | 779449 | 244766.44 | 31.4% | 779449 | 0 | 0 | 0 |  |  | pp
F1096 West Oxford Cylce Route | 63446 | 63446 | 0 | 0% | 63446 | 0 | 0 |  |  | S106 Need to know who is responsible for completing these projects | pp
F5008 West Oxford Cylce Route | 154 | 154 | 0 | 0% | 154 | 0 | 0 |  |  | S106 Need to know who is responsible for completing these projects | pp
F5010 Marsh Lane to Stockleys Rd cycle link | 11721 | 11721 | 4223.99 | 36.04% | 11721 | 0 | 0 |  |  | S106 Need to know who is responsible for completing these projects | pp
F5011 Barton Cycle Link | 48225 | 48225 | 0 | 0% | 48225 | 0 | 0 |  |  | S106 Need to know who is responsible for completing these projects | pp
F6013 Bullingdon Community Centre - provision or enhancement of facilities | 4807 | 4807 | 0 | 0% | 25193 | 20386 |  | 20386 | A Cristofoli | On going S106 Funding due | pp
F6014 Rose Hill provision or enhancement of community facilities | 225820 | 225820 | 1179.23 | 0.5222% | 225820 | 0 | 0 |  | A Cristofoli | S106 Funding - could be used for other schemes but must be in Rosehill area | pp
F6016 Jericho Community Centre - New Building | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | Investigate - £100K budget on Agresso but project is not in Approved Budget
F7007 Woodfarm/headington Community Centre- Improvements | 19887 | 19887 | 0 | 0% | 19887 | 0 | 0 |  | A Cristofoli | S106 Funding - details of project yet to be agreed | pp
G3013 Diamond Place car park footpath extension | 6324 | 6324 | 0 | 0% | 6324 | 0 | 0 |  | A Cristofoli | Local Area Committee project | pp
G3014 East Oxford Community Association Improvements | 2550 | 2550 | 0 | 0% | 2550 | 0 | 0 |  | A Cristofoli | East Oxford Parliament Project | pp
G4006 Florence Park CC Kitchen | 1411 | 1411 | 0 | 0% | 1411 | 0 | 0 |  | A Cristofoli | Completed 2010/11 awaiting final payments | pp
G6010 Mount Place Square Refurbishment | 1401 | 1401 | 0 | 0% | 1401 | 0 | 0 |  | A Cristofoli | Completed 2010/11 | pp
G6011 St Lukes Church Hall Extension |  |  | 0 |  |  | 0 | 0 |  | A Cristofoli | CSW Area Committee project - awaiting matched funding
G6012 South Oxford Community Centre Main Hall Replacement | 9238 | 9238 | 0 | 0% | 9238 | 0 | 0 |  | A Cristofoli | CSW Area Committee project | pp
M5001 Estate Shops Security Measures | 0 | 0 | -582.66 | 0% | 0 | 0 | 0 |  | S Northey | Projected completed 2010/11
M5012 Rose Hill Redevelopment | 0 | 0 | 56186.43 | 0% | 1023 | 1023 |  | 1023 | S Northey | £50K Grant to OCHA coded to project - invoices to be raised by S Northey to offset spend | pp
M5013 Affordable Housing - Garage Sites | 116429 | 116429 | 0 | 0% | 116429 | 0 | 0 |  | S Northey | S106 Funding | pp
M5018 Wood Farm Community Building Project | 56000 | 56000 | 0 | 0% | 56000 | 0 | 0 |  | A Cristofoli | Members to bid. Preliminary costs to be charged to revenue. May see no Capital costs this year | pp
Z3718 St Lukes Church - community/facilities | 16362 | 16362 | 0 | 0% | 16362 | 0 | 0 |  | A Cristofoli | ? Additional S106 funding for G6011 | pp
M5015 Old Fire Station | 2353494 | 2353494 | 1563310.71 | 66.43% | 2653494 | 300000 |  | 300000 | J Bellenger | The additional costs of £300K may be recoverable via bond payment. This forecast is a worst case scenario | pp
Communities and Housing | 583775 | 2937269 | 1624317.7 | 55.3% | 3258678 | 321409 | 0 | 321409 |  |  | pp
A4800 Barton Pool | -21493.28 | 0 | 0 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
A4801 BBL Pool | -17445.83 | 0 | 183.1 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
A4802 BBL LC | 563547.74 | 0 | 0 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
A4803 Ferry LC | 56934.65 | 0 | -1310 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
A4804 Hinksey Pool | 39162.36 | 20000 | 23301.3 | 116.5% | 23301.3 | 3301.3 |  | 3301.3 | I Brooke/ K Reynolds | This phase of work completed | pp
A4805 Temple Cowley Pool | -73493.91 | 0 | -20.04 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
A4806 Ice Rink | -502445.8 | 19520 | 8129.89 | 41.65% | 28129.89 | 8609.89 |  | 8609.89 | I Brooke/ K Reynolds | 20K Retention expected | pp
A4807 Barton Pool Improvements | 45593.4 | 96000 | 96520.81 | 100.5% | 96520.81 | 520.81 |  | 520.81 | I Brooke/ K Reynolds | This phase of work completed | pp
A4809 Ferry Sports Centre Improvements | -56849.84 | 0 | 0 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | This phase of work completed | pp
Z7500 Building Improvements (General Fund) | 102011 | 0 | 0 | 0% | 0 | 0 |  | 0 | I Brooke/ K Reynolds | Allocate to A4800-A4806. | pp
A4808 Blackbird Leys LC Improvements | 335128.44 | 335128.44 | 0 | 0% | 335128 | -0.44 | -0.44 |  | I Brooke/ K Reynolds | This budget to be reallocated - It was set before present understanding of Fusion's repair obligations were known | pp
A4812 Building Improvements (GF Leisure) | 130000 | 130000 | 2000 | 1.538% | 130000 | 0 | 0 |  | I Brooke/ K Reynolds | Various works across all Leisure Centres | pp
A4813 Hinksey Pools main pool liner | 110000 | 110000 | 74717 | 67.92% | 110000 | 0 | 0 |  | I Brooke/ K Reynolds | Costs to be transferred to A4812 - misposted | pp
A4814 Leisure Centre substantive repairs | 425000 | 425000 | 0 | 0% | 425000 | 0 | 0 |  | I Brooke/ K Reynolds | Expected under spend at year end - Budget was set before present understanding of Fusion's repair obligations were known | pp
B0048 Leisure ~ Cemeteries | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0049 Leisure ~ Countryside | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0050 Leisure ~ Depots | 10000 | 10000 | 0 | 0% | 0 | -10000 | -10000 |  | J Bellenger | Expected completion by March 2012 | pp
B0051 Leisure ~ Pavilions | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0026 Parks & cemetery stone wall & path improvements | 35000 | 35000 | 0 | 0% | 35000 | 0 | 0 |  | J Bellenger | Expected completion November 2011 | pp
B0030 Consolidation of Parks depot from South Park to Cutteslowe | 60000 | 60000 | 0 | 0% | 60000 | 0 | 0 |  | J Bellenger | Project to tender October 2011, expected completion December 2011 | pp
B0027 Covered Market - Improvements & Upgrade to Roof | 85000 | 85000 | 0 | 0% | 85000 | 0 | 0 |  | J Bellenger/ M Stewart | Expected to be on budget for 2011/12 | pp
B0028 Covered Market - New Roof Structures to High St Entrances | 30000 | 30000 | 0 | 0% | 30000 | 0 | 0 |  | J Bellenger/ M Stewart | Expected to be on budget for 2011/12 | pp
B1004 - Covered Market repairs/upgrading | 23784 | 23784 | 0 | 0% | 0 | -23784 | -23784 |  | J Bellenger/ M Stewart | Budget b/f from 2010/11 likely to slip to future years | pp
B0010 Covered Market signage improvements | 12147 | 12147 | 0 | 0% | 0 | -12147 | -12147 |  | I Gordon | Likely slippage to 2012/13 | pp
B0036 Investment ~ Covered Market | 70000 | 70000 | 0 | 0% | 70000 | 0 | 0 |  | J Bellenger/ M Stewart | Expected to be on budget for 2011/12 | pp
B0053 Public Toilets | 2500 | 2500 | 0 | 0% | 2500 | 0 | 0 |  |  | Expected completion October 2011 | pp
B0031 Miscellaneous Admin Buildings | 20000 | 20000 | 0 | 0% | 20000 | 0 | 0 |  | K Reynolds | Lift Alarms - Expected completion December 2011 | pp
B0035 Miscellaneous Civic Properties | 4500 | 4500 | 0 | 0% | 4500 | 0 | 0 |  | I Gordon/ NSmith | Carfax Tower expected completion October 2011, New Inn Court Yard February 2012 | pp
B0037 Car Parks | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0038 Direct Service Depots | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0052 Miscellaneous Properties | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0032 Bury Knowle House | 45000 | 45000 | 0 | 0% | 65000 | 20000 |  | 20000 | J Bellenger | Work commenced September 2011, completion expected December 2011 | pp
B1006 Bury Knowle external repair/decoration | 25000 | 25000 | 0 | 0% | 0 | -25000 |  | -25000 | J Bellenger | Budget b/f from 2010/11 -To be vired to B0032 | pp
B0012 BBL CC - wiring Improvements | 25000 | 25000 | 14729.7 | 58.92% | 14730 | -10270 |  | -10270 | K Reynolds | Completed May 2011 | pp
B0015 South Oxford CC - Roof refurbishments | 7006 | 7006 | 0 | 0% | 7006 | 0 |  | 0 | K Reynolds | Completed last year | pp
B9203 Community Centres - Water Bylaws and Legionella | 11500 | 11500 | 2338.8 | 20.34% | 0 | -11500 |  | -11500 | K Reynolds | Completed last year | pp
B9207 Northway Centre Demolition | 18 | 18 | 0 | 0% | 0 | -18 |  | -18 | K Reynolds | Completed last year | pp
B0022 DDA East Oxford Community Centre Lift | 62648 | 62648 | 0 | 0% | 65000 | 2352 |  | 2352 | K Reynolds | Project to tender December 2011, expected completion March 2012 | pp
B0033 Community Centres | 162500 | 162500 | 0 | 0% | 82500 | -80000 | -80000 |  | I Gordon | Forecast for £60K invoiced works plus work in progress and retentions | pp
B0034 Rose Hill Community Centre | 199500 | 199500 | 0 | 0% | 50000 | -149500 | -149500 |  | I Gordon | Project to tender January 2012, costs of £50K expected by February 2012 | pp
B0003 Roof Repairs & Ext Refur 44-46 George St | 30000 | 30000 | 0 | 0% | 0 | -30000 | -30000 |  | J Bellenger | Not in 2011/12 Work plan | pp
B0043 Investment ~ George Street | 50000 | 50000 | 0 | 0% | 0 | -50000 | -50000 |  | J Bellenger | Not in 2011/12 Work plan | pp
B0029 33-35 George Street - Upgrade to Lettable Condition | 57000 | 57000 | 0 | 0% | 0 | -57000 |  | -57000 | J Bellenger | Tenant to carry out repairs - funded by rent free period - saving to Capital Programme | pp
B0040 Investment ~ Broad Street | 55000 | 55000 | 0 | 0% | 55000 | 0 | 0 |  | J Bellenger | Expected to be on budget for 2011/12 | pp
B1001 Blackwells Music Shop repairs | 70000 | 70000 | 0 | 0% | 5000 | -65000 |  | -65000 | J Bellenger | Work most likely to be obligation of tenant - saving to Capital Programme | pp
B0039 Houses and Lodges | 51000 | 51000 | 0 | 0% | 0 | -51000 | -51000 |  | J Bellenger | Not in 2011/12 Work plan | pp
B0041 Investment - Misc City Centre Properties | 0 | 0 | 0 | 0% | 5000 | 5000 | 5000 |  | J Bellenger | Programmed for future years | pp
B0042 Investment ~ Gloucester Green | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0044 Investment ~ Outer City | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0045 Investment ~ St. Michael’s Street | 30000 | 30000 | 0 | 0% | 0 | -30000 | -30000 |  | J Bellenger | Expect to slip to 2012/13 | pp
B0046 Investment ~ Ship Street | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0047 Investment ~ Turl Street | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Programmed for future years | pp
B0054 Town Hall | 200000 | 200000 | 0 | 0% | 216810 | 16810 | 16810 |  | I Gordon | Expected completion by March 2011 - budget can be b/f from 2012/13 | pp
B1002 -Town Hall PA system upgrades | 28190 | 28190 | 0 | 0% | 28190 | 0 | 0 |  | I Gordon | Expected completion by March 2011 | pp
B1003 - Town Hall pigeon proofing | 5000 | 5000 | 0 | 0% | 5000 | 0 | 0 |  | I Gordon | Expected completion by March 2011 | pp
B1005 Town Hall | 10000 | 10000 | 0 | 0% | 10000 | 0 | 0 |  | I Gordon | Expected completion by March 2011 | pp
B0056 City Centre Office Security | 0 | 100000 | 0 | 0% | 100000 | 0 | 0 |  | I Gordon | Design and Tender complete in February 2012, work to commence February 2012 | pp
NEW- Town Hall fire escape (Blue Boar Street) | 0 | 0 | 0 | 0% | 55000 | 55000 |  | 55000 | J Bellenger | No budget for this essential work - could be funded from savings in Capital Programme
Q2000 Offices for the Future | 3440429 | 3440429 | 1866864.28 | 54.26% | 3440429 | 0 | 0 |  | M Westmoreland |  | pp
Funds to be allocated (Future Years) | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | J Bellenger | Extra resource in place from July to progress Capital Programme | pp
Corporate Assets | 6153370.93 | 6253370.44 | 2087454.84 | 33.38% | 5659745 | -493625.44 | -414621.44 | -79004 |  |  | pp
C3041 New server for telephone system | 18000 | 18000 | 6712 | 37.29% | 18000 | 0 | 0 |  | H Bishop |  | pp
C3042 Customer First Programme | 161000 | 161000 | 7914.12 | 4.916% | 161000 | 0 | 0 |  | H Bishop |  | pp
Customer Services | 179000 | 179000 | 14626.12 | 8.171% | 179000 | 0 | 0 | 0 |  |  | pp
A1300 Playground Refurbishment | 685509 | 685509 | 327665.91 | 0% | 435509 | -250000 | -250000 |  | I Brooke | Project Manager projects 2 sites will slip into 12/13 - Pegasus Rd + Florence Park (est. £250k) | pp
A1301 Play Barton | 744465 | 744465 | 29785.24 | 4.001% | 744465 | 0 | 0 |  | I Brooke | All to be spent by year end | pp
NEW Play Barton | 800000 | 800000 | 0 | 0% | 0 | -800000 |  | -800000 | I Brooke | Duplicate bid (to be deleted) Capital Programme already caters for Scheme in A1301 | pp
A2808 Replacement Sports Facilities - Cowley Marsh | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | I Brooke |  | pp
A3125 Milham Ford Park land and Recreational Facilities | 32130 | 32130 | 0 | 0% | 32130 | 0 | 0 |  | I Brooke |  | pp
A3127 Girdlestone Rd improvement to public space |  |  | 0 | 0% | 0 | 0 | 0 |  | I Brooke
A3129 Donnington Recreation Ground Improvements | 44375 | 44375 | 0 | 0% | 44375 | 0 | 0 |  | I Brooke |  | pp
A3120 Florence Park Public Open Space/children Play Area | 25346 | 25346 | 0 | 0% | 25346 | 0 | 0 |  | I Brooke | Consolidate these budgets to fund Barton Pavilion works | pp
A3124 Barton Village Pavillion | 350311 | 350311 | 274684.77 | 78.41% | 350311 | 0 | 0 |  | I Brooke | Consolidate these budgets to fund Barton Pavilion works | pp
A3115 Barton Village Recreation Ground - Improvements | 82545 |  | 0 | 0% | 0 | 0 | 0 |  | I Brooke | Consolidated with A3124 | pp
Z3009 Contribution to Barton Pavillion | 50000 |  | 0 | 0% | 0 | 0 | 0 |  | I Brooke | Consolidated with A3124 | pp
A4810 New Build Competion Pool | 7438071 | 7438071 | 198597.22 | 2.67% | 1000000 | -6438071 | -6438071 |  | I Brooke | Work will not commence until January 2012 at earliest | pp
F7009 Recreation/Sports - City of Oxford | 200000 | 200000 | 0 | 0% | 200000 | 0 | 0 |  | I Brooke | S106 Funding to add to New Build Competition Pool | pp
A1161 Frys Hill Leisure Centre | 140074 | 140074 | 0 | 0% | 140074 | 0 | 0 |  | I Brooke | S106 Funding to add to New Build Competition Pool | pp
F6002 Temple Cowley Pool Provision or enhancement of facilities | 26473 | 26473 | 0 | 0% | 26473 | 0 | 0 |  | I Brooke | S106 Funding to add to New Build Competition Pool | pp
F7003 Temple Cowley/Blackbird Leys - improvements to indoor | 1320 | 1320 | 0 | 0% | 1320 | 0 | 0 |  | I Brooke | S106 Funding to add to New Build Competition Pool | pp
F7010 Slade Area - Indoor/Outdoor sprots facilities | 1260 | 1260 | 0 | 0% | 1260 | 0 | 0 |  | I Brooke | S106 Funding to add to New Build Competition Pool | pp
F6001 Ferry Centre - provision or enhancement of facilities | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6003 Barton Pool - Provision of indoor sports facilities | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6004 St Christophers Place - enhancement of play area | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6005 Barracks lane Allotments - enhancement of facilities | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6006 Sunnymead Park - enhancement of play area facilities | 1830 | 1830 | 0 | 0% | 1830 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6009 Town Furze Allotments - enhancement of facilities | 339 | 339 | 0 | 0% | 339 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F6010 Dene Road Play Area - enhancement of facilities at dene road or bullingdon | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F7001 Cuddesdon Way -relocation of street sports site | 60000 | 60000 | 0 | 0% | 60000 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
F7002 Margaret Road Recreation Ground - Improvments | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Funding - need to know who are the project managers | pp
G1013 Dawson Street Gardens | 0 | 19000 | 0 | 0% | 19000 | 0 | 0 |  |  | East Area Parliament Project - Budget on Agresso but not Approved
G3015 NE Marston Croft Road Recreation Ground | 0 | 25000 | 0 | 0% | 25000 | 0 | 0 |  |  | Joint project with County Council - awaiting start date - Budget on Agresso but not Approved
G3016 Peat Moors all weather pitch | 0 | 17000 | 0 | 0% | 17000 | 0 | 0 |  |  | Cowley Area Committee Project - Budget on Agresso but not Approved
Z3008 Contribution to Skate Park | 50000 | 50000 | 0 | 0% | 50000 | 0 | 0 |  |  | Additional funding to be allocated | pp
Z3010 Rosehill/Iffley Play Sites | 38000 | 38000 | 0 | 0% | 38000 | 0 | 0 |  |  | links to Community Housing Scheme F6014 Rose Hill Improvements - assumed to be spent | pp
Z8009 Bury Knowle Park - Improvements | 14000 | 14000 | 0 | 0% | 14000 | 0 | 0 |  |  | Additional funding to be allocated | pp
NEW Develop new burial space | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7014 Ice Rink improvments of facilities | 6960 | 6960 | 0 | 0% | 6960 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
NEW North/Jericho Area - Provision of indoor sport | 2100 | 2100 | 0 | 0% | 2100 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
NEW Oxrad/Ferry indoor sports | 11018 | 11018 | 0 | 0% | 11018 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7015 Florence park Improvements | 631 | 631 | 0 | 0% | 631 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7016 Herschel Crescent Ground Improvements | 7002 | 7002 | 0 | 0% | 7002 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7013 Rose Hill Play Area Improvements | 3000 | 3000 | 0 | 0% | 3000 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7012 Rose Hill Recreation Ground Improvements | 3000 | 3000 | 0 | 0% | 3000 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
F7011 Rose Hill Work of Art | 8000 | 8000 | 0 | 0% | 8000 | 0 | 0 |  |  | S106 Bids - Work not yet started | pp
City Leisure | 10827759 | 10756214 | 830733.14 | 7.723% | 3268143 | -7488071 | -6688071 | -800000 |  |  | pp
F0011 Pay & Display Parking in the Car Parks | 0 | 92000 | 60505 |  | 60550 | -31450 | -31450 |  | R Summer/ J Munro | £92K for Parking in Parks Machines which should have been rolled forward for 2010-11 as agreed with NK | pp
R0005 MT Vehicles/Plant Replacement Prog. | 783400 | 783400 | 397177.78 | 50.7% | 783400 | 0 | 0 |  | P Einon | Replacement Programme on track at present. | pp
T2266 Purchase of Brown Bins Waste Recycling | 0 | 167500 | 181169 | 108.2% | 230000 | 62500 | 62500 |  | P Dunsdon | Over Budget due to success of scheme | pp
NEW Purchase of two hand operated street sweepers | 30000 | 30000 | 0 | 0% | 30000 | 0 | 0 |  | P Einon | Received in May 2011 paid in April 2011 in Cost Centre R00005 | pp
NEW Purchase of two vehicles for garden waste collection | 308000 | 140500 |  | 0% | 155000 | 14500 | 14500 |  | P Einon | One Large RCV to be purchased rather than Two New Food Waste Vehicles due to the success of the Garden Waste Scheme | pp
NEW Purchase of ANPR for use in car park enforcement | 50000 | 50000 | 0 | 0% | 50000 | 0 | 0 |  | R Summer/ J Munro | To be spent in next three months | pp
Direct Services | 1171400 | 1263400 | 638851.78 | 50.57% | 1308950 | 45550 | 45550 | 0 |  |  | pp
C3039 ICT Infrastructure | 100000 | 100000 | 0 | 0% | 100000 | 0 | 0 |  | A Orchard | There is a large accrual for £989K - this would be payment due to County Council for ICT Equipment. Needs to be settled | pp
NEW ICT Development | 200000 | 200000 | 0 | 0% | 200000 | 0 | 0 |  | A Orchard |  | pp
Business Transformation | 300000 | 300000 | 0 | 0% | 300000 | 0 | 0 | 0 |  |  | pp
GF Total | 21003435.55 | 23608113.06 | 5498081.02 | 23.29% | 15393009 | -8115104.06 | -7057509.06 | -1057595 |  |  | pp
N6380 Windows 05/06 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N6384 Foresters Towers | 792074 | 792074 | 907.61 | 0.1146% | 40000 | -752074 | -752074 |  | C Pyle |  | pp
N6385 Adaptations for disabled | 900000 | 1139500 | 678104.15 | 59.51% | 1139500 | 0 |  | 0 | C Pyle | SCM, GSR and Fergal are currently working on extensions, reports are been written for 5 more properties that need specialist work | pp
Decent Homes |  |  | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N6361 Kitchens & Bathrooms - MRA 04/05 |  |  | 302.85 | 0% | 0 | 0 |  | 0 | C Pyle
N6386 Structural | 100000 | 100000 | 47810.02 | 47.81% | 100000 | 0 |  | 0 | C Pyle |  | pp
N6387 Controlled Entry | 297810 | 287310 | 211675.97 | 73.68% | 287310 | 0 |  | 0 | C Pyle | current contract is nearly finished. New contract, tenders expected back early Oct 11 | pp
N6388 Major Voids | 900000 | 900000 | 458711.86 | 50.97% | 900000 | 0 |  | 0 | C Pyle |  | pp
N6389 Damp-proof works (K&B) | 100000 | 100000 | 39872.94 | 39.87% | 100000 | 0 |  | 0 | C Pyle |  | pp
N6390 Kitchens & Bathrooms | 3500000 | 3126500 | 1458212.81 | 46.64% | 3126500 | 0 |  | 0 | C Pyle | Reduction in programme to fund anticipated increase in replacement heating systems. | pp
N6391 Heating | 1000000 | 1239500 | 781274.42 | 63.03% | 1239500 | 0 |  | 0 | C Pyle | Additional replacement systems needed, funded from reduction in Kitchens/Bathrooms | pp
N6392 Roofing | 200000 | 200000 | 89.72 | 0.04486% | 200000 | 0 |  | 0 | C Pyle | new contract is going out to tender in Oct 11 due to start work in Jan 12 | pp
N6393 External Doors | 200000 | 200000 | 1421.74 | 0.7109% | 200000 | 0 |  | 0 | C Pyle | New contract is going out to tender in Oct 11 | pp
N6394 Windows | 900000 | 900000 | 181346.65 | 20.15% | 900000 | 0 |  | 0 | C Pyle |  | pp
N6395 Electrics | 200000 | 179000 | 12109.42 | 6.765% | 179000 | 0 |  | 0 | C Pyle |  | pp
N6396 Sheltered Blk, George Moore | 210000 | 189000 | 0 | 0% | 60000 | -129000 |  | -129000 | C Pyle |  | pp
N6426 BISF´s |  | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N6427 Shops | 200000 | 179000 | 0 | 0% | 179000 | 0 |  | 0 | C Pyle |  | pp
N6430 Evenlode tower | 0 | 0 | 8720.25 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N6431 Windrush Tower | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N6432 Plowman Tower | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N7006 Northbrook House - Refurbishment | 0 | 0 | 1179.13 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N7010 Headley House - Refurbishment | 0 | 0 | 1532.26 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N7011 Cardinal House - Refurbishment | 1601000 | 350000 | 420155.55 | 120% | 420155.55 | 70155.55 |  | 70155.55 | C Pyle | Final accounts now agreed | pp
N7012 Grantham House - Refurbishment | 0 | 0 | 121 | 0% | 129000 | 129000 |  | 129000 | C Pyle |  | pp
N7013 Bradlands House - Refurbishment | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N7015 Knights House - Refurbishment | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | C Pyle |  | pp
N7017 Aireys | 100000 | 100000 | 17260.73 | 17.26% | 83000 | -17000 |  | -17000 | C Pyle |  | pp
N7018 Minox |  |  | 1982.2 | 0% | 17000 | 17000 |  | 17000 | C Pyle | Funded from the non traditional aireys budget | pp
N7019 Lambourn Road | 0 | 0 | 107995.42 | 0% | 108000 | 108000 |  | 108000 | C Pyle | Final accounts now agreed | pp
Housing Revenue Account | 11200884 | 9981884 | 4430786.7 | 44.39% | 9407965.55 | -573918.45 | -752074 | 178155.55 |  |  | pp
pp
Grand Total | 32204319.55 | 33589997.06 | 9928867.72 | 29.56% | 24800974.55 | -8689022.51 | -7809583.06 | -879439.45 |  |  | pp
pp
pp
Note on B171: lbarker: Spilt between T2266 - £167,500 and R0005 - 140,5000
Note on I165: jmarks: This budget was not needed. Duplicate Bid