| Risk ID | Risk | Corporate Objective | Gross Risk | Residual Risk | Current Risk | Owner | Date Risk Reviewed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Category-000-Service Area Code | Risk Title | Opportunity/Threat | Risk Description | Risk Cause | Consequence | Date raised | 1 to 6 | I | P | I | P | I | P |  |  |
| CEB-001-BT | Lack of Benchmark Data | T | Lack of reliable benchmark data to draw conclusions on council performance | Lack of capacity/other priorities to undertake benchmarking Lack of capacity or interest of other councils to participate Inability or uncertainty on how to obtain data from other sectors | Fundamental Service Review programme is based on incomplete evidence Benchmarking fails to incorporate a wider view of cross-sector performance | 04/11/11 | 6 | 3 | 2 | 3 | 1 | 3 | 1 | JL |  |
| CEB-002-BT | Service Performance | T | Failure to adopt Framework will inhibit continued service improvement | Members disagree with principles of Framework and do not endorse it | Lack of clarity and coordination on direction of future improvement programme Uncertainty for services as to what is expected of them for improvement | 07/11/11 | 6 | 2 | 2 | 2 | 1 | 2 | 1 | JL |  |
| CEB-003-BT | Software capabilities | T | Reliance on LG Inform as a data sharing tool | System is developed within limits of open source technology and meets needs of larger councils only | Unable to meet PIF commitment to share data via LG Inform Requirement to find alternative data hosting arrangement | 04/11/11 | 6 | 3 | 4 | 2 | 3 | 2 | 3 | JL |  |
| CEB-004-BT | Fundamental Service Reviews | T | FSRs do not deliver the savings and improvements required | FSR process is not sufficiently robust and challenging | Savings targets not achieved. Services fail to improve significantly | 04/11/11 | 6 | 3 | 3 | 3 | 2 | 3 | 2 | JL |  |