## Sheet1
Key
ACTIONS MUST BE 'SMART' |  |  |  |  | CLOSED ACTION/Risk
Specific, Measurable, Achievable, Realistic and Time bound
Risk ID | Risk Title | Action Owner | Accept, Contingency, Transfer, Reduce or Avoid | Details of Action | Key Milestones | Milestone Delivery Date | %Action Complete | Date Reviewed
| Increased leafleting | GE | A | Plan for initial uptake of applications | Streamline application process | 2011-05-01 | 100% | 2012-06-27
| Increased leafleting | GE | A | Plan for initial enforcement | Increase enforcment for start of scheme | 2011-05-01 | 100% | 2012-06-27
| Excessive objections | GE | A | Ensure messages & publicity are clear on why powers are being introduced, what will be controlled and how. | Discuss publicity with Media & develop comms plan | 2011-05-01 | 100% | 2012-06-27
| Incorrect zoning | GE | A | Check that no other problem areas are outstanding | Check for leafleting problems with other services | 2010-11-10 | 100% | 2012-06-27
| Enforcement Perception | GE | R | Plan for ongoing enforcement | Produce plan for enforcement activity for year ahead | 2012-08-31 | 0%
| Enforcement Perception | GE | R | Increase the visability of enfrocement activities in key areas of distribution | Raise awareness of enfrocement activity through the media and licensing authority groups | 2012-08-31 | 0%
Insert new row above