## Sheet1
| Capital Budget and Spend as at 30th June 2012 | [13 empty] | APPENDIX B
| Capital Scheme | 2012/13 per Budget book | Approved Carry Forwards | Approved Budget 2012/13 | Latest Budget June 2012 | Profiled Budget | Budget 2013/14 | Budget 2014/15 | Budget 2015/16 | Spend as at 30th June 2012 | Variance to Profiled Budget | % Spend Against Approved Budget | Projected Outturn at 30th June 2012 | Outturn Variance to Approved budget | Outturn Variance due to Slippage | Outrun variance due to Over/ Under spend | Management Accountant | Officer Responsible | Comments
|  | £ | £ | £ |  | £ | £ | £ | £ | £ | £ | % | £ | £ | £ | £
F1323 | F1323 Bridge Over Fiddlers Stream | 0 | 0 | 0 | 200000 | 100000 |  |  |  | 108144.56 | 8144.56 | 54.07% | 200000 | 200000 |  | 200000 |  |  | Improvements to transport infrastructure funded by S106 Contributions. To be added to Capital Programme.Total contributions of £384,633 have been received to fund this project. | F1323
F6013 | F6013 Bullingdon Community Centre -Enhancement of Community Facilities | 0 | 0 | 0 | 0 | 0 |  |  |  | 2008.23 | 2008.23 | 0% | 4807 | 4807 |  | 4807 |  |  | S106 Contributions are held in reserves to fund this work. This is an addition to the 2012/13 Capital Programme and requires budget approval. Project has slipped from previous years
F6015 | F6015 Slade Area Public Work of Art | 0 | 0 | 0 | 0 | 0 |  |  |  | 1600 | 1600 | 0% | 3379 | 3379 |  | 3379 |  |  | S106 Contributions are held in reserves to fund this work. This is an addition to the 2012/13 Capital Programme and requires budget approval. Project has slipped from previous years
F7008 | F7008 Landscaping Work at Lamarsh Road | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 13441.44 | 13441.44 |  | 13441.44 |  |  | S106 Contributions are held in reserves to fund this work. This is an addition to the 2012/13 Capital Programme and requires budget approval. Project has slipped from previous years
F7019 | F7019 Work of Art at Rose Hill | 0 | 0 | 0 | 1000 | 0 |  |  |  | 1000 | 1000 | 100% | 1000 | 1000 |  | 1000 |  |  | S106 Contributions are held in reserves to fund this work. This is an addition to the 2012/13 Capital Programme and requires budget approval. Project has slipped from previous years | F7019
Z3710 | Z3710 St Lukes Church Community Facilities | 0 | 0 | 0 | 0 | 1000 |  |  |  | 0 | -1000 | 0% | 16362 | 16362 |  | 16362 |  |  | S106 Contributions are held in reserves to fund this work. This is an addition to the 2012/13 Capital Programme and requires budget approval. Project has slipped from previous years
M5014 | M5014 West End Partnership | 0 | 0 | 0 | 417225 | 90000 |  |  |  | 87325 | -2675 | 20.93% | 417225 | 417225 |  | 417225 |  |  | Wayfinding Project in West End using S106 Contributions. Project apporval 02/02/12. To be added to 2012/13 Capital Programme. | M5014
#N/A
City | City Development | 0 | 0 | 0 | 618225 | 191000 | 0 | 0 | 0 | 200077.79 | 9077.79 | 32.36% | 656214.44 | 656214.44 | 0 | 656214.44 |  |  |  | #N/A
#N/A
E3511 | E3511 Renovation Grants | 50000 | 0 | 50000 | 50000 | 0 | 50000 | 50000 |  | 0 | 0 | 0% | 50000 | 0 | 0 | 0 | P Swaffield | J Exeley | YTD spend is a credit (refunds exceed expenditure) proj to be on budget (any slippage to be c/fwd request at year-end) | E3511
E3521 | E3521 Disabled Facilities Grants | 640000 | 110000 | 750000 | 750000 | 62550 | 640000 | 640000 | 640000 | 20747.64 | -41802.36 | 2.766% | 750000 | 0 | 0 | 0 | P Swaffield | J Exeley | Spend YTD doesn't match profile set. Proj to be on budget - any underspend at year-end to have cfwd request | E3521
#N/A
Envir | Environmental Development | 690000 | 110000 | 800000 | 800000 | 62550 | 690000 | 690000 | 640000 | 20747.64 | -41802.36 | 2.593% | 800000 | 0 | 0 | 0 |  |  |  | #N/A
#N/A
G1013 | G1013 Dawson Street Gardens | 0 | 19000 | 19000 | 19000 | 0 |  |  |  | 0 | 0 | 0% | 19000 | 0 | 0 | 0 |  |  |  | G1013
G3013 | G3013 Diamond Place car park footpath extension | 0 | 6324 | 6324 | 6324 | 0 |  |  |  | 0 | 0 | 0% | 6324 | 0 | 0 | 0 |  |  |  | G3013
G3014 | G3014 East Oxford Community Association Improvements | 0 | 2550 | 2550 | 2550 | 0 |  |  |  | 0 | 0 | 0% | 2550 | 0 | 0 | 0 |  |  |  | G3014
G4006 | G4006 Florence Park CC Kitchen | 0 | 1411 | 1411 | 1411 | 0 |  |  |  | 0 | 0 | 0% | 1411 | 0 | 0 | 0 |  |  |  | G4006
G6010 | G6010 Mount Place Square Refurbishment | 0 | 382.9 | 382.9 | 382.9 | 0 |  |  |  | 0 | 0 | 0% | 382.9 | 0 | 0 | 0 |  |  |  | G6010
G6011 | G6011 St Lukes Church Hall Extension | 0 | 10000 | 10000 | 10000 | 0 |  |  |  | 0 | 0 | 0% | 10000 | 0 | 0 | 0 |  |  |  | G6011
G6012 | G6012 South Oxford Community Centre Main Hall Replacement | 0 | 9238 | 9238 | 9238 | 0 |  |  |  | 0 | 0 | 0% | 9238 | 0 | 0 | 0 |  |  |  | G6012
G3015 | G3015 NE Marston Croft Road Recreation Ground | 0 | 25000 | 25000 | 25000 | 0 |  |  |  | 0 | 0 | 0% | 25000 | 0 | 0 | 0 |  |  |  | G3015
G3016 | G3016 Peat Moors all weather pitch | 0 | 17000 | 17000 | 17000 | 0 |  |  |  | 0 | 0 | 0% | 17000 | 0 | 0 | 0 |  |  |  | G3016
G3017 | G3017 CCTV Replacement Programme | 84271 | 0 | 84271 | 84271 | 0 |  |  |  | 0 | 0 | 0% | 84271 | 0 | 0 | 0 |  |  |  | #N/A
[14 empty] | 0 | [5 empty] | #N/A
M5015 | M5015 Old Fire Station | 90000 | -12874.99 | 77125.01 | 77125.01 | 36000 |  |  |  | 36186.66 | 186.66 | 46.92% | 77125.01 | 0 | 0 | 0 |  |  |  | M5015
#N/A
Commu | Communities and Housing | 174271 | 78030.91 | 252301.91 | 252301.91 | 36000 | 0 | 0 | 0 | 36186.66 | 186.66 | 14.34% | 252301.91 | 0 | 0 | 0 |  |  |  | #N/A
#N/A
#N/A
A4808 | A4808 Blackbird Leys LC Improvements | 0 | 128278 | 128278 | 128278 | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | -128278 | -128278 | 0 |  |  | This project will not be undertaken until work commences on the New Build Competition Pool - it will most likely slip to 2012/13 | A4808
A4812 | A4812 Building Improvements (GF Leisure) | 0 | 22684 | 22684 | 22684 | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | -22684 | 0 | -22684 |  |  | This budget is to be added to the Leisure Centre Substantive Repairs budget as permitted in the virement rules | A4812
A4813 | A4813 Hinksey Pools main pool liner | 0 | 110000 | 110000 | 110000 | 110000 | 0 | 0 |  | 110000 | 0 | 100% | 110000 | 0 | 0 | 0 |  |  | Any further work to Hinksey Pools will be funded from the Substantive repairs budget | A4813
A4814 | A4814 Leisure Centre substantive repairs | 245000 | 174640.92 | 419640.92 | 419640.92 | 34970 | 110000 | 66000 |  | 35254.57 | 284.57 | 8.401% | 242324.92 | -177316 | -200000 | 22684 |  |  | £200k Slippage due to delay in New Build Competition Pool | A4814
#N/A
Offic | Offices for the Future | [14 empty] | 0 |  |  |  | #N/A
Q2000 | Q2000 Offices for the Future | 270000 | 113346.64 | 383346.64 | 383346.64 | 176673 | 0 | 0 |  | 178031.58 | 1358.58 | 46.44% | 543346.64 | 160000 | 0 | 160000 |  |  | A further £160,000 will be required for Generators in St Aldates Chambers and Town Hall. The funding for this work is currently in an earmarked reserve. | Q2000
#N/A
Commu | Community Centres | [18 empty] | #N/A
B0022 | B0022 DDA East Oxford Community Centre Lift | 0 | 109082.75 | 109082.75 | 109082.75 | 0 |  |  |  | 0 | 0 | 0% | 109082.75 | 0 | 0 | 0 |  |  |  | B0022
B0033 | B0033 Community Centres | 143500 | 172264.54 | 315764.54 | 315764.54 | 52627.3333 |  |  |  | 52625.63 | -1.7033 | 16.67% | 315764.54 | 0 | 0 | 0 |  |  |  | B0033
B0034 | B0034 Rose Hill Community Centre | 149500 | -1500 | 148000 | 148000 | 0 |  |  |  | 2000 | 2000 | 1.351% | 148000 | 0 | 0 | 0 |  |  |  | B0034
#N/A
| Covered Market | [18 empty] | #N/A
B0010 | B0010 Covered Market signage improvements | 20000 | 22941.12 | 42941.12 | 42941.12 | 0 |  |  |  | 0 | 0 | 0% | 42941.12 | 0 | 0 | 0 |  |  |  | B0010
B0027 | B0027 Covered Market - Improvements & Upgrade to Roof | 0 | 76061.31 | 76061.31 | 76061.31 | 0 |  |  |  | 0 | 0 | 0% | 76061.31 | 0 | 0 | 0 |  |  |  | B0027
B0028 | B0028 Covered Market - New Roof Structures to High St Entrances | 85000 | 30000 | 115000 | 115000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 115000 | 0 | 0 | 0 |  |  |  | B0028
B0036 | B0036 Investment ~ Covered Market | 132500 | 99750.77 | 232250.77 | 232250.77 | 5000 |  |  |  | 3638 | -1362 | 1.566% | 232250.77 | 0 | 0 | 0 |  |  |  | B0036
B0063 | B0063 Covered Market Replacement Sprinkler System | 150000 | 0 | 150000 | 150000 | 5000 | 0 | 0 | 0 | 5000 | 0 | 3.333% | 150000 | 0 | 0 | 0 |  |  |  | B0063
B0064 | B0064 Covered Market - Improvements to Emergency Lighting | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 50000 | 0 | 0 | 0 |  |  |  | B0064
#N/A
| Investment Properties | [18 empty] | #N/A
B0003 | B0003 Roof Repairs & Ext Refurbishment 44-46 George St | 0 | 30000 | 30000 | 30000 | 0 |  |  |  | 0 | 0 | 0% | 30000 | 0 | 0 | 0 |  |  |  | B0003
B0040 | B0040 Investment ~ Broad Street | 167500 | 0 | 167500 | 167500 | 0 |  |  |  | 0 | 0 | 0% | 167500 | 0 | 0 | 0 |  |  |  | B0040
B0041 | B0041 Investment - Misc City Centre Properties | 7000 | 0 | 7000 | 7000 | 0 |  |  |  | 0 | 0 | 0% | 7000 | 0 | 0 | 0 |  |  |  | B0041
B0042 | B0042 Investment - Gloucester Green | 5500 | 0 | 5500 | 5500 | 0 |  |  |  | 0 | 0 | 0% | 5500 | 0 | 0 | 0 |  |  |  | B0042
B0044 | B0044 Investment - Outer City | 15000 | 0 | 15000 | 15000 | 0 |  |  |  | 0 | 0 | 0% | 15000 | 0 | 0 | 0 |  |  |  | B0044
B0045 | B0045 Investment ~ St. Michael’s Street | 13000 | 30000 | 43000 | 43000 | 0 |  |  |  | 0 | 0 | 0% | 43000 | 0 | 0 | 0 |  |  |  | B0045
B0046 | B0046 Investment - Ship Street | 20000 | 0 | 20000 | 20000 | 0 |  |  |  | 0 | 0 | 0% | 20000 | 0 | 0 | 0 |  |  |  | B0046
B0070 | B0070 Ramsay House Replacement Comfort Cooling System | 300000 | 0 | 300000 | 300000 | 4000 |  |  |  | 3800 | -200 | 1.267% | 300000 | 0 | 0 | 0 |  |  |  | B0070
#N/A
| Miscellaneous Council Properties | [18 empty] | #N/A
B0031 | B0031 Miscellaneous Admin Buildings | 5000 | 20000 | 25000 | 25000 | 0 |  |  |  | 0 | 0 | 0% | 25000 | 0 | 0 | 0 |  |  |  | B0031
B0035 | B0035 Miscellaneous Civic Properties | 25000 | 27218.43 | 52218.43 | 52218.43 | 18000 |  |  |  | 18343.3 | 343.3 | 35.13% | 52218.43 | 0 | 0 | 0 |  |  |  | B0035
B0037 | B0037 Car Parks | 80000 | 55380 | 135380 | 135380 | 0 |  |  |  | 370.14 | 370.14 | 0.2734% | 135380 | 0 | 0 | 0 |  |  |  | B0037
B0039 | B0039 Houses and Lodges | 0 | 16423.07 | 16423.07 | 16423.07 | 0 |  |  |  | 0 | 0 | 0% | 16423.07 | 0 | 0 | 0 |  |  |  | B0039
B0052 | B0052 Miscellaneous Properties | 75000 | 0 | 75000 | 75000 | 0 |  |  |  | 0 | 0 | 0% | 75000 | 0 | 0 | 0 |  |  |  | B0052
B0053 | B0053 Public Toilets | 0 | 489.1 | 489.1 | 489.1 | 0 |  |  |  | 0 | 0 | 0% | 489.1 | 0 | 0 | 0 |  |  |  | B0053
B0055 | B0055 Property Surveys | 50000 | 7600 | 57600 | 57600 | 48000 |  |  |  | 47150.75 | -849.25 | 81.86% | 57600 | 0 | 0 | 0 |  |  |  | B0055
B0059 | B0059 FIT Panels on Leisure Buildings | 0 | 0 | 0 | 0 | 0 |  |  |  | 1150 | 1150 | 0% | 0 | 0 | 0 | 0 |  |  |  | B0059
B0060 | B0060 Feasibility Studies Depot Relocation | 200000 | 50000 | 250000 | 250000 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0% | 250000 | 0 | 0 | 0 |  |  |  | B0060
#N/A
| Parks & Cemeteries | [18 empty] | #N/A
B0048 | B0048 Leisure - Cemeteries | 13500 | 0 | 13500 | 13500 | 0 |  |  |  | 0 | 0 | 0% | 13500 | 0 | 0 | 0 |  |  |  | B0048
B0050 | B0050 Leisure ~ Depots | 65000 | 9000 | 74000 | 74000 | 3000 |  |  |  | 2746.93 | -253.07 | 3.712% | 74000 | 0 | 0 | 0 |  |  |  | B0050
B0051 | B0051 Leisure - Pavilions | 110500 | 0 | 110500 | 110500 | 0 |  |  |  | 0 | 0 | 0% | 110500 | 0 | 0 | 0 |  |  |  | B0051
B0065 | B0065 Parks & Cemetery - Masonry Walls & Path Improvements | 40000 | 0 | 40000 | 40000 | 7000 | 40000 | 40000 | 0 | 6896 | -104 | 17.24% | 40000 | 0 | 0 | 0 |  |  |  | B0065
B0067 | B0067 Fencing Repairs across the City | 150000 | 0 | 150000 | 150000 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0% | 150000 | 0 | 0 | 0 |  |  |  | B0067
b0071 | B0071 Parks properties (H&S works) | 36648 | 0 | 36648 | 36648 | 0 |  |  |  | 0 | 0 | 0% | 54648 | 18000 | 0 | 18000 |  |  | This budget can be enlarged because Oxford Brookes University have made a contribution of £18,000 towards drainage works at Headington Hill Park | #N/A
A4823 | A4823 Cemetery Development | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 15000 | 0 | 0 | 0 |  |  |  | #N/A
#N/A
| Town Hall | [18 empty] | #N/A
B0054 | B0054 Town Hall | 677500 | 94000 | 795852 | 795852 | 50000 |  |  |  | 50724.67 | 724.67 | 6.374% | 754583.35 | -41268.65 | 0 | -41268.65 |  |  | Virement required to offset overspend on Town Hall Fire Alarm | B0054
B0056 | B0056 City Centre Office Security | 0 | 75903.93 | 75903.93 | 75903.93 | 5000 |  |  |  | 5319.45 | 319.45 | 7.008% | 75903.93 | 0 | 0 | 0 |  |  |  | B0056
B0057 | B0057- Town Hall Fire Alarm | 100000 | 95000 | 195000 | 195000 | 116000 |  |  |  | 114609.65 | -1390.35 | 58.77% | 236268.65 | 41268.65 | 0 | 41268.65 |  |  | Invoice for £121,660 in July takes forecast to £236K. Will need to be absorbed from other projects | B0057
B0068 | B0068 Town Hall - Conference System Refurbishment | 400000 | 0 | 400000 | 400000 | 22000 |  |  |  | 22126.5 | 126.5 | 5.532% | 400000 | 0 | 0 | 0 |  |  |  | B0068
#N/A
Budge | Budget Approved for Future Years - To be allocated | [18 empty] | #N/A
Refur | Refurbishment of Council Buildings | 24352 | 0 | 0 | 0 | 0 | 1400000 | 1400000 | 600000 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  |  |  | #N/A
#N/A
Corpo | Corporate Assets | 3841000 | 1568564.58 | 5409564.58 | 5409564.58 | 657270.3333 | 3450000 | 1656000 | 600000 | 659787.17 | 2516.8367 | 12.2% | 5259286.58 | -150278 | -328278 | 178000 |  |  |  | #N/A
#N/A
C3041 | C3041 New server for telephone system | 0 | 11288 | 11288 | 11288 | 0 |  |  |  | 0 | 0 | 0% | 11288 | 0 | 0 | 0 | M Molyneux | H Bishop | Part of the Customer First Project on track to bespent in 12/13 | C3041
C3042 | C3042 Customer First Programme | 0 | 115669.88 | 115669.88 | 115669.88 | 0 |  |  |  | 0 | 0 | 0% | 115669.88 | 0 | 0 | 0 | M Molyneux | H Bishop | On track to be finished in 12/13 no slippage | C3042
#N/A
Custo | Customer Services | 0 | 126957.88 | 126957.88 | 126957.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 126957.88 | 0 | 0 | 0 |  |  |  | #N/A
#N/A
A1300 | A1300 Playground Refurbishment | 250000 | 164797.12 | 414797.12 | 414797.12 | 180000 | 0 | 0 |  | 175769.82 | -4230.18 | 42.37% | 414797.12 | 0 | 0 | 0 |  |  |  | A1300
A1301 | A1301 Play Barton | 0 | 113537.96 | 113537.96 | 113537.96 | 0 | 0 | 0 |  | 0 | 0 | 0% | 113537.96 | 0 | 0 | 0 |  |  |  | A1301
#N/A
A4810 | A4810 New Build Completion Pool | 6938071 | 644182.98 | 7582253.98 | 7582253.98 | 0 | 0 | 0 |  | 0 | 0 | 0% | 82254 | -7499999.98 | -7500000 | 0 |  |  | Start of construction delayed due to second Judicial Review. Significant slippage expected as construction now unlikely to commence until 13/14. | A4810
#N/A
Z3008 | Z3008 Contribution to Skate Park | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 50000 | 0 | 0 | 0 |  |  |  | Z3008
Z3010 | Z3010 Rosehill/Iffley Play Sites | 0 | 38000 | 38000 | 38000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 38000 | 0 | 0 | 0 |  |  |  | Z3010
#N/A
A4815 | A4815 Leisure Centre Improvement Work | 700000 | 0 | 700000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 700000 | 0 | 0 | 0 |  |  | Ice Rink and Ferry works currently out to tender, with estimated completion date for works November. | A4815
A4817 | A4817 Develop new burial space | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  |  |  | #N/A
A4818 | A4818 Lye Valley & Chiswell Valley Walkways | 62000 | 0 | 62000 | 62000 | 0 | 62000 | 0 | 0 | 0 | 0 | 0% | 62000 | 0 | 0 | 0 |  |  |  | A4818
A4816 | A4816 Sports Pavilions | 450000 | 0 | 450000 | 450000 | 0 | 470000 | 200000 | 0 | 0 | 0 | 0% | 450000 | 0 | 0 | 0 |  |  | Project Manager to commence in September. Initial smaller scale items undertaken by Direct Services likely to take in quarter 4 with larger itmes unlikely to commence until 13/14. A detailed schedule of works will be developed by the appointed project manager. | A4816
A4819 | A4819 Rose Hill Cemetery Water Leak | 8000 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 8000 | 0 | 0 | 0 |  |  |  | #N/A
A4820 | A4820 Upgrade Existing Tennis Courts | 50000 | 0 | 50000 | 50000 | 0 | 60000 | 54000 | 60000 | 0 | 0 | 0% | 50000 | 0 | 0 | 0 |  |  |  | A4820
A4821 | A4821 Upgrade Existing Multi-Use Games Area | 76000 | 0 | 76000 | 76000 | 0 | 48000 | 48000 | 48000 | 0 | 0 | 0% | 76000 | 0 | 0 | 0 |  |  |  | A4821
A4822 | A4822 Recycling & Bin Improvement (City Parks) | 38000 | 0 | 38000 | 38000 | 0 | 13000 | 12000 | 12000 | 0 | 0 | 0% | 38000 | 0 | 0 | 0 |  |  |  | A4822
G6013 | G6013 Cycle Oxford | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 50000 | 50000 | 0 | 0 | 0% | 100000 | 0 | 0 | 0 |  |  | Not a Leisure project | #N/A
#N/A
City | City Leisure | 8672071 | 1010518.06 | 9682589.06 | 9682589.06 | 180000 | 753000 | 364000 | 170000 | 175769.82 | -4230.18 | 1.815% | 2182589.08 | -7499999.98 | -7500000 | 0 |  |  |  | #N/A
#N/A
F0011 | F0011 Pay & Display Parking in the Car Parks | 84000 | 0 | 84000 | 84000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 84000 | 0 | 0 | 0 | L Barker | R Summer/ J Munro |  | F0011
F0012 | F0012 P & R Purchase of Capital Items - Peartree, Redbridge | 0 | 191643.91 | 191643.91 | 191643.91 | 0 | 0 | 0 |  | 0 | 0 | 0% | 191643.91 | 0 | 0 | 0 |  | J Munro |  | F0012
F0014 | F0014 Purchase of ANPR for use in car park enforcement | 0 | 50000 | 50000 | 50000 | 30000 | 0 | 0 |  | 32036.72 | 2036.72 | 64.07% | 50000 | 0 | 0 | 0 | L Barker | R Summer/ J Munro |  | F0014
#N/A
R0005 | R0005 MT Vehicles/Plant Replacement Programme. | 1280000 | 45015.25 | 1500500.25 | 1325015.25 | 276044.7917 | 2301000 | 1991000 | 1799000 | 252248.05 | -23796.7417 | 19.04% | 1500500.25 | 0 |  |  | L Barker | P Einon | There is a budget shortfall in this rolling programme. Slippage of £130,985 in 2010/11 was not carried forward into 2011/12 and part exchange on vehicle disposal of £45,500 in 2011/12 was not factored into the 2012/13 budget. Additional funding is therefore requested for 2012/13 | R0005 | 130984.97
#N/A
T2266 | T2266 Purchase of Brown Bins Waste Recycling | 0 | 7906.83 | 7906.83 | 7906.83 | 0 | 0 | 0 |  | 0 | 0 | 0% | 7906.83 | 0 | 0 | 0 | L Barker | P Dunsdon |  | T2266
T2267 | T2267 Purchase of two hand operated street sweepers | 0 | 30000 | 30000 | 30000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 30000 | 0 | 0 | 0 | L Barker | P Einon |  | T2267
T2268 | T2268 Purchase of two vehicles for garden waste collection | 0 | 155000 | 155000 | 155000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 155000 | 0 | 0 | 0 | L Barker | P Einon |  | T2268
T2269 | T2269 Toilet improvements | 185000 | 0 | 185000 | 185000 | 0 | 175000 | 85000 |  | 0 | 0 | 0% | 190000 | 5000 | 5000 |  |  |  | Works to start July 2012, awaiting consultants report of Florence Park Scheme | T2269
T2270 | T2270 Bin stores for council flats to assist recycling | 325000 | 0 | 325000 | 325000 | 6000 |  |  |  | 5740.28 | -259.72 | 1.766% | 325000 | 0 | 0 | 0 |  |  |  | T2270
T2271 | T2271 Low emission vehicle for litter bin collection | 20000 | 0 | 20000 | 20000 | 0 |  |  |  | 0 | 0 | 0% | 20000 | 0 | 0 | 0 |  |  |  | #N/A
T2272 | T2272 Wyatt Road Resurfacing Works | 0 | 0 | 15000 | 0 | 0 |  |  |  | 0 | 0 | 0% | 15000 | 0 |  |  |  |  | New addition to Capital Programme. Budget approval required - Works to start Sept 2012
#N/A
Direct | Direct Services | 1894000 | 479565.99 | 2564050.99 | 2373565.99 | 312044.7917 | 2476000 | 2076000 | 1799000 | 290025.05 | -22019.7417 | 12.22% | 2569050.99 | 5000 | 5000 | 0 | 0 | 0 |  | #N/A
#N/A
C3039 | C3039 ICT Infrastructure | 150000 | 110434 | 260434 | 260434 | 0 | 200000 | 100000 | 150000 | 3963.42 | 3963.42 | 1.522% | 260434 | 0 | 0 | 0 | P Swaffield | A Orchard | No spend to date but budget to be used for Windows 7 project, in Q3+Q4 | C3039
C3043 | C3043 ICT Development | 0 | 200000 | 200000 | 200000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 200000 | 0 | 0 | 0 | P Swaffield | A Orchard | No spend to date but budget to be used for other urgent IT, in Q3+Q4 | C3043
C3044 | C3044 Software Licences | 177000 | 0 | 177000 | 177000 | 165426 | 177000 | 177000 | 177000 | 162306.18 | -3119.82 | 91.7% | 165426 | -11574 | 0 | -11574 |  |  | Spend loaded into C3039 as C3044 not set up on agresso - curr proj to spend £165k | #N/A
#N/A
ICT s | ICT services | 327000 | 310434 | 637434 | 637434 | 165426 | 377000 | 277000 | 327000 | 166269.6 | 843.6 | 26.08% | 625860 | -11574 | 0 | -11574 |  |  |  | #N/A
#N/A
GF To | GF Total | 15598342 | 3684071.42 | 19472898.42 | 19900638.42 | 1604291.125 | 7746000 | 5063000 | 3536000 | 1548863.73 | -55427.395 | 7.783% | 12472260.88 | -7000637.54 | -7823278 | 822640.44 | 0 | 0 | 0 | #N/A | 0 | 0
Exter | External Contracts
N6384 | N6384 Foresters Towers | 1000000 | 0 | 1000000 | 50000 | 2083 | 1000000 | 1000000 | 1000000 | 2140 | 57 | 4.28% | 50000 | -950000 | -950000 | 0
N6387 | N6387 Controlled Entry | 0 | 0 | 0 | 210000 | 0 | 0 | 0 |  | 0 | 0 | 0% | 210000 | 210000 |  | 210000
N6393 | N6393 External Doors | 200000 | 0 | 200000 | 200000 | 1667 | 200000 | 200000 | 200000 | 402.31 | -1264.69 | 0.2012% | 200000 | 0 |  | 0
N7020 | N7020 External Adaptations | 0 | 0 | 0 | 250000 | 22917 | 0 | 0 |  | 22535 | -382 | 9.014% | 250000 | 250000 |  | 250000
N7021 | N7021 Extensions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17591.44 | 17591.44 | 0% | 0 | 0 |  | 0 |  |  | This relates to 21 Farmer Place and has been funded by the County Council (£66K)
N7018 | N7018 Minox | 0 | 0 | 0 | 19500 | 0 | 0 | 0 |  | 0 | 0 | 0% | 19500 | 19500 |  | 19500
N6394 | N6394 Windows | 300000 | 0 | 300000 | 250000 | 67708 | 300000 | 300000 | 100000 | 67173.06 | -534.94 | 26.87% | 250000 | -50000 |  | -50000
N6389 | N6389 Damp-proof works (K&B) | 0 | 0 | 0 | 90000 | 18750 | 0 | 0 |  | 19181.27 | 431.27 | 21.31% | 90000 | 90000 |  | 90000
N6392 | N6392 Roofing | 250000 | 0 | 250000 | 150000 | 75000 | 250000 | 250000 | 250000 | 73136.3 | -1863.7 | 48.76% | 150000 | -100000 |  | -100000
N6386 | N6386 Structural | 0 | 0 | 0 | 125000 | 7292 | 0 | 0 |  | 7655.37 | 363.37 | 6.124% | 125000 | 125000 |  | 125000
N7010 | N7010 Headley House - Refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 0
N6427 | N6427 Shops | 0 | 0 | 0 | 69000 | 18688 | 0 | 0 |  | 18863.18 | 175.18 | 27.34% | 69000 | 69000 |  | 69000
N6396 | N6396 Sheltered Blocks | 0 | 0 | 0 | 0 | 0 |  |  |  | 109.14 | 109.14 | 0% | 0 | 0
N7028 | N7028 Non Dwelling HRA Assets | 117000 | 0 | 117000 | 48000 | 0 | 117000 | 117000 | 117000 | 0 | 0 | 0% | 48000 | -69000 |  | -69000
N7026 | N7026 Communal Areas | 150000 | 0 | 150000 | 150000 | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0% | 150000 | 0 |  | 0
N7027 | N7027 Environmental Improvements | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0% | 100000 | 0 |  | 0
New C | New Contingency | 19000 | 0 | 19000 | 0 | 0 | 19000 | 19000 | 19000 | 0 | 0 | 0% | 0 | -19000 |  | -19000 |  |  | Utilising budget for specific schemes in line with HRA BP
New F | New Fees | 94000 | 0 | 94000 | 0 | 0 | 94000 | 94000 | 80000 | 0 | 0 | 0% | 0 | -94000 |  | -94000 |  |  | Utilising budget for specific schemes in line with HRA BP
New B | New Build
N7011 | N7011 Cardinal House - Refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2000 | 2000 | 0% | 0 | 0 | 0 | 0 |  |  | It is anticipated that this scheme will be funded from retentions from Contractors
N7019 | N7019 Lambourn Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8364.6 | 8364.6 | 0% | 0 | 0 | 0 | 0
HCA | HCA New Build | 0 | 0 | 0 | 466000 | 0 |  |  |  | 0 | 0 | 0% | 466000 | 466000 | 0 | 466000 |  |  | Work approved and funded within HRA BP but not included within capital programme.
0
Inter | Internal Contracts | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0
N6385 | N6385 Adaptations for disabled | 900000 | 0 | 900000 | 900000 | 223836 | 900000 | 900000 | 900000 | 361617.52 | 137781.52 | 40.18% | 900000 | 0 | 0 | 0
N6390 | N6390 Kitchens & Bathrooms | 2850000 | 0 | 2850000 | 2850000 | 833915 | 2850000 | 2549000 | 2490000 | 861228.19 | 27313.19 | 30.22% | 2850000 | 0 | 0 | 0
N6391 | N6391 Heating | 1256000 | 0 | 1256000 | 1256000 | 276000 | 1256000 | 1221000 | 1221000 | 410744.04 | 134744.04 | 32.7% | 1256000 | 0 | 0 | 0
N6388 | N6388 Major Voids | 850000 | 0 | 850000 | 805000 | 211399 | 830000 | 820000 | 800000 | 78192.32 | -133206.68 | 9.713% | 850000 | 0 | 0 | 0 |  |  | Revised spend in line with capital review.
N6395 | N6395 Electrics | 309000 | 0 | 309000 | 309000 | 90528 | 309000 | 309000 | 309000 | 33237.11 | -57290.89 | 10.76% | 309000 | 0 | 0 | 0
| Housing Revenue Account | 8395000 | 0 | 8395000 | 8297500 | 1849783 | 8375000 | 8029000 | 7736000 | 1984170.85 | 134387.85 | 23.91% | 8342500 | -52500 | -950000 | 897500
| Grand Total | 23993342 | 3684071.42 | 27867898.42 | 28198138.42 | 3454074.125 | 16121000 | 13092000 | 11272000 | 3533034.58 | 78960.455 | 12.53% | 20814760.88 | -7053137.54 | -8773278 | 1720140.44
Financing - General Fund
| Developer contributions | 0 | 0 | 0 | 618225 | [7 empty] | 656215 | 656215 |  | 656214
| Government Funding | 590000 | 0 | 590000 | 590000 |  | 390000 | 390000 | 390000 |  |  |  | 590000 | 0
| Capital Receipts | 3378000 | 0 | 7079787 | 7079787 |  | 2262583 | 1000000 | 632220 |  |  |  | 5586556 | -1493231 | -1559157 | 6426 |  |  | Funded carry forward budgets from unused capital receipts
| Direct Revenue Funding | 3600000 | 0 | 3600000 | 3600000 |  | 1340000 | 1333280 | 1453780 |  |  |  | 3600000 | 0
| Revenue Reserves | 457505 | 0 | 457505 | 457505 |  | 356000 | 0 | 0 |  |  |  | 617505 | 160000 |  | 160000
| DRF For Vehicles | 1291000 | 0 | 1481485 | 1291000 |  | 1230000 | 1270000 | 1370000 |  |  |  | 1421985 | -59500
| Prudential Borrowing | 6281837 | 0 | 6264121 | 6264121 |  | 3467417 | 1064720 |  |  |  |  | 0 | -6264121 | -6264121
| Total General Fund Financing | 15598342 | 0 | 19472898 | 19900638 |  | 9046000 | 5058000 | 3846000 |  |  |  | 12472261 | -7000637 | -7823278 | 822640
Financing - HRA
| MRR | 8395000 | 0 | 8395000 | 8297500 | [7 empty] | 8342500 | -52500 | -950000 | 897500
| Capital receipts | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
| Decent Homes Reserve | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
| Prudential Borrowing | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
| External Contributions | [5 empty] | 8375000 | 8029000 | 7736000
| Total HRA Financing | 8395000 |  | 8395000 | 8297500 |  | 8375000 | 8029000 | 7736000 |  |  |  | 8342500 | -52500 | -950000 | 897500
| Total Financing | 23993342 |  | 27867898 | 28198138 |  | 17421000 | 13087000 | 11582000 |  |  |  | 20814761 | -7053137 | -8773278 | 1720140
0.42
0.42
|  |  |  | 0.42 | [8 empty] | -0.12 | -0.54 | 0 | 0.44
[21 empty] | 45051 | R005
[21 empty] | 44500 | Part Exchanges in 2011/12
89551
[21 empty] | 130984.97 | Not Carried Forward or Accrued in 2010/11
[21 empty] | 220535.97 | Total for R005
[21 empty] | 155000 | T2267
[21 empty] | 30000 | T2268
[21 empty] | 405535.97 | Total Carry Forward
Note on E135: Licensed User: ADDED IN