## CRR
Formal Risk Summary
As at: Jun-2012
Risk | [5 empty] | Date Raised | Owner | Gross |  |  | Current |  | Score | Residual |  |  | Actions
Ref | Title | Risk description | Opp/ threat | Cause | Consequence |  |  | I | P | Gross | I | P | Current | I | P | Residual | Description | Due date | % complete | Owner
CRR-007 | Health & Safety | Existence of operational risks (relating to internal as well as public concerns - property not vehicle) | T | Health and Safety practices are not robust enough. Under investment in property, potential lack of clarity of accountability and of ownership of health and safety | Increased insurance claims and ultimately premium costs. Reputational implications. | 2-Jan-2010 | David Edwards | 4 | 3 | 12 | 4 | 3 | 12 | 3 | 2 | 6 | Create 'one view' of all corporate assets (issues, status of building, budget, work required, timescales). 'One view' being everything documented in consistent and understandable format which can be shared across organisational boundaries. | 1-Mar-2012 | 50% | Steve Sprason
[17 empty] | Complete annual H&S report to CEB including claims record and statement on housing landlord responsibilities | 30/9/12 | 75% | Steve Sprason
[17 empty] | Develop a corporate approach towards health and safety | 1-Mar-2012 | 100% | Steve Sprason
[17 empty] | Complete H&S records on all estate management eledctronic records | 30/9/12 | 75% | Steve Sprason
[17 empty] | Establish Corporate Asset Management Group to create a joined up approach towards management of Corporate Assets | 1-Mar-2012 | 50% | Steve Sprason
CRR-013 | Impact on homelessness of changes in Housing Benefit | Changes in housing benefit and universal housing benefit increase homelessness | T | Changes in housing benefit and universal housing benefit increase homelessness | Cost the council more money in administration and payments to landlords | 1-Dec-2009 | David Edwards | 5 | 3 | 15 | 3 | 5 | 15 | 3 | 3 | 9 | Monitoring and intervention, ensure takeup of benefits | 1-Mar-2012 | 50% | Helen Bishop
CRR-004 | Delivery of key projects = ability to deliver cross cutting projects | People and the council are not developed sufficiently to make risk based decisions, carry out options appraisals. Decision making can be poor. Innovation is not encouraged, low risk appetite. | T | Recent adoption of Project Management methodology (experience in the council is minimal). Conflict between BAU and Project work. Process focused and not fully embedded. | Project methodology is not applied consistently across the council. Budget variations, volatility in results and benefits not realised. Board intervention. Council does not innovate or change. Ability of the council to deliver objectives. | 2-Jan-2010 | Jacqui Yates | 4 | 3 | 12 | 3 | 3 | 9 | 3 | 2 | 6 | CMT act as mentors within boards to encourage innovation and a culture where decisions are taken based on a robust options appraisal | 1-Mar-2012 | 65% | CMT
[17 empty] | Develop clear roles, responsibilities and job descriptions/expectations for managers, heads of, directors | 1-Mar-2012 | 50% | Simon Howick
[17 empty] | Development of a business partner model to project management using centre of knowledge within the Project Management office | 1-Mar-2012 | 100% | Jane Lubbock
[17 empty] | Development of corporate approach to project management via a corporate project management office. | 1-Mar-2012 | 100% | Jane Lubbock
[17 empty] | Development of options appraisal methodology for capital projects | 1-Mar-2012 | 100% | Steve Sprason
CRR-006 | Supplier Management | Ability of the council to manage large contracts and to obtain best value from those contracts | T | Correctly identifying appropriate staff with corporate and commercial awareness to manage contracts (where balancing reduction in staff with keeping best staff to manage contracts) | Council does not realise benefits from large contracts | 2-Jan-2010 | Jacqui Yates | 2 | 4 | 8 | 3 | 3 | 9 | 3 | 2 | 6 | Corporate contract management framework written and will be rolled out during 2012 | 3-Dec-2012 | 10% | Jane Lubbock
[17 empty] | Develop the procurement team as a centre of excellence for relationship management. | 1-Mar-2012 | 100% | Jane Lubbock
[17 empty] | Development and approval of procurement strategy. Ensure consistent approach towards supplier management across the organisation. | 1-Mar-2012 | 100% | Jane Lubbock
[17 empty] | Implement a mentoring/work shadowing programme where expertise can be shared with new contract managers. | 1-Mar-2012 | 70% | Jane Lubbock
[17 empty] | Implement standard contract documentation and approach (based on 4Ps approach to contract management ) | 1-Mar-2012 | 100% | Jane Lubbock
CRR-012 | Failure to achieve budget reductions over four year period | Inability to achieve savings in budget | T | Significant efficiency savings and service reductions as a result of Comprensive Spending Review | Increased use of balances or further reductions to be identified | 1-Oct-2010 | Jacqui Yates | 4 | 3 | 12 | 3 | 3 | 9 | 3 | 3 | 9 | Effective budget monitoring framework in place |  | 85% | Nigel Kennedy
[17 empty] | Proactive management and tracking of major forecast uncertainties |  | 60% | Nigel Kennedy
[17 empty] | Robust MTF planning framework in place | 1-Mar-2012 | 100% | Nigel Kennedy