# Homelessness Strategy (City Executive Board Report 12th September 2012): Appendix 2

# Risk Register

| No. | Risk Description Link to Corporate Obj | Gross Risk | Cause of Risk | Mitigation | Net Risk | Further Management of Risk: Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Current Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Score Impact Score: 1 =Insignificant; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Catastrophic Probability Score: 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost Certain |
|  |  | I | P |  | Mitigating Control: Level of Effectiveness: (HML) | I | P | Action: Action Owner: Mitigating Control: Control Owner: | Outcome required: Milestone Date: | Q 1 ((( | Q 2((( | Q 3((( | Q4((( | I | P |
| 1. | Inadequate consultation to ensure relevance of homelessness strategy objectives`` | 3 | 3 | Lack of consultation and communication of developing Strategy | Consultation plan to include stakeholders and public | 2 | 2 | Implement consultation plan Housing Strategy and Enabling Manager | Consultation Plan implemented and completed by November 2012 |  |  |  |  |  |  |
| 2. | Failure to meet the objectives of the Homelessness Strategy | 4 | 3 | Ineffective monitoring of the strategic objective action plans. | Establish clear monitoring process within the Council’s structure through Housing Board | 3 | 2 | .Ensure regular review through Housing Board Housing Strategy and Enabling Manager | Regular monitoring reports |  |  |  |  |  |  |
| 3. | Changes to housing policy or context and, local, regional and national, making objectives invalid or inappropriate. | 3 | 3 | Economic circumstances, government policy and legislation, political changes. | In addition to regular monitoring, review of the strategy and objectives to ensure it remains relevant to current circumstances. | 3 | 3 | Establish regular and robust monitoring arrangements for policy, context and legislative changes Housing Strategy and Enabling Manager | Mid point review completed by September 2015 |  |  |  |  |  |  |
| . | Negative public and stakeholder understanding / perceptions of homelessness strategy objectives. | 3 | 3 | Failure to communicate objectives and impacts on homelessness in Oxford. | Establish clear communication strategy for the homelessness strategy for when it is adopted. | 2 | 3 | Implement communication strategy Housing Strategy & Enabling Manager | Communication Strategy in place by March 2013. |  |  |  |  |  |  |