APPENDIX 5 - RISK REGISTER

Risk Score: Impact Score: 1=insignificant; 2=minor ;3=moderate; 4=major; 5=catastrophic	Probability Score: 1=Rare;2=Unlikely;3=Possible’4=Likely’5=Almost Certain

| No | Risk description link to corporate obj. | Gross risk | Cause of risk | Mitigation | Net risk | Further Management of Risk Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Control Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Tenants scrutiny panel not established by April 2013. (Strong and Active Communities) | 3 | 3 | Action plan not implemented robustly. | Key dates booked with TPAS to take forward task group. Task group selected by December. Staff member in Housing with specific remit to ensure programme is implemented. | 2 | 2 | Action plan reviewed regularly: Head of Housing/Housing Board | Tenants Housing Scrutiny Panel set up for April 2013 | Q 1 | Q 2 | Q 3 | Q 4 | I | P |
| 2. | Limited number of tenants respond to getting more involved. (Strong and Active Communities) | I 4 | P 3 | Range of methods for engagement not implemented effectively. | Ensure range of tools used for engagement and build up database. | I 3 | P 2 | Publicise outcomes of tenants involvement regularly to promote and encourage more tenants to be involved: C&N Manager | Database of tenants/leaseholders numbers to be regularly reported on website and to Housing Board. |  |  |  |  |  |  |
| 3. | Tenants Strategy not fully embaced by relevant OCC services and do not offer sufficient topics of interest for tenants. (Efficient and Effective Council). | 3 | 3 | OCC services not fully aware of regulatory background for greater tenants involvement | Ensure training for Heads of Service and key staff is implemented in Dec/Jan 2013. | 2 | 1 | Housing Board to develop and regularly review programme of service involvement with tenants: Head of Housing | Monitored through quarterly review of Hosuing Board |  |  |  |  |  |  |