## Risk Register
Communal Flats collection Policy Change | [9 empty] | 2012-11-27
Risk Register
Risk ID | Date Raised | Project / Programme | Risk Category | Description of the Risk | Current Gross Risk Rating |  |  | Mitigating Actions | Action Due Dates | Action owner | Residual Risk Rating |  |  | Status (Open / Closed) | Date of last update
[5 empty] | P | I | Score |  |  |  | P | I | Score | Proximity | Proximity
CEB-001 | 2012-10-24 | Communal Flats collection Policy Change | Political | Policy change is not approved by elected members. The consequence would be that the current target to increase recycling (as set by current members) would take more time, and would be more difficult to achieve. Such a decision would also conflict with the Cleaner Greener campaign. | 2 | 3 | 6 | Cross party consultation; regular updates with council members. | 2012-12-05 | Graham Bourton | 2 | 2 | 4 | Open | 2012-10-25 | Strategic & commercial
CEB-002 | 2012-10-24 | Communal Flats collection Policy Change | Strategic & commercial | We are not able to deliver the project objectives in the way which we intend and therefore not achieve our target recycling rate | 3 | 2 | 6 | We intend to run two pilot schemes offering advice, support and education with two pro-active managing agents. | 2013-06-30 | Stewart Downs | 2 | 2 | 4 | Open | 2012-10-25 | Technical, operational and infrastructure
CEB-003 | 2012-10-24 | Communal Flats collection Policy Change | Strategic & commercial | Exposed to possible challenges | 3 | 3 | 9 | Running the pilot schemes, alongside a 12 month consultation period. 'Ensure that what is on site is reasonable.' | 2013-12-31 | Stewart Downs | 2 | 2 | 4 | Open | 2012-10-25 | Technical, operational and infrastructure
Insert new row above
[16 empty] | 1 | 1 - More Housing Better Housing for all
[16 empty] | 2 | 2 - Stronger & more inclusive communities
[16 empty] | 3 | 3 - Improve the local environment, economy & quality of life
[16 empty] | 4 | 4 - Reduce anti-social behaviour
[16 empty] | 5 | 5 - Tackle climate change & promote environmental resource management
[16 empty] | 6 | 6 - Transform OCC by improving value for money and Service performance
[16 empty] | I | Immanent (within project timeline or current financial year)
[16 empty] | S | Short-term (within MTFS)
[16 empty] | L | Longer term (end of or beyond MTFS)
[16 empty] | Open | Open
[16 empty] | Agreed | Response agreed
[16 empty] | Esc | Escalation agreed
[16 empty] | Closed | Closed
[16 empty] | Rev | To Review
[16 empty] | Trans | Transferred to Issue Log