Homelessness Strategy Action Plan 2013-2018

This Action Plan is a tool for delivering our Homelessness Strategy by determining clear actions, performance targets, responsibilities, resources and monitoring arrangements. Also included within this Plan are actions tackling wider housing and support issues which will be taken forward via other Strategies.  It has an early focus – concentrating on actions to be achieved in the first 12-18 months of the Strategy. This is considered appropriate given current uncertainties with the outcome of some reviews, projects and impact of new national policy.  The Action Plan will be reviewed after the first full year (to 31 March 2014) and revised targets will be set at this stage for later years.

Through robust monitoring we will ensure that our targets are effectively planned, continually delivered and regularly refreshed.  The action plan targets will be subject to our established performance management and business planning cycle.

Responsibility for monitoring the Action Plan is as follows:

| Level | Frequency | Responsibility |
| --- | --- | --- |
| City Executive Board | Annual | Annual review on progress and to determine further actions needed to deliver the plan. |
| Scrutiny - Housing Panel | As per work programme | Review key performance indicators and statistics showing trends, progress to date |
| Corporate Performance Monitoring – Housing Board | Quarterly | Review progress of the complete plan and consider any shifts in resources to tackle under/over performance and corrective action needed |
| Managers | Quarterly | Discuss with relevant team leaders to review progress and resolve any barriers to delivery. To be referred to Departmental Monitoring if unable to resolve. |
| Team | Quarterly | Meet with team members to review progress on action plans and where possible remove barriers to delivery. Refer to managers if unable to resolve |
| Individual | 6 monthly appraisals and regular one to one meetings | Priorities set in appraisals and review meetings. Review progress and barriers and develop individual solutions to remove barriers. |

# PREVENTING AND RESPONDING TO HOMELESSNESS

| GOAL | KEY ACTIONS/MILESTONES | TIMESCALE | RESOURCES | RESPONSIBILITy |
| --- | --- | --- | --- | --- |
| Reduce homelessness caused by parental exclusions | Review homeless mediation services provided by suitably trained and skilled independent mediators with specialist relationship breakdown expertise to ensure maximum effectiveness Develop and introduce re-housing plans with parents and children Ensure revised allocations scheme supports homeless prevention initiatives does not provide incentives for parental exclusions | Sept 2013 June 2013 By Sept 2013 | OCC mainstream Homeless Prevention budgets Existing resources Existing resources | Options Manager Options Manager Allocations Manager |
| Maximise homelessness prevention and best use of resources | Develop a case ownership approach to homeless prevention casework in the Council’s Options Team Adopt policy relating to the new power (in the Localism Act) to discharge full homeless duties into the PRS – Private Sector Offer Revise procedures and staff awareness/training to incorporate any policy change Monitor progress (see also linking actions re: Home Choice and role of private rented sector) | June 2013 February 2013 (CEB) April 2013 Ongoing | Within existing resources Within existing resources Within existing resources Within existing resources | Options Manager Housing Needs Manager Options Manager Options Manager |
| Maximise the role of Home Choice | Produce report and options analysis considering the outcomes of landlord surveys and views of Home Choice to review scope of the scheme and analysis of current activity and performance. Undertake a gaps and options analysis including: Review possibility of creating a social lettings agency Review extension of deposit schemes Review incentives offered to landlords Review advice and support offered to landlords and clients Out of area moves where appropriate | December 2013 | Within existing resources | Private Rented Team Manager |
| Increase access to private rented sector homes | Building on above and through targeted communications, encourage and support people who don’t currently see themselves as landlords but may be prepared to let out property or rooms. Undertake awareness and publicity campaigns through press releases, website, newsletters and targeted approaches e. g. owners of empty homes | Dec 2013 Sept 2013 | Within existing resources Within existing resources | Private Rented Team Manager Private Rented Team Manager supported by Strategy and Enabling team |
| Support and develop services to promote financial inclusion | Support development of Oxford City Financial Inclusion Strategy, with integrated financial management, budgetary skills and benefit advice Review awareness and role and working with Credit Unions Prepare report and review lessons learnt from Demonstration Projects for Universal Credit. Implement any new working practices Improved referrals and access for debt advice and money management follow review of role of advice agencies (outcome of linked Housing Strategy target due Sept 2013) Develop plans to target large families who are likely to be impacted by welfare changes including the Benefit Cap and those affected by under-occupation changes Implement plan and monitor progress | Ongoing and by April 2014 By Sept 2013 By Dec 2013 By Dec 2013 Plan by Apr 2013 Ongoing with review as at end March 2014 | Within existing resources Within existing resources Within existing resources Within existing resources Plan developed within existing resources Resources to deliver to be identified in plan and agreed before implementation | Head of Policy/Head of Housing Head of Housing/Head of Customer Services supported by Housing Needs Manager, Strategy and Enabling Manager, Communities and Neighbourhoods Manager, Housing Benefit Manager and Rents Manager Head of Housing Housing Needs Manager/Landlord Services Manager |
| Develop services for young people | To scope, identify opportunities and to develop a plan to improve education and awareness of housing options for young people Implementation of plan dependant on resources available – but to commence in Jan 2013 and further detail to be included in revised Action Plan Develop a plan to provide awareness and assistance in securing shared accommodation/ Lodger schemes Review options for step down accommodation for young persons needing to move on (gaps around 19-21 year olds) | Subject to inclusion in JHT workplan Jan 2013 start Q1 2014/15 review Dec 2013 Jan 2013 start Q1 2014/15 review By April 2014 | Within existing resources Jan 2013 start Q1 2014/15 review Jan 2013 start Q1 2014/15 review Within existing resources | Housing Needs Manager – but to be developed and delivered through Joint Housing Team with Oxfordshire County Council Rough Sleeping and Single Homelessness Manager with partners |
| Develop social enterprise opportunities in education, training and employment to meet the needs of single homeless people in the City | Work with partners including ASPIRE, Crisis Skylight Café and OFS to identify, develop and sustain employment opportunities for homeless and vulnerable people Develop schemes and identify lead agencies to seek funding and take forward with regard to mentoring | Nov 13 Feb 14 | Within existing resources | Housing Needs Manager |
| Deliver sufficient, appropriate temporary accommodation or accommodation suitable for homelessness prevention at crisis point | Review and /or implement new crisis accommodation solutions including with private sector (Dependant on above action) Review existing services and providers, review need for changes to service provision | April 13 Sept 13 | To be determined | Housing Needs Manager |

PREVENTING AND RESPONDING TO ROUGH SLEEPING

| GOALS | KEY ACTIONS/MILESTONES | TIMESCALE | RESOURCES | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Deliver and review impact of Ns Second Night Out | Reduction in number of new rough sleepers spending 2nd night on the streets. Review NSNO after six months of operation to ensure operational procedures are smooth and clear to all agencies. Review any procedures necessary and communicate to partners Rough sleepers with no local connection are reconnected to services in their local area. | Ongoing – measure by PI By June 2012 Ongoing | Within existing resources Within existing resources Within existing resources Within existing external contract | Rough Sleeping and Single Homelessness Manager – and through external service provider |
| Develop services to tackle the issue of entrenched rough sleepers | Implement plans to tackle entrenched rough sleeping to cover:- Assertive outreach Tasking and targeting Personalised approaches Meaningful activity Alternative accommodation options | As detailed in plan | Within existing resources | Rough Sleeping and Single Homelessness Manager and with partners |
| Improve pathways through supported, specialist accommodation for former rough sleeper | MOPPs redeveloped to provide data on gaps in move-on options. Move-on options from hostels constantly reviewed to find on-going solutions | Ongoing | Within existing resources | Rough Sleeping and Homelessness Manager with partners |
| Ensure sufficient specialist accommodation and support to meet needs of single homeless clients in Oxford City | Full review of rough sleeping/ homeless pathway, including specialist accommodation, with Oxfordshire County Council – including City Council needs to be clearly represented in Supporting People Review Establish full data set on hostels baselines, and data to provide info on gaps in services. Identify and develop all options (and impacts) of any re-modelling of services Implement outcome of review | Review complete Sept 2013 Implementation for April 2014 start Freparation work from Jan 14 or as identified by review | Review within existing resources which will identify resource issues for the future | Rough Sleeping and Single Homelessness Manager |
| Review anti-begging campaigns and messages support organisations who work to get people off the streets | Evaluate scope, impact and outcomes of anti-begging campaign in 2012 including review of local research Learn from experience in developing any 2013 campaign | By April 2013 | Within existing resources | Rough sleeping and single homelessness manager |

# DEVELOPING PARTNERSHIPS AND COMMUNICATIONS

| GOALS | KEY ACTIONS/MILESTONES | TIMESCALE | RESOURCES | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Improved data sharing across services including mental health | Review data sharing protocols) Develop the CHAIN system and joint database | by Sept 12 Ongoing | Within existing resources | Rough Sleeping and Single Homelessness Manager with partners |
| Ensure that Homelessness is recognised as a priority for action within the Health and Well Being Board | Contribute to meetings, events and regular reports to Health and Well Being Board Identify opportunities for joint commissioning including with Health, DAAT, probation Work in partnership to develop supported accommodation projects for single adults with very high and complex needs (including people with undiagnosed mental health problems and personality disorders | Ongoing By Dec 13 | Within existing resources Within existing resources | Housing Needs Manager/Strategy and Enabling Manager Housing Needs Manager |
| Support partnerships which develop effective pathways to enable people to turn their lives around and attain settled homes including adequate housing support when needed | Ensure engagement and involvement in County wide housing and support programmes including Young People Homelessness Supported to Independent Living (SIL) Victims of Domestic Violence Floating support | Ongoing | Within existing resources | Housing Needs Managers |
| Develop and deliver Communications Plan with more targeted information about homelessness and housing options | Annual review of housing communications plan to identify gaps and actions arising from trends and changes and wider public awareness of homelessness, supply and demand for social housing, awareness campaigns including in schools and education, reviewing new ways of engagement) Produce new information as detailed in Annual Plan Produce new/updated information Review new methods of communication e.g. social media Undertake campaigns | Annual review be Dec each year Updating information and campaigns within following financial year as detailed in plan | Within existing resources | Strategy & Enabling Manager : Service Managers Strategy & Enabling Manager as identified in plan |
| Increase awareness of realistic housing options for those people working with potentially homeless clients | Disseminate regular information Continue joint training and awareness across agencies Deliver messages to partnership groups and through Induction schemes | As above Via regular partnership meetings and special events | Existing resources | Housing Needs Managers |
| Develop more listening and learning from homelessness people and service users | Review mechanisms to introduce meaningful and cost effective satisfaction and customer experience feedback – including independent facilitation | Nov 2013 | Within existing resources | Housing Needs Manager |
| Develop information and evidence bases for homelessness | Review and maximise efficiency of recording systems to consider secondary causes and effective equalities monitoring Monitor and review information and trends to inform future policy and service development Annual review of Evidence Base and publicise on website | By June 13 By Oct 13 | Within existing resources Within existing resources | Options Manager Strategy and Enabling Manager |

| Review of existing and introduce new pre-crisis protocols | Enter into preventative pre-possession agreements with RPs and OCC Landlord Services – including for Flexible Tenancies and supported housing Develop sustainment and prevention roles with Private Landlords especially Home Choice Landlords Work with prison homelessness officers to build on existing pre-release services to ensure ex-offenders are able to make homelessness applications and access advice services prior to release Review and improve effectiveness of hospital discharge protocols | Dec 13 Dec 13 Apr 13 Aug 13 | Within existing resources | Options Manager Options Manager/Private Rented Manager Options Manager Options Manager |
| --- | --- | --- | --- | --- |

# DELIVER EXCELLENT HOMELESSSNESS SERVICES

| GOAL | KEY ACTIONS/MILESTONES | TIMESCALE | RESOURCES | RESPONSIBILITy |
| --- | --- | --- | --- | --- |
| Review best practice and seek continual improvement | Evaluate local services against Government ‘Developing Homelessness Strategies: Local Authority Toolkit’ issued in December 2012 Ensure homelessness services strive to meet the national Gold Standard (10 local challenges) Investigate potential to bid for external expertise in developing partnerships in homelessness by May 2013 If successful support reviews and implement any changes | By Dec 13 Review by Oct 13 | Within existing resources Subject to successful bid | Housing Needs Manager Options Manager |
| Review performance and cost effectiveness of homelessness services | Participate in national benchmarking schemes Provide data Review results Bring forward recommendations to improve via service planning and review of Homelessness Strategy targets | Sept 13 Jan 14 April 14 | Within existing resources | Housing Needs Manager/ Finance Manager/ Strategy and Enabling Manager |

We have also set challenging goals and targets to support our Homelessness Strategy aims and to ensure we provide excellent homelessness services

| GOAL | TARGET | Measurement | Priority link |
| --- | --- | --- | --- |
| Prevent households from becoming homeless | Baseline = 637 in 2011/12 Target = 540 | Quarterly | Preventing homelessness |
| Provide tenancy deposits | Baseline = Home Choice – 131 LMDGS Target = Home Choice – 130 | Quarterly | Preventing homelessness |
| Maintain reduced levels of homeless acceptances | Baseline = 120 Target = 120 | Quarterly | Preventing homelessness |
| Number of households in temporary accommodation )snapshot) | Baseline = 129 2011/12 Target = 120 | Monthly | Responding to homelessness |
| Number of households in bed and breakfast accommodation ( snapshot) | Baseline = 0 – 2011/12 Target = 0 | Monthly | Responding to homelessness |
| Number of 16.17 years old in bed and breakfast accommodation ( snapshot) | Baseline = 0 (2011/12) Target = 0 | Monthly | Responding to homelessness |

wider ACTIONs to support the Homelessness Strategy

| Supporting Goal | Supporting Strategy, Policy | Lead |
| --- | --- | --- |
| Use planning powers and the housing enabling role to bring forward new social housing and ensure that Universities make provision for student accommodation | Housing Strategy Relevant Planning SPD | OCC – S&E and Planning |
| Develop schemes to tackle under-occupation in social sector to free up family homes | Housing Strategy | OCC – HNT and landlord services |
| Tackle Tenancy Fraud to recover social housing for those in need of it | Housing Strategy Fraud Policy | OCC – Fraud Team |
| Develop Empty Property Strategy to bring homes into use | Housing Strategy Empty Homes Strategy | OCC – S&Eto be reviewed in 2013 |
| Ensure Allocations Scheme compliments the Homelessness Strategy by assisting with the prevention of homelessness and the use of temporary accommodation for homeless households | Allocations Scheme | OCC – tHNT o be reviewed in 2013 |
| Ensure balance between all housing applicants, homeless households and those moving on from supported housing | Annual Lettings Plan | OCC – Housing Needs Team |
| Greater supply of family housing through de-designation of accommodation for households over 55 years old | Council Housing Policy/Business Plan? | OCC – landlord services |
| Review needs of vulnerable groups such as younger people, older people, BME communities and troubled families/families in difficulty | Revised Housing Strategy 2013 | OCC – S&E - 2013 |

Where actions are necessary across Oxford City Council and wider partnerships  – bold identifies Lead Officer