## Appendix B
Capital Budget and Spend as at 30th June 2013
| Capital Scheme | 2013/14 Budget Approved by Council (Original Estimate) | Slippage Identified Quarter 4 2012/13 | 2013/14 Budget with Carry Forwards | Latest Budget | Spend to 30th June 2013 | Profiled Budget | Variance to Profiled Budget | % Spend Against Latest Budget | Projected Outturn at 30th June 2013 | Outturn Variance to Latest Budget | Outturn Variance due to Slippage | Outrun variance due to Over/ Under spend | Comments | Budget 2014/15 | Budget 2015/16 | Budget 2016/17
|  | £ |  | £ | £ | £ | [8 empty] | £ | £ | £
B0075 | B0075 Stage 2 Museum of Oxford Development | 550000 |  | 550000 | 550000 | 0 | 0 | 0 | 0% | 550000 | 0
G6013 | G6013 Urban Broadband | 325000 |  | 325000 | 325000 | 0 | 0 | 0 | 0% | 325000 | 0
| Policy Culture & Communications | 875000 | 0 | 875000 | 875000 | 0 | 0 | 0 | 0% | 875000 | 0 | 0 | 0 |  | 0 | 0 | 0
F1323 | F1323 Bridge Over Fiddlers Stream | 259703 | -21686.69 | 238016.31 | 238016 | 10190 | 10000 | 190 | 4.281% | 238016.31 | 0.31
F6013 | F6013 Bullingdon Community Centre -Enhancement of Community Facilities |  | 1536.99 | 1536.99 | 1537 | 0 | 0 | 0 | 0% | 1536.99 | -0.01
F7008 | F7008 Landscaping Work at Lamarsh Road |  | 14460.45 | 14460.45 | 14460 | 0 | 0 | 0 | 0% | 14460.45 | 0.45
F0015 | F0015 Cycle Oxford | 190000 | 4503.48 | 194503.48 | 194503 | 7182 | 8000 | -818 | 3.692% | 194503.48 | 0.48 |  |  | Commitments of £12K for signage and £50K contribution to County Council. Further commitments are dependant on whether Project Management switches to Environmental Development Staff | 50000 | 50000
F7006 | F7006 Work of Art - Littlemore | 1560 |  | 1560 | 1560 | 0 | 0 | 0 | 0% | 1560 | 0
F7007 | F7007 Woodfarm / Headington Community Centre - Improveme | 19887 |  | 19887 | 19887 | 0 | 0 | 0 | 0% | 19887 | 0
F7009 | F7009 CCTV Gipsy Lane Campus | 60000 |  | 60000 | 60000 | 0 | 0 | 0 | 0% | 60000 | 0
F7010 | F7010 Work of Art Said Business School | 50000 |  | 50000 | 50000 | 0 | 0 | 0 | 0% | 50000 | 0
F7011 | F7011 Headington Environmental Improvements | 60000 |  | 60000 | 60000 | 0 | 0 | 0 | 0% | 60000 | 0
F7012 | F7012 Rose Hill Recreation Ground Improvements | 3300 |  | 3300 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
F7020 | F7020 Work of Art Shotover View | 14635 |  | 14635 | 14635 | 0 | 0 | 0 | 0% | 14635 | 0
| NEW Sunnymeade Park - Enhancement of Play Area Facilities | [8 empty] | 0 | 0 |  |  |  | 1830
M5014 | M5014 West End Partnership | 217225 |  | 217225 | 217225 | 0 | 0 | 0 | 0% | 217225 | 0
| City Development | 876310 | -1185.77 | 875124.23 | 871823 | 17372 | 18000 | -628 | 1.985% | 871824.23 | 1.23 | 0 | 0 |  | 51830 | 50000 | 0
E3511 | E3511 Renovation Grants | 50000 | -2980 | 47020 | 47020 | -11897.02 | 10435 | -22332.02 | -25.3% | 47020 | 0 |  |  | Refunds for previous years issued grants have been received and offset any spend to date - plan is to spend to budget | 50000 | 50000 | 50000
E3521 | E3521 Disabled Facilities Grants | 840000 | -23410 | 816590 | 816590 | 78600.94 | 225308 | -146707.06 | 9.626% | 816590 | 0 |  |  | Q1 projection was to have spent most of the 12/13 slippage (£200k), however so far although commitments have been made, payments to contractors has been slower than expected. Head of Service is investigating why spend not occurred when planned. | 640000 | 640000 | 640000
E3553 | E3553 Carbon Reduction | 300000 |  | 300000 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | Work to be carried out not Capital
G6014 | G6014 CCTV Project | 25000 |  | 25000 | 25000 | 0 | 0 | 0 | 0% | 25000 | 0
G6015 | G6015 CCTV Rosehill Parade | 18000 |  | 18000 | 18000 | 0 | 0 | 0 | 0% | 18000 | 0
| Environmental Development (Including Community Safety) | 1233000 | -26390 | 1206610 | 906610 | 66703.92 | 235743 | -169039.08 | 5.528% | 906610 | 0 | 0 | 0 |  | 690000 | 690000 | 690000
G1013 | G1013 Dawson Street Gardens | 19000 |  | 19000 | 19000 | 0 | 0 | 0 | 0% | 19000 | 0
G3013 | G3013 Diamond Place car park footpath extension | 6324 |  | 6324 | 6324 | 0 | 0 | 0 | 0% | 6324 | 0
G3014 | G3014 East Oxford Community Association Improvements | 2550 |  | 2550 | 2550 | 0 | 0 | 0 | 0% | 2550 | 0
G4006 | G4006 Florence Park Community Centre Kitchen | 1411 |  | 1411 | 1411 | 0 | 0 | 0 | 0% | 1411 | 0
G3015 | G3015 NE Marston Croft Road Recreation Ground |  | 19300 | 19300 | 19300 | 0 | 0 | 0 | 0% | 19300 | 0
| NEW South Oxford Community Centre Café | [13 empty] | 50000
| NEW St Ebbes Deaf and Hard of Hearing Centre | [13 empty] | 50000
M5015 | M5015 Old Fire Station |  |  |  |  | 0 | 0 | 0 | 0% |  | 0
| Communities and Housing (Now Leisure, Parks & Communities) | 29285 | 19300 | 48585 | 48585 | 0 | 0 | 0 | 0% | 48585 | 0 | 0 | 0 |  | 100000 | 0 | 0
Leisure Centres
A4808 | A4808 Blackbird Leys LC Improvements | 128278 |  | 128278 | 128278 | 0 | 0 | 0 | 0% | 0 | -128278 | -128278 |  | Outdoor works at Blackbird Leys Leisure Centre to take place following completion of new Pool in Q4 2014/15.
A4814 | A4814 Leisure Centre substantive repairs | 310000 | 60900 | 370900 | 370900 | 0 | 0 | 0 | 0% | 370900 | 0 |  |  |  | 66000
Offices for the Future
Q2000 | Q2000 Offices for the Future |  |  |  | 90000 | 250.11 | 0 | 250.11 | 0% | 90000 | 0 |  | 0
Community Centres
B0033 | B0033 Community Centres | 275570 | 91600 | 367170 | 367170 | 9429.22 | 0 | 9429.22 | 2.568% | 367170 | 0 |  |  |  | 313420 | 288200 | 413320
B0034 | B0034 Rose Hill Community Centre | 588000 | -11700 | 576300 | 576300 | 20470.25 | 21000 | -529.75 | 3.552% | 576300 | 0 |  |  | £230K committed to Project Management and Architects Fees | 3200000
Covered Market
B0010 | B0010 Covered Market signage improvements | 26941 | -7501 | 19440 | 19440 | 32105.6 | 19440 | 12665.6 | 165.2% | 33000 | 13560 |  | 13560 | Overspend to be funded from another Covered Market Budget
B0027 | B0027 Covered Market - Improvements & Upgrade to Roof |  | 56900 | 56900 | 56900 | 0 | 0 | 0 | 0% | 56900 | 0
B0028 | B0028 Covered Market - New Roof Structures to High St Entrances | 90000 | 23200 | 113200 | 113200 | 47.29 | 0 | 47.29 | 0.04178% | 113200 | 0
B0036 | B0036 Investment ~ Covered Market | 200000 | 2099.93 | 202099.93 | 202100 | 56545.65 | 57000 | -454.35 | 27.98% | 188539.93 | -13560.07 |  | -13560.07 |  | 150000 | 75000
B0063 | B0063 Covered Market Replacement Sprinkler System | 100000 | 25200 | 125200 | 125200 | 0 | 0 | 0 | 0% | 125200 | 0
B0064 | B0064 Covered Market - Improvements to Emergency Lighting |  |  |  |  | 0
Investment Properties
B0003 | B0003 Roof Repairs & Ext Refurbishment 44-46 George St |  | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0% | 27000 | 0
B0040 | B0040 Investment ~ Broad Street | 103400 | 113880 | 217280 | 217280 | 3460.45 | 5000 | -1539.55 | 1.593% | 217280 | 0 |  |  |  |  | 33800 | 17400
B0041 | B0041 Investment - Misc City Centre Properties | 70000 | -2519.51 | 67480.49 | 67480 | 2963.69 | 3000 | -36.31 | 4.392% | 67480.49 | 0.49 |  |  |  | 10000 | 24000
B0044 | B0044 Investment - Outer City | 47200 |  | 47200 | 47200 | 0 | 0 | 0 | 0% | 47200 | 0 |  |  |  | 38600 | 80700 | 257100
B0045 | B0045 Investment ~ St. Michael’s Street | 43000 | -3750 | 39250 | 39250 | 1615.63 | 2000 | -384.37 | 4.116% | 39250 | 0
B0046 | B0046 Investment - Ship Street | 76220 | -500 | 75720 | 75720 | 3747.79 | 4000 | -252.21 | 4.95% | 75720 | 0
B0043 | B0043 Investment George Street | 203000 |  | 203000 | 203000 | 51200.9 | 50000 | 1200.9 | 25.22% | 203000 | 0 |  |  |  |  | 77800
B0072 | B0072 23-25 Broad Street | 350000 |  | 350000 | 350000 | 0 | 0 | 0 | 0% | 350000 | 0
Miscellaneous Council Properties
B0037 | B0037 Car Parks | 230000 | 66100 | 296100 | 296100 | 1447.19 | 1500 | -52.81 | 0.4888% | 296100 | 0 |  |  | Uncertainty over planned works at Barns Road Car Park to be completed in year | 80000 | 60000 | 50000
B0052 | B0052 Miscellaneous Properties | 90000 |  | 90000 | 90000 | 48754.84 | 48000 | 754.84 | 54.17% | 90000 | 0 | [5 empty] | 14360
B0060 | B0060 Depot Relocation | 1880000 |  | 1880000 | 0 | 0 | 0 | 0 | 0% | 0 | 0
B0073 | B0073 Clearing Channels under Frideswide Bridge | 5000 |  | 5000 | 5000 | 0 | 0 | 0 | 0% | 5000 | 0
B0078 | B0078 Allotments | 3000 |  | 3000 | 3000 | 0 | 0 | 0 | 0% | 3000 | 0 |  |  |  | 13700 | 34450 | 10200
B0079 | B0079 Street Sports Sites | 8110 |  | 8110 | 8110 | 0 | 0 | 0 | 0% | 8110 | 0 |  |  |  |  | 10720
B0077 | B0077 Direct Services Depots | 150000 |  | 150000 | 150000 | 0 | 0 | 0 | 0% | 150000 | 0 |  |  |  |  | 210600 | 25500
B0080 | B0080 Templars Square Refurbishment/Relocation | 150000 |  | 150000 | 150000 | 0 | 0 | 0 | 0% | 150000 | 0
| NEW Bury Knowle House | [14 empty] | 87900
Parks & Cemeteries
B0048 | B0048 Leisure - Cemeteries | 58500 | -3300 | 55200 | 55200 | 3738.04 | 4000 | -261.96 | 6.772% | 55200 | 0 |  |  |  |  | 28070 | 12120
B0050 | B0050 Leisure ~ Depots | 40000 | 3800 | 43800 | 43800 | 0 | 0 | 0 | 0% | 43800 | 0 |  |  |  |  | 18760
B0051 | B0051 Leisure - Pavilions | 470000 | -9700 | 460300 | 460300 | 124376.48 | 125000 | -623.52 | 27.02% | 460300 | 0 |  |  |  | 805000 | 75000
B0065 | B0065 Parks & Cemetery - Masonry Walls & Path Improvements | 40000 | 14600 | 54600 | 54600 | 0 | 0 | 0 | 0% | 54600 | 0 |  |  |  | 40000
B0067 | B0067 Fencing Repairs across the City | 225000 | -53000 | 172000 | 172000 | 76854.7 | 72000 | 4854.7 | 44.68% | 172000 | 0 |  |  |  | 150000
B0071 | B0071 Parks properties (H&S works) |  | 47000 | 47000 | 47000 | 50719 | 47000 | 3719 | 107.9% | 50719 | 3719 |  | 3719
| NEW Parks & Leisure Toilets | [13 empty] | 9200
Town Hall
B0054 | B0054 Town Hall | 417702 | 7778 | 425480 | 335480 | 29503.92 | 30000 | -496.08 | 6.934% | 335480 | 0 |  |  |  | 280000 | 55000 | 50000
B0068 | B0068 Town Hall - Conference System Refurbishment | 300000 | 33000 | 333000 | 333000 | 304.69 | 0 | 304.69 | 0.0915% | 333000 | 0
B0076 | B0076 Town Hall Improvements (OFTF2) | 200000 |  | 200000 | 200000 | 3275.13 | 4000 | -724.87 | 1.638% | 200000 | 0 |  |  | Proposed works likely to exceed budget .Figures to be provided by Simon Howick. Town Hall budget to cover shortfall | 50000
B0069 | B0069 Corporate Property Major Works Programme | 200000 |  | 200000 | 0 | 0 | 0 | 0 | 0% | 0 | 0
B0074 | B0074 R & D Feasibility Fund | 125000 |  | 125000 | 125000 | 16625.3 | 17000 | -374.7 | 13.3% | 125000 | 0 |  |  |  | 125000
Corpo | Corporate Assets (Now Housing & Property) | 7203921 | 481087.42 | 7685008.42 | 5605008 | 537435.87 | 509940 | 27495.87 | 6.993% | 5480449.42 | -124558.58 | -128278 | 3718.93 |  | 5330920 | 1160000 | 850000
C3041 | C3041 New server for telephone system |  | 11288 | 11288 | 11288 | 0 | 0 | 0 | 0% | 11288 | 0
C3042 | C3042 Customer First Programme |  | 115670 | 115670 | 115670 | 0 | 0 | 0 | 0% | 115670 | 0
0
Custo | Customer Services | 0 | 126958 | 126958 | 126958 | 0 | 0 | 0 | 0% | 126958 | 0 |  |  |  | 0 | 0 | 0
A1300 | A1300 Playground Refurbishment |  |  |  | 18146 | 2291.24 | 4536.5 | -2245.26 | 0% | 18146 | 0
A1301 | A1301 Play Barton | 92587 |  | 92587 | 74441 | 0 | 0 | 0 | 0% | 74441 | 0
0
A4810 | A4810 New Build Completion Pool | 7560254 | 646 | 7560900 | 4060900 | 2085 | 2090 | -5 | 0.02758% | 4060900 | 0 |  |  | Slippage due to Judicial review. Work expected to commence July/August. £250K is not an overspend but a virement requested form the Depot Relocation budget
A4815 | A4815 Leisure Centre Improvement Work | 400000 | 47250 | 447250 | 447250 | 0 | 0 | 0 | 0% | 447250 | 0
A4830 | A4830 Develop new burial space | 1000000 |  | 1000000 | 100000 | 0 | 0 | 0 | 0% | 100000 | 0 |  |  | Forecast slippage £900k. Budget needs to be re-profiled across future years to match anticipated expenditure of £100k 13-14, £600k 14-15, and £300k 15-16
A4818 | A4818 Lye Valley & Chiswell Valley Walkways | 62000 | 62000 | 124000 | 124000 | 0 | 0 | 0 | 0% | 124000 | 0
A4816 | A4816 Sports Pavilions | 820000 | 65800 | 885800 | 885800 | 59003.13 | 60000 | -996.87 | 6.661% | 885800 | 0 |  |  | Phase 1 pavilion works are currently being undertaken by Direct Services. Major Project Approval for Grandpont Pavilion and remaining programme being sought at July CEB. | 200000
A4820 | A4820 Upgrade Existing Tennis Courts | 60000 | 9180 | 69180 | 69180 | 0 | 0 | 0 | 0% | 69180 | 0 |  |  |  | 54000 | 60000
A4821 | A4821 Upgrade Existing Multi-Use Games Area | 48000 | 15170 | 63170 | 63170 | -0.2 | 0 | -0.2 | -0.0003166% | 63170 | 0 |  |  |  | 48000 | 48000
A3129 | A3129 Donnington Recreation Ground Improvements | 44375 |  | 44375 | 44375 | 0 | 0 | 0 | 0% | 44375 | 0
A4826 | A4826 Parks Works | 100000 |  | 100000 | 100000 | 0 | 0 | 0 | 0% | 100000 | 0 |  |  |  | 100000 | 50000 | 50000
A4827 | A4827 Cowley Outdoor Gym | 70000 |  | 70000 | 70000 | 0 | 0 | 0 | 0% | 70000 | 0
A4828 | A4828 Valentia Road Playground | 10000 |  | 10000 | 10000 | 0 | 0 | 0 | 0% | 10000 | 0
A4829 | A4829 Oxford Spires Academy | 200000 |  | 200000 | 200000 | 0 | 0 | 0 | 0% | 200000 | 0
| NEW Pavilions Grey Water Harvesting | [14 empty] | 28000
| NEW Horpath Athletics Ground | [14 empty] | 50000 | 450000
| NEW Three Artificial Turf Cricket Wickets | [12 empty] | Request to bring forward full project budget of £36k to 2013/14 to enable greater purchasing power. If wickets are purchased together possible to deliver 4 wickets rather than 3. | 12000 | 12000 | 12000
City | Leisure,Parks & Communities | 10467216 | 187046 | 10667262 | 6267262 | 63379.17 | 66626.5 | -3247.33 | 0.5941% | 6267262 | 0 | 0 | 0 |  | 414000 | 248000 | 512000
F0011 | F0011 Pay & Display Parking in the Car Parks |  | 84000 | 84000 | 84000 | 0 | 8400 | -8400 | 0% | 84000 | 0
F0012 | F0012 P & R Purchase of Capital Items - Peartree, Redbridge | 135000 | 29309 | 164309 | 164309 | 0 | 0 | 0 | 0% | 164309 | 0
F0014 | F0014 Purchase of ANPR for use in car park enforcement |  | 1857 | 1857 | 1857 | 0 | 0 | 0 | 0% | 1857 | 0
0
R0005 | R0005 MT Vehicles/Plant Replacement Programme. | 2562700 | 178879 | 2741579 | 2741579 | 587697.73 | 683200.84 | -95503.11 | 21.44% | 2741579 | 0 |  |  |  | 2200250 | 1799000 | 453000
0
T2269 | T2269 Toilet improvements | 180000 | -3055 | 176945 | 176945 | 51576.3 | 49155.32 | 2420.98 | 29.15% | 176945 | 0 |  |  |  | 80000
T2270 | T2270 Bin stores for council flats to assist recycling |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0
T2273 | T2273 Car Parks Resurfacing | 80000 | 0 | 80000 | 80000 | 0 | 0 | 0 | 0% | 80000 | 0 |  |  |  | 350000 | 350000 | 350000
T2274 | T2274 Gloucester Green Car Park Waterproofing | 100000 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0% | 100000 | 0
0
Direct | Direct Services | 3057700 | 290990 | 3348690 | 3348690 | 639274.03 | 740756.16 | -101482.13 | 19.09% | 3348690 | 0 | 0 | 0 |  | 2630250 | 2149000 | 803000
C3039 | C3039 ICT Infrastructure | 200000 | 0 | 200000 | 200000 | 43153.51 | 50000 | -6846.49 | 21.58% | 200000 | 0 |  |  | To fund any further Windows 7 project costs and other IT projects (e.g. Intranet upgrade) | 100000 | 150000 | 150000
C3044 | C3044 Software Licences | 188574 | 0 | 188574 | 188574 | 176052.5 | 0 | 176052.5 | 93.36% | 188574 | 0 |  |  | Payments to Bytes software have already been made. Total spend matches base budget without 12/13 slippage (£177k), no further spend expected | 177000 | 177000 | 177000
C3045 | C3045 Mobile Working | 98000 | 0 | 98000 | 98000 | 0 | 0 | 0 | 0% | 98000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
C3046 | C3046 System Integration Capability | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0% | 25000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
C3047 | C3047 Oracle 11g Upgrade | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0% | 25000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
C3048 | C3048 Server 2008 Upgrade for Idox | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0% | 25000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
C3049 | C3049 Source Code Management | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0% | 15000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
C3050 | C3050 Tree Managment Software | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0% | 15000 | 0 |  |  | Awaiting spend profiles from Cost centre manager
ICT s | Business Improvement & Technology | 591574 | 0 | 591574 | 591574 | 219206.01 | 50000 | 169206.01 | 37.05% | 591574 | 0 | 0 | 0 |  | 277000 | 327000 | 327000
GF To | GF Total | 24334006 | 1077805.65 | 25424811.65 | 18641510 | 1543371 | 1621065.66 | -77694.66 | 6.07% | 18516952.65 | -124557.35 | -128278 | 3718.93 |  | 9494000 | 4624000 | 3182000
Exter | External Contracts
N6384 | N6384 Foresters Towers | 500000 |  | 500000 | 500000 | 2936.22 | 0 | 2936.22 | 0.5872% | 500000 | 0 |  |  |  | 1500000 | 1500000 | 1500000
N6387 | N6387 Controlled Entry | 210000 |  | 210000 | 210000 | 35572.39 | 35000 | 572.39 | 16.94% | 210000 | 0 |  |  |  | 210000 | 210000 | 210000
N6393 | N6393 External Doors | 200000 |  | 200000 | 200000 | 6632.66 | 0 | 6632.66 | 3.316% | 200000 | 0 |  |  |  | 200000 | 200000 | 200000
N7020 | N7020 External Adaptations | 250000 |  | 250000 | 250000 | 35898.59 | 35000 | 898.59 | 14.36% | 250000 | 0 |  |  |  | 250000 | 250000 | 250000
N7021
N7018 | N7018 Minox | 19000 |  | 19000 | 19000 | 15.73 | 500 | -484.27 | 0.08279% | 19000 | 0 |  |  |  | 19000 | 19000 | 19000
N6394 | N6394 Windows | 250000 |  | 250000 | 250000 | 3719.08 | 0 | 3719.08 | 1.488% | 250000 | 0 |  |  |  | 250000 | 250000 | 250000
N6389 | N6389 Damp-proof works (K&B) | 90000 |  | 90000 | 90000 | 56128.01 | 55000 | 1128.01 | 62.36% | 90000 | 0 |  |  |  | 90000 | 90000 | 90000
N6392 | N6392 Roofing | 150000 |  | 150000 | 150000 | 50693.46 | 50000 | 693.46 | 33.8% | 150000 | 0 |  |  |  | 150000 | 150000 | 150000
N6386 | N6386 Structural | 125000 |  | 125000 | 125000 | 54205.94 | 55000 | -794.06 | 43.36% | 125000 | 0 |  |  |  | 125000 | 125000 | 125000
N6427 | N6427 Shops
N7028 | N7028 Non Dwelling HRA Assets | 117000 |  | 117000 | 117000 | 0 | 0 | 0 | 0% | 117000 | 0 |  |  |  | 117000 | 117000 | 117000
N7026 | N7026 Communal Areas | 150000 |  | 150000 | 150000 | 0 | 0 | 0 | 0% | 150000 | 0 |  |  |  | 150000 | 150000 | 150000
N7027 | N7027 Environmental Improvements | 100000 |  | 100000 | 100000 | 0 | 0 | 0 | 0% | 100000 | 0 |  |  |  | 100000 | 100000 | 100000
New B | New Build
N7029 | N7029 HCA New Build | 7744000 |  | 7744000 | 7744000 | 55307.87 | 40000 | 15307.87 | 0.7142% | 7744000 | 0 |  |  |  | 9366000 | 348000 | 12000
N7031 | N7031 Homes at Barton | 650000 |  | 650000 | 650000 | 0 | 0 | 0 | 0% | 650000 | 0 |  |  |  | 2500000 | 3380000 | 13500000
N7032 | N7032 Estate Enhancements and Regeneration | 500000 |  | 500000 | 500000 | 19125 | 20000 | -875 | 3.825% | 500000 | 0 |  |  |  | 500000 | 500000 | 500000
N7030 | N7030 Horspath Road Depot | 2200000 |  | 2200000 | 2200000 | 0 | 0 | 0 | 0% | 2200000 | 0
| NEW Contribution to Rose Hill | [14 empty] | 1500000
Inter | Internal Contracts
N6385 | N6385 Adaptations for disabled | 900000 |  | 900000 | 900000 | 149376.29 | 226080 | -76703.71 | 16.6% | 900000 | 0 |  |  |  | 900000 | 900000 | 900000
N6390 | N6390 Kitchens & Bathrooms | 2073000 |  | 2073000 | 2073000 | 556865.71 | 503117.1 | 53748.61 | 26.86% | 2073000 | 0 |  |  |  | 2073000 | 1892000 | 1743000
N6391 | N6391 Heating | 1221000 |  | 1221000 | 1221000 | 314453.54 | 282051 | 32402.54 | 25.75% | 1221000 | 0 |  |  |  | 1221000 | 1187000 | 1221000
N6388 | N6388 Major Voids | 820000 |  | 820000 | 820000 | 160999.07 | 205984 | -44984.93 | 19.63% | 820000 | 0 |  |  |  | 800000 | 776000 | 716000
N6395 | N6395 Electrics | 785000 |  | 785000 | 785000 | 75593.75 | 197192 | -121598.25 | 9.63% | 785000 | 0 |  |  |  | 726000 | 666000 | 607000
| Housing Revenue Account | 19054000 | 0 | 19054000 | 19054000 | 1577523.31 | 1704924.1 | -127400.79 | 8.279% | 19054000 | 0 | 0 | 0 |  | 21247000 | 14310000 | 22360000
| Grand Total | 43388006 | 1077805.65 | 44478811.65 | 37695510 | 3120894.31 | 3325989.76 | -205095.45 | 7.017% | 37570952.65 | -124557.35 | -128278 | 3718.93 |  | 30741000 | 18934000 | 25542000
Financing - General Fund
| Arts Council & HLF | 250000 |  | 250000
| Capital Receipts | 15008935 | 702158 | 15711093 | [10 empty] | 4059571 | 559316 | 0
| Developer Contributions | 1065685 | 45458.23 | 1111143.23 | [10 empty] | 1058830
| Direct Revenue Funding | 2965799 |  | 2965799 | [10 empty] | 2160349 | 1085684 | 909413
| General Fund Capital Receipts - New Rosehill | 0 |  | 0 | [11 empty] | 790000
| General Fund Revenue Contributions additional | 1733000 |  | 1733000 | [12 empty] | 1279587
| Government Funding | 482587 | -26390 | 456197 | [10 empty] | 390000 | 390000 | 390000
| Government Grants | 0 |  | 0 | [12 empty] | 150000
| Heritage Lottery fund for Town Hall | 100000 |  | 100000 | [10 empty] | 25000
| Prudential Borrowing for Vehicles | 2385000 | 356578.5 | 2741578.5 | [10 empty] | 2200250 | 1799000 | 453000
| Revenue Reserves | 356000 |  | 356000 | [10 empty] | 0 | 0
| Total General Fund Financing | 24347006 | 1077804.73 | 25424810.73 | [10 empty] | 9894000 | 4624000 | 3182000
Financing - HRA
| MRR | 19054000 |  | 19054000 | [10 empty] | 19247000 | 14310000 | 22360000
| External Contributions | [13 empty] | 2000000
| Total HRA Financing | 19054000 | 0 | 19054000 | [10 empty] | 21247000 | 14310000 | 22360000
| Total Financing | 43401006 | 1077804.73 | 44478810.73 | [10 empty] | 31141000 | 18934000 | 25542000
|  | -13000 |  | -0.09 | [10 empty] | -400000 | 0 | 0
Outrun variance due to Over/ Under spend

## Capital Receipts (hidden)
CAPITAL RECEIPTS - GF RISK ADJUSTED
CAPITAL RECEIPTS - RISK ADJUSTED | 2013/14 £000's | 2014/15 £000's | 2015/16 £000's | 2016/17 £000's
| Anticipated | Anticipated | Anticipated | Anticipated
Balance B/F | 17431551 | 3157352.5 | 376451.5 | 595135.5
Used For Financing (Latest Estimate) | -15711093 | -4059571 | -559316 | 0
St Clements Car Park - E258 | 3634300
Northway Centre Site | 100000
23-25 Broad Street |  | 0
Brasenose Depot & Farmhouse | 0
West Hill Farm | 0
Temple Cowley Pool |  | 1500000
Botley Cemetery Lodge | 50000
Land at Oxford Science Park |  | 0
Diamond Place Car Park |  | 0
Rose Hill Community Centre |  |  | 790000
New Receipts | 3784300 | 1500000 | 790000 | 0
Balance C/F | 5504758 | 376451.5 | 595135.5 | 595135.5
Received

## Agresso (hidden)
Costc | Costc (T) | Agresso Budget | Approved | Latest Budget | Profiled Budget | Spend |  | CAPCE 13/14 | CAPCE 14/15
A1300 | Playground Refurbishment | 18146 | 0 | 18146 | 4536.5 | 2291.24 | A1300 | 0
A1301 | Play Barton | 74441 | 92587 | 74441 | 0 | 0 | A1301 | 0
A3129 | Donnington Recreation Ground Improvements | 44375 | 44375 | 44375 | 0 | 0 | A3129 | 0
A4808 | Blackbird Leys LC Improvements | 128278 | 128278 | 128278 | 0 | 0 | A4808 | 0
A4810 | New Build Competion Pool | 7560900 | 7560900 | 4060900 | 2090 | 2085 | A4810 | -3500000 | 3750000
A4814 | Leisure Centre Substantive Works | 370900 | 370900 | 370900 | 0 | 0 | A4814 | 0
A4815 | Leisure Centre Improvement Work | 447250 | 447250 | 447250 | 0 | 0 | A4815 | 0
A4816 | Sports Pavillions | 885800 | 885800 | 885800 | 60000 | 59003.13 | A4816 | 0
A4818 | Lye Valley & Chiswell Valley Walkways | 124000 | 124000 | 124000 | 0 | 0 | A4818 | 0
A4820 | Upgrade Tennis Courts | 69180 | 69180 | 69180 | 0 | 0 | A4820 | 0
A4821 | Upgrade multi-Use Games Area | 63170 | 63170 | 63170 | 0 | -0.2 | A4821 | 0
A4826 | Parks Works | 100000 | 100000 | 100000 | 0 | 0 | A4826 | 0
A4827 | Cowley Outdoor Gym | 70000 | 70000 | 70000 | 0 | 0 | A4827 | 0
A4828 | Valentia Road Playground | 10000 | 10000 | 10000 | 0 | 0 | A4828 | 0
A4829 | Oxford Spires Academy | 200000 | 200000 | 200000 | 0 | 0 | A4829 | 0
A4830 | Develop New Burial Space | 1000000 | 1000000 | 100000 | 0 | 0 | A4830 | -900000 | 900000
B0003 | Roof Repairs & Ext Refurb - 44-46 George St | 27000 | 27000 | 27000 | 0 | 0 | B0003 | 0
B0010 | Covered Market - signage improvements | 19440 | 19440 | 19440 | 19440 | 32105.6 | B0010 | 0
B0027 | Covered Market - Improvements & Upgrade to Roof | 56900 | 56900 | 56900 | 0 | 0 | B0027 | 0
B0028 | Covered Market - New Roof Structures to High St En | 113200 | 113200 | 113200 | 0 | 47.29 | B0028 | 0
B0033 | Community Centres | 367170 | 367170 | 367170 | 0 | 9429.22 | B0033 | 0
B0034 | Rose Hill Community Centre | 576300 | 576300 | 576300 | 21000 | 20470.25 | B0034 | 0
B0036 | Investment - Covered Market | 202100 | 202099.93 | 202100 | 57000 | 56545.65 | B0036 | 0
B0037 | Car Parks | 296100 | 296100 | 296100 | 1500 | 1447.19 | B0037 | 0
B0040 | Investment - Broad Street | 217280 | 217280 | 217280 | 5000 | 3460.45 | B0040 | 0
B0041 | Investment - Misc City Centre Properties | 67480 | 67480.49 | 67480 | 3000 | 2963.69 | B0041 | 0
B0043 | Investment - George Street | 203000 | 203000 | 203000 | 50000 | 51200.9 | B0043 | 0
B0044 | Investment - Outer City | 47200 | 47200 | 47200 | 0 | 0 | B0044 | 0
B0045 | Investment - St Michaels Street | 39250 | 39250 | 39250 | 2000 | 1615.63 | B0045 | 0
B0046 | Investment - Ship Street | 75720 | 75720 | 75720 | 4000 | 3747.79 | B0046 | 0
B0048 | Leisure - Cemeteries | 55200 | 55200 | 55200 | 4000 | 3738.04 | B0048 | 0
B0050 | Leisure - Depots | 43800 | 43800 | 43800 | 0 | 0 | B0050 | 0
B0051 | Leisure - Pavilions | 460300 | 460300 | 460300 | 125000 | 124376.48 | B0051 | 0
B0052 | Miscellaneous Properties | 90000 | 90000 | 90000 | 48000 | 48754.84 | B0052 | 0
B0054 | Town Hall | 425480 | 425480 | 335480 | 30000 | 29503.92 | B0054 | -90000
B0060 | Depot Relocation Studies | 1880000 | 1880000 | 0 | 0 | 0 | B0060 | -1880000 | 1630000
B0063 | Covered Market Sprinkler System | 125200 | 125200 | 125200 | 0 | 0 | B0063 | 0
B0064 | Covered Market Emergency Lighting | 0 | 0 | 0 | 0 |  | B0064 | 0
B0065 | Parks & Cemetery - Masonry Wall & Path Improvement | 54600 | 54600 | 54600 | 0 | 0 | B0065 | 0
B0067 | Fencing Repairs Across the City | 172000 | 172000 | 172000 | 72000 | 76854.7 | B0067 | 0
B0068 | Town Hall - Conference System Refurbishment | 333000 | 333000 | 333000 | 0 | 304.69 | B0068 | 0
B0071 | Parks Properties Health and Safety Works | 47000 | 47000 | 47000 | 47000 | 50719 | B0071 | 0
B0072 | 23-25 Broad Street | 350000 | 350000 | 350000 | 0 | 0 | B0072 | 0
B0073 | Clearing Channels under Frideswide Bridge | 5000 | 5000 | 5000 | 0 | 0 | B0073 | 0
B0074 | R & D Feasibility Fund | 125000 | 125000 | 125000 | 17000 | 16625.3 | B0074 | 0
B0075 | Stage 2 Museum of Oxford Development | 550000 | 550000 | 550000 | 0 | 0 | B0075 | 0
B0076 | Town Hall Improvements | 200000 | 200000 | 200000 | 4000 | 3275.13 | B0076 | 0
B0077 | Direct Services Depots | 150000 | 150000 | 150000 | 0 | 0 | B0077 | 0
B0078 | Allotments | 3000 | 3000 | 3000 | 0 | 0 | B0078 | 0
B0079 | Street Sports Sites | 8110 | 8110 | 8110 | 0 | 0 | B0079 | 0
B0080 | Templars Square Refurbishment/Relocation | 150000 | 150000 | 150000 | 0 | 0 | B0080 | 0
C3039 | ICT Infrastructure | 200000 | 200000 | 200000 | 50000 | 43153.51 | C3039 | 0
C3041 | New server for telephone system | 11288 | 11288 | 11288 | 0 | 0 | C3041 | 0
C3042 | Customer First Programme | 115670 | 115670 | 115670 | 0 | 0 | C3042 | 0
C3044 | Software Licences | 188574 | 188574 | 188574 | 0 | 176052.5 | C3044 | 0
C3045 | Mobile Working | 98000 | 98000 | 98000 | 0 | 0 | C3045 | 0
C3046 | System Integration Capability | 25000 | 25000 | 25000 | 0 | 0 | C3046 | 0
C3047 | Oracle 11g Upgrade | 25000 | 25000 | 25000 | 0 | 0 | C3047 | 0
C3048 | Server 2008 Upgrade for Idox | 25000 | 25000 | 25000 | 0 | 0 | C3048 | 0
C3049 | Source Code Management | 15000 | 15000 | 15000 | 0 | 0 | C3049 | 0
C3050 | Tree Managment Software | 15000 | 15000 | 15000 | 0 | 0 | C3050 | 0
E3511 | Renovation Grants | 47020 | 47020 | 47020 | 10435 | -11897.02 | E3511 | 0
E3521 | Disabled Facilities Grants | 816590 | 816590 | 816590 | 225308 | 78600.94 | E3521 | 0
E3553 | Carbon Reduction | 300000 | 300000 | 0 | 0 | 0 | E3553 | -300000 | 0
F0011 | Pay & Display Parking in the Car Parks | 84000 | 84000 | 84000 | 8400 | 0 | F0011 | 0
F0012 | P & R Puchase of Capital Items - Peartree, Redbrid | 164309 | 164309 | 164309 | 0 | 0 | F0012 | 0
F0014 | ANPR for Car Park Enforcement | 1857 | 1857 | 1857 | 0 | 0 | F0014 | 0
F0015 | Cycle Oxford | 194503 | 194503 | 194503 | 8000 | 7182 | F0015 | 0
F1323 | Bridge Over Fiddlers Stream | 238016 | 238016 | 238016 | 10000 | 10190 | F1323 | 0
F6013 | Bullingdon Community Centre - provision or enhance | 1537 | 1537 | 1537 | 0 | 0 | F6013 | 0
F7006 | Work of Art - Littlemore | 1560 | 1560 | 1560 | 0 | 0 | F7006 | 0
F7007 | Woodfarm / Headington Community Centre - Improveme | 19887 | 19887 | 19887 | 0 | 0 | F7007 | 0
F7008 | Lamarsh Road Landscaping | 14460 | 14460.45 | 14460 | 0 | 0 | F7008 | 0
F7009 | CCTV Gipsy Lane Campus | 60000 | 60000 | 60000 | 0 | 0 | F7009 | 0
F7010 | Work of Art Said Business School | 50000 | 50000 | 50000 | 0 | 0 | F7010 | 0
F7011 | Headington Environmental Improvements | 60000 | 60000 | 60000 | 0 | 0 | F7011 | 0
F7012 | Rose Hill Recreation Ground Improvements | 3300 | 3300 | 0 | 0 | 0 | F7012 | -3300 | 3300
F7020 | Work of Art Shotover View | 14635 | 14635 | 14635 | 0 | 0 | F7020 | 0
G1013 | Dawson Street Gardens | 19000 | 19000 | 19000 | 0 | 0 | G1013 | 0
G3013 | Diamond Place car park footpath extension | 6324 | 6324 | 6324 | 0 | 0 | G3013 | 0
G3014 | East Oxford Community Associaltion Improvements | 2550 | 2550 | 2550 | 0 | 0 | G3014 | 0
G3015 | NE Marston Croft Road Recreation Ground | 19300 | 19300 | 19300 | 0 | 0 | G3015 | 0
G4006 | Florence Park CC Kitchen | 1411 | 1411 | 1411 | 0 | 0 | G4006 | 0
G6013 | Urban Broadband | 325000 | 325000 | 325000 | 0 | 0 | G6013 | 0
G6014 | CCTV Project | 25000 | 25000 | 25000 | 0 | 0 | G6014 | 0
G6015 | CCTV Rosehill Parade | 18000 | 18000 | 18000 | 0 | 0 | G6015 | 0
M5014 | West End Partnership (Growth Points Grant) | 217225 | 217225 | 217225 | 0 | 0 | M5014 | 0
M5015 | Old Fire Station | 0 | 0 | 0 | 0 |  | M5015 | 0
N6384 | Foresters Towers | 500000 | 500000 | 500000 | 0 | 2936.22 | N6384 | 0
N6385 | Adaptations for disabled | 900000 | 900000 | 900000 | 226080 | 149376.29 | N6385 | 0
N6386 | Structural | 125000 | 125000 | 125000 | 0 | 54205.94 | N6386 | 0
N6387 | Controlled Entry | 210000 | 210000 | 210000 | 0 | 35572.39 | N6387 | 0
N6388 | Major Voids | 820000 | 820000 | 820000 | 205984 | 160999.07 | N6388 | 0
N6389 | Damp-proof works (K&B) | 90000 | 90000 | 90000 | 0 | 56128.01 | N6389 | 0
N6390 | Kitchens & Bathrooms | 2073000 | 2073000 | 2073000 | 503117.1 | 556865.71 | N6390 | 0
N6391 | Heating | 1221000 | 1221000 | 1221000 | 282051 | 314453.54 | N6391 | 0
N6392 | Roofing | 150000 | 150000 | 150000 | 0 | 50693.46 | N6392 | 0
N6393 | External Doors | 200000 | 200000 | 200000 | 0 | 6632.66 | N6393 | 0
N6394 | Windows | 250000 | 250000 | 250000 | 0 | 3719.08 | N6394 | 0
N6395 | Electrics | 785000 | 785000 | 785000 | 197192 | 75593.75 | N6395 | 0
N6427 | Shops | 0 | 0 | 0 | 0 | 0 | N6427 | 0
N7018 | Minox | 19000 | 19000 | 19000 | 0 | 15.73 | N7018 | 0
N7020 | External Adaptations | 250000 | 250000 | 250000 | 0 | 35898.59 | N7020 | 0
N7026 | Communal Areas | 150000 | 150000 | 150000 | 0 | 0 | N7026 | 0
N7027 | Environmental Improvements | 100000 | 100000 | 100000 | 0 | 0 | N7027 | 0
N7028 | Non Dwelling HRA Assets | 117000 | 117000 | 117000 | 0 | 0 | N7028 | 0
N7029 | HCA New Build | 7744000 | 7744000 | 7744000 | 0 | 55307.87 | N7029 | 0
N7030 | Horspath Road Depot | 2200000 | 2200000 | 2200000 | 0 | 0 | N7030 | 0
N7031 | Homes at Barton | 650000 | 650000 | 650000 | 0 | 0 | N7031 | 0
N7032 | Estate Enhancements and Regeneration | 500000 | 500000 | 500000 | 20000 | 19125 | N7032 | 0
Q2000 | Offices for the Future | 0 | 0 | 90000 | 0 | 250.11 | Q2000 | 90000
R0005 | MT Vehicles/Plant Replacement Prog. | 2741579 | 2741579 | 2741579 | 683200.84 | 587697.73 | R0005 | 0
T2269 | Toilet Improvements | 176945 | 176945 | 176945 | 49155.32 | 51576.3 | T2269 | 0
T2270 | Bin Stores for Council Flats to Assist Recycling | 0 | 0 | 0 | 0 | 0 | T2270 | 0
T2273 | Car Parks Resurfacing | 80000 | 80000 | 80000 | 0 | 0 | T2273 | 0
T2274 | Gloucester Green Car Park Waterproofing | 100000 | 100000 | 100000 | 0 | 0 | T2274 | 0
B0069 | Corporate Property Major Works Programme |  | 200000 | 0 | 0 | 0
|  | 44278810 | 44478810.87 | 37695510 | 3055489.76 | 3120894.31 |  | -6583300 | 6283300
|  |  | 44478810.73 |  | 3325989.76 | 3120894.31 |  | -300000
0
Costc | Costc (T) | Approved budget | Amount
A1300 | Playground Refurbishment | 18146 | 2291.24
A1301 | Play Barton | 74441 | 0
A3129 | Donnington Recreation Ground Improvements | 44375 | 0
A4808 | Blackbird Leys LC Improvements | 128278 | 0
A4810 | New Build Competion Pool | 7560900 | 2085
A4814 | Leisure Centre Substantive Works | 370900 | 0
A4815 | Leisure Centre Improvement Work | 447250 | 0
A4816 | Sports Pavillions | 885800 | 59003.13
A4818 | Lye Valley & Chiswell Valley Walkways | 124000 | 0
A4820 | Upgrade Tennis Courts | 69180 | 0
A4821 | Upgrade multi-Use Games Area | 63170 | -0.2
A4824 | Meadowe Lane Skate Park | 0 | 1120
A4826 | Parks Works | 100000 | 0
A4827 | Cowley Outdoor Gym | 70000 | 0
A4828 | Valentia Road Playground | 10000 | 0
A4829 | Oxford Spires Academy | 200000 | 0
A4830 | Develop New Burial Space | 1000000 | 0
B0003 | Roof Repairs & Ext Refurb - 44-46 George St | 27000 | 0
B0010 | Covered Market - signage improvements | 19440 | 32105.6
B0027 | Covered Market - Improvements & Upgrade to Roof | 56900 | 0
B0028 | Covered Market - New Roof Structures to High St En | 113200 | 47.29
B0033 | Community Centres | 367170 | 9429.22
B0034 | Rose Hill Community Centre | 576300 | 20470.25
B0036 | Investment - Covered Market | 202100 | 56545.65
B0037 | Car Parks | 296100 | 1447.19
B0040 | Investment - Broad Street | 217280 | 3460.45
B0041 | Investment - Misc City Centre Properties | 67480 | 2963.69
B0043 | Investment - George Street | 203000 | 51200.9
B0044 | Investment - Outer City | 47200 | 0
B0045 | Investment - St Michaels Street | 39250 | 1615.63
B0046 | Investment - Ship Street | 75720 | 3747.79
B0048 | Leisure - Cemeteries | 55200 | 3738.04
B0050 | Leisure - Depots | 43800 | 0
B0051 | Leisure - Pavilions | 460300 | 124376.48
B0052 | Miscellaneous Properties | 90000 | 48754.84
B0054 | Town Hall | 425480 | 29503.92
B0060 | Depot Relocation Studies | 1880000 | 0
B0063 | Covered Market Sprinkler System | 125200 | 0
B0064 | Covered Market Emergency Lighting | 0 | -516.54
B0065 | Parks & Cemetery - Masonry Wall & Path Improvement | 54600 | 0
B0067 | Fencing Repairs Across the City | 172000 | 76854.7
B0068 | Town Hall - Conference System Refurbishment | 333000 | 304.69
B0071 | Parks Properties Health and Safety Works | 47000 | 50719
B0072 | 23-25 Broad Street | 350000 | 0
B0073 | Clearing Channels under Frideswide Bridge | 5000 | 0
B0074 | R & D Feasibility Fund | 125000 | 16625.3
B0075 | Stage 2 Museum of Oxford Development | 550000 | 0
B0076 | Town Hall Improvements | 200000 | 3275.13
B0077 | Direct Services Depots | 150000 | 0
B0078 | Allotments | 3000 | 0
B0079 | Street Sports Sites | 8110 | 0
B0080 | Templars Square Refurbishment/Relocation | 150000 | 0
C3039 | ICT Infrastructure | 50000 | 43153.51
C3041 | New server for telephone system | 11288 | 0
C3042 | Customer First Programme | 115670 | 0
C3044 | Software Licences | 188574 | 176052.5
C3045 | Mobile Working | 98000 | 0
C3046 | System Integration Capability | 25000 | 0
C3047 | Oracle 11g Upgrade | 25000 | 0
C3048 | Server 2008 Upgrade for Idox | 25000 | 0
C3049 | Source Code Management | 15000 | 0
C3050 | Tree Managment Software | 15000 | 0
E3511 | Renovation Grants | 10435 | -11897.02
E3521 | Disabled Facilities Grants | 225308 | 78600.94
E3553 | Carbon Reduction | 300000 | 0
F0011 | Pay & Display Parking in the Car Parks | 8400 | 0
F0015 | Cycle Oxford | 194503 | 7182
F1323 | Bridge Over Fiddlers Stream | 238016 | 10190
F6013 | Bullingdon Community Centre - provision or enhance | 1537 | 0
F7006 | Work of Art - Littlemore | 1560 | 0
F7007 | Woodfarm / Headington Community Centre - Improveme | 19887 | 0
F7008 | Lamarsh Road Landscaping | 14460 | 0
F7009 | CCTV Gipsy Lane Campus | 60000 | 0
F7010 | Work of Art Said Business School | 50000 | 0
F7011 | Headington Environmental Improvements | 60000 | 0
F7012 | Rose Hill Recreation Ground Improvements | 3300 | 0
F7020 | Work of Art Shotover View | 14635 | 0
G1013 | Dawson Street Gardens | 19000 | 0
G3013 | Diamond Place car park footpath extension | 6324 | 0
G3014 | East Oxford Community Associaltion Improvements | 2550 | 0
G3015 | NE Marston Croft Road Recreation Ground | 19300 | 0
G4006 | Florence Park CC Kitchen | 1411 | 0
G6013 | Urban Broadband | 325000 | 0
G6014 | CCTV Project | 25000 | 0
G6015 | CCTV Rosehill Parade | 18000 | 0
M5014 | West End Partnership (Growth Points Grant) | 217225 | 0
M5015 | Old Fire Station | 0 | -472.36
N6384 | Foresters Towers | 500000 | 2936.22
N6385 | Adaptations for disabled | 226080 | 149376.29
N6386 | Structural | 125000 | 54205.94
N6387 | Controlled Entry | 210000 | 35572.39
N6388 | Major Voids | 205984 | 160999.07
N6389 | Damp-proof works (K&B) | 90000 | 56128.01
N6390 | Kitchens & Bathrooms | 503117.1 | 556865.71
N6391 | Heating | 282051 | 314453.54
N6392 | Roofing | 150000 | 50693.46
N6393 | External Doors | 200000 | 6632.66
N6394 | Windows | 250000 | 3719.08
N6395 | Electrics | 197192 | 75593.75
N6427 | Shops | 0 | -4643.5
N7011 | Cardinal House - Refurbishment | 0 | 583.9
N7018 | Minox | 19000 | 15.73
N7020 | External Adaptations | 250000 | 35898.59
N7026 | Communal Areas | 150000 | 0
N7027 | Environmental Improvements | 100000 | 0
N7028 | Non Dwelling HRA Assets | 117000 | 0
N7029 | HCA New Build | 7744000 | 55307.87
N7030 | Horspath Road Depot | 2200000 | 0
N7031 | Homes at Barton | 650000 | 0
N7032 | Estate Enhancements and Regeneration | 20000 | 19125
Q2000 | Offices for the Future | 0 | 250.11
R0005 | MT Vehicles/Plant Replacement Prog. | 683200.84 | 587697.73
T2269 | Toilet Improvements | 49155.32 | 51576.3
T2270 | Bin Stores for Council Flats to Assist Recycling | 0 | -6816.22
|  | 36028433.26 | 3110149.59

## Sheet3 (hidden)
CAPITAL BUDGET 2013-17
| 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18
General Fund Capital Programme | £ | £ | £ | £ | £
F1323 Bridge Over Fiddlers Stream | 259703
F0015 Cycle Oxford | 190000 | 50000 | 50000
NEW Woodfarm/Headington Community Centre Improvements | 19887
NEW Donnington Recreation Ground Improvements | 44375
NEW CCTV Gypsy Lane Campus | 60000
NEW Headington Environmental Improvements | 60000
NEW Rose Hill Recreation Ground Improvements | 3300
NEW Work of Art Littlemore | 1560
NEW West End Partnership | 217225
NEW Work of Art Shotover View | 14635
NEW Work of Art - Said Business School | 50000
NEW Sunnymead Park - Enhancement of Play Area Facilities |  | 1830
S11 City Development Total | 920685 | 51830 | 50000 | 0 | 0
E3511 Renovation Grants | 50000 | 50000 | 50000 | 50000 | 50000
E3521 Disabled Facilities Grants | 840000 | 640000 | 640000 | 640000 | 640000
NEW Carbon Reduction | 300000
S12 Environmental Development Total | 1190000 | 690000 | 690000 | 690000 | 690000
G1013 Dawson Street Gardens | 19000
G3013 Diamond Place Car Park Footpath Extension | 6324
G3014 East Oxford Community Association Improvements | 2550
G4006 Florence Park Community Centre Kitchen | 1411
NEW Urban Broadband | 325000
NEW CCTV Project | 25000
NEW CCTV Rosehill Parade | 18000
NEW East Oxford Project |  | 200000
NEW Café South Oxford Community Centre |  | 50000
NEW St Ebbes Deaf and Hard of Hearing Centre |  | 50000
S41 Community Development Team | 397285 | 300000 | 0 | 0 | 0
A4808 Blackbird Leys Leisure Centre Improvements | 128278
A4814 Leisure Centre Substantive Repairs | 310000 | 66000
B0010 Covered Market - Signage Improvements | 26941
B0028 Covered Market - New Roof Structures to High Street Entrances | 90000
B0034 Rose Hill Community Centre | 88000
B0036 Investment - Covered Market | 50000
B0045 Investment - St Michael's Street | 43000
B0046 Investment - Ship Street | 20000
B0052 Miscellaneous Properties | 75000
B0054 Town Hall Improvements | 297702
B0060 Feasibility Studies Depot Relocation | 1880000
B0063 Covered Market - Replacement Sprinkler System | 100000
B0065 Parks & Cemetery - Masonry Walls & Path Improvements | 40000 | 40000
B0067 Fencing Repairs Across The City | 225000 | 150000
B0068 Town Hall -Conference System Refurbishment | 300000
NEW Rose Hill Community Centre | 500000 | 3200000
NEW 23-25 Broad Street | 350000
NEW Clearing Channels Under Frideswide Bridge | 5000
NEW Jericho Community Centre |  | 200000
NEW R & D Feasibility Fund | 125000 | 125000
NEW Stage 2 Museum of Oxford Development | 550000
NEW Town Hall | 200000 | 50000
Repairs & Maintenance Programme:
B0069 Refurbishment of Council Buildings | 200000
NEW Bury Knowle House | 0 | 0 | 87900 | 0
NEW Community Centres | 275570 | 313420 | 288200 | 413320
NEW Cemeteries | 58500 | 0 | 28070 | 12120
NEW Covered Market | 150000 | 150000 | 75000 | 0
NEW Car Parks | 230000 | 80000 | 60000 | 50000
NEW Direct Services Depots | 150000 | 0 | 210600 | 25500
NEW Investment Properties ~ Broad Street | 103400 | 0 | 33800 | 17400
NEW Investment Properties ~ City Centre Misc. | 70000 | 10000 | 24000 | 0
NEW Investment Properties ~ George Street | 203000 | 0 | 77800 | 0
NEW Investment Properties ~ Outer City | 47200 | 38600 | 80700 | 257100
NEW Investment Properties ~ Ship Street | 56220 | 0 | 0 | 0
NEW Allotments | 3000 | 13700 | 34450 | 10200
NEW Street Sports Sites | 8110 | 0 | 10720 | 0
NEW Leisure & Parks ~ Depots | 40000 | 0 | 18760 | 0
NEW Leisure & Parks ~ Pavilions | 470000 | 805000 | 75000 | 0
NEW Leisure & Parks ~ Toilets | 0 | 9200 | 0 | 0
NEW Miscellaneous Properties | 15000 | 0 | 0 | 14360
NEW Town Hall | 120000 | 280000 | 55000 | 50000
S14 Corporate Property Total | 7603921 | 5530920 | 1160000 | 850000 | 0
NEW Templars Square Refurbishment/Relocation | 150000
S21 Customer Services Total | 150000 | 0 | 0 | 0 | 0
A1301 Play Barton | 92587
A4810 New Build Competition Pool | 7560254
A4815 Leisure Centre Improvement Work | 400000
A4816 Sports Pavilions | 820000 | 200000
A4818 Lye Valley & Chiswell Valley Walkways | 62000
A4820 Upgrade Existing Tennis Courts | 60000 | 54000 | 60000
A4821 Upgrade Multi-Use Games Area | 48000 | 48000 | 48000
A4822 Recycling & Bin Improvement (City Parks) | 13000 | 12000 | 12000
NEW Develop new burial space | 1000000
NEW Parks Works | 100000 | 100000 | 50000 | 50000 | 50000
NEW Cowley Outdoor Gym | 70000
NEW Valentia Road Playground | 10000
NEW Pavilions Grey Water Harvesting |  |  | 28000
NEW Horpath Athletics Ground |  |  | 50000 | 450000
NEW Three Artificial Turf Cricket Wickets |  | 12000 | 12000 | 12000
NEW Oxford Spires Academy | 200000
S22 Leisure & Parks Total | 10435841 | 426000 | 260000 | 512000 | 50000
F0012 Park & Ride Purchase of Capital Items - Peartree, Redbridge, Seacourt | 135000
R0005 Vehicle & Plant Replacement Programme | 2562700 | 2200250 | 1799000 | 453000 | 500000
T2269 Toilet improvements | 180000 | 80000
NEW Car Parks Resurfacing | 80000 | 350000 | 350000 | 350000 | 350000
NEW Gloucester Green Car Park Waterproofing | 100000
S23 Direct Services Total | 3057700 | 2630250 | 2149000 | 803000 | 850000
C3039 ICT Infrastructure | 200000 | 100000 | 150000 | 150000 | 150000
C3044 Software Licences | 188574 | 177000 | 177000 | 177000 | 177000
NEW Mobile Working | 98000
NEW System Integration Capability (Middleware) | 25000
NEW Oracle 11g Upgrade | 25000
NEW Server 2008 Upgrade for Idox | 25000
NEW Source Code Management | 15000
NEW Tree Management Software | 15000
S03 Business Improvement & Technology Total | 591574 | 277000 | 327000 | 327000 | 327000
Total General Fund Schemes | 24347006 | 9906000 | 4636000 | 3182000 | 1917000
Housing Revenue Account Capital Programme |  |  |  |  | £
| £ | £ | £ | £
1500000
N6384 Tower Blocks | 500000 | 1500000 | 1500000 | 1500000 | 210000
N6387 Controlled Entry | 210000 | 210000 | 210000 | 210000 | 200000
N6393 External Doors | 200000 | 200000 | 200000 | 200000 | 250000
N7020 External Adaptations | 250000 | 250000 | 250000 | 250000 | 19000
N7018 Minox | 19000 | 19000 | 19000 | 19000
N6394 Windows | 250000 | 250000 | 250000 | 250000 | 250000
N6389 Damp-proof works (K&B) | 90000 | 90000 | 90000 | 90000 | 90000
N6392 Roofing | 150000 | 150000 | 150000 | 150000 | 150000
N6386 Structural | 125000 | 125000 | 125000 | 125000 | 125000
N7028 Non Dwelling HRA Assets | 117000 | 117000 | 117000 | 117000 | 117000
N7026 Communal Areas | 150000 | 150000 | 150000 | 150000 | 150000
N7027 Environmental Improvements | 100000 | 100000 | 100000 | 100000 | 100000
N6385 Adaptations for disabled | 900000 | 900000 | 900000 | 900000 | 900000
N6390 Kitchens & Bathrooms | 2073000 | 2073000 | 1892000 | 1743000 | 1594000
N6391 Heating | 1221000 | 1221000 | 1187000 | 1221000 | 1187000
N6388 Major Voids | 820000 | 800000 | 776000 | 716000 | 750000
N6395 Electrics | 785000 | 726000 | 666000 | 607000 | 547000
NEW Affordable Homes Programme | 7744000 | 9366000 | 348000 | 12000
NEW Horspath Depot | 2200000 | 0 | 0 | 0
NEW Homes at Barton | 650000 | 2500000 | 3380000 | 13500000 | 11013000
NEW Estate Enhancements and Regeneration | 500000 | 500000 | 500000 | 500000 | 500000
NEW Contribution to Rosehill | 0 |  | 1500000
Total Housing Revenue Account Schemes | 19054000 | 21247000 | 14310000 | 22360000 | 19652000
Total Capital Programme | 43401006 | 31153000 | 18946000 | 25542000 | 21569000
FINANCING
Financing - General Fund
Developer contributions | 210000
Government Funding | 482587 | 390000 | 390000 | 390000 | 390000
Capital Receipts | 16077335 | 1598881 | 256920
Direct Revenue Funding | 1362699 | 1697839 | 1829080 | 387640 | 1056587
Revenue Reserves | 356000 | 0 | 0
DRF For Vehicles | 1314000 | 1270000 | 1370000
New Bids Funding
HRA Revenue re Rose Hill
General Fund Revenue Contributions additional | 1733000 |  |  | 1279587
Capital Receipts | 1428000 | 3656200 |  | 521773 | 720413
Government Grants |  |  |  | 150000
Developer Contributions | 855685 | 1058830
General Fund Capital Receipts - New Rosehill |  |  | 790000
Vehicles and plant- Prudential Borrowing | 177700 | 209250 |  | 453000 | 500000
Heritage Lottery fund for Town Hall | 100000 | 25000
Arts Council & HLF | 250000
Financing - HRA
Revenue | 19054000 | 19247000 | 14310000 | 22360000 | 19652000
HCA Grant |  | 2000000
TOTAL FINANCING | 43401006 | 31153000 | 18946000 | 25542000 | 22319000

## Sheet4 (hidden)
Capital Budget 2013/14 to 2016/17
| Capital Scheme | Budget 2013/14 | 2013/14 Budget as at 30/11/12 | Slippage since budget prepared | Budget for 2013/14 New Bids & Slippage | Budget 2014/15 | Budget 2015/16 | Budget 2016/17 | Budget 2017/18
|  | £ |  |  |  | £ | £ | £ | £
F1323 | F1323 Bridge Over Fiddlers Stream |  | 75000 | 75000 | 75000
F6013 | F6013 Bullingdon Community Centre -Enhancement of Community Facilities |  | 0 | 0 | 0
F6015 | F6015 Slade Area Public Work of Art |  | 0 | 0 | 0
F7008 | F7008 Landscaping Work at Lamarsh Road |  | 0 | 0 | 0
F7019 | F7019 Work of Art at Rose Hill |  | 0 | 0 | 0
Z3710 | Z3710 St Lukes Church Community Facilities |  | 0 | 0 | 0
M5014 | M5014 West End Partnership |  | 0 | 0 | 0
City | City Development | 0 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0
E3511 | E3511 Renovation Grants | 50000 | 50000 | 0 | 50000 | 50000
E3521 | E3521 Disabled Facilities Grants | 640000 | 840000 | 200000 | 840000 | 640000 | 640000 | 640000 | 640000
E3553 | Carbon Reduction | 300000 | 300000 | 0 | 300000
Envir | Environmental Development | 990000 | 1190000 | 200000 | 1190000 | 690000 | 640000 | 640000 | 640000
G1013 | G1013 Dawson Street Gardens |  | 19000 | 19000 | 19000
G3013 | G3013 Diamond Place car park footpath extension |  | 6324 | 6324 | 6324
G3014 | G3014 East Oxford Community Association Improvements |  | 2550 | 2550 | 2550
G4006 | G4006 Florence Park CC Kitchen |  | 1411 | 1411 | 1411
G6010 | G6010 Mount Place Square Refurbishment |  | 0 | 0 | 0
G6011 | G6011 St Lukes Church Hall Extension |  | 0 | 0 | 0
G6012 | G6012 South Oxford Community Centre Main Hall Replacement |  | 0 | 0 | 0
G3015 | G3015 NE Marston Croft Road Recreation Ground |  | 0 | 0 | 0
G3016 | G3016 Peat Moors all weather pitch |  | 0 | 0 | 0
G3017 | G3017 CCTV Replacement Programme |  | 0 | 0 | 0
0
M5015 | M5015 Old Fire Station |  | 0 | 0 | 0
Commu | Communities and Housing | 0 | 29285 | 29285 | 29285 | 0 | 0 | 0 | 0
A4808 | A4808 Blackbird Leys leisure centre Improvements | 128278 | 128278 | 0 | 128278 | 0
A4812 | A4812 Building Improvements (GF Leisure) | 0 | 0 | 0 | 0 | 0
A4813 | A4813 Hinksey Pools main pool liner | 0 | 0 | 0 | 0 | 0
A4814 | A4814 Leisure Centre substantive repairs | 310000 | 310000 | 0 | 310000 | 66000
0
Offic | Offices for the Future |  | 0 | 0 | 0
Q2000 | Q2000 Offices for the Future | 0 | 0 | 0 | 0 | 0
0
| Community Centres |  | 0 | 0 | 0
B0022 | B0022 DDA East Oxford Community Centre Lift |  | 0 | 0 | 0
B0033 | B0033 Community Centres |  | 0 | 0 | 0
B0034 | B0034 Rose Hill Community Centre |  | 88000 | 88000 | 88000
0
| Covered Market |  | 0 | 0 | 0
B0010 | B0010 Covered Market signage improvements |  | 26941 | 26941 | 26941
B0027 | B0027 Covered Market - Improvements & Upgrade to Roof |  | 0 | 0 | 0
B0028 | B0028 Covered Market - New Roof Structures to High St Entrances | 0 | 90000 | 90000 | 90000 | 0
B0036 | B0036 Investment ~ Covered Market |  | 50000 | 50000 | 50000
B0063 | B0063 Covered Market Replacement Sprinkler System | 0 | 100000 | 100000 | 100000 | 0 | 0
B0064 | B0064 Covered Market - Improvements to Emergency Lighting | 0 | 0 | 0 | 0 | 0 | 0
0
| Investment Properties |  | 0 | 0 | 0
B0003 | B0003 Roof Repairs & Ext Refurbishment 44-46 George St |  | 0 | 0 | 0
B0040 | B0040 Investment ~ Broad Street |  | 0 | 0 | 0
B0041 | B0041 Investment - Misc City Centre Properties |  | 0 | 0 | 0
B0042 | B0042 Investment - Gloucester Green |  | 0 | 0 | 0
B0044 | B0044 Investment - Outer City |  | 0 | 0 | 0
B0045 | B0045 Investment ~ St. Michael’s Street |  | 43000 | 43000 | 43000
B0046 | B0046 Investment - Ship Street |  | 20000 | 20000 | 20000
B0070 | B0070 Ramsay House Replacement Comfort Cooling System |  | 0 | 0 | 0
0
| Miscellaneous Council Properties |  | 0 | 0 | 0
B0031 | B0031 Miscellaneous Admin Buildings |  | 0 | 0 | 0
B0035 | B0035 Miscellaneous Civic Properties |  | 0 | 0 | 0
B0037 | B0037 Car Parks |  | 0 | 0 | 0
B0039 | B0039 Houses and Lodges |  | 0 | 0 | 0
B0052 | B0052 Miscellaneous Properties |  | 75000 | 75000 | 75000
B0053 | B0053 Public Toilets |  | 0 | 0 | 0
B0055 | B0055 Property Surveys |  | 0 | 0 | 0
B0059 | B0059 FIT Panels on Leisure Buildings |  | 0 | 0 | 0
B0060 | B0060 Feasibility Studies Depot Relocation | 1750000 | 1880000 | 130000 | 1880000 | 0 | 0
0
| Parks & Cemeteries |  | 0 | 0 | 0
B0048 | B0048 Leisure - Cemeteries |  | 0 | 0 | 0
B0050 | B0050 Leisure ~ Depots |  | 0 | 0 | 0
B0051 | B0051 Leisure - Pavilions |  | 0 | 0 | 0
B0065 | B0065 Parks & Cemetery - Masonry Walls & Path Improvements | 40000 | 40000 | 0 | 40000 | 40000 | 0
B0067 | B0067 Fencing Repairs across the City | 150000 | 225000 | 75000 | 225000 | 150000 | 0
b0071 | B0071 Parks properties (H&S works) |  | 0 | 0 | 0
A4823 | A4823 Cemetery Development | 0 | 0 | 0 | 0 | 0 | 0
0
| Town Hall |  | 0 | 0 | 0
B0054 | B0054 Town Hall |  | 297702 | 297702 | 297702
B0056 | B0056 City Centre Office Security |  | 0 | 0 | 0
B0057 | B0057- Town Hall Fire Alarm |  | 0 | 0 | 0
B0068 | B0068 Town Hall - Conference System Refurbishment |  | 300000 | 300000 | 300000
0
Budge | Budget Approved for Future Years - To be allocated |  | 0 | 0 | 0
Refurbishment | Refurbishment of Council Buildings | 1400000 | 1400000 | 0 | 1400000 | 1400000 | 910000
Corpo | Corporate Assets | 3778278 | 5073921 | 1295643 | 5073921 | 1656000 | 910000 | 0 | 0
C3041 | C3041 New server for telephone system |  | 0 | 0 | 0
C3042 | C3042 Customer First Programme |  | 0 | 0 | 0
Custo | Customer Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A1300 | A1300 Playground Refurbishment | 0 | 0 | 0 | 0 | 0
A1301 | A1301 Play Barton | 0 | 92587 | 92587 | 92587 | 0
A4810 | A4810 New Build Completion Pool | 7500000 | 7560254 | 60254 | 7560254 | 0
|  |  | 0 | 0 | 0
Z3008 | Z3008 Contribution to Skate Park | 0 | 0 | 0 | 0 | 0
Z3010 | Z3010 Rosehill/Iffley Play Sites | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0
A4815 | A4815 Leisure Centre Improvement Work | 0 | 400000 | 400000 | 400000 | 0 | 0
A4817 | A4817 Develop new burial space | 1000000 | 1000000 | 0 | 1000000 | 0 | 0
A4818 | A4818 Lye Valley & Chiswell Valley Walkways | 62000 | 62000 | 0 | 62000 | 0 | 0
A4816 | A4816 Sports Pavilions | 470000 | 820000 | 350000 | 820000 | 200000 | 0
A4819 | A4819 Rose Hill Cemetery Water Leak | 0 | 0 | 0 | 0 | 0 | 0
A4820 | A4820 Upgrade Existing Tennis Courts | 60000 | 60000 | 0 | 60000 | 54000 | 60000
A4821 | A4821 Upgrade Existing Multi-Use Games Area | 48000 | 48000 | 0 | 48000 | 48000 | 48000
A4822 | A4822 Recycling & Bin Improvement (City Parks) | 13000 | 13000 | 0 | 13000 | 12000 | 12000
F0015 | G6013 Cycle Oxford | 100000 | 190000 | 90000 | 190000 | 50000 | 50000
City | City Leisure | 9253000 | 10245841 | 992841 | 10245841 | 364000 | 170000 | 0 | 0
F0011 | F0011 Pay & Display Parking in the Car Parks | 0 | 0 | 0 | 0 | 0
F0012 | F0012 P & R Purchase of Capital Items - Peartree, Redbridge | 0 | 135000 | 135000 | 135000 | 0
F0014 | F0014 Purchase of ANPR for use in car park enforcement | 0 | 0 | 0 | 0 | 0
R0005 | R0005 Motor Transport Vehicles/Plant Replacement Programme. | 2301000 | 2385000 | 84000 | 2385000 | 1991000 | 1799000
T2266 | T2266 Purchase of Brown Bins Waste Recycling | 0 | 0 | 0 | 0 | 0
T2267 | T2267 Purchase of two hand operated street sweepers | 0 | 0 | 0 | 0 | 0
T2268 | T2268 Purchase of two vehicles for garden waste collection | 0 | 0 | 0 | 0 | 0
T2269 | T2269 Toilet improvements | 175000 | 180000 | 5000 | 180000 | 80000
T2270 | T2270 Bin stores for council flats to assist recycling |  | 0 | 0 | 0
T2271 | T2271 Low emission vehicle for litter bin collection |  | 0 | 0 | 0
T2272 | T2272 Wyatt Road Resurfacing Works |  | 0 | 0 | 0
Direct | Direct Services | 2476000 | 2700000 | 224000 | 2700000 | 2071000 | 1799000 | 0 | 0
C3039 | C3039 ICT Infrastructure | 200000 | 200000 | 0 | 200000 | 100000 | 150000 | 150000 | 150000
C3043 | C3043 ICT Development | 0 | 0 | 0 | 0 | 0
C3044 | C3044 Software Licences | 188574 | 188574 | 0 | 188574 | 177000 | 177000 | 177000 | 177000
ICT s | ICT services | 388574 | 388574 | 0 | 388574 | 277000 | 327000 | 327000 | 327000
NEW BIDS
| 23-25 Broad Street | 350000 |  |  | 350000 | 0 | 0 | 0 | 0
| S106 Woodfarm/Headington Community Centre Improvements | 19887 |  |  | 19887 | 0 | 0 | 0 | 0
| S106 Donnington Recreation Ground Improvements | 44375 |  |  | 44375 | 0 | 0 | 0 | 0
| S106 CCTV Gipsy Lane Campus | 60000 |  |  | 60000 | 0 | 0 | 0 | 0
| S106 Headington Environmental Improvements | 60000 |  |  | 60000 | 0 | 0 | 0 | 0
| S106 Bridge Over Fiddlers Stream | 184703 |  |  | 184703 | 0 | 0 | 0 | 0
| S106 Rose Hill Recreation Ground Improvements | 3300 |  |  | 3300 | 0 | 0 | 0 | 0
| S106 Work of Art Littlemore | 1560 |  |  | 1560 | 0 | 0 | 0 | 0
| S106 West End Contributions | 217225 |  |  | 217225 | 0 | 0 | 0 | 0
| S106 Work of Art Shotover View | 14635 |  |  | 14635 | 0 | 0 | 0 | 0
| S106 Sunnymead Park - Enhancement of Pay Area Facilities | 0 |  |  | 0 | 1830 | 0 | 0 | 0
| Plant and Motor Transport Replacement Programme | 177700 |  |  | 177700 | 209250 | 0 | 453000 | 500000
| Car Parks Resurfacing | 80000 |  |  | 80000 | 350000 | 350000 | 350000 | 350000
| Gloucester Green Car Park Waterproofing | 100000 |  |  | 100000 | 0 | 0 | 0 | 0
| S106 Work of Art Said Business School | 50000 |  |  | 50000 | 0 | 0 | 0 | 0
| Rose Hill Community Centre | 500000 |  |  | 500000 | 3200000 | 0 | 0 | 0
| East Oxford Project | 0 |  |  | 0 | 200000 | 0 | 0 | 0
| Jericho Community Centre | 0 |  |  | 0 | 200000 | 0 | 0 | 0
| Property Repairs and Maintenance Programme | 600000 |  |  | 600000 | 300000 | 250000 | 850000 | 750000
| Stage 2 of Museum of Oxford development (New) | 550000 |  |  | 550000 | 0 | 0 | 0 | 0
| Pavilions Grey Water Harvesting | 0 |  |  | 0 | 0 | 28000 | 0 | 0
| Renovation Grants |  |  |  | 0 |  | 50000 | 50000 | 50000
| Source Code Management | 15000 |  |  | 15000 | 0 | 0 | 0 | 0
| System Integration Capability (Middleware) | 25000 |  |  | 25000 | 0 | 0 | 0 | 0
| Oracle 11g Upgrade | 25000 |  |  | 25000 | 0 | 0 | 0 | 0
| Tree Management Software | 15000 |  |  | 15000 | 0 | 0 | 0 | 0
| Urban Broadband | 325000 |  |  | 325000 |  |  |  | 0
| Parks works | 100000 |  |  | 100000 | 100000 | 50000 | 50000 | 50000
| Horspath Athletics Ground | 0 |  |  | 0 | 0 | 50000 | 450000 | 0
| SQL Server 2008 Upgrade for Idox | 25000 |  |  | 25000 | 0 | 0 | 0 | 0
| Town Hall Improvements | 200000 |  |  | 200000 | 50000 | 0 | 0 | 0
| Templar Square Refurbishment/Relocation | 150000 |  |  | 150000 | 0 | 0 | 0 | 0
| CCTV Project | 25000 |  |  | 25000 | 0 | 0 | 0 | 0
| Three Artificial Turf Cricket Wickets | 0 |  |  | 0 | 12000 | 12000 | 12000 | 0
| Mobile Working | 98000 |  |  | 98000 |  | 0 | 0 | 0
| R & D Feasibility Fund | 125000 |  |  | 125000 | 125000 | 0 | 0 | 0
| Cowley Outdoor Gym | 70000 |  |  | 70000
| CCTV Rosehill Parade | 18000 |  |  | 18000
| Café South Poxfordshire Community Centre |  |  |  | 0 | 50000
| St Ebbs Deaf and Hard of Hearing Centre |  |  |  | 0 | 50000
| Clearing channels under Frideswide Bridget | 5000 |  |  | 5000
| Valentia Road Playground | 10000 |  |  | 10000
| Oxford Spires Academy | 0 |  |  | 200000
200000
| NEW BIDS | 4244385 | 0 | 0 | 4644385 | 4848080 | 790000 | 2215000 | 1700000
GF To | General Fund Total | 21130237 | 19702621 | 2816769 | 24347006 | 9906080 | 4636000 | 3182000 | 2667000
|  | New Bids |  |  | 4444385
|  | Slippage |  |  | 10656621
|  | Original Budget |  |  | 9046000
200000
|  |  | 19702621 | 2828343 | 24347006
|  |  | 0 | -11574
Exter | External Contracts
N6384 | N6384 Tower Blocks | 500000 |  |  | 500000 | 1500000 | 1500000 | 1500000 | 1500000
N6387 | N6387 Controlled Entry | 210000 |  |  | 210000 | 210000 | 210000 | 210000 | 210000
N6393 | N6393 External Doors | 200000 |  |  | 200000 | 200000 | 200000 | 200000 | 200000
N7020 | N7020 External Adaptations | 250000 |  |  | 250000 | 250000 | 250000 | 250000 | 250000
N7021 | N7021 Extensions | 0 |  |  | 0 | 0
N7018 | N7018 Minox | 19000 |  |  | 19000 | 19000 | 19000 | 19000 | 19000
0
N6394 | N6394 Windows | 250000 |  |  | 250000 | 250000 | 250000 | 250000 | 250000
N6389 | N6389 Damp-proof works (K&B) | 90000 |  |  | 90000 | 90000 | 90000 | 90000 | 90000
N6392 | N6392 Roofing | 150000 |  |  | 150000 | 150000 | 150000 | 150000 | 150000
N6386 | N6386 Structural | 125000 |  |  | 125000 | 125000 | 125000 | 125000 | 125000
N7010 | N7010 Headley House - Refurbishment | 0 |  |  | 0 | 0
N6427 | N6427 Shops | 0 |  |  | 0 | 0
N6396 | N6396 Sheltered Blocks |  |  |  | 0
N7028 | N7028 Non Dwelling HRA Assets | 117000 |  |  | 117000 | 117000 | 117000 | 117000 | 117000
N7026 | N7026 Communal Areas | 150000 |  |  | 150000 | 150000 | 150000 | 150000 | 150000
N7027 | N7027 Environmental Improvements | 100000 |  |  | 100000 | 100000 | 100000 | 100000 | 100000
New C | New Contingency |  |  |  | 0
New F | New Fees |  |  |  | 0
0
New B | New Build |  |  |  | 0
N7011 | N7011 Cardinal House - Refurbishment | 0 |  |  | 0 | 0
N7019 | N7019 Lambourn Road | 0 |  |  | 0 | 0
HCA | HCA New Build |  |  |  | 0
0
Inter | Internal Contracts |  |  |  | 0
0
N6385 | N6385 Adaptations for disabled | 900000 |  |  | 900000 | 900000 | 900000 | 900000 | 900000
N6390 | N6390 Kitchens & Bathrooms | 2073000 |  |  | 2073000 | 2073000 | 1892000 | 1743000 | 1594000
N6391 | N6391 Heating | 1221000 |  |  | 1221000 | 1221000 | 1187000 | 1221000 | 1187000
N6388 | N6388 Major Voids | 820000 |  |  | 820000 | 800000 | 776000 | 716000 | 750000
N6395 | N6395 Electrics | 785000 |  |  | 785000 | 726000 | 666000 | 607000 | 547000
| Contribution to Rosehill |  |  |  | 0 |  | 1500000
| New Additions | 11094000 |  |  | 11094000 | 12366000 | 4228000 | 14012000 | 11513000
| Housing Revenue Account | 19054000 | 0 | 0 | 19054000 | 21247000 | 14310000 | 22360000 | 19652000 | 0
| Grand Total | 40184237 | 19702621 | 2816769 | 43401006 | 31153080 | 18946000 | 25542000 | 22319000
Financing - General Fund
| Developer contributions |  |  |  | 210000
| Government Funding | 390000 |  |  | 482587 | 390000 | 390000 | 390000 | 390000
| Capital Receipts | 13447153 |  |  | 13580935 | 624701 | 571316 |  |  | Changed
| Direct Revenue Funding | 1462699 |  |  | 2965799 | 2160349 | 1085684 | 909413 | 1056587 | Changed
| Revenue Reserves | 356000 |  |  | 356000 | 0 | 0
| Prundetial Borrowing for Vehicles | 1230000 |  |  | 2207300 | 1781750 | 1799000 |  |  | Matched to expenditure on vehicles
| Prudential Borrowing | 0 |  |  | 0 | 0 | 0 | 0
New Bids Funding
| HRA Revenue re Rose Hill |  |  |  | 0
| General Fund Revenue Contributions additional | 1733000 |  |  | 1733000 |  |  | 1279587
| Capital Receipts | 1228000 |  |  | 1428000 | 3656200 | 0 | 0 | 720413
| Government Grants |  |  |  | 0 |  |  | 150000
| Developer Contributions | 755685 |  |  | 855685 | 1058830
| General Fund Capital Receipts - New Rosehill |  |  |  | 0 |  | 790000
| Prudential borrowing | 0 |  |  | 0 | 0 | 0 | 0
| Vehicles and plant- Pru Borrowing | 177700 |  |  | 177700 | 209250 | 0 | 453000 | 500000
| Heritage Lottery fund for Town Hall | 100000 |  |  | 100000 | 25000
| Arts Council & HLF | 250000 |  |  | 250000
| Total General Fund Financing | 21130237 | 0 | 0 | 24347006 | 9906080 | 4636000 | 3182000 | 2667000
Financing - HRA
| Revenue | 19054000 |  |  | 19054000 | 19247000 | 14310000 | 22360000 | 19652000
Capital receipts
Decent Homes Reserve
Prudential Borrowing
External Contributions
| HCA Grant |  |  |  |  | 2000000
| Total HRA Financing | 19054000 | 0 | 0 | 19054000 | 21247000 | 14310000 | 22360000 | 19652000
| Total Financing | 40184237 | 0 | 0 | 43401006 | 31153080 | 18946000 | 25542000 | 22319000
| (Surplus)/ Deficit | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Sheet5 (hidden)
Source | Budget for 2013/14 | Budget 2014/15 | Budget 2015/16 | Budget 2016/17 | Budget 2017/18
Arts Council & HLF | 250000
Capital Receipts | 13580935 | 624701 | 571316
Capital Receipts | 1428000 | 3656200 | 0 | 0 | 720413
Developer Contributions | 210000
Developer Contributions | 855685 | 1058830
Direct Revenue Funding | 2965799 | 2160349 | 1085684 | 909413 | 1056587
General Fund Capital Receipts - New Rosehill | 0 |  | 790000
General Fund Revenue Contributions additional | 1733000 |  |  | 1279587
Government Funding | 482587 | 390000 | 390000 | 390000 | 390000
Government Grants | 0 |  |  | 150000
Heritage Lottery fund for Town Hall | 100000 | 25000
Prudential Borrowing for Vehicles | 2207300 | 1781750 | 1799000
Revenue Reserves | 356000 | 0 | 0
Prudential Borrowing for Vehicles | 177700 | 209250 | 0 | 453000 | 500000
Row Labels | Sum of Budget for 2013/14 | Sum of Budget 2017/18 | Sum of Budget 2016/17 | Sum of Budget 2015/16 | Sum of Budget 2014/15
Arts Council & HLF | 250000
Capital Receipts | 15008935 | 720413 | 0 | 571316 | 4280901
Developer Contributions | 1065685 |  |  |  | 1058830
Direct Revenue Funding | 2965799 | 1056587 | 909413 | 1085684 | 2160349
General Fund Capital Receipts - New Rosehill | 0 |  |  | 790000
General Fund Revenue Contributions additional | 1733000 |  | 1279587
Government Funding | 482587 | 390000 | 390000 | 390000 | 390000
Government Grants | 0 |  | 150000
Heritage Lottery fund for Town Hall | 100000 |  |  |  | 25000
Prudential Borrowing for Vehicles | 2385000 | 500000 | 453000 | 1799000 | 1991000
Revenue Reserves | 356000 |  |  | 0 | 0
Grand Total | 24347006 | 2667000 | 3182000 | 4636000 | 9906080

## Profiles (hidden)
Costc |  | Approved budget | Sum of months | P3 Spend | P3 Profile | April | May | June | July | August | September | October | November | December | January | February | March
A1300 | Playground Refurbishment | 18146 | 18146 | 2291.24 | 4536.5 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667 | 1512.1667
A1301 | Play Barton | 74441 | 74441 | 0 | 0 |  |  |  | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222 | 8271.2222
A3129 | Donnington Recreation Ground Improvements | 44375 | 44375 | 0 | 0 | [9 empty] | 14791.6667 | 14791.6667 | 14791.6667
A4808 | Blackbird Leys LC Improvements | 128278 | 128278 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 3278 | 50000 | 50000 | 15000
A4810 | New Build Competion Pool | 4060900 | 4060090 | 2085 | 2090 |  | 0 | 2090 | 2000 | 507000 | 507000 | 507000 | 507000 | 507000 | 507000 | 507000 | 507000
A4814 | Leisure Centre Substantive Works | 370900 | 370900 | 0 | 0 |  | 0 | 0 | 1000 | 0 |  | 61650 | 61650 | 61650 | 61650 | 61650 | 61650
A4815 | Leisure Centre Improvement Work | 447250 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A4816 | Sports Pavillions | 885800 | 885800 | 59003.13 | 60000 |  | 30000 | 30000 | 5400 | 5400 | 64000 | 129000 | 129000 | 140000 | 149000 | 102000 | 102000
A4818 | Lye Valley & Chiswell Valley Walkways | 124000 | 124000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000
A4820 | Upgrade Tennis Courts | 69180 | 69180 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69180
A4821 | Upgrade multi-Use Games Area | 63170 | 63170 | -0.2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63170
A4826 | Parks Works | 100000 | 100000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
A4827 | Cowley Outdoor Gym | 70000 | 70000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
A4828 | Valentia Road Playground | 10000 | 10000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
A4829 | Oxford Spires Academy | 200000 | 200000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
A4830 | Develop New Burial Space | 100000 | 100000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
B0003 | Roof Repairs & Ext Refurb - 44-46 George St | 27000 | 27000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000
B0010 | Covered Market - signage improvements | 19440 | 19440 | 32105.6 | 19440 |  | 0 | 19440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0027 | Covered Market - Improvements & Upgrade to Roof | 56900 | 56900 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56900
B0028 | Covered Market - New Roof Structures to High St En | 113200 | 113200 | 47.29 | 0 |  | 0 | 0 | 5000 | 0 | 0 | 2500 | 0 | 0 | 0 | 13200 | 92500
B0033 | Community Centres | 367170 | 367170 | 9429.22 | 0 |  | 0 | 0 | 500 | 0 | 3700 | 42363 | 0 | 40250 | 24125 | 0 | 256232
B0034 | Rose Hill Community Centre | 576300 | 576000 | 20470.25 | 21000 | 7000 | 7000 | 7000 | 50000 | 50000 | 50000 | 55000 | 70000 | 70000 | 70000 | 70000 | 70000
B0036 | Investment - Covered Market | 202100 | 202100 | 56545.65 | 57000 |  | 0 | 57000 | 18350 | 3500 | 30000 | 30000 | 31250 | 26250 | 4250 | 0 | 1500
B0037 | Car Parks | 296100 | 296100 | 1447.19 | 1500 |  | 0 | 1500 | 9000 | 0 | 0 | 2300 | 6500 | 15000 | 500 | 16000 | 245300
B0040 | Investment - Broad Street | 217280 | 217280 | 3460.45 | 5000 |  | 0 | 5000 | 45000 | 60000 | 0 | 0 | 0 | 0 | 57500 | 0 | 49780
B0041 | Investment - Misc City Centre Properties | 67480 | 67480 | 2963.69 | 3000 |  | 0 | 3000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42480
B0043 | Investment - George Street | 203000 | 203000 | 51200.9 | 50000 |  | 0 | 50000 | 1500 | 0 | 0 | 1000 | 0 | 26250 | 1250 | 0 | 123000
B0044 | Investment - Outer City | 47200 | 47200 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47200
B0045 | Investment - St Michaels Street | 39250 | 39250 | 1615.63 | 2000 |  | 0 | 2000 | 5000 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
B0046 | Investment - Ship Street | 75720 | 75720 | 3747.79 | 4000 |  | 0 | 4000 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 58720
B0048 | Leisure - Cemeteries | 55200 | 55200 | 3738.04 | 4000 |  | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 45500 | 0 | 0 | 5700
B0050 | Leisure - Depots | 43800 | 43800 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 9800
B0051 | Leisure - Pavilions | 460300 | 460300 | 124376.48 | 125000 |  | 55000 | 70000 | 0 | 0 | 136875 | 28750 | 0 | 0 | 0 | 0 | 169675
B0052 | Miscellaneous Properties | 90000 | 90000 | 48754.84 | 48000 | 16000 | 16000 | 16000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 39000
B0054 | Town Hall | 335480 | 335480 | 29503.92 | 30000 |  | 0 | 30000 | 14625 | 21875 | 31250 | 23750 | 13125 | 56875 | 34875 | 23605 | 85500
B0060 | Depot Relocation Studies | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0063 | Covered Market Sprinkler System | 125200 | 129375 | 0 | 0 |  | 0 | 0 | 65000 | 50000 | 10000 | 4375 | 0 | 0 | 0 | 0 | 0
B0065 | Parks & Cemetery - Masonry Wall & Path Improvement | 54600 | 54600 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54600
B0067 | Fencing Repairs Across the City | 172000 | 172000 | 76854.7 | 72000 | 36000 | 0 | 36000 | 36000 | 32000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0
B0068 | Town Hall - Conference System Refurbishment | 333000 | 400000 | 304.69 | 0 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 10000 | 0 | 370000
B0071 | Parks Properties Health and Safety Works | 47000 | 47000 | 50719 | 47000 | 47000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0072 | 23-25 Broad Street | 350000 | 350000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
B0073 | Clearing Channels under Frideswide Bridge | 5000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0074 | R & D Feasibility Fund | 125000 | 125000 | 16625.3 | 17000 | 5000 | 5000 | 7000 | 7000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 93000
B0075 | Stage 2 Museum of Oxford Development | 550000 | 47000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 43750 | 3250 | 0 | 0 | 0 | 0 | 0
B0076 | Town Hall Improvements | 200000 | 200000 | 3275.13 | 4000 |  | 0 | 4000 | 111000 | 54000 | 20000 | 11000 | 0 | 0 | 0 | 0 | 0
B0077 | Direct Services Depots | 150000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0078 | Allotments | 3000 | 2500 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0
B0079 | Street Sports Sites | 8110 | 6850 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 850 | 0 | 0
B0080 | Templars Square Refurbishment/Relocation | 150000 | 150000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 135000 | 7500 | 0 | 0
C3039 | ICT Infrastructure | 200000 | 200020 | 43153.51 | 50000 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16680
C3041 | New server for telephone system | 11288 | 0 | 0 | 0
C3042 | Customer First Programme | 115670 | 0 | 0 | 0
C3044 | Software Licences | 188574 | 0 | 176052.5 | 0 |  | 0
C3045 | Mobile Working | 98000 | 0 | 0 | 0
C3046 | System Integration Capability | 25000 | 0 | 0 | 0
C3047 | Oracle 11g Upgrade | 25000 | 0 | 0 | 0
C3048 | Server 2008 Upgrade for Idox | 25000 | 0 | 0 | 0
C3049 | Source Code Management | 15000 | 0 | 0 | 0
C3050 | Tree Managment Software | 15000 | 0 | 0 | 0
E3511 | Renovation Grants | 47020 | 47020 | -11897.02 | 10435 | 2690 | 3660 | 4085 | 2695 | 2880 | 3415 | 3935 | 4630 | 3675 | 5460 | 5620 | 4275
E3521 | Disabled Facilities Grants | 816590 | 816590 | 78600.94 | 225308 | 95192 | 61488 | 68628 | 45276 | 48384 | 57372 | 66108 | 77784 | 61740 | 91728 | 94416 | 48474
E3553 | Carbon Reduction | 0 | 0 | 0 | 0
F0011 | Pay & Display Parking in the Car Parks | 84000 | 84000 | 0 | 8400 |  |  | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400
F0012 | P & R Puchase of Capital Items - Peartree, Redbrid | 164309 | 164309 | 0 | 0 | [9 empty] | 60487.45 | 80649.94 | 23171.61
F0014 | ANPR for Car Park Enforcement | 1857 | 1857 | 0 | 0 | [11 empty] | 1857
F0015 | Cycle Oxford | 194503 | 194503 | 7182 | 8000 |  | 0 | 8000 |  |  |  | 24417.1667 | 32417.1667 | 32417.1667 | 32417.1667 | 32417.1667 | 32417.1667
F1323 | Bridge Over Fiddlers Stream | 238016 | 248016 | 10190 | 10000 |  | 10000 |  |  |  |  | 39669.3333 | 39669.3333 | 39669.3333 | 39669.3333 | 39669.3333 | 39669.3333
F6013 | Bullingdon Community Centre - provision or enhance | 1537 | 1537 | 0 | 0 | [5 empty] | 1537
F7006 | Work of Art - Littlemore | 1560 | 1560 | 0 | 0 | [5 empty] | 1560
F7007 | Woodfarm / Headington Community Centre - Improveme | 19887 | 19887 | 0 | 0 | [5 empty] | 19887
F7008 | Lamarsh Road Landscaping | 14460 | 14460 | 0 | 0 | [5 empty] | 14460
F7009 | CCTV Gipsy Lane Campus | 60000 | 60000 | 0 | 0 | [5 empty] | 20000 | 20000 | 20000
F7010 | Work of Art Said Business School | 50000 | 50000 | 0 | 0 | [5 empty] | 25000 | 25000
F7011 | Headington Environmental Improvements | 60000 | 60000 | 0 | 0 | [5 empty] | 20000 | 20000 | 20000
F7012 | Rose Hill Recreation Ground Improvements | 0 | 0 | 0 | 0 | [5 empty] | 0
F7020 | Work of Art Shotover View | 14635 | 14635 | 0 | 0 | [5 empty] | 14635
G1013 | Dawson Street Gardens | 19000 | 0 | 0 | 0
G3013 | Diamond Place car park footpath extension | 6324 | 0 | 0 | 0
G3014 | East Oxford Community Associaltion Improvements | 2550 | 0 | 0 | 0
G3015 | NE Marston Croft Road Recreation Ground | 19300 | 0 | 0 | 0
G4006 | Florence Park CC Kitchen | 1411 | 0 | 0 | 0
G6013 | Urban Broadband | 325000 | 0 | 0 | 0
G6014 | CCTV Project | 25000 | 0 | 0 | 0
G6015 | CCTV Rosehill Parade | 18000 | 0 | 0 | 0
M5014 | West End Partnership (Growth Points Grant) | 217225 | 0 | 0 | 0
N6384 | Foresters Towers | 500000 | 0 | 2936.22 | 0 |  | 0 | 0
N6385 | Adaptations for disabled | 900000 | 900000 | 149376.29 | 226080 | 65790 | 82170 | 78120 | 57510 | 78120 | 57510 | 82170 | 98640 | 49320 | 98640 | 73980 | 78030
N6386 | Structural | 125000 | 0 | 54205.94 | 0 |  | 0 | 0
N6387 | Controlled Entry | 210000 | 0 | 35572.39 | 0 |  | 0 | 0
N6388 | Major Voids | 820000 | 820000 | 160999.07 | 205984 | 59942 | 74866 | 71176 | 52398 | 71176 | 52398 | 74866 | 89872 | 44936 | 89872 | 67404 | 71094
N6389 | Damp-proof works (K&B) | 90000 | 0 | 56128.01 | 0 |  | 0 | 0
N6390 | Kitchens & Bathrooms | 2073000 | 2073000 | 556865.71 | 503117.1 | 141585.9 | 171644.4 | 189886.8 | 196313.1 | 144280.8 | 167083.8 | 208129.2 | 181802.1 | 154438.5 | 155267.7 | 200044.5 | 162523.2
N6391 | Heating | 1221000 | 1221000 | 314453.54 | 282051 | 77533.5 | 89865.6 | 114651.9 | 116361.3 | 127106.1 | 127106.1 | 90354 | 86691 | 65201.4 | 72405.3 | 81196.5 | 172527.3
N6392 | Roofing | 150000 | 0 | 50693.46 | 0 |  | 0 | 0
N6393 | External Doors | 200000 | 0 | 6632.66 | 0 |  | 0 | 0
N6394 | Windows | 250000 | 0 | 3719.08 | 0 |  | 0 | 0
N6395 | Electrics | 785000 | 785000 | 75593.75 | 197192 | 57383.5 | 71670.5 | 68138 | 50161.5 | 68138 | 50161.5 | 71670.5 | 86036 | 43018 | 86036 | 64527 | 68059.5
N7018 | Minox | 19000 | 0 | 15.73 | 0 |  | 0 | 0
N7020 | External Adaptations | 250000 | 0 | 35898.59 | 0 |  | 0 | 0
N7026 | Communal Areas | 150000 | 0 | 0 | 0
N7027 | Environmental Improvements | 100000 | 0 | 0 | 0
N7028 | Non Dwelling HRA Assets | 117000 | 0 | 0 | 0
N7029 | HCA New Build | 7744000 | 0 | 55307.87 | 0 |  | 0 | 0
N7030 | Horspath Road Depot | 2200000 | 0 | 0 | 0
N7031 | Homes at Barton | 650000 | 0 | 0 | 0
N7032 | Estate Enhancements and Regeneration | 500000 | 500000 | 19125 | 20000 |  |  | 20000 | 10000 | 10000 | 10000 |  |  | 150000 | 150000 | 150000
Q2000 | Offices For the Future | 90000
R0005 | MT Vehicles/Plant Replacement Prog. | 2741579 | 2741579 | 587697.73 | 683200.84 | 385191.35 | 220971.62 | 77037.87 | 238516.9 | 139272.16 | 247290.54 | 283753.45 | 291704.28 | 344342.12 | 222067.7 | 235776.2 | 55654.81
T2269 | Toilet Improvements | 176945 | 176945 | 51576.3 | 49155.32 | 4919.07 | 14739.52 | 29496.73 | 39317.18 | 29496.73 | 19658.59 | 14739.52 | 14739.52 | 9838.14 |  |  | 0
T2273 | Car Parks Resurfacing | 80000 | 80000 | 0 | 0 | [6 empty] | 40000 | 40000
T2274 | Gloucester Green Car Park Waterproofing | 100000 | 100000 | 0 | 0 |  |  |  | 25000 | 25000 | 25000 | 25000
GRAND TOTAL |  | 37695510 | 22671243 | 3120644.2 | 3055489.76 | 1019399.4867 | 932267.8067 | 1103822.4667 | 1266767.3689 | 1572742.1789 | 1897492.9189 | 2069593.5589 | 1950373.7889 | 2166492.0489 | 2175185.7056 | 2027810.6956 | 4489294.9756