## cvhtmsrv
Audit Tracker
Ref | Review | Review Date | Issue Noted | Risk Rating | Recommendation | Updater | Owner | Due Date | Forecast Completion Date | % Complete | Comments
EA002 | Certification of Claims and Returns | 23-Mar-2010 | All PC and Laptop Assets recorded with user and location details. All infrastructure Assets to be documented (with photographic evidence where possible) with location details | Medium | The Council should obtain a record of the laptop allocations and confirm their location | Fiona Colcutt | Jane Lubbock | 31-Jan-2011 |  | 95 | As part of the Windows 7 project, all laptops have been reallocated with an up-to-date list of asset numbers and their locations/owners prepared. The last areas are being updated during December once the PARIS upgrade has been completed
IA404 | Business Continuity Management | 1/8/13 | BCP's are out of dateand not reviewed on a regular basis | High | Implement a compliance process to ensure that BCP's are reviewed at least annually and that version control is enforced for each plan | Jeremy Thomas | Jeremy Thomas | 2013-11-30 |  | 0 | recommendation agreed
IA405 | Business Continuity Management | 1/8/13 | Failure to identify all dependencies of service area critical activities could result in unforeseen delays and ineffective co-ordination of recovery activities | High | Conduct a Business Impact Analysis workshop to identify all critical activities, and review all third party services and supply dependencies for service BCPs to ensure captured, and ensure detailed in the BCPs | Jeremy Thomas | Jeremy Thomas | 2013-12-31 |  | 0 | recommendation agreed
IA406 | Business Continuity Management | 1/8/13 | A lack of information contained within BCPs which is necessary for recovery could result in unforseen delays and ineffective co-ordination of recovery activities | Medium | Undertake a review of the Service Area BCPs to ensure that they meet the requirements outlined in the Corporate BCP | Jeremy Thomas | Jeremy Thomas | 2013-12-31 |  | 0 | recommendation agreed
IA407 | Business Continuity Management | 1/8/13 | Inconsistent plans could result in key information required for successful service recovery being omitted | Medium | Ensure that all service BCPs use the same template in line with changes required in previous actions | Jeremy Thomas | Jeremy Thomas | 2014-03-31 |  | 0 | recommendation agreed
IA396 | HR Policy Review | 1-Mar-2013 | Performance Improvement Policy- The staff expectations section within the policy is limited and there is little information on how staff can maintain or improve performance. | Medium | A section is added in the policy for staff on how they can maintain or improve their own performance | Simon Howick | Simon Howick | 1-Apr-2013 | 31/1/2014 | 10 | A first draft was expected by 30/9/13 nfor consultation with trade unions thereafter. Delay in producing paper due to other priorities but first draft expected early November.
IA172 | ICT | 27-Apr-2010 | We were informed that no user access reviews have been performed recently, to determine who has access to particular network shared drives and if the access rights granted are appropriate. Similarly no formal reviews have been performed to determine and validate the level of access available to users in the applications such as CRM and Iworld. | Medium | The user access rights to network shares should be reviewed, to ensure that only authorised City Council staff can access the specific network shares they are entitled to access. Formal reviews covering user access rights within applications in the system should be performed to identify any remove any excess privileges available to users. | Fiona Colcutt | Jane Lubbock | 30-Apr-2010 |  | 95 | All admin rights have been removed for Windows 7 users. The final users will be upgraded to Windows 7 once the PARIS upgrade has been completed. Staff are no longer able to download any software onto their laptops fiving the Council control of the applications used.
IA395 | HR Policy Review | 1-Mar-2013 | Organisational Change Policy The majority of other Councils incorporate the redundancy pay scheme within their policy whereas the Council’s equivalent policy is included in a separate document | Medium | The redundancy pay scheme policy is included within the Organisational Change policy. | Simon Howick | Simon Howick | 1-Apr-2013 |  | 100 | This recommendation is not agreed - redundancy pay is covered in the discretionary payments policy (a separate document from org change) because it includes items which are unrelated to org change. We will ensure read across between the 2 documents
IA400 | Housing Benefits | 1-Mar-2013 | Quality checks in 2012/13 started in mid-October following a restructure (during which time checks were suspended). The restructure saw additional resources brought in and a team leader (Sharon Warner) taking responsibility to ensure the quality checking process is properly implemented. A new target was set to check 4% of claims processed (this will increase to 10% from January 2013). Our review showed that the 4% target was not met during the two months tested (November and December). Quality checks are one element of the process for ensuring benefit is assessed correctly. The subsidy team throughout the year carry out checks to ensure the right amount of subsidy is reported. Errors from this process do not form part of the quality checks, however issues found are fed back to assessors. The Council continue to fall below the lower threshold of Local Authority error which ensures the maximum subsidy for overpayment. The issues last year related to resources, this seems to have been dealt with to an extent as resources have been brought in and clear management of the process has been established. The Council is now concentrating its efforts on achieving greater efficiency of the checking process. | Low | Checks will be carried out consistently on a monthly basis throughout the remainder of the year and the new target will be achieved on a monthly basis. | Helen Bishop | Helen Bishop | 31-Mar-2013 |  | 100 | This is completed. Quality checks being carried out daily, the target of 10% has been met almost every day, with a couple of exceptional circumstances eg Windows 7 upgrade.
IA401 | Health and Safety:Housing Stock and Corporate Assets | 1/8/13 | The data on Uniform system is not upto date | Low | The electrical inspections data is uploaded to ensure the Uniform system is upto date and a key performance indicator is introduced that all repairs data is communicated to the Corporate Property Team within 14 days | Steve Stansfield | Steve Stansfield | 2013-12-31 |  | 50 | Recommendation agreed and Direct Services approach will be reveiwed and amended
IA402 | Health and Safety:Housing Stock and Corporate Assets | 1/8/13 | The reports currently being run for monitoring purposes are not as effective as they could be due to the electrical data on Uniform not being up to date | Low | The electrical inspections data is uploaded to ensure the U@niform system is up todate | Steve Stansfield | Steve Stansfield | 2013-12-31 |  | 50 | Recommendation agreed and Direct Services approach will be reveiwed and amended
IA403 | Health and Safety:Housing Stock and Corporate Assets | 1/8/13 | Uniform is updated manually for legislation changes with no automated way of changing the next inspection dates within Uniform | Low | The Council should explore whether the Uniform system can accommodate possible blanket changes to all report due dates for a certain inspection in order to comply with any new legislation or internal policy changes | Steve Stansfield | Steve Stansfield | 2013-09-30 |  | 100 | Recommendation agreed and fully implemented
Mon Nov 04 15:37:51 2013 |  | 1