## cvhtmsrv
Formal Risk Summary
(Oxford)
As at: Sep-2013
Risk | [5 empty] | Date Raised | Owner | Gross |  | Current |  | Residual |  | Comments | Controls
Ref | Title | Risk description | Opp/ threat | Cause | Consequence |  |  | I | P | I | P | I | P |  | Control description | Due date | Status | Progress | Action Owner
CRR-019 | ICT Resilience | Resilience of ICT function - managing projects and improvements alongside business as usual | T | Numerous projects running concurently across the Council all needing ICT support; limited resources and vacant posts within ICT | Inability to provide good quality and consistent service | 1-Apr-2013 | Jacqui Yates | 4 | 4 | 4 | 3 | 3 | 2 |  | Cross skilling of staff in ICT and BIT | 30-Jun-2013 | In Progress | 20% | Jane Lubbock
[15 empty] | Ensure key posts are filled in ICT | 31-Dec-2013 | In Progress | 70% | Jane Lubbock
[15 empty] | Projects are prioritised within available resources, and an ongoing project work plan is in place, as approved by CMT. | 31-Mar-2014 | In Progress | 100% | Jane Lubbock
[15 empty] | Rationalise number of applications requiring support | 30-Sep-2014 | Not Started | 0% | Jane Lubbock
[15 empty] | Regular reporting on progress of key projects to Organisational Development Board, by way of highlight reports | 31-Mar-2014 | In Progress | 100% | Jane Lubbock
[15 empty] | Transfer helpdesk to County to increase capacity | 30-Sep-2013 | In Progress | 95% | Jane Lubbock
CRR-022 | Welfare Reform | Changes to legislation regarding Welfare Reform will impact financially, directly and indirectly on the Council | T | Changes in Legislation | Increased homelessness; increase costs; increase arrears; increase DHP payments | 1-Apr-2013 | Jacqui Yates | 4 | 4 | 4 | 3 | 4 | 3 |  | Commission review of welfare reforms on Oxford residents | 1-May-2014 | In Progress | 60% | Helen Bishop
[15 empty] | Engagement with third sector and other partners to ensure coordinated approach to service delivery | 1-May-2014 | In Progress | 30% | Helen Bishop
[15 empty] | Ensure learning from pilots is communicated and acted upon across the organisation | 1-May-2014 | In Progress | 75% | Helen Bishop
[15 empty] | Monthly reporting of rent arrears, DHP allocations | 1-May-2014 | Ongoing | 100% | Helen Bishop
[15 empty] | Monthly review of impact on stakeholders, council tenants and council tax payers | 31-Jul-2013 | Completed | 100% | Helen Bishop
[15 empty] | Review DHP policy | 1-May-2013 | Completed | 100% | Helen Bishop
[15 empty] | Update financial impact on council in MTFS | 31-Dec-2013 | Completed | 100% | Helen Bishop
CRR-023 | Managing Capital Projects and Contract Management | The need to ensure efficient management of captal projects and contracts | T | Poor Governance on major projects | Cost overruns; non delivery of projects; slippage of projects, cost to the authority | 1-Apr-2013 | David Edwards | 4 | 4 | 4 | 3 | 4 | 2 |  | Ensure staff undertaking projects are appropriately trained | 31-Dec-2013 | Not Started | 0% | Jane Lubbock
[15 empty] | Establish robust methodology for project management using PRINCE 2 principles through Capital Asset Management Group | 31-Dec-2013 | In Progress | 30% | Jane Lubbock
[15 empty] | Review procedures for approving and monitoring projects | 31-Mar-2014 | Not Started | 0% | Nigel Kennedy
CRR-020 | Robustness of Medium Term Financial Plan | Medium Term Financial Plan savings not delivered and pressures not accurately recorded | T | Ongoing Central Government cuts and current savings not being met | Inability to produce a balanced budget, or further saving needing to be made in the future | 1-Apr-2013 | Jacqui Yates | 4 | 3 | 3 | 3 | 3 | 2 |  | Annual review of the Medium Term Financial plan to confirm savings are deliverable and pressures recorded | 31-Dec-2013 | In Progress | 50% | Nigel Kennedy
[15 empty] | Ensure action plans in place for delivery of savings | 30-Sep-2013 | In Progress | 75% | Nigel Kennedy
[15 empty] | Ensure key stakeholders are kept upto date on progress of plan and monitoring | 31-Dec-2013 | In Progress | 100% | Nigel Kennedy
[15 empty] | Produce accurate, timely monitoring reports | 31-Dec-2013 | In Progress | 80% | Nigel Kennedy
CRR-021 | Adverse Weather | The impact of adverse weather on service delivery and adverse financial impact on Council | T | Increase risk of flooding and other adverse weather conditions | Affecting service delivery, increased cost, resource shortfall | 1-Apr-2013 | Tim Sadler | 4 | 3 | 4 | 2 | 4 | 2 |  | Emergency Planning Team set up | 1-May-2013 | In Progress | 100% | Jeremy Thomas
[15 empty] | Ensure early warning processes are in place to advise of early warning systems | 30-Sep-2013 | In Progress | 90% | John Copley
[15 empty] | Set aside budget | 1-May-2013 | Completed | 100% | Nigel Kennedy
CRR-024 | Emergency Planning and Business Continuity | Failure to ensure Emergency Planning and Business Continuity procedures are in place, tested and robust | T | Inadequate plans, not tested, not kept up to date. System failures, failure of partners to deliver services | Civil unrest; impact on service delivery | 1-Apr-2013 | Jacqui Yates | 4 | 3 | 3 | 3 | 3 | 2 |  | Business Continuity Plans are up to date and reviewed for consistency/compatability | 31-Dec-2013 | In Progress | 50% | Jeremy Thomas
[15 empty] | Ensure Emergency Planning procedures and Business Continuity plans are tested annually | 31-Mar-2014 | Not Started | 0% | Jeremy Thomas
[15 empty] | Regularly review Emergency plan contacts list to ensure up to date | 31-Dec-2013 | In Progress | 50% | Jeremy Thomas
CRR-025 | Health & Safety of People | Health & Safety of People | T | Not maintaing a robust Health & Safety policy, and ensuring it is carried out in all service areas. | Increase cost; potental financial penalties; potential insurance claims | 1-Apr-2013 | Jacqui Yates | 4 | 3 | 3 | 3 | 3 | 3 |  | Ensure bi-annual workplace assessments are up to date | 31-Mar-2014 | In Progress | 50% | Simon Howick
[15 empty] | Ensure H&S training undertaken by new staff and regular refreshers delivered either on line or toolbox talks eg fire/first aid arrangements | 30-Sep-2013 | In Progress | 50% | Simon Howick
[15 empty] | Ensure Health and Safety Policy is reviewed and kept up to date | 1-Apr-2013 | Completed | 100% | Simon Howick
CRR-026 | Health & Safety of Property | Health & Safety of Property | T | Not maintaing a robust Health & Safety policy, and ensuring it is carried out in all service areas. | Increase cost; potental financial penalties; public safety in public buildings; potential insurance claims | 1-Apr-2013 | David Edwards | 4 | 3 | 3 | 3 | 3 | 3 |  | Ensure H&S policy is reviewed and kept upto date relating to staff and building | 31-Mar-2014 | Not Started | 0% | Simon Howick
[15 empty] | Ensure statutory H&S risk areas around fire risk assessment, asbestos, water are regularly reviewed and reported to CAMG | 31-Mar-2014 | In Progress | 50% | Stephen Clarke
[15 empty] | Training of staff to be carried out using ilearn and other forms such as MPG session | 31-Mar-2014 | Not Started | 0% | Simon Howick
CRR-027 | Fraud | Risk of fraud against the council | T | Internal fraud by staff, cyber attacks on councils ICT systems, fraudulent claims for council tax and hoUsing benefits and council tax discounts, fraudulent claims for payment | Reputation; Cost | 1-Apr-2013 | Jacqui Yates | 4 | 3 | 3 | 3 | 3 | 2 |  | Annual review of procedures for combating fraud by internal audit | 31-Mar-2014 | Not Started | 0% | Nigel Kennedy
[15 empty] | Ensure internal policies around preventing bribery fraud and corruption, whilstle blowing and money laundering are annually reviwed and communicated to staff | 31-Mar-2014 | Completed | 100% | Nigel Kennedy
[15 empty] | Raise awareness with staff of fraud issues | 31-Dec-2013 | In Progress | 50% | Nigel Kennedy
[15 empty] | Regular reporting to Audit and Governance Committee | 1-May-2014 | Completed | 100% | Nigel Kennedy
[15 empty] | Training of staff to be carried out using ilearn and other forms such as MPG session | 31-Dec-2013 | In Progress | 50% | Nigel Kennedy
CRR-028 | Data Protection | Risk of breaching the Data Protection Act | T | Staff not being aware of the policy; being careless with data | Reputation; financial penalties | 1-Apr-2013 | Jacqui Yates | 4 | 3 | 3 | 3 | 3 | 2 |  | Obtain and retain Public Service Network compliance | 30-Oct-2013 | In Progress | 80% | Jane Lubbock
[15 empty] | Raise awareness and training of staff by the use of ilearn. | 31-Dec-2013 | In Progress | 50% | Jane Lubbock
[15 empty] | Raise awareness and training of staff, carrying out a session at MPG | 30-Jun-2013 | Completed | 100% | Jane Lubbock
[15 empty] | Review data protection policy | 30-Jun-2013 | Completed | 100% | Jane Lubbock
CRR-029 | Managerial Capacity | Managers become overstretched lose sight and focus on service delivery and performance suffers | T | Too many competing priorities, lack of capacity to deliver | Services are not delivered or not deliverd effectively. Additional costs are incurred by the council. Customers unrest with service delivery, higher complaints | 1-Apr-2013 | Peter Sloman | 4 | 3 | 4 | 2 | 3 | 3 |  | Ensure appropriate arrangements in place for prioritising work and allocating appropriate resources, and deprioritising other work | 31-Mar-2014 | In Progress | 80% | Simon Howick
[15 empty] | Ensure managers are adequately trained for the tasks in hand | 31-Mar-2014 | In Progress | 80% | Simon Howick
[15 empty] | Ensure sufficient financial and staffing resources for the tasks being undertaken | 31-Mar-2014 | In Progress | 80% | Simon Howick
Current Risk Score
This is the risk score at the time that the risk is reviewed. When the risk is first identified it will be the same as the gross risk score. The current risk score is tracked to
ensure that progress is being made to manage the risk and reduce the Council’s exposure.
Residual Risk Score
This is the risk score after mitigating actions have taken place. The residual risk score shows how effective your action plans are at managing the risk.