# Appendix B: Housing Strategy Risk Register – City Executive Board – 11th December 2013

| No. | Risk Description Link to Corporate Obj | Gross Risk | Cause of Risk | Mitigation | Net Risk | Further Management of Risk: Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Current Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Score Impact Score: 1 =Insignificant; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Catastrophic Probability Score: 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost Certain |
|  |  | I | P |  | Mitigating Control: Level of Effectiveness: (HML) | I | P | Action: Action Owner: Mitigating Control: Control Owner: | Outcome required: Milestone Date: | Q 1 ((( | Q 2((( | Q 3((( | Q4((( | I | P |
| 1. | Failure to meet the objectives of the Housing Strategy and Action Plan 2012 to 2015 | 4 | 3 | Ineffective monitoring of the strategic objective action plans. | Establish clear monitoring process within the Council’s structure through relevant Board, Scrutiny and Tenant Involvement Structures | 3 | 2 | •Tenant Scrutiny Panel now established •Local offer and Annual report for tenants •Housing Panel (sub-group of Scrutiny Committee) operating well •Internal governance and review from Housing Strategy Delivery Board and Housing Programme Board meetings |  |  |  |  |  |  |  |
| 2 | Changes to housing policy or context and, local, regional and national, making objectives invalid or inappropriate. | 3 | 3 | Economic circumstances, government policy and legislation, political changes. | In addition to regular monitoring, review of the strategy and objectives in 2013 to ensure it remains relevant to current circumstances. | 3 | 3 | Establish regular and robust monitoring arrangements for policy, context and legislative changes Housing Strategy and Enabling Manager | Mid point review completed by September 2013 |  |  |  |  |  |  |
| 3 | Negative public understanding/perceptions of Housing Strategy Objectives |  |  | Failure to communicate objectives and impacts on housing in Oxford. | Establish clear communication strategy for the housing strategy when it is adopted | 2 | 3 | On going communication and engagement of housing strategy objectives and in particular of individual projects and programmes. Strategy and Enabling manager. |  |  |  |  |  |  |  |