Risk Register.

| Risk ID | Risk | Corporate Objective | Gross Risk | Residual Risk | Current Risk | Owner | Date Risk Reviewed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Category-000-Service Area Code | Risk Title | Opportunity/Threat | Risk Description | Risk Cause | Consequence | Date raised | 1 to 6 | I | P | I | P | I | P |  |  |
| CEB-001-DS | Council Service Reputation | T | Customer dissatisfaction with the level of service provision. | Poor service planning and delivery | Loss of future business. Damaging to aspiration for World-Class service provision | 19/05/11 | 6 | 1 | 3 | 3 | 1 | 3 | 1 | JR | 01.12.11 |
| CEB-002-DS | Low demand for services | T | Not enough external income is achieved to meet budgetary requirements | Poor financial consideration, estimating and planning. Uncompetitive pricing. Legal constraints | Spare capacity not utilised. Income not achieved | 19/05/11 | 6 | 3 | 3 | 3 | 2 | 3 | 2 | JR | 01.12.11 |
| CEB-003-DS | Political | T | Charging for discretionary services - adverse opinion of Council from members of the public | Not clearly communicating the differentials of Statutory Services and Discretional Services | Assumption that Council is charging when provision is all encumbering in Council taxation | 19/05/11 | 2 | 2 | 4 | 2 | 3 | 2 | 4 | JR | 01.12.11 |
| CEB-004-DS | Service based on Ability to Pay | T | Socioeconomic accusations towards the Council | Some citizens able to afford extra service, others not | Discontent among communities. Accusations of unfairness | 19/05/11 | 2 | 2 | 4 | 2 | 2 | 2 | 2 | JR | 01.12.11 |

Risk Action Plan

| Risk ID | Risk Title | Action Owner | Accept, Contingency, Transfer, Reduce or Avoid | Details of Action | Key Milestone | Milestone Delivery Date | Date Reviewed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CEB-001-DS | Council Service Reputation | J. Ridgley | Reduce | Robust marketing plan Market assessment for all target areas of potential Business. Quick, sustained levels of query response and resolution. Commercially capable staff to lead on service delivery with ongoing monitoring of performance. Robust operational management protocols. | Marketing Plans in place; Market assessments for relevant opportunity; Monthly Performance review meetings with service providers; Review processes for customer focus. | July 2011 Annual & monthly | 19/05/11 |
| CEB-002-DS | Low demand for services | J. Ridgley | Reduce | Market USP’s; Expand existing (doing more of what we are good at); F2F customer liaison; Maintain business successes | Learn from early wins Trade Waste expansion/increase recycling Additional MOT provision | July 2011 | 19/05/11 |
| CEB-003-DS | Political | J. Ridgley | Reduce | Communication depicting Council offering choice; Communication is consistent and clearly define differences of Statutory and Discretionary; Clear communication on budgetary position | Consistent message from corporate centre on relevant press releases; Consistent script flow in contact centres | Monthly & Quarterly | 19/05/11 |
| CEB-004-DS | Service based on Ability to Pay | J. Ridgley | Reduce | Clear communication on budgetary position; Communication depicting Council offering choice; Offering individual income related concessions where possible | CRM System interfaced with Benefits systems; Consistent message from corporate centre on relevant press releases; Consistent script flow in contact centres | May 2011 Monthly & Quarterly | 19/05/11 |
| CEB-005-DS | Failure to recover costs through charges | J Ridgley | Reduce | Understand direct costs; good market information re demand and price elasticity; monitoring and adjusting price accordingly | Proposal sheet for each service line to be charged for signed of by Fianance and legal | July 2011, monthly reviews | 3/6/11 |