To: Scrutiny Finance Panel

Date: 8 October 2014

Report of: Scrutiny Panel Chair

Title: Scrutiny Review of the Medium Term Financial Strategy (MTFS) 2015-19

Summary and Recommendations Purpose of report: To propose to the Panel an outline scope and timetable for review of the MTFS for 2015 to 2019. Key decision: No Scrutiny Lead Member: Councillor Simmons Policy Framework: Effective, Efficient Council Recommendation(s): Comment on and agree the focus for the scrutiny budget review. Comment on and agree the process timetable. Set dates for: Initial meeting to identify extra information and questions – 11 December 2014 3 meetings with officers and Board Members – w/c 12 January 2015 Drafting recommendations – 21 Finance Panel meeting Review of final Budget Report – 4 February 2015

Introduction

- The draft budget and MTFS is schedule to be agreed at the City Executive Board (CEB) meeting on 17 December 2014.  The paperwork for this meeting will be published by 9 December 2014.

- The budget proposals are currently being developed via a review of all the grant assumptions, savings and efficiencies, challenges, pressures, reserves and contingencies agreed in the MTFS in February 2014.  The Head of Finance has advised that this exercise will involve a more detailed review of base budgets than in previous years.

- As in previous years, it is proposed that the scrutiny review process will begin once the consultation budget and MTFS is advertised for consultation.

Scope and Timetable

- The Chair recommends that the focus for the Panel is:

- Policy and schemes for allocating contingencies and earmarked reserves,

- Assumptions for grants and corporate challenges,

- Robustness of savings and efficiencies,

- Estimates for current and new income streams,

- Budget pressures and link to current spending,

- All proposals within the HRA and Business Plan,

- Whether the budget proposals support the City Council’s Corporate Plan.

- The Chair recommends that the Panel follow the process used in previous years, the outline and timing of this process is detailed in the table below.

| Stage | What happens | When |
| --- | --- | --- |
| Draft budget published | Consultation budget published in City Executive Board paperwork for 17 December meeting. | 9 December 2014 (by 5pm) |
| Scrutiny Members consulted | Request to all Scrutiny Councillors to highlight issues for consideration by the Finance Panel. | 10 December 2014 |
| Initial meeting to identify additional information and questions | Finance Panel members consider the information presented in the consultation budget, budget monitoring for 2014/15 and data on contingencies and decide: Extra information required Questions Housing Panel members are asked to contribute to housing questions. | 11 December 2014 |
| Information requests sent | Request for answers and information sent out to the organisation for response. | 15 December 2014 |
| City Executive Board meeting | Consultation Budget considered by City Executive Board. | 17 December 2014 |
| Scrutiny review meetings with Board Members and Senior Officers | 3 meetings: Executive Director City Regeneration and Housing plus appropriate Board Members and the Head of Service for Housing. Housing Panel Members to attend housing discussion. Executive Director Community Services plus appropriate Board Members. Executive Director Organisational Development and Corporate Services, Chief Executive and appropriate Board Members. Information gathered and responses to question used as the basis for discussions on budget proposals. Panel Members to hold a summary session at the end of each meeting to identify any final questions or requests. | Three dates in w/c 12 January 2015 Responses to information requests to be received no later than 3 days before these meetings Any final requests and questions out by 16 January 2015 |
| Draft recommendations agreed | Finance Panel members consider evidence gathered and agree draft recommendations. | 21 January 2015 Finance Panel meeting |
| Scrutiny report drafted | Scrutiny report drafted around agreed recommendation areas. | 21 January to 5 February 2015 |
| Final Budget Report published | Final Budget Report published in the paperwork for the 11 February City Executive Board meeting. | 3 February 2015 (by 5pm) |
| Final review meeting | Finance Panel Members consider any significant changes in the published Budget Report. | 4 February 2015 |
| Scrutiny report finalised | Any changes made following the final review meeting. | 4 February 2015 |
| Report out to Board Member for comment | Opportunity for Board Member to consider recommendations and make comment before consideration at the City Executive Board. | 5 February 2015 |
| Report circulated to all Scrutiny Members | Report circulated to all Scrutiny Councillors for consideration as it can’t be formally agreed at a Scrutiny Committee Meeting. | 5 February 2015 |
| Final report published | Panel report published as a supplement to the City Executive Board paperwork for 11 February CEB. | 6 February 2015 |
| Scrutiny report presented to City Executive Board | Councillor Simmons to present the scrutiny report. | 11 February 2015 CEB meeting |
| Scrutiny report and budget report considered by Council | Councillor Simmons to present the scrutiny report. | 18 February 2015 Council meeting |

- This timetable does not allow the final report to go to the City Executive Board via the Scrutiny Committee.  Instead it consults all scrutiny councillors at the questioning and final report stages.  This is acceptable within the operational arrangements agreed by the Scrutiny Committee.  The Scrutiny Committee will have an opportunity to discuss and agree the budget scrutiny process at its meeting on 10 November 2014.

Name and contact details of author:-

Name: Andrew Brown on behalf of the Chair of the Finance Scrutiny Panel

Job title: Scrutiny Officer

Service Area: Law and Governance

Tel: 01865 252230 e-mail: abrown2@oxford.gov.uk

List of background papers: None

Version number: 1