| Risk ID | Risk | Gross Risk | Residual Risk | Current Risk | Owner | Date Risk Reviewed |
| --- | --- | --- | --- | --- | --- | --- |
|  | Risk Title | Risk Description | Risk Cause | Consequence | Mitigating Action | Date raised | I | P | I | P | I | P |  |  |
| CEB-001-BT | Lack of Benchmark Data | Lack of reliable benchmark data to draw conclusions on council performance | Lack of capacity/other priorities to undertake benchmarking Lack of capacity or interest of other councils to participate Inability or uncertainty on how to obtain data from other sectors | Corporate Efficiency Review programme is based on incomplete evidence Benchmarking fails to incorporate a wider view of cross-sector performance | Performance Manager works with services to encourage full engagement with benchmarking clubs and other benchmarking activities alongside service planning and target-setting | 06/11/14 | 3 | 2 | 3 | 1 | 3 | 1 | JL |  |
| CEB-002-BT | Service Performance | Failure to adopt Framework will inhibit continued service improvement | Members disagree with principles of Framework and do not endorse it | Lack of clarity and coordination on direction of future improvement programme Uncertainty for services as to what is expected of them for improvement | Communications Plan developed to include all stakeholders in the principles and requirements set out within the Performance Improvement Framework | 06/11/14 | 2 | 2 | 2 | 1 | 2 | 1 | JL |  |
| CEB-003-BT | Software capabilities | Reliance on LG Inform as a data sharing tool | System is developed within limits of open source technology and meets needs of larger councils only | Unable to meet PIF commitment to share data via LG Inform Requirement to find alternative data hosting arrangement | Continue to use LGInform comparator data to inform the OBM ‘heatmap’ but also participate in a range of other benchmarking clubs | 06/11/14 | 3 | 4 | 2 | 3 | 2 | 3 | JL |  |
| CEB-004-BT | Corporate Efficiency Reviews | Corporate Efficiency Reviews do not deliver the savings and improvements required | Process is not sufficiently robust and challenging | Savings targets not achieved. Services fail to improve significantly | Robust governance and monitoring arrangements established for all key corporate projects | 06/11/11 | 3 | 3 | 3 | 2 | 3 | 2 | JL |  |