## CAMAC Report
Month |  | September
Capital Budget and Spend as at 30th September 2014 - Appendix 2
Cost Centre | Service Area | Capital Scheme | Project Sponsor | Project Manager | Total Budget | Spend over Previous 5 Years | Budget Allocated to Future Years | Original Budget 2014/15 | 2013/14 Year End carry forwards | Original Budget with carry forwards 2014/15 | Latest Budget 2014/15 | Profiled Budget 2014/15 | Spend to 30th Sept 2014 | Variance to Profiled Budget at 30th Sept 2014 | Projected Outturn at 30th Sept 2014 | Outturn Variance to Latest Budget | Outturn Variance due to Slippage | Outturn variance due to Over/ Under spend | RAG Status | Gateway Stage Completed | PID Required? | PID Received? | PID Approved by CAMAC | PM Comments
[5 empty] | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £
B0087 | S13 | Property Investment Strategy | David Edwards | Jane Winfield | 7000000 | 0 | 0 | 7000000 | 0 | 7000000 | 7000000 | 0 | 0 | 0 | 7000000 | 0 | 0 | 0 | 1 |  | No |  |  | Offer has been made to Landlord. Awaiting response.
B0077 | S13 | Direct Services Depots | Graham Bourton | Bruce Thompson | 404415 | 104616.5 | 236100 | 0 | 45383.5 | 45383.5 | 63698.5 | 56971.9384 | 63698.5 | 6726.5616 | 63698.5 | 0 | 0 | 0 | 1 |  | Yes | No | No | Phase 1 project closure statement now prepared for CAMAG
R0005 | S23 | MT Vehicles/Plant Replacement Programme. | Graham Bourton | Ian Bourton | 13304950.09 | 6583339.09 | 3730480 | 2731750 | 97381.04 | 2829131.04 | 2991131 | 958198.65 | 846203.42 | -111995.23 | 2991131 | 0 | 0 | 0 | 1 |  | No
T2270 | S23 | Bin Stores for Council Flats to Assist Recycling | Graham Bourton | Geoff Corps | 329158.04 | 329158.04 | 0 | 0 | 0 | 0 | 0 | 0 | 7832.96 | 7832.96 | 0 | 0 | 0 | 0 | 1 |  | No
T2273 | S23 | Car Parks Resurfacing | Graham Bourton | Roy Summers | 1430000 | 58270.13 | 1000000 | 350000 | 21729.87 | 371729.87 | 371729.87 | 185865 | 193706.48 | 7841.48 | 371729.87 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Change to original programme of works. Diamond Place will be deferred, Union Street brought forward
T2274 | S23 | Gloucester Green Car Park Waterproofing | Graham Bourton | Roy Summers | 100000 | 3311.9 | 0 | 0 | 96688.1 | 96688.1 | 96688.1 | 38675.2 | 0 | -38675.2 | 96688.1 | 0 | 0 | 0 | 1 |  | No
T2275 | S23 | MOT Service Bay Extension | Graham Bourton | Ian Bourton | 160000 | 109010 | 0 | 0 | 50990 | 50990 | 50990 | 50990 | 47538.01 | -3451.99 | 50990 | 0 | 0 | 0 | 1 |  | No
T2276 | S23 | Invest to Save - Bin Washing Service | Graham Bourton | Jeff Ridgely | 83000 | 0 | 0 | 83000 | 0 | 83000 | 83000 | 0 | 0 | 0 | 83000 | 0 | 0 | 0 | 1 |  | No |  |  | No commentary received, update from PM required.
T2277 | S23 | Food waste collection from flats | Graham Bourton | Jeff Ridgely | 486000 | 0 | 357000 | 129000 | 0 | 129000 | 129000 | 0 | 0 | 0 | 129000 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Project has started. Update on planned programme will be available by the end of Q3 after some data analysis has been completed.
T2279 | S23 | Leys Parking | Graham Bourton | Geoff Corps | 87000 | 0 | 0 | 87000 | 0 | 87000 | 87000 | 0 | 195 | 195 | 87000 | 0 | 0 | 0 | 3 |  | No
B0086 | S23 | Extension to Seacourt Park & Ride (Part of feasibility reports) | Graham Bourton | Nick Twigg | 2000000 | 0 | 1600000 | 400000 | 0 | 400000 | 400000 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 1 |  | Yes | No | No | Project at Feasibility Studies Stage. Slippage expected into 2015/16
F0011 | S23 | Pay & Display Parking in the Car Parks | Graham Bourton | Jason Munro | 151552.62 | 80338.62 | 0 | 0 | 71214 | 71214 | 71214 | 35607 | 21078.9 | -14528.1 | 71214 | 0 | 0 | 0 | 1 |  | No
F0012 | S23 | P & R Puchase of Capital Items - Peartree, Redbrid | Graham Bourton | Jason Munro | 99791.09 | 99791.09 | 0 | 0 | 0 | 0 | 0 | 0 | 4076.42 | 4076.42 | 0 | 0 | 0 | 0 | 1 |  | No
T2280 | S23 | Heavy Goods Vehicle Testing Facility | Graham Bourton | Ian Bourton | 160000 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 3 |  | Yes | No | No | Awaiting decision on planning application meeting to be held on 5 January 2014, if approval granted start on site 14 days after approval to due to call in period.
T2281 | S23 | Parking Opposite Blackbird Leys Pool | Graham Bourton | Shaun Hatton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | Planning has been granted trial bores are planned to be undertaken, start on site expected Monday 17 November with 80% completion before Christmas break, planning maybe an issue. Bills of Quantity have now been price contract price of £227k, Direct Services have agreed to absorb cost as only £200k allocated to project.
A1300 | S22 | Playground Refurbishment | Ian Brooke | Stuart Fitzsimmons | 3215223.8 | 3212065.8 | 0 | 0 | 4582.02 | 4582.02 | 3158 | 3158 | 3158 | 0 | 3158 | 0 | 0 | 0 | 1 |  | No |  |  | Main project complete. Residual budgets to be allocated further improvememts
A1301 | S22 | Play Barton | Ian Brooke | Stuart Fitzsimmons | 382167.57 | 382167.57 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | Main project complete. Residual budgets to be allocated further improvememts
A3129 | S22 | Donnington Recreation Ground Improvements | Ian Brooke | Stuart Fitzsimmons | 48125 | 3750 | 44375 | 0 | 44375 | 44375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | This is S106 monies which we still have to undertake feasibility on.
A4808 | S13 | Blackbird Leys LC Improvements | Ian Brooke | Lucy Cherry | 617479.76 | 489201.76 | 128278 | 128278 | 0 | 128278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | Scheme due to commence following the completion + 3 month period of the new pool development
A4810 | S22 | New Build Completion Pool | Ian Brooke | Mace (ext)/Hagan Lewisham (int) | 9479983.59 | 3567156.33 | 612500 | 5543900 | -131072.74 | 5412827.26 | 5300327.26 | 2140706.75 | 2802093.05 | 661386.3 | 5300327.26 | 0 | 0 | 0 | 1 | 4 | Yes | Yes | Yes | No commentary received. Update from PM required.
A4814 | S13 | Leisure Centre substantive repairs | Ian Brooke | Martin Shaw | 861269.58 | 540541.06 | 0 | 66000 | 254728.52 | 320728.52 | 320728.52 | 106898.8157 | 38389.71 | -68509.1057 | 320728.52 | 0 | 0 | 0 | 1 |  | No |  |  | £120K comitted to CSP. Remaining to cover defect works following handover to Fusion. Works in progress at Barton & Ferry Pools. Other works to be identified
A4815 | S22 | Leisure Centre Improvement Work | Ian Brooke | Hagan Lewisman | 724011.73 | 281019.38 | 0 | 447250 | -4257.65 | 442992.35 | 442992.35 | 110748 | 0 | -110748 | 442992.35 | 0 | 0 | 0 | 3 |  | Yes | No | No | Ferry Leisure Centre improvements are likely to slip to 2015/16 while new options are considered. Original plans for spin studio and soft play area at Ferry involved the removal of a squash court. Alternative improvement works retaining all existing squash courts are also being considered.
A4816 | S22 | Sports Pavilions | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 75000 | 0 | 75000 | 1201000 | 159279.54 | 1360279.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Grandpont and Blackbird Leys Pavilions are now completed. Direct Services are progressing works at Sandy Lane. Cutteslowe Pavilion is on hold to see if we can attain £200,000 in February for the Football Foundation.
A4816 Grandpont | S22 | Sports Pavilions - Grandpont | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 573000 | 0 | 0 | 0 | 0 | 0 | 573000 | 480000 | 483955 | 3955 | 573000 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Complete
A4816 BBL | S22 | Sports Pavilions - Blackbird Leys | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 469000 | 0 | 0 | 0 | 0 | 0 | 469000 | 280000 | 288267 | 8267 | 469000 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Complete
A4816 Cutteslowe | S22 | Sports Pavilions - Cutteslowe | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 460000 | 0 | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 0 | 0 | -460000 | -460000 | 0 | 1 |  | No |  |  | On hold to see if we can sucessfully bid for £200,000 funding in February from the Football Foundation
A4816 Sandy Lane | S22 | Sports Pavilions - Sandy Lane | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 142000 | 0 | 0 | 0 | 0 | 0 | 142000 | 50000 | 50000 | 0 | 142000 | 0 | 0 | 0 | 1 |  | Yes | Yes | No
A4816 Mace Fees | S22 | Sports Pavilions - Mace Fees | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 90000 | 0 | 0 | 0 | 0 | 0 | 90000 | 55000 | 58350 | 3350 | 90000 | 0 | 0 | 0 | 1 |  | No |  |  | n/a
A4816 Other | S22 | Sports Pavilions - Other | Ian Brooke | Mace (ext.)/Hagan Lewisham (into) | 25780 | 0 | 0 | 0 | 0 | 0 | 25780 | 6500 | 3700 | -2800 | 25780 | 0 | 0 | 0 | 1 |  | No |  |  | n/a
A4818 | S22 | Lye Valley & Chiswell Valley Walkways | Ian Brooke | Stuart Fitzsimmons | 124000 | 60000 | 0 | 0 | 64000 | 64000 | 64000 | 24000 | 0 | -24000 | 64000 | 0 | 0 | 0 | 1 |  | No |  |  | Both projects complete. Site inspections to be undertaken in December before paying the invoice.
A4820 | S22 | Upgrade Existing Tennis Courts | Ian Brooke | Hagan Lewisman | 202876.75 | 71707.87 | 60000 | 54000 | 17168.88 | 71168.88 | 71168.88 | 40292.25 | 26071.26 | -14220.99 | 71168.88 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | Remains on track
A4821 | S22 | Upgrade Existing Multi-Use Games Area | Ian Brooke | Hagan Lewisman | 268993.59 | 162316.59 | 48000 | 48000 | -1322.56 | 46677.44 | 58677 | 58677 | 68073 | 9396 | 58677 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | Remains on track
A4826 | S22 | Parks Works ( Fit trails etc) | Ian Brooke | Stuart Fitzsimmons | 353477.75 | 74301.75 | 100000 | 100000 | 25698.25 | 125698.25 | 179176 | 93544 | 120344.96 | 26800.96 | 179176 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | On target to complete by year end
A4827 | S22 | Cowley Outdoor Gym | Ian Brooke | Groundwork (ext) Stuart Fitzsimmons (int) | 70000 | 44944 | 0 | 0 | 25056 | 25056 | 25056 | 6264 | 0 | -6264 | 25056 | 0 | 0 | 0 | 1 |  | No |  |  | Complete
A4828 | S22 | Valentia Road Playground | Ian Brooke | Stuart Fitzsimmons | 10000 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 2500 | 10000 | 7500 | 10000 | 0 | 0 | 0 | 1 |  | No |  |  | Drainage works complete. Some minor landscaping to be undertaken in 2015
A4829 | S22 | Oxford Spires Academy | Ian Brooke | MTP (external) Margaret Stevens (int) | 500000 | 0 | 350000 | 500000 | 0 | 500000 | 150000 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | No commentary received. Update from Project Manager required.
A4830 | S22 | Develop new burial space | Ian Brooke | Trevor Jackson | 1000000 | 0 | 950000 | 300000 | 100000 | 400000 | 50000 | 14750 | 7980 | -6770 | 30000 | -20000 | -20000 | 0 | 3 |  | Yes | Yes | No | No commentary received. Update from Project Manager required.
A4831 | S22 | Three Artificial Turf Cricket Wickets | Ian Brooke | Phil Jones | 12000 | 0 | 12000 | -24000 | 36000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | No
A4835 | S22 | Biomass store at Cutteslowe Park to supply new pool | Ian Brooke | Stuart Fitzsimmons | 55000 | 0 | 0 | 90000 | 0 | 90000 | 55000 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 2 |  | No |  |  | Feasibility studies to be completed
B0033 | S13 | Community Centres (Backlog R&M) | Ian Brooke | Mark Spriggs | 1741270.4 | 385891.48 | 901520 | 313420 | 225582.92 | 539002.92 | 453858.92 | 110060.7881 | 80083.96 | -29976.8281 | 180000 | -273858.92 | -273858.92 | 0 | 1 |  | Yes | No | No | Minimal repairs being carried out this year, awaiting strategic review of community centres to determine future spend. Slippage expected into 2015/16
B0048 | S13 | Leisure Cemeteries | Ian Brooke | Trevor Jackson | 114855.89 | 92758.89 | 19097 | 0 | 0 | 0 | 3000 | 3000 | 8381.8 | 5381.8 | 3000 | 0 | 0 | 0 | 1 |  | No |  |  | combine with A4830
B0050 | S13 | Leisure - Depots | Ian Brooke | TBA | 133750.77 | 71190.77 | 18760 | 0 | 43800 | 43800 | 43800 | 0 | 0 | 0 | 43800 | 0 | 0 | 0 | 2 |  | No |  |  | No commentary received. Update from PM required.
B0067 | S13 | Fencing Repairs across the City | Ian Brooke | Stuart Fitzsimmons | 450051.78 | 304044.61 | 0 | 150000 | -3992.83 | 146007.17 | 146007.17 | 35406.7387 | 30062.27 | -5344.4687 | 146007.17 | 0 | 0 | 0 | 2 |  | Yes | Yes | No | On target for completion by year end.
B0079 | S13 | Street Sports Sites | Ian Brooke | Hagan Lewisman | 18830 | 0 | 10720 | 0 | 8110 | 8110 | 8110 | 0 | 0 | 0 | 8110 | 0 | 0 | 0 | 2 |  | No |  |  | Budget to be added to A4821 (Multi-use games areas)
B0085 | S13 | Parks & Leisure Toilets | Ian Brooke | Neil Smith | 9200 | 0 | 0 | 9200 | 0 | 9200 | 9200 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 2 |  | No |  |  | Works to be agreed at Cutteslowe Park
F7012 | S11 | Rose Hill Recreation Ground Improvements | Ian Brooke | Part of wider rose Hill project | 3300 | 0 | 0 | 3300 | 0 | 3300 | 3300 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 1 |  | No |  |  | Works under way - due for completion 04/12/14
F7022 | S11 | Sunnymeade Park - Enhancement of Play Area Facilities | Ian Brooke | Ian Haynes | 1830 | 0 | 0 | 1830 | 0 | 1830 | 1830 | 0 | 0 | 0 | 1830 | 0 | 0 | 0 | 1 |  | No |  |  | S106 funds to add to Parks programme of works
G1013 | S22 | Dawson Street Gardens | Ian Brooke | No Scheme in place | 19000 | 0 | 0 | 0 | 19000 | 19000 | 19000 | 0 | 0 | 0 | 0 | -19000 | 0 | -19000 | 1 |  | No |  |  | To be removed from Capital Programme
G3015 | S22 | NE Marston Croft Road Recreation Ground | Ian Brooke | Mike Scott | 25000 | 5700 | 0 | 0 | 19300 | 19300 | 19300 | 0 | 0 | 0 | 19300 | 0 | 0 | 0 | 2 |  | No |  |  | No commentary received. Update from PM required.
G3017 | S22 | South Oxford Community Centre Café | Ian Brooke | Paul Atkins | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 2 |  | No |  |  | Awaiting community association feedback on latest design. Project intended to be part funded by the association. Latest costs circa £190k.
B0065 | S13 | Parks & Cemetery - Masonry Walls & Path Improvements | Ian Brooke | Neil Smith | 119926 | 85627.68 | 0 | 40000 | -5701.68 | 34298.32 | 34298.32 | 0 | 14148 | 14148 | 34298.32 | 0 | 0 | 0 | 1 |  | No
G6013 | S01 | Superconnected Cities | Jane Lubbock | Gerrard Barker | 4989000 | 15716.22 | 0 | 4675000 | 298283.78 | 4973283.78 | 4973283.78 | 100000 | 123881.3 | 23881.3 | 1300000 | -3673283.78 | -500000 | -3173283.78 | 3 |  | Yes | Yes | No | Concession project is being re-scoped. This is reflected in the forecast position.
C3039 | S03 | ICT Infrastructure | Jane Lubbock | Paul Fleming | Rolling Programme | 2075763.52 | 200000 | 100000 | -71878.67 | 28121.33 | 79392.33 | 20641.92 | 25766.87 | 5124.95 | 79392.33 | 0 | 0 | 0 | 3 |  | No |  |  | No commentary received. Update from Project Manager required.
C3044 | S03 | Software Licences | Jane Lubbock | Paul Fleming | 1012045.88 | 343968.88 | 504000 | 177000 | -2402 | 174598 | 164077 | 164077 | 164077 | 0 | 164077 | 0 | 0 | 0 | 1 |  | No |  |  | Rolling Programme
C3045 | S03 | Mobile Working | Jane Lubbock | Paul Fleming | 98000 | 5168.32 | 0 | 0 | 92831.68 | 92831.68 | 92831.68 | 69624 | 6930 | -62694 | 92831.68 | 0 | 0 | 0 | 1 |  | No
C3046 | S03 | System Integration Capability | Jane Lubbock | Paul Fleming | 12000 | 12000 | 0 | 0 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
C3047 | S03 | Oracle 11g Upgrade | Jane Lubbock | Paul Fleming | 25000 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 1 |  | No
C3048 | S03 | Server 2008 Upgrade for Idox | Jane Lubbock | Paul Fleming | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
C3049 | S03 | Source Code Management | Jane Lubbock | Paul Fleming | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
C3050 | S03 | Tree Management Software | Jane Lubbock | Paul Fleming | 14250 | 14250 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
C3053 | S03 | New Council website in Drupal | Jane Lubbock | Paul Fleming | 110000 | 0 | 15000 | 15000 | 0 | 15000 | 95000 | 0 | 7386.8 | 7386.8 | 95000 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | No commentary received. Update from Project Manager required.
C3054 | S03 | Purchase of web service (API's) | Jane Lubbock | Paul Fleming | 84000 | 0 | 0 | 71000 | 0 | 71000 | 84000 | 3360 | 0 | -3360 | 84000 | 0 | 0 | 0 | 1 |  | No
B0003 | S13 | Roof Repairs & Ext Refurbishment 44-46 George St | Jane Winfield | Michael Stewart | 29923 | 2923 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 0 | 0 | 27000 | 0 | 0 | 0 | 2 |  | No |  |  | Awaiting confirmation of RAMP strategy
B0027 | S13 | Covered Market - Improvements & Upgrade to Roof | Jane Winfield | Michael Stewart | 78928.69 | 26835.54 | 0 | 0 | 52093.15 | 52093.15 | 52093.15 | 0 | 88.26 | 88.26 | 52093.15 | 0 | 0 | 0 | 2 |  | No
B0028 | S13 | Covered Market - New Roof Structures to High St Entrances | Jane Winfield | Michael Stewart | 115000 | 13886.29 | 0 | 100000 | 1113.71 | 101113.71 | 101113.71 | 33701.1995 | 9697.92 | -24003.2795 | 101113.71 | 0 | 0 | 0 | 2 |  | Yes | No | No | Detailed design near completion and revised cost estimate to be undertaken.
B0036 | S13 | Investment - Covered Market | Jane Winfield | Michael Stewart | 573194.36 | 248146.07 | 75000 | 150000 | 100048.29 | 250048.29 | 250048.29 | 18578.5879 | 34938.8 | 16360.2121 | 250048.29 | 0 | 0 | 0 | 2 |  | Yes | No | No | Various projects ongoing. Budget committed but some carry over to 2015-16 is expected.
B0037 | S23 | Car Parks | Jane Winfield | Jason Munro | 438793.37 | 248793.37 | 110000 | 0 | 0 | 0 | 80000 | 32000 | 26045.48 | -5954.52 | 80000 | 0 | 0 | 0 | 1 |  | No |  |  | Work on target with agreed programme for 14/15
B0040 | S13 | Investment - Broad Street | Jane Winfield | Michael Stewart | 303896.03 | 155186.63 | 51200 | 127280 | -29770.6 | 97509.4 | 97509.4 | 24377.35 | 601.68 | -23775.67 | 97509.4 | 0 | 0 | 0 | 2 |  | No |  |  | Comprises four projects in Broad Street. All currently on track to complete this financial year.
B0041 | S13 | Investment - Misc City Centre Properties | Jane Winfield | Ian Gordon | 52150.51 | 15829.74 | 24000 | 10000 | 2320.77 | 12320.77 | 12320.77 | 0 | 1231.42 | 1231.42 | 12320.77 | 0 | 0 | 0 | 2 |  | No
B0043 | S13 | Investment George Street | Jane Winfield | Richard Davison | 180368 | 1568 | 77800 | 50500 | 50500 | 101000 | 101000 | 0 | 0 | 0 | 101000 | 0 | 0 | 0 | 1 |  | Yes | No | No | Window replacements for 33-36 George Street. Costs received from Direct Services over £100K therefore independent view on cost being sought.
B0044 | S13 | Investment - Outer City | Jane Winfield | Philip Yerburgh | 413759.42 | 28751.68 | 337800 | 38600 | 8607.74 | 47207.74 | 47207.74 | 0 | 0 | 0 | 47207.74 | 0 | 0 | 0 | 3 |  | No |  |  | This relates to the Enterprise centre. Works are being discussed but no PID will be required as the budget is under £100,000
B0045 | S13 | Investment - St. Michael’s Street | Jane Winfield | Michael Stewart | 33647 | 27611.59 | 0 | 0 | 6035.41 | 6035.41 | 6035.41 | 0 | 0 | 0 | 6035.41 | 0 | 0 | 0 | 1 |  | No
B0046 | S13 | Investment - Ship Street | Jane Winfield | Michael Stewart | 76220 | 4997.9 | 0 | 65720 | 5502.1 | 71222.1 | 71222.1 | 0 | 950 | 950 | 71222.1 | 0 | 0 | 0 | 1 |  | No
B0052 | S13 | Miscellaneous Properties | Jane Winfield | Michael Stewart | 80937 | 56712.08 | 14360 | 0 | 9864.92 | 9864.92 | 9864.92 | 9865 | 23950.11 | 14085.11 | 9864.92 | 0 | 0 | 0 | 1 |  | No
B0072 | S13 | 23-25 Broad Street | Jane Winfield | Ian Gordon | 350000 | 37604.45 | 0 | 300000 | 12395.55 | 312395.55 | 312395.55 | 75755.9209 | 200977.47 | 125221.5491 | 312395.55 | 0 | 0 | 0 | 1 |  | No |  |  | Works complete final account being agreed.
B0073 | S13 | Clearing Channels under Frideswide Bridge | Jane Winfield | Steve Smith | 5000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 2 |  | No
B0078 | S13 | Allotments | Jane Winfield | Stuart Fitzsimmons | 61350 | 0 | 44650 | 13700 | 3000 | 16700 | 16700 | 0 | 0 | 0 | 16700 | 0 | 0 | 0 | 2 |  | No
B0080 | S13 | Templars Square Refurbishment/Relocation | Jane Winfield | Martin Shaw | 23829.03 | 9533.32 | 0 | 115000 | 25466.68 | 140466.68 | 14295.71 | 14296 | 14295.71 | -0.29 | 14295.71 | 0 | 0 | 0 | 1 |  | No
B0081 | S23 | Car Parking Oxpens | Jane Winfield | Roy Summers | 3300000 | 158040.57 | 0 | 3000000 | 141959.43 | 3141959.43 | 3141959.43 | 1519765.57 | 1126198.15 | -393567.42 | 3141959.43 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Scheme on target, delays in getting contract signed for Decking Contractor, payment could not be made.
B0088 | S13 | Barns Road Car Park | Jane Winfield | Mike Scott | 128254.23 | 0 | 0 | 80000 | 128254.23 | 208254.23 | 128254.23 | 0 | 0 | 0 | 128254.23 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | Project progressing well landlord has made cash settlement offer at £450k against our consultants response at £250k
G3018 | S22 | St Ebbes Deaf and Hard of Hearing Centre | Jane Winfield | TBA | 50000 | 0 | 0 | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 2 |  | No
M5015 | S13 | Old Fire Station | Jane Winfield | Martin Shaw | 4063552.76 | 4062754.76 | 0 | 0 | 0 | 0 | 798 | 798 | 798 | 0 | 798 | 0 | 0 | 0 | 1 |  | No
T2269 | S23 | Toilet improvements | Jane Winfield | Geoff Corps | 509055.18 | 328835.59 | 0 | 170000 | 10219.59 | 180219.59 | 180219.59 | 38026.42 | 30152.25 | -7874.17 | 180219.59 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | On Target with works programme
E3511 | S12 | Renovation Grants | John Copley | Ian Wright | Rolling Programme | 141354.7 | 150000 | 50000 | 6313.43 | 56313.43 | 56313.43 | 28156.48 | 18483.86 | -9672.62 | 56313.43 | 0 | 0 | 0 | 1 |  | No |  |  | Discretionary grants being managed in case required for DFG overspend.
E3521 | S12 | Disabled Facilities Grants | John Copley | Ian Wright | Rolling Programme | 3306081.76 | 1920000 | 640000 | -5456.23 | 634543.77 | 634543.77 | 317271.98 | 286169.67 | -31102.31 | 634543.77 | 0 | 0 | 0 | 1 |  | No |  |  | Possible overspend flagged earlier in year - being managed and possibly using any underspend in E3511 (Renovation Grants)
E3554 | S12 | Additional SALIX Plus funding | John Copley | Jo Colwell | 600000 | 0 | 400000 | 200000 | 0 | 200000 | 200000 | 0 | 0 | 0 | 300000 | 100000 | 100000 | 0 | 1 |  | No
E3555 | S12 | Flood Alleviation at Northway & Marston | John Copley | John Copley | 1700000 | 0 | 1400000 | 300000 | 0 | 300000 | 300000 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 2 |  | Yes | Yes | No | Project dependant on external funding and risk of not delivering is high. Some slippage expected into 2015/16
E3556 | S12 | Additional CCTV to Speedwell street | John Copley | Richard Adams | 40000 | 0 | 0 | 40000 | 0 | 40000 | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 1 |  | No |  |  | Tendering process started in November.
F0015 | S12 | Cycle Oxford | John Copley | Jo Colwell/Mai Jarvis | 366999.28 | 14952.28 | 79206 | 240503 | 61544.24 | 302047.24 | 272841 | 50805.75 | 24830 | -25975.75 | 272841 | 0 | 0 | 0 | 2 |  | Yes | Yes | No | Cycle City is a programme of projects. Budget has now been allocated to each project.
G6014 | S12 | CCTV Project | John Copley | Richard Adams | 25000 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 1 |  | No |  |  | Consideration of suite upgrade and cameras in the St Clements area. To be started after Speedwell St project finishes (E3556).
G6015 | S12 | CCTV Rosehill Parade | John Copley | Richard Adams | 18000 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 1 |  | No
F1323 | S11 | Bridge Over Fiddlers Stream | Michael Crofton-Briggs | Steve Smith | 409031.04 | 181015.04 | 228016 | 70000 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | No |  |  | Awaiting new agreement with landowner before commencing
F6013 | S11 | Bullingdon Community Centre - Facility Enhancements | Michael Crofton-Briggs | Lorriane Freeman | 30000 | 29105.27 | 0 | 0 | 894.73 | 894.73 | 894.73 | 0 | 0 | 0 | 894.73 | 0 | 0 | 0 | 1 |  | No
F7006 | S11 | Work of Art - Littlemore | Michael Crofton-Briggs | Lorriane Freeman | 1693 | 133 | 0 | 0 | 1560 | 1560 | 1560 | 780 | 825 | 45 | 1560 | 0 | 0 | 0 | 1 |  | No
F7007 | S11 | Woodfarm / Headington Community Centre - Improvements | Michael Crofton-Briggs | Lorriane Freeman | 19887 | 0 | 19887 | 19887 | 0 | 19887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
F7008 | S11 | Landscaping Work at Lamarsh Road | Michael Crofton-Briggs | Stewart Thorpe | 17924 | 16892.44 | 0 | 0 | 1031.56 | 1031.56 | 1031.56 | 0 | 0 | 0 | 1031.56 | 0 | 0 | 0 | 1 |  | No
F7009 | S11 | CCTV Gipsy Lane Campus | Michael Crofton-Briggs | Karen Crossan | 60000 | 0 | 60000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | S106 funds, will not be started until items E3556 and G6014 have been completed.
F7011 | S11 | Headington Environmental Improvements | Michael Crofton-Briggs | Stewart Thorpe | 60000 | 0 | 0 | 60000 | 0 | 60000 | 60000 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 1 |  | No
F7019 | S11 | Work of Art Rose Hill | Michael Crofton-Briggs | Lorriane Freeman | 14310.17 | 12022.17 | 2288 | 0 | 2288 | 2288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No |  |  | S106 Funding to be drawn down
F7020 | S11 | Work of Art Shotover View | Michael Crofton-Briggs | Lorriane Freeman | 14635 | 0 | 14635 | 14635 | 0 | 14635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
F7023 | S11 | Templars Square Public Safety Measures | Michael Crofton-Briggs | Lorriane Freeman | 14512 | 0 | 0 | 10000 | 0 | 10000 | 14512 | 14512 | 14511.98 | -0.02 | 14512 | 0 | 0 | 0 | 1 |  | No
F7024 | S11 | St Clements Environmental Improvements | Michael Crofton-Briggs | Lorriane Freeman | 50000 | 0 | 50000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | No
M5014 | S11 | West End Partnership | Michael Crofton-Briggs | Michael Crofton Briggs | 2025749.3 | 1355749.3 | 335000 | 217225 | 0 | 217225 | 335000 | 0 | 0 | 0 | 335000 | 0 | 0 | 0 | 1 |  | No |  |  | Contribution towards Frideswide Square
B0074 | S32 | R & D Feasibility Fund | Nigel Kennedy | Jonathan Marks | 550000 | 1106.81 | 300000 | 125000 | 123893.19 | 248893.19 | 248893.19 | 0 | 3300 | 3300 | 248893.19 | 0 | 0 | 0 | 1 |  | No |  |  | £100K allocated to fund Redbridge P&R feasibility studies.
C3051 | S32 | Veriscan Solution, Identity Authentication Solution | Nigel Kennedy | Scott Warner | 20000 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 20000 | 10765 | -9235 | 20000 | 0 | 0 | 0 | 1 |  | No |  |  | Installation of 5 scanners complete, software upgrade imminent.
C3052 | S32 | Fraud Solutions and Data Warehouse | Nigel Kennedy | Scott Warner | 53000 | 0 | 12000 | 41000 | 0 | 41000 | 41000 | 20000 | 0 | -20000 | 41000 | 0 | 0 | 0 | 1 |  | No |  |  | DCLG funding approved, specification to be finalised in Jan 15.
B0075 | S01 | Stage 2 Museum of Oxford Development | Peter McQuitty | Ceri Gorton | 496999.94 | 62609.94 | 407190 | 0 | 0 | 0 | 27200 | 0 | 0 | 0 | 27200 | 0 | 0 | 0 | 2 |  | Yes | Yes | No | PID sent 30/09/14. HLF bid for £2m match funding due to be submitted 14/11/14 with decision due in March 2015.
B0054 | S13 | Town Hall | Simon Howick | Richard Davison | 1113589.54 | 638056.36 | 105000 | 280000 | 115533.18 | 395533.18 | 370533.18 | 185266.59 | 245414.32 | 60147.73 | 370533.18 | 0 | 0 | 0 | 1 |  | Yes | Yes | No | Works to toilets complete. Two further projects underway.
B0068 | S13 | Town Hall - Conference System Refurbishment | Simon Howick | Richard Davison | 399988.03 | 118228.81 | 180000 | 266611 | 15148.22 | 281759.22 | 101759.22 | 8944.6354 | 7774.5 | -1170.1354 | 101759.22 | 0 | 0 | 0 | 1 |  | Yes | No | No | Conference system tender evaluation being carried out. Project to start during January 2015.
B0076 | S13 | Town Hall 30s extn refurb | Simon Howick | Richard Davison | 438000 | 171104.44 | 0 | 50000 | 98895.56 | 148895.56 | 266895.56 | 228836.2531 | 249435.84 | 20599.5869 | 266895.56 | 0 | 0 | 0 | 1 | 4 | Yes | Yes | Yes | Works complete final account being agreed
B0089 | S13 | Council Chamber Conference System | Simon Howick | Ian Gordon | 75000 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 1 |  | No |  |  | Project cancelled
B0090 | S13 | St Aldates Chambers Security | Simon Howick | Chris Ridges | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 1 |  | No |  |  | All orders placed and project to start on site by end of January 2015.
B0082 | S13 | Garages | Stephen Clarke | Phil Allmond | 351000 | 123279.62 | 117000 | 117000 | -6279.62 | 110720.38 | 110720.38 | 55360.19 | 63692.06 | 8331.87 | 110720.38 | 0 | 0 | 0 | 1 |  | No |  |  | Rolling Programme
M5020 | S13 | Empty Homes CPO Revolving Fund | Stephen Clarke | David Scholes | 750000 | 0 | 500000 | 250000 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | -250000 | -250000 | 0 | 1 |  | No |  |  | Project slipped to 2015/16
M5021 | S13 | Equity Loan Scheme for Teachers | Stephen Clarke | Steve Northey | 600000 | 0 | 450000 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 2 |  | No |  |  | Awaiting uptake by eligiable workers
N5019 | S22 | Property Acquisitions | Stephen Clarke | David Scholes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | No |  |  | On track for £1m spend by end of 14/15. 1st property acquired 16/12/14. 2 units in the pipeline. Last one being actively searched for
|  | General Fund Sub-Total |  |  | 75769743.56 | 31268790.37 | 18437862 | 32270589 | 2700282.2 | 34970871.2 | 34651540.7 | 8002614.9779 | 8000557.15 | -2057.8279 | 30055398 | -4596142.7 | -1403858.92 | -3192283.78
B0034 | S24 | Rose Hill Community Centre | Ian Brooke | Clarkson Alliance (ext)/Nick Twigg (int) | 4327461.98 | 249227.98 | 0 | 3994300 | 83934 | 4078234 | 4078234 | 50000 | 71741.45 | 21741.45 | 4078234 | 0 | 0 | 0 | 1 | 2 | Yes | Yes | No | Contractors expected on site November 2014. Foundations will be laid and main structure should be constructed by 31st March 2015
N7035 | S24 | Rose Hill Drainage | Ian Brooke | Ian Haynes | 40000 | 0 | 0 | 40000 | 0 | 40000 | 40000 | 40000 | 40000 | 0 | 40000 | 0 | 0 | 0 | 2 |  | No
N7030 | S24 | Horspath Road Depot | Jane Winfield | Mike Scott | 1488000 | 0 | 0 | 1538000 | 0 | 1538000 | 1488000 | 1488000 | 1475159.4 | -12840.6 | 1488000 | 0 | 0 | 0 | 1 | 4 | Yes | No | No | Acquisition of Land and Building now completed. Capital Programme Management Group requested to review if PID required.
N6384 | S24 | Tower Blocks | Stephen Clarke | EC Harris (ext)/Jack Bradley (int) | 16451436 | 630610.69 | 15541825.31 | 279000 | 0 | 279000 | 279000 | 209250 | 237812 | 28562 | 279000 | 0 | 0 | 0 | 1 | 2 | Yes | Yes | Yes | Project on schedule, on budget and out to tender.
N6385 | S24 | Adaptations for disabled | Stephen Clarke | Bruce Thompson | Rolling Programme | 4203354.57 | 1987000 | 615000 | 0 | 615000 | 559091 | 261430.96 | 276401.33 | 14970.37 | 559091 | 0 | 0 | 0 | 1 |  | No |  |  | No issues at present
N6386 | S24 | Structural | Stephen Clarke | Jonathan Gould | Rolling Programme | 681752.41 | 404000 | 128000 | 0 | 128000 | 128000 | 51200 | 39769.38 | -11430.62 | 128000 | 0 | 0 | 0 | 1 |  | No |  |  | Day to Day budget for major structural works
N6387 | S24 | Controlled Entry | Stephen Clarke | Jonathan Gould | Rolling Programme | 849029.11 | 679000 | 215000 | 0 | 215000 | 215000 | 0 | 0 | 0 | 215000 | 0 | 0 | 0 | 1 |  | No |  |  | Contract has been placed and materials on order. Works to start on site early January 2015. CDM-C in place.
N6388 | S24 | Major Voids | Stephen Clarke | Sean Fry | Rolling Programme | 3670045.83 | 2513000 | 841000 | 0 | 841000 | 668636 | 312654.19 | 235873.98 | -76780.21 | 668636 | 0 | 0 | 0 | 1 |  | No |  |  | The Capital % element of major works has significantly reduced over the past few years, now running at 70/30 split. The revenue element of this HRA budget is showing an overspend but these 2 budget lines are on profile.
N6389 | S24 | Damp-proof works (K&B) | Stephen Clarke | Jonathan Gould | Rolling Programme | 414683.46 | 291000 | 92000 | 0 | 92000 | 92000 | 24840 | 43440.1 | 18600.1 | 92000 | 0 | 0 | 0 | 1 |  | No |  |  | Ad hoc damp prooofing works
N6390 | S24 | Kitchens & Bathrooms | Stephen Clarke | Bruce Thompson | Rolling Programme | 15155366.64 | 5764000 | 2163000 | 0 | 2163000 | 2797529 | 1174962.18 | 1207895.09 | 32932.91 | 2797529 | 0 | 0 | 0 | 1 |  | No |  |  | Slippage is possible due to undertaking other large scale projects, meeting has been held to review outstanding units for 2014/15. Contracts team to issue Finance revised profile for remaining months.
N6391 | S24 | Heating | Stephen Clarke | Sean Fry | Rolling Programme | 6484941.79 | 4594000 | 1457000 | 0 | 1457000 | 1603388 | 853002.42 | 855945.74 | 2943.32 | 1603388 | 0 | 0 | 0 | 1 |  | No |  |  | Team have caught up with programme, on target with agreed number of units for 2014/15
N6392 | S24 | Roofing | Stephen Clarke | Jonathan Gould | Rolling Programme | 571558.87 | 486000 | 154000 | 0 | 154000 | 304000 | 165801.6 | 213304.29 | 47502.69 | 354000 | 50000 | 0 | 0 | 1 |  | No |  |  | Project currently proceeding within projected timescales. Virement requested from windows project.
N6393 | S24 | External Doors | Stephen Clarke | Jonathan Gould | Rolling Programme | 564130.88 | 646000 | 205000 | 0 | 205000 | 205000 | 0 | 0 | 0 | 105000 | -100000 | 0 | 0 | 1 |  | No |  |  | Works intended to be procured from an existing framework agreement contract. Procurement preparing report for Director sign-off. Contract still intended to be passed to Direct Services for installation starting early 2015.
N6394 | S24 | Windows | Stephen Clarke | Jonathan Gould | Rolling Programme | 1301927.81 | 808000 | 256000 | 0 | 256000 | 106000 | 34386.4 | 5477.85 | -28908.55 | 56000 | -50000 | 0 | 0 | 2 |  | No |  |  | Works intended to be procured from an existing framework agreement contract. Procurement preparing report for Director sign-off. Virement to Kitchens & Bathrooms requested
N6395 | S24 | Electrics | Stephen Clarke | Jonathan Gould | Rolling Programme | 954065.63 | 2007000 | 744000 | 0 | 744000 | 347662 | 146018.04 | 190386.62 | 44368.58 | 347662 | 0 | 0 | 0 | 1 |  | No |  |  | Budget allocation for HRA dwellings, team have been asked to undertake work in communal areas. Bruce Thompson to speak to Jonathan Gould about transferring these costs to N7020, otherwise the agreed number of dwelling units cannot be achieved in this year.
N7020 | S24 | Extensions & Major Adaptions | Stephen Clarke | Jonathan Gould | Rolling Programme | 594181.22 | 969000 | 308000 | 0 | 308000 | 308000 | 0 | -14578.31 | -14578.31 | 408000 | 100000 | 0 | 0 | 1 |  | Yes | No | No | Fairfax Avenue awaiting tender awared. 3 other addresses awaiting pricing and mobilisation / planning
N7026 | S24 | Communal Areas | Stephen Clarke | Jonathan Gould | Rolling Programme | 124744.48 | 486000 | 154000 | 0 | 154000 | 154000 | 78540 | 54236.69 | -24303.31 | 154000 | 0 | 0 | 0 | 1 |  | No |  |  | Further FRA works completed and works to be programmed
N7027 | S24 | Environmental Improvements | Stephen Clarke | Jonathan Gould | Rolling Programme | 102375.6 | 323000 | 103000 | 60000 | 163000 | 103000 | 33990 | 22488.28 | -11501.72 | 103000 | 0 | 0 | 0 | 1 |  | No |  |  | Contracts in place works to start Nov 2014
N7029 | S24 | HCA New Build | Stephen Clarke | EC Harris (ext)/A Shaw (int) | 17011006.58 | 3082672.89 | 827000 | 12657000 | 444333.69 | 13101333.69 | 13101333.69 | 6714667 | 3949730.65 | -2764936.35 | 13265333.69 | 164000 | 0 | 0 | 2 |  | Yes | Yes | No | This programme has slipped (4 - 6 weeks), talks are ongoing with the contractor to bring it back on time. The overall budget is requested to be increased from the digital inclusion project budget.
N7031 | S24 | Homes at Barton | Stephen Clarke | EC Harris (ext)/Alan Wylde (int) | 11482561.44 | 40561.44 | 11338000 | 104000 | 0 | 104000 | 104000 | 52000 | 35722.3 | -16277.7 | 104000 | 0 | 0 | 0 | 3 |  | Yes | Yes | No | No commentary received. Update from Project Manager required.
N7032 | S24 | Great Estates: Estate Enhancements and Regeneration | Stephen Clarke | Martin Shaw, Jonathan Gould, Fiona Piercy | 4910694.24 | 741461.24 | 3232000 | 1025000 | -41461.24 | 983538.76 | 937233 | 356773.66 | 298553.83 | -58219.83 | 937233 | 0 | 0 | 0 | 3 |  | Yes | No | No | No commentary received. Update from Project Manager required.
N7033 | S24 | Energy Efficiency Initiatives | Stephen Clarke | Deborah Haynes | 1321000 | 0 | 808000 | 513000 | 0 | 513000 | 513000 | 0 | 2178 | 2178 | 513000 | 0 | 0 | 0 | 1 |  | Yes | Yes | Yes | Project now undertaking Structural, Asbestos checks. Electrical updates required for Phase 1 installs
N7036 | S24 | Food Waste Collection | Stephen Clarke | Geoff Corps | 155000 | 0 | 42000 | 113000 | 0 | 113000 | 113000 | 0 | 0 | 0 | 113000 | 0 | 0 | 0 | 1 |  | Yes | No | No | No commentary. Update from PM required.
N7034 | S24 | Digital Inclusion | TBA Helen or Peter McQ | TBA | 164000 | 0 | 0 | 164000 | 0 | 164000 | 164000 | 0 | 0 | 0 | 0 | -164000 | 0 | 0 | 3 |  | No |  |  | Project Suspended
|  | HRA Sub-Total |  |  | 57351160.24 | 40416692.54 | 53745825.31 | 27862300 | 546806.45 | 28409106.45 | 28409106.69 | 12047516.45 | 9241538.67 | -2805977.78 | 28409106.69 | 0 | 0 | 0
|  | Grand Total |  |  | 133120903.8 | 71685482.91 | 72183687.31 | 60132889 | 3247088.65 | 63379977.65 | 63060647.39 | 20050131.4279 | 17242095.82 | -2808035.6079 | 58464504.69 | -4596142.7 | -1403858.92 | -3192283.78
Approved Capital Budgets 2015/16 - 2017/18
Cost Centre | Service Area | Capital Scheme | Project Sponsor | Project Manager | Total Budget (£) | Spend over Previous 5 Years (£) | Budget Allocated to Future Years (£) |  |  |  | Latest Budget 2014/15 (£) | Profiled Budget 2014/15 (£) | Spend to 30th September2014 (£) | Variance to Profiled Budget at 30th September2014 (£) | Projected Outturn at 30th November 2014 (£) | Outturn Variance to Latest Budget (£) | Outturn Variance due to Slippage (£) | Outturn variance due to Over/ Under spend (£) | RAG Status | Gateway Stage Completed | PID Required? | PID Received? | PID Approved | Comments
A4832 | S11 | Pavilions Grey Water Harvesting | Ian Brooke | TBA |  |  | 28000 | [11 empty] | 1 |  | No |  |  | Budget is included with Pavilions Budget in reports to Project Board
A4833 | S13 | Horspath Athletics Ground | Ian Brooke | TBA |  |  | 500000 | [11 empty] | 3 |  | Yes | No | No | Projects due to commence in future years -for information only
A4834 | S13 | Cutteslowe Park Splash Feature | Ian Brooke | TBA |  |  | 100000 | [11 empty] | 2 |  | No
A4837 | S13 | Quarry Pavilion | Ian Brooke | TBA |  |  | 600000 | [11 empty] | 3 |  | Yes | No | No
B0083 | S13 | East Oxford Project | Jane Winfield | TBA |  |  | 200000 | [11 empty] | 3 |  | Yes | No | No
B0084 | S13 | Jericho Community Centre | Jane Winfield | TBA |  |  | 200000 | [11 empty] | 3 |  | Yes | No | No
B0032 | S22 | Bury Knowle House | Martin Shaw | TBA |  |  | 87900 | [11 empty] | 2 |  | No
B0069 | S22 | Corporate Property Planned Maintenance Programme | Martin Shaw | TBA |  |  | 310000 | [11 empty] | 3 |  | Yes | No | No
F7010 | S22 | Work of Art Said Business School | Michael Crofton-Briggs | TBA |  |  | 50000 | [11 empty] | 2 |  | No
A4836 | S22 | Improve Court Place Farm Car Park | Ian Brooke | TBA |  |  | 80000 | [11 empty] | 2 |  | No
|  | Total GF Budgets from 2015/16 onwards |  |  |  |  | 12155900
83688287.31
83688287.31
0