## Example Monitoring Form
Capital Gateway Project Monthly Monitoring Form |  | October |  | A Capital Project |  | A Capital Code
| Project Manager | 2014/15 |  |  |  | Date Form Required | 2014-11-15
| A Project Manager | Last Month | Current Month
| Progress Assessment Score for the Period | 0 | 6.6143 |  |  | Latest Annual Budget | Cumulative Spend
Individual Scores (from -2 to +2) |  | Applicable | Score |  |  | £ | £
Feasibilty (Gateway 0) |  | 0 | 0
Bid Approval (Gateway 1) |  | 7 | 1.7143 |  |  | 150000 | 122000
Initiation and Procurement (Gateway 2) |  | 6 | 1.5 |  |  | 1
Contract Award and Delivery (Gateway 3) |  | 4 | 2
Monitoring (Gateway 4) |  | 5 | 1.4 |  |  | Project on target progressing well
Completion (Gateway 5) |  | 6 | 0
Scoring Key |  |  | Score
Unlikely Will be Completed |  |  | -4
Encountering Difficulties |  |  | -2
Neutral |  |  | 0
Progressing |  |  | 2
Complete |  |  | 4
Feasibilty (Gateway 0) |  | Applicable |  | Comments | Actions | Who | When
1 | The Project is in line with Council objectives | N | 0
2 | Initial consultant and investigation costs identifieed | N | 0
3 | Project Client has been assigned | N | 0
4 | Initial cost estimate | N | 0
5 | Outline Project Brief prepared | N | 0
6 | Key benefits identified | N | 0
7 | Major Risks have been identified | N | 0
Bid Approval (Gateway 1) |  | Applicable | Score | Comments | Actions | Who | When
1 | The Project is in line with Council objectives and scored | Y | 4 | 4
2 | Full Project Brief prepared | N | 0 | Not required as project already approved. | None.
3 | Project Client identified | Y | 4
4 | Project Manager identified | Y | 4
5 | Full Capital and Revenue breakdown of costs prepared | Y
6 | Project governance structure agreed | Y | 4
7 | Internal Resources identified | Y | 4
8 | External consultants identified | N | 0 | Not required. | None.
9 | Procurement methodology identified | Y | 4
Initiation and Procurement (Gateway 2) |  | Applicable | Score | Comments | Actions | Who | When
1 | Budget has been allocated (Council Approval) | Y | 4
2 | Full PID prepared and approved by CAMAC | Y | -2 | This being undertaken retrospectively and as such not had CAMAC approval as yet. | PID prepared and submitted to Monitoring Group for approval onto CAMAC. | PM | 2014-11-17
3 | Actual project costs completed - both capital and revenue | Y | 4
4 | Risk register populated and completed | Y | 4
5 | Successful contactor identified | Y | 4
6 | Procurement methodology signed off by the procurement team | Y | 4
Contract Award and Delivery (Gateway 3) |  | Applicable | Score | Comments | Actions | Who | When
1 | Full budget released | Y | 4
2 | Contract placed | Y | 4
3 | On site management team in place | Y | 4
4 | All relevent permissions in place | Y | 4
5 | Project Plan prepared | Y | -2 | Not prepared as yet. | Will have to prepare a Project Plan detailing project's critical events. | PM | 2014-11-17
Monitoring (Gateway 4) |  | Applicable | Score | Comments | Actions | Who | When
1 | Project Budget profiled on Agresso in line with Project Plan | Y | -2 | Given Project Plan isn't completed as yet the profiling of the budget on Agresso is as yet unfinished. | Once Project Plan is complete, profiling will be undertaken. | PM/Management Accountant | 2014-11-17
2 | Project spend within approved budget | Y | 4
3 | Project will be spent in accordance with profiled budgets | Y | 4
4 | Project scope unchanged | Y | 4
5 | Project Manager completing monitoring reports monthly | Y | 4
Completion (Gateway 5) |  | Applicable | Score | Comments | Actions | Who | When
1 | Final account agreed | Y
2 | All defects attended to under the contract | Y
3 | No outstanding claims | Y
4 | Project Closure Statement completed by Project Manager | Y
5 | Project Closure Statement approved by CAMAC | Y
6 | Scheme has achieved initial business case objectives | Y
Delivery
|  |  |  | Feasibility (G0) | 2 | 1 | -0.5 | -2 | 0
|  |  |  | Bid Approval (G1) | 2 | 1 | -0.5 | -2 | 1.7143
|  |  |  | Initiation & Procurement (G2) | 2 | 1 | -0.5 | -2 | 1.5
|  |  |  | Contract Award & Delivery (G3) | 2 | 1 | -0.5 | -2 | 2
|  |  |  | Monitoring (G4) | 2 | 1 | -0.5 | -2 | 1.4
|  |  |  | Completion (G5) | 2 | 1 | -0.5 | -2 | 0
EXAMPLE