## Blank Risk Register
Appendix 4 |  | Risk Register for Digital Strategy
[5 empty] | Date Raised | Owner | Gross |  | Current |  | Residual |  | Comments | Controls
Title | Risk description | Opp/ threat | Cause | Consequence |  |  | I | P | I | P | I | P |  | Control description | Due date | Status | Progress % | Action Owner
Strategy | The Strategy is not approved | Threat | Insufficient support from members to adopt | Reputation suffers from not adopting Local Government Digital Service Standard. | September 2016 | Neil Lawrence | 2 | 2 | 2 | 1 | 2 | 1 | Retaining our current apporach will not encourage innovation and better outcomes | Emphasize national evidence about success of approach | November 2016
Finance | Actions within the Strategy cannot be afforded | Threat | Financial pressures on the Council require reductions in spending on ICT services | Individual actions and ambitions within the strategy cannot be delivered | September 2016 | Neil Lawrence | 2 | 3 | 2 | 3 | 2 | 1 | GDS experience is that better designed services cost less to develop and maintain | A sound business case to accompany each request for funding to show the benefits and risks
Inconsistency | Failure to adopt best practice approaches across all digital services | Threat | Lack of support from staff or time imperative to deliver services quickly | Delivery of online services that fail to meet customer need which then have poor take up | September 2016 | Neil Lawrence | 2 | 3 | 2 | 3 | 2 | 1 | Change in approach requires culture change which is harder to achieve | Ensure all ICT workplan projects are assessed for compliance. Provide advice and support for staff in adopting the approach
Equality | Failure to adopt better standards for accessibility | Threat | Lack of support from staff or time imperative to deliver services quickly | Failure to give all customers access to digital services. Possibility of challenge | September 2016 | Neil Lawrence | 4 | 3 | 3 | 3 | 2 | 1 |  | Ensure assisted digital services are in place. Action plan to improve accessibility online. Set standards for external developers
Collaboration | New digital services are built with other councils | Opportunity | Common needs shared with others result in project collaboration | Shared costs and risks. Better control over outcomes | September 2016 | Neil Lawrence | 2 | 3 | 3 | 3 | 3 | 4 | Examples of this are already happening in London and Scotland | Build on current national sector involvement. Publicise new projects