**Appendix 1: Oxford City Council Safeguarding Action Plan June 2017-June 2018**



**Key Influences/inputs**

* Corporate Plan
* The Section 11 Self-Assessment Audit
* Woods Review
* OFSTED Report Oxfordshire County Council
* Youth Ambition Audit
* Oxfordshire Safeguarding Children’s Board (OSCB) Business Plan
* Oxfordshire Safeguarding Adults (OSAB) Business Plan
* City Council Children and Young Peoples Plan

This year the Section 11 Self- Assessment Audit was a joint audit between the OSCB and OSAB. It was also more thorough than it has been previously.

The Action Plan Framework is based on the Section 11 Standards and it is aimed at moving the Council from a ‘green’ rated standard to a ‘blue’ rated standard (from good to best practice).

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Area identified for Improvement | Action | Measure | Outcome | Impact | Lead | Completion date |
| **Leadership,**  **Strategy and working together** | **Policy and Procedure**  Review positions/responsibilities in relation to attendance to identified safeguarding meetings.  Complete a review of Oxford City Council Safeguarding Policy. Integrate the key external service changes  Implement a central recording system for safeguarding concerns (SharePoint)  Provide training to staff on the new reporting system  Integrate the agreed safeguarding champion structure  Develop in partnership with OSCB safeguarding templates for community organisations  Align department safeguarding policy and procedure with central **functions. Ensure input from relevant departments.**  Integrate safeguarding into the work of the Sustainable City Board  **Communications**  Develop a safeguarding communication strategy that delivers relevant key messages throughout the year  Develop and design in collaboration with young people a safeguarding information inclusive of information on what safeguarding issues are and how to raise a safeguarding concern  Develop and design a children and young person friendly complaint information tool  .  **Links to the Community safety partnership**  ***Language schools***  Review current plan and capacity commitment to language school work  **Hotel watch/taxi licensin**g  Promote safeguarding of vulnerable adults and children in Hotels, Guesthouses & B’B’s across the city under the OSCB Child Sexual Exploitation Sub-group and national campaign ‘Say Something if you See Something’.  Domestic abuse  **Child Sexual Exploitation and exploitation**  Continue to work with OSCB CSE (Child Sexual Exploitation & Exploitation) Sub-group and Kingfisher Team in delivering the CSE Action plan aims  *To develop effective community engagement to promote safeguarding and awareness of issues such as CSE, Human Trafficking and Prevent*  *Review further implications with regard to vulnerable adult’s responsibilities.* | Scope out strategic and operational meetings. Discussion and allocation of meetings.  Draft to progress through programme boards.  New reporting programme up and running  Continue to explore options for IT system  .Dates set and available  Identified staff to complete bespoke champion training  Attendance to workshop. Participate in draft templates.  Visible on the agenda of r City Board  Put forward proposal to Communications Team as silver priority for the coming year  Sessions with young people  Draft information  .  Annual review of all hotels, Guesthouses, B&B’s and Short Let accommodation.  Regular attendance at CSE sub-groups and associated meeting and carryout any agreed actions | Agreed role attendance to each meeting. Regular attendance.  Active new policy available on website  Quarterly report evidencing use of system,  Guidance manual for staff on reporting online available on intranet  Delivered training across City Council departments on using on line system  Active champions, providing one to one advice and guidance across Oxford City Council  Signed off template at OSCB training subgroup    Discussed and agreed at City board  Draft Communication Strategy for safeguarding and key messaging throughout the year  .  Printed information readily available at sessions and on the internet.  Develop an information sharing network to tackle the exploitation of vulnerable individuals with partners to reduce crime, identify gaps in safeguarding and identify relevant training or support agencies. Hold annual conference to highlight issues identified by the membership.  Clear framework in place  . | Emerging issues identified/communicated and managed.  One clear policy being applied across departments standardised consistent approach.  Ability to evidence referral journey. Staff knowledgeable and up to date with process and procedure.  Ability to identify under and over reporting in vulnerable groups and departments  Resilient structure. Stronger internal partnership  Templates being used by resident associations, community groups commissioned through Oxford City Council  Organisational agreement  Visible current issues for staff. Raised awareness.  Provide a clear structure for key messaging from serious case reviews  Children and young people using services and have a raised awareness of safeguarding issues. Gained understanding of where to go for help and how to access it.  Ability to recognise the signs of vulnerability and how to report it. This would give owners/managers/staff and visitor to feel confident of their stay in the city.  Children, Parent & Carers and the wider community are aware of the risks of CSE | VJ  DG  DG  LG/  GW  DG  DG  VJ  DG  HL  HB  RA  LL  LL  LL  RA | June 2017  June 2018  June 2087  June 2018  July 2017  Sept 17  ?  On-going  On-going  On going |
| **Commissioning service delivery and effective practice** | **Visible current issues to staff to raise awareness. Provide a clear structure for key messaging from serious case reviews.**  Complete a safeguarding Audit of Youth Ambition services.  **Procurement**  Review of safeguarding standards in relation to contracting and contract monitoring  Ensure all grant and commissioned services are required to and evidence suitable safeguarding policy and procedure before funding is committed.  Agree and prioritise which external assessment tools are to be used within Oxford City Council centrally and department specific.  Ensure staff attend the required training to enable them to effectively and confidentially use the tools within their roles.  Develop a consistent process across oxford city council delivering learning across the City Council from Serious case reviews.  **Training**  Annual review of training needs and content  Measure training outcomes in practice and assess effectiveness of training staff.  To promote the support available to staff through the Employee Assistance Programme ‘Work Well’ and to develop further support where required  Continued data reports to service heads from HR.  Continue to Work with the OSCB and OSAB Training Groups/ workshops to develop training programmes that meet the needs of our staff.  Continue to deliver internal safeguarding awareness briefing throughout the year | Agreed programme of areas to cover  Included in written guidance and application process  Safeguarding officers Meeting held to discuss tools  Identify central tools, department tools, staff clear about responsibilities, confident to use.  Identify relevant training, advertise dates  Clear framework for delivering messages. Meaningful and relevant to services.  Collate training completion figures at year end. Review on-going training needs and refreshers continue to collate and evaluate feedback forms after sessions | Complete audit  Written report with recommendations for consideration  Agreed tools to use.  Available on keeping people safe page  Staff attending training  Quarterly sub training group meeting – plan and support the delivery and development of internal training packages  Provide a collective report to safeguarding raining sub group to continually improve our training by listening to staff feedback | Safeguarding staff questionnaire evidence increase in staff using forms. | DG/HL  AD/DP  JT | June 17  Dec 17 |
| **Performance and resource management** | Ensure our volunteers are included in the opportunity to attend the safeguarding awareness briefing sessions.  Record attendance and completion  Centrally collate volunteer roles/information  Categorise volunteer type   * Need for safeguarding training. * Vulnerability/risk support | Information to be regularly provided to volunteers about safeguarding sessions available. | Expand key messaging and safeguarding updates and information to our community of volunteers. |  | ST  ST/DG |  |
| **Outcomes and experiences of service users using statutory services.** | Have clear actions in relation to young carers ?  Ensure that staff who require it engage in the Think family approach agenda |  |  |  |  |  |

**Document Control**

|  |  |  |
| --- | --- | --- |
| **Document** | Oxford City Council  Safeguarding Action Plan 2017-18 | |
| **Owner** | Tim Sadler, Executive Director, Community Services | |
| **Author** | Daniella Granito  Safeguarding Co ordinator | |
| **Date last reviewed** | | April 2017 |
| **Next Review Date Due** |  | |
| **Version** | 1 | |

**Name:** ‘Oxford City Council Safeguarding Action Plan’

**File Location:** M:\Policy, Culture and Commmunications\Policy\Safeguarding\Action plans\Safeguarding Action Plan 2016-17 - April 2015 vs 2.docx