## Risk Register Current
Key
APPENDIX A
RED RISK (>=15)
CLOSED RISK
Risk ID | Risk | [5 empty] | Corporate Objective | Gross Risk |  | Residual Risk |  | Current Risk |  | Owner | Date Risk Reviewed | Proximity of Risk (Projects/ Contracts Only)
Category-000-Service Area Code | Risk Title | Opportunity/Threat | Risk Description | Risk Cause | Consequence | Date raised | 1 to 6 | I | P | I | P | I | P
CRR-001 | Delivery of key projects = ability to deliver cross cutting projects | T | People and the council are not developed sufficiently to make risk based decisions, carry out options appraisals. Decision making can be poor. Innovation is not encouraged, low risk appetite. | Recent adoption of Project Management methodology (experience in the council is minimal). Conflict between BAU and Project work. Process focused and not fully embedded. | Project methodology is not applied consistently across the council. Budget variations, volatility in results and benefits not realised. Board intervention. Council does not innovate or change. Ability of the council to deliver objectives. | 2010-01-12 | 6 | 4 | 3 | 3 | 2 | 4 | 3 | JY | 2011-01-31
CRR-002 | Financial Reporting | T | Accounts qualified | Changes in financial regulations and Accounting standards leading to much greater complexity, loss of staff skills and delivery of robust internal controls | Reputation 1) ability to borrow funds in the future (negative perception of the council's ability to manage its finances) 2) Lack of confidence in internal support 3) additional audit costs | 2010-01-12 | 6 | 5 | 3 | 5 | 2 | 5 | 3 | JY | 2011-01-31
CRR-003 | Supplier Management | T | Ability of the council to manage large contracts and to obtain best value from those contracts | Correctly identifying appropriate staff with corporate and commercial awareness to manage contracts (where balancing reduction in staff with keeping best staff to manage contracts) | Council does not realise benefits from large contracts | 2010-01-12 | 6 | 3 | 4 | 2 | 3 | 3 | 3 | JY | 2011-01-31
CRR-004 | Health and Safety | T | Existence of operational risks (relating to internal as well as public concerns - property not vehicle). | Health and Safety practices are not robust enough. Under investment in property, potential lack of clarity of accountability and of ownership of health and safety | Increased insurance claims and ultimately premium costs. Reputational implications. | 2010-01-12 | 1, 3 | 4 | 3 | 2 | 2 | 3 | 3 | DE | 2011-01-31
CRR-005 | Failure to achieve budget reductions over four year period | T | Inability to achieve savings in budget | Significant efficiency savings and service reductions as a result of Comprehensive Spending Review | Increased use of balances or further reductions to be identified | 2010-10-31 | 6 | 4 | 3 | 3 | 3 | 3 | 3 | JY | 2011-01-31
CRR-006 | Impact on homelessness of changes in Housing Benefit | T | Changes in housing benefit and universal housing benefit increase homelessness | Changes in housing benefit and universal housing benefit increase homelessness | Cost the council more money in administration and payments to landlords | 2009-12-01 | 1 | 5 | 3 | 4 | 3 | 4 | 4 | DE | 2011-01-31
CRR-007 | Management of HRA reform and self-financing | T | That the self financing regime is difficult to administer and the 30 year cashflow is not favourable to the council | From the 1st April 2012 the HRA subsidy system is replaced with self financing, this entails the council taking on £200m of debt, keeping the income from rents and self financing the service |  | 2011-01-31 | 6 | 4 | 3 | 4 | 3 | 4 | 3 | JY | 2011-01-31

## Management of the Risk
Key
ACTIONS MUST BE 'SMART' |  |  |  |  | CLOSED ACTION/Risk
Specific, Measurable, Achievable, Realistic and Time bound
Risk ID | Risk Title | Action Owner | Accept, Contingency, Transfer, Reduce or Avoid | Details of Action | Key Milestones | %Action Complete | Date Reviewed
CRR-001 | Delivery of key projects | JL | Reduce | Development of corporate approach to project management via a corporate project management office. | Submit 'Vision for Corporate Functions' to CMT End June | 100% | 2010-05-17
CRR-001 | Delivery of key projects | JL | Reduce | Development of a business partner model to project management using centre of knowledge within the Project Management office | Update actions following on from approval of 'Vision for Corporate Functions' End June | 100% | 2010-05-17
CRR-001 | Delivery of key projects | SH | Reduce | Develop clear roles, responsibilities and job descriptions/expectations for managers, heads of, directors | 2010-12-01 | 10% | 2011-01-20
CRR-001 | Delivery of key projects | SS | Reduce | Development of options appraisal methodology for capital projects | 2010-04-30 | 100% | 2011-03-31
CRR-002 | Financial Reporting | NK | Reduce | Deliver Final Accounts and working papers within agreed timetable | 2011-01-01 | 80% | 2011-03-31
CRR-002 | Financial Reporting | NK | Reduce | Ensure robust quality assurance around working papers prior to submission | 2011-01-01 | 80% | 2011-03-31
CRR-002 | Financial Reporting | NK | Reduce | Identify issues within previous years audits and resolve them | 2011-01-01 | 100% | 2011-03-31
CRR-003 | Supplier Management | JL | Reduce | Development and approval of procurement strategy. Ensure consistent approach towards supplier management across the organisation. | 1) CEB approval of strategy 15-feb-10. 2) Develop operation principles for contract management to apply to all contracts 30-June-10. 3) Agree with internal audit programme of audit 31-May-10 | 100% | 2010-05-17
CRR-003 | Supplier Management | JL | Reduce | Implement standard contract documentation and approach (based on 4Ps approach to contract management ) | Put in place and forms part of the Leisure contract | 100% | 2011-03-31
CRR-003 | Supplier Management | JL | Reduce | Develop the procurement team as a centre of excellence for relationship management. | training programme on contract management best practice ran for key staff in summer 2010 | 100% | 2011-03-31
CRR-003 | Supplier Management | JL | Reduce | Implement a mentoring/work shadowing programme where expertise can be shared with new contract managers. | Procurement team provide support to contract managers, formal network of experts to share expertise to be put in place | 50% | 2011-03-31
CRR-004 | Health and Safety | SS | Reduce | Establish Corporate Asset Management Group to create a joined up approach towards management of Corporate Assets | Group first meeting 28-Feb-10 | 50% | 2011-03-31
CRR-004 | Health and Safety | SS | Reduce | Develop a corporate approach towards health and safety | Agree detailed actions with HR - 31-March-10 | 100% | 2011-03-31
CRR-004 | Health and Safety | SS | Reduce | Create 'one view' of all corporate assets (issues, status of building, budget, work required, timescales). 'One view' being everything documented in consistent and understandable format which can be shared across organisational boundaries. | One view developed 31-Aug-10 | 50% | 2011-03-31
CRR-008 | Failure to achieve budget reductions over four year period | NK | T | Detailed monitoring, early intervention | Ongoing | 50% | 2011-03-31
CRR-009 | Impact on homelessness of changes in Housing Benefit | HB | T | Monitoring and intervention, ensure takeup of benefits | Ongoing | 50% | 2011-03-31
CRR-010 | Management of HRA reform and self-financing | GS | T | Establish Board, engage consultants, agree debt profile, write asset management plan and business plan | May 2011- April 2012 | 10% | 2011-03-31

## Key
Risk ID Categories
CRR-000 | Corporate Risk Register
SRR-000 | Service Risk Register
CEB-000 | CEB reports
PRR-000 | Project/Programme Risk Register
PCRR-000 | Planning Corporate Risk Register
PSRR-000 | Planning Service Risk Register
Service Area Codes
PCC | Policy, Culture & Communication | CS | Customer Services
CD | City Development | FI | Finance
CHCD | Community Housing & Community Development | BT | Business Transformation
CA | Corporate Assets | PS | Procurement & Shared Services
OCH | Oxford City Homes | CP | Corporate Performance
CW | City Works | LG | Law and Governance
ED | Environmental Development | CRP | Corporate Secretariat
CL | City Leisure | PE | People & Equalities
Corporate Objective Key
1: More Housing Better Housing for all
2: Stronger & more inclusive communities
3: Improve the local environment, economy & quality of life
4: Reduce anti-social behaviour
5: Tackle climate change & promote environmental resource management
6: Transform OCC by improving value for money and Service performance