Performance Summary Green = target met Scrutiny Committee Trends compare relative performance with Amber = within tolerance Prd: previous month Red = outside tolerance Prev Year End: previous March June-2019 Year on Year: the same period from the previous year Measure Owner Result 2017/18 Latest Data Year End Target 2018/19 RAG Trends Comments Ref Description Target Result Prd Year on Year BIT019i BIT019i: % all contact carried out online Helen Bishop 37.1% 38.0% 42.9% 40% G We are currently on track and exceeding target. WR001 WR001: Number of people moved into work by the Welfare Reform Programme Paul Wilding 44 Number 13 Number 7 Number 50 Number A We are currently behind profile but the team is currently supporting many customers with seeking work so are hopeful to catch up later in the year. BV009 BV009: Percentage of Council Tax collected Tanya Bandekar 97.72% 30.65% 30.62% 97.75% A By 30/06 we had collected £27.9m that equates to 30.62% of the total 19/20 collectable debit. With the end of June profiled target being 30.65% we were just £25k short of this target. Recovery action has been initiated against all those accounts in arrears and hopefully we will soon be back on track. BI001 BI001: The % of Council spend with local business Amanda Durnan 67.34% 9.00% 74.67% 54% G We have exceeded our requirements for this quarter. We continue to try to increase local spend by requesting stakeholders to include a local supplier when tendering, however, this is dependent on the requirements, and the locality of the head office of the Supplier. CS004 CS004: Enquiries resolved by customer service centre without hand off Helen Bishop 94.44% 90.00% 93.80% 90% G We are currently on track and currently exceeding target Measure Owner Result 2017/18 Latest Data Year End Target 2018/19 RAG Trends Comments Ref Target Result Prd Year on Year CH001 CH001: Days lost to sickness Paul Adams 7.60 days 1.62 days 1.63 days 6.50 A The year-end projection for sickness absence 6.52 days/per FTE, which is marginally above the corporate target rate. Comparison of the year to date figures with the corresponding period in 2018/19 indicates that the proportion of long-term sickness of the overall rate is far lower (45%). There are 5 service areas whose projected year end sickness absence figure is above the Council target: Community Services; Financial Services; Housing Services; Regeneration and Economy; and Regulatory Services and Community Safety. The HRBP team continues to work with the relevant service areas on measures to absence address cases and ensure that appropriate and timely interventions are in place. CS054 CS054: Time taken to determine DHP applications Paul Wilding 12 Working Days 10 Working Days 14 Working Days 10 Working Days G DHP assessment is under major pressure from UC rollout. 40% of applications now come from UC customers, where we have to wait 5 weeks for confirmation of UC entitlement from DWP. This delay makes the 10 days often impossible to meet. HB DHP remains well under 10 days to assess. Measure Owner Result Latest Data Year End Target 2018/19 RAG Trends Comments Ref 2017/18 Target Result Prd Year on Year ED002 ED002:Implementation of measures to reduce the city council’s carbon footprint by 5% each year Jo Colwell 446 Tonnes 0 Tonnes 84 Tonnes 408 Number G Barton Neighbourhood Centre refurbishment - LED lighting and controls upgrade completed - Est 12tCO2/year reduction. Continuing delays to Solar car port installation at Leys pools due to contractor breaching contract and subsequent contract termination - June 19. Exploring and planning alternative completion options with alternative contractor - negotiating completion options/prices. Avoided energy overspend from energy billing checks/in-house energy bureau =- £8433.65 for the financial year to date. LP119 LP119: The number people taking part in our youth ambition programme Ian Brooke 6,155 Number 1,500 Number 1,351 Number 6,000 Number A We are currently slightly under target. This is due to not all of the funded activities having submitted their participation data at this stage. We have drawn up a leaflet for all of the summer activities that we deliver and for all of the funded activities. This will be used in a campaign this summer. CS003 CS003: Customer calls answered on the council’s main telephone service lines without hanging up Helen Bishop 94.10% 95.00% 93.91% 95% A 3 We are currently slightly under target. We recruited an additional 5 officers in June but due to training we would not have seen the benefit of them until July, so our resource levels were stretched. Due to other leavers in June we also have another 2 vacancies to fill. Positives that we reduced our opening hours to 8am-5pm in June which has given us more resource capacity at the start of the day. We also re-instated our automated missed bins service on 12th June which gives responses to customers without the need for them to speak to an officer. Measure Owner Result 2017/18 Latest Data Year End Target 2018/19 Rag Trends Comments Ref Description Target Result Prd Year On Year FN045 Amount of overpaid Housing Benefit collected Tanya Bandekar Not Recorded £500,000 £623,790 £3,000,000 G In June we recovered a total of £201k of overpaid Housing Benefit. The majority of this, almost £145k, was from deductions / offsets of Housing Benefit. The cumulative figure recovered in 19/20 to date is almost £624k. The target for 2019/20 is to recover £3m. LP220 LP220: Number of people from our target groups using our leisure facilities Ian Brooke 775,703 Number 199,700 Number 189,326 Number 798,970 Number R Officers are pressing Fusion and closely monitoring their delivery approach for outreach working to increase the number of visits for the organisations key target groups. CoS031 CoS031: Effective delivery of the capital programme Ian Brooke Not Recorded 82% 82% 82% G On track CS025 CS025: Percentage of Business Rates Collected Tanya Bandekar 98.14% 30.50% 31.34% 98.5% G The good start to Business rates collection in 2019/20 continues. At the end of Q1 we had collected just under £34m that was over £900k above the profiled target of 30.5%.