Scrutiny Budget Review 2020/21 – Scoping Document

| Review Topic | Budget Review 2020/21 and Medium Term Financial Plan to 2023-24 |
| --- | --- |
| Lead Member Review Group | Councillor James Fry |
| Other Review Group Members | Councillor Craig Simmons Councillor Chewe Munkonge Councillor Roz Smith Members of the Housing Panel will be invited to scrutinise Housing-related budgetary items: Councillor Nadine Bely-Summers Councillor Mike Gotch Councillor Richard Howlett Councillor Sian Taylor Councillor Elizabeth Wade Councillor Dick Wolff Tony Buchanan (tenant co-optee) |
| Officer Support and allocate hours | Scrutiny Officer support – approx. 2-3 days per week from mid-December 2019 to mid-February 2020. Additional support from the Head of Financial Services, Management Accountancy Manager and other Senior Officers. |
| Background | The Finance Panel is responsible for scrutinising finance and budgetary issues and decisions, including the Budget 2020/21 decision. The Budget 2020/21 paperwork will be published for consultation on 11 December 2019, ahead of a final decision by full Council on 13 February 2019. In recent years the Panel has formed a Budget Review Group to scrutinise the budget proposals in detail before reporting to Cabinet in February. |
| Rationale | To scrutinise the Council’s draft budget for 2020/21 and medium term financial plan for the following three years, and provide public assurance of the Council’s budget setting processes and decisions. |
| Key lines of inquiry | Areas of focus for the Budget Review Group this year to include: Slippage in the Capital Programme Business rate income The overall shape of expenditure and income (gross and net) at a high level, including data for recent years and future years. The evolution of Council budgets over recent years, tracking changes from original approved budgets to final outturn. The impact on council finances of the establishment of the council owned companies, Oxford Direct Services Ltd and Oxford City Housing Ltd In addition to the joint ventures in relation to land at Barton and Oxpens. Estimates of gross and net income and expenditure Past and projected changes to external funding streams. Service area budget proposals including planned savings and efficiencies, cost pressures and staffing (FTE) impacts. Contingencies and earmarked reserves. HRA Business Plan in the light of the changes to interest rates charged by the Public Works Loan Board The expected impacts of any national government policy changes following the December 2019 UK General Election. |
| Indicators of Success | Robust independent scrutiny of budget proposals; Detailed consideration of key lines of inquiry; The production of an evidenced based report with recommendations; Broad agreement on conclusions and recommendations amongst Review Group members; The majority of recommendations are agreed by the Cabinet. |
| Methodology/ Approach | Evidence gathering to include: A budget briefing by the Head of Financial Services, Reviewing Budget 2020/21 paperwork, including options or bids presented to members; Submitting written questions to Senior Officers and reviewing their responses; Meetings with Executive Directors, Assistant Chief Executive and Heads of Service. |
| Specify Witnesses/ Experts | Assistant Chief Executive; Executive Director – Development; Executive Director for Sustainable City; Executive Director – Communities and Customer (Interim) Interim Director of Housing; Head of Financial Services; Head of Housing Services; Head of Planning Services; Head of Community Services; Head of Business Improvement; Head of Law and Governance Head of Regulatory Services and Community Safety Management Accountancy Manager. |
| Out of scope | Detailed estimates in relation to ODS and OCHL company business plans are out of scope, but not their overall impact on the Council’s budget and Medium Term Financial Plan. |
| Projected start date | 11 December 2019 | Draft Report Deadline | 29 January 2019 for Finance Panel |
| Meeting Frequency | 4 meetings in January 2019 | Projected completion date | 12 February 2019 Cabinet |

Draft outline of meetings

Meeting one – 6 January 2020, 6:00 – 8:00pm

6pm: Finance overview, and consider service area budget proposals for: Assistant Chief Executive (Caroline Green) Nigel Kennedy (Head of Financial Services) Chief Executive, Gordon Mitchell, is unavailable in early January.

Meeting two - 8 January 2020, 6:00pm - 8.00pm

To consider service area budget proposals and form draft recommendations for: Planning and sustainable development (Tim Sadler and Adrian Arnold) Housing Services (Paul Leo and Stephen Clarke) Regeneration and Economy (Tom Bridgman and Jane Winfield) Housing Panel members to be invited to contribute to the discussion on Housing Services

Meeting three – 20 January 2019, 6:00pm - 8.00pm

To consider draft recommendations from previous meetings, to consider budget proposals and form draft recommendations for: Communities and Customers (Ian Brook, Helen Bishop and Ian Wright) Law and Governance (Nigel Kennedy and Anita Bradley)

Meeting Four – 29 January 2019 (as part of Finance Panel)

To consider the draft review group report.