|  |  |  |  |  |  |  |  |  |  | Appendix 1 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Appendix 1 – Meanwhile in Oxfordshire Risk Register |  |  |  |  |
| Last | Updated | 29/10/20 |  |  |  |  |  |  |  |  |  |  |  |
| Updated By | CL | Risk Register |  |  |  |  |  |  |  |  |  |  |
| Revision | 30/10/20 |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  |  | Current Risk - | Current Risk | Current Risk | Risk | Mitigating Actions | Action |  |  |  |  |
| NO. | Raised | Risk Type | Risk Description | Probability | Impact | Score | Response |  | Due Date | Risk Owner | Risk Status | Comments |  |
| A | Financial |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Cabinet Report to be completed and |  |  |  |  |  |
|  | Nov-20 | Threat | OxLEP Funding not secured, contract not agreed | 2 | 5 | 10 | Reduce | Members briefed | Nov-20 | CL/SW | Response agreed | OxLEP funding time limited |  |
|  |  |  | Capital Funding not approved – programme would |  |  |  |  | Options appraisal and Business Case |  |  |  |  |  |
|  | Nov-20 | Threat | terminate and Council at risk of consultant fees | 3 | 5 | 15 | Reduce | required for Programme | Nov-20 | CL/SW/MP | Response agreed | OxLEP funding time limited |  |
|  |  |  | Programme not met for delivery by March 2021 |  |  |  |  | Conclude consultant appointments and |  |  |  |  |  |
|  | Nov-20 | Threat | and resulting loss of OxLEP funding | 3 | 5 | 15 | Reduce | close programme monitoring with consultants | ongoing | CL/SW | To review |  |  |
|  | Nov-20 | Threat | Programme non-compliance with re: State Aid | 3 | 5 | 15 | Reduce | Instruction to Browne Jacobson for legal advice on State Aid | Nov-20 | CL/SW/MP | Due 5/11/2020 |  |  |
|  |  |  |  |  |  |  |  | Early appointment of operator required, ITT |  |  |  |  |  |
|  | Nov-20 | Threat | Market conditions limit viability | 3 | 4 | 12 | Reduce | to be prepared | Nov-20 | CL/SW | Escalation agreed |  |  |
| B | Feasibility |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Options appraisals to include detailed cost |  |  |  |  |  |
|  | Jan-21 | Threat | Business Case not viable | 3 | 4 | 12 | Reduce | appraisals. | Jan-21 | CL/SW | Escalation agreed |  |  |
|  |  |  |  |  |  |  |  | Planning pre-app required as part of the |  |  |  |  |  |
|  | Jan-21 | Threat | Planning restrictions on design and use | 3 | 3 | 9 | Reduce | feasibility works | Jan-21 | CL/SW | Response agreed |  |  |
| C | Covid -19 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Government restrictions delay building |  |  |  |  | Earliest contractor appointment - form of |  |  |  |  |  |
|  | Jan-21 | Threat | construction works | 3 | 4 | 12 | Reduce | contract to be reviewed | Jan-21 | CL/SW | Open |  |  |
|  | Risk Matrix |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Probability |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Almost certain | 5 | 10 | 15 | 20 | 25 |  |  |  |  |  |
|  |  |  | Likely | 4 | 8 | 12 | 16 | 20 |  |  |  |  |  |
|  |  |  | Possible | 3 | 6 | 9 | 12 | 15 |  |  |  |  |  |
|  |  |  | Unlikely | 2 | 4 | 6 | 8 | 10 |  |  |  |  |  |
|  |  |  | Rare | 1 | 2 | 3 | 4 | 5 |  |  |  |  |  |
|  |  |  | Impact | Insignificant | Minor | Moderate | Major | Severe |  |  |  |  |  |
|  |  |  |  | Probability | Impact |  |  |  |  |  |  |  |  |
|  |  |  |  | .1 Rare | .1 Negligible |  |  |  |  |  |  |  |  |
|  |  |  |  | .2 Unlikely | .2 Minor |  |  |  |  |  |  |  |  |
|  |  |  |  | .3 Possible | .3 Moderate |  |  |  |  |  |  |  |  |
|  |  |  |  | .4 Likely | .4 Major |  |  |  |  |  |  |  |  |
|  |  |  |  | .5 Almost certain | .5 Catastrophic |  |  |  |  |  |  |  |  |

| RISK CATEGORY | RISK TYPE | RISK RESPONSE | RISK STATUS |
| --- | --- | --- | --- |
| Strategic & Commercial | Threat | Avoid | Open |
| Economic, financial |  |  |  |
| & Market | Opportunity | Reduce | Response agreed |
|  |  | Fallback/ |  |
| Legal & regulatory |  | Contingency | Escalation agreed |
| Organisational, human |  |  |  |
| &management |  | Accept | Closed |
| Political |  | Share Transfer | To review |
| Environmental |  |  | Transferred to issue Log |
| Technical, operational |  |  |  |
| & infrastructure |  |  |  |

|  |  | RISK MATRIX |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Probability |  |  |  |  |  |  |  |  |
| Almost Certain | 5 | 5 | 10 | 15 | 20 | 25 |  | 25 |
| Likely | 4 | 4 | 8 | 12 | 16 | 20 |  | 0 |
| Possible | 3 | 3 | 6 | 9 | 12 | 15 |  | 15 |
| Unlikely | 2 |  |  |  |  |  |  |  |
|  |  | 2 | 4 | 6 | 8 | 10 |  | 16 |
| Rare | 1 | 1 | 2 | 4 | 4 | 5 |  | 12 |
|  |  | 1 | 2 | 3 | 4 | 5 |  | 10 |
|  | Impact Insignificant | Minor | Moderate | Major | Severe |  |  |
|  |  |  |  |  |  |  | 9 |
|  |  |  |  |  |  |  |  | 8 |
|  |  |  |  |  |  |  |  | 5 |
|  |  |  |  |  |  |  |  | 6 |
|  |  |  |  |  |  |  |  | 5 |
|  |  |  |  |  |  |  |  | 4 |
|  |  |  |  |  |  |  |  | 3 |
|  |  |  |  |  |  |  |  | 2 |
|  |  |  |  |  |  |  |  | 1 |