|  |  |
| --- | --- |
| Commissioning Timetable | When |
| Agreement of scope | January 2020 |
| Needs analysis | February 2020 |
| Feasibility study launch event including senior leaders OCC and OCCG | November 2020 |
| Commissioning intentions, shared with Steering Group and JMG | January 2021 |
| Scope agreed by all parties | January 2021 |
| Business Case submitted to DLT | January 2021 |
| Drafting contracts, tender documents and service specifications | Mid-March |
| Provider workshop date advertised on SE business portal with high level commissioning intentions around the remodelled services | April 2021 |
| Release of tender documents onto the portal | 18th May 2021 |
| Close of advert on the portal | 28th June 2021 |
| Bids Evaluated – panel moderation | 8th & 9th July 2021 |
| Provider Interviews held | 20th & 21st July 2021 |
| 2nd Stage negotiation | August & September 2021 |
| Recommendations Report for Approval | September 2021 |
| Provider (s) notified of Contract Award | October 2021 |
| Contract signed | October 2021 |
| Mobilisation of services | October 2021 |
| Contract Start Date | April 2022 |