|  |  |
| --- | --- |
| To: | Housing and Homelessness Panel |
| Date:  Report of: | 06 October 2021  **Head of Housing Services** |
| Title of Report: | **Housing and Carbon Reduction** |

|  |  |  |
| --- | --- | --- |
| Summary and recommendations | | |
| Purpose of report: | | To update the Housing and Homelessness Panel on the activity of the Council relating to carbon reduction in terms of its own housing stock |
| Corporate Priority: | | Pursue a zero carbon Oxford, Deliver more affordable housing |
| Policy Framework: | | Corporate Plan |
| Recommendation(s):That the Panel resolves to: | | |
| 1. | Note the report having agreed any recommendations to Cabinet arising from it | |

|  |  |
| --- | --- |
| Appendices | |
| Appendix 1 | Draft Campaign Plan |
|  |  |

# Introduction and Background

1. Oxford City Council (OCC) have set a target of getting 95% of the housing stock (currently at 7,626) to an EPC C or above by 2030.
2. The current MTFP (HRA Business Plan) includes circa £7m to fund this ambition. Prior to the rent reduction measures brought in by central government that negatively impacted borrowing OCC had made significant investments in energy efficiency measures not only to reduce carbon but also to help tackle fuel poverty objectives. This year has seen OCC planning how to significantly ‘scale up ‘our programmes. Some works have already begun using both base budget together with an additional £382k of central Government funding following our successful bid to the Green Homes Grant Local Authority Delivery (LAD) scheme. A further bid to the Governments Social Housing Decarbonisation Fund (SHDF) is currently being worked on. The HRA base budget is currently considered adequate to support the target achievement but this can only be confirmed once firm prices on contract packages are received.
3. Although OCC have already completed many improvements to our housing stock, there remains significant works to be completed to achieve the targets. Using data from the Councils Carbon Management database (CROHM), we can target those properties EPC D or below and understand what works are required to achieve the 95% EPC C target.
4. Each year the Scrutiny Committee undertakes a ‘deep dive’ into a topic of particular concern to its members over a course of multiple meetings through a Review Group. At its August 2021 meeting it was agreed that the topic for Review Group for the current civic year would be Child Poverty.

# Current Situation and CHROHM Data

1. The stock data indicates that the following numbers of properties currently fall within the respective EPC ratings:

|  |  |  |
| --- | --- | --- |
| **Maximum    Sap Score** | **Number of Properties** | **%** |
| **A (>100)** | **2** | **0.03%** |
| **A** | **21** | **0.28%** |
| **B** | **138** | **1.81%** |
| **C** | **4950** | **64.91%** |
| **D** | **2357** | **30.91%** |
| **E** | **136** | **1.78%** |
| **F** | **22** | **0.29%** |
| **G** | **0** | **0.00%** |
| **Total** | **7626** | **100%** |

1. A total of at least 2,515 properties require work in order to move them from an EPC rating of below C into C or above.
2. EPC surveys will continue to be carried out until March 2022 therefore the above numbers will change over time as data is validated and targeted carbon reduction programmes are delivered including main stream planned maintenance programmes which have energy efficiency savings e.g. roof, window and door replacement programmes.

**Projects and Works to Achieve the Targets**

1. An example of some of the possible areas of works required is below, although this is not an exhaustive list.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Solar options which include duel coil cylinders and PV panels | | | | |
| Remedial works to seal chimneys | | |  |  |
| Roofing works to joists, rafters and insulation | | | |  |
| Solid floor alterations | |  |  |  |
| LED lighting |  |  |  |  |
| Wall insulations internal and external | | | |  |
| Draught proofing | |  |  |  |
| Hot water system alterations | | |  |  |
| Controls and automation of systems | | | |  |
| Component elements (windows, doors) | | | |  |

**LAD and SHDF Projects**

1. OCC has successfully applied for LAD1b funding and is in the process of improving 240 properties. As part of this programme 90 of the 240 will have a whole house assessment which is part of the PAS2035 approach dictated by BEIS to receive funding. The whole house assessment will produce a medium and long term plan for each property and using this information we can get them to an EPC C in the medium term and increase our knowledge of the practical implications of doing further works whilst the property is occupied and indeed what is practical to achieve overall. Improvements will need to be sequenced in the correct order and linked with cyclical maintenance programmes. Renewable energy and other insulation measures can also be considered as part of a whole house retrofit and planned when a property becomes empty to avoid disruption.
2. OCC is currently producing a bid to the SHDF to implement energy efficiency improvements in voids working with Oxford Direct Services. ODS are in the process of getting their PAS2030 accreditation so they can implement improvements as part of the PAS2035 whole house retrofit. The target is 125 Void properties currently at EPC D or below to be brought up to at least an EPC C. This will target fabric first and to get our properties heat pump ready. It will also need to look at ventilation as part of the works.

**Resources and Draft Timeline**

1. These programmes will need additional staffing resource to deliver namely:
2. External expert support:

An external carbon and sustainability consultancy will need to be procured and is required to specify, price and validate the works and then prepare both works and tender packages acting as Contract Administrator, Quality auditing, QS and commercial functions to support the packages of works.

1. Internal client team:

Our own internal property services team will require a suitable team with the relevant skills to advise on technical aspects and client the works to ensure maximum benefits and value can be achieved. This team would oversee the programmes, assist in the development of the packages needed, bring together the Employers requirements on new build and Schedules and product specifications with ODS, seek and secure external funding opportunities and provide the reporting function required to both Council and Central Government on global carbon targets and performance.

1. Resident Engagement and Communication:

In addition we will need to increase our resource with regard to resident engagement and support and we are currently starting to plan a communications campaign to secure maximum buy in and take up. (See Appendix 1 for Draft Campaign Plan)

1. Additional resources can be contained within the current budget allocation
2. Resourcing Energy works is currently very challenging as many of the social housing providers including local authorities are looking to implement carbon projects and the demand and cost for this skill sector is currently very high. Contractors in the market are in demand and OCC will, like many organisations face challenges in the supply chain. The advantage we hope to achieve with ODS becoming qualified and approved with PAS2030 accreditation to undertake this work will enable a significant amount of the work to be carried out in house or managed via specialist contractors where necessary.
3. Below is an initial indicative draft programme over the target period. It is possible that work packages may be achievable earlier and the initial analysis and creation of the packages will determine the overall programme. This will be identifiable in year two onwards and the programme can be fully confirmed.

|  |  |  |
| --- | --- | --- |
| **Year No** | **Calendar Year** | **Activities** |
| 1 | 2021 - 2022 | Procure Consultant – Prepare specifications and packages for ODS – Tenders  Continue to work with ODS on their PAS2030 and MCS accreditation  ODS and OCC to ensure the management and staff are in place to manage the EPC C 2030 works.  Bid for SHDF to partially fund the Voids programme  Implement LAD1b improvements  Communication Campaign begins |
| 2 | 2022 - 2023 | Resident Engagement and communications campaign continuation  Procurement of works packages  Plan packages for latter part of 2022/2023, 2023/2024 & 2024/2025 include validation of works, final costing, planning applications, specifications. Begin work onsite packages for 2022/2023 |
| 3 | 2023 – 2024 | Start on site for 23/24 work packages – Finalise design & package for 2025/26 inc validation, specification, planning applications & S20  process |
| 4 | 2024 – 2025 | Start on site for 24/25 work packages – Finalise design & package for 2027/28 inc validation, specification, planning applications & S20  process |
| 5 | 2025 - 2026 | Start on site for 25/26 work packages – Finalise design & package for 2028/29 inc validation, specification, planning applications & S20  process |
| 6 | 2026 - 2027 | Start on site for 26/27 work packages – Finalise design & package for 2029/30 inc validation, specification, planning applications & S20  process |
| 7 | 2027 – 2028 | Start on site for 27/28 work packages |
| 8 | 2028 – 2029 | Start on site for 28/29 work packages |
| 9 | 2029 - 2030 | Start on site for 29/30 work packages |

.

|  |  |
| --- | --- |
| **Report author** | Malcolm Peek |
| Job title | Property Services Manager |
| Service area or department | Housing Services |
| Telephone |  |
| e-mail | mpeek@oxford.gov.uk |