## Sheet1
Appendix 4: Risk Register
[5 empty] | Date Raised | Owner | Gross |  | Current |  | Residual |  | Comments | Controls
Title | Risk description | Opp/ threat | Cause | Consequence |  |  | I | P | I | P | I | P |  | Control description | Due date | Status | Progress % | Action Owner
Income generation not as predicted | Applications reduced or increased and not as predicted | O/T | Income is based on predicted numbers from review of Selective licensing - true numbers will not be known until licensing starts | resources not being matched to demand | Jan 2021 | Gail Siddall | 3 | 3 | 3 | 2 | 2 | 2 | Build in flexibility in staffing to increase/decrease if scheme income and costs are out of balance | Provide Net zero budget. Budget based on predicted workload on annual basis and ensure resources aligned
Scheme not approved | Secretary of State must approve the scheme before it can be implemented | T | The Council do not make a compelling enough case for the introduction of selective licensing | Regulation of the sector would continue to be piecemeal and operated on a reactive basis - leaving many occupiers I the private rented sector living in poor housing conditions. Rogue/criminal landlords would be able to continue to operate with limited resources available to tackle poor practices in a fair and consistent manner | Jan 2021 | Gail Siddall | [6 empty] | City wide schemes have recently been turned down by the Secretary of State | Ensure that the evidence presented to the Secretary of State provides clear evidence of the need for selective licensing to tackle the poor conditions experienced in the private rented sector throughout the city.
legal challenge / judicial review | The decision to introduce a selective licensing scheme could be subject to a legal challenge via a Judicial Review | T | Statutory requirements not met. Insufficient resources provided to fulfil requirements. Insufficient evidence base. Lack of wider consultation | The time table for introducing the scheme would be altered and extra unbudgeted spending would be required to defend the legal challenge. | Nov 2020 | Gail Siddall | 3 | 3 | 3 | 2 | 2 | 2 | A number of challenges have been brought against councils introducing property licensing schemes - for various reasons with varying success | External experts have been employed to ensure that consultation exercise has been undertaken widely - all statutory requirements have been met and robust evidence for proving need for scheme provided
Insufficient evidence base | The consultation project does not provide sufficient evidence to support an approach for the future of the scheme or is undertaken in an unrealistic timeframe. | Opp and Threat | Lack of interest; insufficient marketing, promotion, inaccurate targeting of audience. Affected by COVID -19 pandemic aftermath | The consultation exercise does not ensure all stakeholders in the private rented sector, including those living within the sector, have a voice. This could lead to uneven responses and insufficient evidence of the need for a scheme. | Mar 2020 | Gail Siddall | 3 | 3 | 3 | 2 | 2 | 2 |  | Ensure that statutory consultation period is satisfied and undertaken at an appropriate time. Independent consultation supplier with appropriate skill base and resources used to carry out consultation to reach all stakeholders
Recommendations not approved | The recommendations of the report are not approved | Threat | Insufficient support from members to proceed with statutory consultation | Scheme will not proceed and problems in private rented sector will continue to be dealt with reactively | Mar 2020 | Gail Siddall | 3 | 2 | 3 | 2 | 2 | 2 |  | Review and implement appropriate consultation project and ensure requirements of legislation fulfilled.
Legal challenge | A legal challenge to the proposals is put forward as a judicial review | Opp and Threat | Statutory requirements not met. Insufficient resources provided to fulfil requirements. Insufficient evidence base. Lack of wider consultation | Scheme will not proceed until legal challenge resolved | Mar 2020 | Gail Siddall | 3 | 3 | 3 | 2 | 2 | 2 |  | Ensure that statutory requirements for proving the case for selective licensing is robust and are met and that sufficient resources provided to undertake comprehensive consultation.
Changes to Government Policy | Change in government policy in relation to Selective licensing schemes which require their approval | Threat | The COVID 19 pandemic may reduce the appetite for regulatory activity including the introduction of discretionary licensing schemes | The government may not approve the scheme or require further evidence from the council | January 2021 | Gail Siddall | 4 | 3 | 4 | 3 | 4 | 3 | Government policy will be kept under review throughout the consultation period. | If policy is changed officers will review and inform cabinet
IT system | The number of applications expected in year 1 will require a robust and tested application processing system | Threat | The current system is not designed to cope with a large number of applications. It requires manual transference of data from one system to another. | Applications not processed in timely manner and staff input into processing will be increased leading to further costs. Reputational damage to the scheme will occur if licences are delayed. | January 2021 | Gail Siddall/Michelle Iddon | 3 | 4 | 3 | 4 | 3 | 4 | The Council is implementing a robotic system to improve efficiencies in the applications process - | The robotic processing is being introduced before selective licensing ( if agreed) will be implemented, giving the opportunity to test the system.
Impacts on the housing market | The rollout of selective licensing may have some unintended impacts on the housing market | Threat | Selective licensing will be used to enable the improvement of standards in the PRS. Landlords will need to pay for a licence, and some landlords will need to invest in their properties to comply with minimum statutory standards. The scheme will also drive financial transparency in the sector, which will not be welcomed by all Landlords. | Some landlords may exit the market and others will rely more on professionals to manage their stock. Others may use the scheme as a reason to justify increasing rents which could impact affordability in the housing market. | 2020-07-01 | Gail Siddall/ Nerys Parry | 4 | 3 | 4 | 2 | 3 | 2 |  | Close working between Regulatory Services and Community Safety and Housing Services to ensure impacts on the housing market, tenants and prospective PRS tenants are considered, closely monitored, and responded to throughout the design process, and into implementation (if licensing goes ahead). Consider how selective licensing and the council's PRS access schemes align (such as Homechoice), to ensure homeless families can access the PRS. |  | Ongoing |  | Gail Siddall/ Nerys Parry