# Housing Strategy (CEB Report 7th December 2011): Risk Register

| No. | Risk Description Link to Corporate Obj | Gross Risk | Cause of Risk | Mitigation | Net Risk | Further Management of Risk: Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Current Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Score Impact Score: 1 =Insignificant; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Catastrophic Probability Score: 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost Certain |
|  |  | I | P |  | Mitigating Control: Level of Effectiveness: (HML) | I | P | Action: Action Owner: Mitigating Control: Control Owner: | Outcome required: Milestone Date: | Q 1 ((( | Q 2((( | Q 3((( | Q4((( | I | P |
| 1. | Failure to meet the objectives of the draft Housing Strategy 2011/12 to 2015/16. | 4 | 3 | Ineffective monitoring of the strategic objective action plans. | Establish clear monitoring process within the Council’s structure including CEB and CMT, Scrutiny and tenants panel. | 3 | 2 | Link monitoring into wider partnership structures (e.g. OSP) to ensure contribution and buy-in form external agencies / partners. Strategy & Enabling Manager. | Set monitoring meetings on relevant agendas for internal and partnership meetings. By April 2012. |  |  |  |  |  |  |
| 2. | Changes to housing policy or context and, local, regional and national, making objectives invalid or inappropriate. | 3 | 3 | Economic circumstances, government policy and legislation, political changes. | Establish annual review of the strategy and objectives to ensure it remains relevant to current circumstances. | 3 | 3 | Establish Housing strategy monitoring group under the Physical and Economic Regen Board. Strategy and Enabling Manager | Annual review completed by December 2012. |  |  |  |  |  |  |
| 3. | Negative public understanding / perceptions of housing strategy objectives. | 3 | 3 | Failure to communicate objectives and impacts on housing in Oxford. | Establish clear communication strategy for the housing strategy for when it is adopted. | 2 | 3 | Ongoing communication and engagement of housing strategy objectives and in particular of individual projects and programmes. Strategy & Enabling Manager | Communication Strategy in place by December 2011. |  |  |  |  |  |  |