## Capital Programme
Appendix 6
Draft Capital Programme 2011/12 to 2015/16
Capital Scheme | Budget 2010-11 Agresso | Spend as at 31st March 11 | Variance to current budget | Carry forward requested | Comment | Budget 2012 Agresso | Budget 2013 Agresso | Budget 2014 Agresso | Budget 2015 Agresso | 2011/12 | Cary Forward | Restated 2011/12 | Spend as at 30th August | Variation | 2011/12 Forecast outurn | % Spend Against Budget | Variation | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17
[18 empty] | £ | £ | £ | £
General Fund Capital Programme | [14 empty] | £ | [6 empty] | £
A1500 Paradise Street - work of art | 661 | 0 | -661 | 661 | BC:Developer Contribution - has not spend in 2010/11 but the scheme is due to complete in 2011/12 | 0 | 0 | 0 | 0 | 0 | 661 | 661 | 294 | -367 | 294 | 44.48% | -367
F0010 Gloucester Green Safety Measures | [10 empty] | 0 | 0 | 2165.23 | 2165.23 | 0 | 0% | 0
F1323 Bridge Over Fiddlers Stream | 2855 | 2855.38 | 0.38 | -0.38 |  | 56057 | 0 | 0 | 0 | 0 | -0.38 | -0.38 | 0 | 0.38 | -0.38 | 0% | 0
F1330 Wwork at Donnington Middle School |  |  |  | 0 | [5 empty] | 1662 | 0 | 1662 | 84 | -1578 | 1662 | 5.054% | 0
F1332 West End Contributions |  |  |  | 0 | [5 empty] | 172271 | 0 | 172271 | 0 | -172271 | 172271 | 0% | 0
F6015 Slade Area Public Work of Art | 6743 | 750 | -5993 | 5993 | BC:Developer Contribution - the scheme commence late but this will be spent in 2011/12 | 0 | 0 | 0 | 0 | 0 | 5993 | 5993 | 114 | -5879 | 5993 | 1.902% | 0
F7004 Littlemore Village Hall - improvement of facilities | 10000 | 10000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F7005 Oxford Road /Littlemore improvement |  |  |  | 0 | [5 empty] | 17624 | 0 | 17624 | 0 | -17624 | 17624 | 0% | 0
F7006 Work of art littlemore |  |  |  | 0 | [5 empty] | 17850 | 0 | 17850 | 133 | -17717 | 17850 | 0.7451% | 0
NEW Landscaping Work Lamarsh Road | [14 empty] | 12500
NEW Landscaping Work Lamarsh Road | [14 empty] | 3229
NEW CCTV Gipsy Lane Campus | [14 empty] | 60000
M5002 Refurbishment of Bonn Square | 8035 | 7175.76 | -859.24 | 859 | BC: I have been told that the scheme has been competed however, there is still a small amount of internal recharges has not been paid | 0 | 0 | 0 | 0 | 0 | 859 | 859 | -620 | -1479 | 859 | -72.18% | 0
M5014 West End Partnership (Growth Points Grant) | 252203 | 125111.55 | -127091.45 | 127091 | BC: the scheme is a continuous project and funded from an external grant so, any under spend will be carried forward to 2011/12 as in previous years | 770000 | 0 | 0 | 0 | 35000 | 127091 | 162091 | 10875 | -151216 | 162091 | 6.709% | 0
M5016 Housing Delivery (Funded via New Growth Points) | 184671 | 0 | -184671 | 184671 | BC: this is 2009/10 under spend grant and recent review of eligible capital expenditure definition has let to substantial carry forward. In 2011/12 will ensure expenditure on actual housing delivery. | 0 | 0 | 0 | 0 | 0 | 184671 | 184671 | 35500 | -149171 | 184671 | 19.22% | 0
NEW Land at Barton |  |  |  | 0 | [5 empty] | 500000 | 0 | 500000 | 0 | -500000 | 0 | 0% | -500000
S11 City Development Total | 465168 | 145892.69 | -319275.31 | 319274.62 |  | 826057 | 0 | 0 | 0 | 744407 | 319274.62 | 1063681.62 | 48545.23 | -1015136.39 | 639043.62 | 4.564% | -424638 | 0 | 0 | 0 | 0 | 0
E3511 Renovation Grants | 30000 | -4448.91 | -34448.91 | 34449 | Grant refunds exceeded expenditure | 50000 | 50000 | 50000 | 50000 | 50000 | 34449 | 84449 | -3400.83 | -87849.83 | 84449 | -4.027% | 0 | 50000 | 50000 | 50000
E3521 Disabled Facilities Grants | 695000 | 646530.15 | -48469.85 | 0 | 09/10 cfwd already slipped into 11/12 (£28,192) - addditional funding (£55k already received to further add to 11/12 budget | 695000 | 640000 | 640000 | 640000 | 640000 | 0 | 640000 | 92806.72 | -547193.28 | 695000 | 14.5% | 55000 | 640000 | 640000 | 640000 | 640000 | 640000
S12 Environmental Development Total | 725000 | 642081.24 | -82918.76 | 34449 |  | 745000 | 690000 | 690000 | 690000 | 690000 | 34449 | 724449 | 89405.89 | -635043.11 | 779449 | 12.34% | 55000 | 690000 | 690000 | 690000 | 640000 | 640000
F1096 West Oxford Cylce Route | 16152 | 15998.15 | -153.85 | 0 | BC:Developer Contribution - Invoice received after the year end and this has now been paid in 2011/12 | 0 | 0 | 0 | 0 | 63446 | 0 | 63446 | 0 | -63446 | 63446 | 0% | 0
F5008 West Oxford Cylce Route | 16152 | 15998.15 | -153.85 | 154 | BC:Developer Contribution - Invoice received after the year end and this has now been paid in 2011/12 | 0 | 0 | 0 | 0 | 0 | 154 | 154 | 0 | -154 | 154 | 0% | 0
F5010 Marsh Lane to Stockleys Rd cycle link | 50001 | 38279.82 | -11721.18 | 11721 | BC:Developer Contribution - the scheme has commenced late and this will be completed in 2011/12 | 0 | 0 | 0 | 0 | 0 | 11721 | 11721 | 4223.99 | -7497.01 | 11721 | 36.04% | 0
F5011 Barton Cycle Link | 0 | 0 | 0 | 0 |  | 48225 | 0 | 0 | 0 | 48225 | 0 | 48225 | 0 | -48225 | 48225 | 0% | 0
F6012 Wood Farm Community Centre - provision or enhancement of facilities | 50000 | 50000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F6013 Bullingdon Community Centre - provision or enhancement of facilities | 18500 | 13693 | -4807 | 4807 | BC:Developer Contribution - on going scheme and this will be spent in 2011/12 | 0 | 0 | 0 | 0 | 0 | 4807 | 4807 | 0 | -4807 | 25193 | 0% | #REF!
F6014 Rose Hill provision or enhancement of community facilities |  |  |  | 0 | [5 empty] | 225820 | 0 | 225820 | 0 | -225820 | 225820 | 0% | 0
F7007 Woodfarm/headington Community Centre- Improvements |  |  |  | 0 | [5 empty] | 19887 | 0 | 19887 | 0 | -19887 | 19887 | 0% | 0
G3013 Diamond Place car park footpath extension | 6324 | 0 | -6324 | 6324 | JG: I was told that this project was completed back in October and have been accruing for the invoice since then. I was expecting Property to have paid the invoice at the end of the year. | 0 | 0 | 0 | 0 | 0 | 6324 | 6324 | 0 | -6324 | 6324 | 0% | 0
G3014 East Oxford Community Association Improvements | 2550 | 0 | -2550 | 2550 | JG: I was requested to move an additional £2550 from revenue but forgot to add this to the total to be slipped into 11/12. The reason for the slippage is that the specifications for the project are still being agreed | 4880 | 0 | 0 | 0 | 0 | 2550 | 2550 | 0 | -2550 | 2550 | 0% | 0
G4006 Florence Park CC Kitchen | 4057 | 2646.25 | -1410.75 | 1411 | JG: received confirmation on 10/03/11 that one item for this project (notice board) is outstanding and won't be completed until early 11/12 The £1400 needs slipping into 11/12. What I appear to have done is slipped £1400 from G6010 instead of G4006. | 0 | 0 | 0 | 0 | 0 | 1411 | 1411 | 0 | -1411 | 1411 | 0% | 0
G6010 Mount Place Square Refurbishment | 11602 | 10200.53 | -1401.47 | 1401 | JG: slipped the £1400 from the wrong code. Should have been from G4006. Therefore the variance should be £2801, I was informed on the 10th March that this would not be fully completed and the underspend would need slipping. | 1400 | 0 | 0 | 0 | 0 | 1401 | 1401 | 0 | -1401 | 1401 | 0% | 0
G6012 South Oxford Community Centre Main Hall Replacement | 8100 | 6962 | -1138 | 1138 | JG: I was informed by JMB on 22nd March that this project would be finished by the end of the year. An AJ was input into the system so I am assuming that this is the final amount. | 0 | 0 | 0 | 0 | 8100 | 1138 | 9238 | 0 | -9238 | 9238 | 0% | 0
M5012 Rose Hill Redevelopment | 0 | 109348.81 | 109348.81 | 0 | JG: This project has been going on for a number of years and each year the spend has been accrued for to offset it against the expected income. However this treatment is incorrect. Any income should not show in this line. The project has now been invoiced for and the capital element of the receipt is in the funding area. | 0 | 0 | 0 | 0 |  | 0 | 0 | 1023 | 1023 | 1023 | 0% | 1023
M5013 Affordable Housing - Garage Sites |  |  |  | 0 | [5 empty] | 116429 | 0 | 116429 | 0 | -116429 | 116429 | 0% | 0
M5015 Old Fire Station | 1601956 | 915239.96 | -686716.04 | 686716 | JG: There have been a number of delays to this project. | 1874756 | 90000 | 0 | 0 | 1666778 | 686716 | 2353494 | 1189193.93 | -1164300.07 | 2653494 | 50.53% | 300000 | 90000
M5018 Wood Farm Community Building Project |  |  |  | 0 | [5 empty] | 56000 | 0 | 56000 | 0 | -56000 | 56000 | 0% | 0
Z3718 St Lukes Church - community/facilities |  |  |  | 0 | [5 empty] | 16362 |  | 16362 | 0 | -16362 | 16362 | 0% | 0
S13 Community Housing & Development Total | 1785394 | 1178366.67 | -607027.33 | 716222 |  | 1929261 | 90000 | 0 | 0 | 2221047 | 716222 | 2937269 | 1194440.92 | -1742828.08 | 3258678 | 40.67% | 321409 | 90000 | 0 | 0 | 0 | 0
A4800 Barton Pool | 10237 | 31730.28 | 21493.28 | -21493.28 | Over spend netted off under spend from A4800 to A4809 which leaves £267,638 under spend, request to carry forward to 2011/12 | 0 | 0 | 0 | 0 | 0 | -21493.28 | -21493.28 | 0 | 21493.28 |  | 0% | 21493.28
A4801 BBL Pool | 38350 | 55795.83 | 17445.83 | -17445.83 | spend from A4800 to | 0 | 0 | 0 | 0 | 0 | -17445.83 | -17445.83 | 183.1 | 17628.93 |  | -1.05% | 17445.83
A4802 BBL LC | 671533 | 107985.26 | -563547.74 | 563547.74 | A4809 which leaves £267,638 | 0 | 0 | 0 | 0 | 0 | 563547.74 | 563547.74 | 0 | -563547.74 |  | 0% | -563547.74
A4803 Ferry LC | 135877 | 78942.35 | -56934.65 | 56934.65 | under spend, request | 0 | 0 | 0 | 0 | 0 | 56934.65 | 56934.65 | -1310 | -58244.65 |  | -2.301% | -56934.65
A4804 Hinksey Pool | 125636 | 86473.64 | -39162.36 | 39162.36 | to carry forward to | 0 | 0 | 0 | 0 | 0 | 39162.36 | 39162.36 | 22021.3 | -17141.06 | 23301 | 56.23% | -15861.36
A4805 Temple Cowley Pool | 10837 | 84330.91 | 73493.91 | -73493.91 | 2011/12 | 0 | 0 | 0 | 0 | 0 | -73493.91 | -73493.91 | -20.04 | 73473.87 | 28130 | 0.02727% | 101623.91
A4806 Ice Rink | 256863 | 759308.8 | 502445.8 | -502445.8 |  | 0 | 0 | 0 | 0 | 0 | -502445.8 | -502445.8 | 1651.58 | 504097.38 | 96521 | -0.3287% | 598966.8
A4807 Barton Pool Improvements | 614880 | 602286.6 | -12593.4 | 12593.4 |  | 33000 | 0 | 0 | 0 | 33000 | 12593.4 | 45593.4 | 76686.91 | 31093.51 |  | 168.2% | -45593.4
A4808 Blackbird Leys LC Improvements | 730958 | 433829.56 | -297128.44 | 297128.44 |  | 38000 | 0 | 0 | 0 | 38000 | 297128.44 | 335128.44 | 0 | -335128.44 | 335128.44 | 0% | 0
A4809 Ferry Sports Centre Improvements | 570673 | 657522.84 | 86849.84 | -86849.84 |  | 30000 | 0 | 0 | 0 | 30000 | -86849.84 | -56849.84 | 0 | 56849.84 |  | 0% | 56849.84
B0003 Roof Repairs & Ext Refur 44-46 George St |  |  |  | 0 | [5 empty] | 30000 | 0 | 30000 | 0 | -30000 |  | 0% | -30000
B0010 Covered Market signage improvements |  |  |  | 0 | [5 empty] | 12147 | 0 | 12147 | 0 | -12147 |  | 0% | -12147
B0012 BBL CC - wiring Improvements | 10000 | 0 | -10000 | 10000 | BC: due to delay of scheme this amount is requested be carry forward to 2011/12 | 15000 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | -10000 | 14730 | 0% | 4730
B0014 South oxford CC - replacement rainwater goods | 79510 | 79510.06 | 0.06 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14729.7 | 14729.7 | 0 | 0% | 0
B0015 South Oxford CC - Roof refurbishments | 40218 | 33212.06 | -7005.94 | 7006 | BC: £7,006 request to carry forward to 2011/12 | 0 | 0 | 0 | 0 | 0 | 7006 | 7006 | 0 | -7006 | 7006 | 0% | 0
B8347 South Oxon Comm. Centre - install new lift 04/05 | 7586 | 7585.87 | -0.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
B9202 Parks properties (H&S works | 3352 | 3351.8 | -0.2 | 0 |  | 36648 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
B9203 Community Centres - Water Bylaws and Legionella | 30000 | 18500 | -11500 | 11500 | BC: pay £18,500 for B9021 then the balance of £ 11,500 request to carry forward to 2011/12 | 0 | 0 | 0 | 0 |  | 11500 | 11500 | 0 | -11500 |  | 0% | -11500
Communkity centres | [14 empty] | 82500
Rose hill community centre | [14 empty] | 50000
B9207 Northway Centre Demolition | 54476 | 54458.06 | -17.94 | 18 | BC: the scheme is a continuous project so, any under spend will be carried forward to 2011/12 | 0 | 0 | 0 | 0 |  | 18 | 18 | 0 | -18 |  | 0% | -18
F1103 Beenhams, Railway Lane - Affordable Housing Scheme | 145000 | 145000 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
Q2000 Offices for the Future | 883000 | 995571.16 | 112571.16 | -112571 | Carry forward overspend to fund by 11/12 budget | 3823000 | 522000 | 0 | 0 | 3553000 | -112571 | 3440429 | 973410.89 | -2467018.11 | 3440429 | 28.29% | 0 | 792000
Z7500 Building Improvements (General Fund) | 102011 | 0 | -102011 | 102011 | Budget to be increased by £82k to match approved budget agreed at council - then this is to be used to fund any overspends in A4800-A4806. | 787000 | 630000 | 700000 | 700000 | 0 | 102011 | 102011 | 0 | -102011 |  | 0% | -102011
B0022 DDA East Oxford Community Centre Lift | 2352 | 2352 | 0 | 0 |  | 62648 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 65000 | 0% | 65000
B1001 Blackwells Music Shop repairs | 10000 | 0 | -10000 | 10000 | BC: due to delay of scheme this amount is requested be carry forward to 2011/12 | 60000 | 0 | 0 | 0 | 35000 | 10000 | 45000 | 0 | -45000 | 5000 | 0% | -40000
B1002 -Town Hall PA system upgrades | 30000 | 1810 | -28190 | 28190 | BC: due to delay of scheme this amount is requested be carry forward to 2011/12 | 0 | 0 | 0 | 0 | 0 | 28190 | 28190 | 0 | -28190 | 28190 | 0% | 0
B1003 - Town Hall pigeon proofing | 5000 | 0 | -5000 | 5000 | BC: due to delay of scheme this amount is requested be carry forward to 2011/12 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | -5000 | 5000 | 0% | 0
B1004 - Covered Market repairs/upgrading | 1216 | 1216.45 | 0.45 | 0 |  | 23784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
B1005 Town Hall |  |  |  | 0 | [5 empty] | 10000 | 0 | 10000 | 0 | -10000 | 10000 | 0% | 0
B1006 Bury Knowle external repair/decoration |  |  |  | 0 | [5 empty] | 25000 | 0 | 25000 | 0 | -25000 |  | 0% | -25000
Z7506 Building Improvements (GF Leisure) | 130000 | 0 | -130000 | 130000 | BC: the scheme is a continuous project so, any under spend will be carried forward to 2011/12 | 0 | 0 | 0 | 0 |  | 130000 | 130000 | 0 | -130000 | 130000 | 0% | 0
NEW Parks and cemetery stone wall & path improvements |  |  |  | 0 | [5 empty] | 35000 | 0 | 35000 | 0 | -35000 | 35000 | 0% | 0
NEW Refurbishment of Council Buildings |  |  |  | 0 | [5 empty] | 1000000 | 0 | 1000000 | 0 | -1000000 |  | 0% | -1000000 | 2011000 | 1400000 | 1400000 | 600000 | 600000
NEW Improvements and upgrade of roof at covered market |  |  |  | 0 | [5 empty] | 85000 | 0 | 85000 | 0 | -85000 | 85000 | 0% | 0
NEW Installation to new roof structures at Avenue A3 from High St in Cov Mark |  |  |  | 0 | [5 empty] | 30000 | 0 | 30000 | 0 | -30000 | 30000 | 0% | 0 | 85000
Investment covered market | [14 empty] | 70000
Public toilets | [14 empty] | 2500
Misc admin buildings | [14 empty] | 20000
Misc civic proiperties | [14 empty] | 4500
Bury knowle House | [14 empty] | 65000
Investment broad street | [14 empty] | 55000
Investment city centre properties | [14 empty] | 5000
Property surveys | [14 empty] | 100000
Town Hall | [14 empty] | 216810
NEW Upgrade to lettable condition 33-35 George St |  |  |  | 0 | [5 empty] | 57000 | 0 | 57000 | 0 | -57000 |  | 0% | -57000
NEW Hinksey Pools main pool liner |  |  |  | 0 | [5 empty] | 110000 | 0 | 110000 | 16151 | -93849 | 110000 | 14.68% | 0
NEW Leisure Centre substantive repairs |  |  |  | 0 | [5 empty] | 425000 | 0 | 425000 | 0 | -425000 | 425000 | 0% | 0 | 245000 | 110000 | 66000
NEW Consolidation of Parka department South Parks to Cutteslowe | 130000 | 0 | -130000 | 0 | BC: the scheme is a continuous project so, any under spend will be carried forward to 2011/12 | 0 | 0 | 0 | 0 | 60000 | 0 | 60000 | 0 | -60000 | 60000 | 0% | 0
B0056 City Centre Office Security | [14 empty] | 100000
NEW- Town Hall fire escape (Blue Boar Street) | [14 empty] | 55000
S14 Corporate Assets Total | 4829565 | 4240773.53 | -588791.47 | 458791.93 |  | 4909080 | 1152000 | 700000 | 700000 | 5568147 | 458791.93 | 6026938.93 | 1103504.44 | -4923434.49 | 5759745.44 | 18.31% | -267193.49 | 3133000 | 1510000 | 1466000 | 600000 | 600000
C3041 New server for telephone system | 18000 | 0 | -18000 | 18000 | c-fwd to 11/12 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 6712 | -11288 | 18000 | 37.29% | 0
NEW Customer First Programme |  |  |  | 0 | [5 empty] | 161000 | 0 | 161000 | 0 | -161000 | 161000 | 0% | 0
S21 Customer Services Total | 18000 | 0 | -18000 | 18000 |  | 0 | 0 | 0 | 0 | 161000 | 18000 | 179000 | 6712 | -172288 | 179000 | 3.75% | 0 | 0 | 0 | 0 | 0 | 0
A1161 Frys Hill Leisure Centre | 1738062 | 1152552.56 | -585509.44 | 0 | schemes delayed into 11-12. Due to small budget set in 11-12, carryfwd of any underspend required. | 100000 | 0 | 0 | 0 | 140074 | 0 | 140074 | 0 | -140074 | 140074 | 0% | 0
A1300 Playground Refurbishment | 1738062 | 1152552.56 | -585509.44 | 585509 | schemes delayed into 11-12. Due to small budget set in 11-12, carryfwd of any underspend required. | 100000 | 0 | 0 | 0 | 808062 | 585509 | 1393571 | 149539.48 | -1244031.52 | 435509 | 10.73% | -958062 | 250000
A2808 Replacement Sports Facilities - Cowley Marsh | 49783 | 49775 | -8 | 0 | BC:Developer Contribution - waiting a final invoice and this will be spent in 2011/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
A3115 Barton Village Recreation Groung - Improvements |  |  |  | 0 | [5 empty] | 82545 | 0 | 82545 | 0 | -82545 | 0 | 0% | -82545
A3120 Florence Park Public Open Space/children Play Area |  |  |  | 0 | [5 empty] | 25346 | 0 | 25346 | 0 | -25346 | 25346 | 0% | 0
A3124 Barton Village Pavillion | 10000 | 2232.2 | -7767.8 | 7768 | BC:Developer Contribution - on going scheme and this will be spent in 2011/12 | 207362 | 0 | 0 | 0 | 182608 | 7768 | 190376 | 270564.34 | 80188.34 | 350311 | 142.1% | 159935
A3125 Milham Ford Park land and Recreational Facilities |  |  |  | 0 | [5 empty] | 32130 | 0 | 32130 | 0 | -32130 | 32130 | 0% | 0
A3129 Donnington Recreation Ground Improvements |  |  |  | 0 | [5 empty] | 44375 | 0 | 44375 | 0 | -44375 | 44375 | 0% | 0
F6001 Ferry Centre - provision or enhancement of facilities | 19306 | 19306 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F6002 Temple Cowley Pool Provision or enhancement of facilities |  |  |  | 0 | [5 empty] | 26473 | 0 | 26473 | 0 | -26473 | 26473 | 0% | 0
F6003 Barton Pool - Provision of indoor sports facilities | 8640 | 8640 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F6004 St Christophers Place - enhancement of play area | 8057 | 8057 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F6005 Barracks lane Allotments - enhancement of facilities | 112 | 112.29 | 0.29 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F6006 Sunnymead Park - enhancement of play area facilities |  |  |  | 0 | [5 empty] | 1830 | 0 | 1830 | 0 | -1830 | 1830 | 0% | 0
F6009 Town Furze Allotments - enhancement of facilities | 677 | 338.5 | -338.5 | 339 | BC:Developer Contribution - on going scheme and this will be spent in 2011/12 | 0 | 0 | 0 | 0 | 0 | 339 | 339 | 0 | -339 | 339 | 0% | 0
F6010 Dene Road Play Area - enhancement of facilities at dene road or bullingdon | 17669 | 17669 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F7001 Cuddesdon Way -relocation of street sports site |  |  |  | 0 | [5 empty] | 60000 | 0 | 60000 | 0 | -60000 | 60000 | 0% | 0
F7002 Margaret Road Recreation Ground - Improvments |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
F7003 Temple Cowley/Blackbird Leys - improvements to indoor |  |  |  | 0 | [5 empty] | 1320 | 0 | 1320 | 0 | -1320 | 1320 | 0% | 0
Z3008 Contribution to Skate Park |  |  |  | 0 | [5 empty] | 50000 | 0 | 50000 | 0 | -50000 | 50000 | 0% | 0
Z3009 Contribution to Barton Pavilion |  |  |  | 0 | [5 empty] | 50000 | 0 | 50000 | 0 | -50000 | 0 | 0% | -50000
A1301 Play Barton | 800000 | 55535.5 | -744464.5 | 744465 | Scheme delayed due to funding uncertainty (Playbuilder grant initially pulled by central govt - then re-instated) | 0 | 0 | 0 | 0 | 800000 | 744465 | 1544465 | 20000 | -1524465 | 744465 | 1.295% | -800000
A4810 New Build Competion Pool | 635000 | 561929.36 | -73070.64 | 73071 | Exp of £562k to be transferred from Revenue - any underspend to needed in 11/12 for final project tender stage expenditure | 7365000 | 500000 | 0 | 0 | 7365000 | 73071 | 7438071 | 157496 | -7280575 | 1000000 | 2.117% | -6438071 | 6938071
Z8009 Bury Knowle Park - Improvements | 14000 | 0 | -14000 | 14000 | c-fwd to 11/12 | 0 | 0 | 0 | 0 | 0 | 14000 | 14000 | 0 | -14000 | 14000 | 0% | 0
Z3010 Rosehill/IffleY Play Sites | 38000 | 0 | -38000 | 38000 | Linked to £37k Revenue budget in Parks which is part of a larger Rose Hill.scheme in Comm Housing (F6014) | 0 | 0 | 0 | 0 | 0 | 38000 | 38000 | 0 | -38000 | 38000 | 0% | 0
NEW Develop new burial space | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 1000000
NEW Ice Rink improvments of facilities | [9 empty] | 6960 | 0 | 6960 | 0 | -6960 | 6960 | 0% | 0
NEW North/Jericho Area - Provision of indoor sport | [9 empty] | 2100 | 0 | 2100 | 0 | -2100 | 2100 | 0% | 0
NEW Slade Area - Indoor/Outdoor sprots facilities | [9 empty] | 1260 | 0 | 1260 | 0 | -1260 | 1260 | 0% | 0
NEW Recreation/Sports - City of Oxford | [9 empty] | 200000 | 0 | 200000 | 0 | -200000 | 200000 | 0% | 0
NEW Oxrad/Ferry indoor sports | [9 empty] | 11018 | 0 | 11018 | 0 | -11018 | 11018 | 0% | 0
NEW Florence park Improvements | [9 empty] | 631 | 0 | 631 | 0 | -631 | 631 | 0% | 0
NEW Herschel Crescent Ground Improvements | [9 empty] | 7002 | 0 | 7002 | 0 | -7002 | 7002 | 0% | 0
NEW Rose Hill Play Area Improvements | [9 empty] | 3000 | 0 | 3000 | 0 | -3000 | 3000 | 0% | 0
G1013 Dawson Street Gardens | [14 empty] | 19000
G3015 NE Marston Croft Road Recreation Ground | [14 empty] | 25000
G3016 Peat Moors all weather pitch | [14 empty] | 17000
NEW Rose Hill Recreation Ground Improvements | [9 empty] | 3000 | 0 | 3000 | 0 | -3000 | 3000 | 0% | 0
NEW Rose Hill Work of Art | [9 empty] | 8000 | 0 | 8000 | 0 | -8000 | 8000 | 0% | 0
S22 City Leisure Total | 5077368 | 3028699.97 | -2048668.03 | 1463152 |  | 7772362 | 500000 | 0 | 0 | 9912734 | 1463152 | 11375886 | 597599.82 | -10778286.18 | 3268143 | 5.253% | -8107743 | 7188071 | 1000000 | 0 | 0 | 0
A1217 Aristotle Lane Improvements | 1880 | 1850 | -30 | 0 | BC:Developer Contribution - waiting a final invoice and this will be spent in 2011/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
pay and siplay machine sin parks | [14 empty] | 60550
F6011 Meadow Lane - improvements to recreational facilities | 31500 | 31500 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
R0005 MT Vehicles/Plant Replacement Prog. | 1892178 | 925555.81 | -966622.19 | 491400 | Undelivered vehicles and replacement programme carry over | 292000 | 1280000 | 1719000 | 1678000 | 292000 | 491400 | 783400 | 193424.01 | -589975.99 | 783400 | 24.69% | 0
Brown bins for recycling |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 230000 | 0% | 230000
NEW Purchase of two hand operated street sweepers |  |  |  | 0 | [5 empty] | 30000 | 0 | 30000 | 0 | -30000 | 30000 | 0% | 0
NEW Purchase of two vehicles for garden waste collection |  |  |  | 0 | [5 empty] | 308000 | 0 | 308000 | 0 | -308000 | 155000 | 0% | -153000
NEW Purchase of ANPR for use in car park enforcement |  |  |  | 0 | [5 empty] | 50000 | 0 | 50000 | 0 | -50000 | 50000 | 0% | 0
NEW Pay & Display machines | 600000 | 595739.65 | -4260.35 | 0 | No carry forward required | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 84000
S23 City Works Total | 2525558 | 1554645.46 | -970912.54 | 491400 |  | 292000 | 1280000 | 1719000 | 1678000 | 680000 | 491400 | 1171400 | 193424.01 | -977975.99 | 1308950 | 16.51% | 137550 | 84000 | 0 | 0 | 0 | 0
C3039 ICT Infrastructure | 330703 | 280703.04 | -49999.96 | 0 |  | 99069 | 150000 | 200000 | 100000 | 100000 | 0 | 100000 | 0 | -100000 | 100000 | 0% | 0 | 150000 | 200000 | 100000
NEW ICT Development |  |  |  | 0 | [5 empty] | 200000 | 0 | 200000 | 0 | -200000 | 200000 | 0% | 0
S31 Business Transformation Total | 330703 | 280703.04 | -49999.96 | 0 |  | 99069 | 150000 | 200000 | 100000 | 300000 | 0 | 300000 | 0 | -300000 | 300000 | 0% | 0 | 150000 | 200000 | 100000 | 0 | 0
Existing Programme | [14 empty] | 15493009.06 |  | 15493009.06 | 11335071 | 3400000 | 2256000 | 1240000 | 1240000
0
New Capital Schemes | [16 empty] | 0
1 Floyd Row | [16 empty] | 0 | 125000 | 0 | 0 | 0 | 0
CCTV Replacement Programme | [16 empty] | 0 | 84271 | 0 | 0 | 0 | 0
Vehicle & Plant Replacement Programme | [16 empty] | 0 | 1280000 | 2301000 | 1991000 | 1799000 | 483000
New Depot | [16 empty] | 0 | 0 | 2000000 | 0 | 0 | 0
Leisure Centre Improvement Work | [16 empty] | 0 | 700000 | 0 | 0 | 0 | 0
Software Licences | [16 empty] | 0 | 177000 | 177000 | 177000 | 177000 | 177000
Northway Playing Field (Purchase of Land) | [14 empty] | 20000 |  | 20000 | 0 | 0 | 0 | 0 | 0
Covered Market Replacement Sprinker System | [16 empty] | 0 | 150000 | 0 | 0 | 0 | 0
Cemetery Development | [16 empty] | 0 | 15000 | 0 | 0 | 0 | 0
Corporate Property Planned Maintenace Programme Yrs 5 & 6 | [16 empty] | 0 | 0 | 0 | 0 | 310000 | 310000
Covered Market - Improvements to Emergency Lighting | [16 empty] | 0 | 50000 | 0 | 0 | 0 | 0
Lye Valley & Chiswell Valley Walkways | [16 empty] | 0 | 62000 | 62000 | 0 | 0 | 0
ICT Infrastructure | [16 empty] | 0 | 0 | 0 | 0 | 150000 | 150000
Sports Pavillions | [16 empty] | 0 | 450000 | 470000 | 200000 | 0 | 0
Rose Hill Cemetery Water Leak | [16 empty] | 0 | 8000 | 0 | 0 | 0 | 0
Parks & Cemetery - Masonry Walls & Path Improvements | [16 empty] | 0 | 40000 | 40000 | 40000 | 0 | 0
Town Hall - Fire Alarm replacement & upgrade | [16 empty] | 0 | 100000 | 0 | 0 | 0 | 0
Upgrade Existing Tennis Courts | [16 empty] | 0 | 50000 | 60000 | 54000 | 60000 | 24000
Upgrade Existing Multi-Use Games Area | [16 empty] | 0 | 76000 | 48000 | 48000 | 48000 | 64000
Recycling & Bin Improvement (City Parks) | [16 empty] | 0 | 38000 | 13000 | 12000 | 12000 | 0
Fencing Repairs across the City | [16 empty] | 0 | 150000 | 150000 | 150000 | 0 | 0
Town Hall - Audio visual equipment etc | [16 empty] | 0 | 400000
Carbon reduction | [18 empty] | 300000
Toilet improvments | [17 empty] | 185000 | 175000 | 80000
Cycle Oxford | [17 empty] | 100000 | 100000 | 50000 | 50000 | 50000
Bin stores for council flats to assit recycling | [17 empty] | 325000
Low emmission vehicle for litter bin collection | [17 empty] | 20000
Total New Capital Schemes | [14 empty] | 20000 |  | 20000 | 4585271 | 5896000 | 2802000 | 2606000 | 1258000
Total General Fund Schemes | 15756756 | 11071162.6 | -4685593.4 | 3501289.55 |  | 16572829 | 3862000 | 3309000 | 3168000 | 20277335 | 3501289.55 | 23778624.55 | 3233632.31 | -20544992.24 | 15513009.06 | 13.6% | -8265615.49 | 15920342 | 9296000 | 5058000 | 3846000 | 2498000
N6380 Windows 05/06 | 0 | -6522.55 | -6522.55 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
N6384 Foresters Towers | 779000 | 136926.17 | -642073.83 | 642074 | to fund future work programme | 150000 | 0 | 0 | 0 | 150000 | 642074 | 792074 | 874 | -791200 | 792074 | 0.1103% | 0
N6385 Adaptations for disabled | 580000 | 1158390.88 | 578390.88 | 0 |  | 900000 | 0 | 0 | 0 | 900000 | 0 | 900000 | 510244 | -389756 | 1139500 | 56.69% | 239500
Decent Homes |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
N6386 Structural | 100000 | 283712.4 | 183712.4 | 0 |  | 100000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 23851 | -76149 | 100000 | 23.85% | 0
N6387 Controlled Entry | 200000 | 2190.23 | -197809.77 | 197810 | Delayed start on the scheme | 100000 | 0 | 0 | 0 | 100000 | 197810 | 297810 | 213875 | -83935 | 287310 | 71.82% | -10500
N6388 Major Voids | 700000 | 1025104.11 | 325104.11 | 0 |  | 900000 | 0 | 0 | 0 | 900000 | 0 | 900000 | 252967 | -647033 | 900000 | 28.11% | 0
N6389 Damp-proof works (K&B) | 100000 | 102012.78 | 2012.78 | 0 |  | 100000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 20608 | -79392 | 100000 | 20.61% | 0
N6390 Kitchens (excluding wiring) | 4200000 | 2715289.05 | -1484710.95 | 0 | Decent homes schemes, to fund future overspends in these schemes | 3500000 | 0 | 0 | 0 | 3500000 | 0 | 3500000 | 1024928 | -2475072 | 3126500 | 29.28% | -373500
N6391 Heating | 1000000 | 1116274.29 | 116274.29 | 0 |  | 1000000 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 518777 | -481223 | 1239500 | 51.88% | 239500
N6392 Roofing | 200000 | 194792.24 | -5207.76 | 0 |  | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | -200000 | 200000 | 0% | 0
N6393 External Doors | 200000 | 200141.87 | 141.87 | 0 |  | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000 | 1882 | -198118 | 200000 | 0.941% | 0
N6394 Windows | 400000 | 418996.4 | 18996.4 | 0 |  | 900000 | 0 | 0 | 0 | 900000 | 0 | 900000 | 125310 | -774690 | 900000 | 13.92% | 0
N6395 Electrics | 400000 | 107723.58 | -292276.42 | 0 |  | 200000 | 0 | 0 | 0 | 200000 | 0 | 200000 | 12238 | -187762 | 179000 | 6.119% | -21000
N6396 Sheltered Blk, George Moore | 6783 | 6782.53 | -0.47 | 60000 |  | 150000 | 0 | 0 | 0 | 150000 | 60000 | 210000 | 0 | -210000 | 60000 | 0% | -150000
N6426 BISF´s | 0 | -434.17 | -434.17 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0
N6427 Shops | 200000 | 0 | -200000 | 200000 | to fund future work programme | 0 | 0 | 0 | 0 | 100000 | 200000 | 300000 | 0 | -300000 | 179000 | 0% | -121000
N6430 Evenlode tower | 0 | -895.13 | -895.13 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 8720 | 8720 | 0 | 0% | 0
N6431 Windrush Tower | 0 | -895.13 | -895.13 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
N6432 Plowman Tower | 67412 | 67411.53 | -0.47 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | -17.1 | -17.1 | 0 | 0% | 0
N7006 Northbrook House - Refurbishment | 43078 | 43077.67 | -0.33 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
N7010 Headley House - Refurbishment | 74122 | 74121.63 | -0.37 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 1370 | 1370 | 0 | 0% | 0
N7011 Cardinal House - Refurbishment | 7103784 | 3752617.88 | -3351166.12 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 66141 | 66141 | 420156 | 0% | 420156
N7012 Grantham House - Refurbishment | 768837 | 0 | -768837 | 1601000 | to fund future work programme | 100000 | 0 | 0 | 0 |  | 1601000 | 1601000 | 0 | -1601000 | 129000 | 0% | -1472000
N7013 Bradlands House - Refurbishment | 38613 | 38613.3 | 0.3 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
N7015 Knights House - Refurbishment | 1155 | 1154.58 | -0.42 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
N7017 Aireys | 0 | 212335.55 | 212335.55 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 19359 | 19359 | 83000 | 0% | 83000
N7019 Lambourn Road | 3281216 | 3281215.72 | -0.28 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 63996 | 63996 | 17000 | 0% | 17000
New Bids | [14 empty] | 108000 |  | 108000 | [5 empty] | 9446000 | 9360000 | 9285000 | 9210000 | 9140000
HRA New Capital Schemes
Tower Blocks | [17 empty] | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Adaptations for the disabled | [17 empty] | 900000 | 900000 | 900000 | 900000 | 900000
N6388 Major Voids | [17 empty] | 850000 | 830000 | 820000 | 800000 | 776000
Kitchens (excluding wiring) | [17 empty] | 1636000 | 1636000 | 1488000 | 1488000 | 1339000
Electrics (part of kitchen programme) | [17 empty] | 595000 | 595000 | 476000 | 417000 | 357000
Electrics rewires/upgrades | [17 empty] | 309000 | 309000 | 309000 | 309000 | 309000
Bathrooms | [17 empty] | 619000 | 619000 | 585000 | 585000 | 553000
Central Heating boilers | [17 empty] | 792000 | 792000 | 770000 | 770000 | 748000
Central Heating carcusses | [17 empty] | 464000 | 464000 | 451000 | 451000 | 439000
Roofs and associated works | [17 empty] | 250000 | 250000 | 250000 | 250000 | 250000
windows | [17 empty] | 300000 | 300000 | 300000 | 100000 | 100000
doors | [17 empty] | 200000 | 200000 | 200000 | 200000 | 200000
communal areas | [17 empty] | 150000 | 150000 | 150000 | 150000 | 150000
Environmental improvements | [17 empty] | 100000 | 100000 | 100000 | 100000 | 100000
related assets garages , shops etc | [17 empty] | 117000 | 117000 | 117000 | 117000 | 117000
contingency 5% major repairs | [17 empty] | 19000 | 19000 | 19000 | 19000 | 19000
Fees 7% | [17 empty] | 94000 | 94000 | 94000 | 80000 | 80000
Total Housing Revenue Account Capital Schemes | 20444000 | 14930137.41 | -5513862.59 | 2700884 |  | 8500000 | 0 | 0 | 0 | 8500000 | 2700884 | 11200884 | 2865122.9 | -8335761.1 | 10160040 | 25.58% | -1040844 | 8395000 | 8375000 | 8029000 | 7736000 | 7437000
0
Total Capital Programme | 36200756 | 26001300.01 | -10199455.99 | 6202173.55 |  | 25072829 | 3862000 | 3309000 | 3168000 | 28777335 | 6202173.55 | 34979508.55 | 6098755.21 | -28880753.34 | 25673049.06 | 17.44% | -9306459.49 | 24315342 | 17671000 | 13087000 | 11582000 | 9935000
Financing
Developer contributions | 500000 | 416055.99 | -83944.01 | 29506 | [7 empty] | 1584691 |  |  | 1744628 |  | 159937
Government Funding | 2050000 | 1547333 | -502667 | 311762 | [7 empty] | 4648280 |  |  | 3848280 |  | -800000 | 590000 | 390000 | 390000 | 390000 | 390000
Capital Receipts | 4822542 | 1496702 | -3325840 | 1396396 | [7 empty] | 7152242 |  |  | 6261809 |  | -890433 | 3700000 | 2512583 | 1000000 | 632220
Direct Revenue Funding-council repairs, dfg and ICT | 2500000 | 2404834 | -95166 | 0 | [7 empty] | 1723292 |  |  | 1423292 |  | -300000 | 3600000 | 1340000 | 1333280 | 1453780 | 1463000
Revenue Reserves | [14 empty] | 772000 |  | 772000 | 457505 | 356000
DRF for vehicles sinking fund | 4000000 | 4037688 | 37688 | 1763625 | [7 empty] | 1091400 |  |  | 1463000 |  | 371600 | 1291000 | 1230000 | 1270000 | 1370000 | 645000
Prudential Borrowing | [11 empty] | 7578720 |  |  |  |  | -7578720 | 6281837 | 3467417 | 1064720
MRA | 5300000 | 5367455 | 67455 | 0 | [7 empty] | 5200000 |  |  | 5200000 |  | 0 | 8395000 | 8375000 | 8029000 | 7736000
Total Financing | 13872542 | 9902612.99 | -3969929.01 | 3501289 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23778625 |  |  | 15513009 | 0 | -8265616 | 24315342 | 17671000 | 13087000 | 11582000 | 2498000
(Shortfall)/ Surplus | [11 empty] | #REF! |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | #REF!
Additional DRF | [17 empty] | 2000000 | 390000 | 340000 | 1000000 | 500000
Base drf | [14 empty] | 1423292 | 1150000 | 1200000 | 1150000 | 1200000 | 1100000 | 610000 | 610000
[15 empty] | 1423292 |  |  | 3150000 | 1590000 | 1440000 | 1610000 | 1110000
Prud Borrowing
Pool | [18 empty] | 535000 | 535000 | 535000 | 535000
Pru borrowing other | [19 empty] | 285000 | 285000 | 285000
[21 empty] | 142000 | 142000
65000
Reduction of pru borrwoing | [17 empty] | -90000 | -100000 | -100000 | -100000 | -100000
[20 empty] | -100000 | -100000 | -100000
[21 empty] | -90000 | -90000
[15 empty] | 0 | 0 | 0 | -90000 | 435000 | 620000 | 672000 | 737000
Note on H25: mmolyneux: PS to complete budget adjustment
Note on H26: mmolyneux: PS to put adjustment in agresso
Note on V172: nkennedy: #150k added for leys pavillion
Note on H238: mmolyneux: Cat is adjusting these budgets
Note on S245: nkennedy: play barton reduce by #800k
Note on V245: nkennedy: new bid #200k plus dfg
Note on A247: nkennedy: see mtfp spreadhseet
Note on V247: nkennedy: include #0.39m for extra drf re nhb
Note on W247: nkennedy: include #0.39m for extra drf re nhb
Note on X247: nkennedy: include #1m for extra drf re nhb
Note on Y247: nkennedy: include #1m for extra drf re nhb
Note on Z247: nkennedy: include #1m for extra drf re nhb
Note on S248: nkennedy: nhb #472 + #300k contingency
Note on V248: nkennedy: vat contributions
Note on W248: nkennedy: vat contributions
Note on X248: nkennedy: none specific -balancing figure
Note on A249: nkennedy: see separate spreadsheet
Note on Z249: nkennedy: adjusted to fit cap programme
Note on V250: nkennedy: #150k on sports paviliions
Note on W250: nkennedy: To cover shortfall in capital reciepts
Note on X250: nkennedy: To cover shortfall in capital reciepts
Note on Y250: nkennedy: To cover shortfall in capital reciepts