To: 	City Executive Board

Date:	8th February 2012

Report of:		Head of City Development

Title of Report: 	OXFORD CYCLE CITY

# Summary and Recommendations

Purpose of report:  To seek endorsement of the Oxford Cycle City project and draft Project Plan contained in this report

# Key decision?  No

Executive lead member:  Councillor Colin Cook

Policy Framework:  Oxford Core Strategy 2026

Oxford Sustainable Community Strategy

Recommendation(s):   The City Executive Board is asked to:

(1)  Endorse the objectives and draft project plan set out in this report and receive a subsequent report in due course on the specific initiatives and schemes proposed by the working group;

(2) Note the additional background information set out in this report.

# Appendices

- Risk register

# Background

- Oxford is acknowledged as one of few true ‘Cycling Cities’ in the United Kingdom. According to the 2001 Census, 15% of journeys made to work were by bike. This compares with less than 3% for the rest of the England and Wales. However there are still many barriers to cycling in Oxford, from the sometimes limited availability of secure cycle parking, to the poor cycling environment experienced where cyclists have to use heavily-trafficked roads.

- There is potential to increase both the number and proportion of trips by bike to similar levels seen in the top performing cities in the UK. For example, Cambridge is similar in size and character to Oxford, being an historic yet dynamic university city, but in 2001 saw nearly 26% of trips to work by residents being made by bike.

- To facilitate this, the Oxford Cycle City project will, through joint working with stakeholders, identify gaps in the provision of cycle network links as well as cycle parking provision and subsequently cross reference this with the available funding. This will lead to a prioritised list of cycle path schemes being developed, and may also include wider initiatives to promote cycling.

- The City Council will act as the lead authority on the project, which it is hoped will, over time, encourage a substantial increase in cycle trips in Oxford relative to other travel modes.

# Oxford Cycling City - Objectives

- The project objectives are as follows:

  - To establish a stakeholder working group tasked with progressing Oxford Cycling City;

  - To identify an integrated package of cycle improvement and promotional measures, and

  - To identify the means of delivering some of these measures over a 4 year period, with early wins and longer-term goals.

- Once these objectives have been met, the lead officer will prepare a further report for formal endorsement by CEB, containing the details of what has been agreed by the project group.

Project Plan

- The project plan suggested below is indicative, and dependent on the capacity of the lead project officer. The timetable also depends on resources being available from partner organisations (in particular, Oxfordshire County Council).

| Stage | Task | When | Responsibility |
| --- | --- | --- | --- |
| 1 | Invite stakeholders to sit on working group, and circulate draft terms of reference and long list of schemes / initiatives | Jan/Feb 2012 | Lead officer in liaison with County Council |
| 2 | Working Group Meeting 1 – agree purpose/goal, terms of reference, suggestions for refinement of long list (including rationale for prioritisation) and funding opportunities | Feb 2012 | Lead officer |
| 3 | Circulate prioritised shortlist of schemes / initiatives based on analysis of funding/resource opportunities and stakeholder views | Mar 2012 | Lead officer in liaison with County Council |
| 4 | Working Group Meeting 2 – refine & broadly agree prioritised shortlist of schemes | Apr 2012 | Lead officer |
| 5 | Circulate draft final package of measures, with costings, funding source (with any gaps identified) and indicative timeline and responsibilities for implementation to seek stakeholder input. | May 2012 | Lead officer in liaison with other partners |
| 6 | Final draft strategy & action plan to go forward to CEB and possible County Cabinet | May 2012 | Lead officer |
| 7 | CEB approval | Jul 2012 | Board Member |

Stakeholders

- The following individuals and organisations will be invited to take part in joint stakeholder working as set out above (note the list is subject to further addition by officers):

  - Oxford City Council Board Member for City Development (or a nominated substitute)

  - The appropriate Oxfordshire County Council Cabinet Member

  - Oxfordshire County Council officer(s)

  - Cyclox (local cycle campaign / interest group)

  - Cyclists’ Touring Club (CTC)

  - Sustrans South East (sustainable transport charity and campaign group)

All the above organisations have representatives based in the local area.

# Funding and Implementation

- The biggest source of funding available to implement cycle schemes in the short term derive from planning obligations (Section 106 Agreements), and are held by Oxfordshire County Council. The County Council’s records indicate that there is approximately £560,000 that may be available from such funds. It is important to note two important provisos with regards to how this is spent:

  - Most Section 106 funds are limited in scope to the vicinity of the development from which they derive;

  - Any capital spend on a particular scheme will normally require the agreement of the County Council, and may be subject to competition from non-cycling schemes.

- The Council’s Executive Board in its consultation budget, proposes to allocate a total of £300, 000 capital funds for Oxford Cycle City, to be spent over a 4 year period, plus an additional £10,000 per year revenue to support implementation. This is intended for targeted creation of more cycle lanes and better signage in Oxford and is subject to agreement by full Council in February.

- Looking ahead, the City Council expect to adopt the Community Infrastructure Levy (CIL) Tariff in April 2013. From the point of its adoption, the City Council will have greater flexibility to spend capital raised through CIL on community infrastructure. Unlike Section 106 funds, the City and County Councils will be able to pool CIL money allocated towards cycling, for schemes anywhere in the City.

# Climate Change and Environmental Impact

- The proposals set out in this report would have a very positive impact with regards to climate change. Cycling is a virtually zero-carbon form of transport, and is emission-free. Impact on the local environment will also be positive, as more cyclists means less congestion and less localised air pollution.

# Equalities Impact

- Enabling Oxford residents, workers and visitors to cycle safely and comfortably will have a positive impact on social inclusion and equality. Travelling by bicycle is very low-cost, even taking into account bicycle purchase and maintenance, therefore there are potentially significant benefits for those on low incomes. In developing a framework, the stakeholder group can consider whether to target less well-off areas of Oxford towards reducing health inequalities and improving access to employment and services from such areas. There are also clear links with broader Go Active initiatives in Oxford.

# Level of Risk

- A Risk Register is attached as Appendix 1.

# Legal implications

- The purpose of this report is to set out objectives and a project plan. There are no identified legal implications.

- It is necessary to identify a power to implement this scheme and the City Council  can rely on Section 2 of the Local Government Act 2000. This grants, subject to certain conditions, the power to do anything which is considered likely to achieve the promotion or improvement of the economic, social or environmental well-being of the area.

# Financial implications

- These are set out within the body of the report.

Name and contact details of author:-

Matt Bates

Senior Planner (Planning Policy)

City Development

Tel: 01865 252277 e-mail: mbates@oxford.gov.uk

Version number:  6

Appendix 1 – Risk Register

| Risk ID | Risk | Corporate Objective | Gross Risk | Residual Risk | Current Risk | Owner | Date Risk Reviewed | Proximity of Risk (Projects/ Contracts only) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Category-000-Service Area Code | Risk Title | Opportunity/ Threat | Risk Description | Risk Cause | Consequence | Date raised | 1 to 6 | I | P | I | P | I | P |  |  |  |
| SRR-001-CD | CEB do not accept report recommendation 1 | Threat | CEB do not accept need for or direction of implementation | Unexpected political views | Lack of basis for spending capital funds available | 03/01/12 | 3,5 | 3 | 1 | 3 | 1 | 3 | 1 | Matt Bates |  |  |
| SRR-002-CD | Lack of officer time | Threat | The lead officer nominated for the project is also joint leading on another major project that will significantly constrain his time over certain periods. | Lack of a bespoke project officer for Oxford Cycle City | Project milestones are missed | 23/12/11 | 3,5 | 2 | 4 | 2 | 2 | 2 | 4 | Tim Sadler |  |  |
| SRR-003-CD | Insufficient involvement of stakeholders | Threat | County Council is a key partner which may lack resources or political buy-in to be fully involved. Other stakeholders are expected to volunteer time so availability is not guaranteed | Non-alignment of stakeholder priorities. Lack of individuals’ availability | A less joined-up outcome across organisations, and potential lack of buy-in, leading to delayed implementation of outcomes. | 23/12/11 | 3,5 | 3 | 2 | 3 | 2 | 3 | 2 | Matt Bates |  |  |

Risk Register Action Plan Template

| Risk ID | Risk Title | Action Owner | Accept, Contingency, Transfer, Reduce or Avoid | Details of Action | Key Milestone | Milestone Delivery Date | %Action Complete | Date Reviewed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SRR-001-CD | CEB do not accept report recommendation 1 | Matt Bates | Avoid | Change objectives and strategy for improving cycling opportunities in consultation with members | Next available CEB meeting | 4 April 2012 |  |  |
| SRR-002-CD | Lack of officer time | Tim Sadler | Contingency | Employ a bespoke project manager on a short-term basis or commission a consultant to manage the project | Project Stage 3 | 31 March 2012 |  |  |
| SRR-003-CD | Insufficient involvement of stakeholders | Matt Bates | Accept | The City Council would find it difficult to mitigate this risk as it cannot manage or reasonably predict the changing priorities and resources of other organisations. However there is thought to be generally good buy-in from stakeholders hence low probability of risk being realised. | n/a | n/a |  |  |