## Sheet1
APPENDIX 1
No. | Risk | Description | Cause | Consequence | Impact | Probability | Risk Owner | Control / Action description | Due Date | Action Owner | Residual Impact | Residual Probability
3 | Workforce sustainability | Delivery of future ambitions | Recruitment and retention of staff in certain areas; national shortage of certain roles and skills; unable to compete on salary; increased demand / ambition. Capacity and ability to change. | Increased workload putting pressure on capacity. Resulting in poor morale, impact on wellbeing, high turnover, increased sickness, poorer outcomes and impact on service delivery, | 4 | 4 | Helen Bishop | Delivery of an agreed local pay deal with Unions | 31.03.24 | Tom Hook | 3 | 3
[8 empty] | Development and implementation of a pay and grading review | 01.07.24 | Gail Malkin
[8 empty] | Continued implementation of Leadership Development | 31.03.25 | Gail Malkin
[8 empty] | Continue workshops on People policies and procedure for managers | 31.03.25 | Gail Malkin
[8 empty] | Digital skills training programme for all staff | 30.09.24 | Gail Malkin
[8 empty] | Continued delivery of occupational health and Employee Assistance Programme provision | 31.03.25 | Gail Malkin
[8 empty] | Continued delivery of comprehensive internal communications campaign for the People Programme | 31.03.25 | Gail Malkin
[8 empty] | Continued development of recruitment procedure to include proactive recruitment campaigns and better outreach to community networks | 31.03.25 | Gail Malkin
[8 empty] | Development of "Grow our Own" apprenticeships | 31.03.25 | Gail Malkin