## sk notes (hidden)
meeting notes 19/12/23 ; Sonal & Rachel
1 | cfwds budgets on smarsheet are different to Agresso , Rachel to lock down cells
2 | look at doing a agresso vs smartsheet recs
Carolyn email 19/12:
At this can we please have a chat about how we work together now Paul is in the Project Accountancy role as there are several things we need to progress before year end and ongoing:
Approach to running numbers for paybacks on projects
Feasibility tracker need to tidy up what projects have allocations, reflect it in Agresso and what confirm what needs to be repaid to the feasibility from projects that have gone to Cabinet e.g. Cemetery and Odeon and reflect that in Agresso
Rectifying incorrect account codes as we have POs and invoices going to Legal because the account codes have been used by procurement
Setting up the new account codes so capital budgets can be monitored properly. James offered to do this before he left and Anna you said you would do it but we really need to sort this before the new financial year as it is getting really messy to monitor capital at project level
Correcting Agresso in terms of projects that have been charged recently that have closed in terms of ongoing spend - Depot, Cowley Marsh, Floyds Row, Seacourt and Museum
Tidy up open projects and check if they should be closed so wrong charges cannot continue
We then have the meeting the following day to go through the deeper dive into capital spend monitoring.

## DB Dashboard (hidden)
Capital Spend Analysis
|  |  | Original Budget 2023/24 | Forecast @ Q3 | Latest Budget 23/24 | Spend to Date |  | % Spent | Forecast Spend 23/24 | Forecast Variance 23/24 this Month | Forecast Variance 23/24 from Q2
| General Fund Total |  | 77182456.26 | 70824530.44 | 113104951.49 | 27429206.66 |  | 24.25% | 70824530.44 | -42280421.05 | 0
| HRA Total |  | 158254860 | 97311099.68 | 126144842.75 | 23401349.13 |  | 18.55% | 97311099.68 | -28833743.07 | 0
| Total Capital Programme |  | 235437316.26 | 168135630.12 | 239249794.24 | 50830555.79 |  | 21.25% | 168135630.12 | -71114164.12 | 0
General Fund Breakdown
Housing Delivery lines (5 projects) along with Regeneration Property purchase make up 50% of the latest General Fund Programme budget:
M5025 | Barton Park - Purchase by Council |  | 11051609.13 | 10311865 | 17769988.93 | 6646509.79 |  | 37.4% | 5844583 | -11925405.93
M5026 | Housing Company Loans (excl Barton Park) |  | 14051609.13 | 15059611 | 23916000.13 | 5599810.04 |  | 23.41% | 5046250 | -18869750.13
M5032 | Barton Park - loan to OCHL |  | 0 | 10311865 | 9214379.8 | 0 |  | 0% | 5844583 | -3369796.8
M5035 | Growth Deal Registered Provider Payments |  | 272000 | 3341000 | 0 | 0 |  | #DIV/0! | 0 | 0
M5037 | Northern Gateway (Oxford North) |  | 0 | 9993538 | 1153416 | 2218.05 |  | 0.1923% | 1153416 | 0
B0117 | Regeneration Property |  | 0 | 3000000 | 3402.38 | 3402.38 |  | 100% | 3402.38 | 0
| Sub-Total |  | 25375218.26 | 52017879 | 52057187.24 | 12251940.26 |  | 23.54% | 17892234.38 | -34164952.86
| % Total GF Programme |  | 32.88% | 73.45% | 46.03% | 44.67%
| Remaining General Fund Projects Total |  | 51807238 | 18806651.44 | 61047764.25 | 15177266.4 |  | 24.86% | 52932296.06 | -8115468.19
Other General Fund Projects with largest budgets:
R0005 | MT Vehicles/Plant Replacement Programme. |  | 5774279 | 6138848 | 3500000.19 | 648122.35 |  | 18.52% | 3500000 | -0.19
M5024 | National Homelessness Property Fund |  | 0 | 0 | 633961.96 | 157663.93 |  | 24.87% | 633961.96 | 0
B0083 | East Oxford Community Centre |  | 4223967 | 3670039 | 3500000.27 | 1379582.93 |  | 39.42% | 3245000 | -255000.27
M5035 | Growth Deal Registered Provider Payments |  | 272000 | 3341000 | 0 | 0 |  | #DIV/0! | 0 | 0
B0092 | Cave Street Development (Standingford House) |  | 0 | 3051099 | 194134.47 | 146694.01 |  | 75.56% | 194134.47 | 0
General Fund Schemes by project type 2023/24
| Project Classification | Projects | Latest Budget | Spend to Date | % Spent | Q3 Forecast | Q2 Forecast | Variance from Q2 | Forecast Spend | Projects Over Schedule | % Projects Reporting Over Schedule
| Project - Development | 32 | 32997763.43 | 9483075.35 | 28.74% | 26125267.88 | 27043155.73 | -917887.85 | 24941839.43 | 0 | 0%
| Project - ICT | 26 | 3206010.22 | 829961.63 | 25.89% | 3139516.34 | 2709193 | 430323.34 | 2128516.34 | 0 | 0% | Excludes ICT rolling programme line
| Project - Compliance | 4 | 2527208.89 | 721953.59 | 28.57% | 2984117.67 | 2206426.29 | 777691.38 | 2984117.67 | 0 | 0% | Town Hall Dry Risers, Gloucester Green Car park ventilation, Old Gas Works Railway and Pipe Bridges
| Project - Other | 12 | 7881453.9 | 376964.95 | 4.783% | 7419729.9 | 1896867.93 | 5522861.97 | 724191.74 | 0 | 0% | Projects not fitting into other categories including sustainabilty schemes
| Rolling Programme | 9 | 5214109.59 | 1207440.96 | 23.16% | 6680665.01 | 6790304.2 | -109639.19 | 6680665.01 | 0 | 0% | Includes vehicle replacement, on-going Covered Market improvements, some ICT schemes (rolling phone / laptop replacement)
| Housing Company Loans | 2 | 33130379.93 | 5599810.04 | 16.9% | 10890833 | 13043000 | -2152167 | 10890833 | 0 | 0% | Loans to OCH(I)L for Barton purchases and OCH(D)L for Development schemes
| Other Capital Spend | 14 | 28148025.53 | 9203621.14 | 32.7% | 13584400.64 | 13624467.78 | -40067.14 | 13616004.64 | 0 | 0% | Includes: Regen (Investment) Property purchase, Council purchase of Barton Park phase 1 properties (offset by sale to OCHL), Grants e.g DFGs, Clean Bus Tech and contributions to external schemes
| General Fund Total | 99 | 113104951.49 | 27422827.66 | 24.25% | 70824530.44 | 67313414.93 | 3511115.51 | 61966167.83 | 0 | 0%
-6508978.66
0
General Fund Schemes by Service Area 2023/24
| Service Area | Projects | Feasibility Stage | Design & Spec Stage | In Deilvery Stage | Completed |  | Closed | Non Gateway | Total Budget | Spend to Date | % Spend to Date | Variance from Q2
| Business Improvement | 29 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3164509.88 | 1255177.22 | 39.66% | -512126.4
| Financial Services | 6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3028810.6 | 28766.5 | 0.9498% | 525248
| Community Services | 11 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8042419.11 | 1663725.45 | 20.69% | 240818.17
| Corporate Property | 37 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9358990.57 | 1765041.11 | 18.86% | 959063.34
| Housing Services | 7 | 0 | 0 | 0 | 0 |  | 0 | 2 | 1259102.31 | 180421.09 | 14.33% | -121730.04
| Housing Delivery | 6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 54139784.86 | 12248537.88 | 22.62% | -17571168
| Regulatory & Community Safety | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 74897.07 | £12m capital receipt at Rose Hill rec'd earlier than forecast, reducing loan requirement
| Regeneration & Economy | 33 | 0 | 0 | 0 | 0 |  | 0 | 0 | 27339463.7 | 8590984.3 | 31.42% | -1109068.88
| Environmental Sustainability | 7 | 0 | 0 | 0 | 0 |  | 0 | 0 | 885604.94 | 44121.44 | 4.982% | -688785.09
| Planning Services | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2188825 | 953987.7 | 43.58% | 273883
| Oxford Direct Services | 3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3684658.52 | 690568.97 | 18.74% | -3000168.44
| General Fund Total | 144 | 0 | 0 | 0 | 0 |  | 0 | 2 | 113092169.49 | 27421331.66 | 24.25% | -20929137.27 | Slippage of technolgy projects associated with Depot project
|  |  | Original Budget 2023/24 | Forecast @ Q3 | Latest Budget 23/24 | Spend to Date |  | % Spent | Forecast Spend 23/24 | Forecast Variance 23/24 this Month | Forecast Variance 23/24 from Q2
| HRA Total |  | 158254860 | 97311099.68 | 126144842.75 | 23401349.13 |  | 18.55% | 97311099.68 | -28833743.07 | 0
The following 3 projects (OCHL Purchases and Development sites) make up over 50% of the HRA Programme budget:
N7054 | Properties Purchased From OCHL |  | 83684822 | 41731891 | 23911742.39 | 7943686.37 |  | 33.22% | 25688743 | 1777000.61
N7061 | Northfield Hostel |  | 9524123 | 1947000 | 21999763.48 | 1239045.19 |  | 5.632% | 5698890 | -16300873.48
N7062 | Lanham Way |  | 3185122 | 4368030 | 6711853.38 | 1952169.75 |  | 29.09% | 4136012 | -2575841.38
|  |  | 96394067 | 48046921 | 52623359.25 | 11134901.31 |  | 21.16% | 35523645 | -17099714.25
|  |  | 60.91% | 49.37% | 41.72% | 47.58%
| Remaining HRA Projects Total |  | 61860793 | 49264178.68 | 73521483.5 | 12266447.82 |  | 16.68% | 61787454.68 | -11734028.82
HRA Schemes by project type 2023/24
| Project Classification | Projects | Latest Budget | Spend to Date | % Spent | Q3 Forecast | Q2 Forecast | Variance from Q2 | Forecast Spend | Projects Over Schedule | % Projects Reporting Over Schedule
| Project - Development | 4 | 10837541.52 | 2792914.11 | 25.77% | 9537236.02 | 1602946.91 | 7934289.11 | 9537236.02 | 0 | 0%
| Project - Compliance | 1 | 207021 | 0 | 0% | 207021 | 176802 | 30219 | 207021 | 0 | 0%
| Project - Other | 2 | 22815597.23 | 5126350.07 | 22.47% | 24226047.23 | 430000 | 23796047.23 | 973572.9 | 0 | 0%
| Rolling Programme | 23 | 21386481.81 | 2423747.2 | 11.33% | 18773339.76 | 19255814.75 | -482474.99 | 16518516.7 | 0 | 0%
| Other Capital Spend | 11 | 70898201.19 | 13058337.75 | 18.42% | 44567455.67 | 48593033.22 | -4025577.55 | 44182226.67 | 0 | 0%
| HRA Total | 41 | 126144842.75 | 23401349.13 | 18.55% | 97311099.68 | 70058596.88 | 27252502.8 | 71418573.29 | 0 | 0%
| Overall GF + HRA Total | 140 | 239249794.24 | 50824176.79 | 21.24% | 168135630.12 |  | 30763618.31 | 133384741.12 | 0 | 0%
Capital Expenditure in Previous Years
General Fund Schemes Historic Spending
| Project Classification | 19/20 Original Budget | 19/20 Spend | % Budget Spent | 20/21 Original Budget | 20/21 Spend |  | % Budget Spent | 21/22 Original Budget | 21/22 Spend | % Budget Spent | 22/23 Budget | 22/23 Spend
| Project - Development | 8970164 | 5547778.93 | 61.85% | 8445858.67 | 6137524.01 |  | 72.67% | 20842819 | 13655749.43 | 65.52% | 32914155 | 9483075.35
| Project - ICT | 2357782 | 2249933.96 | 95.43% | 2341620 | 1459690.49 |  | 62.34% | 2493052 | 1626799.96 | 65.25% | 1509018 | 829961.63
| Project - Compliance | 260000 | 82128.68 | 31.59% | 76350 | 111537.19 |  | 146.1% | 112261 | 324330.5 | 288.9% | 262123 | 721953.59
| Project - Other | 875362 | 295515.2 | 33.76% | 821989 | 341323.04 |  | 41.52% | 1342118 | 405464.15 | 30.21% | 1582443 | 376964.95
| Sub-Total | 12463308 | 8175356.77 | 65.6% | 11685817.67 | 8050074.73 |  | 68.89% | 24790250 | 16012344.04 | 64.59% | 36267739 | 11411955.52
| Rolling Programme | 6102425 | 4667771.62 | 76.49% | 3992307 | 4189868.34 |  | 104.9% | 3741370 | 2314908.31 | 61.87% | 5328660 | 1207440.96
| Housing Company Loans | 15984000 | 9702082.76 | 60.7% | 26464316 | 27081102.02 |  | 102.3% | 37936037 | 2364391.6 | 6.233% | 13689308 | 5599810.04
| Other Capital Spend | 9648596 | 8020461.65 | 83.13% | 55421650 | 8262325.37 |  | 14.91% | 39887363 | 13864479.99 | 34.76% | 43237847 | 9203621.14
| General Fund Total | 44198329 | 30565672.8 | 69.16% | 97564090.67 | 47583370.46 |  | 48.77% | 106355020 | 34556123.94 | 32.49% | 98523554 | 27422827.66
| Live General Fund Projects | 67 |  |  | 76 |  |  |  | 55 |  |  | 87 | 87
| Projects Completed | 20 |  |  | 12 |  |  |  | 7 |  |  | N/A | N/A
| >£1m Projects Completed | 0 |  |  | 1 |  |  |  | 1
HRA Schemes Historic Spending
| Project Classification | 19/20 Original Budget | 19/20 Spend | % Budget Spent | 20/21 Original Budget | 20/21 Spend |  | % Budget Spent | 21/22 Original Budget | 21/22 Spend | % Budget Spent | 22/23 Budget | 22/23 Spend
| Project - Development | 1730000 | 283055.4 | 16.36% | 4138000 | 794230.97 |  | 19.19% | 3942200 | 291241.38 | 7.388% | 3138000 | 2792914.11
| Project - Compliance | 0 | 0 |  | 0 | 0 |  |  | 102000 | 0 |  | 102000 | 0
| Project - Other | 250000 | 80799.36 |  | 0 | 26470.89 |  | #DIV/0! | 169200 | 3976.44 | 2.35% | 195000 | 5126350.07
| Rolling Programme | 11889535 | 10508061.92 | 88.38% | 12212000 | 7755522.7 |  | 63.51% | 12366226 | 8650312.46 | 69.95% | 13937000 | 2423747.2
| Other Capital Spend | 1793743 | 1141211.61 | 63.62% | 28653000 | 12605779.02 |  | 43.99% | 63148107 | 34508072.37 | 54.65% | 95085000 | 13058337.75
| HRA Total | 15663278 | 12013128.29 | 76.7% | 45003000 | 21182003.58 |  | 47.07% | 79727733 | 43453602.65 | 54.5% | 112457000 | 23401349.13
| Overal GF + HRA Total | 59861607 | 42578801.09 | 71.13% | 142567090.67 | 68765374.04 |  | 48.23% | 186082753 | 78009726.59 | 41.92% | 210980554 | 50824176.79
| Live HRA Projects | 22 |  |  | 22 |  |  |  | 26 |  |  | 34
| Overall Live Projects | 89 |  |  | 98 |  |  |  | 81 |  |  | 121
| Total PMs updating | 32 |  |  | 41 |  |  |  | 55 |  |  | 51
| Projects per PM | 2.7812 |  |  | 2.3902 |  |  |  | 1.4727 |  |  | 2.3725
Historic Spending by Year (% Original Budget)
|  | Original Budget £'000 | Actual Spend £'000 | % Spend
| 2019/20 | 59861.607 | 42578.8011 | 71.13%
| 2020/21 | 142567.0907 | 68765.374 | 48.23%
| 2021/22 | 186082.753 | 78009.7266 | 41.92%
| 2022/23 (YTD) | 210980.554 | 50824.1768 | 24.09%
| General Fund Project Classification | 19/20 Original Budget | 19/20 Spend | % Budget Spent | 20/21 Original Budget | 20/21 Spend |  | % Budget Spent | 21/22 Original Budget | 21/22 Spend | % Budget Spent | 22/23 Budget | 22/23 Spend
| Housing Company Loans | 15984000 | 9702082.76 | 60.7% | 26464316 | 27081102.02 |  | 102.3% | 37936037 | 2364391.6 | 6.233% | 13689308 | 5599810.04
| General Fund Spend by Type | Housing Company Loans |  |  |  | General Fund: |  |  | Housing Company Loans
|  | Original Budget £'000 | Actual Spend £'000 | % Spend
| 2019/20 | 15984000 | 9702082.76 | 60.7%
| 2020/21 | 26464316 | 27081102.02 | 102.3%
| 2021/22 | 37936037 | 2364391.6 | 6.233%
| 2022/23 (YTD) | 13689308 | 5599810.04 | 40.91%
| HRA Project Classification | 19/20 Original Budget | 19/20 Spend | % Budget Spent | 20/21 Original Budget | 20/21 Spend |  | % Budget Spent | 21/22 Original Budget | 21/22 Spend | % Budget Spent | 22/23 Budget | 22/23 Spend
| Rolling Programme | 11889535 | 10508061.92 | 88.38% | 12212000 | 7755522.7 |  | 63.51% | 12366226 | 8650312.46 | 69.95% | 13937000 | 2423747.2
| HRA Spend by Type | Rolling Programme |  |  |  | HRA: |  |  | Rolling Programme
|  | Original Budget £'000 | Actual Spend £'000 | % Spend
| 2019/20 | 11889535 | 10508061.92 | 88.38%
| 2020/21 | 12212000 | 7755522.7 | 63.51%
| 2021/22 | 12366226 | 8650312.46 | 69.95%
| 2022/23 (YTD) | 13937000 | 2423747.2 | 17.39%

## sk (hidden)
Data
Project Classification2 | Project Classification | Sum of Latest 2023/24 Budget | Sum of Spend to 31/12/23 | Sum of 2023/24 Outturn Forecast
Other Capital Spend GF | Other Capital Spend | 28148025.53 | 9210000.14 | 13584400.64
Project - Development GF | Project - Development | 32997763.43 | 9483075.35 | 26125267.88
Project - ICT GF | Project - ICT | 3206010.22 | 829961.63 | 3139516.34
Project - Other GF | Project - Other | 7881453.9 | 376964.95 | 7419729.9
Housing Company Loans GF | Housing Company Loans | 33130379.93 | 5599810.04 | 10890833
Project - Compliance GF | Project - Compliance | 2527208.89 | 721953.59 | 2984117.67
Project - Compliance HRA | Project - Compliance | 207021 | 0 | 207021
Project - Development HRA | Project - Development | 10837541.52 | 2792914.11 | 9537236.02
Project - Other HRA | Project - Other | 22815597.23 | 5126350.07 | 24226047.23
rolling programme GF | Rolling Programme | 5214109.59 | 1207440.96 | 6680665.01
Total Result |  | 146965111.24 | 35348470.84 | 104794834.69
Data
Project Classification2 | Project Classification | Sum of Latest 2023/24 Budget | Sum of Spend to 31/12/23 | Sum of 2023/24 Outturn Forecast
Other Capital Spend HRA | Other Capital Spend | 70898201.19 | 13058337.75 | 44567455.67
Rolling Programme HRA | Rolling Programme | 21386481.81 | 2423747.2 | 18773339.76
Housing Company Loans GF | Housing Company Loans | 33130379.93 | 5599810.04 | 10890833
Project - Compliance GF | Project - Compliance | 2527208.89 | 721953.59 | 2984117.67
Project - Compliance HRA | Project - Compliance | 207021 | 0 | 207021
Project - Development HRA | Project - Development | 10837541.52 | 2792914.11 | 9537236.02
Project - Other HRA | Project - Other | 22815597.23 | 5126350.07 | 24226047.23
rolling programme GF | Rolling Programme | 5214109.59 | 1207440.96 | 6680665.01
Total Result |  | 167016541.16 | 30930553.72 | 117866715.36

## FinanceAppB (Current Month)
Capital Budget and Spend as at 30th September 2024
[18 empty] | 2024/25 Forecast Variance |  |  |  |  | Smartsheet Forecast | [6 empty] | Future Year Budgets (per 24/25 MTFP Budget)
Cost Centre | Capital Scheme | Service Area | Progress Update Provider | GF / HRA | Project Classification | Project Classification | Gateway Stage | Programme Status | Risk Status | 2024/25 Original Budget | Carry Forwards | Adjustments Since Original Budget | Latest 2024/25 Budget | Profiled Budget | Spend to 30/09/24 | % Budget Spent | Budget Remaining | Forecast Variance | Variance due to Slippage | Over / Under Spend | 2024/25 Outturn Forecast | manually updated (PS) | 2024/25 Smartsheet Forecast | Smarsheet Comment Updated | PM Overview (From Smartsheets) | PM Variance Comment (From Smartsheets) | Key Risks and Mitigations (From Smartsheets) | Next Key Milestone (From Smartsheets) | Management Accountant Comments | 2025-26 Approved Budget | 2026-27 Approved Budget | 2027-28 Approved Budget | Total Budget 2024-25 to 2027-28
[10 empty] | £ | £ | £ | £ | £ | £ |  | £ | £ | £ | £ | £ | [8 empty] | £ | £ | £ | £
General Fund Capital Programme
Communities and People Directorate
| Community Services Projects | [10 empty] | 0 | [5 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0
A4820 | Upgrade Existing Tennis Courts | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 108190.83 | 0 | 108190.83 | 54095.41 | 2568.62 | 2.374% | 105622.21 | -108190.83 | -108190.83 | 0 | 0 | Y | 0 | 0 | That works have completed at Hinksey Park and Botley Park, this has included resurfacing and repainting of the courts. We have worked closely with the cabinet member and local ward cllrs to promote this. At Bury Knowle Park resurfacing works have also been completed to now include tennis and multi use games area at the site. Planning permission has been granted and works are now complete for the refurbishment of the pavilion and associated outdoor spaces. We are currently reviewing potential for works at Cutteslowe Park and Alexandra Park to resurface the existing tennis courts utilising S106 contributions from the Wychwood School developments | £33,000 CIL contributions from Headington Action are not currently showing on current budget. Once this has been allocated the project should show a small overspend due to unforseen costs in delivery of Hinksey Park and Botley Park resurfacing. | Charging scheme at Hinskey & Botley received some criticism locally and from members. We have worked closely with members to mitigate this and have addressed their concerns. Tennis courts at Alexandra Park have significantly deteriorated and are in need of resurfacing - proposal for works using S106 contributions. Cutteslowe Park is in need of significant improvements as court conditions are poor - proposals for utilising S106 contributions working in partnership with Courtside to review options for delivery | Work starts June 2023 |  | 0 | 0 | 0 | 108190.83
A4847 | Rose Hill Community Centre - Parking Management | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 10000 | 0 | 10000 | 5000 | 0 | 0% | 10000 | 0 | 0 | 0 | 10000 |  | 10000 | 0 | We are currently working with colleagues within the car parking team to develop a clear scope for this. It is likely that the £10k capital allocation will slip to 24/25. | 0 | Timescales and budget if part of a wider project | Traffic order obtained. |  | 0 | 0 | 0 | 10000
A4852 | Bodycams for Community Safety Team | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 23000 | 0 | 23000 | 11500 | 22977.5 | 99.9% | 22.5 | 0 | 0 | 0 | 23000 |  | 23000 | 0 | Project completed. Final spend approx £27K (under budged of £60K) Closure Report to be completed by Richard Adams | 0 | - | NFA |  | 0 | 0 | 0 | 23000
A4855 | Leys Youth Hub | Community Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 11395.07 | 1060199 | 1071594.07 | 535797.04 | 77320.35 | 7.215% | 994273.72 | -20000 | -20000 | 0 | 1051594.07 | Y | 1051594.07 | 0 | Works commenced on site on 23 September 2024. Overall, good progress has been made on site with the commencement of the Phase 1 demolition / enabling works to the rear of the Leisure Centre. ODS have reported works are currently on programme with the completion date of the 25 March 2025 remaining achievable. The final RIBA Stage 4 architectural, structural and civil design package and fire strategy report and plans was issued on 25 September 2024. The final RIBA Stage 4 mechanical and electrical design was issued on 30 September 2024. A majority of the building contract between Oxford City Council and ODS has now been agreed. Schedule of Amendments have been finalised and the completed Stage 4 design. The items left to be confirmed are detailed below: - Contract Sum Analysis. - Contract Programme. - Contractor’s Proposals. The above information was expected back from ODS by the end of September 2024 as part of their Stage 2 tender submission. However, due to delays in finalising the M&E Stage 4 design and coordination with the other consultants, the final Stage 4 design pack was issued later than originally planned. This has resulted in ODS not being able to commence pricing until 30 September 2024 when the full pack was issued. ODS are currently completing their pricing for the Stage 2 tender and will submit this on 18 October 2024. | Retention (remaining 2.5% of construction budget) to be paid 25/26. | RISK & MITIGATION: Recent demolition activities consisting of partition block wall removal raised possible stabilisation issues to an adjoining wall. All internal partitions (previously connected to the linear wall) has been removed leaving but a set of rack backs with the aim in maintaining lateral stability. The Structural Engineer attended site to confirm stability of the wall as it is currently, we received an initial response to say that it ‘seems safe’ and have requested a more definitive response and are awaiting this formal confirmation. It is worth noting that a CDM site audit was carried out on 4 October 2024, an extract from report follows: ‘Although this visit was to carry out a general CDM inspection across the site on behalf of the Client, focus was also to be made to the recent demolition activities consisting of partition block wall removal posing possible stabilisation issues to adjoining wall. At the time of visit, all internal partitions (previously connected to linear wall) has been removed leaving but a set of rack backs with the aim in maintaining lateral stability. New blockwork had started to be constructed to the and adjoined to linear wall via the use of steel starter kits. Although from a H&S perspective, in this scenario, there were no obvious and immediate concerns regarding stability, the Structural Engineer is attending site on Monday 7th October to carry out a check and to provide professional opinion. Following this visit, there may be a required change in approach regarding re-build. The CDM PD / CDM Advisor highlighted that there may be the requirement for a pier to be constructed in a suitable position along the linear wall to provide further stabilisation in support of normal use as the length of single skin blockwork (once rack backs are removed) would likely exceed 6m from adjoining walls. SE & Arch to confirm. Crack in block work noticed above central door however, needle has been installed and at the time of visit, infill block work was nearly complete.’ RISK: The costs within the budget estimate ODS provided, are all provisional until Stage 4 design & scope is complete, therefore there is a risk on the cost of the scheme even after having Value engineered the scheme at this stage. RISK: Programme extends beyond the funding deadline, 31 March 2025. MITIGATION: Weekly precontract meetings to monitor progress and mitigate any potential slippage to keep project on track. Review work that could potentially be bought forward i.e. site setup, demolition. The following risk (The Funding Agreement Clause 18.5) was raised at DB on 5/02/24 and the recommendation was – Proceed with signing grant funding agreement, recognising that the funding could be withdrawn with 3 months’ notice RISK: The Funding Agreement Clause 18.5 stipulates that The Funder may terminate (without cause) agreement by giving three months’ notice in writing, provided that the Recipient shall be entitled to claim Grant funds that it has already spent on Eligible Expenditure. MITIGATION: Either remove or agree in side letter that they do not apply probably side letter as unusual to amend GFA. (note: The funder have made clear that they cannot make changes, that there are many local authorities who have accepted and that the alternative is to not accept the funding.) | Phase 2 Demolition to commence 14 October 2024 |  | 0 | 0 | 0 | 1071594.07
A4858 | Leisure Invest to Save - Leisure Contract | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 2400000 |  | 640000 | 3040000 | 1520000 | 0 | 0% | 3040000 | 0 | 0 | 0 | 3040000 |  | 3040000 | 0 | Cabinet and Council approval has been given. A deed of variation has been drafted by our legal team, with the purpose to protect the Council in relation to repayment of the capital loaned to them. This is now with Serco for their approval and agreement is likely by return. Replacement and improvement of long lead in items such as Gym Equipment has been completed at Ferry, Barton and Leys. The feedback from customers has been very positive. The governance of the project is through the Maintenance meeting with Serco that also picks up the Dilapidations and is chaired by Property Services and Supported by Leisure. | 0 | 0 | 0 |  | 0 | 0 | 0 | 3040000
B0075 | Museum of Oxford Development | Community Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0083 | East Oxford Community Centre | Community Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 4223967 | -62276.73 | -661690 | 3500000.27 | 1750000.13 | 1379582.93 | 39.42% | 2120417.34 | -255000.27 | -255000.27 | 0 | 3245000 | Y | 3245000 | 0 | Commence on site 6th March 2024 | Presently early design changes led to delays which have a mitigation strategy to meet original Practical Completion dates | Access for Community Centre and Residential. Ongoing Coordination meetings in place to decide a mutually agreeable strategy. These are now planned on a weekly basis at site level and monthly for combined project teams. The logistics of completing shared sewers and paved areas between community centre and residential means completion of that area will not be until October 6th. EOCC is targeted as end of June 2025 but occupation will not be [possible till paving work is concluded to allow means of escape from the community centre. | Complete roof works 11th November 2024 |  | 2124657 | 0 | 0 | 5624657.27
B0096 | Bullingdon Community Centre | Community Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 63135.84 | 0.1 | 63135.94 | 31567.97 | 94011.86 | 148.9% | -30875.92 | 0 | 0 | 0 | 63135.94 |  | 63135.94 | 0 | Practical Completion achieved | 0 | Cost report submitted for increase over budget to date Final account can now be submitted | Practical Completion achieved December 2022 together with Commission and handover |  | 0 | 0 | 0 | 63135.94
B0150 | Hinksey Pool Liner Replacement | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 18385 | 18385 | 9192.5 | 0 | 0% | 18385 | 0 | 0 | 0 | 18385 |  | 18385 | 0 | 0 | 0 | 0 | Variation instructed to original order, now to include pool side repair |  | 0 | 0 | 0 | 18385
B0158 | Street Sports Lighting Upgrade | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 70000 | 0 | 70000 | 35000 | 69000 | 98.57% | 1000 | -1000 | -1000 | 0 | 69000 |  | 69000 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 70000
B0159 | Redbridge Masterplan | Community Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 98113 | 40000 | 138113 | 69056.5 | 18264.19 | 13.22% | 119848.81 | -88103 | -88103 | 0 | 50010 |  | 50010 | 0 | Consultants (commercial and reference masterplan) recommendation agreed pending review of Decision Notice. Infrastructure and Transport consultant tenders now active. | Extended consultant procurement process including finalising contract terms. | Comparative analysis of options and assessing preferred options will be difficult to agree with competing demands for site. Need to engage with County with regard to transport and alternate park & ride site adjacency Members concerned at transport limitations and impact on options appraisal. Review of existing transport studies proposed to confirm there are growth opportunities within existing transport infrastructure. | Lead consultants to be appointed August 2024 Infrastructure & transport consultant tenders August 2024 |  | 0 | 0 | 0 | 138113
| Community Services Projects Total | [8 empty] | 6623967 | 321558.01 | 1096894.1 | 8042419.11 | 4021209.55 | 1663725.45 | 20.69% | 6378693.66 | -472294.1 | -472294.1 | 0 | 7570125.01 |  | 7570125.01 | [6 empty] | 2124657 | 0 | 0 | 10167076.11
| Housing Services Projects | [16 empty] | 0 | [11 empty] | 0 | 0 | 0
B0102 | Replace or refurbish Lifts | Housing Services | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 140000 | 119484 | -150000 | 109484 | 54742 | 3733.62 | 3.41% | 105750.38 | 0 | 0 | 0 | 109484 |  | 109484 | 0 | On-going maintenance and inspections with repairs | 0 | 0 | Requires budget approvals, Section 20, cabinet report,contract extension procurement |  | 0 | 150000 | 0 | 259484
B0108 | Floyds Row Refurbishment | Housing Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 48283 |  | 0 | 48283 | 24141.5 | 12239.41 | 25.35% | 36043.59 | -36044 | -36044 | 0 | 12239 |  | 12239 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 48283
C3057 | Housing System Replacement | Housing Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | -9112.5 | #DIV/0! | 9112.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | Tenant Portal - The tenant portal was successfully made live on 11th September. A soft launch of the portal was made to Tenant Ambassadors. | 0 | - Resources and capacity are critical for managing the volume of work activities, which are continuously being prioritized. - Ensure the supplier's resources and capacity are booked and available when needed. Request and book resources as early as possible. | Tenant Portal - Extend the launch to new tenants during sign-up |  | 0 | 0 | 0 | 0
M5024 | National Homelessness Property Fund | Housing Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 9. Other Capital Spend |  |  | 0 | 633961.96 | 0 | 633961.96 | 316980.98 | 157663.93 | 24.87% | 476298.03 | 0 | 0 | 0 | 633961.96 |  | 633961.96 | 0 | Further NHPF payment of £1,780k due in March 23, followed by a final payment of £976k in June 2023 | 0 | WRONG PM RECORDED - SHOULD BE RICHARD WOOD OR PAUL WILDING | 0 |  | 0 | 0 | 0 | 633961.96
M5038 | Roken House | Housing Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 0 | 95556.35 | 0 | 95556.35 | 47778.18 | 3019.9 | 3.16% | 92536.45 | 61943.65 | 61943.65 | 0 | 157500 | 413427 | 157500 | 0 | Jan 22 - Architects appointed. April 22 - Property purchased (£1.4m). Works Spec prepared. Asbestos Survey commissioned. Jun 22 - Planning App submitted. M&E consultants appointed. Full spec being prepared. Slight project delays due to additional surveys and reports having to be commissioned - M&E survey (inc Fire Strategy); Flood Risk Asst (for planning). Oct 22 - Planning approval secured. Building Control application in. Tender pack for works prepared and with ODS for pricing. Project currently has c. 5 weeks delay to programme. Nov 22 - Pricing to spec (with options) undertaken. Assessment (ahead of contract award) on 21st Nov 22. Dec 22 - M&E pricing still awaited. Jan 23 - ODS pricing confirmed and verified by indep QS. Decision made to increase the budget envelope by £200k and to award the contract - Now back on (enhanced) budget. May 23 - Contract Award (to ODS) June 23 - SoS Dec 23 (Budget) Cabinet recommendation to move project from GF to HRA - Approved at full Council in Jan 24. Mar 24 - Handover of 8 homes / PC (9th home - old office -pending final Building Control sign-off) Aug 24 - BC sign-off completed (Flat 9). PC achieved. All homes let. | Final Account settlement underway | Some additional items and Architects Instructions have been necessitated but negotiations underway to minimise costs (max expected overspend c.£63k) | Finance to move entire project into HRA (2023/24 year end closedown) including RRTBR inclusion in the DLUHC 'pooling return' re spend. |  | 0 | 0 | 0 | 95556.35
M5039 | UK Shared Prosperity Fund Invesment Plan | Housing Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 65000 | 190000 | 116817 | 371817 | 185908.5 | 0 | 0% | 371817 | 0 | 0 | 0 | 371817 |  | 371817 | 0 | Following agreement at development board (17th July) UKSPF capital expenditure for this year will focus on the Market Street scheme design and delivery - up to £170k has been allocated for 23/24. The remaining £20k capital has been made available to progress St Michael's Street, ahead of delivery in 24/25. The focus for revenue expenditure this year is to cover the officer time in delivering the Match My Project trial to support community organisations and social value delivery. There is a small allocation (£35k) planned to deliver training and business development support through a third party. Advice from legal suggests this may be possible through direct grant award to a partnership of local providers - OSEP, CAG, Cooperative Futures. This will need Director sign off. Members have expressed concerns that the Wayfinding upgrade had been removed from the plan and we are exploring options to reintroduce in the programme's final year 24/25, using some of the funding allocated to skills. | 0 | 0 | See Market Street project for latest dates |  | 0 | 0 | 0 | 371817
M5040 | Brownfield Land Release Fund (BLRF) | Housing Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 9. Other Capital Spend |  |  | 0 |  | 0 | 0 | 0 | 12876.73 | n/a | -12876.73 | 340213 | 340213 | 0 | 340213 |  | 340213 | 0 | Two contracts signed (March 24) for survey work (Bailey Garner) and demolition and enabling works (ODS) - now programmed in during Q3 & 4 2024/25. Relates to 5 sites (Underhill, Leiden, BBL x3) | 0 | 0 | Surveys; Planning App; and party wall info |  | 0 | 0 | 0 | 0
| Housing Services Projects Total | [8 empty] | 253283 | 1039002.31 | -33183 | 1259102.31 | 629551.16 | 180421.09 | 14.33% | 1078681.22 | 366112.65 | 366112.65 | 0 | 1625214.96 |  | 1625214.96 | [6 empty] | 0 | 150000 | 0 | 1409102.31
| Oxford Direct Services Projects | [10 empty] | 0 | [5 empty] | 0 | 0 |  |  |  | 0 | [6 empty] | 0 | 0 | 0
R0005 | MT Vehicles/Plant Replacement Programme. | Oxford Direct Services | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 5774279 | 405675.19 | -2679954 | 3500000.19 | 1750000.1 | 648122.35 | 18.52% | 2851877.84 | -0.19 | -0.19 | 0 | 3500000 | Y | 3500000 | 0 | We have made good progress in decarbonizing our fleet, however we are at the difficult stages of trying convert vehicles that have no suitable charging solution or are expensive to convert to electric. As such every vehicle needs assessing on a case by case basis. Where possible we are looking to extend the life of assets to keep the cost of fleet down for both ODS and OCC. This is to make most efficiency of the fleet whilst keep expenditure down versus trying to improve our green footprint of the fleet. The impact this will have on the Capital programme is a potential carry over every year as we will no longer be replacing on the typical fixed 7 year term. This also means a more detailed management of the running costs across the whole fleet on a continuous basis. Lead times on vehicles has come down so if vehicle running costs increase on a particular asset then we will look to replace asap. As well as a cost benefit to ODS and the Council by extending asset life, there may be scope to decarbonize more of the fleet as newer longer range assets come into the market, EV prices decrease due to the new ZEV mandate, and alternative solutions to infrastructure charging become available. Note that we are still following our previous replacement lifecycle for depreciation (usually 7 years) and the extend life will continue with no depreciation for any additional years beyond its normal life. As such I have reviewed the capital program and estimated a reduction in overall spend for this year. | Extending life of assets and rolling over budgets | The project is still subject to planning of replacement Electric vehicles across all services based on Net Zero targets. It is a very complex replacement due to many vehicles being taken home or calculating power requirements at depots and economic considerations. We would like to support OCC’s aim full decarbonization of the fleet by 2030 but this can only be achieved with new infrastructure and some high cost electric vehicles. If we buy diesel now then we are tied in for another 7 years. As such we are deferring replacement of some assets until decisions have been made on future replacement methods and strategy. The biggest risk is vehicles going wrong and the lead times being too long to replace the asset quickly. Therefore we are continuing to keep a fleet of pool vehicles to offset VOR and any unforeseen vehicle issues. The planning of the programme will no longer be as straightforward as it used to be and will require closer monitoring of asset running costs. That being said we have changed the budget to a fixed amount per year and plan to only replace fixed life assets and any assets that are starting to cost more for maintenance or reaching 10+ years. | There are still a number of electric vehicles outstanding on order, due to one supplier's production delays and space/charging constraints at depots. | This feels like something that we need to have a meeting with Owain to discuss ahead of Q2 as it has the potential to be a high value swing I think | 7301909 | 3256938 | 3000000 | 17058847.19
T2273 | Car Parks Resurfacing | Oxford Direct Services | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 200000 | 88691.54 | -138692 | 149999.54 | 74999.77 | 42346.62 | 28.23% | 107652.92 | 138084.23 | 138084.23 | 0 | 288083.77 |  | 288083.77 | 0 | Work underway at Ferry Pool Work planned for Gloucester Green and Walton Well Road CCTV upgrade required at Gloucester Green | 0 | No notable current risks to programme. | Ferry pool completion during July | Emma Gubbins has received a planned programme but was waiting on a response to a couple of issues | 138692 | 0 | 0 | 288691.54
T2309 | Cowley Marsh Extension | Oxford Direct Services | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 34658.79 | 0 | 34658.79 | 17329.39 | 100 | 0.2885% | 34558.79 | 0 | 0 | 0 | 34658.79 |  | 34658.79 | 0 | Area now in use by public Awaiting advice on hedge planting from ODS arboricultural services. The row of Cypress trees on the boundary with the CM yard have been removed as an additional cost to the project. These had been neglected and were in a dangerous condition. This was reported at a previous board several months ago and budgeted at £14k. The final account is due to be closed out once the hedging costs are know and if they can be planted this season | 0 | None | Discharge of planning conditions can now proceed following completion of all works (subject to hedge planting) Stated as November so that will be the date on discharge |  | 0 | 0 | 0 | 34658.79
| Oxford Direct Services Projects Total | [8 empty] | 5974279 | 529025.52 | -2818646 | 3684658.52 | 1842329.26 | 690568.97 | 18.74% | 2994089.55 | 138084.04 | 138084.04 | 0 | 3822742.56 |  | 3822742.56 | [6 empty] | 7440601 | 3256938 | 3000000 | 17382197.52
| Communities and People Directorate Total | [8 empty] | 12851529 | 1889585.84 | -1754934.9 | 12986179.94 | 6493089.97 | 2534715.51 | 0.53758 | 10451464.43 | 31902.59 | 31902.59 | 0 | 13018082.53 | 0 | 13018082.53 | 0 | 0 | 0 | 0 | 0 | 0 | 9565258 | 3406938 | 3000000 | 28958375.94
Development Directorate
| Corporate Property Projects | [10 empty] | 0 | [17 empty] | 0 | 0 | 0
A4856 | Conversion of stored water system to mains at Cutteslowe Lower Pavillion | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 130000 |  | 0 | 130000 | 65000 | 0 | 0% | 130000 | 0 | 0 | 0 | 130000 |  | 130000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 130000
A4857 | Leisure infrastucture life cycle investment (dilaps) | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 840000 | 840000 | 420000 | 168668 | 20.08% | 671332 | 0 | 0 | 0 | 840000 |  | 840000 | 0 | Dilaps draft JCT contract sent to Serco for review, aiming to commence works in September | 0 | 0 | Define the packages of work |  | 560000 | 0 | 0 | 1400000
A4859 | Leisure Centre Capital Works & Replacements | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 200000 |  | 0 | 200000 | 100000 | 8650 | 4.325% | 191350 | 0 | 0 | 0 | 200000 |  | 200000 | 0 | Defining what capital projects will sit outside of the dilaps, working with Serco to understand the ask before proceeding. | 0 | 0 | Define the packages by exclusion of the dilaps |  | 200000 | 200000 | 0 | 600000
A4860 | Community Centres Capital Works & Replacements | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 430000 |  | -430000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Developing initial design | 0 | 0 | Define the packages of work |  | 0 | 150000 | 0 | 150000
A4861 | Hinksey Splash | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 18385 |  | 61615 | 80000 | 40000 | 0 | 0% | 80000 | 145822.13 | 145822.13 | 0 | 225822.13 |  | 225822.13 | 0 | Contract agreed - awaiting start date from contractor, but will be in September | Contingency was included which may not be required | The project needs to be completed by 15th March to comply with the external funding deadline | Work starts on site on 14th Oct 24 |  | 200000 | 0 | 0 | 280000
B0031 | Planned Building Improvements | Corporate Property | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 750000 | 251982.31 | -500000 | 501982.31 | 250991.15 | 11719.75 | 2.335% | 490262.56 | 0 | 0 | 0 | 501982.31 |  | 501982.31 | 0 | 0 | 0 | 0 | 0 |  | 1250000 | 750000 | 750000 | 3251982.31
B0033 | Community Centres | Corporate Property | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3042.03 | n/a | -3042.03 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0100 | Gloucester Green Car Park (H&S) | Corporate Property | 0 | GF | Project - Compliance | Project - Compliance GF | 0 |  |  | 300000 | 70730.14 | 0 | 370730.14 | 185365.07 | 51260.68 | 13.83% | 319469.46 | 0 | 0 | 0 | 370730.14 |  | 370730.14 | 0 | Works completed by ODS in September in line with revised programme. Awaiting Final account sign off | 0 | 0 | Works are complete |  | 0 | 0 | 0 | 370730.14
B0101 | Capital Works at Covered Market | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 200000 | 395.36 | 688057.67 | 888453.03 | 444226.51 | 12861.63 | 1.448% | 875591.4 | -881218.03 | -881218.03 | 0 | 7235 | Y | 7235 | 0 | Awaiting outcome of the covered market masterplan | 0 | Changing priorities. Scope of proposed works will likely be reviewed now draft Master Plan report for the Covered Market has been received and fully reviewed. | 0 |  | 200000 | 200000 | 200000 | 1488453.03
B0104 | Old Gas Works Bridges | Corporate Property | 0 | GF | Project - Compliance | Project - Compliance GF | 0 |  |  | 1000000 | 770635.67 | 0 | 1770635.67 | 885317.83 | 543923.49 | 30.72% | 1226712.18 | 206908.78 | 206908.78 | 0 | 1977544.45 |  | 1977544.45 | 0 | main works to bridge completed - Bearing replacement works underway pending approval from TA - Due to reopen on 31st Oct | 0 | "Bridge is due to be lifting with jacking taking place from underneath. Following this bridge being raised the bearings that the bridge rests on will be replaced. Once this has been completed the project will essentially be completed, other than snagging and demobilsaition. " | Temporary Bridge Opening - 31st July 24 |  | 0 | 0 | 0 | 1770635.67
B0106 | Covered Market Roof Works (Capitalised Planned Maintenance) | Corporate Property | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 525000 | 163057.67 | -688057.67 | 0 | 0 | 0 | 0% | 0 | 648057.67 | 648057.67 | 0 | 648057.67 |  | 648057.67 | 0 | "Covered Market Roof Project was determined by procurement and legal. New project for phase 6c to be done by property services. Phase 7 has been passed over and added to the Masterplan for the Covered Market." | 0 | Access to enable the delivery of Phase 6c of the works is provided. Working in conjunction with Master plan delivery, other major refurbishments at the same time. Ability to share welfare facilities. Deliveries to and from Market St, which is currently semi pedestrianised. | Project initiation |  | 0 | 0 | 0 | 0
B0111 | Town Hall Dry Risers | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 35802.91 | n/a | -35802.91 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0117 | Regeneration Property | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 3402.38 | 0 | 3402.38 | 1701.19 | 3402.38 | 100% | 0 | 0 | 0 | 0 | 3402.38 |  | 3402.38 | 0 | Remainder of funds to be used within the capital programme due to changes in PWLB lending rules. Unlikely to make any further acquisitions | 0 | 0 | Purchase complete. Remaining budget to be considered as part of the budget process |  | 0 | 0 | 0 | 3402.38
B0124 | Port Meadow Moorings | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 0 | 0 | 0 | -5279.22 | #DIV/0! | 5279.22 | 0 | 0 | 0 | 0 |  | 0 | 0 | The last Project Board was held on the 5th August. It was agreed that this project would now be split: -Property to progress the tender for the new contract for managing the moorings with the target of April 2025 for the new contractor in place; -Regeneration to progress longer term feasibility work to include commissioning commercial advice. A new PID and report will be presented to ARG on the 1st October with a request for a budget to cover external advice and internal staff time. | 0 | The site sits adjacent to an SSSI, SAC and SAM and has Freemen of the City of Oxford and the Wolvercote Commoners managing the area. The impact of any proposals on this sensitive landscape will need to be very carefully assessed and a clear communications strategy put in place. The timescale for considering future options may be longer than usual due to the above sensitivity and the need to work with the EA. Starting work now will ensure that sufficient time is available to accommodate other organisations timescales and governance. | Report to ARG - 1st October 2024 |  | 0 | 0 | 0 | 0
B0125 | City Centre Restart (CIL Funded) | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 5324.01 | 34000 | 39324.01 | 19662 | 1109 | 2.82% | 38215.01 | 0 | 0 | 0 | 39324.01 |  | 39324.01 | 0 | My understanding is that CIL should show a total of £8,000 budget for city centre projects. This should be split to £1,368.49 for 2023/2024 and £6631.51 for 2024/2025. My understanding is that any extra shown against CIL, should have been allocated to the Covered Market. | 0 | 0 | 0 |  | 0 | 0 | 0 | 39324.01
B0126 | Asset Surveys | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 300000 | -250000 | 50000 | 25000 | 102.52 | 0.205% | 49897.48 | 0 | 0 | 0 | 50000 |  | 50000 | 0 | Running in conjunction with aquisition of new asset management sysytem to determine requirements and details needed to populate the system | 0 | """Access will be the key risk. Flow of information to contractor Health & Safety Information for properties.""" | Asset Management System in place |  | 250000 | 0 | 0 | 300000
B0129 | Town Hall Options | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 166273 | -141201 | 25072 | 12536 | 1281 | 5.109% | 23791 | -10072 | -10072 | 0 | 15000 |  | 15000 |  | New Regeneration Manager (started July 2024) to progress project forward. Next steps are to: - develop PID for feasibility and viability studies (RIBA Stage 1) - develop and agree brief for feasibility and viability studies | Delays to definition of brief for feasibility and viability studies leading to slippage of forecasted spend into next financial year. | RISK 1. There are multiple planned and ongoing works in the Town Hall (Lots 1, 2 and 4). There is a risk that proposed design options do not align with these works and the investment that they have involved. MITIGATION 1: Work closely with the wider project team to understand the scope and timescales for works and raise any potential clashes / synergies with aims of future design options. Ensure the briefing information (including floorplans) provided to the consultant team for Lot 3 captures all relevant and up to date information for the building. | Develop and agree PID and brief for feasibility / viability study - February 2025 |  | 0 | 0 | 0 | 25072
B0133 | New Burial Space | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 214682.87 | 139317 | 353999.87 | 176999.93 | 61705.71 | 17.43% | 292294.16 | -60000 | -60000 | 0 | 293999.87 |  | 293999.87 |  | Planning approval held up because access to field not secured by property, so archaeology and EA requested borehole ground investigations cannot be carried out. Final legal documents for VP are still with solicitors for signing. Property plan to get VP first then negotiate License with farmer, around ground investigations, for the maintenance of the land before construction works. Additional measures to ensure no adverse impact on parking available to sports clubs has been put back to them (and RFU and Sport England) with aim they can now remove their objection. Athletics Club agreeable, and Property team finalising agreements with Athletics Club, OPT, and ODS - those these latter two can only be concluded following planning approval. Landscape Officer confirmed no objection. EA Pre App advice confirmed suitability of site, but they now wanting more monitoring from boreholes. Proposed monitoring plan gone to them in April 24. Comments back received, and meeting now scheduled to agree a drainage design and monitoring plan to their satisfaction. County Highways unreasonably asking for large scale highway infrastructure of: road widening; bus stops, and pedestrian crossing from the very low traffic small burial meadow, that were not requested from the much larger adjacent sports pitches development. Good availability of reclaimed burial plots, and ODS making good progress exploring options for giving up to 3 years extra supply in existing cemeteries while property deals and planning are concluded. | Delays on planning and property work | Risk: signing agreement with farmer promptly to obtain VP and enable archaeology and borehole works and planning approval. Caused delays to programme - new programme now agreed at DB. Delays will cause extra resource and consultant cost budget pressure. Mitigations: property team prioritising finalising the terms he offered. Risk: County Highways could continue to ask for an unreasonable amount of additional highway improvements. Causing budget, and or time pressure if c278 takes a long while to agree with lawyers. Mitigations: OCC Director to meet County Budget has been included. Try to push for early agreement and drafting of 278 Risk: property negotiation progress with Athletics Club, OPT and ODS slow . Mitigation: monthly meetings to track and minute actions. Risk: ODS costing of works schedules comes in over budgetted market rates, but under 10% over and Directors require ODS to be instructed. Then budget pressure on works and resource costs and programme. Risk of gap in availability just of new (not reclaimed) burial plots from Spring 2025. Mitigations: Burial service are stretching the remaining burial space available, and there is always good reclaimed burial availability. Reactive comms agreed. ODS looking at feasibility of releasing other small areas of land in existing cemetries | Property sign agreement with farmer, and gain access to field. Oct/Nov24 |  | 1323000 | 420869 | 0 | 2097868.87
B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 215 | n/a | -215 | 0 | 0 | 0 | 0 |  | 0 |  | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0138 | Enabling works - Decarbonisation Project | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 638576.39 | -638576 | 0.39 | 0.19 | 0 | 0% | 0.39 | 0 | 0 | 0 | 0.39 |  | 0.39 | 0 | 1. Hinksey Commissioning complete. 2. Project Handed over to Property 08/02/2023 3. Currently reviewing O&M manuals/ Health and safety files. | 0 | Barton Leisure Centre PHX heat exchanger claim by Willmott Dixon due to the pool water high levels of chlorine alleged to have caused corrosin on the heat exchanger. | Completion of Hinksey Commissioning work |  | 638576 | 0 | 0 | 638576.39
B0142 | Stock condition surveys (including bridge works) | Corporate Property | 0 | GF | Rolling Programme | Rolling Programme GF | 0 |  |  | 500000 | 819586.29 | -1000000 | 319586.29 | 159793.15 | 23140 | 7.241% | 296446.29 | 680413.71 | 680413.71 | 0 | 1000000 |  | 1000000 | 0 | Project demand via ARG and DB - funding includes 46 George st, South Park & Alexandra sports projects | 0 | Key risks: 1. Additional cost to meet the programme and bridge opening at the end of May 2024 2. Delays to appointment of Contractor; 3. Labour and material shortages; 4. Increased material prices; 5. Delays in obtaining work permits; 6. Delays due to adverse weather conditions | 0 |  | 300000 | 600000 | 600000 | 1819586.29
B0143 | Town Hall Relocation | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 23420.7 | 455590.27 | 479010.97 | 239505.49 | 39913.14 | 8.332% | 439097.83 | -289010.97 | -289010.97 | 0 | 190000 | Y | 190000 | 0 | Town Hall Projects have been reorganized from 3 Phases into 4 Lots. This Project was previously called Phase 1 and is now Lot 1. Phase 1 activities have been split between Lot 1 and newly created Lot 4 for ICT Works (overseen by Rocco Labellarte) Lot 1 and Lot 4 activities both have budget allocated from Phase 1 budget (B0143) Key works in Lot 1: - Signing off of historic building control application - ongoing - Old Museum Shop to Display Area - target start in January 2025 - Movement of Print and Post function - awaiting clarifications Key works in Lot 4: - WiFi Expansion - target installation 21/10/24 - 16/12/24 (w/e and out of hours working) - Upgrades to PBX (Server) Room - consists of enabling works to upgrade the room (ceiling, walls, doors, AC) followed by upgrades to cabinets. Target final installation June 2025. - IT Build Room - Basement room to surveyed to identify damp issues to be addressed. Target completion date is February 2025 | Slight delays to start of PBX room upgrade and print and post room relocation will result in forecasted spend moving into next financial year. | Coordination of all projects related to Town Hall. Regular meetings with Property teams to ensure no conflicting work areas. | WiFi Expansion part 1 - December 2024 |  | 0 | 0 | 0 | 479010.97
B0147 | Repairs to 2-4 Gloucester Street and 24-26 George St | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 2943.19 | n/a | -2943.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | Project practical completion has been achieved, waiting for final accounts to be concluded with ODS. Possible further works required but negotiations with new tenant are underway and due to be concluded the coming weeks. | 0 | Budget spend is being scrutinised by QS & CA for validity | Completion October 2023 |  | 0 | 0 | 0 | 0
B0149 | Tumbling Bay Embankment Works | Corporate Property | 0 | GF | Project - Compliance | Project - Compliance GF | 0 |  |  | 0 | 15185.5 | 16000 | 31185.5 | 15592.75 | 5667.87 | 18.17% | 25517.63 | 250000 | 250000 | 0 | 281185.5 |  | 281185.5 | 0 | Project is still in design stage awating permits for EA. Public engagement and planning once these stages are achieved. | 0 | Public access is now restricted with Heras Fencing & signage. | Design Completion / Tender |  | 250000 | 0 | 0 | 281185.5
B0151 | Bus Shelters | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 15049.79 | 0 | 15049.79 | 7524.9 | 9811 | 65.19% | 5238.79 | 0 | 0 | 0 | 15049.79 |  | 15049.79 | 0 | The Bus Shelter Tender was launched on the 22nd July with a closing date of the 6th September. The bids will be evaluated during September/ early October with the contract commencing in November 2024. The tender has included the station and NHS shelters for information only to allow these to potentially be included in the contract in the future. Further discussion with Network Rails/GWR and the NHS will be required once the supplier has been appointed. | 0 | Programme delay- the programme timeframe has slipped but the tender process is on target for the award of contract before the current contract ends in late November/early December. Lack of interest in the tendering opportunity - 6 suppliers were interested but only 2 bids were received, one being the current incumbant. Lack of resource to secure and manage new contract - PM has input from Property, Procurement, Legal and County to keep things on track Public opinion- negative press re replacement of bus shelters - explain the reasoning via positive promotion of the new contract and the opportunities it will bring in terms of improved services and the use of sustainable materials, fact that shelters will be recycled etc. Planning and highways issues - it will be the responsibility of the contractor to obtain necessary permissions for any new shelters etc. and this will be made clear during the market engagement. | Contract Award- November/December 2024 |  | 0 | 0 | 0 | 15049.79
B0153 | HSBC Options | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 55000 | 55000 | 29615.38 | 0 | 0% | 55000 | -43000 | -43000 | 0 | 12000 |  | 12000 | 0 | Initial and midway meetings have been carried out with consultant and now awaiting completion of draft report to consider for internal approval | Left time for internal approval before using rest of budget | Confirm once report received | Receipt of draft report by 25th October |  | 0 | 0 | 0 | 55000
B0154 | Covered Market masterplan and enabling works | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 1513991 | 356604.39 | -1072948 | 797647.39 | 321900.62 | 373487.13 | 46.82% | 424160.26 | -124668.39 | -124668.39 | 0 | 672979 | Slip £2m. ND update 03.08.23 = I’ve not seen this Finance Capital Monitoring report previously. The Cabinet report dated 08.02.23 reported a forecast 23/24 spend of £670K, which doesn't match the figure on Column V of this spreadsheet of £2.5Mil - so I'm unclear where the £2.5Mil figure has come from. Column X of this report does match my latest Smartsheet forecasted spend for 23/24 dated 19.07.23, which is £500K. | 672979 | 0 | Project management and design team consultants including Principal Designer now appointed. Key Stage One milestone works to review and revise the current masterplan and essential works proposals completed and under review by Project Board. Proposals to be finalised and supported by a revised business case for approval before progressing to detailed design in the new year. Property Services scope of remedial works to be identified separately. Consultation is on-going with All Souls College in respect of college proposals to extend and refurbish High Street properties including air rights development and market entrance improvements. Works will help offset OCC masterplan costs. | Stage 3 approval to proceed pending approval to OCC MTFP and wider budgetary constraints | Project concerns over additional budget to deliver essential utilities work now largely mitigated following completion of Stage 2 review. Proposals and business case under review including reduced scope within original masterplan budget and option for additional funding supported by a revised business case. Preferred option pending decision by project board. Revised proposals will require a revised business case with separation between essential works and masterplan works as part of a revised viability model. Central Government funding uncertainty = current SPF £300K funding allocation within project’s £6.5m budget could be at risk, as it may need to be used to fund other under-funded R&E projects. Loss of public/wider interest = possible member perception that project progress is taking too long to materialise & possible political/ reputational ramifications of this. Mitigation - consultants have completed Stage One review providing more certainty on deliverability. | Consultant team now working to September deadline to complete a project and budget review for delivery of the masterplan. Draft review tabled at OCM Board 17/09/2024 |  | 589820 | 2906795 | 3265551 | 7559813.39
B0156 | Waterways - Condition Survey / Long Bridges | Corporate Property | 0 | GF | Project - Compliance | Project - Compliance GF | 0 |  |  | 355000 | -342.42 | 0 | 354657.58 | 177328.79 | 121101.55 | 34.15% | 233556.03 | 0 | 0 | 0 | 354657.58 |  | 354657.58 | 0 | Condition survey now completed. | 0 | 0 | Project Initiation | Smartsheet forecast was <25,000 but had to amend to allow formulae to work | 0 | 0 | 0 | 354657.58
B0157 | Works Town Hall | Corporate Property | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 1500000 | 1915.25 | -980000 | 521915.25 | 318649.93 | 266212.35 | 51.01% | 255702.9 | 1000000 | 1000000 | 0 | 1521915.25 | PS budget for roof & facade clean & Ceilings - slip 1.8M | 1521915.25 | 0 | Works are being split into phases from Asset data and surveys | 0 | 0 | Appointment of design team |  | 1000000 | 1000000 | 500000 | 3021915.25
B0162 | Property Services Works to Town Hall | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 0 | 0 | -57692.31 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Project Inititation | 0 | 0 | Project initiation |  | 0 | 0 | 0 | 0
B0165 | Stone walls & Railing programme | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 100000 |  | 0 | 100000 | 50000 | 0 | 0% | 100000 | 0 | 0 | 0 | 100000 |  | 100000 | 0 | Budget code not on P2P and unable to raise orders - Issue raised with Finance (PS) orders ready to issue once code sorted out | 0 | 0 | Project Initiation |  | 0 | 0 | 0 | 100000
B0166 | Broad street roofing & Façade project | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 2000000 |  | -1800000 | 200000 | 100000 | 0 | 0% | 200000 | -80000 | -80000 | 0 | 120000 |  | 120000 | 0 | 19 to 20 Broad Street are currently been surveyed by TMD and awaiting results at the end of October. The broader Broad Street project for the remaining properties is due to go onto intend W/C 7th October 2024 | 0 | Access for erecting scaffolding is restricted to specific days, seasonal markets and university exams. | 19 to 20 Broad Street: Design and Tender, Broader scheme: Survey |  | 500000 | 1000000 | 300000 | 2000000
B0167 | Fire Risk Assessment programme works | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 50000 |  | 0 | 50000 | 25000 | 11800 | 23.6% | 38200 | 0 | 0 | 0 | 50000 |  | 50000 | 0 | Depending on survey outputs and specific action types. This budget is difficult to define, as works need to be categorised for delivery by Capital program first, however, where these do not coincide , this budget applies. | 0 | 0 | 0 |  | 0 | 0 | 0 | 50000
B0168 | Bridge investment work | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 500000 |  | -100000 | 400000 | 200000 | 0 | 0% | 400000 | -320000 | -320000 | 0 | 80000 |  | 80000 | 0 | Tumbling Bay and Trill Mill bridges went to DB on the 7th of October 2024 and was approved to proceed. | 0 | None foreseen | 0 |  | 300000 | 0 | 0 | 700000
B0169 | M&E Capital budget to fund capital replacement of assets including Fire Equipment, Bas Boilers, Electrical works and any components at End of Life (EoL) where there is statutory, H&S or Income need | Corporate Property |  | GF | Project - Other | Project - Other GF | 0 |  |  | 150000 |  | -150000 | 0 | 0 | 0 | 0% | 0 | 70000 | 70000 | 0 | 70000 |  | 70000 | 0 | Hinksey pool boiler replacement feasibility and design underway | 0 | Not enough detail on further equipment needs, currently exploring options with providers | 0 |  | 0 | 150000 | 150000 | 300000
C3089 | ICT - Asset Management System | Corporate Property | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 318662 | 281338 | -318662 | 281338 | 129848.3 | 12500 | 4.443% | 268838 | -131338 | -131338 | 0 | 150000 |  | 150000 | 0 | A scoping document has been issued to a long list of suppliers, the returns will be reviewed and from this a short list of suppliers will be selected and invited to tender for the contract. | Due to the project timeline we will only just be starting system implementation during the current financial year. | The project timeline is very tight and only minor delays will impact on the overall project timeline. Fortnightly project board meetings and weekly meetings with our external consultant are in place to ensure that the chance of any delays are kept to a minimum. | Agree and draft the specification to be used for Tender process. Late July - August 2024. |  | 300000 | 0 | 0 | 581338
E3569 | General Fund Capital Reserve (SCS works & Energy) | Corporate Property | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 1000000 |  | -500000 | 500000 | 250000 | 0 | 0% | 500000 | 0 | 0 | 0 | 500000 |  | 500000 | 0 | To be used for SCS for GF in 25/26 - slip full amount into 25/26 & 26/27 | 0 | 0 | 0 |  | 500000 | 0 | 0 | 1000000
| Corporate Property Projects Total | [8 empty] | 11541038 | 4097817.3 | -6279864.73 | 9358990.57 | 4593866.87 | 1765041.11 | #DIV/0! | 7593949.46 | 1061894.9 | 1061894.9 | 0 | 10420885.47 |  | 10420885.47 | [6 empty] | 8361396 | 7377664 | 5765551 | 30863601.57
| Regeneration & Economy Projects | [10 empty] | 0 | [17 empty] | 0 | 0 | 0
A4853 | City Wide Cycling Infrastructure Contribution | Regeneration & Economy | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 60000 | 31569.16 | -36216 | 114517.16 | 27676.58 | 15282 | 13.34% | 99235.16 | -32517.16 | -32517.16 | 0 | 82000 |  | 82000 | 0 | 7 carriageway locations approved for installation at County CMD, 75 racks, 150 spaces. ODS to install after order is 'made'. Next set of racks proposals being progressed, including Cowley Rd. 'Latest Budget' not updated at time of data entry, in hand with Account Manager. | Additional time is probably required for processing upcoming location approvals, could take longer than previously expected. | >County/City/ODS under resourced leading to delays | Carriageway rack installs Nov-Dec 24 |  | 114517 | 0 | 0 | 229034.16
B0074 | R & D Feasibility Fund | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 500000 | 413815 | -451000 | 462815 | 215599.81 | 0 | 0% | 462815 | 40000 | 40000 | 0 | 502815 | Y | 502815 | 0 | September 2024 Update - Allocations for 24/25 - Templars Square, BNG Feasibility, Floyds Row, HSBC Options, Bury Knowle House, Union Street Car Park, 42 & 46a George Street and Redbridge Masterplan - totalling £512,000. £401,815 budget remaining for 24/25. | 0 | RISKS * Funding is insufficient for the number of schemes requiring feasibility funding. * Continuing to commence further feasibility funded schemes may not be sustainable from a financing or resourcing perspective. MITIGATIONS * Review existing feasibility schemes on on-going basis to assess whether project profilied correctly or can be paused or stopped. * Introduce top up of feasibility budget when projects reach delivery stage and seek budget approval i.e. request gross budget and return the feasibility. * Potentially need to prioritise new bids arising against existing projects to assess options for reallocation of funding. | N/A - budget is allocated to approved schemes at the feasibility stage. |  | 500000 | 200000 | 0 | 1162815
B0081 | Car Parking Oxpens | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 3081.05 | -3081 | 0.05 | 0.03 | 0 | 0% | 0.05 | 3080.95 | 3080.95 | 0 | 3081 |  | 3081 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0.05
B0084 | Jericho Community Centre | Regeneration & Economy | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 200000 | 0 | 0 | 200000
B0086 | Seacourt Park & Ride Extension | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 1262.5 | n/a | -1262.5 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0092 | Cave Street Development (Standingford House) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 178638.47 | 15496 | 194134.47 | 97067.24 | 146694.01 | 75.56% | 47440.46 |  | 0 | 0 | 194134.47 | 200000 | 194134.47 | 0 | Project is not meeting feasibility targets due to economic uncertainties and unstable build costs. It has been decided to 'mothball' the project and investigate meanwhile uses Line in cabinet paper December 2023 to explain The following statement has been issued to Ward Councillors Statement on Oxford City Council’s decision to pause Cave Street redevelopment: “Oxford City Council has taken the decision to pause the redevelopment of Standingford House, on Cave Street, due to the present challenging economic climate. “The Cave Street site will remain a City Council asset, allowing for meanwhile options to be explored that could bring the site back into temporary use. “The decision comes as significant cost increases – both in the construction and the cost of borrowing – mean the agreed budget for the Standingford House redevelopment is no longer sufficient. The Council is responsible for effectively managing its budget and assets and has considered various options to continue with the redevelopment. However, all would require an increased budget and a long-term payback period, putting increased pressure on the Council’s Medium Term Financial Plan. “Plans to replace Standingford House with modern small business units were approved by Cabinet in 2021 as the building did not comply with the required national legislation for Minimum Energy Efficiency Standards (MEES) for commercial properties and the building was in poor condition. It needed urgent repair and maintenance. “Demolition of the former building is complete, and the site has been secured. Consideration will be given to how the site might best be used in the short to medium term, until economic conditions support bringing forward the planned development of small business units.” ENDS The site will be secured (small budget held say £50k) and a handover made to properties w/c 4/12/2003. Housing services are investigating a meanwhile use as TA by installing pods. A project board dedicated to this will be held on a monthly basis. | 0 | TBA on meanwhile uses | Meanwhile uses considered January 2023 |  | 0 | 0 | 0 | 194134.47
B0098 | 1-3 George Street | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 166732.7 | 0 | 166732.7 | 83366.35 | 109067.18 | 65.41% | 57665.52 | -161732.7 | -161732.7 | 0 | 5000 |  | 5000 | 0 | - Works on site have been completed. - OCC/ODS agreed that LADs would be paused for 8 weeks to allow ODS the chance to gather all BREEAM information and finalise accreditation. We may be able to get a 'Good' rating, 'Very Good' very unlikely. - 14/08/24: Caroline/Carolyn/Simon met to discuss, as ODS not making any progress with BREEAM after 5 weeks. - Agreed way forward on 15/08/24: ODS/OCC to work together to finalise BREEAM, to meet to discuss variations line by line with ODS in September, and both sides to put together a qualitative narrative report to describe what they believe 'went wrong' or caused severe delays and financial loss. - ODS/OCC to meet 11/09/24 to discuss variations | Due to ongoing project delay - Ongoing OCC officer and legal costs relating to extended programme and delays - Late invoicing by ODS: ODS invoiced in 2024/25 for works completed in 2023/24 - Consultant payment: payments to consultants were left to the end of the project, so an estimated £10k will be invoiced to OCC for QS and contract admin services | -The project still remains in significant delay, practical completion is now on hold until we can establish BREEAM status. - BREAAM: Risk that ODS will not complete BREEAM as agreed between OCC and ODS. To mitigate this risk, OCC have agreed to meet regularly and support in completing works. - OCC/ODS are in final accounts negotiations which can be lengthy. There are disagreements on contractual obligations on both sides. In order to understand all variations and their legitimacy, ODS have agreed to meet to run through them line by line. In this meeting, ODS will have to demonstrate two things: that the variations were legitimate client changes or instructions, and substantiation/evidence of works. - Risk of having to go to external mediation in case disagreements cannot be resolved. this will cause further delays and add cost. - risk of loss of income as the property sits empty, without an operator. OCC is working with Savills to arrange viewings. OCC Property has been in talks with potential tenants on possible lease agreements and rent. - risk of clawback for OxLEP funding. This is unlikely, but OCC/ODS working together to find a position both sides are comfortable to reach PC. OCC also working with Savills to ensure a tenant moves in asap. | BREEAM Workshop 1 - 22/08/24 |  | 0 | 0 | 0 | 166732.7
B0112 | Future Options for City Centre Land (Odeon) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | -205651.15 | 336103 | 130451.85 | 65225.92 | 24686.56 | 18.92% | 105765.29 | -130451.85 | -130451.85 | 0 | 0 | Y | 0 | 0 | Planning application resolution to grant is on Agenda for the October Committee. This is a 1 month delay on project, and was due mainly to the request for additional work to the visual assessment information. Drafting of s106 being finalised, and Press release comms agreed in preparation for after Resolution to Grant achieved. Developer and operator requested a revision to lease boundaries to accommodate cycle parking area and store for community space. Acceptable and legals being progressed. | Contingency unspent so far in 24/25 Note- £98K property payment due in Feb/Mar 25 | Agreement being reached with the LPA on s106 and visual information. Mitigations: additional meetings as required, and correctly articulating wide range of significant benefits and improved Gloucester Green elevation and maximised active frontages to benefit Gloucester Green - a key project and city centre aim. Right to Light injunction risk - mitigate through progressing appropriation process. Minimising future reputational risk to Council - in its public servant role by s106 ensuring community space is available in perpetuity to at least serve local city centre residents as well as other wider groups. Mitigation by liaison with communities and economic team. And list of approved uses in sub lease between Staycity and Makespace. | Resolution to grant - Oct 24 |  | 0 | 0 | 0 | 130451.85
B0114 | Diamond Place Redevelopment | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 9935.5 | 64 | 9999.5 | 4999.75 | 2365 | 23.65% | 7634.5 | 0 | 0 | 0 | 9999.5 |  | 9999.5 |  | OCC Client Brief approved at Development Board on the 4th March and has been sent to OX Place for consideration. Ox Place have now confirmed that they will not be able to provide any update until January 2025. The local GPs have now heard back from BOB ICB who have confirmed that no funding was approved by their Executive Board for the move to South Parade but this didn't rule out potential funding in the future due to the change of government. Officers met with Peter Redman from BOB ICB in September. He was unable to confirm whether funding would be available for Diamond Place in the future or not but has agreed to provide information regarding the size of health facility they would require at Diamond Place. This will be shared with Ox Place. | 0 | The Neighbourhood Forum have clear ideas about the redevelopment of the site. The Stakeholder workshops have helped to explore the key challenges of developing the site and the forum are now considering a review of the neighbourhood plan. The Neighbourhood Forum also have different expectations about the timescale for any potential redevelopment. We will continue to engage with them through the tri-partite meetings and involve Ox Place in these meetings in the new year. | Ox Place to provide update on feasibility work - January 2025 |  | 74770 | 0 | 0 | 84769.5
B0116 | Osney Mead Path Works (HIF) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 564914 | 1398635.13 | -564914 | 1398635.13 | 699317.56 | 0 | 0% | 1398635.13 | 0 | 0 | 0 | 1398635.13 | Jenny - surely most of this happens next year ? Need to leave in 23/24 as deadline for claim is March 24 | 1398635.13 | 0 | It has been agreed that HIF funding allocated for Pathworks to be focused on the pathworks associated with the proposed Oxpens River bridge. The funding for the pathworks improvements to the west of the railway to Osney Mead would then need to be secured from elsewhere. Discussions have taken place with Homes England and Oxford University on the principles involved. Balfour Beatty have been appointed as contractor to deliver the bridge and pathworks. A Deed of Variation to the HIF Funding agreement was received from Homes England and returned with comments and a further version of the DofV has been received. Back to back funding agreements have been drafted re the OFAS element of the funding with the Environment Agency but are still subject to review and discussion. However, an agreement with University of Oxford has not been agreed which presents a risk to the drawdown of funding with regard to clawback by Homes England. This has been reported to Cabinet who have agreed to accept the risk. Funding has to be drawn down by March 25 (subject to signing the DofV) and details of spend evidenced and pre conditions and milestones met. | 0 | There remain risks relating to the ability to claim the funding from Homes England. A Deed of Variation has been drafted to extend the period to claim funding up to March 25 and resolve other issues. Evidence of spend is required to make the claim and there is a risk that there will not be sufficient spend on the pathworks by March 25 as delivery is now delayed by the JR of the planning decision. Also if funding is spent without the University delivering housing at Osney Mead there is a risk of clawback. | Deed of Variation from Homes England for the HIF funding to be progressed - Requirement to conclude by 24 Sept 2024 |  | 0 | 0 | 0 | 1398635.13
B0118 | Oxford Ice Rink Development | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 36704 | 0 | 36704 | 18352 | 25553.6 | 69.62% | 11150.4 | 0 | 0 | 0 | 36704 |  | 36704 |  | Prior and Partners have completed the draft pre-app which was reviewed by the Project Board and Development Board in August. The pre-app was submitted on the 23rd August and the pre-app meeting will be held on the 14th October. Lead members were updated at the weekly leaders meeting in early September. The project board will be updated on the pre-app discussions at the end of October. | 0 | 1. Alternative locations may not be achievable within the timescale required for delivery of a new ice rink. 2. Alternative locations outside of the city centre may be politically unacceptable. Members briefings have confirmed that these options can be explored by officers. 2. Access to the new location and provision of sufficient parking for ice rink users is a key issue. | First pre-app meeting with LPA - October 2024 |  | 0 | 0 | 0 | 36704
B0119 | Oxford Station Feasibility | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 51563.3 | 0 | 51563.3 | 25781.65 | 0 | 0% | 51563.3 | -44301.98 | -44301.98 | 0 | 7261.32 |  | 7261.32 |  | Drafting materials to support input and decisions ahead of publication, including digital accessibility requirements. Response to LC17 sewer constraint in car park - did not object to land disposal | Forecast spend is confirmed. Other budget may slip as stakeholder engagement approach needs to be confirmed. | New Risk of sewer in becket St car park - impacts/mitigations considered and will now be a constraint. Draft risk register last updated with Board Nov 2023; to update next following stakeholder engagement sessions (date tbc) The RED risks are now: • DfT does not agree to fund Oxfordshire Connect or remains uncertain (now red, was amber) but masterplan is revenue generating towards rail costs • Highway modelling is not available to inform optimal crossing points and design and highway improvements to Becket St or Botley Rd - likelihood increased given no further data /resources being available, and increased potential impact given better understanding of pressures. • Delay reaching alignment on how to proceed with engagement. Public consultation remains uncertain until alignment around COMPF/rail strategy are understood . • Rail regulator does not agree parking reduction/ uncertainty how much parking would need to be re-provided – ORR are engaged at Oxfordshire Connect Programme Delivery Group. NR leading Connectivity Study update + LC17 process will require statutory consult local authorities + others on reduction | Further engagement around alignment of rail strategy and OSM publication, including dates. Further engagement also needed with COMPF team. |  | 0 | 0 | 0 | 51563.3
B0120 | Osney Bridge (Growth Deal) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 7184694 | 96329.26 | 177397 | 7458420.26 | 3729210.13 | 406159.65 | 5.446% | 7052260.61 | -6472459.26 | -6472459.26 | 0 | 985961 | Jenny - surely most of this happens next year ? Profile updated | 985961 | 0 | Planning permission granted but subject to Judicial Review. Further submission has been made to County for Technical approvals: AIP, Section 38 & CAT 3 checks - near to conclusion - but still awaiting AiP sign off. S106(3) Highways Act notice published on 2nd May for 6 weeks, process due to conclude shortly. Initial priced packages received by BB - showing increase from previous estimates. Due to delays further funding to cover CEs and Risk is needed. Circa 1.35m. University being approached. OxWED have been approached re. Land behind ice rink for crane as this could reduce the above figure and reduce risks from flooding. Delays have made risk of completed by March 2025 very high so approach to County to seek agreement to extend funding to allow construction in 2025. | Delay to programme | Risk of JR proceeding delaying programme beyond 2025. Situation being monitored. Meeting the final Growth deal & HIF spending deadlines. Work underway to secure the funding for 2025. Negotiations with OXWED in relation to enabling works and land use. Further information to be provided re crane positioning. Risk budget will not be sufficient. On going work with BB re cost of PCSA and bridge construction. | Confirmation on extension of Growth Deal funding |  | 0 | 0 | 0 | 7458420.26
B0122 | City Cycle Schemes (Growth Deal) | Regeneration & Economy | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 431332.3 | 0 | 431332.3 | 215666.15 | 23096 | 5.355% | 408236.3 | -213332.3 | -213332.3 | 0 | 218000 | 603000 | 218000 | 0 | Donnington Rec shared cycleway / footway: Info for condition discharge, and updated landscape schemes on Agenda for October Planning Committee for approval. SIgnificant support letters from community in favour of path through park. Liaison with Cllrs, residents, and football club done, and ongoing. Subject to planning approval, works can start on site early November. Contract with ODS being finalised and signed. And ODS can mark out pitches during construction to preference of football club, while allowing cycle access through too. Legal finalising s106 wording. Marsh Lane Rec: completed, apart from Property completing agreement with Christchurch for preferred connection to the highway. Scheme functions without. | Delayed start to site works due to awaiting planning approval of updated scheme information and condition info. | Risk - not getting planning discharge of conditions and updated landscape scheme. Mitigation: - provided case officer with all info she needs; and generated positive consultation comments of support, incl from football club and residents association. Risk - Legal resurce at City and County not sufficientto produce s106 document on time. Mitigation: ongoing liaison with legal lead. Risk - ODS have delays in gearing up for work. Mitigation: worked is booked in diary, and keep close liaison ongoing. Risk: consultant CA and PD cause delays and extra costs. Mitigation: Managing good relationships and asking for input as early as possible | Planning approval of conditions and updated landscape scheme - Oct 24 |  | 0 | 0 | 0 | 431332.3
B0128 | Greenways Cycling Project | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 39250 | 53000 | 92250 | 46125 | 33007 | 35.78% | 59243 | 0 | 0 | 0 | 92250 |  | 92250 |  | Project has now completed baseline analysis and route prioritization. Next steps is on the ground surveys and finalising first 50km of routes. | 0 | Insufficient officer resource leads to project delays (now addressed by increasing capacity at City and stitching this project into wider Movement and Place Framework programme with County) Project completes without supporting delivery of schemes (should be addressed through successful scope and good clienting) | Target contract start - 8 January 2024 |  | 0 | 0 | 0 | 92250
B0130 | CIL Feasibility | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 43350 | 0 | 43350 | 21675 | 0 | 0% | 43350 | 0 | 0 | 0 | 43350 |  | 43350 | 0 | £50k budget remaining is ear-marked for Cowley Branch Line feasibility. £6,650 has been allocated to revenue spend in relation to Legal advice, however further Legal costs (c£20k) have now been incurred. After meeting Legal fees, remaining unallocated CIL budget can cfwd to 23/24 be reallocated to another project. | 0 | 0 | 0 |  | 0 | 0 | 0 | 43350
B0131 | Meanwhile In Oxfordshire | Regeneration & Economy | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 0 | 1722 | 80595 | 82317 | 41158.5 | 2364 | 2.872% | 79953 | 0 | 0 | 0 | 82317 |  | 82317 | 0 | Undertaken Facilitated meeting on how Makespace and OCC can work together in future. Ongoing Comms and TikToks for Market additions through Meanwhile Prepare for Lessons learnt meetings with operator and then with all project partners ( OXLEP & Districts) Prepare doc for LGC award submission. Ongoing Liaison with Makespace on progress of final schemes | 0 | Viability of Phase 2, years 2 & 3 based on Revenue income. | 17 Jan lessons learnt with MS 18 Jan lessons learnt with OXLEP & districts |  | 0 | 0 | 0 | 82317
B0132 | Coach Parking Feasibility | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 10000 | 10000 | 20000 | 10000 | 0 | 0% | 20000 | 0 | 0 | 0 | 20000 |  | 20000 |  | **Feasibility funding in place, with project having been on pause due to need to sequence with wider County strategic transport policies. Current intention between City and County officers is to progress study as part of new "Central Oxfordshire Movement & Place Framework" programme of work. Atkins consultants have now been commissioned to undertake this feasibility study. Target milestones remain TBC** | 0 | 0 | June-Aug 2024: report commissioned and started / inception date planned |  | 0 | 0 | 0 | 20000
B0141 | City Centre Public Realm (Kiosks Project) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 179987 | 61047.3 | 0 | 241034.3 | 120517.15 | 78560.32 | 32.59% | 162473.98 | -50000 | -50000 | 0 | 191034.3 |  | 191034.3 | 0 | Cabinet in place, and date obtained from SSE for them to connect it. Currently then arranging for supply comppany to fit meter following SSE work. Hoardings in place until new electric supply connected and working, then disconnection can be done for other power supply on 38 -40 George St, and paving works completed. | Delays from utility companies | Risk of delays due to SSE process to connect new Cabinet, and due to Npower lead times to fit meter. Mitigation: regular chasing and communication. Risks of ODS electrician work slow to progress connections of power bollards, and finish Cabinet to LSD market satisfaction. Risk of delays due to SSE process to carry out disconnections of Odeon wall infrastructure following new Cabinet live. Mitigation: schedule in time for all forms and chasing required; and OCC payments timescales. | SSE connect supply to new cabinet - Nov 24 |  | 0 | 0 | 0 | 241034.3
B0145 | St Michael's Street Levelling Works | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 168817 | 6826.57 | 233183 | 408826.57 | 204413.28 | 23682.78 | 5.793% | 385143.79 | -120807 | -120807 | 0 | 288019.57 | Construction pushed back to Q4 24-25. Budget requires adjustment via finance team. £53k spend 22-23, 20k budget 23-24, £402k budget 24-25 | 288019.57 | 0 | Investigative trench survey confirmed an estimated £19.8k additional costs (main cost Virgin Media). Agreed with HoS/HoF to vire from unallocated City Restart CIL. Budget remains under £500k. Crossing £500k threshold would require Leader delegation (Brown/Hollingsworth) for decision to proceed. S278 progressing. Potential for COMPF/ZEZ/SPF underspend contribution for enhancements, potentially reintroducing removed elements. Construction planned for Jan-Mar 25. | Reprofiling of billing programme | > Works/Legal delay affecting SPF spend criteria deadline - construction programme reviewed and agreed with ODS, early engagement with Legal > Services cause unexpected delays - GPR survey / investigative trenches, increased budget, early engagement with utilities | Proceeding to contract with ODS |  | 0 | 0 | 0 | 408826.57
B0146 | Ice Rink Car Parking | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 100000 | 26065.93 | -110000 | 16065.93 | 8032.97 | 10415 | 64.83% | 5650.93 | 0 | 0 | 0 | 16065.93 | Y | 16065.93 | 0 | The latest proposal for 12 parking spaces has internal approval and consultants have prepared a planning application to reflect this. The project is on hold until there are sufficient staff resources within the regeneration team to support it. | 0 | Risk 1: New proposals not acceptable to planning & user groups Mitigation 1: Meeting with user group, pre-app discussions. Risk 2: Ice rink users unhappy with proposals leading to reputational risk. Mitigation 2: Reduce risk by open dialogue and good Comms | Project on hold |  | 130000 | 0 | 0 | 146065.93
B0148 | Oxford Flood Alleviation HIF Contribution | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 4350000 | 0 | 4350000 | 2175000 | 0 | 0% | 4350000 | 0 | 0 | 0 | 4350000 | Jenny - surely most of this happens next year ? Need to leave in 23/24 as deadline for claim is March 24 | 4350000 | 0 | Homes England have provided a revise Deed of Variation to the funding agreement. This has addressed some significant issues with the original funding agreement including extending the period for the draw down of the funding to March 2025. Response has been sent and final version awaited. Capacity funding has been received for 22/23 and 23/24 to address some of the HIF internal costs to date. A bid has been made for capacity funding for 24/25 and HE have requested further details. | Funding is going to be required to be drawn down by March 2025 and will then be passed to the EA. | This HIF is particularly complex as there are two elements of works being funded separately from the housing delivery which is being facilitated by the funding. There remains a risk that it will not be possible to claim the funding, which requires pre conditions to be met and evidence of spend. A recovery strategy is sought related to housing delivery and this is subject to discussions with U of O. There is a risk that if housing is not delivered at Osney Mead that the funding could be clawed back by Homes England. | Agreement of Deed of variation - October 24 |  | 0 | 0 | 0 | 4350000
B0152 | Cowley Branch Line Full Busines Case | Regeneration & Economy | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 1689183 | 887426.13 | 23060 | 2599669.13 | 1299834.57 | 1428388.09 | 54.94% | 1171281.04 | 0 | 0 | 0 | 2599669.13 | £2,467,817 I've updaded this on Smartsheet | 2599669.13 | 0 | Project is up and running. Programme Panel meetings taking place every 4 weeks as well as NwR progress meetings. Pedestrian and Cycle bridge design (Oxford Cowley station) RIBA stage 1 completed and RIBA stage 2 underway. commissioning of the Infrastructure Place Study (IPS) was completed just before Christmas, just subject to contract formal signing taking place Wed 17th Jan. Formal inception meeting to take place on Wed 17th Jan and IPS team already invited to attend several working groups and engagement meetings. Additional work has also been commissioned by County on Development of a developer contributions strategy for infrastructure to support the reopening of CBL, this has been completed and it is anticipated that the IPS team will pick this up and progress it further. Although CDM principal Designer was not part of the IPS commission, lead consultant has provided cost estimate for this should we wish to instruct it. | 0 | 0 | Completion of RIBA stage 2 concept design Pedestrian and cycle bridge - End Feb 2024. |  | 653350 | 0 | 0 | 3253019.13
B0160 | Templars Square (GF Element) | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 0 | 0 | 3846.16 | 404 | n/a | -404 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 100000 | 0 | 0 | 100000
B0161 | Floyds Row (Feasibility2024) | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 1050000 |  | -1000000 | 50000 | 26923.08 | 0 | 0% | 50000 | -23000 | -23000 | 0 | 27000 |  | 27000 | 0 | Draft report received and comments reverted back to Carter Jonas. Scope of project increased to include wider regeneration area. | Allowance of time for internal approvals | Property is vacant during process but is regularly inspected by vacant property team. Business rates will need to be mitigated. | Instruct Carter Jonas for further feasibility on wider regeneration project |  | 0 | 0 | 0 | 50000
B0163 | Network infrastructure installations (utilities, Comms & Energy) | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 40000 |  | 0 | 40000 | 20000 | 0 | 0% | 40000 | 0 | 0 | 0 | 40000 |  | 40000 | 0 | In progress no spend in year - slip 40K to 25/26 | 0 | 0 | 0 |  | 40000 | 40000 | 40000 | 160000
B0164 | Waterways investment | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 500000 |  | -500000 | 0 | 0 | 0 | 0% | 0 | 500000 | 500000 | 0 | 500000 |  | 500000 | 0 | Long Bridges | 0 | 0 | Start on site 05/08/2024 |  | 500000 | 0 | 0 | 500000
B0170 | Salary Costs across the Council to be capitalised | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 323000 |  | -323000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
B0171 | Regeneration Property Purchase/Odeon | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 212000 | 212000 | 106000 | 713.2 | 0.3364% | 211286.8 | -212000 | -212000 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 9880657 | 20821963 | 5466423 | 36381043
B0172 | Bury Knowle House | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 41000 | 41000 | 22076.92 | 0 | 0% | 41000 | 0 | 0 | 0 | 41000 |  | 41000 | 0 | Design team out to RFQ, will then be appointed following review of returns. | 0 | 0 | Appointment of design team - November 2024 |  | 0 | 0 | 0 | 41000
B0173 | Union Street Car Park | Regeneration & Economy |  | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 65000 | 65000 | 35000 | 731 | 1.125% | 64269 | 0 | 0 | 0 | 65000 |  | 65000 | 0 | Awaiting further information on ownership of small area that could be incorporated into the site to increase the footprint of the proposed development. Prices for an outline massing study will be sought be the end of July 24. Tender for viability advice will be sought during August 24 | 0 | 0 | Land ownership information - 30th September 2024 |  | 0 | 0 | 0 | 65000
M5033 | Blackbird Leys Regeneration (GF Element) | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 5586876 | 6553772.05 | -3784648 | 8356000.05 | 4178000.03 | 6258552.41 | 74.9% | 2097447.64 | 785779.95 | 785779.95 | 0 | 9141780 | Karoline - is this right - hif is only £6m | 9141780 | 0 | COMMUNITY CENTRE: Design/Planning: - Design freeze achieved, with minor coordination between disciplines still ongoing, design team working on planning submission - Energy consultants asking for 5 weeks to produce assessments and reports, which may delay submission date - OCC discussing fee and programme for Stage 4 drawings to be produced by Jessop & Cook for tender (both fitout and S&C) - OCC/PBT discussing procurement strategy for community centre. PBT preferred route is 1-stage D&B, with one single contractor delivering both shell & core and fitout. - OCC agrees that having one contractor delivering both scopes will simplify and expedite delivery, but is concerned with loss of control over design due to D&B contract. OCC to increase design control by requesting detailed Stage 4 drawings for tender and detailed ERs. Programme: - Programme has been affected by design development delays on externals. Planning submission date has now slipped to mid September 2024. - Design freeze anticipated for 16/08/24 - Final Exhibition: w/c 09/09/24 - Submission: 20/09/24 Budget: - design team has been working on VE exercises on shell & core, guided by PBT's QS. - S&C still over budget but PBT agreed they now have a viable/buildable design (JG at Procurement meeting) -D&S reviewing/revising cost plan for fitout to reflect latest design PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. | Delay to planning submission for outline application submission and therefore start on site. Current delay of 5 months from original submission date of end of March 2024. This has pushed construction costs for community centre shell & core to 25/26, 26/27. We are currently studying procurement options for the community centre - traditional, 1-stage D&B and 2-stage D&B. Each option has a slightly different programme but all show construction starting 25/26, whereas before, we had forecast SoS for 24/25. I'm unsure if I've missed something in my 24/25 forecast as £5.2m is substantial, but Jason J is away and I need to sit down with him and go over line by line to see what I've missed or if the 24/25 forecast was too high. Will be able to confirm these numbers when he gets back on 22/07. | - Community Centre delivery: This is still a major risk to the project, as it has the potential to delay the occupation of Block A. This planning condition is being questioned by PBT, and is relatively vague in wording. KSM to confirm. -The programme has slipped due to delays in design development, and planning submission has now been pushed to 20 Sept 2024. This means there will be slippage on completion date for the centre. - Community Centre Budget: After VE exercises, S&C still over budget, but PBT agrees there is no more scope for VE and are happy to proceed to tender. Revised cost report for fitout to be issued. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2. - OCC/PBT discussing Ph 2 options - Peabody confident they can get a viable Ph 2 scheme, which will de-risk the delivery of housing and therefore risk of claw back for HIF by Homes England. - Comms & Engagement: Still a risk to relations as this project gets more politically sensitive. Comms around Community Centre especially sensitive as the planning submission date has been moved back several times as the project faces delays at design development stage. Parish Council/Community have expressed concerns about delays and worries about housing being delivered without the community centre have returned. OCC to continue to attend Parish Council meetings and communicate with concerned parties to assuage concerns. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024. | Community Centre Design Freeze: 16/08/24 |  | 4866000 | 5452000 | 4121439 | 22795439.05
T2301 | Depot Rationalisation | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 266645 | 0 | 266645 | 133322.5 | 0 | 0% | 266645 | 0 | 0 | 0 | 266645 |  | 266645 | 0 | Work has continued during 2022 to explore using Horspath to accommodate the majority of ODS business to free up other depot sites and to allow for some growth in ODS business. This option was reliant on leasing extra land of a couple of hectares in size to store vehicles and other spill over activity that the existing Horspath depot site would not be big enough to accommodate. Several sites in the vicinity have been looked at but none can accommodate a long lease that would provide the business certainty ODS would need. The city work is now on pause with the agreement that ODS are going to scope out what staying on their existing sites mean and whether they could physically rationalise into the other depot sites freeing up Horspath to save them rental costs. Monitoring of other site opportunities will continue. We await update from ODS in order to feed into confidential scrutiny update requested as part of budget process. | 0 | Identification of a suitable site to create parking for ODS operations. Feasibility - Review of ODSL operational requirements to include as tender document for RIBA 0-2 reports. Clear and robust gateways to be set for RIBA 0; RIBA 1 and RIBA 2 | Update expected end of August from ODS |  | 0 | 0 | 0 | 266645
| Regeneration & Economy Projects Total | [8 empty] | 17947471 | 14858789.7 | -5525961 | 27339463.7 | 13634188.33 | 8590984.3 | 5.5049 | 18748479.4 | -6131741.35 | -6131741.35 | 0 | 21207722.35 |  | 21207722.35 | [6 empty] | 17059294 | 26513963 | 9627862 | 80540582.7
| Housing Delivery Projects | [10 empty] | 0 | [17 empty] | 0 | 0 | 0
M5025 | Barton Park - Purchase by Council | Housing Delivery | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 11051609.13 | 3362379.8 | 3356000 | 17769988.93 | 8884994.47 | 6646509.79 | 37.4% | 11123479.14 | -11925405.93 | -11925405.93 | 0 | 5844583 |  | 5844583 | 0 | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Remainder of in year budget removed from programme | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | 0 |  | 17848472.83 | 5789066.94 | 4962150.08 | 46369678.78
M5026 | Housing Company Loans (excl Barton Park) | Housing Delivery | 0 | GF | Housing Company Loans | Housing Company Loans GF | 0 |  |  | 14051609.13 | 7708000 | 2156391 | 23916000.13 | 11958000.07 | 5599810.04 | 23.41% | 18316190.09 | -18869750.13 | -18869750.13 | 0 | 5046250 |  | 5046250 | 0 | The programme has been updated in Sep24 following a review of the OX Place BP. | Revised loan activity now adjusted due to updated HRA stage payments, better cash management and programme planning. | The activity of loan drawdowns is completely development led and we have experienced delays and removed the optimum bias from the programme. | 0 | Latest forecast via email suggests £8.73m slippage OCH(D)L (non-Barton) loans £17.808m | 36634000 | 20762000 | 29739609 | 111051609.13
M5032 | Barton Park - loan to OCHL | Housing Delivery | 0 | GF | Housing Company Loans | Housing Company Loans GF | 0 |  |  | 0 | 2036379.8 | 7178000 | 9214379.8 | 4607189.9 | 0 | 0% | 9214379.8 | -3369796.8 | -3369796.8 | 0 | 5844583 |  | 5844583 | 0 | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Remainder of in year budget removed from programme | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Acquisition of social housing from next phase of development. | Latest forecast via email suggests £6.75m slippage OCH(I)L (Barton) loans | 0 | 5789066.94 | 4962150.08 | 19965596.82
M5034 | Affordable Housing Supply | Housing Delivery | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 1958000 | 128000 | 0 | 2086000 | 1043000 | 0 | 0% | 2086000 | -1958000 | -1958000 | 0 | 128000 |  | 128000 | 0 | s106 Top-up/ Enabling grant. Dec 22 Delegated decision re £650k agreed to enable a 9 unit tenure switch to SR at Barton Park - with P4P. Grant Agreement to be finalised and detailed delivery programme awaited (July 24). Sept 23 Cabinet committed the remaining £1.3m as further funding into the BBL Regen project (for phase 2) if required - to ensure viability. July 24 update - Included in Peabody modelling and assumed to be required to make the scheme stack. | Reprofiling into future years | 0 | Grant Agreement for P4P for additional affordable homes at Barton Park. |  | 0 | 0 | 0 | 2086000
M5035 | Growth Deal Registered Provider Payments | Housing Delivery | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 272000 |  | -272000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Passing on grant received from County. No funding from the Capital Programme. All incoming funding received (£10,530,000) is paid out to the relevant projects as 90% on SoS and 10% at PC. £3,470k paid to L&G for William Morris Court £4,340k paid to Catalyst/ Peabody for Littlemore Park. £2,720k committed to A2Dominion for Gibbs Cres, with £2,448k paid to date. | 0 | All agreements sealed. But see comment above about terminating the agreement with A2D. | Continue to manage and monitor 'stalled site' with A2D at Gibbs Crescent. £272k due at PC. There is a risk that this will not be paid, and that the £2,448k already paid will need to be clawed back (and then repaid to County). A2D are seeking replacement funding direct from Homes England (with the claim currently held pending). |  | 272000 | 0 | 0 | 272000
M5037 | Northern Gateway (Oxford North) | Housing Delivery | Jenny Barker | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 1153416 | 0 | 1153416 | 576708 | 2218.05 | 0.1923% | 1151197.95 | 0 | 0 | 0 | 1153416 |  | 1153416 | 0 | It has not been possible to agree the drawdown and spend of the HIF grant and a request has been made to Homes England to withdraw from the funding agreement. | 0 | Homes England have advised they will be seeking repayment of the funding currently held | Confirmation from Homes England re the withdrawal from the Funding agreement and confirmation that funding held is to be returned. |  | 0 | 0 | 0 | 1153416
| Housing Supply Projects Total | [8 empty] | 27333218.26 | 14388175.6 | 12418391 | 54139784.86 | 27069892.44 | 12248537.88 | 0.6101 | 41891246.98 | -36122952.86 | -36122952.86 | 0 | 18016832 | 0 | 18016832 | [6 empty] | 54754472.83 | 32340133.88 | 39663909.16 | 180898300.73
| Planning Projects | [10 empty] | 0 | [17 empty] | 0 | 0 | 0
C3091 | ICT - scanning of all paper planning files | Planning Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 150000 | 0 | 150000 | 75000 | 10092 | 6.728% | 139908 | -90000 | -90000 | 0 | 60000 |  | 60000 | 0 | BUDGET NOTE: It is currently understood that any budget not spent in this financial year 24/25 (forecast at £90k) will be folded into the 25/26 Town Hall Lot 2 budget (B0157) to contribute towards the overall costs of the scanning project, which will come out of this budget (B0157). The overall costs of the scanning project will be estimated and taken to Cabinet for approval in January 2025. The majority of the spend is likely to take place in the 25/26 financial year. PROJECT UPDATE: Two main options for a scanning project are being considered: - Option 1 - A business case for digitising the Councils archive was prepared in June 2024. It recommended an internal auditing / cataloguing process of files stored to be carried out by each Service area to set the requirements and specification for a digitisation project by a third-party supplier. - Option 2 - Following the recommendations of the Fire Risk assessment, an alternative option has been explored which accelerates the removal of files from the Town Hall Basement. In this option a third-party supplier removes and catalogues the files stored. This catalogue could then be used to set the requirements and specification for a digitisation project by a third-party supplier. - An update report was provided to the Town Hall Project Board 03.10.24 with a detailed comparison of estimate programmes and costs (internal and external) between the two options. - Option 1 is the recommended approach to the Scanning Project. The next step will be to speak to Heads of Services with files in the Town Hall Basement and refine the estimated internal resource needed to undertake the project. Following this the aim is to submit an updated Business Case to OCB 26.11.24 for approval to take to cabinet in January 2025. Horspath Road File relocation Files stored at Horspath Road were relocated 15/10/24 to allow the building to be converted for alternative use. These are now stored in the Town Hall Flat, whilst the planning for the overall digitisation project is progressed. | Delays to the start of the scanning project whilst most suitable route is defined, leading to forecasted spend being moved into next financial year | RISK 1 - Fire risk of ongoing storage of combustible (paper-based) material in the town hall basement MITIGATION 1 - Limited and controlled access to Town Hall Basement Area. Prioritise removal / relocation of material in escape routes. Progressing Scanning Project will lead to removal of significant number of files from the Town Hall Basement. RISK 2 - Potential breach of legal requirements for retention of and access to archive material. MITIGATION 2 - Clarification of Records Retention and Disposal Schedule as well as public access requirements. Identification of documents that need to be retained will be part of initial part of the project. | Relocate Files from Horspath Road to Town Hall - October 2024 |  | 0 | 0 | 0 | 150000
E3511 | Essential Repairs Grant | Planning Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 15000 | 22107.97 | 0 | 37107.97 | 18553.99 | 5000 | 13.47% | 32107.97 | -7107.97 | -7107.97 | 0 | 30000 |  | 30000 | 0 | Increased ERG budget has been approved in Council Budget to help waiting list of clients. | 0 | Not enough contractors for work type | 0 |  | 15000 | 15000 | 15000 | 82107.97
E3521 | Disabled Facilities Grants | Planning Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 1200000 | 353748.55 | 0 | 1553748.55 | 776874.27 | 941334.45 | 60.58% | 612414.1 | 0 | 0 | 0 | 1553748.55 |  | 1553748.55 | 0 | BAU in HIA with referrals being progressed. | 0 | County Council Occupational Therapists are funded so there is no backlog and the service is actively promoting the availability of funding. Liaising with hospitals to enable discharge. | 0 |  | 1200000 | 1200000 | 1200000 | 5153748.55
E3561 | Additional DFG Funding CLOSED | Planning Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 0 | 4968.48 | 0 | 4968.48 |  | -2438.75 | -49.08% | 7407.23 | -4968.48 | -4968.48 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 4968.48
T2299 | Controlled Parking Zones | Planning Services | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 57000 | 386000 | 443000 | 221500 | 0 | 0% | 443000 | -84920 | -84920 | 0 | 358080 | 53K spent this financial year spend for 24/25 to be decided when next priority list discussed with county council so 447K remaining | 358080 | 0 | Paper presented to 7/10/24 Development Board (DB) indicating County Council is requesting the release of £358,080 to cover the review of 7 existing CPZ zones in the city. Recommendation from DB to check whether this would be a key decision and need to go to Cabinet, also to brief LU. DB also supportive of remaining funds (£84,920) being returned to the CIL pot and not re-profiled. Post DB Update - Confirmation that Cabinet decision is required - is on forward plan for December 2024. | 0 | Cabinet does not agree to release the funds. | Release of £358,080 to County Council. |  | 0 | 0 | 0 | 443000
| Planning Projects Total | [8 empty] | 1215000 | 587825 | 386000 | 2188825 | 1091928.26 | 953987.7 | 0.31703 | 1234837.3 | -186996.45 | -186996.45 | 0 | 2001828.55 |  | 2001828.55 | [6 empty] | 1215000 | 1215000 | 1215000 | 5833825
| Development Directorate Total | [8 empty] | 58036727.26 | 33932607.6 | 998565.27 | 93027064.13 | 46389875.9 | 23558550.99 | 25.32% | 69468513.14 | -41379795.76 | -41379795.76 | 0 | 51647268.37 |  | 51647268.37 | [6 empty] | 81390162.83 | 67446760.88 | 56272322.16 | 298136310
Corporate Resources
Business Improvement Projects
C3044 | ICT Software and Licences | Business Improvement | 0 | GF | rolling programme | rolling programme GF | 0 |  |  | 245000 |  | 0 | 245000 | 122500 | 402356.99 | 164.2% | -157356.99 | 0 | 0 | 0 | 245000 |  | 245000 | 0 | NOT A PROJECT. NO TARGET COMPLETION THEREFORE. | 0 | 0 | Not a project | Single year licenses paid from revenue so need to consider how to change funding | 245000 | 245000 | 245000 | 980000
C3058 | CRM Lagan Replacement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 48264 | 0 | 48264 | 24132 | 0 | 0% | 48264 | 0 | 0 | 0 | 48264 |  | 48264 | 0 | This project has been renamed the ASM Replacement as Lagan was replaced by ASM. requirements have been gathered. Need to sense check them with ODS before going to market. | 0 | 0 | Sense check business requirements with ODS |  | 0 | 0 | 0 | 48264
C3060 | End-Point Devices (Desktops/Laptops) | Business Improvement | 0 | GF | rolling programme | rolling programme GF | 0 |  |  | 150000 | 204366.83 | 0 | 354366.83 | 177183.42 | 42567.81 | 12.01% | 311799.02 | 0 | 0 | 0 | 354366.83 |  | 354366.83 | 0 | 0 | 0 | 0 | Closed |  | 150000 | 150000 | 150000 | 804366.83
C3066 | Telephony Device Refresh | Business Improvement | 0 | GF | rolling programme | rolling programme GF | 0 |  |  | 60000 | -26309.57 | 0 | 33690.43 | 16845.22 | 30411.79 | 90.27% | 3278.64 | 0 | 0 | 0 | 33690.43 |  | 33690.43 | 0 | Not a project. Funding for device replacements as needed. | 0 | 0 | Not a project. Funding for device replacements as needed. NO TARGET COMPLETION THEREFORE. |  | 60000 | 60000 | 60000 | 213690.43
C3068 | Windows 2008 Server Replacement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | -3495 | #DIV/0! | 3495 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
C3072 | Forms Engine Replacement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 10800 | n/a | -10800 | 0 | 0 | 0 | 0 |  | 0 | 0 | Project is closed. Residual capital of £642. | 0 | No risks noted. | Implementing waste forms. |  | 0 | 0 | 0 | 0
C3081 | Capitalised ICT Projects | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 163200 | 452445.87 | 0 | 615645.87 | 307822.94 | 487626.21 | 79.21% | 128019.66 | 0 | 0 | 0 | 615645.87 |  | 615645.87 | 0 | NOT AN ICT PROJECT - FUNDING SET ASIDE FOR ADDITIONAL FUTURE PROJECTS IF REQUIRED. NO TARGET COMPLETION THEREFORE. | 0 | 0 | 0 |  | 163200 |  |  | 778845.87
C3082 | Website Redesign | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 3106.25 | 0 | 3106.25 | 1553.13 | 627 | 20.19% | 2479.25 | 0 | 0 | 0 | 3106.25 |  | 3106.25 | 0 | Website has gone live (phase 1) | 0 | 0 | Complete migration of pages (pahse 2) |  | 0 | 0 | 0 | 3106.25
C3085 | ICT - I-trent replacement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 75000 | -75000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Current plan is to extend contract to 31.03.28. Current contract is to 31.03.25. We are not in a good position to specify our exact needs. We need to improve use of current system and be clear about business needs before starting a procurement exercise. We are currently investing to improve processes and application. | Project delayed | 0 | 0 |  | 20000 | 55000 | 0 | 75000
C3086 | ICT - QL Exploitation Programme | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 256000 | -29344.12 | 4000 | 230655.88 | 115327.94 | 212746.5 | 92.24% | 17909.38 | 154844.12 | 154844.12 | 0 | 385500 |  | 385500 | 0 | Versaa Forms - PEEP Form (Pilot) : Technical issues have been resolved. The OCC and ODS Versaa environments have been rebuilt and all environments have been successfully upgraded. Versaa Forms - Tenancy Services : The off-the-shelf Tenancy Services product issues have also been resolved. The handover of the product was completed at the end of September. Predictive Arrears (MARS) : The MARS solution has been successfully implemented. Notice has been issued to Mobysoft, who are currently progressing the off-boarding process. OCC has completed it's decommissioning tasks. Sub-Account & Former Arrears Solution : Requirements have been agreed, development completed and test cycle 1 completed. Housing Needs System Solution - Work has now started on the ITT Supplier Contract. Contractor Portal : Requirements have been gathered and process maps developed | Although the forecast reflects an overspend, it is mitigated by the N7072 being under budget. Collectively the 2 budgets will reflect an underspend due to slippage on some elements of the programme. | - Budget forecast predicts this project will be over budget by the end of the financial year. This is mitigated by N7072 being under budget (all expenditure has been captured in the primary capital budget. - The adoption of the new solution is being facilitated through engagement with Business Areas, with a prioritized focus on key areas. - Resource and capacity management are crucial for handling the volume of work activities, which are continuously being prioritised. - Unforseen delays are introduced due to timescales involved in investigating and resolving technically complex issues involving multiple 3rd Party Suppliers. | Versaa Forms - PEEP Form (Pilot) - Complete UAT (Oct 24) - Pre Go-Live Activities (Oct 24) - Soft Launch (Pilot Users) (Nov 24) Versaa Forms - Tenancy Services - Product and process familiarisation (Oct 24) - Testing Phase (Nov 24) |  | 78000 | 78000 | 78000 | 464655.88
C3087 | ICT - replacing Netcall contact centre telephony and resource management system | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 29468.62 | 0 | 29468.62 | 14734.31 | 34283.92 | 116.3% | -4815.3 | 0 | 0 | 0 | 29468.62 |  | 29468.62 | 0 | Project concludes in November 2024 | 0 | Demand on ICT resources is high and whilst the business requirements have been identified, we are struggling with a higher-than-usual BAU demand, to provide resource and focus to moving this project forwards. | Publish RFQ - August 2024 |  | 0 | 0 | 0 | 29468.62
C3088 | ICT - replacing Uniform (building control and planning) | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 100000 |  | 0 | 100000 | 50000 | 0 | 0% | 100000 | 0 | 0 | 0 | 100000 |  | 100000 | 0 | This project is about replacing the Uniform information management system and related EDMS (unsupported) for a modern cloud-based solution. Current contract runs out end of March 2026 and coincides with decomissioning of on-prem hosting of current solution. Project is currently at a pre-procurement stage (phase 2). The Invitation to Tender is being written with a specification identified by consultants from feedback from the Council's Uniform users. This is being reviewed with input from the project board (ICT, Procurement, Finance, Legal, Data Governance, Planning and Regulatory Services). The related contract has also been drafted by legal, which is also being reviewed by the Project Board. When the ITT and contract have been completed, the procurement process can commence (Target November 24) Project resources (time, budget, team) for the full migration in phase 3 are uncertain at present and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the level of resourcing required for the next stage. | Full costs of the solution, including resourcing and costs of migration to be identified in the procurement phase of the project and will depend on which supplier is chosen. See forecast spend for annual contract costs anticipated - current annual costs of contract and hosting to be redirected when new contract is planned to start (March 26). | The ITT and contract are being written to best protect the council's interests and ensure that suppliers will be able to deliver the required solution for the project. Project resources (time, budget, team) for the full solution and migration in phase 3 are uncertain and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the full level of resourcing required for the next stage. | Target November 24: ITT and contract to be sent out |  | 0 | 0 | 0 | 100000
C3090 | ICT - Extension of existing Alemba case managmenet system | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 4004 | 0 | 4004 | 2002 | 0 | 0% | 4004 | 0 | 0 | 0 | 4004 |  | 4004 | 0 | Alemba system has been set up for use by the People Team. | 0 | 0 | 0 |  | 0 | 0 | 0 | 4004
C3092 | ICT - Replacement of IKEN - L&G case management system | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 67500 | 0 | 67500 | 33750 | 35125 | 52.04% | 32375 | 0 | 0 | 0 | 67500 |  | 67500 | 0 | Implementation programme has been delayed because access for testers to MS365 is not yet available. Iken have suspended implementation pending confirmation from OCC of a workable solution. | 0 | Delay causing risk of delay to Council's transition to cloud-based Outlook application | Agreement of contract with Hable - 31 Jan 2024 |  | 0 | 0 | 0 | 67500
C3093 | ICT - Replacement of ArcGIS geospatial mapping system | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 25000 | 0 | 25000 | 12500 | 0 | 0% | 25000 | 0 | 0 | 0 | 25000 |  | 25000 | 0 | Completed | 0 | 0 | 0 |  | 0 | 0 | 0 | 25000
C3094 | ICT - Information @ Work major upgrade | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 3000 | 15000 | 0 | 18000 | 9000 | 0 | 0% | 18000 | 0 | 0 | 0 | 18000 |  | 18000 | 0 | PO Signed in September. Go live in October. | 0 | 0 | 0 |  | 0 | 0 | 0 | 18000
C3095 | ICT - Redesign of Council Website | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 51658 | 0 | 51658 | 25829 | 627 | 1.214% | 51031 | 0 | 0 | 0 | 51658 |  | 51658 | 0 | Completed in May 2023 | 0 | 0 | 0 |  | 0 | 0 | 0 | 51658
C3097 | ICT - Refresh of content and taxonomy of the Council Website | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 25000 | 21150 | 0 | 46150 | 23075 | 1500 | 3.25% | 44650 | 0 | 0 | 0 | 46150 |  | 46150 | 0 | A project plan for 'phase two' is in place, which will see us systematically improve each area of the council's website. A pilot project has been carried out with the council tax team, which is due to complete in the next couple of weeks. We will then move on to improve the recycling and jobs sections of the website. Meanwhile, a website working group has been established to bring together content, digital, customer and citizen teams to work on the website improvements. Terms of reference have been drawn up and will be brought to OCB in October for approval. | 0 | Risk that the website improvements end when the current additional resource is removed in November 2024, without having completed the process of optimising all high usage areas of the website for customer self-service. Mitigation: permanent increase in resourcing of web content management. October update: ICT is extending the resource until March 2025. A budget bid has been submitted to create a permanent resource from 2025/26. | Draft project plan for phase two of website |  | 0 | 0 | 0 | 46150
C3099 | Third-party consultancy for Azure Active Directory and M365 migration from SCC, security setup and configuration. | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 135000 |  | 0 | 135000 | 67500 | 0 | 0% | 135000 | 0 | 0 | 0 | 135000 |  | 135000 | 0 | Awaiting contract signature of main SCC contract. | 0 | 0 | 0 |  | 0 | 0 | 0 | 135000
C3100 | Itrent system improvement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 30000 |  | 0 | 30000 | 15000 | 0 | 0% | 30000 | 0 | 0 | 0 | 30000 |  | 30000 | 0 | Work has started to implement data retention module, reporting module is being evaluated and recruitment process improvements taking place. | 0 | Team capacity to deliver improvements - setting clear priorities and need to limit new work | data retention module implemented |  | 0 | 0 | 0 | 30000
C3101 | I@W renewal or replacement | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 300000 |  | 0 | 300000 | 150000 | 0 | 0% | 300000 | 0 | 0 | 0 | 300000 |  | 300000 | 0 | Requirements gathering underway as of 1st September | 0 | 0 | 0 |  | 0 | 0 | 0 | 300000
C3102 | Cyber security monitoring and response service | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 115000 |  | 0 | 115000 | 57500 | 0 | 0% | 115000 | 0 | 0 | 0 | 115000 |  | 115000 | 0 | Monitoring and response services in place | 0 | 0 | 0 |  | 0 | 0 | 0 | 115000
C3103 | Upgrade/replace Kirona DRS (this is an ODS system) | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 75000 |  | 0 | 75000 | 37500 | 0 | 0% | 75000 | 0 | 0 | 0 | 75000 |  | 75000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 75000
C3104 | Windows security server upgrades | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 75000 |  | 0 | 75000 | 37500 | 0 | 0% | 75000 | 0 | 0 | 0 | 75000 |  | 75000 | 0 | Project due to complete on time. | 0 | 0 | 0 |  | 0 | 0 | 0 | 75000
C3105 | Migration of Mod.gov | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 90000 |  | 0 | 90000 | 45000 | 0 | 0% | 90000 | 0 | 0 | 0 | 90000 |  | 90000 | 0 | No change since last update | 0 | 0 | 0 |  | 0 | 0 | 0 | 90000
C3106 | Migration of SCC to cloud hosted alternatives | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 107000 |  | 0 | 107000 | 53500 | 0 | 0% | 107000 | 0 | 0 | 0 | 107000 |  | 107000 | 0 | Contract negotiations underway. | 0 | 0 | Contract Signature delayed to September 2024 |  | 0 | 0 | 0 | 107000
C3107 | Replacement of Uniform IDOX (additional funding) | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 25000 |  | 0 | 25000 | 12500 | 0 | 0% | 25000 | 0 | 0 | 0 | 25000 |  | 25000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 25000
C3108 | Online forms development (2x resources to accelerate) | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 160000 |  | 0 | 160000 | 80000 | 0 | 0% | 160000 | 0 | 0 | 0 | 160000 |  | 160000 | 0 | 0 | 0 | 0 | 0 |  | 160000 | 0 | 0 | 320000
C6000 | ICT - feasibility | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 180000 | 0 | 180000 | 90000 | 0 | 0% | 180000 | 0 | 0 | 0 | 180000 |  | 180000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 180000
| Business Improvement Projects Total | [8 empty] | 2114200 | 1121309.88 | -71000 | 3164509.88 | 1582254.96 | 1255177.22 | 39.66% | 1909332.66 | 154844.12 | 154844.12 | 0 | 3319354 |  | 3319354 | [6 empty] | 876200 | 588000 | 533000 | 5161709.88
Financial Services Projects
C3080 | Telephony Contract Replacement | Financial Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 22599.5 | n/a | -22599.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | Additional requirements being processed via Procurement in March. In the region of £25k additional spend. PO raised in early May. Go live at end of October. | 0 | ODS to join the pilot test in June. | Go Live / End of August, early September |  | 0 | 0 | 0 | 0
C3084 | Agresso Update | Financial Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 6167 | n/a | -6167 | 0 | 0 | 0 | 0 |  | 0 | 0 | Project Team and Board have now been formed and project has started | 0 | Working with Project team to complete Cycle 3 of UAT | Cycle 3 UAT- 24th December |  | 0 | 0 | 0 | 0
C3096 | ICT - Open Revenue Cloud Migration | Financial Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 50000 |  | 0 | 50000 | 25000 | 0 | 0% | 50000 | 0 | 0 | 0 | 50000 |  | 50000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 50000
C3098 | ICT - Agresso upgrade and migration to Cloud | Financial Services | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 | 193219.6 | 0 | 193219.6 | 96609.8 | 0 | 0% | 193219.6 | 0 | 0 | 0 | 193219.6 |  | 193219.6 | 0 | Project has gone live | 0 | 0 | Post implementation intensive care |  | 0 | 0 | 0 | 193219.6
B0144 | Salary Costs across the Council to be capitalised | Financial Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 380000 | 1057591 | 323000 | 1760591 | 880295.5 | 0 | 0% | 1760591 | 0 | 0 | 0 | 1760591 |  | 1760591 | 0 | 0 | 0 | 0 | 0 |  | 663000 | 663040 | 663040 | 3749671
M5023 | OxWED Loans | Financial Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 3750000 |  | -2725000 | 1025000 | 512500 | 0 | 0% | 1025000 | -1025000 | -1025000 | 0 | 0 | Suggest this all gets pushed back to next year | 0 | 0 | £325k loan payment approved in 2023/24 due to extended programme. Potential further release will be in future years subject to final business case. | 0 | 0 | 0 |  | 0 | 0 | 0 | 1025000
| Financial Services Projects Total | [8 empty] | 4180000 | 1250810.6 | -2402000 | 3028810.6 | 1514405.3 | 28766.5 | 0.9498% | 3000044.1 | -1025000 | -1025000 | 0 | 2003810.6 |  | 2003810.6 | [5 empty] | 0 | 663000 | 663040 | 663040 | 5017890.6
Law & Governance
C3083 | FOI System | Law & Governance | 0 | GF | Project - ICT | Project - ICT GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 7875 | n/a | -7875 | 0 | 0 | 0 | 0 |  | 0 | 0 | All key users have now been trained. System went live on 26/06/2023. Webform and disclosure log have gone live. The decision has been made to publish FOIs which are deemed to have some public interest. | 0 | 0 | Contract to begin 31/03/2023 | will need to be a budget bid as not enough funds to cover ongoing costs! | 0 | 0 | 0 | 0
L1000 | Audio & Visual Equipment | Law & Governance | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 |  |  | 0 | 12782 | 0 | 12782 | 6391 | 0 | 0% | 12782 | -12782 | -12782 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 12782
| Law & Governance Projects Total | [8 empty] | 0 | 12782 | 0 | 12782 | 6391 | 7875 | 0% | 4907 | -12782 | -12782 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 12782
| Corporate Resources Directorate Total | [8 empty] | 6294200 | 2384902.48 | -2473000 | 6206102.48 | 3103051.26 | 1291818.72 | 20.82% | 4914283.76 | -882937.88 | -882937.88 | 0 | 5323164.6 |  | 5323164.6 | [5 empty] | 0 | 1539200 | 1251040 | 1196040 | 10192382.48
Chief Executive
| Environmental Sustainability Projects | [16 empty] | 0
B0127 | ZEZ Phase 1 Feasibility | Environmental Sustainability | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 141000 | 0 | 141000 | 70500 | 0 | 0% | 141000 | 0 | 0 | 0 | 141000 |  | 141000 | 0 | Phase 1 complete and terms agreed on revenue share for phase 1 - legal agreement progressing. Phase 2 - Project on hold, but likely to un-pause soon, awaiting decision on City Council role in project. | 0 | Risk around ZEZ pilot being enforced while there is significant delay to the ZEZ and stakeholders in Pilot area likely to be vocal about the impacts on the | Complete legal agreement with County re. Phase 1 revenue share |  | 0 | 0 | 0 | 141000
E3557 | Oxford and Abingdon Flood Alleviation Scheme | Environmental Sustainability | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 0 | 0 | 0 | 2.44 | n/a | -2.44 | 0 | 0 | 0 | 0 |  | 0 | 0 | Have now entered into the Option Agreement. legal are providing advice and draft notices on the land which requires advertising prior to disposal (open space) Terms agreed for the disposal of the fields adjacent to Redbridge Hollow - Fisher German have confirmed values look reasonable. EA have provided HOTs but they confirm Council will need to provide VP - this doesn't reflect the agreement so have asked EA to confirm. | 0 | Risk 1. Project Risks- Gaining Planning permission and CPO Inquiry Mitigation for these is being managed by the EA (OCC support on Project Board and Sponsoring Group) Risk 2. OCC Risk- overlap of OFAS with OCC plans for Seacourt and Redbridge P&R's Mitigation - Open dialogue & sharing of information and timetables for OFAS and OCC plans for Seacourt & Redbridge P&R. Risk 3. Originally, OCC agreed a contribution of kind of up to £1m, including internal staff resource as a key stakeholder/contribution to the project 4-5 years ago. The length of time the project has taken and changes in staff, alongside post covid impacts on Legal and Property resource meant there was insufficient internal staff resources to do this work. This has been resolved with a dedicated external Property Services contractor, Richard Waple, as Lead Officer and an external Legal Services contractor, Ian Goldsmith. Professional Fees have started to be reimbursed by the EA. To date, all of OCC's Professional Fees have been reimbursed to the end of November 2022. OCC remains a committed partner to the scheme. | Agreement of Option Agreement September 2023. Planning permission late 2023. CPO to be confirmed December 2024. - complete |  | 250000 | 0 | 0 | 250000
E3558 | Go Ultra Low Oxford - On Street | Environmental Sustainability | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 494706.03 | 0 | 494706.03 | 247353.01 | 0 | 0% | 494706.03 | 0 | 0 | 0 | 494706.03 |  | 494706.03 | 0 | >September 2024 - Agreement still not issued by County. Escalated to 151 Officer and Head of Corp Servs. This needs to be in place before the LEVI tender is published - planned end October 24 August 2024 - draft of agreement due from County but no date given for this yet. LEVI work taking priority for all Oxon Councils as tender due for this by September 2024. June 2024 - meetings taking place in June with County for the reimbursement method of the allocated funding as well as the transfer of the GULO assets to County control. May 2024 - no new progress, project remains paused. - City are seeking reimbursement of investment through revenue share, which has been agreed in principle >Project Paused- County is seeking full integration of GULO P2 into LEVI, with all new onstreet contracts entered into by County highways. Permission to enter into a back-to-back agreement now received from Funder (OZEV) .City are seeking reimbursement of investment through revenue share, which has been agreed in principle. Ongoing delays on LEVI timeline, GULO timelines likely to shift significantly backwards, to early 2025. | 0 | OGP2ZR005 - Agreement with County not signed by end October for the GULO funds transfer. Mitigation - Escalate and if still no progress consider using the funds outside LEVI for alternative A/C charging in car parks. OGP2ZR004 - Substantial delay to GULO Infrastructure delivery in Oxford. County officers have stated intention to withdraw permission for city to take GULO forward on the highway, and demand full integration of GULO into LEVI under County contract ownership. Onstreet delivery timelines for LEVI are currently set to early 2025. Mitigation: Officers are seeking urgent confirmation on proposed GULO timelines, with the aim of securing a 2024 delivery. | Agreement on City to County transition - updated deadline Jul 2024 |  | 0 | 0 | 0 | 494706.03
E3560 | Go Ultra Low Oxford - Taxis | Environmental Sustainability | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 | 38326.56 | 0 | 38326.56 | 19163.28 | 19015 | 49.61% | 19311.56 | 0 | 0 | 0 | 38326.56 |  | 38326.56 | 0 | update 1-10-24. Legal have now assigned someone to look at the leases. Supplier engagement for sign off will commence once we have the completed leases. Project delivery complete but close out still in progress.. Some minor transition items outstanding (as build-drawings, full lease signatures). | N/A | September 24 - Lease signing due before the end of October. Once completed, this project can be closed down as all deliverables will be completed. Leases for some sites off street sites to be finalised and signed by both parties. Nilesh and Sue progressing with legal during September Final invoice paid to Blink Charging (formerly EB Charging). As built drawings sent over for all sites. O&M documentation sent over- to be reviewed. | Transition & handover sign-off |  | 0 | 0 | 0 | 38326.56
E3565 | Decarbonisation Fund - OCC element | Environmental Sustainability | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 105142.35 | 0 | 105142.35 | 52571.18 | 0 | 0% | 105142.35 | 0 | 0 | 0 | 105142.35 |  | 105142.35 | 0 | 1. Hinksey's completion date 27 with Practical Completion. issued 10 February 2023 by F&G due to outsanding documents. 2. Two trees completed still monitoring the health of the trees. 3. Salix Audit oustanding. To start after final account. 4. Pool Cover works outstanding completed on the 18 of January 2023. 5. Indipendant inspection for the pool cover complete. 6. Barton L Centre PHX to be send for testing by specilialst on the meturlugy of the heat exchanger. | 0 | Claim from WD on Barton Leisure Centre PHX damage due to what they allege as high levels of chlorine. Mitigation - OCC has sent the PHX | 1. Commmissioning complete 2. Pool Cover Cover works completion and indipendant inspection of safety issues. May include security. Complete 3. Report from Inspector complete and submitted to OCC from reveiw. |  | 0 | 0 | 0 | 105142.35
E3568 | Leisure Centre LED Lighting Feasibility | Environmental Sustainability | 0 | GF | Project - Development | Project - Development GF | 0 |  |  | 0 | 6430 | 0 | 6430 | 3215 | 3840 | 59.72% | 2590 | -2590 | -2590 | 0 | 3840 |  | 3840 | 0 | The survey drawing work completed. We are waiting on access to the Technician at Serco to populate the type and lux of light fittings surveyed. | Managed a better deal - £2590 less than budgeted | The lighting data sheets have been sufficiently completed to fufill the requirements but not as full as initially hoped. The site support was not sufficient to do this due to ongoing commitments. It was not possible to extend the project further | All visits completed except with Technician at Serco |  | 0 | 0 | 0 | 6430
E3570 | Biodiversity Net Gain (Feasibility) | Environmental Sustainability | 0 | GF | Project - Other | Project - Other GF | 0 |  |  | 0 |  | 100000 | 100000 | 53846.16 | 21264 | 21.26% | 78736 | -47000 | -47000 | 0 | 53000 |  | 53000 | 0 | TVERC ecological surveys completed. Legal review of Conservation Covenant v s.106. | 0 | 1) If the project were to show that none of the candidate sites are cost effective/viable for BNG use. Mitigated by careful selection of sites using economical, maintenance, property and planning background knowledge. 2) If the project is unable to gather reliable information on Council pipeline BNG costs it may not be possible to make a financial case for the use of council-owned land for BNG offsetting. Mitigate by working with the development teams to gather useable information. 3) If the ecological survey season is missed in 2024, then that element of works would be delayed to summer 2025. This risk has been mitigated by the successful appointment of an ecological consultant and the survey works are now completed (as of August 2024). | Completion of habitat assessments, enhancement modelling & report. Final reports due from ecological consultant 15/11/24. |  | 0 | 0 | 0 | 100000
| Environmental Sustainability Projects Total | [8 empty] | 0 | 785604.94 | 100000 | 885604.94 | 446648.63 | 44121.44 | 4.982% | 841483.5 | -49590 | -49590 | 0 | 836014.94 |  | 836014.94 | [6 empty] | 250000 | 0 | 0 | 211572.35
| Chief Executive Total | [8 empty] | 0 | 785604.94 | 100000 | 885604.94 | 446648.63 | 44121.44 | 4.982% | 841483.5 | -49590 | -49590 | 0 | 836014.94 |  | 836014.94 | [5 empty] | 0 | 250000 | 0 | 0 | 211572.35
| General Fund Total | [8 empty] | 77182456.26 | 38992700.86 | -3129369.63 | 113104951.49 | 56432665.76 | 27429206.66 | 24.25% | 85675744.83 | -42280421.05 | -42280421.05 | 0 | 70824530.44 |  | 70824530.44 | [5 empty] | 0 | 92744620.83 | 72104738.88 | 60468362.16 | 337498640.77
Housing Revenue Account Capital Programme
HRA - Property Services Schemes
N6384 | Tower Blocks | HRA | 0 | HRA | Project - Development | Project - Development HRA | 0 |  |  | 1000000 | 560386.98 | -1300000 | 260386.98 | 130193.49 | 6630.02 | 2.546% | 253756.96 | 0 | 0 | 0 | 260386.98 |  | 260386.98 | 0 | Negotiations in progress - slip 1.3M to 25/26 | 0 | 0 | 0 |  | 1300000 | 0 | 0 | 1560386.98
N6385 | Adaptations for disabled | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 800000 | 244000.05 | -244000 | 800000.05 | 389360.02 | 812853.47 | 101.6% | -12853.42 | 0 | 0 | 0 | 800000.05 |  | 800000.05 | 0 | ODS budget demand led - 168K remaining at end of Feb | 0 | 0 | 0 |  | 750000 | 650000 | 650000 | 2850000.05
N6386 | Structural | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 2000000 | 138550.28 | 49204 | 2187754.28 | 713877.14 | 42418.58 | 1.939% | 2145335.7 | 0 | 0 | 0 | 2187754.28 |  | 2187754.28 | 0 | "Concrete works Work completed to 1 scheme, ongoing for 3 others and still to start at last. General subsidence and cracking. On demand budget - Update on 29/08 POs raised to the Sum of £137,112.50 for Phase 1, 10 properites completed to RIBA stage 2. Cabnet report in process for 1 Million spend" | 0 | 0 | 0 |  | 2000000 | 2000000 | 2000000 | 8187754.28
N6387 | Controlled Entry | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 100000 | 416969.14 | -198978 | 317991.14 | 148995.57 | 3351.79 | 1.054% | 314639.35 | -217991.14 | -217991.14 | 0 | 100000 |  | 100000 | 0 | Survey being completed in this year. First reports due back (priority blocks) week ending 11th Oct | 0 | 0 | 0 |  | 333000 | 75000 | 75000 | 800991.14
N6388 | Major Voids | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 1000000 | 277537.56 | -277538 | 999999.56 | 499999.78 | 732142.12 | 73.21% | 267857.44 | 0.44 | 0.44 | 0 | 1000000 |  | 1000000 | 0 | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. This is also a delegated budget to ODS. Demand led. Orders for a number of major voids have recently been placed. | 0 | 0 | 0 |  | 1000000 | 1000000 | 1000000 | 3999999.56
N6389 | Damp-proof works (K&B) | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 440558.02 | -396844 | 43714.02 | 21857.01 | 0 | 0% | 43714.02 | 0 | 0 | 0 | 43714.02 |  | 43714.02 | 0 | "A rolling programme where repairs are done as they come in. There has been an increase in the number of damp issues during autumn and winter months. Work needs to be done to identify persistent issues to make installations planned rather than re-active" | 0 | 0 | 0 |  | 0 | 0 | 0 | 43714.02
N6390 | Kitchens & Bathrooms | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 250000 | 250000 | 0 | 250000 |  | 250000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
N7057 | Kitchens | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 230352.8 | -230353 | -0.2 | -0.1 | 0 | 0% | -0.2 | 0.2 | 0.2 | 0 | 0 |  | 0 | 0 | "These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. 13 Complete June 23 expected 104" | 0 | 0 | 0 |  | 0 | 0 | 0 | -0.2
N7049 | Compulsory purchase of property | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 797.81 | n/a | -797.81 | 0 | 0 | 0 | 0 |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 0 | 0 | 0
N7058 | Bathrooms | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 173732.92 | -173733 | -0.08 | -0.04 | 0 | 0% | -0.08 | 0.08 | 0.08 | 0 | 0 |  | 0 | 0 | Capital programme budget | 0 | 0 | 0 |  | 0 | 0 | 0 | -0.08
N6391 | Heating | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 107710 | 107710 | 0 | 107710 |  | 107710 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
N7059 | Boilers Only | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 500000 | 556694.87 | 268903 | 1325597.87 | 662798.94 | 854559.95 | 64.47% | 471037.92 | -1325597.87 | -1325597.87 | 0 | 0 |  | 0 | 0 | This is a demand led budget and is part of the ongoing Decent homes and compliance work required by OCC as a landlord. 75 complete YTD 130 Predicted year end. Projected £1,500,000k spend does not include CO which needs to be added in. No slippage reported yet | 0 | 0 | 0 |  | 500000 | 500000 | 500000 | 2825597.87
N7060 | Heating Systems | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 500000 | 154823.06 | -107710 | 547113.06 | 273556.53 | 21564.04 | 3.941% | 525549.02 | 107710 | 107710 | 0 | 654823.06 |  | 654823.06 | 0 | This is delegated budget to ODS and is part of the Decent Homes works | 0 | 0 | 0 |  | 500000 | 500000 | 500000 | 2047113.06
N6392 | Roofing | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 190750.66 | 0 | 190750.66 | 95375.33 | 0 | 0% | 190750.66 | 0 | 0 | 0 | 190750.66 |  | 190750.66 | 0 | orders placed and 26 properties and properties still to be validated for remaining budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 190750.66
N6395 | Electrics | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 2000000 | 11276.87 | -63353 | 1947923.87 | 1052361.93 | 300478.46 | 15.43% | 1647445.41 | 0 | 0 | 0 | 1947923.87 |  | 1947923.87 | 0 | Delegated budget to ODS and is on target to deliver. We have agreed to fund 165 properties | 0 | 0 | 0 |  | 2000000 | 700000 | 500000 | 5147923.87
N6434 | Doors and Windows | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | -372914.51 | 372915 | 0.49 | 0.25 | 0 | 0% | 0.49 | 0 | 0 | 0 | 0.49 |  | 0.49 | 0 | Nationwide are still completing properties from last years programme and have had access issues. A programme of works for this year has been identified and submitted for Nationwide to price. | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.49
N7020 | Extensions & Major Adaptions | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 1000000 | 101947.93 | 825439 | 1927386.93 | 763693.47 | 189314.57 | 9.822% | 1738072.36 | -1452120.98 | -1452120.98 | 0 | 475265.95 |  | 475265.95 | 0 | Commented as per each single project | 0 | 0 | 0 |  | 700000 | 700000 | 700000 | 4027386.93
N7026 | Communal Areas | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 728491.33 | -728491 | 0.33 | 0.17 | 6533.1 | 1979727% | -6532.77 | 728491 | 728491 | 0 | 728491.33 |  | 728491.33 | 0 | Capital programme budget | Demand led budget | 0 | 0 |  | 0 | 0 | 0 | 0.33
N7033 | Energy Efficiency Initiatives | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 7450000 | 2984617.65 | -3560193 | 6874424.65 | 3526612.32 | 120865.01 | 1.758% | 6753559.64 | -292914.44 | -292914.44 | 0 | 6581510.21 |  | 6581510.21 | 0 | Broken down into specific projects | 0 | 0 | 0 |  | 12750000 | 2325000 | 2325000 | 24274424.65
N7044 | Lift Replacement Programme | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 100000 | 108463.97 | -105032 | 103431.97 | 1715.98 | 34345.14 | 33.21% | 69086.83 | 46568.03 | 46568.03 | 0 | 150000 |  | 150000 | 0 | No further significant lifts replacments for this current year but planning 25/26 - Large number of stair lift replacments expected | 0 | Awaiting procurement of Lift consultant to develop upodated replacement program | 0 |  | 550000 | 150000 | 150000 | 953431.97
N7048 | Fire doors | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 1500000 | 80228.4 | 1990949 | 3571177.4 | 1590588.7 | 42766.86 | 1.198% | 3528410.54 | -571177.4 | -571177.4 | 0 | 3000000 |  | 3000000 | 0 | Awaiting ODS to submit costs for five blocks - Then need quotes for QS to review | Contract approval and resource. | Re-focusing on high risk buildings as per BSR requirements, project being priced | 0 | Procurement of blocks done in stages and delaying work | 1500000 | 1500000 | 1500000 | 8071177.4
N7067 | Renewal Of Fire Alarm Panels | HRA | 0 | HRA | Project - Compliance | Project - Compliance HRA | 0 |  |  | 60000 | 147021 | 0 | 207021 | 103510.5 | 0 | 0% | 207021 | 0 | 0 | 0 | 207021 |  | 207021 | 0 | Alarm and detection system at Headley House completed (June 2023), next site to be identified and procured. | 0 | Completion of this project affects Fire safety, thus important to maintain progress | 0 |  | 60000 | 75000 | 60000 | 402021
N7052 | HRA Stock Condition Survey | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 400000 | -4673.1 | 333246 | 728572.9 | 297606.45 | 109947.18 | 15.09% | 618625.72 | 0 | 0 | 0 | 728572.9 |  | 728572.9 | 0 | 4,118/7,888 (52.2%) of HRA dwellings surveyed | 0 | 0 | 0 |  | 200000 | 0 | 0 | 928572.9
N7032 | Great Estates Programme | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 308156.97 | -308157 | -0.03 | -0.01 | 0 | 0% | -0.03 | 6180.03 | 6180.03 | 0 | 6180 |  | 6180 | 0 | Move 400K to FRA programme and put 500k reserve for bin store project | 0 | 0 | 0 |  | 0 | 0 | 0 | -0.03
N7071 | Fencing | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 850855.63 | -600000 | 250855.63 | 125427.82 | 0 | 0% | 250855.63 | 0 | 0 | 0 | 250855.63 |  | 250855.63 | 0 | Demand led/ lower demand than previous years. | Lower demand than expected | 0 | 0 |  | 0 | 0 | 0 | 250855.63
N7072 | QL Improvements | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 | 490000 | -245000 | 245000 | 122500 | 0 | 0% | 245000 | 0 | 0 | 0 | 245000 |  | 245000 | 0 | Please see QL Exploitation | 0 | 0 | 0 |  | 0 | 0 | 0 | 245000
N7073 | Southfield Park Leases | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 0 | 1500000 | 0 | 1500000 | 750000 | 0 | 0% | 1500000 | 0 | 0 | 0 | 1500000 |  | 1500000 | 0 | Alex Miller (Corporate Assets) has made contact with Lincoln College regarding the proposal. Lincoln College have, in turn, contacted their solicitor and valuer to get initial input but are awaiting their response before having a conversation with us. | 0 | The key risk is that the valuation of the lease extension under the statutory process is higher than the budget envelope of £1.5m. The other risk is that Lincoln College may wish to decline informal discussions however there is a statutory process that we can fall back on as mitigation if necessary. The appointment of JLL (Real Estate & Property Consultancy) has to advise on valuation and negotiation has also provided assurance that best value will be obtained. | JLL providing valuation report - TBC |  | 0 | 0 | 0 | 1500000
N7074 | Oxford North Develpment | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 13538505 | 1156859.27 | -202 | 14695162.27 | 7347581.13 | 1017088.88 | 6.921% | 13678073.39 | -9231031.27 | -9231031.27 | 0 | 5464131 |  | 5464131 | 0 | Cabinet approvals secured in March 2023. Moving to contract signing SoS achieved (June 23) | 0 | The scheme has planning and the obligations of this will be picked up by Hill through the contract. However, appropriate due diligence will be done. s73 submitted in May 24 for 2 extra flats in the podium area of blocks 6&7. Scheme is in contract and on-site although query over the housing trajectory which does not align with the development agreement. Issue has been noted with careful monitoring on site. Reprofiling took place in April to move all units from 24/25 to 25/26 Technical risks will be the responsibility of Hill through the contract. Due diligence on going. Energy strategy negotiations taking place throughout first half of 2024 | Monitor site progress and staged payments |  | 8114472 | 1525090 | 1283000 | 25617724.27
N7075 | LAHF Acquisitions | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 0 | -129548.66 | 442253 | 312704.34 | 156352.17 | -4426.18 | -1.415% | 317130.52 | 0 | 0 | 0 | 312704.34 |  | 312704.34 | 0 | 7 of 7 properties purchased, void completed and let. | 0 | Budget- overall budget allows for property purchase, associated costs & void works although final void costs confirmed once work is completed. Market price fluctuations - all properties either purchased or in conveyancing Sales fall through - accepted risk, OCC are cash buyers but cannot avoid chain sales Underspend - there may be budget left over following property purchases | Purchase of remaining 2 properties by 30/11/23 - complete |  | 0 | 0 | 0 | 312704.34
N7076 | Major Voids – Kitchens and Bathrooms | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 |  | 499999.96 | 499999.96 | 249999.98 | 74609.77 | 14.92% | 425390.19 | 0 | 0 | 0 | 499999.96 |  | 499999.96 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 499999.96
N7077 | Climate Change | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Update will be shared as of next month | 0 | 0 | 0 |  | 0 | 4000000 | 4000000 | 8000000
N7078 | LAHF 2 Acquisitions | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 | 690678.52 | 0 | 690678.52 | 345339.26 | 1020101.3 | 147.7% | -329422.78 | 0 | 0 | 0 | 690678.52 |  | 690678.52 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 690678.52
N7080 | Retained Right to Buy Receipts (Acquisitions) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 | 820540 | 2179460 | 3000000 | 1500000 | 1036973.3 | 34.57% | 1963026.7 | 1060450 | 1060450 | 0 | 4060450 |  | 4060450 | 0 | Delivery Total 3/18 homes met PC and LET, 4/17 legally completed with a further 15 to be delivered by March 28th 2025. Next legal completion dates for remaining 13/17: 1) 31/10/2024 2) 31/10/2024 3) 31/10/2024 4) 31/10/2024 5) 12/11/2024 6) 19/11/2024 7) 26/11/2024 8) 04/12/2024 9) 04/12/024 10) 14/01/2025 11) 14/01/2025 12 14/01/2025 13) 14/01/2025 Void works estimated to complete by early March 2025 to enable letting and prgramme completion by end of March 2025. Projected Spend = £4,060,450 Actual Spend (To Date) = £1,243,906.27 ODS Projected Spend = £196,743.18 ODS Actual Spend (To Date) = £18,743.18 Forecast Remaining Budget = -£1,060,450 (This will move into approved RRTBR budget for 2025/26 £3,0000) | 0 | 0 | 0 |  | 3000000 | 3000000 | 15000000 | 24000000
N7081 | Retained Right to Buy Receipts (Additional) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 1000000 |  | 0 | 1000000 | 500000 | 0 | 0% | 1000000 | 0 | 0 | 0 | 1000000 |  | 1000000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1000000
N7084 | Alice Smith (Heating) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 200000 |  | 0 | 200000 | 100000 | 0 | 0% | 200000 | 0 | 0 | 0 | 200000 |  | 200000 | 0 | System replaced 2019. sustainability team opportunity for improvements to currnetl systme controls | 0 | 0 | 0 |  | 0 | 0 | 0 | 200000
N7085 | Renewal of Solar and Energy infrastructure | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 15000 |  | 0 | 15000 | 7500 | 0 | 0% | 15000 | -10000 | -10000 | 0 | 5000 |  | 5000 | 0 | Feasibility work to establish current conditions | 0 | 0 | 0 |  | 15000 | 0 | 15000 | 45000
N7086 | Extensions (5/6 Beds) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 300000 |  | -300000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 600000 | 0 | 0 | 600000
N7087 | SHWP Urgent Works | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 500000 |  | 0 | 500000 | 250000 | 0 | 0% | 500000 | 0 | 0 | 0 | 500000 |  | 500000 | 0 | Projects being reviewed unlikely need in current year but may form part of D&M need in 25/26 - Slip 500K into 25/26 | 0 | 0 | 0 |  | 0 | 0 | 0 | 500000
N7088 | Tower Blocks Additional Works | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 1500000 |  | -1500000 | 0 | 0 | 0 | 0% | 0 | 260000 | 260000 | 0 | 260000 |  | 260000 | 0 | Multiple remedial works being planned by Fortem - Framework with procurement for Specialist services (PM/CM/CoW, etc) | 0 | 0 | 0 |  | 2500000 | 1000000 | 0 | 3500000
N7089 | Housing for Older People - white goods and communal areas | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 50000 |  | 0 | 50000 | 25000 | 0 | 0% | 50000 | 0 | 0 | 0 | 50000 |  | 50000 | 0 | Housing Management call demand led - no requests to date this year | 0 | 0 | 0 |  | 0 | 0 | 0 | 50000
N7090 | Digital Noticeboards for towerblocks | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 50000 |  | 0 | 50000 | 25000 | 0 | 0% | 50000 | 0 | 0 | 0 | 50000 |  | 50000 | 0 | Orders now being raised on QL for ODS (electrical works) and ITSL group (TV and anti-tamper case). ICT arranging data ports and broadband for all 5 blocks. | 0 | 0 | 0 |  | 0 | 0 | 0 | 50000
N7091 | Capital R&M Works Investment | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 2500000 |  | 0 | 2500000 | 1250000 | 0 | 0% | 2500000 | 0 | 0 | 0 | 2500000 |  | 2500000 | 0 | Slip full budget into 25/26 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2500000
N7092 | Communal Capital investment works to Council Homes | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 4500000 |  | 1120539 | 5620539 | 2810269.5 | 67177.48 | 1.195% | 5553361.52 | 0 | 0 | 0 | 5620539 |  | 5620539 | 0 | 0 | 0 | 0 | 0 |  | 4500000 | 4500000 | 4500000 | 19120539
N7093 | ExternalCapital investment works to Council Homes | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 4500000 |  | -371960 | 4128040 | 2064020 | 1015000.41 | 24.59% | 3113039.59 | 0 | 0 | 0 | 4128040 |  | 4128040 | 0 | 0 | 0 | 0 | 0 |  | 4500000 | 4000000 | 0 | 12628040
N7094 | Internal Capital investment works to Council Homes | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 3500000 |  | 377767 | 3877767 | 1938883.5 | 1639268.99 | 42.27% | 2238498.01 | 0 | 0 | 0 | 3877767 |  | 3877767 | 0 | 0 | 0 | 0 | 0 |  | 3500000 | 3500000 | 7500000 | 18377767
N7095 | Tower Blocks - Fire Alarm System Replacement | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Specification updated, PM allocated, soft market testing for prices will determine route of governance. | 0 | Staff changes have introduced slight delays, working to re-confirm design. | 0 |  | 800000 | 0 | 0 | 800000
N7096 | Stock Decency Improvement Works (Legislative) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 5000000 | 10000000 | 10000000 | 25000000
N7097 | Leiden Road (c. 12 affordable homes) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 50000 | 50000 | 0 | 50000 |  | 50000 | 0 | Seeking to mobilise this project | 0 | No deliverable scheme yet demonstrated with a programme | Scheme devt appraisal review to drive expected costs down |  | 898000 | 2705000 | 457000 | 4060000
N7098 | Underhill Circus (c. 11 affordable homes) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 50000 | 50000 | 0 | 50000 |  | 50000 | 0 | Seeking to mobilise this project | 0 | No deliverable scheme yet demonstrated with a programme | Scheme devt appraisal review to drive expected costs down |  | 698000 | 2193000 | 509000 | 3400000
N7099 | Additional Units (RRTBR) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
N7100 | Additonal Programme (RRTBRs) | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
N7042 | Barton Regeneration | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 |  |  | 0 | 598360.3 | 0 | 598360.3 | 299180.15 | 0 | 0% | 598360.3 | 0 | 0 | 0 | 598360.3 |  | 598360.3 | 0 | Agreed works completed | 0 | 0 | 0 |  | 0 | 0 | 0 | 598360.3
N7070 | Major Refurbishment Masons Road | HRA | 0 | HRA | Project - Development | Project - Development HRA | 0 |  |  | 0 | 586178.52 | 0 | 586178.52 | 293089.26 | -2818.23 | -0.4808% | 588996.75 | 0 | 0 | 0 | 586178.52 |  | 586178.52 | 0 | Orders have been placed with ODS and 3 properties remaining to be done with 4 underway | 0 | 0 | 0 |  | 0 | 0 | 0 | 586178.52
HRA - Housing Supply Schemes
N7047 | Social Rented Housing Acquisitions | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 0 | -78775.84 | 78776 | 0.16 | 0.08 | 97920.27 | 61200169% | -97920.11 | 0 | 0 | 0 | 0.16 |  | 0.16 | 0 | ODS void works from 20/21 to end 22/23 capitalised/ charged into this budget - so all reconciled to April 23. The £23k retention from the Abbey Homes acquisition (45 homes) is also due to be paid in 23/24 from this budget, after defects work is completed and certified. (Jan 24 update - Awaiting confirmation of completed defects work before payment.) 2023/24 programme: Target: 9 acquisitions. Year End: 11 homes. | Budget to be reset by finance and closed at end of 2023/24 year. No longer to be used. | RETIRING THIS COST CENTRE FROM END 2023/24 | Settlement of all final ODS works costs for 23/24 acquisitions asap - but will go past year end. |  | 0 | 0 | 0 | 0.16
N7051 | Acquisition of Additional Units | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 3000000 |  | -3000000 | 0 | -1500000 | 0 | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Acquisition of 9 units (off-plan) - Only £25k retention left in budget as required. | 0 | Construction issues mitigated by the employment of a Council clerk of works to regularly inspections and reports on issues and progress to the PM in the construction phase. | Payment of final retention sum (£25k) in Qtr 2 22/23 - To be actioned (Oct 22) |  | 0 | 0 | 0 | 0
N7050 | East Oxford development | HRA | 0 | HRA | Project - Development | Project - Development HRA | 0 |  |  | 6793288 | 844370.5 | 0 | 7637658.5 | 422185.25 | 1445103.57 | 18.92% | 6192554.93 | -1300305.5 | -1300305.5 | 0 | 6337353 |  | 6337353 | 0 | Planning consent (Ctte Jan 21). Conditions being met. Working with Arcadis to develop a delivery programme. Sept 21 - Agt on route to market (separate to community centre refurb) - Housing Devt now being mobilised. Jan 22 - Build contract tenders issued. Plan to award in Feb 22. ODS undertaking demolition of all sites May to July 22, then site handover to residential. SOS Q3 2022/23, completion Q4 2023/24 (tbc - after tenders assessed). Jun 23 - Mobilising for SoS Tender results were poor - going back out to market again. Cost risk, although consultants believe that the expected budget envelope should still be sufficient (Mar 22). Impact on SoS expected to delay from Jan 23 to Mar 23. Professional Services costs paid by General Fund and will be apportioned over into HRA at year end by Finance. Oct 22 - Tenders from open tender assessed (inc financial due diligence) and contract award decision made (Dec 22). To now reset budget and programme following this. End Dec update - Contract now with Legal - expect to sign/ seal in Feb 23. Jan 23 - Homes England have confirmed that grant application is now approved. Oct 23 - Demolitions Complete. Having to move to 2nd tenderer - contract discussions underway and targeting contract signing in Nov 23 for SoS in early 2024. Contract with Life Build now signed and mobilising for SoS in March 24. Technical SoS achieved in Mar 24. Collins Street - Build progressing well - Above foundation (Jul 24). Princes Street - LifeBuild unable to access site for main works due to ODS on EOCC site adjacent - meetings to try to resolve. Lifebuild may have to delay build start to Sept 24 - likely cost implications being assessed. DSA to sign (OCHL to OCC) Mar 23-Jul 24 | 0 | Princes St works on site delayed due to access, levels issues, so will incur additional costs and time. 23wk delay as currently expecting to SOS 23 Sept'24. Significant issues re construction management plan and delay to Princes Street SOS ODS on target for completion of CC timber frame by 20th Sept, which will enable Lifebuild to SOS at Princes Street on 23rd. Difficult tight sites to develop, co-ordination required with community centre main contractor on Princes Street. Solutions to the levels and drainage issues in shared footpath between both developments have been reached, but need to be be approved. Finance: Delays to SOS at Princes and potential impact of level issue will incur loss & expense claim, therefore increased build costs and programme delay. Planning: No issues identified re conditions, except condition 4 at Collins Street. Looking like Collins will be finished before the Community Centre (CC), so Collins completed units may need to remain vacant until CC reaches PC - this has been taken up with Planners. Both projects now scheduled for completion Sept 25. | Princes Street site - Resolving issues for Life Build to start and assessing additional cost liability (HRA & GF) as a result. Report expected to escalate to Devt Board/ CMT following EOCC Project Board meeting on 19th July 24. |  | 264385 | 0 | 0 | 6601738
N7054 | Properties Purchased From OCHL | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 83684822 | 18962944.39 | -78736024 | 23911742.39 | 11955871.19 | 7943686.37 | 33.22% | 15968056.02 | 1777000.61 | 1777000.61 | 0 | 25688743 |  | 25688743 | 0 | The June 24 appraisals show a significant increase in OX Place costs, but most of these increases have not been passed onto the HRA. The HRA appraisals show c. £14m more possible spend. Most significant is a c. £16m increase in costs (and numbers of units) at R/B, but Sandy Lane Rec has seen a £2m decrease. For the purpose of this monitoring however, the current (Feb 24) MTFP budget is used, so the spend forecasts at Redbridge have been decreased proportionately in each year to reduce the overall budget forecasts by £14m. There are high levels of spend certainty with 3 (of 10) schemes, comprising c.17% of the overall budget, that are in delivery or expected to be soon, and where delivery risks are low. These schemes comprise of 100% of the spend forecast in 24/25 and 75% of the forecast in 25/26, so slippage in these two years is expected to be minimal. 3 of the schemes are targeting planning committee approval in the next 4 months. 3 already have consent and one is awaiting the s.106 only. The remaining 3 schemes are the largest schemes in the programme - all forecast in the later years of the programme with £222m spend (62% of this budget). There has been considerable slippage in programme dates with many now revised. The larger schemes are now forecast to run to 2031/32. | Slippage of some schemes in programme into later years | Developing more rigour to the business plan re capital spends | Collaboration Agreement and associated documents, esp Development Agreements and Delivery Strategy (per scheme); plus Payment Schedules to be developed and agreed. | Slippage figure to tie in with Dave W email 27 July 2023 | 42139726 | 46264902 | 39787056 | 152103426.39
N7061 | Northfield Hostel | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 9524123 | 1760836.48 | 10714804 | 21999763.48 | 10999881.74 | 1239045.19 | 5.632% | 20760718.29 | -16300873.48 | -16300873.48 | 0 | 5698890 |  | 5698890 | 0 | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission to be made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Now confirmed as in Year 4 OGD. Requires land sale; build contract signing; & planning consent by end March 22. Due to go to Plg Ctte on 9th March. Other critical path work (land and build contract) to follow in March. 15 Mar 22 - Approved at Plg Ctte. s.106 being finalised now. End March - s.106 agreed and land sale being progressed. June 22 - Re-tender using OCHL Framework to secure best price. Land now acquired from County. Sept 22 - tenders back and being assessed. Oct 22 - PSCA expected late Nov 22 Nov 22 - Budget to be reviewed in Dec 22/Jan 23 once more price certainty is secured. Currently forecasting a TSC (exc interest) of £19.65m (if a £16m build cost can be achieved). This would give a budget pressure of £3,250k, but the scheme would still meet HRA financial parameters and the higher Abovo costs have been tested in the draft HRA BP preparation (Nov 22). New budget to go to March 23 Cabinet and then Council. PCSA due to be issued March 23. Homes England bid by end March 23 also. June 23 - PCSA sealed and work underway. Demolition Aug 23. Main contract SoS Dec 23. HE Grant issue - looking to purchase adjacent County site to over come this. Reports into HSB and Devt Board (June 23) and cabinet report for Aug 23. Sale by County Cabinet agreed end Sept 23. Oxford City full Council agreement budget in Oct 23. Solicitors instructed and sale expected to complete late Oct/ Nov 23. Jan 24 - decision not to award build contract and to re-tender. Above reversed and Equans to be appointed. Feb- July 24 Price and contract negotiations with Equans. Demolition works underway. | 0 | Pre-Planning application and consultation used to mitigate planning risk. Tender for build contract re-run through new OCHL framework (Lot2). Risk to delivery completing by Homes England deadline/ Need to secure funding from the HE AHP programme. Legal risk: Contract issue over liability levels. Complexity about process to include other site. | Build tender result, then revised cost schedule and programme to be confirmed. To establish whether we have sufficient price certainty (and limited risk) re costings, as to whether to submit a Homes England AHP funding bid in early Jan 23. Early March 23 - PCSA to be signed Jun 23 - Sealed! Now PCSA work (to complete in Feb 24). Demolition contract to be let - to SoS for demolition phase May 24 - targeting demolition completion July 24. DSA to sign (OCHL to OCC) Jul 24 HE grant claim. |  | 10153801 | 701464 | 0 | 32855028.48
N7062 | Lanham Way | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 3185122 | -670795.62 | 4197527 | 6711853.38 | 3355926.69 | 1952169.75 | 29.09% | 4759683.63 | -2575841.38 | -2575841.38 | 0 | 4136012 |  | 4136012 | 0 | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Planning issues being resolved with architects and across teams. Mar 22 - Significant redesign required to reduce number of units. Sept 22 - Planning consent secured (at committee) for 10 homes. Conditions and s.106 pending Nov 22 - Build Contract tender out (on framework) - Due back Jan 23 Jan 23 - Tender back - being assessed. (Feb 23) s106 drafted and ready to sign Jun 23 - Land purchased. Build contract to be signed imminently. Final legals to build contract. Possible slight delay to SoS due to ecology (translocation window) Build contract signed and SoS achieved in Dec 23. DSA to sign (OCHL to OCC) Mar 24 - Jul 24 | 0 | Build issues - Site Meetings and EA engaged Contractor has undertaken detailed technical risk analysis with none identified to date - contingency in budget After acquisition scheme will be private highway for OCC to maintain - adequate provisions in place Remove or minimise any provisional sums re finance - robust programme tracking | Tracking progress through site meetings and programme tracking |  | 1103548 | 0 | 0 | 7815401.38
N7079 | SHAP Acquisitions | HRA | 0 | HRA | Project - Other | Project - Other HRA | 0 |  |  | 0 |  | 209999.81 | 209999.81 | 104999.9 | 237881.41 | 113.3% | -27881.6 | 0 | 0 | 0 | 209999.81 |  | 209999.81 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 209999.81
N7068 | Juniper | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 0 | 385229 | 0 | 385229 | 192614.5 | 0 | 0% | 385229 | 0 | 0 | 0 | 385229 |  | 385229 | 0 | Now Juniper only - 2 units (with ODS). Tucker is being progressed by OCHL. Thomson was dropped in favour of a land deal to support the Railway Lane devt with OCHL/ Cantay. Still pending a proposal and cost from ODS (likely for one unit only now due to ground constraints). PROPOSE TO CLOSE THIS PROJECT AS UNVIABLE (and reallocate funding to support the Northfield scheme budget pressure through the 23/24 final budget process) | 0 | Requires planning submission and works programme. | Awaiting financial appraisal and programme. Issue concerning ground conditions pending (re statutory services running through the site). |  | 0 | 0 | 0 | 385229
N7066 | Next Steps Accommodation Programme | HRA | 0 | HRA | Other Capital Spend | Other Capital Spend HRA | 0 |  |  | 0 | 581746.12 | 0 | 581746.12 | 290873.06 | 0 | 0% | 581746.12 | 0 | 0 | 0 | 581746.12 |  | 581746.12 | 0 | Buying 5 one bed flats for rough sleepers in a Housing First model. Completed on 3 in March 21 (Q4) and remaining two will be in April 21 (Q1 21/22). 5 NSAP units completed. A new bid to buy 10 further units in 21/22 made in April 2021, and award of funding confirmed (June 21) - team mobilising and contacting agents. Sept 21 - 1st unit completed. Oct 21 - Additional grant ask from MHCLG (to replace £550k that was to be funded from OGD) now under consideration/ sign-off. Jan 22 - 4 RSAP units completed. Last 6 properties in conveyancing and expect to complete by end March 2022. 15th Mar 22 - Initial 8 completions (cost c. £1,540k plus min £50k refurb costs). 9 units now completed (9th one was today - £175k). 10th (last) home expected to complete on 28/3/22 (£135k). SDLT exempt. End Mar 22 - All 10 RSAP properties now purchased and void works are underway with ODS. First 2 tranches of grant per dwelling claimed. Now awaiting PC. July 2022 - All works now complete - Homes are lettable and are let. | 0 | None | Expect void works spend to be capitalised into this project - Value TBC. Project can then close. Expect a £500k underspend |  | 0 | 0 | 0 | 581746.12
N7040 | Blackbird Leys Regeneration (HRA) | HRA | 0 | HRA | Project - Development | Project - Development HRA | 0 |  |  | 1504000 | -446659.48 | 1295977 | 2353317.52 | 644844.36 | 1343998.75 | 57.11% | 1009318.77 | 0 | 0 | 0 | 2353317.52 |  | 2353317.52 | 0 | PHASE 1 UPDATE: - S278 still sits with County for approval/agreement. Street lighting design pending, but County has agreed to sign without technical approval for lighting. - Badger Issue: new badger sett built, now ecologist to check that badgers have gone to the new sett. This will de-risk the Knights Rd site development significantly. - Delays in going through safety gateway new Building Act for tall buildings. Issues in trying to get a case manager assigned, over 12 weeks delayed and ongoing. HIF: -Last HIF claim in August LEGAL: - Budget for internal capital charges set - JO, BM and KSM discussed legal works for Phase 2 should be c. £50k, with £30k uplift in case of CPO -JO to lead on procurement for legal consultants using framework PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. COMMS: - Comms ongoing, with Peabody consultants leading - Community Centre events and comms ongoing and led by TbD | 0 | - S278: this is a risk to delay in programme and S278 works SoS. Signing of S278 is said to be imminent. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2, strategy to be agreed. Delay risk as Ph 2 may need a new planning application. - Comms & Engagement: Still a risk. Need to send out comms especially to update on site works and conditions. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024. | Signing of S278: 'imminent' (?) End of August |  | 172000 | 172000 | 172000 | 2869317.52
[23 empty] | 0 |  | #N/A
| Housing Revenue Account Total | [8 empty] | 158254860 | 35379791.98 | -67489809.23 | 126144842.75 | 56899442.97 | 23401349.13 | 18.55% | 102743493.62 | -28833743.07 | -28833743.07 | 0 | 97311099.68 |  | 97311099.68 | [6 empty] | 112101932 | 93736456 | 93183056 | 422305594.27
| Grand Total | [8 empty] | 235437316.26 | 74372492.84 | -70619178.86 | 239249794.24 | 113332108.73 | 50830555.79 | 21.25% | 188419238.45 | -71114164.12 | -71114164.12 | 0 | 168135630.12 |  | 168135630.12 | [6 empty] | 204846552.83 | 165841194.88 | 153651418.16 | 759804235.04
24456762.26
[15 empty] | % Latest Budget |  | % Original Budget |  |  |  | 137669669.1 |  |  | 0 | #DIV/0!
[13 empty] | General Fund Spend v Budget |  | 24.25% |  | 35.54% | [6 empty] | 0
[13 empty] | HRA Spend v Budget |  | 18.55% |  | 14.79% |  |  |  | -30465961.02 |  |  | 0
[13 empty] | Total Spend v Budget |  | 21.25% |  | 21.59%
| Original budget £235,623,351 | [15 empty] | total bud | total fot | variance
| Control checks | [11 empty] | 238651433.94 |  | 50830555.79 |  | #REF! | #REF! | #REF!
Note on B258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Track change from Q2
Note on W26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: YTD Actuals manually adjusted
Note on W80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added in agreed Feasibility payback of £13,990 from B0115 and £170k from B0112.
Note on W86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £170k budget removed is to be paid back to Feasibility Budget (B0074)
Note on W91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At DB discussed £100k underspend forecast - slipped into 24/25?
Note on W126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PM (R Nixon) confirmed £57k forecast spend for 23/24. £96k to be slipped into 24/25
Note on AE99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sonal - see my comment on Planner Data for this (24/25 budget only needs to be £120k (£100k + slippage). PM confirmed

## FinanceAppB (Qtr Movement) (hidden)
Capital Budget and Spend as at 30th September 2023
[21 empty] | 2023/24 Forecast Variance from Q1 Position |  |  |  | Smartsheet Forecast | [6 empty] | Future Year Budgets (per 21/22 MTFP Budget)
Cost Centre | Capital Scheme | Service Area | Progress Update Provider | GF / HRA | Project Classification | Project Classification | Gateway Stage | Programme Status | Risk Status | 2023/24 Original Budget | Carry Forwards | Adjustments Since Original Budget | Forecast @ Q1 | Forecast @ Q1 | Forecast @ Q3 | Latest 2023/24 Budget | Profiled Budget | Spend to 31/09/2023 | % Budget Spent | Budget Remaining | Forecast Variance | Variance due to Slippage | Over / Under Spend | 2023/24 Outturn Forecast | 2023/24 Smartsheet Forecast | Smarsheet Comment Updated | PM Overview (From Smartsheets) | PM Variance Comment (From Smartsheets) | Key Risks and Mitigations (From Smartsheets) | Next Key Milestone (From Smartsheets) | Management Accountant Comments | 2024-25 Approved Budget | 2025-26 Approved Budget | 2026-27 Approved Budget | Total Budget 2023-24 to 2026-27
[10 empty] | £ | £ | £ |  |  |  | £ | £ | £ |  | £ | £ | £ | £ | £ | [7 empty] | £ | £ | £ | £
General Fund Capital Programme
Communities and People Directorate
| Community Services Projects | [10 empty] | 0 | [8 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
A4820 | Upgrade Existing Tennis Courts | Community Services | Paul Backman | GF | Project - Other | Project - Other GF | Rolling Programme | On target | Low | 0 | 0 | 108190.83 | 35000 | 35000 |  | 108190.83 | 54095.41 | 2568.62 | 2.374% | 105622.21 | -35000 | -35000 | 0 | 0 | 0 | 0 | That works have completed at Hinksey Park and Botley Park, this has included resurfacing and repainting of the courts. We have worked closely with the cabinet member and local ward cllrs to promote this. At Bury Knowle Park resurfacing works have also been completed to now include tennis and multi use games area at the site. Planning permission has been granted and works are now complete for the refurbishment of the pavilion and associated outdoor spaces. We are currently reviewing potential for works at Cutteslowe Park and Alexandra Park to resurface the existing tennis courts utilising S106 contributions from the Wychwood School developments | £33,000 CIL contributions from Headington Action are not currently showing on current budget. Once this has been allocated the project should show a small overspend due to unforseen costs in delivery of Hinksey Park and Botley Park resurfacing. | Charging scheme at Hinskey & Botley received some criticism locally and from members. We have worked closely with members to mitigate this and have addressed their concerns. Tennis courts at Alexandra Park have significantly deteriorated and are in need of resurfacing - proposal for works using S106 contributions. Cutteslowe Park is in need of significant improvements as court conditions are poor - proposals for utilising S106 contributions working in partnership with Courtside to review options for delivery | Work starts June 2023 | 0 | 0 | 0 | 0 | 108190.83
A4847 | Rose Hill Community Centre - Parking Management | Community Services | Natalie Oakley | GF | Project - Other | Project - Other GF | Feasibility | Off Target | Medium | 0 | 0 | 10000 | 10000 | 10000 |  | 10000 | 5000 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 |  | 10000 | 10000 | 0 | We are currently working with colleagues within the car parking team to develop a clear scope for this. It is likely that the £10k capital allocation will slip to 24/25. | 0 | Timescales and budget if part of a wider project | Traffic order obtained. | 0 | 0 | 0 | 0 | 10000
B0075 | Museum of Oxford Development | Community Services | 0 | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10191 |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 10191 | 10191 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 0
B0083 | East Oxford Community Centre | Community Services | Douglas Kerrigan | GF | Project - Development | Project - Development GF | Delivery | Awaiting new Schedule | Medium | 4223967 | -2115 | -721851.73 | 3670039 | 3000000 |  | 3500000.27 | 1750000.13 | 1379582.93 | 39.42% | 2120417.34 | 245000 | 245000 | 0 | 3245000 | 3245000 | 0 | Commence on site 6th March 2024 | Presently early design changes led to delays which have a mitigation strategy to meet original Practical Completion dates | Access for Community Centre and Residential. Ongoing Coordination meetings in place to decide a mutually agreeable strategy. These are now planned on a weekly basis at site level and monthly for combined project teams. The logistics of completing shared sewers and paved areas between community centre and residential means completion of that area will not be until October 6th. EOCC is targeted as end of June 2025 but occupation will not be [possible till paving work is concluded to allow means of escape from the community centre. | Complete roof works 11th November 2024 | 0 | 2124657 | 0 | 0 | 5624657.27
B0150 | Hinksey Pool Liner Replacement | Corporate Property | Luca Minetola | GF | Project - Other | Project - Other GF | Completed | On target | Low | 0 | 0 | 18385 | 1000000 | 131615 |  | 18385 | 9192.5 | 0 | 0% | 18385 | -113230 |  | -113230 | 18385 | 18385 | 0 | 0 | 0 | 0 | Variation instructed to original order, now to include pool side repair | 0 | 0 | 0 | 0 | 18385
B0096 | Bullingdon Community Centre | Community Services | Douglas Kerrigan | GF | Project - Development | Project - Development GF | Completed | On target | Low | 0 | -412655 | 475790.94 | 951923 | 51795 |  | 63135.94 | 31567.97 | #VALUE! | #VALUE! | #VALUE! | 13717.94 | 0 | 13717.94 | 65512.94 | 65512.94 | 0 | Practical Completion achieved | 0 | Cost report submitted for increase over budget to date Final account can now be submitted | Practical Completion achieved December 2022 together with Commission and handover | 0 | 0 | 0 | 0 | 63135.94
| Community Services Projects Total | [8 empty] | 4223967 | -414770 | -109484.96 | 5666962 | 3238601 |  | 3699712.04 | 1849856.01 | #VALUE! | #VALUE! | #VALUE! | 110487.94 | 210000 | -99512.06 | 3349088.94 | 3349088.94 | [6 empty] | 2124657 | 0 | 0 | 5824369.04
| Housing Services Projects | [26 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
B0102 | Replace or refurbish Lifts | Housing Services | Luca Minetola | GF | Rolling Programme | Rolling Programme GF | Design & Specification | Awaiting new Schedule | High | 140000 | 43294 | -73810 | 119484 | 119484 |  | 109484 | 54742 | 3733.62 | 3.41% | 105750.38 | -10000 |  | -10000 | 109484 | 109484 | 0 | On-going maintenance and inspections with repairs | 0 | 0 | Requires budget approvals, Section 20, cabinet report,contract extension procurement | 0 | 0 | 150000 | 0 | 259484
B0108 | Floyds Row Refurbishment | Housing Services | 0 | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 48283 | 99217 | -99217 | 99217 | 0 |  | 48283 | 24141.5 | 12239.41 | 25.35% | 36043.59 | 12239 | 12239 | 0 | 12239 | 12239 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 48283
C3057 | Housing System Replacement | Housing Services | Alison Cornacchia | GF | Project - ICT | Project - ICT GF | Delivery | Completed | High | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | -9112.5 | #DIV/0! | 9112.5 | 0 | 0 | 0 | 0 | 0 | 0 | Tenant Portal - The tenant portal was successfully made live on 11th September. A soft launch of the portal was made to Tenant Ambassadors. | 0 | - Resources and capacity are critical for managing the volume of work activities, which are continuously being prioritized. - Ensure the supplier's resources and capacity are booked and available when needed. Request and book resources as early as possible. | Tenant Portal - Extend the launch to new tenants during sign-up | 0 | 0 | 0 | 0 | 0
M5024 | National Homelessness Property Fund | Housing Services | TBC - Paul Wilding | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 0 | 0 | 633961.96 | 0 | 633962 |  | 633961.96 | 316980.98 | 157663.93 | 24.87% | 476298.03 | -0.04 | 0 | 0 | 633961.96 | 633961.96 | 0 | Further NHPF payment of £1,780k due in March 23, followed by a final payment of £976k in June 2023 | 0 | WRONG PM RECORDED - SHOULD BE RICHARD WOOD OR PAUL WILDING | 0 | 0 | 0 | 0 | 0 | 633961.96
M5038 | Roken House | Housing Services | Dave Scholes | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | Off Target | Low | 0 | -500 | 96056.35 | 1659500 | 653286 |  | 95556.35 | 47778.18 | 3019.9 | 3.16% | 92536.45 | -495786 | -495786 | 0 | 157500 | 157500 | 0 | Jan 22 - Architects appointed. April 22 - Property purchased (£1.4m). Works Spec prepared. Asbestos Survey commissioned. Jun 22 - Planning App submitted. M&E consultants appointed. Full spec being prepared. Slight project delays due to additional surveys and reports having to be commissioned - M&E survey (inc Fire Strategy); Flood Risk Asst (for planning). Oct 22 - Planning approval secured. Building Control application in. Tender pack for works prepared and with ODS for pricing. Project currently has c. 5 weeks delay to programme. Nov 22 - Pricing to spec (with options) undertaken. Assessment (ahead of contract award) on 21st Nov 22. Dec 22 - M&E pricing still awaited. Jan 23 - ODS pricing confirmed and verified by indep QS. Decision made to increase the budget envelope by £200k and to award the contract - Now back on (enhanced) budget. May 23 - Contract Award (to ODS) June 23 - SoS Dec 23 (Budget) Cabinet recommendation to move project from GF to HRA - Approved at full Council in Jan 24. Mar 24 - Handover of 8 homes / PC (9th home - old office -pending final Building Control sign-off) Aug 24 - BC sign-off completed (Flat 9). PC achieved. All homes let. | Final Account settlement underway | Some additional items and Architects Instructions have been necessitated but negotiations underway to minimise costs (max expected overspend c.£63k) | Finance to move entire project into HRA (2023/24 year end closedown) including RRTBR inclusion in the DLUHC 'pooling return' re spend. | 0 | 0 | 0 | 0 | 95556.35
M5039 | UK Shared Prosperity Fund Invesment Plan | Housing Services | Matthew Broadbent | GF | Other Capital Spend | Other Capital Spend GF | Rolling Programme | On target | Low | 65000 | 0 | 306817 |  | 0 |  | 371817 | 185908.5 | #VALUE! | #VALUE! | #VALUE! | 371817 | 371817 | 0 | 743634 | 371817 | 0 | Following agreement at development board (17th July) UKSPF capital expenditure for this year will focus on the Market Street scheme design and delivery - up to £170k has been allocated for 23/24. The remaining £20k capital has been made available to progress St Michael's Street, ahead of delivery in 24/25. The focus for revenue expenditure this year is to cover the officer time in delivering the Match My Project trial to support community organisations and social value delivery. There is a small allocation (£35k) planned to deliver training and business development support through a third party. Advice from legal suggests this may be possible through direct grant award to a partnership of local providers - OSEP, CAG, Cooperative Futures. This will need Director sign off. Members have expressed concerns that the Wayfinding upgrade had been removed from the plan and we are exploring options to reintroduce in the programme's final year 24/25, using some of the funding allocated to skills. | 0 | 0 | See Market Street project for latest dates |  | 0 | 0 | 0 | 371817
| Housing Services Projects Total | [8 empty] | 253283 | 142011 | 863808.31 | 1878201 | 1406732 |  | 1259102.31 | 629551.16 | #VALUE! | #VALUE! | #VALUE! | -121730.04 | -111730 | -10000 | 1656818.96 | 1285001.96 | [6 empty] | 0 | 150000 | 0 | 1409102.31
| Regulatory & Community Safety Projects | [10 empty] | 0 | [8 empty] | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
A4845 | CCTV Suite Upgrade | Regulatory & Community Safety | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 10583 | -10583 | 10583 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
A4852 | Bodycams for Community Safety Team | Regulatory & Community Safety | Daniel Courtenay | GF | Project - Other | Project - Other GF | Delivery | Completed | Low | 0 | 60450 | -37450 | 60450 | 60450 |  | 23000 | 11500 | 22977.5 | 99.9% | 22.5 | -37450 | -37450 |  | 23000 | 23000 | 0 | Project completed. Final spend approx £27K (under budged of £60K) Closure Report to be completed by Richard Adams | 0 | - | NFA | 0 | 0 | 0 | 0 | 23000
E3577 | Oxford and Abingdon Flood Alleviation Scheme | Regulatory & Community Safety | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 60450 | 0 |  | 0 | 0 | 7875 | n/a | -7875 | 0 | 0 |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
E3511 | Essential Repairs Grant | Regulatory & Community Safety | Becky Walker | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 15000 | 5015 | 17092.97 | 20015 | 45000 |  | 37107.97 | 18553.99 | 487626.21 | 1314% | -450518.24 | -15000 | -15000 | 0 | 30000 | 30000 | 0 | Increased ERG budget has been approved in Council Budget to help waiting list of clients. | 0 | Not enough contractors for work type | 0 | 0 | 15000 | 15000 | 15000 | 82107.97
E3521 | Disabled Facilities Grants | Regulatory & Community Safety | Becky Walker | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 1200000 | -21452 | 375200.55 | 1595926 | 1421433 |  | 1553748.55 | 776874.27 | -1857 | -0.1195% | 1555605.55 | 132315.55 | 132315.55 | 0 | 1553748.55 | 1553748.55 | 0 | BAU in HIA with referrals being progressed. | 0 | County Council Occupational Therapists are funded so there is no backlog and the service is actively promoting the availability of funding. Liaising with hospitals to enable discharge. | 0 | 0 | 1200000 | 1200000 | 1200000 | 5153748.55
E3561 | Additional DFG Funding CLOSED | Regulatory & Community Safety | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 4968.48 |  | 0 |  | 4968.48 |  | 45.25 | 0.9107% | 4923.23 | -4968.48 | -4968.48 | 0 | 0 | 0 | #N/A | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4968.48
| Regulatory & Community Safety Projects Total | [8 empty] | 1215000 | 54596 | 349229 | 1747424 | 1526883 |  | 1618825 | 806928.26 | #VALUE! | #VALUE! | #VALUE! | 74897.07 | 74897.07 | 0 | 1606748.55 | 1606748.55 | [6 empty] | 1215000 | 1215000 | 1215000 | 5263825
| Oxford Direct Services Projects | [10 empty] | 0 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
R0005 | MT Vehicles/Plant Replacement Programme. | Oxford Direct Services | Owain Pearce | GF | Rolling Programme | Rolling Programme GF | Rolling Programme | Off Target | Low | 5774279 | 1558482 | -3832760.81 | 6138848 | 6440585 |  | 3500000.19 | 1750000.1 | 648122.35 | 18.52% | 2851877.84 | -2940585 | -2940585 | 0 | 3500000 | 3500000 | 0 | We have made good progress in decarbonizing our fleet, however we are at the difficult stages of trying convert vehicles that have no suitable charging solution or are expensive to convert to electric. As such every vehicle needs assessing on a case by case basis. Where possible we are looking to extend the life of assets to keep the cost of fleet down for both ODS and OCC. This is to make most efficiency of the fleet whilst keep expenditure down versus trying to improve our green footprint of the fleet. The impact this will have on the Capital programme is a potential carry over every year as we will no longer be replacing on the typical fixed 7 year term. This also means a more detailed management of the running costs across the whole fleet on a continuous basis. Lead times on vehicles has come down so if vehicle running costs increase on a particular asset then we will look to replace asap. As well as a cost benefit to ODS and the Council by extending asset life, there may be scope to decarbonize more of the fleet as newer longer range assets come into the market, EV prices decrease due to the new ZEV mandate, and alternative solutions to infrastructure charging become available. Note that we are still following our previous replacement lifecycle for depreciation (usually 7 years) and the extend life will continue with no depreciation for any additional years beyond its normal life. As such I have reviewed the capital program and estimated a reduction in overall spend for this year. | Extending life of assets and rolling over budgets | The project is still subject to planning of replacement Electric vehicles across all services based on Net Zero targets. It is a very complex replacement due to many vehicles being taken home or calculating power requirements at depots and economic considerations. We would like to support OCC’s aim full decarbonization of the fleet by 2030 but this can only be achieved with new infrastructure and some high cost electric vehicles. If we buy diesel now then we are tied in for another 7 years. As such we are deferring replacement of some assets until decisions have been made on future replacement methods and strategy. The biggest risk is vehicles going wrong and the lead times being too long to replace the asset quickly. Therefore we are continuing to keep a fleet of pool vehicles to offset VOR and any unforeseen vehicle issues. The planning of the programme will no longer be as straightforward as it used to be and will require closer monitoring of asset running costs. That being said we have changed the budget to a fixed amount per year and plan to only replace fixed life assets and any assets that are starting to cost more for maintenance or reaching 10+ years. | There are still a number of electric vehicles outstanding on order, due to one supplier's production delays and space/charging constraints at depots. | This feels like something that we need to have a meeting with Owain to discuss ahead of Q2 as it has the potential to be a high value swing I think | 7301909 | 3256938 | 3000000 | 17058847.19
T2273 | Car Parks Resurfacing | Oxford Direct Services | Oliver Hearn | GF | Rolling Programme | Rolling Programme GF | Rolling Programme | On target | Low | 200000 | 406433 | -456433.46 | 742297 | 300000 |  | 149999.54 | 74999.77 | 42346.62 | 28.23% | 107652.92 | -11916.23 | -11916.23 | 0 | 288083.77 | 288083.77 | 0 | Work underway at Ferry Pool Work planned for Gloucester Green and Walton Well Road CCTV upgrade required at Gloucester Green | 0 | No notable current risks to programme. | Ferry pool completion during July | Emma Gubbins has received a planned programme but was waiting on a response to a couple of issues | 138692 | 0 | 0 | 288691.54
T2309 | Cowley Marsh Extension | Oxford Direct Services | Douglas Kerrigan | GF | Project - Development | Project - Development GF | Delivery | On target | Low | 0 | 0 | 34658.79 | 0 | 82326 |  | 34658.79 | 17329.39 | 142774.16 | 411.9% | -108115.37 | -47667.21 | 0 | -47667.21 | 34658.79 | 34658.79 | 0 | Area now in use by public Awaiting advice on hedge planting from ODS arboricultural services. The row of Cypress trees on the boundary with the CM yard have been removed as an additional cost to the project. These had been neglected and were in a dangerous condition. This was reported at a previous board several months ago and budgeted at £14k. The final account is due to be closed out once the hedging costs are know and if they can be planted this season | 0 | None | Discharge of planning conditions can now proceed following completion of all works (subject to hedge planting) Stated as November so that will be the date on discharge | 0 | 0 | 0 | 0 | 34658.79
T2307 | Transformation Funding | Oxford Direct Services | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | 0% | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
T2308 | Additional Technology Requirements | Oxford Direct Services | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | 0% | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
| Oxford Direct Services Projects Total | [8 empty] | 5974279 | 1964915 | -4254535.48 | 6881145 | 6822911 |  | 3684658.52 | 1842329.26 | #VALUE! | 22.61% | #VALUE! | -3000168.44 | -2952501.23 | -47667.21 | 3822742.56 | 3822742.56 | [6 empty] | 7440601 | 3256938 | 3000000 | 17382197.52
[28 empty] | 0 | #N/A | #N/A | #N/A
| Communities and People Directorate Total | [8 empty] | 11666529 | 1746752 | -3150983.13 | 16173732 | 12995127 |  | 10262297.87 |  | #VALUE! | 29.3% | #VALUE! | -2936513.47 | -2779334.16 | -157179.27 | 10435399.01 | 10063582.01 | 0 | 0 | 0 | 0 | 0 | 0 | 10780258 | 4621938 | 4215000 | 29879493.87
[28 empty] | 0 | 0 | 0
Development Directorate | [27 empty] | 0 | 0 | 0
| Corporate Property Projects | [10 empty] | 0 | [15 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
B0100 | Gloucester Green Car Park (H&S) | Corporate Property | Luca Minetola | GF | Project - Compliance | Project - Compliance GF | Completed | Completed | N/A | 300000 | 241916 | -171185.86 | 241916 | 71030 |  | 370730.14 | 185365.07 | #VALUE! | 0% | 370730.14 | 299700.14 | 0 | 299700.14 | 370730.14 | 370730.14 | 0 | Works completed by ODS in September in line with revised programme. Awaiting Final account sign off | 0 | 0 | Works are complete | 0 | 0 | 0 | 0 | 370730.14
B0031 | Planned Building Improvements | Corporate Property | Luca Minetola | GF | Rolling Programme | Rolling Programme GF | Completed | Completed | Low | 750000 | 0 | -248017.69 | 241916 | 750000 |  | 501982.31 | 250991.15 | 11719.75 | 2.335% | 490262.56 | -248017.69 | 0 | -248017.69 | 501982.31 | 501982.31 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 750000 | 750000 | 3251982.31
B0101 | Capital Works at Covered Market | Corporate Property | Luca Minetola | GF | Project - Development | Project - Development GF | Design & Specification | Awaiting new Schedule | Low | 200000 | 28863 | 659590.03 | 29043 | 1464 |  | 888453.03 | 444226.51 | 12861.63 | 1.448% | 875591.4 | 5771 | 5771 | 0 | 7235 | 7235 | 0 | Awaiting outcome of the covered market masterplan | 0 | Changing priorities. Scope of proposed works will likely be reviewed now draft Master Plan report for the Covered Market has been received and fully reviewed. | 0 | 0 | 200000 | 200000 | 200000 | 1488453.03
B0104 | Old Gas Works Bridges | Corporate Property | Luca Minetola | GF | Project - Compliance | Project - Compliance GF | Delivery | Off Target | Medium | 1000000 | 20451 | 750184.67 | 20451 | 1679065 |  | 1770635.67 | 885317.83 | 543923.49 | 30.72% | 1226712.18 | 298479.45 | 0 | 298479.45 | 1977544.45 | 1977544.45 | 0 | main works to bridge completed - Bearing replacement works underway pending approval from TA - Due to reopen on 31st Oct | 0 | "Bridge is due to be lifting with jacking taking place from underneath. Following this bridge being raised the bearings that the bridge rests on will be replaced. Once this has been completed the project will essentially be completed, other than snagging and demobilsaition. " | Temporary Bridge Opening - 31st July 24 | 0 | 0 | 0 | 0 | 1770635.67
B0106 | Covered Market Roof Works (Capitalised Planned Maintenance) | Corporate Property | Luca Minetola | GF | Rolling Programme | Rolling Programme GF | Delivery | Awaiting new Schedule | Low | 525000 | 131406 | -656406 | 557406 | 52925 |  | 0 | 0 | -22222 | #DIV/0! | 22222 | 595132.67 | 595132.67 | 0 | 648057.67 | 648057.67 | 0 | "Covered Market Roof Project was determined by procurement and legal. New project for phase 6c to be done by property services. Phase 7 has been passed over and added to the Masterplan for the Covered Market." | 0 | Access to enable the delivery of Phase 6c of the works is provided. Working in conjunction with Master plan delivery, other major refurbishments at the same time. Ability to share welfare facilities. Deliveries to and from Market St, which is currently semi pedestrianised. | Project initiation | 0 | 0 | 0 | 0 | 0
B0110 | Covered Market Vacant Unit Works | Corporate Property | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | n/a | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
B0111 | Town Hall Dry Risers | Corporate Property | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 12110 | -12110 | 12110 | 0 |  | 0 | 0 | 25429.91 | n/a | -25429.91 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 0
B0117 | Regeneration Property | Corporate Property | Emma Gubbins | GF | 0 | 0 GF | Completed | Awaiting new Schedule | Medium | 0 | 0 | 3402.38 | 3000000 | 0 |  | 3402.38 | 1701.19 | #VALUE! | #VALUE! | #VALUE! | 3402.38 | 3402.38 | 0 | 3402.38 | 3402.38 | 0 | Remainder of funds to be used within the capital programme due to changes in PWLB lending rules. Unlikely to make any further acquisitions | 0 | 0 | Purchase complete. Remaining budget to be considered as part of the budget process | 0 | 0 | 0 | 0 | 3402.38
B0124 | Port Meadow Moorings | Corporate Property | Jane Norman | GF | 0 | 0 GF | Feasibility | Awaiting new Schedule | Low | 0 | 0 | 0 | 3000000 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | The last Project Board was held on the 5th August. It was agreed that this project would now be split: -Property to progress the tender for the new contract for managing the moorings with the target of April 2025 for the new contractor in place; -Regeneration to progress longer term feasibility work to include commissioning commercial advice. A new PID and report will be presented to ARG on the 1st October with a request for a budget to cover external advice and internal staff time. | 0 | The site sits adjacent to an SSSI, SAC and SAM and has Freemen of the City of Oxford and the Wolvercote Commoners managing the area. The impact of any proposals on this sensitive landscape will need to be very carefully assessed and a clear communications strategy put in place. The timescale for considering future options may be longer than usual due to the above sensitivity and the need to work with the EA. Starting work now will ensure that sufficient time is available to accommodate other organisations timescales and governance. | Report to ARG - 1st October 2024 | 0 | 0 | 0 | 0 | 0
B0125 | City Centre Restart (CIL Funded) | Corporate Property | Diana Fawcett | GF | Project - Development | Project - Development GF | Delivery | On target | Low | 0 | 0 | 39324.01 | 3000000 | 40000 |  | 39324.01 | 19662 | #VALUE! | #VALUE! | #VALUE! | -675.99 | -675.99 | 0 | 39324.01 | 39324.01 | 0 | My understanding is that CIL should show a total of £8,000 budget for city centre projects. This should be split to £1,368.49 for 2023/2024 and £6631.51 for 2024/2025. My understanding is that any extra shown against CIL, should have been allocated to the Covered Market. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39324.01
B0126 | Asset Surveys | Corporate Property | Luca Minetola | GF | Project - Development | Project - Development GF | Design & Specification | On target | Low | 0 | 120000 | -70000 | 300000 | 300000 |  | 50000 | 25000 | 102.52 | 0.205% | 49897.48 | -250000 | -250000 | 0 | 50000 | 50000 | 0 | Running in conjunction with aquisition of new asset management sysytem to determine requirements and details needed to populate the system | 0 | """Access will be the key risk. Flow of information to contractor Health & Safety Information for properties.""" | Asset Management System in place | 0 | 250000 | 0 | 0 | 300000
B0136 | Covered Market CCTV | Corporate Property | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 73648 | -73648 | 73648 | 0 |  | 0 | 0 | #VALUE! | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
B0138 | Enabling works - Decarbonisation Project | Corporate Property | TBC | GF | Project - Other | Project - Other GF | Completed | At Risk | Medium | 0 | 698610 | -698609.61 | 698610 | 660481 |  | 0.39 | 0.19 | 0 | 0% | 0.39 | -660480.61 | -660480.61 | 0 | 0.39 | 0.39 | 0 | 1. Hinksey Commissioning complete. 2. Project Handed over to Property 08/02/2023 3. Currently reviewing O&M manuals/ Health and safety files. | 0 | Barton Leisure Centre PHX heat exchanger claim by Willmott Dixon due to the pool water high levels of chlorine alleged to have caused corrosin on the heat exchanger. | Completion of Hinksey Commissioning work | 0 | 638576 | 0 | 0 | 638576.39
B0139 | SAC Feasibility | Corporate Property | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 37965 | -37965 | 37965 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
B0142 | Stock condition surveys (including bridge works) | Corporate Property | Luca Minetola | GF | Rolling Programme | Rolling Programme GF | Delivery | On target | Medium | 500000 | 0 | -180413.71 | 1592500 | 888345 |  | 319586.29 | 159793.15 | 23140 | 7.241% | 296446.29 | 111655 |  | 111655 | 1000000 | 1000000 | 0 | Project demand via ARG and DB - funding includes 46 George st, South Park & Alexandra sports projects | 0 | Key risks: 1. Additional cost to meet the programme and bridge opening at the end of May 2024 2. Delays to appointment of Contractor; 3. Labour and material shortages; 4. Increased material prices; 5. Delays in obtaining work permits; 6. Delays due to adverse weather conditions | 0 | 0 | 300000 | 600000 | 600000 | 1819586.29
B0143 | Town Hall Relocation | Corporate Property | Nathan Breeze | GF | Project - Development | Project - Development GF | Delivery | On target | Low | 0 | 0 | 479010.97 | 1000000 | 645590 |  | 479010.97 | 239505.49 | 97621.14 | 20.38% | 381389.83 | -455590 | -455590 |  | 190000 | 190000 | 0 | Town Hall Projects have been reorganized from 3 Phases into 4 Lots. This Project was previously called Phase 1 and is now Lot 1. Phase 1 activities have been split between Lot 1 and newly created Lot 4 for ICT Works (overseen by Rocco Labellarte) Lot 1 and Lot 4 activities both have budget allocated from Phase 1 budget (B0143) Key works in Lot 1: - Signing off of historic building control application - ongoing - Old Museum Shop to Display Area - target start in January 2025 - Movement of Print and Post function - awaiting clarifications Key works in Lot 4: - WiFi Expansion - target installation 21/10/24 - 16/12/24 (w/e and out of hours working) - Upgrades to PBX (Server) Room - consists of enabling works to upgrade the room (ceiling, walls, doors, AC) followed by upgrades to cabinets. Target final installation June 2025. - IT Build Room - Basement room to surveyed to identify damp issues to be addressed. Target completion date is February 2025 | Slight delays to start of PBX room upgrade and print and post room relocation will result in forecasted spend moving into next financial year. | Coordination of all projects related to Town Hall. Regular meetings with Property teams to ensure no conflicting work areas. | WiFi Expansion part 1 - December 2024 | 0 | 0 | 0 | 0 | 479010.97
B0149 | Tumbling Bay Embankment Works | Corporate Property | Luca Minetola | GF | Project - Compliance | Project - Compliance GF | Design & Specification | On target | Low | 0 | 0 | 31185.5 | 0 | 200000 |  | 31185.5 |  | 5667.87 | 18.17% | 25517.63 | 81185.5 |  | 81185.5 | 281185.5 | 281185.5 | 0 | Project is still in design stage awating permits for EA. Public engagement and planning once these stages are achieved. | 0 | Public access is now restricted with Heras Fencing & signage. | Design Completion / Tender | 0 | 250000 | 0 | 0 | 281185.5
B0151 | Bus Shelters | Corporate Property | Jane Norman | GF | Project - Other | Project - Other GF | Feasibility | On target | Medium | 0 | 0 | 15049.79 | 1000000 | 28284 |  | 15049.79 | 7524.9 | 9811 | 65.19% | 5238.79 | -13234.21 |  | -13234.21 | 15049.79 | 15049.79 | 0 | The Bus Shelter Tender was launched on the 22nd July with a closing date of the 6th September. The bids will be evaluated during September/ early October with the contract commencing in November 2024. The tender has included the station and NHS shelters for information only to allow these to potentially be included in the contract in the future. Further discussion with Network Rails/GWR and the NHS will be required once the supplier has been appointed. | 0 | Programme delay- the programme timeframe has slipped but the tender process is on target for the award of contract before the current contract ends in late November/early December. Lack of interest in the tendering opportunity - 6 suppliers were interested but only 2 bids were received, one being the current incumbant. Lack of resource to secure and manage new contract - PM has input from Property, Procurement, Legal and County to keep things on track Public opinion- negative press re replacement of bus shelters - explain the reasoning via positive promotion of the new contract and the opportunities it will bring in terms of improved services and the use of sustainable materials, fact that shelters will be recycled etc. Planning and highways issues - it will be the responsibility of the contractor to obtain necessary permissions for any new shelters etc. and this will be made clear during the market engagement. | Contract Award- November/December 2024 | 0 | 0 | 0 | 0 | 15049.79
B0153 | HSBC Options | Corporate Property | Kate Protheroe | GF | Project - Development | Project - Development GF | Feasibility | On target | Low | 0 | 0 | 55000 | 1000000 | 30000 |  | 55000 | 29615.38 | 0 | 0% | 55000 | -18000 |  | -18000 | 12000 | 12000 | 0 | Initial and midway meetings have been carried out with consultant and now awaiting completion of draft report to consider for internal approval | Left time for internal approval before using rest of budget | Confirm once report received | Receipt of draft report by 25th October | 0 | 0 | 0 | 0 | 55000
B0154 | Covered Market masterplan and enabling works | Corporate Property | Andrew Humpherson | GF | Project - Development | Project - Development GF | Delivery | On target | Medium | 1513991 | 0 | -716343.61 | 1000000 | 500000 |  | 797647.39 | 321900.62 | 373487.13 | 46.82% | 424160.26 | 172979 |  | 172979 | 672979 | 672979 | 0 | Project management and design team consultants including Principal Designer now appointed. Key Stage One milestone works to review and revise the current masterplan and essential works proposals completed and under review by Project Board. Proposals to be finalised and supported by a revised business case for approval before progressing to detailed design in the new year. Property Services scope of remedial works to be identified separately. Consultation is on-going with All Souls College in respect of college proposals to extend and refurbish High Street properties including air rights development and market entrance improvements. Works will help offset OCC masterplan costs. | Stage 3 approval to proceed pending approval to OCC MTFP and wider budgetary constraints | Project concerns over additional budget to deliver essential utilities work now largely mitigated following completion of Stage 2 review. Proposals and business case under review including reduced scope within original masterplan budget and option for additional funding supported by a revised business case. Preferred option pending decision by project board. Revised proposals will require a revised business case with separation between essential works and masterplan works as part of a revised viability model. Central Government funding uncertainty = current SPF £300K funding allocation within project’s £6.5m budget could be at risk, as it may need to be used to fund other under-funded R&E projects. Loss of public/wider interest = possible member perception that project progress is taking too long to materialise & possible political/ reputational ramifications of this. Mitigation - consultants have completed Stage One review providing more certainty on deliverability. | Consultant team now working to September deadline to complete a project and budget review for delivery of the masterplan. Draft review tabled at OCM Board 17/09/2024 | 0 | 589820 | 2906795 | 3265551 | 7559813.39
B0155 | Contingency to cover cost inflation rises | Corporate Property | 0 | GF | Other Capital Spend | Other Capital Spend GF | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2000 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | -2000 |  | -2000 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
B0156 | Waterways - Condition Survey / Long Bridges | Corporate Property | Luca Minetola | GF | Project - Compliance | Project - Compliance GF | Completed | Completed | Low | 355000 | 0 | -342.42 | 1000000 | 90000 |  | 354657.58 | 177328.79 | 121101.55 | 34.15% | 233556.03 | 264657.58 | 264657.58 |  | 354657.58 | 354657.58 | 0 | Condition survey now completed. | 0 | 0 | Project Initiation | Smartsheet forecast was <25,000 but had to amend to allow formulae to work | 0 | 0 | 0 | 354657.58
B0157 | Works Town Hall | Corporate Property | Luca Minetola | GF | Project - Development | Project - Development GF | Design & Specification | On target | Low | 1500000 | 0 | -978084.75 | 1000000 | 200000 |  | 521915.25 | 318649.93 | 266212.35 | 51.01% | 255702.9 | 1321915.25 | 1321915.25 |  | 1521915.25 | 1521915.25 | 0 | Works are being split into phases from Asset data and surveys | 0 | 0 | Appointment of design team | 0 | 1000000 | 1000000 | 500000 | 3021915.25
B0147 | Repairs to 2-4 Gloucester Street and 24-26 George St | Corporate Property | Luca Minetola | GF | Project - Development | Project - Development GF | Completed | Completed | Low | 0 | 0 | 0 | 770000 | 616385 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | -616385 | -616385 | 0 | 0 | 0 | 0 | Project practical completion has been achieved, waiting for final accounts to be concluded with ODS. Possible further works required but negotiations with new tenant are underway and due to be concluded the coming weeks. | 0 | Budget spend is being scrutinised by QS & CA for validity | Completion October 2023 | 0 | 0 | 0 | 0 | 0
| Corporate Property Projects Total | [8 empty] | 6643991 | 1364969 | -1810379.3 | 20575565 | 6755569 | 0 | 6198580.7 | 3066582.2 | 1491078.34 | 24.06% | #VALUE! | 890494.47 | 207747.28 | 682747.19 | 7646063.47 | 7646063.47 | [6 empty] | 4478396 | 5456795 | 5315551 | 21449322.7
| Regeneration & Economy Projects | [10 empty] | 0 | [15 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
M5033 | Blackbird Leys Regeneration (GF Element) | Regeneration & Economy | Karoline Soisalo De Mendonca | GF | Project - Development | Project - Development GF | Design & Specification | At Risk | High | 5586876 | 205663 | 2563461.05 | 8680256 | 8903897 |  | 8356000.05 | 4178000.03 | #VALUE! | #VALUE! | #VALUE! | 237883 | 237883 | 0 | 9141780 | 9141780 | 0 | COMMUNITY CENTRE: Design/Planning: - Design freeze achieved, with minor coordination between disciplines still ongoing, design team working on planning submission - Energy consultants asking for 5 weeks to produce assessments and reports, which may delay submission date - OCC discussing fee and programme for Stage 4 drawings to be produced by Jessop & Cook for tender (both fitout and S&C) - OCC/PBT discussing procurement strategy for community centre. PBT preferred route is 1-stage D&B, with one single contractor delivering both shell & core and fitout. - OCC agrees that having one contractor delivering both scopes will simplify and expedite delivery, but is concerned with loss of control over design due to D&B contract. OCC to increase design control by requesting detailed Stage 4 drawings for tender and detailed ERs. Programme: - Programme has been affected by design development delays on externals. Planning submission date has now slipped to mid September 2024. - Design freeze anticipated for 16/08/24 - Final Exhibition: w/c 09/09/24 - Submission: 20/09/24 Budget: - design team has been working on VE exercises on shell & core, guided by PBT's QS. - S&C still over budget but PBT agreed they now have a viable/buildable design (JG at Procurement meeting) -D&S reviewing/revising cost plan for fitout to reflect latest design PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. | Delay to planning submission for outline application submission and therefore start on site. Current delay of 5 months from original submission date of end of March 2024. This has pushed construction costs for community centre shell & core to 25/26, 26/27. We are currently studying procurement options for the community centre - traditional, 1-stage D&B and 2-stage D&B. Each option has a slightly different programme but all show construction starting 25/26, whereas before, we had forecast SoS for 24/25. I'm unsure if I've missed something in my 24/25 forecast as £5.2m is substantial, but Jason J is away and I need to sit down with him and go over line by line to see what I've missed or if the 24/25 forecast was too high. Will be able to confirm these numbers when he gets back on 22/07. | - Community Centre delivery: This is still a major risk to the project, as it has the potential to delay the occupation of Block A. This planning condition is being questioned by PBT, and is relatively vague in wording. KSM to confirm. -The programme has slipped due to delays in design development, and planning submission has now been pushed to 20 Sept 2024. This means there will be slippage on completion date for the centre. - Community Centre Budget: After VE exercises, S&C still over budget, but PBT agrees there is no more scope for VE and are happy to proceed to tender. Revised cost report for fitout to be issued. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2. - OCC/PBT discussing Ph 2 options - Peabody confident they can get a viable Ph 2 scheme, which will de-risk the delivery of housing and therefore risk of claw back for HIF by Homes England. - Comms & Engagement: Still a risk to relations as this project gets more politically sensitive. Comms around Community Centre especially sensitive as the planning submission date has been moved back several times as the project faces delays at design development stage. Parish Council/Community have expressed concerns about delays and worries about housing being delivered without the community centre have returned. OCC to continue to attend Parish Council meetings and communicate with concerned parties to assuage concerns. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024. | Community Centre Design Freeze: 16/08/24 | 0 | 4866000 | 5452000 | 4121439 | 22795439.05
A4853 | City Wide Cycling Infrastructure Contribution | Regeneration & Economy | Mim Norvell | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 60000 | 12500 | -17146.84 | 122456 | 147465 |  | 114517.16 | 27676.58 | 15282 | 13.34% | 99235.16 | -65465 | -65465 | 0 | 82000 | 82000 | 0 | 7 carriageway locations approved for installation at County CMD, 75 racks, 150 spaces. ODS to install after order is 'made'. Next set of racks proposals being progressed, including Cowley Rd. 'Latest Budget' not updated at time of data entry, in hand with Account Manager. | Additional time is probably required for processing upcoming location approvals, could take longer than previously expected. | >County/City/ODS under resourced leading to delays | Carriageway rack installs Nov-Dec 24 | 0 | 114517 | 0 | 0 | 229034.16
B0081 | Car Parking Oxpens | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 0 | -517 | 517.05 | 224838 | 3081 |  | 0.05 | 0.03 | 0 | 0% | 0.05 | 0 | 0 | 0 | 3081 | 3081 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 0.05
B0086 | Seacourt Park & Ride Extension | Regeneration & Economy | 0 | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 0 | 137846 | -137846 | 137846 | 0 |  | 0 | 0 | 1262.5 | n/a | -1262.5 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 0
B0092 | Cave Street Development (Standingford House) | Regeneration & Economy | Douglas Kerrigan | GF | Project - Development | Project - Development GF | Feasibility | Awaiting new Schedule | N/A | 0 | -14902 | 209036.47 | 3051099 | 500000 |  | 194134.47 | 97067.24 | 146694.01 | 75.56% | 47440.46 | -305865.53 |  | -305865.53 | 194134.47 | 194134.47 | 0 | Project is not meeting feasibility targets due to economic uncertainties and unstable build costs. It has been decided to 'mothball' the project and investigate meanwhile uses Line in cabinet paper December 2023 to explain The following statement has been issued to Ward Councillors Statement on Oxford City Council’s decision to pause Cave Street redevelopment: “Oxford City Council has taken the decision to pause the redevelopment of Standingford House, on Cave Street, due to the present challenging economic climate. “The Cave Street site will remain a City Council asset, allowing for meanwhile options to be explored that could bring the site back into temporary use. “The decision comes as significant cost increases – both in the construction and the cost of borrowing – mean the agreed budget for the Standingford House redevelopment is no longer sufficient. The Council is responsible for effectively managing its budget and assets and has considered various options to continue with the redevelopment. However, all would require an increased budget and a long-term payback period, putting increased pressure on the Council’s Medium Term Financial Plan. “Plans to replace Standingford House with modern small business units were approved by Cabinet in 2021 as the building did not comply with the required national legislation for Minimum Energy Efficiency Standards (MEES) for commercial properties and the building was in poor condition. It needed urgent repair and maintenance. “Demolition of the former building is complete, and the site has been secured. Consideration will be given to how the site might best be used in the short to medium term, until economic conditions support bringing forward the planned development of small business units.” ENDS The site will be secured (small budget held say £50k) and a handover made to properties w/c 4/12/2003. Housing services are investigating a meanwhile use as TA by installing pods. A project board dedicated to this will be held on a monthly basis. | 0 | TBA on meanwhile uses | Meanwhile uses considered January 2023 | 0 | 0 | 0 | 0 | 194134.47
B0098 | 1-3 George Street | Regeneration & Economy | Karoline Soisalo De Mendonca | GF | Project - Development | Project - Development GF | Delivery | Off Target | High | 0 | -339924 | 506656.7 | 1056845 | 377292 |  | 166732.7 | 83366.35 | 109067.18 | 65.41% | 57665.52 | -372292 | -372292 |  | 5000 | 5000 | 0 | - Works on site have been completed. - OCC/ODS agreed that LADs would be paused for 8 weeks to allow ODS the chance to gather all BREEAM information and finalise accreditation. We may be able to get a 'Good' rating, 'Very Good' very unlikely. - 14/08/24: Caroline/Carolyn/Simon met to discuss, as ODS not making any progress with BREEAM after 5 weeks. - Agreed way forward on 15/08/24: ODS/OCC to work together to finalise BREEAM, to meet to discuss variations line by line with ODS in September, and both sides to put together a qualitative narrative report to describe what they believe 'went wrong' or caused severe delays and financial loss. - ODS/OCC to meet 11/09/24 to discuss variations | Due to ongoing project delay - Ongoing OCC officer and legal costs relating to extended programme and delays - Late invoicing by ODS: ODS invoiced in 2024/25 for works completed in 2023/24 - Consultant payment: payments to consultants were left to the end of the project, so an estimated £10k will be invoiced to OCC for QS and contract admin services | -The project still remains in significant delay, practical completion is now on hold until we can establish BREEAM status. - BREAAM: Risk that ODS will not complete BREEAM as agreed between OCC and ODS. To mitigate this risk, OCC have agreed to meet regularly and support in completing works. - OCC/ODS are in final accounts negotiations which can be lengthy. There are disagreements on contractual obligations on both sides. In order to understand all variations and their legitimacy, ODS have agreed to meet to run through them line by line. In this meeting, ODS will have to demonstrate two things: that the variations were legitimate client changes or instructions, and substantiation/evidence of works. - Risk of having to go to external mediation in case disagreements cannot be resolved. this will cause further delays and add cost. - risk of loss of income as the property sits empty, without an operator. OCC is working with Savills to arrange viewings. OCC Property has been in talks with potential tenants on possible lease agreements and rent. - risk of clawback for OxLEP funding. This is unlikely, but OCC/ODS working together to find a position both sides are comfortable to reach PC. OCC also working with Savills to ensure a tenant moves in asap. | BREEAM Workshop 1 - 22/08/24 | 0 | 0 | 0 | 0 | 166732.7
T2301 | Depot Rationalisation | Regeneration & Economy | Douglas Kerrigan | GF | Project - Development | Project - Development GF | Feasibility | Awaiting new schedule | High | 0 | 0 | 266645 | 500000 | 266890 |  | 266645 | 133322.5 | #VALUE! | -53.51% | 409319.16 | -245 | -245 | 0 | 266645 | 266645 | 0 | Work has continued during 2022 to explore using Horspath to accommodate the majority of ODS business to free up other depot sites and to allow for some growth in ODS business. This option was reliant on leasing extra land of a couple of hectares in size to store vehicles and other spill over activity that the existing Horspath depot site would not be big enough to accommodate. Several sites in the vicinity have been looked at but none can accommodate a long lease that would provide the business certainty ODS would need. The city work is now on pause with the agreement that ODS are going to scope out what staying on their existing sites mean and whether they could physically rationalise into the other depot sites freeing up Horspath to save them rental costs. Monitoring of other site opportunities will continue. We await update from ODS in order to feed into confidential scrutiny update requested as part of budget process. | 0 | Identification of a suitable site to create parking for ODS operations. Feasibility - Review of ODSL operational requirements to include as tender document for RIBA 0-2 reports. Clear and robust gateways to be set for RIBA 0; RIBA 1 and RIBA 2 | Update expected end of August from ODS | 0 | 0 | 0 | 0 | 266645
B0112 | Future Options for City Centre Land (Odeon) | Regeneration & Economy | Carri Unwin | GF | Project - Development | Project - Development GF | Delivery | On target | Medium | 0 | 35406 | 95045.85 | 71063 | 170000 |  | 130451.85 |  | 24686.56 | 18.92% | 105765.29 | -170000 |  | -170000 | 0 | 0 | 0 | Planning application resolution to grant is on Agenda for the October Committee. This is a 1 month delay on project, and was due mainly to the request for additional work to the visual assessment information. Drafting of s106 being finalised, and Press release comms agreed in preparation for after Resolution to Grant achieved. Developer and operator requested a revision to lease boundaries to accommodate cycle parking area and store for community space. Acceptable and legals being progressed. | Contingency unspent so far in 24/25 Note- £98K property payment due in Feb/Mar 25 | Agreement being reached with the LPA on s106 and visual information. Mitigations: additional meetings as required, and correctly articulating wide range of significant benefits and improved Gloucester Green elevation and maximised active frontages to benefit Gloucester Green - a key project and city centre aim. Right to Light injunction risk - mitigate through progressing appropriation process. Minimising future reputational risk to Council - in its public servant role by s106 ensuring community space is available in perpetuity to at least serve local city centre residents as well as other wider groups. Mitigation by liaison with communities and economic team. And list of approved uses in sub lease between Staycity and Makespace. | Resolution to grant - Oct 24 | 0 | 0 | 0 | 0 | 130451.85
B0141 | City Centre Public Realm (Kiosks Project) | Community Services | Carri Unwin | GF | Project - Development | Project - Development GF | Delivery | On target | Low | 179987 | 18277 | 42770.3 | 43277 | 190000 |  | 241034.3 |  | 78560.32 | 32.59% | 162473.98 | 1034.3 | 1034.3 | 0 | 191034.3 | 191034.3 | 0 | Cabinet in place, and date obtained from SSE for them to connect it. Currently then arranging for supply comppany to fit meter following SSE work. Hoardings in place until new electric supply connected and working, then disconnection can be done for other power supply on 38 -40 George St, and paving works completed. | Delays from utility companies | Risk of delays due to SSE process to connect new Cabinet, and due to Npower lead times to fit meter. Mitigation: regular chasing and communication. Risks of ODS electrician work slow to progress connections of power bollards, and finish Cabinet to LSD market satisfaction. Risk of delays due to SSE process to carry out disconnections of Odeon wall infrastructure following new Cabinet live. Mitigation: schedule in time for all forms and chasing required; and OCC payments timescales. | SSE connect supply to new cabinet - Nov 24 | 0 | 0 | 0 | 0 | 241034.3
B0116 | Osney Mead Path Works (HIF) | Regeneration & Economy | Roland Parsloe | GF | Project - Development | Project - Development GF | Design & Specification | At Risk | High | 564914 | 18914 | 814807.13 | 5422914 | 1113324 |  | 1398635.13 | 699317.56 | #VALUE! | #VALUE! | #VALUE! | 285311.13 | 285311.13 | 0 | 1398635.13 | 1398635.13 | 0 | It has been agreed that HIF funding allocated for Pathworks to be focused on the pathworks associated with the proposed Oxpens River bridge. The funding for the pathworks improvements to the west of the railway to Osney Mead would then need to be secured from elsewhere. Discussions have taken place with Homes England and Oxford University on the principles involved. Balfour Beatty have been appointed as contractor to deliver the bridge and pathworks. A Deed of Variation to the HIF Funding agreement was received from Homes England and returned with comments and a further version of the DofV has been received. Back to back funding agreements have been drafted re the OFAS element of the funding with the Environment Agency but are still subject to review and discussion. However, an agreement with University of Oxford has not been agreed which presents a risk to the drawdown of funding with regard to clawback by Homes England. This has been reported to Cabinet who have agreed to accept the risk. Funding has to be drawn down by March 25 (subject to signing the DofV) and details of spend evidenced and pre conditions and milestones met. | 0 | There remain risks relating to the ability to claim the funding from Homes England. A Deed of Variation has been drafted to extend the period to claim funding up to March 25 and resolve other issues. Evidence of spend is required to make the claim and there is a risk that there will not be sufficient spend on the pathworks by March 25 as delivery is now delayed by the JR of the planning decision. Also if funding is spent without the University delivering housing at Osney Mead there is a risk of clawback. | Deed of Variation from Homes England for the HIF funding to be progressed - Requirement to conclude by 24 Sept 2024 | 0 | 0 | 0 | 0 | 1398635.13
B0148 | Oxford Flood Alleviation HIF Contribution | Regeneration & Economy | Jenny Barker | GF | Project - Development | Project - Development GF | Feasibility | Off Target | Medium | 0 | 0 | 4350000 | 0 | 4350000 |  | 4350000 | 2175000 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 4350000 | 4350000 | 0 | Homes England have provided a revise Deed of Variation to the funding agreement. This has addressed some significant issues with the original funding agreement including extending the period for the draw down of the funding to March 2025. Response has been sent and final version awaited. Capacity funding has been received for 22/23 and 23/24 to address some of the HIF internal costs to date. A bid has been made for capacity funding for 24/25 and HE have requested further details. | Funding is going to be required to be drawn down by March 2025 and will then be passed to the EA. | This HIF is particularly complex as there are two elements of works being funded separately from the housing delivery which is being facilitated by the funding. There remains a risk that it will not be possible to claim the funding, which requires pre conditions to be met and evidence of spend. A recovery strategy is sought related to housing delivery and this is subject to discussions with U of O. There is a risk that if housing is not delivered at Osney Mead that the funding could be clawed back by Homes England. | Agreement of Deed of variation - October 24 | 0 | 0 | 0 | 0 | 4350000
B0120 | Osney Bridge (Growth Deal) | Regeneration & Economy | Roland Parsloe | GF | Project - Development | Project - Development GF | Design & Specification | At Risk | High | 7184694 | 75949 | 197777.26 | 4694694 | 1400000 |  | 7458420.26 | 3729210.13 | #VALUE! | 0% | 7458420.26 | -414039 | -414039 | 0 | 985961 | 985961 | 0 | Planning permission granted but subject to Judicial Review. Further submission has been made to County for Technical approvals: AIP, Section 38 & CAT 3 checks - near to conclusion - but still awaiting AiP sign off. S106(3) Highways Act notice published on 2nd May for 6 weeks, process due to conclude shortly. Initial priced packages received by BB - showing increase from previous estimates. Due to delays further funding to cover CEs and Risk is needed. Circa 1.35m. University being approached. OxWED have been approached re. Land behind ice rink for crane as this could reduce the above figure and reduce risks from flooding. Delays have made risk of completed by March 2025 very high so approach to County to seek agreement to extend funding to allow construction in 2025. | Delay to programme | Risk of JR proceeding delaying programme beyond 2025. Situation being monitored. Meeting the final Growth deal & HIF spending deadlines. Work underway to secure the funding for 2025. Negotiations with OXWED in relation to enabling works and land use. Further information to be provided re crane positioning. Risk budget will not be sufficient. On going work with BB re cost of PCSA and bridge construction. | Confirmation on extension of Growth Deal funding | 0 | 0 | 0 | 0 | 7458420.26
B0122 | City Cycle Schemes (Growth Deal) | Regeneration & Economy | Carri Unwin | GF | Project - Other | Project - Other GF | Delivery | On target | Medium | 0 | 118102 | 313230.3 | 869764 | 603415 |  | 431332.3 | 215666.15 | #VALUE! | #VALUE! | #VALUE! | -385415 | -385415 | 0 | 218000 | 218000 | 0 | Donnington Rec shared cycleway / footway: Info for condition discharge, and updated landscape schemes on Agenda for October Planning Committee for approval. SIgnificant support letters from community in favour of path through park. Liaison with Cllrs, residents, and football club done, and ongoing. Subject to planning approval, works can start on site early November. Contract with ODS being finalised and signed. And ODS can mark out pitches during construction to preference of football club, while allowing cycle access through too. Legal finalising s106 wording. Marsh Lane Rec: completed, apart from Property completing agreement with Christchurch for preferred connection to the highway. Scheme functions without. | Delayed start to site works due to awaiting planning approval of updated scheme information and condition info. | Risk - not getting planning discharge of conditions and updated landscape scheme. Mitigation: - provided case officer with all info she needs; and generated positive consultation comments of support, incl from football club and residents association. Risk - Legal resurce at City and County not sufficientto produce s106 document on time. Mitigation: ongoing liaison with legal lead. Risk - ODS have delays in gearing up for work. Mitigation: worked is booked in diary, and keep close liaison ongoing. Risk: consultant CA and PD cause delays and extra costs. Mitigation: Managing good relationships and asking for input as early as possible | Planning approval of conditions and updated landscape scheme - Oct 24 | 0 | 0 | 0 | 0 | 431332.3
B0145 | St Michael's Street Levelling Works | Regeneration & Economy | Mim Norvell | GF | Project - Development | Project - Development GF | Delivery | On target | Medium | 168817 | 0 | 240009.57 | 35000 | 20000 |  | 408826.57 | 204413.28 | 23682.78 | 5.793% | 385143.79 | 268019.57 | 268019.57 |  | 288019.57 | 288019.57 | 0 | Investigative trench survey confirmed an estimated £19.8k additional costs (main cost Virgin Media). Agreed with HoS/HoF to vire from unallocated City Restart CIL. Budget remains under £500k. Crossing £500k threshold would require Leader delegation (Brown/Hollingsworth) for decision to proceed. S278 progressing. Potential for COMPF/ZEZ/SPF underspend contribution for enhancements, potentially reintroducing removed elements. Construction planned for Jan-Mar 25. | Reprofiling of billing programme | > Works/Legal delay affecting SPF spend criteria deadline - construction programme reviewed and agreed with ODS, early engagement with Legal > Services cause unexpected delays - GPR survey / investigative trenches, increased budget, early engagement with utilities | Proceeding to contract with ODS | 0 | 0 | 0 | 0 | 408826.57
B0146 | Ice Rink Car Parking Feasibility | Community Services | Jane Norman | GF | Project - Development | Project - Development GF | Design & Specification | On target | Medium | 100000 | 0 | -83934.07 | 46190 | 0 |  | 16065.93 |  | 10415 | 64.83% | 5650.93 | 16065.93 | 16065.93 | 0 | 16065.93 | 16065.93 | 0 | The latest proposal for 12 parking spaces has internal approval and consultants have prepared a planning application to reflect this. The project is on hold until there are sufficient staff resources within the regeneration team to support it. | 0 | Risk 1: New proposals not acceptable to planning & user groups Mitigation 1: Meeting with user group, pre-app discussions. Risk 2: Ice rink users unhappy with proposals leading to reputational risk. Mitigation 2: Reduce risk by open dialogue and good Comms | Project on hold | 0 | 130000 | 0 | 0 | 146065.93
B0131 | Meanwhile In Oxfordshire | Regeneration & Economy | Clayton Lavallin | GF | Other Capital Spend | Other Capital Spend GF | Completed | On target | Low | 0 | 281496 | -199179 | 535370 | 85595 |  | 82317 | 41158.5 | #VALUE! | #VALUE! | #VALUE! | -3278 | -3278 | 0 | 82317 | 82317 | 0 | Undertaken Facilitated meeting on how Makespace and OCC can work together in future. Ongoing Comms and TikToks for Market additions through Meanwhile Prepare for Lessons learnt meetings with operator and then with all project partners ( OXLEP & Districts) Prepare doc for LGC award submission. Ongoing Liaison with Makespace on progress of final schemes | 0 | Viability of Phase 2, years 2 & 3 based on Revenue income. | 17 Jan lessons learnt with MS 18 Jan lessons learnt with OXLEP & districts | 0 | 0 | 0 | 0 | 82317
B0130 | CIL Feasibility | Regeneration & Economy | 0 | GF | Project - Other | Project - Other GF | Feasibility | 0 | Low | 0 | 150000 | -106650 | 100000 | 43350 |  | 43350 | 21675 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 43350 | 43350 | 0 | £50k budget remaining is ear-marked for Cowley Branch Line feasibility. £6,650 has been allocated to revenue spend in relation to Legal advice, however further Legal costs (c£20k) have now been incurred. After meeting Legal fees, remaining unallocated CIL budget can cfwd to 23/24 be reallocated to another project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43350
B0152 | Cowley Branch Line Full Busines Case | Regeneration & Economy | Rui Marcelino | GF | Other Capital Spend | Other Capital Spend GF | Feasibility | On target | Low | 1689183 | 0 | 910486.13 | 100000 | 2467817 |  | 2599669.13 | 1299834.57 | #VALUE! | #VALUE! | #VALUE! | 131852.13 | 131852.13 | 0 | 2599669.13 | 2599669.13 | 0 | Project is up and running. Programme Panel meetings taking place every 4 weeks as well as NwR progress meetings. Pedestrian and Cycle bridge design (Oxford Cowley station) RIBA stage 1 completed and RIBA stage 2 underway. commissioning of the Infrastructure Place Study (IPS) was completed just before Christmas, just subject to contract formal signing taking place Wed 17th Jan. Formal inception meeting to take place on Wed 17th Jan and IPS team already invited to attend several working groups and engagement meetings. Additional work has also been commissioned by County on Development of a developer contributions strategy for infrastructure to support the reopening of CBL, this has been completed and it is anticipated that the IPS team will pick this up and progress it further. Although CDM principal Designer was not part of the IPS commission, lead consultant has provided cost estimate for this should we wish to instruct it. | 0 | 0 | Completion of RIBA stage 2 concept design Pedestrian and cycle bridge - End Feb 2024. | 0 | 653350 | 0 | 0 | 3253019.13
B0074 | R & D Feasibility Fund | Regeneration & Economy | Rachel Haverson | GF | Project - Development | Project - Development GF | Feasibility | On target | Medium | 500000 | 0 | -37185 | 138862 | 475500 |  | 462815 | 215599.81 | #VALUE! | #VALUE! | #VALUE! | 27315 | 27315 | 0 | 502815 | 502815 | 0 | September 2024 Update - Allocations for 24/25 - Templars Square, BNG Feasibility, Floyds Row, HSBC Options, Bury Knowle House, Union Street Car Park, 42 & 46a George Street and Redbridge Masterplan - totalling £512,000. £401,815 budget remaining for 24/25. | 0 | RISKS * Funding is insufficient for the number of schemes requiring feasibility funding. * Continuing to commence further feasibility funded schemes may not be sustainable from a financing or resourcing perspective. MITIGATIONS * Review existing feasibility schemes on on-going basis to assess whether project profilied correctly or can be paused or stopped. * Introduce top up of feasibility budget when projects reach delivery stage and seek budget approval i.e. request gross budget and return the feasibility. * Potentially need to prioritise new bids arising against existing projects to assess options for reallocation of funding. | N/A - budget is allocated to approved schemes at the feasibility stage. | 0 | 500000 | 200000 | 0 | 1162815
| Allocated Feasibility Funding (various schemes) |  |  | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 0 | 182405 | 407183.67 | 575973 | 636266 | 0 | 589588.67 | 0 | #VALUE! | #VALUE! | #VALUE! | -161051.31 | -20851.81 | -140199.5 | 475214.69 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0
B0114 | Diamond Place Redevelopment | Regeneration & Economy |  | GF | 0 | 0 GF | Feasibility | Awaiting new Schedule | Medium | 0 | 4119 | 5880.5 | 53119 | 56600 |  | 9999.5 |  | #VALUE! | #VALUE! | #VALUE! | -46600.5 |  | -46600.5 | 9999.5 | 9999.5 | 0 | OCC Client Brief approved at Development Board on the 4th March and has been sent to OX Place for consideration. Ox Place have now confirmed that they will not be able to provide any update until January 2025. The local GPs have now heard back from BOB ICB who have confirmed that no funding was approved by their Executive Board for the move to South Parade but this didn't rule out potential funding in the future due to the change of government. Officers met with Peter Redman from BOB ICB in September. He was unable to confirm whether funding would be available for Diamond Place in the future or not but has agreed to provide information regarding the size of health facility they would require at Diamond Place. This will be shared with Ox Place. | 0 | The Neighbourhood Forum have clear ideas about the redevelopment of the site. The Stakeholder workshops have helped to explore the key challenges of developing the site and the forum are now considering a review of the neighbourhood plan. The Neighbourhood Forum also have different expectations about the timescale for any potential redevelopment. We will continue to engage with them through the tri-partite meetings and involve Ox Place in these meetings in the new year. | Ox Place to provide update on feasibility work - January 2025 | 0 | 74770 | 0 | 0 | 84769.5
B0118 | Oxford Ice Rink Development | Regeneration & Economy |  | GF | 0 | 0 GF | Feasibility | On target | Medium | 0 | 10047 | 26657 | 63407 | 98102 |  | 36704 |  | #VALUE! | #VALUE! | #VALUE! | -61398 |  | -61398 | 36704 | 36704 | 0 | Prior and Partners have completed the draft pre-app which was reviewed by the Project Board and Development Board in August. The pre-app was submitted on the 23rd August and the pre-app meeting will be held on the 14th October. Lead members were updated at the weekly leaders meeting in early September. The project board will be updated on the pre-app discussions at the end of October. | 0 | 1. Alternative locations may not be achievable within the timescale required for delivery of a new ice rink. 2. Alternative locations outside of the city centre may be politically unacceptable. Members briefings have confirmed that these options can be explored by officers. 2. Access to the new location and provision of sufficient parking for ice rink users is a key issue. | First pre-app meeting with LPA - October 2024 | 0 | 0 | 0 | 0 | 36704
B0119 | Oxford Station Feasibility | Regeneration & Economy |  | GF | 0 | 0 GF | Feasibility | On Hold | Low | 0 | 83363 | -31799.7 | 138571 | 228363 |  | 51563.3 |  | #VALUE! | #VALUE! | #VALUE! | -221101.68 | -221101.68 | 0 | 7261.32 | 7261.32 | 0 | Drafting materials to support input and decisions ahead of publication, including digital accessibility requirements. Response to LC17 sewer constraint in car park - did not object to land disposal | Forecast spend is confirmed. Other budget may slip as stakeholder engagement approach needs to be confirmed. | New Risk of sewer in becket St car park - impacts/mitigations considered and will now be a constraint. Draft risk register last updated with Board Nov 2023; to update next following stakeholder engagement sessions (date tbc) The RED risks are now: • DfT does not agree to fund Oxfordshire Connect or remains uncertain (now red, was amber) but masterplan is revenue generating towards rail costs • Highway modelling is not available to inform optimal crossing points and design and highway improvements to Becket St or Botley Rd - likelihood increased given no further data /resources being available, and increased potential impact given better understanding of pressures. • Delay reaching alignment on how to proceed with engagement. Public consultation remains uncertain until alignment around COMPF/rail strategy are understood . • Rail regulator does not agree parking reduction/ uncertainty how much parking would need to be re-provided – ORR are engaged at Oxfordshire Connect Programme Delivery Group. NR leading Connectivity Study update + LC17 process will require statutory consult local authorities + others on reduction | Further engagement around alignment of rail strategy and OSM publication, including dates. Further engagement also needed with COMPF team. | 0 | 0 | 0 | 0 | 51563.3
B0128 | Greenways Cycling Project | Regeneration & Economy |  | GF | 0 | 0 GF | Feasibility | Awaiting new Schedule | Medium | 0 | 0 | 92250 | 106000 | 106000 |  | 92250 |  | #VALUE! | #VALUE! | #VALUE! | -13750 | -13750 | 0 | 92250 | 92250 | 0 | Project has now completed baseline analysis and route prioritization. Next steps is on the ground surveys and finalising first 50km of routes. | 0 | Insufficient officer resource leads to project delays (now addressed by increasing capacity at City and stitching this project into wider Movement and Place Framework programme with County) Project completes without supporting delivery of schemes (should be addressed through successful scope and good clienting) | Target contract start - 8 January 2024 | 0 | 0 | 0 | 0 | 92250
B0129 | Town Hall Options | Corporate Property |  | GF | 0 | 0 GF | Idea | Off Target | Low | 0 | -6146 | 31218 | 48854 | 47201 |  | 25072 |  | #VALUE! | #VALUE! | #VALUE! | -32201 |  | -32201 | 15000 | 15000 | 0 | New Regeneration Manager (started July 2024) to progress project forward. Next steps are to: - develop PID for feasibility and viability studies (RIBA Stage 1) - develop and agree brief for feasibility and viability studies | Delays to definition of brief for feasibility and viability studies leading to slippage of forecasted spend into next financial year. | RISK 1. There are multiple planned and ongoing works in the Town Hall (Lots 1, 2 and 4). There is a risk that proposed design options do not align with these works and the investment that they have involved. MITIGATION 1: Work closely with the wider project team to understand the scope and timescales for works and raise any potential clashes / synergies with aims of future design options. Ensure the briefing information (including floorplans) provided to the consultant team for Lot 3 captures all relevant and up to date information for the building. | Develop and agree PID and brief for feasibility / viability study - February 2025 | 0 | 0 | 0 | 0 | 25072
B0132 | Coach Parking Feasibility | Regeneration & Economy |  | GF | 0 | 0 GF | Feasibility | On target | Low | 0 | 20000 | 0 | 20000 | 20000 |  | 20000 |  | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 20000 | 20000 | 0 | **Feasibility funding in place, with project having been on pause due to need to sequence with wider County strategic transport policies. Current intention between City and County officers is to progress study as part of new "Central Oxfordshire Movement & Place Framework" programme of work. Atkins consultants have now been commissioned to undertake this feasibility study. Target milestones remain TBC** | 0 | 0 | June-Aug 2024: report commissioned and started / inception date planned | 0 | 0 | 0 | 0 | 20000
B0133 | Cemetery Feasibility | Corporate Property |  | GF | 0 | 0 GF | Design & Specification | On target | Medium | 0 | 71022 | 282977.87 | 146022 | 80000 |  | 353999.87 |  | #VALUE! | #VALUE! | #VALUE! | 213999.87 | 213999.87 | 0 | 293999.87 | 293999.87 | 0 | Planning approval held up because access to field not secured by property, so archaeology and EA requested borehole ground investigations cannot be carried out. Final legal documents for VP are still with solicitors for signing. Property plan to get VP first then negotiate License with farmer, around ground investigations, for the maintenance of the land before construction works. Additional measures to ensure no adverse impact on parking available to sports clubs has been put back to them (and RFU and Sport England) with aim they can now remove their objection. Athletics Club agreeable, and Property team finalising agreements with Athletics Club, OPT, and ODS - those these latter two can only be concluded following planning approval. Landscape Officer confirmed no objection. EA Pre App advice confirmed suitability of site, but they now wanting more monitoring from boreholes. Proposed monitoring plan gone to them in April 24. Comments back received, and meeting now scheduled to agree a drainage design and monitoring plan to their satisfaction. County Highways unreasonably asking for large scale highway infrastructure of: road widening; bus stops, and pedestrian crossing from the very low traffic small burial meadow, that were not requested from the much larger adjacent sports pitches development. Good availability of reclaimed burial plots, and ODS making good progress exploring options for giving up to 3 years extra supply in existing cemeteries while property deals and planning are concluded. | Delays on planning and property work | Risk: signing agreement with farmer promptly to obtain VP and enable archaeology and borehole works and planning approval. Caused delays to programme - new programme now agreed at DB. Delays will cause extra resource and consultant cost budget pressure. Mitigations: property team prioritising finalising the terms he offered. Risk: County Highways could continue to ask for an unreasonable amount of additional highway improvements. Causing budget, and or time pressure if c278 takes a long while to agree with lawyers. Mitigations: OCC Director to meet County Budget has been included. Try to push for early agreement and drafting of 278 Risk: property negotiation progress with Athletics Club, OPT and ODS slow . Mitigation: monthly meetings to track and minute actions. Risk: ODS costing of works schedules comes in over budgetted market rates, but under 10% over and Directors require ODS to be instructed. Then budget pressure on works and resource costs and programme. Risk of gap in availability just of new (not reclaimed) burial plots from Spring 2025. Mitigations: Burial service are stretching the remaining burial space available, and there is always good reclaimed burial availability. Reactive comms agreed. ODS looking at feasibility of releasing other small areas of land in existing cemetries | Property sign agreement with farmer, and gain access to field. Oct/Nov24 | 0 | 1323000 | 420869 | 0 | 2097868.87
| Regeneration & Economy Projects Total | [8 empty] | 16034471 | 881215 | 10335685.57 | 26406447 | 21753892 |  | 27310535.57 | 13121307.73 | 266976.19 | #VALUE! | #VALUE! | -910169.78 | -294104.75 | -616065.03 | 20843722.22 | 20368507.53 | [6 empty] | 6263867 | 5652000 | 4121439 | 42758252.9
| Housing Delivery Projects | [10 empty] | 0 | [15 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
M5025 | Barton Park - Purchase by Council | Housing Delivery | David Watt | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | Off Target | Medium | 11051609.13 | 1495609 | 5222770.8 | 10311865 | 12513000 |  | 17769988.93 | 8884994.47 | 6646509.79 | 37.4% | 11123479.14 | -6668417 | -6668417 | 0 | 5844583 | 5844583 | 0 | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Remainder of in year budget removed from programme | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | 0 | 0 | 17848472.83 | 5789066.94 | 4962150.08 | 46369678.78
M5026 | Housing Company Loans (excl Barton Park) | Housing Delivery | David Watt | GF | Housing Company Loans | Housing Company Loans GF | Other Capital Spend | Off Target | High | 14051609.13 | 12040000 | -2175609 | 15059611 | 0 |  | 23916000.13 | 11958000.07 | 5599810.04 | 23.41% | 18316190.09 | 5046250 | 5046250 | 0 | 5046250 | 5046250 | 0 | The programme has been updated in Sep24 following a review of the OX Place BP. | Revised loan activity now adjusted due to updated HRA stage payments, better cash management and programme planning. | The activity of loan drawdowns is completely development led and we have experienced delays and removed the optimum bias from the programme. | 0 | Latest forecast via email suggests £8.73m slippage OCH(D)L (non-Barton) loans £17.808m | 36634000 | 20762000 | 29739609 | 111051609.13
M5032 | Barton Park - loan to OCHL | Housing Delivery | David Watt | GF | Housing Company Loans | Housing Company Loans GF | Other Capital Spend | Off Target | Medium | 0 | 1481608 | 7732771.8 | 10311865 | 12513000 |  | 9214379.8 | 4607189.9 | 0 | 0% | 9214379.8 | -6668417 | -6668417 | 0 | 5844583 | 5844583 | 0 | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Remainder of in year budget removed from programme | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. | Acquisition of social housing from next phase of development. | Latest forecast via email suggests £6.75m slippage OCH(I)L (Barton) loans | 0 | 5789066.94 | 4962150.08 | 19965596.82
M5034 | Affordable Housing Supply | Housing Delivery | Dave Scholes | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 1958000 | 0 | 128000 | 914000 | 128000 |  | 2086000 | 1043000 | 0 | 0% | 2086000 | 0 | 0 |  | 128000 | 128000 | 0 | s106 Top-up/ Enabling grant. Dec 22 Delegated decision re £650k agreed to enable a 9 unit tenure switch to SR at Barton Park - with P4P. Grant Agreement to be finalised and detailed delivery programme awaited (July 24). Sept 23 Cabinet committed the remaining £1.3m as further funding into the BBL Regen project (for phase 2) if required - to ensure viability. July 24 update - Included in Peabody modelling and assumed to be required to make the scheme stack. | Reprofiling into future years | 0 | Grant Agreement for P4P for additional affordable homes at Barton Park. | 0 | 0 | 0 | 0 | 2086000
M5035 | Growth Deal Registered Provider Payments | Housing Delivery | Dave Scholes | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | Off Target | Medium | 272000 | 781000 | -1053000 | 3341000 | 434000 |  | 0 | 0 | 0 | 0% | 0 | -434000 | -434000 |  | 0 | 0 | 0 | Passing on grant received from County. No funding from the Capital Programme. All incoming funding received (£10,530,000) is paid out to the relevant projects as 90% on SoS and 10% at PC. £3,470k paid to L&G for William Morris Court £4,340k paid to Catalyst/ Peabody for Littlemore Park. £2,720k committed to A2Dominion for Gibbs Cres, with £2,448k paid to date. | 0 | All agreements sealed. But see comment above about terminating the agreement with A2D. | Continue to manage and monitor 'stalled site' with A2D at Gibbs Crescent. £272k due at PC. There is a risk that this will not be paid, and that the £2,448k already paid will need to be clawed back (and then repaid to County). A2D are seeking replacement funding direct from Homes England (with the claim currently held pending). | 0 | 272000 | 0 | 0 | 272000
M5037 | Northern Gateway (Oxford North) | Housing Delivery | Jenny Barker | GF | Project - Development | Project - Development GF | Delivery | Off Target | High | 0 | 747538 | 405878 | 9993538 | 10000000 |  | 1153416 | 576708 | 2218.05 | 0.1923% | 1151197.95 | -8846584 | -8846584 |  | 1153416 | 1153416 | 0 | It has not been possible to agree the drawdown and spend of the HIF grant and a request has been made to Homes England to withdraw from the funding agreement. | 0 | Homes England have advised they will be seeking repayment of the funding currently held | Confirmation from Homes England re the withdrawal from the Funding agreement and confirmation that funding held is to be returned. | 0 | 0 | 0 | 0 | 1153416
| Housing Supply Projects Total | [8 empty] | 27333218.26 | 16545755 | 10260811.6 | 49931879 | 35588000 |  | 54139784.86 | 27069892.44 | 12248537.88 | 22.62% | 41891246.98 | -17571168 | -17571168 | 0 | 18016832 | 18016832 | [6 empty] | 54754472.83 | 32340133.88 | 39663909.16 | 180898300.73
| Planning Projects | [10 empty] | 0 | [15 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
T2299 | Controlled Parking Zones | Planning Services | Rachel Nixon | GF | Project - Other | Project - Other GF | Delivery | 0 | Low | 0 | 250000 | 193000 | 500000 | 53000 |  | 443000 | 221500 | 0 | 0% | 443000 | 305080 | 305080 | 0 | 358080 | 358080 | 0 | Paper presented to 7/10/24 Development Board (DB) indicating County Council is requesting the release of £358,080 to cover the review of 7 existing CPZ zones in the city. Recommendation from DB to check whether this would be a key decision and need to go to Cabinet, also to brief LU. DB also supportive of remaining funds (£84,920) being returned to the CIL pot and not re-profiled. Post DB Update - Confirmation that Cabinet decision is required - is on forward plan for December 2024. | 0 | Cabinet does not agree to release the funds. | Release of £358,080 to County Council. | 0 | 0 | 0 | 0 | 443000
F7011 | Headington Environmental Improvements | Corporate Property | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 3050 | -3050 | 33831 | 0 |  | 0 | 0 | #VALUE! | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
F7024 | St Clements Environmental Improvements | Planning Services | 0 | GF | Project - Other | Project - Other GF | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 31197 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | -31197 | -31197 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
| Planning Projects Total | [8 empty] | 0 | 253050 | 189950 | 583831 | 84197 |  | 443000 | 221500 | #VALUE! | #VALUE! | #VALUE! | 273883 | 273883 | 0 | 358080 | 358080 | [6 empty] | 0 | 0 | 0 | 443000
| Development Directorate Total | [8 empty] | 50011680.26 | 19044989 | 18976067.87 | 97497722 | 64181658 |  | 88091901.13 | 43479282.37 | 14006592.41 | 15.9% | #VALUE! | -17316960.31 | -17383642.47 | 66682.16 | 46864697.69 | 46389483 |  | 0 | 0 | 0 | 0 |  | 65496735.83 | 43448928.88 | 49100899.16 | 245548876.33
Corporate Resources
Business Improvement Projects
C3044 | ICT Software and Licences | Business Improvement | Rocco Labellarte | GF | rolling programme | rolling programme GF | Rolling Programme | 0 | Low | 245000 | 0 | 0 | 245000 | 265570 |  | 245000 | 122500 | 402356.99 | 164.2% | -157356.99 | -20570 | 0 | -20570 | 245000 | 245000 | 0 | NOT A PROJECT. NO TARGET COMPLETION THEREFORE. | 0 | 0 | Not a project | Single year licenses paid from revenue so need to consider how to change funding | 245000 | 245000 | 245000 | 980000
C3039 | ICT Infrastructure - minor costs CLOSED | Business Improvement | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
C3058 | CRM Replacement | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Design & Specification | Off Target | Medium | 0 | 655 | 47609 | 50930 | 50930 |  | 48264 | 24132 | 0 | 0% | 48264 | -2666 | -2666 | 0 | 48264 | 48264 | 0 | This project has been renamed the ASM Replacement as Lagan was replaced by ASM. requirements have been gathered. Need to sense check them with ODS before going to market. | 0 | 0 | Sense check business requirements with ODS | 0 | 0 | 0 | 0 | 48264
C3060 | End-Point Devices (Desktops/Laptops) | Business Improvement | Rocco Labellarte | GF | rolling programme | rolling programme GF | Rolling Programme | Completed | N/A | 150000 | 24022 | 180344.83 | 50930 | 300676 |  | 354366.83 | 177183.42 | 41913.81 | 11.83% | 312453.02 | 53690.83 | 53690.83 | 0 | 354366.83 | 354366.83 | 0 | 0 | 0 | 0 | Closed | 0 | 150000 | 150000 | 150000 | 804366.83
C3062 | Datacentre Upgrade |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50930 | 0 |  | 0 | 0 | -8940 | #DIV/0! | 8940 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
C3066 | Telephony Device Refresh | Business Improvement | Rocco Labellarte | GF | rolling programme | rolling programme GF | Rolling Programme | On target | Low | 60000 | -16987 | -9322.57 | 50930 | 88334 |  | 32570.43 | 16845.22 | 30411.79 | 93.37% | 2158.64 | -54643.57 | -54643.57 | 0 | 33690.43 | 33690.43 | 0 | Not a project. Funding for device replacements as needed. | 0 | 0 | Not a project. Funding for device replacements as needed. NO TARGET COMPLETION THEREFORE. | 0 | 60000 | 60000 | 60000 | 212570.43
C3068 | Windows 2008 Server Replacement | Business Improvement | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 18270 | -18270 | 50930 | 0 |  | 120 | 0 | -2841 | -2368% | 2961 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 120
C3070 | Business Process Automation Full Rollout | Business Improvement | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 50930 | 0 |  | 0 | 0 | -15667 | #DIV/0! | 15667 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
C3072 | Forms Engine Replacement | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Completed | Off Target | High | 0 | 87108 | -87108 | 50930 | 9038 |  | 0 | 0 | -22597 | #DIV/0! | 22597 | -9038 |  | -9038 | 0 | 0 | 0 | Project is closed. Residual capital of £642. | 0 | No risks noted. | Implementing waste forms. | 0 | 0 | 0 | 0 | 0
C3077 | Info@Work Enterprise Upgrade Rollout | Business Improvement | 0 | GF | Project - ICT | Project - ICT GF | 0 | 0 | 0 | 0 | 0 | 0 | 50930 | 0 |  | 1000 | 0 | 0 | 0% | 1000 | 1000 | 1000 | 0 | 1000 | 1000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 1000
C3082 | Website Redesign | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Closed | On target | Low | 0 | 0 | 3106.25 | 50930 | 85350 |  | 3106.25 | 1553.13 | 627 | 20.19% | 2479.25 | -82243.75 | -82243.75 | 0 | 3106.25 | 3106.25 | 0 | Website has gone live (phase 1) | 0 | 0 | Complete migration of pages (pahse 2) | 0 | 0 | 0 | 0 | 3106.25
C3083 | FOI System | Business Improvement | Grace Wigham | GF | Project - ICT | Project - ICT GF | Completed | On target | Low | 0 | 0 | 0 | 50930 | 0 |  | 0 | 0 | 31500 | n/a | -31500 | 0 | 0 | 0 | 0 | 0 | 0 | All key users have now been trained. System went live on 26/06/2023. Webform and disclosure log have gone live. The decision has been made to publish FOIs which are deemed to have some public interest. | 0 | 0 | Contract to begin 31/03/2023 | will need to be a budget bid as not enough funds to cover ongoing costs! | 0 | 0 | 0 | 0
C3084 | Agresso Update | Business Improvement | Sonal Khade | GF | Project - ICT | Project - ICT GF | Delivery | On target | Low | 0 | 0 | 0 | 50930 | 92202 |  | 0 | 0 | 6167 | n/a | -6167 | -92202 | -92202 | 0 | 0 | 0 | 0 | Project Team and Board have now been formed and project has started | 0 | Working with Project team to complete Cycle 3 of UAT | Cycle 3 UAT- 24th December | 0 | 0 | 0 | 0 | 0
C3085 | ICT - I-trent replacement | Business Improvement | Gail Malkin | GF | Project - ICT | Project - ICT GF | 0 | 0 | N/A | 0 | 0 | 0 | 50930 | 75000 |  | 0 | 0 | 0 | 0% | 0 | -75000 | -75000 | 0 | 0 | 0 | 0 | Current plan is to extend contract to 31.03.28. Current contract is to 31.03.25. We are not in a good position to specify our exact needs. We need to improve use of current system and be clear about business needs before starting a procurement exercise. We are currently investing to improve processes and application. | Project delayed | 0 | 0 | 0 | 20000 | 55000 | 0 | 75000
C3086 | ICT - QL Exploitation Programme | Business Improvement | Alison Cornacchia | GF | Project - ICT | Project - ICT GF | Delivery | At Risk | Medium | 256000 | 0 | -25344.12 | 50930 | 605000 |  | 230655.88 | 115327.94 | 212746.5 | 92.24% | 17909.38 | -219500 | -219500 | 0 | 385500 | 385500 | 0 | Versaa Forms - PEEP Form (Pilot) : Technical issues have been resolved. The OCC and ODS Versaa environments have been rebuilt and all environments have been successfully upgraded. Versaa Forms - Tenancy Services : The off-the-shelf Tenancy Services product issues have also been resolved. The handover of the product was completed at the end of September. Predictive Arrears (MARS) : The MARS solution has been successfully implemented. Notice has been issued to Mobysoft, who are currently progressing the off-boarding process. OCC has completed it's decommissioning tasks. Sub-Account & Former Arrears Solution : Requirements have been agreed, development completed and test cycle 1 completed. Housing Needs System Solution - Work has now started on the ITT Supplier Contract. Contractor Portal : Requirements have been gathered and process maps developed | Although the forecast reflects an overspend, it is mitigated by the N7072 being under budget. Collectively the 2 budgets will reflect an underspend due to slippage on some elements of the programme. | - Budget forecast predicts this project will be over budget by the end of the financial year. This is mitigated by N7072 being under budget (all expenditure has been captured in the primary capital budget. - The adoption of the new solution is being facilitated through engagement with Business Areas, with a prioritized focus on key areas. - Resource and capacity management are crucial for handling the volume of work activities, which are continuously being prioritised. - Unforseen delays are introduced due to timescales involved in investigating and resolving technically complex issues involving multiple 3rd Party Suppliers. | Versaa Forms - PEEP Form (Pilot) - Complete UAT (Oct 24) - Pre Go-Live Activities (Oct 24) - Soft Launch (Pilot Users) (Nov 24) Versaa Forms - Tenancy Services - Product and process familiarisation (Oct 24) - Testing Phase (Nov 24) | 0 | 78000 | 78000 | 78000 | 464655.88
C3087 | ICT - replacing Netcall contact centre telephony and resource management system | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | 0 | 0 | Low | 0 | 0 | 29468.62 | 50930 | 75000 |  | 29468.62 | 14734.31 | 34283.92 | 116.3% | -4815.3 | -45531.38 | -45531.38 | 0 | 29468.62 | 29468.62 | 0 | Project concludes in November 2024 | 0 | Demand on ICT resources is high and whilst the business requirements have been identified, we are struggling with a higher-than-usual BAU demand, to provide resource and focus to moving this project forwards. | Publish RFQ - August 2024 | 0 | 0 | 0 | 0 | 29468.62
C3088 | ICT - replacing Uniform (building control and planning) | Business Improvement | Lan Nguyen | GF | Project - ICT | Project - ICT GF | Rolling Programme | On target | Medium | 100000 | 0 | 0 | 50930 | 0 |  | 100000 | 50000 | 0 | 0% | 100000 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | This project is about replacing the Uniform information management system and related EDMS (unsupported) for a modern cloud-based solution. Current contract runs out end of March 2026 and coincides with decomissioning of on-prem hosting of current solution. Project is currently at a pre-procurement stage (phase 2). The Invitation to Tender is being written with a specification identified by consultants from feedback from the Council's Uniform users. This is being reviewed with input from the project board (ICT, Procurement, Finance, Legal, Data Governance, Planning and Regulatory Services). The related contract has also been drafted by legal, which is also being reviewed by the Project Board. When the ITT and contract have been completed, the procurement process can commence (Target November 24) Project resources (time, budget, team) for the full migration in phase 3 are uncertain at present and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the level of resourcing required for the next stage. | Full costs of the solution, including resourcing and costs of migration to be identified in the procurement phase of the project and will depend on which supplier is chosen. See forecast spend for annual contract costs anticipated - current annual costs of contract and hosting to be redirected when new contract is planned to start (March 26). | The ITT and contract are being written to best protect the council's interests and ensure that suppliers will be able to deliver the required solution for the project. Project resources (time, budget, team) for the full solution and migration in phase 3 are uncertain and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the full level of resourcing required for the next stage. | Target November 24: ITT and contract to be sent out | 0 | 0 | 0 | 0 | 100000
C3089 | ICT - Asset Management System | Business Improvement | Ted Bowler | GF | Project - ICT | Project - ICT GF | Design & Specification | On target | Low | 318662 | 0 | -37324 | 50930 | 300000 |  | 281338 | 129848.3 | 12500 | 4.443% | 268838 | -150000 | -150000 | 0 | 150000 | 150000 | 0 | A scoping document has been issued to a long list of suppliers, the returns will be reviewed and from this a short list of suppliers will be selected and invited to tender for the contract. | Due to the project timeline we will only just be starting system implementation during the current financial year. | The project timeline is very tight and only minor delays will impact on the overall project timeline. Fortnightly project board meetings and weekly meetings with our external consultant are in place to ensure that the chance of any delays are kept to a minimum. | Agree and draft the specification to be used for Tender process. Late July - August 2024. | 0 | 300000 | 0 | 0 | 581338
C3090 | ICT - Extension of existing Alemba case managmenet system | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Closed | Off Target | Low | 0 | 0 | 4004 | 50930 | 20000 |  | 4004 | 2002 | 0 | 0% | 4004 | -15996 | -15996 | 0 | 4004 | 4004 | 0 | Alemba system has been set up for use by the People Team. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4004
C3091 | ICT - scanning of all paper planning files | Business Improvement | Nathan Breeze | GF | Project - ICT | Project - ICT GF | Feasibility | Awaiting new Schedule | Medium | 0 | 0 | 150000 | 50930 | 150000 |  | 150000 | 75000 | 10092 | 6.728% | 139908 | -90000 | -90000 | 0 | 60000 | 60000 | 0 | BUDGET NOTE: It is currently understood that any budget not spent in this financial year 24/25 (forecast at £90k) will be folded into the 25/26 Town Hall Lot 2 budget (B0157) to contribute towards the overall costs of the scanning project, which will come out of this budget (B0157). The overall costs of the scanning project will be estimated and taken to Cabinet for approval in January 2025. The majority of the spend is likely to take place in the 25/26 financial year. PROJECT UPDATE: Two main options for a scanning project are being considered: - Option 1 - A business case for digitising the Councils archive was prepared in June 2024. It recommended an internal auditing / cataloguing process of files stored to be carried out by each Service area to set the requirements and specification for a digitisation project by a third-party supplier. - Option 2 - Following the recommendations of the Fire Risk assessment, an alternative option has been explored which accelerates the removal of files from the Town Hall Basement. In this option a third-party supplier removes and catalogues the files stored. This catalogue could then be used to set the requirements and specification for a digitisation project by a third-party supplier. - An update report was provided to the Town Hall Project Board 03.10.24 with a detailed comparison of estimate programmes and costs (internal and external) between the two options. - Option 1 is the recommended approach to the Scanning Project. The next step will be to speak to Heads of Services with files in the Town Hall Basement and refine the estimated internal resource needed to undertake the project. Following this the aim is to submit an updated Business Case to OCB 26.11.24 for approval to take to cabinet in January 2025. Horspath Road File relocation Files stored at Horspath Road were relocated 15/10/24 to allow the building to be converted for alternative use. These are now stored in the Town Hall Flat, whilst the planning for the overall digitisation project is progressed. | Delays to the start of the scanning project whilst most suitable route is defined, leading to forecasted spend being moved into next financial year | RISK 1 - Fire risk of ongoing storage of combustible (paper-based) material in the town hall basement MITIGATION 1 - Limited and controlled access to Town Hall Basement Area. Prioritise removal / relocation of material in escape routes. Progressing Scanning Project will lead to removal of significant number of files from the Town Hall Basement. RISK 2 - Potential breach of legal requirements for retention of and access to archive material. MITIGATION 2 - Clarification of Records Retention and Disposal Schedule as well as public access requirements. Identification of documents that need to be retained will be part of initial part of the project. | Relocate Files from Horspath Road to Town Hall - October 2024 | 0 | 0 | 0 | 0 | 150000
C3092 | ICT - Replacement of IKEN - L&G case management system | Business Improvement | Amanda Ball | GF | Project - ICT | Project - ICT GF | Delivery | Awaiting new Schedule | N/A | 0 | 0 | 67500 | 50930 | 75000 |  | 67500 | 33750 | 35125 | 52.04% | 32375 | -7500 | -7500 | 0 | 67500 | 67500 | 0 | Implementation programme has been delayed because access for testers to MS365 is not yet available. Iken have suspended implementation pending confirmation from OCC of a workable solution. | 0 | Delay causing risk of delay to Council's transition to cloud-based Outlook application | Agreement of contract with Hable - 31 Jan 2024 | 0 | 0 | 0 | 0 | 67500
C3093 | ICT - Replacement of ArcGIS geospatial mapping system | Business Improvement | David Butler | GF | Project - ICT | Project - ICT GF | Closed | On target | N/A | 0 | 0 | 25000 | 50930 | 25000 |  | 25000 | 12500 | 0 | 0% | 25000 | 0 | 0 | 0 | 25000 | 25000 | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
C3094 | ICT - Information @ Work major upgrade | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Other Capital Spend | 0 | 0 | 3000 | 0 | 15000 | 50930 | 15000 |  | 18000 | 9000 | 0 | 0% | 18000 | 3000 | 3000 | 0 | 18000 | 18000 | 0 | PO Signed in September. Go live in October. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
C3095 | ICT - Redesign of Council Website | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Closed | On target | N/A | 0 | 0 | 51658 | 50930 | 100000 |  | 51658 | 25829 | 627 | 1.214% | 51031 | -48342 | -48342 | 0 | 51658 | 51658 | 0 | Completed in May 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51658
C3096 | ICT - Open Revenue Cloud Migration | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | 0 | 0 | 0 | 50000 | 0 | 0 | 50930 | 0 |  | 50000 | 25000 | 0 | 0% | 50000 | 50000 | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
C3097 | ICT - Refresh of content and taxonomy of the Council Website | Business Improvement | Tom Jennings | GF | Project - ICT | Project - ICT GF | Delivery | On target | 0 | 25000 | 0 | 21150 | 50930 | 25000 |  | 46150 | 23075 | 1500 | 3.25% | 44650 | 21150 | 21150 | 0 | 46150 | 46150 | 0 | A project plan for 'phase two' is in place, which will see us systematically improve each area of the council's website. A pilot project has been carried out with the council tax team, which is due to complete in the next couple of weeks. We will then move on to improve the recycling and jobs sections of the website. Meanwhile, a website working group has been established to bring together content, digital, customer and citizen teams to work on the website improvements. Terms of reference have been drawn up and will be brought to OCB in October for approval. | 0 | Risk that the website improvements end when the current additional resource is removed in November 2024, without having completed the process of optimising all high usage areas of the website for customer self-service. Mitigation: permanent increase in resourcing of web content management. October update: ICT is extending the resource until March 2025. A budget bid has been submitted to create a permanent resource from 2025/26. | Draft project plan for phase two of website | 0 | 0 | 0 | 0 | 46150
C3088 | ICT - replacing Uniform (building control and planning) | Business Improvement | Lan Nguyen | GF | Project - ICT | Project - ICT GF | Rolling Programme | On target | Medium | 100000 | 0 | 0 | 50930 | 0 |  | 100000 | 50000 | 0 | 0% | 100000 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | This project is about replacing the Uniform information management system and related EDMS (unsupported) for a modern cloud-based solution. Current contract runs out end of March 2026 and coincides with decomissioning of on-prem hosting of current solution. Project is currently at a pre-procurement stage (phase 2). The Invitation to Tender is being written with a specification identified by consultants from feedback from the Council's Uniform users. This is being reviewed with input from the project board (ICT, Procurement, Finance, Legal, Data Governance, Planning and Regulatory Services). The related contract has also been drafted by legal, which is also being reviewed by the Project Board. When the ITT and contract have been completed, the procurement process can commence (Target November 24) Project resources (time, budget, team) for the full migration in phase 3 are uncertain at present and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the level of resourcing required for the next stage. | Full costs of the solution, including resourcing and costs of migration to be identified in the procurement phase of the project and will depend on which supplier is chosen. See forecast spend for annual contract costs anticipated - current annual costs of contract and hosting to be redirected when new contract is planned to start (March 26). | The ITT and contract are being written to best protect the council's interests and ensure that suppliers will be able to deliver the required solution for the project. Project resources (time, budget, team) for the full solution and migration in phase 3 are uncertain and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the full level of resourcing required for the next stage. | Target November 24: ITT and contract to be sent out | 0 | 0 | 0 | 0 | 100000
C3098 | ICT - Agresso upgrade and migration to Cloud | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Closed | Completed | 0 | 0 | 0 | 193219.6 | 50930 | 350000 |  | 193219.6 | 96609.8 | 0 | 0% | 193219.6 | -156780.4 | -156780.4 | 0 | 193219.6 | 193219.6 | 0 | Project has gone live | 0 | 0 | Post implementation intensive care | 0 | 0 | 0 | 0 | 193219.6
C6000 | ICT - feasibility | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | 0 | 0 | 0 | 0 | 0 | 180000 | 50930 | 180000 |  | 180000 | 90000 | 0 | 0% | 180000 | 0 | 0 | 0 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
C3081 | Capitalised ICT Projects | Business Improvement | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Idea | Awaiting new Schedule | N/A | 163200 | 0 | 452445.87 | 386600 | 386600 |  | 615645.87 | 307822.94 | 522005.21 | 84.79% | 93640.66 | 229045.87 | 229045.87 | 0 | 615645.87 | 615645.87 | 0 |  |  |  |  | 0 | 163200 | 0 | 0 | 778845.87
| Business Improvement Projects Total | [8 empty] | 1470862 | 113068 | 1243137.48 | 2006710 | 3273700 |  | 2827067.48 | 1402713.06 | 1291811.22 | 45.69% | 1535256.26 | -512126.4 | -482518.4 | -29608 | 2761573.6 | 2761573.6 | [6 empty] | 1016200 | 588000 | 533000 | 4964267.48
Financial Services Projects
M5023 | OxWED Loans | Financial Services | n/a | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | On target | Low | 3750000 | 0 | -2725000 | 0 | 0 |  | 1025000 | 512500 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | £325k loan payment approved in 2023/24 due to extended programme. Potential further release will be in future years subject to final business case. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025000
B0144 | Salary Costs across the Council to be capitalised | Financial Services | 0 | GF | Other Capital Spend | Other Capital Spend GF | Other Capital Spend | 0 | 0 | 380000 | 0 | 1380591 | 480000 | 1203380 |  | 1760591 | 880295.5 | 0 | 0% | 1760591 | 557211 | 557211 | 0 | 1760591 | 1760591 | 0 | 0 | 0 | 0 | 0 | 0 | 663000 | 663040 | 663040 | 3749671
C3067 | Paris Payment System, Replacement / PCI DSS | Financial Services | 0 | GF | Project - ICT | Project - ICT GF | 0 | 0 | 0 | 0 | 98304 | -98304 | 98304 | 0 |  | 0 | 0 | #VALUE! | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
C3078 | Revs and Bens System Replacement | Financial Services | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 7622 | -7622 | 7622 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | 81489 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
C3080 | Telephony Contract Replacement | Financial Services | Rocco Labellarte | GF | Project - ICT | Project - ICT GF | Delivery | Off Target | Medium | 0 | 41675 | -41675 | 41675 | 31963 |  | 0 | 0 | 0 | 0% | 0 | -31963 | -31963 | 0 | 0 | 0 | 0 | Additional requirements being processed via Procurement in March. In the region of £25k additional spend. PO raised in early May. Go live at end of October. | 0 | ODS to join the pilot test in June. | Go Live / End of August, early September | 0 | 0 | 0 | 0 | 0
| Financial Services Projects Total | [8 empty] | 4130000 | 147601 | -1492010 | 627601 | 1235343 |  | 2785591 | 1392795.5 | #VALUE! | -2.925% | #VALUE! | 525248 | 525248 | 0 | 1760591 | 1760591 |  |  | #N/A | #N/A | #N/A | #N/A | 663000 | 663040 | 663040 | 4774671
Law & Governance
L1000 | Audio & Visual Equipment | Law & Governance | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 110000 | -97218 | 110000 | 8887 |  | 12782 | 6391 | 0 | 0% | 12782 | 0 | 0 | 0 | 8887 | 8887 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | 12782
| Law & Governance Projects Total | [8 empty] | 0 | 110000 | -97218 | 110000 | 8887 |  | 12782 | 6391 | 0 | 0% | 12782 | 0 | 0 | 0 | 8887 | 8887 | [6 empty] | 0 | 0 | 0 | 12782
| Corporate Resources Directorate Total | [8 empty] | 5600862 | 370669 | -346090.52 | 2744311 | 4517930 |  | 5625440.48 | 2801899.56 | #VALUE! | 21.52% | #VALUE! | 13121.6 | 42729.6 | -29608 | 4531051.6 | 4531051.6 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 1679200 | 1251040 | 1196040 | 9751720.48
Chief Executive
| Environmental Sustainability Projects | [26 empty] | 0 | 0 | 0
E3558 | Go Ultra Low Oxford - On Street | Environmental Sustainability | Vikki Robins | GF | Project - Other | Project - Other GF | Design & Specification | Awaiting new Schedule | Medium | 0 | 18620 | 476086.03 | 518620 | 501750 |  | 494706.03 | 247353.01 | 0 | 0% | 494706.03 | -501750 | -501750 | 0 | 0 | 0 | 0 | >September 2024 - Agreement still not issued by County. Escalated to 151 Officer and Head of Corp Servs. This needs to be in place before the LEVI tender is published - planned end October 24 August 2024 - draft of agreement due from County but no date given for this yet. LEVI work taking priority for all Oxon Councils as tender due for this by September 2024. June 2024 - meetings taking place in June with County for the reimbursement method of the allocated funding as well as the transfer of the GULO assets to County control. May 2024 - no new progress, project remains paused. - City are seeking reimbursement of investment through revenue share, which has been agreed in principle >Project Paused- County is seeking full integration of GULO P2 into LEVI, with all new onstreet contracts entered into by County highways. Permission to enter into a back-to-back agreement now received from Funder (OZEV) .City are seeking reimbursement of investment through revenue share, which has been agreed in principle. Ongoing delays on LEVI timeline, GULO timelines likely to shift significantly backwards, to early 2025. | 0 | OGP2ZR005 - Agreement with County not signed by end October for the GULO funds transfer. Mitigation - Escalate and if still no progress consider using the funds outside LEVI for alternative A/C charging in car parks. OGP2ZR004 - Substantial delay to GULO Infrastructure delivery in Oxford. County officers have stated intention to withdraw permission for city to take GULO forward on the highway, and demand full integration of GULO into LEVI under County contract ownership. Onstreet delivery timelines for LEVI are currently set to early 2025. Mitigation: Officers are seeking urgent confirmation on proposed GULO timelines, with the aim of securing a 2024 delivery. | Agreement on City to County transition - updated deadline Jul 2024 | 0 | 0 | 0 | 0 | 494706.03
E3557 | Oxford and Abingdon Flood Alleviation Scheme | Environmental Sustainability | Emma Gubbins | GF | 0 | 0 GF | Other Capital Spend | On target | High | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | Have now entered into the Option Agreement. legal are providing advice and draft notices on the land which requires advertising prior to disposal (open space) Terms agreed for the disposal of the fields adjacent to Redbridge Hollow - Fisher German have confirmed values look reasonable. EA have provided HOTs but they confirm Council will need to provide VP - this doesn't reflect the agreement so have asked EA to confirm. | 0 | Risk 1. Project Risks- Gaining Planning permission and CPO Inquiry Mitigation for these is being managed by the EA (OCC support on Project Board and Sponsoring Group) Risk 2. OCC Risk- overlap of OFAS with OCC plans for Seacourt and Redbridge P&R's Mitigation - Open dialogue & sharing of information and timetables for OFAS and OCC plans for Seacourt & Redbridge P&R. Risk 3. Originally, OCC agreed a contribution of kind of up to £1m, including internal staff resource as a key stakeholder/contribution to the project 4-5 years ago. The length of time the project has taken and changes in staff, alongside post covid impacts on Legal and Property resource meant there was insufficient internal staff resources to do this work. This has been resolved with a dedicated external Property Services contractor, Richard Waple, as Lead Officer and an external Legal Services contractor, Ian Goldsmith. Professional Fees have started to be reimbursed by the EA. To date, all of OCC's Professional Fees have been reimbursed to the end of November 2022. OCC remains a committed partner to the scheme. | Agreement of Option Agreement September 2023. Planning permission late 2023. CPO to be confirmed December 2024. - complete | 0 | 250000 | 0 | 0 | 250000
E3560 | Go Ultra Low Oxford - Taxis | Environmental Sustainability | Vikki Robins | GF | Project - Other | Project - Other GF | Delivery | Off Target | Low | 0 | 137491 | -99164.44 | 137491 | 40076 |  | 38326.56 | 19163.28 | 19015 | 49.61% | 19311.56 | -1749.44 | -1749.44 | 0 | 38326.56 | 38326.56 | 0 | update 1-10-24. Legal have now assigned someone to look at the leases. Supplier engagement for sign off will commence once we have the completed leases. Project delivery complete but close out still in progress.. Some minor transition items outstanding (as build-drawings, full lease signatures). | N/A | September 24 - Lease signing due before the end of October. Once completed, this project can be closed down as all deliverables will be completed. Leases for some sites off street sites to be finalised and signed by both parties. Nilesh and Sue progressing with legal during September Final invoice paid to Blink Charging (formerly EB Charging). As built drawings sent over for all sites. O&M documentation sent over- to be reviewed. | Transition & handover sign-off | 0 | 0 | 0 | 0 | 38326.56
E3563 | Clean Bus Technology Grants | Environmental Sustainability | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 174060 | -174060 | 174060 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
E3565 | Decarbonisation Fund - OCC element | Environmental Sustainability | Luca Minetola | GF | Project - Development | Project - Development GF | Completed | At Risk | High | 0 | 905617 | -800474.65 | 905617 | 120268 |  | 105142.35 | 52571.18 | 0 | 0% | 105142.35 | -15125.65 | -15125.65 | 0 | 105142.35 | 105142.35 | 0 | 1. Hinksey's completion date 27 with Practical Completion. issued 10 February 2023 by F&G due to outsanding documents. 2. Two trees completed still monitoring the health of the trees. 3. Salix Audit oustanding. To start after final account. 4. Pool Cover works outstanding completed on the 18 of January 2023. 5. Indipendant inspection for the pool cover complete. 6. Barton L Centre PHX to be send for testing by specilialst on the meturlugy of the heat exchanger. | 0 | Claim from WD on Barton Leisure Centre PHX damage due to what they allege as high levels of chlorine. Mitigation - OCC has sent the PHX | 1. Commmissioning complete 2. Pool Cover Cover works completion and indipendant inspection of safety issues. May include security. Complete 3. Report from Inspector complete and submitted to OCC from reveiw. | 0 | 0 | 0 | 0 | 105142.35
B0127 | ZEZ Phase 1 Feasibility | Environmental Sustainability | Mai Jarvis | GF | Project - Development | Project - Development GF | Idea | Awaiting new Schedule | Medium | 0 | 141000 | 0 | 141000 | 141000 |  | 141000 | 70500 | 3840 | 2.723% | 137160 | -141000 | -141000 | 0 | 0 | 0 | 0 | Phase 1 complete and terms agreed on revenue share for phase 1 - legal agreement progressing. Phase 2 - Project on hold, but likely to un-pause soon, awaiting decision on City Council role in project. | 0 | Risk around ZEZ pilot being enforced while there is significant delay to the ZEZ and stakeholders in Pilot area likely to be vocal about the impacts on the | Complete legal agreement with County re. Phase 1 revenue share | 0 | 0 | 0 | 0 | 141000
E3567 | Town Hall Lighting Upgrade (SALIX) | Environmental Sustainability | 0 | GF | 0 | 0 GF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | #VALUE! | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
E3568 | Leisure Centre LED Lighting Feasibility | Environmental Sustainability | David Oldham | GF | Project - Development | Project - Development GF | Completed | Completed | High | 0 | 0 | 6430 | 0 | 33000 |  | 6430 | 3215 | 21264 | 330.7% | -14834 | -29160 | -29160 | 0 | 3840 | 3840 | 0 | The survey drawing work completed. We are waiting on access to the Technician at Serco to populate the type and lux of light fittings surveyed. | Managed a better deal - £2590 less than budgeted | The lighting data sheets have been sufficiently completed to fufill the requirements but not as full as initially hoped. The site support was not sufficient to do this due to ongoing commitments. It was not possible to extend the project further | All visits completed except with Technician at Serco | 0 | 0 | 0 | 0 | 6430
| Environmental Sustainability Projects Total | [8 empty] | 0 | 1376788 | -591183.06 | 1876788 | 836094 |  | 785604.94 | 392802.47 | #VALUE! | #VALUE! | #VALUE! | -688785.09 | -688785.09 | 0 | 147308.91 | 147308.91 | [6 empty] | 250000 | 0 | 0 | 252572.35
| Chief Executive Total | [8 empty] | 0 | 1376788 | -591183.06 | 1876788 | 836094 |  | 785604.94 | 392802.47 | #VALUE! | #VALUE! | #VALUE! | -688785.09 | -688785.09 | 0 | 147308.91 | 147308.91 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 252572.35
| General Fund Total | [8 empty] | 67279071.26 | 22539198 | 14887811.16 | 118292553 | 82530809 |  | 104765244.42 | 46673984.4 | 18268211.42 | 17.44% | #VALUE! | -20929137.27 | -20809032.12 | -120105.11 | 61978457.21 | 61131425.52 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 78206193.83 | 49321906.88 | 54511939.16 | 285432663.03
[11 empty] | 28695 | [16 empty] | #VALUE! | #VALUE! | #VALUE!
Housing Revenue Account Capital Programme | [27 empty] | 0 | 0 | 0
HRA - Property Services Schemes | [27 empty] | 0 | 0 | 0
N6384 | Tower Blocks | HRA | Luca Minetola | HRA | Project - Development | Project - Development HRA | Design & Specification | On target | N/A | 1000000 | 883642 | -1623255.02 | 883642 | 731469.77 |  | 260386.98 | 130193.49 | 6630.02 | 2.546% | 253756.96 | -471082.79 | -471082.79 | 0 | 260386.98 | 260386.98 | 0 | Negotiations in progress - slip 1.3M to 25/26 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 1560386.98
N6385 | Adaptations for disabled | HRA | Luca Minetola | HRA | Other Capital Spend | Other Capital Spend HRA | Rolling Programme | On target | Low | 800000 | 0 | 0.05 | 1156000 | 1200000 |  | 800000.05 | 389360.02 | 812853.47 | 101.6% | -12853.42 | -399999.95 | -399999.95 | 0 | 800000.05 | 800000.05 | 0 | ODS budget demand led - 168K remaining at end of Feb | 0 | 0 | 0 | 0 | 750000 | 650000 | 650000 | 2850000.05
N6386 | Structural | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Medium | 2000000 | 283008 | -95253.72 | 2716474.62 | 2000000 |  | 2187754.28 | 713877.14 | 42418.58 | 1.939% | 2145335.7 | 187754.28 | 187754.28 | 0 | 2187754.28 | 2187754.28 | 0 | "Concrete works Work completed to 1 scheme, ongoing for 3 others and still to start at last. General subsidence and cracking. On demand budget - Update on 29/08 POs raised to the Sum of £137,112.50 for Phase 1, 10 properites completed to RIBA stage 2. Cabnet report in process for 1 Million spend" | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 2000000 | 8187754.28
N6387 | Controlled Entry | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 100000 | 11522 | 206469.14 | 294522 | 300000 |  | 317991.14 | 148995.57 | 3351.79 | 1.054% | 314639.35 | -200000 | -200000 | 0 | 100000 | 100000 | 0 | Survey being completed in this year. First reports due back (priority blocks) week ending 11th Oct | 0 | 0 | 0 | 0 | 333000 | 75000 | 75000 | 800991.14
N6388 | Major Voids | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Medium | 1000000 | -72350 | 72349.56 | 614650 | 700000 |  | 999999.56 | 499999.78 | 732142.12 | 73.21% | 267857.44 | 300000 | 300000 | 0 | 1000000 | 1000000 | 0 | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. This is also a delegated budget to ODS. Demand led. Orders for a number of major voids have recently been placed. | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 3999999.56
N6389 | Damp-proof works (K&B) | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Medium | 0 | 3883 | 39831.02 | 122883 | 500000 |  | 43714.02 | 21857.01 | 0 | 0% | 43714.02 | -456285.98 | -456285.98 | 0 | 43714.02 | 43714.02 | 0 | "A rolling programme where repairs are done as they come in. There has been an increase in the number of damp issues during autumn and winter months. Work needs to be done to identify persistent issues to make installations planned rather than re-active" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43714.02
N6390 | Kitchens & Bathrooms | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | 0 | 0 | 0 | 0 | 0 | 1300000 | 1673681 |  | 0 | 0 | 0 | 0% | 0 | -1423681 | -1423681 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N7057 | Kitchens | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | 0 | 0 | 32475 | -32475.2 | 673514 | 0 |  | -0.2 | -0.1 | 0 | 0% | -0.2 | 0 | 0 | 0 | 0 | 0 | 0 | "These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. 13 Complete June 23 expected 104" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2
N7058 | Bathrooms | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 0 | -31949 | 31948.92 | 425782 | 0 |  | -0.08 | -0.04 | 0 | 0% | -0.08 | 0 | 0 | 0 | 0 | 0 | 0 | Capital programme budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.08
N6391 | Heating | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | N/A | 0 | 0 | 0 | 1893675 | 2500710 |  | 0 | 0 | 745992 | n/a | -745992 | -2393000 | 0 | 0 | 107710 | 107710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N7031 | Homes at Barton | HRA | 0 | HRA | Rolling Programme | Rolling Programme HRA | 0 | 0 | 0 | 0 | -238332 | 238332 | 1893675 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
N7059 | Boilers Only | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 500000 | -56439 | 882036.87 | 759648 | 0 |  | 1164404.87 | 662798.94 | 264296.95 | 22.7% | 900107.92 | 0 | 0 | 0 | 0 | 0 | 0 | This is a demand led budget and is part of the ongoing Decent homes and compliance work required by OCC as a landlord. 75 complete YTD 130 Predicted year end. Projected £1,500,000k spend does not include CO which needs to be added in. No slippage reported yet | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 2664404.87
N7060 | Heating Systems | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 500000 | -458325 | 505438.06 | 0 | 0.44 |  | 708306.06 | 273556.53 | -134164.96 | -18.94% | 842471.02 | -0.44 | -0.44 |  | 0 | 0 | 0 | This is delegated budget to ODS and is part of the Decent Homes works | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 2208306.06
N6392 | Roofing | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | N/A | 0 | -238332 | 429082.66 | 725189 | 700000 |  | 190750.66 | 95375.33 | 0 | 0% | 190750.66 | -509249.34 | -509249.34 | 0 | 190750.66 | 190750.66 | 0 | orders placed and 26 properties and properties still to be validated for remaining budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190750.66
N6395 | Electrics | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | N/A | 2000000 | -21701 | -30375.13 | 1292474 | 1062326 |  | 1947923.87 | 1052361.93 | 300478.46 | 15.43% | 1647445.41 | 885597.87 | 885597.87 | 0 | 1947923.87 | 1947923.87 | 0 | Delegated budget to ODS and is on target to deliver. We have agreed to fund 165 properties | 0 | 0 | 0 | 0 | 2000000 | 700000 | 500000 | 5147923.87
N6434 | Doors and Windows | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | 0 | 0 | -105913 | 105913.49 | 507087 | 691000 |  | 0.49 | 0.25 | 0 | 0% | 0.49 | -690999.51 | -690999.51 | 0 | 0.49 | 0.49 | 0 | Nationwide are still completing properties from last years programme and have had access issues. A programme of works for this year has been identified and submitted for Nationwide to price. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49
N7020 | Extensions & Major Adaptions | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | 0 | 0 | 1000000 | 370892 | 556494.93 | 1105892 | 400000 |  | 1927386.93 | 763693.47 | 189314.57 | 9.822% | 1738072.36 | 75265.95 | 75265.95 | 0 | 475265.95 | 475265.95 | 0 | Commented as per each single project | 0 | 0 | 0 | 0 | 700000 | 700000 | 700000 | 4027386.93
N7026 | Communal Areas | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 0 | 29884 | -29883.67 | 731773 | 831135.99 |  | 0.33 | 0.17 | 6533.1 | 1979727% | -6532.77 | -102644.66 | -102644.66 | 0 | 728491.33 | 728491.33 | 0 | Capital programme budget | Demand led budget | 0 | 0 | 0 | 0 | 0 | 0 | 0.33
N7033 | Energy Efficiency Initiatives | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Delivery | Off Target | Low | 7450000 | 90915 | -666490.35 | 2075915 | 3938000 |  | 6874424.65 | 3526612.32 | 120865.01 | 1.758% | 6753559.64 | 2643510.21 | 2643510.21 | 0 | 6581510.21 | 6581510.21 | 0 | Broken down into specific projects | 0 | 0 | 0 | 0 | 12750000 | 2325000 | 2325000 | 24274424.65
N7044 | Lift Replacement Programme | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | At Risk | Medium | 100000 | 123713 | -120281.03 | 373899 | 494968.34 |  | 103431.97 | 1715.98 | 34345.14 | 33.21% | 69086.83 | -344968.34 | -344968.34 | 0 | 150000 | 150000 | 0 | No further significant lifts replacments for this current year but planning 25/26 - Large number of stair lift replacments expected | 0 | Awaiting procurement of Lift consultant to develop upodated replacement program | 0 | 0 | 550000 | 150000 | 150000 | 953431.97
N7048 | Fire doors | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 1500000 | 228615 | 1842562.4 | 2337594 | 900000 |  | 3571177.4 | 1590588.7 | 42766.86 | 1.198% | 3528410.54 | 500000 | 500000 | 0 | 1400000 | 3000000 | 0 | Awaiting ODS to submit costs for five blocks - Then need quotes for QS to review | Contract approval and resource. | Re-focusing on high risk buildings as per BSR requirements, project being priced | 0 | Procurement of blocks done in stages and delaying work | 1500000 | 1500000 | 1500000 | 8071177.4
N7067 | Renewal Of Fire Alarm Panels | HRA | Luca Minetola | HRA | Project - Compliance | Project - Compliance HRA | Rolling Programme | On target | Medium | 60000 | 0 | 147021 | 102000 | 176802 |  | 207021 | 103510.5 | 0 | 0% | 207021 | 30219 | 30219 | 0 | 207021 | 207021 | 0 | Alarm and detection system at Headley House completed (June 2023), next site to be identified and procured. | 0 | Completion of this project affects Fire safety, thus important to maintain progress | 0 | 0 | 60000 | 75000 | 60000 | 402021
N7052 | HRA Stock Condition Survey | HRA | Luca Minetola | HRA | Project - Other | Project - Other HRA | Delivery | On target | N/A | 400000 | 138753 | 189819.9 | 333753 | 185000 |  | 728572.9 | 297606.45 | 109947.18 | 15.09% | 618625.72 | 543572.9 | 543572.9 | 0 | 728572.9 | 728572.9 | 0 | 4,118/7,888 (52.2%) of HRA dwellings surveyed | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 928572.9
N7032 | Great Estates Programme | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | On target | Low | 0 | 352817 | -352817.03 | 1588254 | 1212381.51 |  | -0.03 | -0.01 | 0 | 0% | -0.03 | -1206201.51 | -1206201.51 | 0 | 6180 | 6180 | 0 | Move 400K to FRA programme and put 500k reserve for bin store project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03
N7071 | Fencing | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | 0 | On target | Low | 0 |  |  |  | 400000 |  | 250855.63 | 125427.82 | 0 | 0% | 250855.63 | -149144.37 | -149144.37 | 0 | 250855.63 | 250855.63 | 0 | Demand led/ lower demand than previous years. | Lower demand than expected | 0 | 0 | 0 | 0 | 0 | 0 | 250855.63
N7072 | QL Improvements | HRA | Alison Cornacchia | HRA | Project - Other | Project - Other HRA | Delivery | 0 | 0 | 0 |  |  |  | 0 |  | 245000 | 122500 | 0 | 0% | 245000 | 245000 | 245000 | 0 | 245000 | 245000 | 0 | Please see QL Exploitation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245000
N7073 | Southfield Park Leases | HRA | Bill Graves | HRA | Other Capital Spend | Other Capital Spend HRA | Delivery | At Risk | Low | 0 |  |  |  | 1500000 |  | 1500000 | 750000 | 0 | 0% | 1500000 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | Alex Miller (Corporate Assets) has made contact with Lincoln College regarding the proposal. Lincoln College have, in turn, contacted their solicitor and valuer to get initial input but are awaiting their response before having a conversation with us. | 0 | The key risk is that the valuation of the lease extension under the statutory process is higher than the budget envelope of £1.5m. The other risk is that Lincoln College may wish to decline informal discussions however there is a statutory process that we can fall back on as mitigation if necessary. The appointment of JLL (Real Estate & Property Consultancy) has to advise on valuation and negotiation has also provided assurance that best value will be obtained. | JLL providing valuation report - TBC | 0 | 0 | 0 | 0 | 1500000
N7074 | Oxford North Develpment | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Delivery | On target | Low | 13538505 |  |  |  | 8356000 |  | 14695162.27 | 7347581.13 | 1017088.88 | 6.921% | 13678073.39 | -2891869 | -2891869 | 0 | 5464131 | 5464131 | 0 | Cabinet approvals secured in March 2023. Moving to contract signing SoS achieved (June 23) | 0 | The scheme has planning and the obligations of this will be picked up by Hill through the contract. However, appropriate due diligence will be done. s73 submitted in May 24 for 2 extra flats in the podium area of blocks 6&7. Scheme is in contract and on-site although query over the housing trajectory which does not align with the development agreement. Issue has been noted with careful monitoring on site. Reprofiling took place in April to move all units from 24/25 to 25/26 Technical risks will be the responsibility of Hill through the contract. Due diligence on going. Energy strategy negotiations taking place throughout first half of 2024 | Monitor site progress and staged payments | 0 | 8114472 | 1525090 | 1283000 | 25617724.27
N7075 | LAHF Acquisitions | HRA | Andy Dorrington | HRA | Other Capital Spend | Other Capital Spend HRA | Completed | Completed | Low | 0 |  |  |  | 2330320 |  | 312704.34 | 156352.17 | -4426.18 | -1.415% | 317130.52 | -2017615.66 | -2017615.66 | 0 | 312704.34 | 312704.34 | 0 | 7 of 7 properties purchased, void completed and let. | 0 | Budget- overall budget allows for property purchase, associated costs & void works although final void costs confirmed once work is completed. Market price fluctuations - all properties either purchased or in conveyancing Sales fall through - accepted risk, OCC are cash buyers but cannot avoid chain sales Underspend - there may be budget left over following property purchases | Purchase of remaining 2 properties by 30/11/23 - complete | 0 | 0 | 0 | 0 | 312704.34
N7076 | Major Voids – Kitchens and Bathrooms | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 499999.96 | 249999.98 | 74609.77 |  | 425390.19 | 499999.96 | 499999.96 | 0 | 499999.96 | 499999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.96
N7077 | Climate Change |  | Luca Minetola |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update will be shared as of next month | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 8000000
N7042 | Barton Regeneration | HRA | Luca Minetola | HRA | Rolling Programme | Rolling Programme HRA | Rolling Programme | 0 | 0 | 0 | 18150 | 580210.3 | 618150 | 601494.59 |  | 598360.3 | 299180.15 | 21264 | 3.554% | 577096.3 | -3134.29 | -3134.29 | 0 | 598360.3 | 598360.3 | 0 | Agreed works completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598360.3
N7070 | Major Refurbishment Masons Road | HRA | Luca Minetola | HRA | Project - Development | Project - Development HRA | Delivery | On target | Medium | 0 | 0 | 586178.52 | 750000 | 815557.14 |  | 586178.52 | 293089.26 | 42418.58 | 7.236% | 543759.94 | -229378.62 | -229378.62 | 0 | 586178.52 | 586178.52 | 0 | Orders have been placed with ODS and 3 properties remaining to be done with 4 underway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586178.52
HRA - Housing Supply Schemes
N7047 | Social Rented Housing Acquisitions | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Completed | On target | Low | 0 | 317918 | -317917.84 | 817918 | 2834236 |  | 0.16 | 0.08 | 97920.27 | 61200169% | -97920.11 | -2834235.84 | 0 | -2834235.84 | 0.16 | 0.16 | 0 | ODS void works from 20/21 to end 22/23 capitalised/ charged into this budget - so all reconciled to April 23. The £23k retention from the Abbey Homes acquisition (45 homes) is also due to be paid in 23/24 from this budget, after defects work is completed and certified. (Jan 24 update - Awaiting confirmation of completed defects work before payment.) 2023/24 programme: Target: 9 acquisitions. Year End: 11 homes. | Budget to be reset by finance and closed at end of 2023/24 year. No longer to be used. | RETIRING THIS COST CENTRE FROM END 2023/24 | Settlement of all final ODS works costs for 23/24 acquisitions asap - but will go past year end. | 0 | 0 | 0 | 0 | 0.16
N7051 | Acquisition of Additional Units | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Completed | Completed | Low | 3000000 | 25318 | -3025318 | 2050318 | 2466000 |  | 0 | -1500000 | 0 | 0% | 0 | -2466000 | 0 | -2466000 | 0 | 0 | 0 | Acquisition of 9 units (off-plan) - Only £25k retention left in budget as required. | 0 | Construction issues mitigated by the employment of a Council clerk of works to regularly inspections and reports on issues and progress to the PM in the construction phase. | Payment of final retention sum (£25k) in Qtr 2 22/23 - To be actioned (Oct 22) | 0 | 0 | 0 | 0 | 0
N7050 | East Oxford development | HRA | Dave Scholes | HRA | Project - Development | Project - Development HRA | Delivery | Off Target | Medium | 6793288 | 607060 | 237310.5 | 3420060 | 3522000 |  | 7637658.5 | 422185.25 | 1445103.57 | 18.92% | 6192554.93 | 2815353 | 2815353 | 0 | 6337353 | 6337353 | 0 | Planning consent (Ctte Jan 21). Conditions being met. Working with Arcadis to develop a delivery programme. Sept 21 - Agt on route to market (separate to community centre refurb) - Housing Devt now being mobilised. Jan 22 - Build contract tenders issued. Plan to award in Feb 22. ODS undertaking demolition of all sites May to July 22, then site handover to residential. SOS Q3 2022/23, completion Q4 2023/24 (tbc - after tenders assessed). Jun 23 - Mobilising for SoS Tender results were poor - going back out to market again. Cost risk, although consultants believe that the expected budget envelope should still be sufficient (Mar 22). Impact on SoS expected to delay from Jan 23 to Mar 23. Professional Services costs paid by General Fund and will be apportioned over into HRA at year end by Finance. Oct 22 - Tenders from open tender assessed (inc financial due diligence) and contract award decision made (Dec 22). To now reset budget and programme following this. End Dec update - Contract now with Legal - expect to sign/ seal in Feb 23. Jan 23 - Homes England have confirmed that grant application is now approved. Oct 23 - Demolitions Complete. Having to move to 2nd tenderer - contract discussions underway and targeting contract signing in Nov 23 for SoS in early 2024. Contract with Life Build now signed and mobilising for SoS in March 24. Technical SoS achieved in Mar 24. Collins Street - Build progressing well - Above foundation (Jul 24). Princes Street - LifeBuild unable to access site for main works due to ODS on EOCC site adjacent - meetings to try to resolve. Lifebuild may have to delay build start to Sept 24 - likely cost implications being assessed. DSA to sign (OCHL to OCC) Mar 23-Jul 24 | 0 | Princes St works on site delayed due to access, levels issues, so will incur additional costs and time. 23wk delay as currently expecting to SOS 23 Sept'24. Significant issues re construction management plan and delay to Princes Street SOS ODS on target for completion of CC timber frame by 20th Sept, which will enable Lifebuild to SOS at Princes Street on 23rd. Difficult tight sites to develop, co-ordination required with community centre main contractor on Princes Street. Solutions to the levels and drainage issues in shared footpath between both developments have been reached, but need to be be approved. Finance: Delays to SOS at Princes and potential impact of level issue will incur loss & expense claim, therefore increased build costs and programme delay. Planning: No issues identified re conditions, except condition 4 at Collins Street. Looking like Collins will be finished before the Community Centre (CC), so Collins completed units may need to remain vacant until CC reaches PC - this has been taken up with Planners. Both projects now scheduled for completion Sept 25. | Princes Street site - Resolving issues for Life Build to start and assessing additional cost liability (HRA & GF) as a result. Report expected to escalate to Devt Board/ CMT following EOCC Project Board meeting on 19th July 24. | 0 | 264385 | 0 | 0 | 6601738
N7055 | Use Of Recycled Capital Grants | HRA | 0 | HRA | 0 | 0 HRA | 0 | 0 | 0 | 0 | 27737 | -27737 | 27737 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0
N7054 | Properties Purchased From OCHL | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Other Capital Spend | On target | Medium | 83684822 | -1467427 | -58305652.61 | 41731891 | 25688743 |  | 23911742.39 | 11955871.19 | 7943686.37 | 33.22% | 15968056.02 | 0 | 0 | 0 | 25688743 | 25688743 | 0 | The June 24 appraisals show a significant increase in OX Place costs, but most of these increases have not been passed onto the HRA. The HRA appraisals show c. £14m more possible spend. Most significant is a c. £16m increase in costs (and numbers of units) at R/B, but Sandy Lane Rec has seen a £2m decrease. For the purpose of this monitoring however, the current (Feb 24) MTFP budget is used, so the spend forecasts at Redbridge have been decreased proportionately in each year to reduce the overall budget forecasts by £14m. There are high levels of spend certainty with 3 (of 10) schemes, comprising c.17% of the overall budget, that are in delivery or expected to be soon, and where delivery risks are low. These schemes comprise of 100% of the spend forecast in 24/25 and 75% of the forecast in 25/26, so slippage in these two years is expected to be minimal. 3 of the schemes are targeting planning committee approval in the next 4 months. 3 already have consent and one is awaiting the s.106 only. The remaining 3 schemes are the largest schemes in the programme - all forecast in the later years of the programme with £222m spend (62% of this budget). There has been considerable slippage in programme dates with many now revised. The larger schemes are now forecast to run to 2031/32. | Slippage of some schemes in programme into later years | Developing more rigour to the business plan re capital spends | Collaboration Agreement and associated documents, esp Development Agreements and Delivery Strategy (per scheme); plus Payment Schedules to be developed and agreed. | Slippage figure to tie in with Dave W email 27 July 2023 | 42139726 | 46264902 | 39787056 | 152103426.39
N7061 | Northfield Hostel | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Design & Specification | Off Target | Medium | 9524123 | 1734116 | 10741524.48 | 1947000 | 1261000 |  | 21999763.48 | 10999881.74 | 1239045.19 | 5.632% | 20760718.29 | 4437890 | 4437890 | 0 | 5698890 | 5698890 | 0 | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission to be made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Now confirmed as in Year 4 OGD. Requires land sale; build contract signing; & planning consent by end March 22. Due to go to Plg Ctte on 9th March. Other critical path work (land and build contract) to follow in March. 15 Mar 22 - Approved at Plg Ctte. s.106 being finalised now. End March - s.106 agreed and land sale being progressed. June 22 - Re-tender using OCHL Framework to secure best price. Land now acquired from County. Sept 22 - tenders back and being assessed. Oct 22 - PSCA expected late Nov 22 Nov 22 - Budget to be reviewed in Dec 22/Jan 23 once more price certainty is secured. Currently forecasting a TSC (exc interest) of £19.65m (if a £16m build cost can be achieved). This would give a budget pressure of £3,250k, but the scheme would still meet HRA financial parameters and the higher Abovo costs have been tested in the draft HRA BP preparation (Nov 22). New budget to go to March 23 Cabinet and then Council. PCSA due to be issued March 23. Homes England bid by end March 23 also. June 23 - PCSA sealed and work underway. Demolition Aug 23. Main contract SoS Dec 23. HE Grant issue - looking to purchase adjacent County site to over come this. Reports into HSB and Devt Board (June 23) and cabinet report for Aug 23. Sale by County Cabinet agreed end Sept 23. Oxford City full Council agreement budget in Oct 23. Solicitors instructed and sale expected to complete late Oct/ Nov 23. Jan 24 - decision not to award build contract and to re-tender. Above reversed and Equans to be appointed. Feb- July 24 Price and contract negotiations with Equans. Demolition works underway. | 0 | Pre-Planning application and consultation used to mitigate planning risk. Tender for build contract re-run through new OCHL framework (Lot2). Risk to delivery completing by Homes England deadline/ Need to secure funding from the HE AHP programme. Legal risk: Contract issue over liability levels. Complexity about process to include other site. | Build tender result, then revised cost schedule and programme to be confirmed. To establish whether we have sufficient price certainty (and limited risk) re costings, as to whether to submit a Homes England AHP funding bid in early Jan 23. Early March 23 - PCSA to be signed Jun 23 - Sealed! Now PCSA work (to complete in Feb 24). Demolition contract to be let - to SoS for demolition phase May 24 - targeting demolition completion July 24. DSA to sign (OCHL to OCC) Jul 24 HE grant claim. | 0 | 10153801 | 701464 | 0 | 32855028.48
N7062 | Lanham Way | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Delivery | On target | Low | 3185122 | 813030 | 2713701.38 | 4368030 | 2800000 |  | 6711853.38 | 3355926.69 | 1952169.75 | 29.09% | 4759683.63 | 1336012 | 1336012 | 0 | 4136012 | 4136012 | 0 | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Planning issues being resolved with architects and across teams. Mar 22 - Significant redesign required to reduce number of units. Sept 22 - Planning consent secured (at committee) for 10 homes. Conditions and s.106 pending Nov 22 - Build Contract tender out (on framework) - Due back Jan 23 Jan 23 - Tender back - being assessed. (Feb 23) s106 drafted and ready to sign Jun 23 - Land purchased. Build contract to be signed imminently. Final legals to build contract. Possible slight delay to SoS due to ecology (translocation window) Build contract signed and SoS achieved in Dec 23. DSA to sign (OCHL to OCC) Mar 24 - Jul 24 | 0 | Build issues - Site Meetings and EA engaged Contractor has undertaken detailed technical risk analysis with none identified to date - contingency in budget After acquisition scheme will be private highway for OCC to maintain - adequate provisions in place Remove or minimise any provisional sums re finance - robust programme tracking | Tracking progress through site meetings and programme tracking | 0 | 1103548 | 0 | 0 | 7815401.38
N7068 | Juniper | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Closed | Awaiting new Schedule | High | 0 | -51170 | -1149601 | 1586000 | 385229 |  | 385229 | 192614.5 | 0 | 0% | 385229 | -385229 | 0 | -385229 | 0 | 385229 | 0 | Now Juniper only - 2 units (with ODS). Tucker is being progressed by OCHL. Thomson was dropped in favour of a land deal to support the Railway Lane devt with OCHL/ Cantay. Still pending a proposal and cost from ODS (likely for one unit only now due to ground constraints). PROPOSE TO CLOSE THIS PROJECT AS UNVIABLE (and reallocate funding to support the Northfield scheme budget pressure through the 23/24 final budget process) | 0 | Requires planning submission and works programme. | Awaiting financial appraisal and programme. Issue concerning ground conditions pending (re statutory services running through the site). | 0 | 0 | 0 | 0 | 385229
N7066 | Next Steps Accommodation Programme | HRA | Dave Scholes | HRA | Other Capital Spend | Other Capital Spend HRA | Completed | Completed | Low | 0 | 710783 | -129036.88 | 710783 | 581746 |  | 581746.12 | 290873.06 | 0 | 0% | 581746.12 | 0.12 | 0.12 | 0 | 581746.12 | 581746.12 | 0 | Buying 5 one bed flats for rough sleepers in a Housing First model. Completed on 3 in March 21 (Q4) and remaining two will be in April 21 (Q1 21/22). 5 NSAP units completed. A new bid to buy 10 further units in 21/22 made in April 2021, and award of funding confirmed (June 21) - team mobilising and contacting agents. Sept 21 - 1st unit completed. Oct 21 - Additional grant ask from MHCLG (to replace £550k that was to be funded from OGD) now under consideration/ sign-off. Jan 22 - 4 RSAP units completed. Last 6 properties in conveyancing and expect to complete by end March 2022. 15th Mar 22 - Initial 8 completions (cost c. £1,540k plus min £50k refurb costs). 9 units now completed (9th one was today - £175k). 10th (last) home expected to complete on 28/3/22 (£135k). SDLT exempt. End Mar 22 - All 10 RSAP properties now purchased and void works are underway with ODS. First 2 tranches of grant per dwelling claimed. Now awaiting PC. July 2022 - All works now complete - Homes are lettable and are let. | 0 | None | Expect void works spend to be capitalised into this project - Value TBC. Project can then close. Expect a £500k underspend | 0 | 0 | 0 | 0 | 581746.12
N7040 | Blackbird Leys Regeneration (HRA) | HRA | Karoline Soisalo De Mendonca | HRA | Project - Development | Project - Development HRA | Delivery | On target | Medium | 1504000 | -63379 | 912696.52 | 425071 | 1625977 |  | 2353317.52 | 644844.36 | 1343998.75 | 57.11% | 1009318.77 | 727340.52 | 727340.52 | 0 | 2353317.52 | 2353317.52 | 0 | PHASE 1 UPDATE: - S278 still sits with County for approval/agreement. Street lighting design pending, but County has agreed to sign without technical approval for lighting. - Badger Issue: new badger sett built, now ecologist to check that badgers have gone to the new sett. This will de-risk the Knights Rd site development significantly. - Delays in going through safety gateway new Building Act for tall buildings. Issues in trying to get a case manager assigned, over 12 weeks delayed and ongoing. HIF: -Last HIF claim in August LEGAL: - Budget for internal capital charges set - JO, BM and KSM discussed legal works for Phase 2 should be c. £50k, with £30k uplift in case of CPO -JO to lead on procurement for legal consultants using framework PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. COMMS: - Comms ongoing, with Peabody consultants leading - Community Centre events and comms ongoing and led by TbD | 0 | - S278: this is a risk to delay in programme and S278 works SoS. Signing of S278 is said to be imminent. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2, strategy to be agreed. Delay risk as Ph 2 may need a new planning application. - Comms & Engagement: Still a risk. Need to send out comms especially to update on site works and conditions. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024. | Signing of S278: 'imminent' (?) End of August | 0 | 172000 | 172000 | 172000 | 2869317.52
0
| Housing Revenue Account Total | [8 empty] | 139639860 | 3998914 | -44887172.78 | 82361253.62 | 75365777.78 |  | 104302818.42 | 45978430.81 | 18450649.24 | 17.69% | #VALUE! | -3947204.49 | 4131260.35 | -5685464.84 | 71418573.29 | 73403802.29 | [6 empty] | 69542500 | 56723900 | 78214000 | 305573569.94
| Grand Total | [8 empty] | 206918931.26 | 26538112 | -29999361.62 | 200653806.62 | 157896586.78 |  | 209068062.84 | 92652415.21 | 36718860.66 | 17.56% | #VALUE! | -24876341.76 | -16677771.77 | -5805569.95 | 133397030.5 | 134535227.81 | [6 empty] | 153599731 | 133717242 | 116539061 | 612924096.84
-4061622.74
[18 empty] | % Latest Budget |  | % Original Budget | [5 empty] | 0 | #DIV/0!
[16 empty] | General Fund Spend v Budget |  | 17.44% |  | 27.15% | [5 empty] | 0
[13 empty] | 184605824.62 |  |  | HRA Spend v Budget |  | 17.69% |  | 13.21% | [5 empty] | 0
[16 empty] | Total Spend v Budget |  | 17.56% |  | 17.75%
[10 empty] | 192867322.13 | -13325640.62 |  |  |  |  | 185152062.71
Note on L201: jmarriott: Includes -£350k correction re duplicated slippage
Note on L209: jmarriott: Includes -£400k correction re duplicated slippage
Note on V167: jmarriott: £5k spend per Mai update 03/02/21

## Cfwd (hidden)
A4845 | Y021 | OX-1003643 | 10583 | 2021/22 Final Capital Slippage | 0 | -10583
A4852 | Y021 | OX-1003643 | 60450 | 2021/22 Final Capital Slippage | 23000 | -37450
A4853 | Y021 | OX-1003643 | 12500 | 2021/22 Final Capital Slippage | 31569.16 | 19069.16
B0081 | Y021 | OX-1003643 | -517 | 2021/22 Final Capital Slippage | 3081.05 | 3598.05
B0083 | Y021 | OX-1003643 | -2115 | 2021/22 Final Capital Slippage | -62276.73 | -60161.73
B0086 | Y021 | OX-1003643 | 137846 | 2021/22 Final Capital Slippage | 0 | -137846
B0092 | Y021 | OX-1003643 | -14902 | 2021/22 Final Capital Slippage | 178638.47 | 193540.47
B0096 | Y021 | OX-1003643 | -412655 | 2021/22 Final Capital Slippage | 63135.84 | 475790.84
B0098 | Y021 | OX-1003643 | -339924 | 2021/22 Final Capital Slippage | 166732.7 | 506656.7
B0100 | Y021 | OX-1003643 | 241916 | 2021/22 Final Capital Slippage | 70730.14 | -171185.86
B0101 | Y021 | OX-1003643 | 28863 | 2021/22 Final Capital Slippage | 395.36 | -28467.64
B0102 | Y021 | OX-1003643 | 43294 | 2021/22 Final Capital Slippage | 119484 | 76190
B0104 | Y021 | OX-1003643 | 20451 | 2021/22 Final Capital Slippage | 770635.67 | 750184.67
B0106 | Y021 | OX-1003643 | 131406 | 2021/22 Final Capital Slippage | 163057.67 | 31651.67
B0108 | Y021 | OX-1003643 | 99217 | 2021/22 Final Capital Slippage | 0 | -99217
B0111 | Y021 | OX-1003643 | 12110 | 2021/22 Final Capital Slippage | 0 | -12110
B0112 | Y021 | OX-1003643 | 35406 | 2021/22 Final Capital Slippage | -205651.15 | -241057.15
B0114 | Y021 | OX-1003643 | 4119 | 2021/22 Final Capital Slippage | 9935.5 | 5816.5
B0115 | Y021 | OX-1003643 | 3095 | 2021/22 Final Capital Slippage | 0 | -3095
B0116 | Y021 | OX-1003643 | 18914 | 2021/22 Final Capital Slippage | 1398635.13 | 1379721.13
B0118 | Y021 | OX-1003643 | 10047 | 2021/22 Final Capital Slippage | 36704 | 26657
B0119 | Y021 | OX-1003643 | 83363 | 2021/22 Final Capital Slippage | 51563.3 | -31799.7
B0120 | Y021 | OX-1003643 | 75949 | 2021/22 Final Capital Slippage | 96329.26 | 20380.26
B0122 | Y021 | OX-1003643 | 118102 | 2021/22 Final Capital Slippage | 431332.3 | 313230.3
B0126 | Y021 | OX-1003643 | 120000 | 2021/22 Final Capital Slippage | 300000 | 180000
B0127 | Y021 | OX-1003643 | 141000 | 2021/22 Final Capital Slippage | 141000 | 0
B0129 | Y021 | OX-1003643 | -6146 | 2021/22 Final Capital Slippage | 166273 | 172419
B0130 | Y021 | OX-1003643 | 150000 | 2021/22 Final Capital Slippage | 43350 | -106650
B0131 | Y021 | OX-1003643 | 281496 | 2021/22 Final Capital Slippage | 1722 | -279774
B0132 | Y021 | OX-1003643 | 20000 | 2021/22 Final Capital Slippage | 10000 | -10000
B0133 | Y021 | OX-1003643 | 71022 | 2021/22 Final Capital Slippage | 214682.87 | 143660.87
B0134 | Y021 | OX-1003643 | 20000 | 2021/22 Final Capital Slippage | 0 | -20000
B0136 | Y021 | OX-1003643 | 73648 | 2021/22 Final Capital Slippage | 0 | -73648
B0138 | Y021 | OX-1003643 | 698610 | 2021/22 Final Capital Slippage | 638576.39 | -60033.61
B0139 | Y021 | OX-1003643 | 37965 | 2021/22 Final Capital Slippage | 0 | -37965
B0141 | Y021 | OX-1003643 | 18277 | 2021/22 Final Capital Slippage | 61047.3 | 42770.3
C3058 | Y021 | OX-1003643 | 655 | 2021/22 Final Capital Slippage | 48264 | 47609
C3060 | Y021 | OX-1003643 | 24022 | 2021/22 Final Capital Slippage | 204366.83 | 180344.83
C3066 | Y021 | OX-1003643 | -16987 | 2021/22 Final Capital Slippage | -26309.57 | -9322.57
C3067 | Y021 | OX-1003643 | 98304 | 2021/22 Final Capital Slippage | 0 | -98304
C3068 | Y021 | OX-1003643 | 18270 | 2021/22 Final Capital Slippage | 0 | -18270
C3072 | Y021 | OX-1003643 | 87108 | 2021/22 Final Capital Slippage | 0 | -87108
C3078 | Y021 | OX-1003643 | 7622 | 2021/22 Final Capital Slippage | 0 | -7622
C3079 | Y021 | OX-1003643 | 5600 | 2021/22 Final Capital Slippage | 0 | -5600
C3080 | Y021 | OX-1003643 | 41675 | 2021/22 Final Capital Slippage | 0 | -41675
E3511 | Y021 | OX-1003643 | 5015 | 2021/22 Final Capital Slippage | 22107.97 | 17092.97
E3521 | Y021 | OX-1003643 | -21452 | 2021/22 Final Capital Slippage | 353748.55 | 375200.55
E3558 | Y021 | OX-1003643 | 18620 | 2021/22 Final Capital Slippage | 494706.03 | 476086.03
E3560 | Y021 | OX-1003643 | 137491 | 2021/22 Final Capital Slippage | 38326.56 | -99164.44
E3563 | Y021 | OX-1003643 | 174060 | 2021/22 Final Capital Slippage | 0 | -174060
E3565 | Y021 | OX-1003643 | 905617 | 2021/22 Final Capital Slippage | 105142.35 | -800474.65
F7011 | Y021 | OX-1003643 | 3050 | 2021/22 Final Capital Slippage | 0 | -3050
L1000 | Y000 | OX-1003643 | 110000 | 2021/22 Final Capital Slippage | 12782 | -97218
M5025 | Y021 | OX-1003643 | 1495609 | 2021/22 Final Capital Slippage | 3362379.8 | 1866770.8
M5026 | Y021 | OX-1003643 | 12040000 | 2021/22 Final Capital Slippage | 7708000 | -4332000
M5032 | Y021 | OX-1003643 | 1481608 | 2021/22 Final Capital Slippage | 2036379.8 | 554771.8
M5033 | Y021 | OX-1003643 | 205663 | 2021/22 Final Capital Slippage | 6553772.05 | 6348109.05
M5035 | Y021 | OX-1003643 | 781000 | 2021/22 Final Capital Slippage | 0 | -781000
M5037 | Y021 | OX-1003643 | 747538 | 2021/22 Final Capital Slippage | 1153416 | 405878
M5038 | Y021 | OX-1003643 | -500 | 2021/22 Final Capital Slippage | 95556.35 | 96056.35
R0005 | Y021 | OX-1003643 | 1558482 | 2021/22 Final Capital Slippage | 405675.19 | -1152806.81
T2273 | Y021 | OX-1003643 | 406433 | 2021/22 Final Capital Slippage | 88691.54 | -317741.46
T2299 | Y021 | OX-1003643 | 250000 | 2021/22 Final Capital Slippage | 57000 | -193000
|  |  | 22567893 | 0 | 27637688.68 | 5069795.68

## Planner Data 141024 (hidden)
Full-Year & FUTURE BUDGET | [11 empty] | YTD BUDGET
Costc | Costc(T) | Original/Capital Y0 | Vire-SY | Approved Budget | Amount | Variance | CAPY1 | CAPY2 | CAPY3 | Total Budget | Check | Costc | Costc(T) | Original/Capital Y0 | Vire-SY | Approved Budget | Amount | Variance |  | Costc | Costc(T) | Original/Capital Y0 | Vire-SY | Approved Budget | Amount
A4820 | Upgrade Existing Tennis Courts | 0 | 108190.83 | 108190.83 | 2568.62 | -105622.21 | 0 | 0 | 0 | 108190.83 | 0 | A4820 | Upgrade Existing Tennis Courts | 0 | 54095.41 | 54095.41 | 2568.62 | -51526.79 | 0 | A4820 | Upgrade Existing Tennis Courts | 32081 | 202728.59 | 234809.59 | 149618.15
A4847 | Rose Hill Community Centre - Parking Management | 0 | 10000 | 10000 | 0 | -10000 | 0 | 0 | 0 | 10000 | 0 | A4847 | Rose Hill Community Centre - Parking Management | 0 | 5000 | 5000 | 0 | -5000 | 0 | A4847 | Rose Hill Community Centre - Parking Management | 0 | 9166 | 9166 | 0
A4852 | Bodycams for Community Safety Team | 0 | 23000 | 23000 | 22977.5 | -22.5 | 0 | 0 | 0 | 23000 | 0 | A4852 | Bodycams for Community Safety Team | 0 | 11500 | 11500 | 22977.5 | 11477.5 | 0 | A4852 | Bodycams for Community Safety Team | 0 | 55408.47 | 55408.47 | 0
A4853 | City Wide Cycling Infrastructure Contribution | 60000 | -4646.84 | 114517.16 | 12395 | -42958.16 | 114517 | 0 | 0 | 229034.16 | 0 | A4853 | City Wide Cycling Infrastructure Contribution | 30000 | -2323.42 | 27676.58 | 15282 | -12394.58 | 0 | A4853 | City Wide Cycling Infrastructure Contribution | 80162.17 | -16000.04 | 64162.13 | 84081.82
A4855 | Leys Youth Hub | 0 | 1071594.07 | 1071594.07 | 36957.85 | -1034636.22 | 0 | 0 | 0 | 1071594.07 | 0 | A4855 | Leys Youth Hub | 0 | 535797.04 | 535797.04 | 77320.35 | -458476.69 | 0 | A4855 | Leys Youth Hub | 0 | 54925.32 | 54925.32 | 33671
A4856 | Conversion of stored water system to mains at Cutteslowe Lower Pavillion | 130000 | 0 | 130000 | 0 | -130000 | 0 | 0 | 0 | 130000 | 0 | A4856 | Conversion of stored water system to mains at Cutteslowe Lower Pavillion | 65000 | 0 | 65000 | 0 | -65000 | 0 | B0031 | Planned Building Improvements | 687450 | 0 | 687450 | 226882.92
A4857 | Leisure infrastucture life cycle investment (dilaps) | 0 | 840000 | 840000 | 84419.55 | -755580.45 | 560000 | 0 | 0 | 1400000 | 0 | A4857 | Leisure infrastucture life cycle investment (dilaps) | 0 | 420000 | 420000 | 168668 | -251332 | 0 | B0074 | R & D Feasibility Fund | 366640 | 40164.71 | 406804.71 | 0
A4858 | Leisure Invest to Save - Leisure Contract | 2400000 | 640000 | 3040000 | 0 | -3040000 | 0 | 0 | 0 | 3040000 | 0 | A4858 | Leisure Invest to Save - Leisure Contract | 1200000 | 320000 | 1520000 | 0 | -1520000 | 0 | B0075 | Stage 2 Museum of Oxford Development | 0 | 0 | 0 | 68664.36
A4859 | Leisure Centre Capital Works & Replacements | 200000 | 0 | 200000 | 8650 | -191350 | 200000 | 200000 | 0 | 600000 | 0 | A4859 | Leisure Centre Capital Works & Replacements | 100000 | 0 | 100000 | 8650 | -91350 | 0 | B0081 | Car Parking Oxpens | 0 | 2824.09 | 2824.09 | 0
A4860 | Community Centres Capital Works & Replacements | 430000 | -430000 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | A4860 | Community Centres Capital Works & Replacements | 215000 | -215000 | 0 | 0 | 0 | 0 | B0083 | East Oxford Community Centre | 3716848.75 | -3166863.92 | 549984.83 | 588547.06
A4861 | Hinksey Splash | 18385 | 61615 | 80000 | 0 | -80000 | 200000 | 0 | 0 | 280000 | 0 | A4861 | Hinksey Splash | 9192.5 | 30807.5 | 40000 | 0 | -40000 | 0 | B0086 | Seacourt Park & Ride Extension | 0 | 0 | 0 | 4665.05
B0031 | Planned Building Improvements | 750000 | -248017.69 | 501982.31 | -13277.85 | -515260.16 | 1250000 | 750000 | 750000 | 3251982.31 | 0 | B0031 | Planned Building Improvements | 375000 | -124008.85 | 250991.15 | 11719.75 | -239271.4 | 0 | B0092 | Cave Street Development (Standingford House) | 4487256.55 | -4303936.28 | 183320.27 | 26498.81
B0033 | Community Centres | 0 | 0 | 0 | 3042.03 | 3042.03 | 0 | 0 | 0 | 0 | 0 | B0033 | Community Centres | 0 | 0 | 0 | 3042.03 | 3042.03 | 0 | B0096 | Bullingdon Community Centre | 0 | 47475.74 | 47475.74 | -1900.36
B0074 | R & D Feasibility Fund | 500000 | -37185 | 462815 | 0 | -462815 | 500000 | 200000 | 0 | 1162815 | 0 | B0074 | R & D Feasibility Fund | 250000 | -34400.19 | 215599.81 | 0 | -215599.81 | 0 | B0098 | 1-3 George Street | 0 | 345825.96 | 345825.96 | 242990.04
B0075 | Stage 2 Museum of Oxford Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0075 | Stage 2 Museum of Oxford Development | 0 | 0 | 0 | 0 | 0 | 0 | B0100 | Gloucester Green Car Park (H&S) | 0 | 65106.23 | 65106.23 | 499.06
B0081 | Car Parking Oxpens | 0 | 0.05 | 0.05 | 0 | -0.05 | 0 | 0 | 0 | 0.05 | 0 | B0081 | Car Parking Oxpens | 0 | 0.03 | 0.03 | 0 | -0.03 | 0 | B0101 | Capital works at Covered Market | 0 | 6605.16 | 6605.16 | 6839.73
B0083 | East Oxford Community Centre | 4223967 | -723966.73 | 3500000.27 | 366047.76 | -3133952.51 | 2124657 | 0 | 0 | 5624657.27 | 0 | B0083 | East Oxford Community Centre | 2111983.5 | -361983.37 | 1750000.13 | 1379582.93 | -370417.2 | 0 | B0102 | Replace or refurbish Lifts | 109519.03 | 0 | 109519.03 | 0
B0084 | Jericho Community Centre | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000 | 0 | B0084 | Jericho Community Centre | 0 | 0 | 0 | 0 | 0 | 0 | B0104 | Old Gas Works Bridges | 1411564 | 127467.25 | 1539031.25 | 706857.62
B0086 | Seacourt Park & Ride Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0086 | Seacourt Park & Ride Extension | 0 | 0 | 0 | 1262.5 | 1262.5 | 0 | B0106 | Covered Market Planned Maintenance - Roof | 0 | 364738.03 | 364738.03 | 215449.8
B0092 | Cave Street Development (Standingford House) | 0 | 194134.47 | 194134.47 | 135620.7 | -58513.77 | 0 | 0 | 0 | 194134.47 | 0 | B0092 | Cave Street Development (Standingford House) | 0 | 97067.24 | 97067.24 | 146694.01 | 49626.77 | 0 | B0108 | Floyds Row Refurbishment | 0 | -0.2 | -0.2 | 11898.79
B0096 | Bullingdon Community Centre | 0 | 63135.94 | 63135.94 | 17106.31 | -46029.63 | 0 | 0 | 0 | 63135.94 | 0 | B0096 | Bullingdon Community Centre | 0 | 31567.97 | 31567.97 | 94011.86 | 62443.89 | 0 | B0110 | Covered Market Vacant Unit Works | 0 | 0 | 0 | -22221.5
B0098 | 1-3 George Street | 0 | 166732.7 | 166732.7 | 37206.67 | -129526.03 | 0 | 0 | 0 | 166732.7 | 0 | B0098 | 1-3 George Street | 0 | 83366.35 | 83366.35 | 109067.18 | 25700.83 | 0 | B0111 | Town Hall Dry Risers | 0 | 0 | 0 | -22382.9
B0100 | Gloucester Green Car Park (H&S) | 300000 | 70730.14 | 370730.14 | 51260.68 | -319469.46 | 0 | 0 | 0 | 370730.14 | 0 | B0100 | Gloucester Green Car Park (H&S) | 150000 | 35365.07 | 185365.07 | 51260.68 | -134104.39 | 0 | B0112 | City Centre Land Redevelopment (Cinema Project) | 146713.75 | -98141.75 | 48572 | 252043.73
B0101 | Capital works at Covered Market | 200000 | 688453.03 | 888453.03 | 12861.63 | -875591.4 | 200000 | 200000 | 200000 | 1488453.03 | 0 | B0101 | Capital works at Covered Market | 100000 | 344226.51 | 444226.51 | 12861.63 | -431364.88 | 0 | B0114 | Diamond Place Redevelopment | 51879.56 | 0 | 51879.56 | 39248.5
B0102 | Replace or refurbish Lifts | 140000 | -30516 | 109484 | 11364.6 | -98119.4 | 0 | 150000 | 0 | 259484 | 0 | B0102 | Replace or refurbish Lifts | 70000 | -15258 | 54742 | 3733.62 | -51008.38 | 0 | B0115 | Covered Market Masterplan | 0 | -0.93 | -0.93 | 3395
B0104 | Old Gas Works Bridges | 1000000 | 770635.67 | 1770635.67 | 666879.03 | -1103756.64 | 0 | 0 | 0 | 1770635.67 | 0 | B0104 | Old Gas Works Bridges | 500000 | 385317.83 | 885317.83 | 543923.49 | -341394.34 | 0 | B0116 | Osney Path Works (HIF funded) | 868936.8 | 669336.23 | 1538273.03 | -2930.87
B0106 | Covered Market Planned Maintenance - Roof | 525000 | -525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0106 | Covered Market Planned Maintenance - Roof | 262500 | -262500 | 0 | 0 | 0 | 0 | B0117 | Regeneration Property | 0 | 0 | 0 | 0
B0108 | Floyds Row Refurbishment | 48283 | 0 | 48283 | 12239.41 | -36043.59 | 0 | 0 | 0 | 48283 | 0 | B0108 | Floyds Row Refurbishment | 24141.5 | 0 | 24141.5 | 12239.41 | -11902.09 | 0 | B0118 | Oxford Ice Rink Development | 0 | 89920.3 | 89920.3 | 85224
B0111 | Town Hall Dry Risers | 0 | 0 | 0 | 35802.91 | 35802.91 | 0 | 0 | 0 | 0 | 0 | B0111 | Town Hall Dry Risers | 0 | 0 | 0 | 35802.91 | 35802.91 | 0 | B0119 | Oxford Station Feasibility | 209317.53 | 0 | 209317.53 | 130000
B0112 | City Centre Land Redevelopment (Cinema Project) | 0 | 130451.85 | 130451.85 | 937.76 | -129514.09 | 0 | 0 | 0 | 130451.85 | 0 | B0112 | City Centre Land Redevelopment (Cinema Project) | 0 | 65225.92 | 65225.92 | 24686.56 | -40539.36 | 0 | B0120 | Osney Bridge (Growth Deal) | 4794734.6 | -3603161.67 | 1191572.93 | 1032051.72
B0114 | Diamond Place Redevelopment | 0 | 9999.5 | 9999.5 | 0 | -9999.5 | 74770 | 0 | 0 | 84769.5 | 0 | B0114 | Diamond Place Redevelopment | 0 | 4999.75 | 4999.75 | 2365 | -2634.75 | 0 | B0122 | City Cycle Schemes (Growth Deal) | 668901.68 | -115811.77 | 553089.91 | 117271.97
B0116 | Osney Path Works (HIF funded) | 564914 | 833721.13 | 1398635.13 | 0 | -1398635.13 | 0 | 0 | 0 | 1398635.13 | 0 | B0116 | Osney Path Works (HIF funded) | 282457 | 416860.56 | 699317.56 | 0 | -699317.56 | 0 | B0124 | Port Meadow Moorings | 0 | 0 | 0 | 0
B0117 | Regeneration Property | 0 | 3402.38 | 3402.38 | 0 | -3402.38 | 0 | 0 | 0 | 3402.38 | 0 | B0117 | Regeneration Property | 0 | 1701.19 | 1701.19 | 3402.38 | 1701.19 | 0 | B0125 | City Centre Restart (CIL Funded) | 0 | 5499.6 | 5499.6 | 101.99
B0118 | Oxford Ice Rink Development | 0 | 36704 | 36704 | -5883.9 | -42587.9 | 0 | 0 | 0 | 36704 | 0 | B0118 | Oxford Ice Rink Development | 0 | 18352 | 18352 | 25553.6 | 7201.6 | 0 | B0126 | Asset Surveys | 0 | 274980 | 274980 | 429.08
B0119 | Oxford Station Feasibility | 0 | 51563.3 | 51563.3 | -10071.82 | -61635.12 | 0 | 0 | 0 | 51563.3 | 0 | B0119 | Oxford Station Feasibility | 0 | 25781.65 | 25781.65 | 0 | -25781.65 | 0 | B0127 | ZEZ Phase 1 Feasibility | 129240.6 | 0 | 129240.6 | 0
B0120 | Osney Bridge (Growth Deal) | 7184694 | 273726.26 | 7458420.26 | 389448.61 | -7068971.65 | 0 | 0 | 0 | 7458420.26 | 0 | B0120 | Osney Bridge (Growth Deal) | 3592347 | 136863.13 | 3729210.13 | 406159.65 | -3323050.48 | 0 | B0128 | Greenways Cycling Project | 97159.6 | -48579.8 | 48579.8 | 11000
B0122 | City Cycle Schemes (Growth Deal) | 0 | 431332.3 | 431332.3 | 7800 | -423532.3 | 0 | 0 | 0 | 431332.3 | 0 | B0122 | City Cycle Schemes (Growth Deal) | 0 | 215666.15 | 215666.15 | 23096 | -192570.15 | 0 | B0129 | Town Hall Options | 0 | 174154.01 | 174154.01 | 23727
B0124 | Port Meadow Moorings | 0 | 0 | 0 | -5279.22 | -5279.22 | 0 | 0 | 0 | 0 | 0 | B0124 | Port Meadow Moorings | 0 | 0 | 0 | -5279.22 | -5279.22 | 0 | B0130 | CIL Feasibility | 0 | 39734.61 | 39734.61 | 0
B0125 | City Centre Restart (CIL Funded) | 0 | 39324.01 | 39324.01 | 248.01 | -39076 | 0 | 0 | 0 | 39324.01 | 0 | B0125 | City Centre Restart (CIL Funded) | 0 | 19662 | 19662 | 1109 | -18553 | 0 | B0131 | Meanwhile In Oxfordshire | 0 | 4583 | 4583 | 3034
B0126 | Asset Surveys | 0 | 50000 | 50000 | 102.52 | -49897.48 | 250000 | 0 | 0 | 300000 | 0 | B0126 | Asset Surveys | 0 | 25000 | 25000 | 102.52 | -24897.48 | 0 | B0132 | Coach Parking Feasibility | 18332 | -9166 | 9166 | 0
B0127 | ZEZ Phase 1 Feasibility | 0 | 141000 | 141000 | 0 | -141000 | 0 | 0 | 0 | 141000 | 0 | B0127 | ZEZ Phase 1 Feasibility | 0 | 70500 | 70500 | 0 | -70500 | 0 | B0133 | New Burial Space | 110928.77 | 234904.41 | 345833.18 | 154991.86
B0128 | Greenways Cycling Project | 0 | 92250 | 92250 | 37997 | -54253 | 0 | 0 | 0 | 92250 | 0 | B0128 | Greenways Cycling Project | 0 | 46125 | 46125 | 33007 | -13118 | 0 | B0138 | Enabling works - Decarbonisation Project | 0 | 605397.09 | 605397.09 | 21904.84
B0129 | Town Hall Options | 0 | 25072 | 25072 | 0 | -25072 | 0 | 0 | 0 | 25072 | 0 | B0129 | Town Hall Options | 0 | 12536 | 12536 | 1281 | -11255 | 0 | B0141 | City Centre Public Realm (Kiosks Project) | 293565.9 | -119411.9 | 174154 | 120726.25
B0130 | CIL Feasibility | 0 | 43350 | 43350 | 0 | -43350 | 0 | 0 | 0 | 43350 | 0 | B0130 | CIL Feasibility | 0 | 21675 | 21675 | 0 | -21675 | 0 | B0142 | Stock condition surveys (including bridge works) | 802025 | 12232.02 | 814257.02 | 64781.43
B0131 | Meanwhile In Oxfordshire | 0 | 82317 | 82317 | 0 | -82317 | 0 | 0 | 0 | 82317 | 0 | B0131 | Meanwhile In Oxfordshire | 0 | 41158.5 | 41158.5 | 2364 | -38794.5 | 0 | B0143 | Relocation to Town Hall | 0 | 174159.12 | 174159.12 | 49428.99
B0132 | Coach Parking Feasibility | 0 | 20000 | 20000 | 0 | -20000 | 0 | 0 | 0 | 20000 | 0 | B0132 | Coach Parking Feasibility | 0 | 10000 | 10000 | 0 | -10000 | 0 | B0144 | Salary Costs across the Council to be capitalised | 857021 | 245997.11 | 1103018.11 | 21127.87
B0133 | New Burial Space | 0 | 353999.87 | 353999.87 | 53599.71 | -300400.16 | 1323000 | 420869 | 0 | 2097868.87 | 0 | B0133 | New Burial Space | 0 | 176999.93 | 176999.93 | 61705.71 | -115294.22 | 0 | B0145 | St Michael's Street Levelling Works | 54996 | -36663.86 | 18332.14 | 11742.04
B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | 0 | 0 | 0 | 215 | 215 | 0 | B0146 | Ice Rink Car Parking Feasibility | 0 | 44944.15 | 44944.15 | 22480.07
B0138 | Enabling works - Decarbonisation Project | 0 | 0.39 | 0.39 | 0 | -0.39 | 638576 | 0 | 0 | 638576.39 | 0 | B0138 | Enabling works - Decarbonisation Project | 0 | 0.19 | 0.19 | 0 | -0.19 | 0 | B0147 | Repairs to 2-4 Gloucester Street and 24-26 George St | 247482 | 317496.78 | 564978.78 | 616267.05
B0141 | City Centre Public Realm (Kiosks Project) | 179987 | 61047.3 | 241034.3 | 105157.22 | -135877.08 | 0 | 0 | 0 | 241034.3 | 0 | B0141 | City Centre Public Realm (Kiosks Project) | 89993.5 | 30523.65 | 120517.15 | 78560.32 | -41956.83 | 0 | B0148 | Oxford Flood Alleviation Scheme (OFAS) HIF Contribution | 3987210 | 0 | 3987210 | 0
B0142 | Stock condition surveys (including bridge works) | 500000 | -180413.71 | 319586.29 | 20248.52 | -299337.77 | 300000 | 600000 | 600000 | 1819586.29 | 0 | B0142 | Stock condition surveys (including bridge works) | 250000 | -90206.85 | 159793.15 | 23140 | -136653.15 | 0 | B0149 | Tumbling Bay Embankment Works | 0 | 29650.75 | 29650.75 | 14108.75
B0143 | Relocation to Town Hall | 0 | 479010.97 | 479010.97 | 24658.2 | -454352.77 | 0 | 0 | 0 | 479010.97 | 0 | B0143 | Relocation to Town Hall | 0 | 239505.49 | 239505.49 | 39913.14 | -199592.35 | 0 | B0150 | Hinksey Pool Liner Replacement | 137490 | -16851.69 | 120638.31 | 131615
B0144 | Salary Costs across the Council to be capitalised | 380000 | 1380591 | 1760591 | 0 | -1760591 | 663000 | 663040 | 663040 | 3749671 | 0 | B0144 | Salary Costs across the Council to be capitalised | 190000 | 690295.5 | 880295.5 | 0 | -880295.5 | 0 | B0151 | Bus Shelters | 0 | 25925.11 | 25925.11 | 11343.21
B0145 | St Michael's Street Levelling Works | 168817 | 240009.57 | 408826.57 | 11407.26 | -397419.31 | 0 | 0 | 0 | 408826.57 | 0 | B0145 | St Michael's Street Levelling Works | 84408.5 | 120004.78 | 204413.28 | 23682.78 | -180730.5 | 0 | B0152 | Cowley Branch Line Full Busines Case | 2780047.8 | -768654.34 | 2011393.46 | 837029.72
B0146 | Ice Rink Car Parking Feasibility | 100000 | -83934.07 | 16065.93 | 5200 | -10865.93 | 130000 | 0 | 0 | 146065.93 | 0 | B0146 | Ice Rink Car Parking Feasibility | 50000 | -41967.03 | 8032.97 | 10415 | 2382.03 | 0 | B0153 | HSBC Options | 0 | -2 | -2 | 933.52
B0147 | Repairs to 2-4 Gloucester Street and 24-26 George St | 0 | 0 | 0 | -37297.68 | -37297.68 | 0 | 0 | 0 | 0 | 0 | B0147 | Repairs to 2-4 Gloucester Street and 24-26 George St | 0 | 0 | 0 | 2943.19 | 2943.19 | 0 | B0154 | Covered Market masterplan and enabling works | 2291500 | -1820375.85 | 471124.15 | 138510.5
B0148 | Oxford Flood Alleviation Scheme (OFAS) HIF Contribution | 0 | 4350000 | 4350000 | 0 | -4350000 | 0 | 0 | 0 | 4350000 | 0 | B0148 | Oxford Flood Alleviation Scheme (OFAS) HIF Contribution | 0 | 2175000 | 2175000 | 0 | -2175000 | 0 | B0155 | Contingency to cover cost inflation rises | 1191580 | -1189746.8 | 1833.2 | 0
B0149 | Tumbling Bay Embankment Works | 0 | 31185.5 | 31185.5 | 5667.87 | -25517.63 | 250000 | 0 | 0 | 281185.5 | 0 | B0149 | Tumbling Bay Embankment Works | 0 | 15592.75 | 15592.75 | 5667.87 | -9924.88 | 0 | B0156 | Waterways - Long Bridges/Tumbling Bay | 265814 | -242899 | 22915 | 88399
B0150 | Hinksey Pool Liner Replacement | 0 | 18385 | 18385 | 0 | -18385 | 0 | 0 | 0 | 18385 | 0 | B0150 | Hinksey Pool Liner Replacement | 0 | 9192.5 | 9192.5 | 0 | -9192.5 | 0 | B0157 | Works Town Hall | 1833200 | -1393232 | 439968 | 444517.1
B0151 | Bus Shelters | 0 | 15049.79 | 15049.79 | 0 | -15049.79 | 0 | 0 | 0 | 15049.79 | 0 | B0151 | Bus Shelters | 0 | 7524.9 | 7524.9 | 9811 | 2286.1 | 0 | B0159 | Redbridge Masterplan | 0 | 94118.75 | 94118.75 | 4562
B0152 | Cowley Branch Line Full Business Case | 1689183 | 910486.13 | 2599669.13 | 1421395.09 | -1178274.04 | 653350 | 0 | 0 | 3253019.13 | 0 | B0152 | Cowley Branch Line Full Business Case | 844591.5 | 455243.07 | 1299834.57 | 1428388.09 | 128553.52 | 0 | C3044 | Software Licences | 245000 | 18854.46 | 263854.46 | 265570
B0153 | HSBC Options | 0 | 55000 | 55000 | 0 | -55000 | 0 | 0 | 0 | 55000 | 0 | B0153 | HSBC Options | 0 | 29615.38 | 29615.38 | 0 | -29615.38 | 0 | C3057 | Housing System Replacement | 0 | 0 | 0 | 18589.56
B0154 | Covered Market masterplan and enabling works | 1513991 | -716343.61 | 797647.39 | 156325.48 | -641321.91 | 589820 | 2906795 | 3265551 | 7559813.39 | 0 | B0154 | Covered Market masterplan and enabling works | 756995.5 | -435094.88 | 321900.62 | 373487.13 | 51586.51 | 0 | C3058 | CRM Lagan Replacement | 0 | 46682.44 | 46682.44 | 2666
B0156 | Waterways - Long Bridges/Tumbling Bay | 355000 | -342.42 | 354657.58 | 8780.87 | -345876.71 | 0 | 0 | 0 | 354657.58 | 0 | B0156 | Waterways - Long Bridges/Tumbling Bay | 177500 | -171.21 | 177328.79 | 121101.55 | -56227.24 | 0 | C3060 | End-Point Devices (Desktops/Laptops) | 137490 | 138109.52 | 275599.52 | 94067.8
B0157 | Works Town Hall | 1500000 | -978084.75 | 521915.25 | 267740.35 | -254174.9 | 1000000 | 1000000 | 500000 | 3021915.25 | 0 | B0157 | Works Town Hall | 807692.31 | -489042.38 | 318649.93 | 266212.35 | -52437.58 | 0 | C3062 | Datacentre Upgrade | 0 | 0 | 0 | 0
B0158 | Street Sports Lighting Upgrade | 0 | 70000 | 70000 | 69000 | -1000 | 0 | 0 | 0 | 70000 | 0 | B0158 | Street Sports Lighting Upgrade | 0 | 35000 | 35000 | 69000 | 34000 | 0 | C3066 | Telephony Device Refresh | 54996 | 25971.24 | 80967.24 | 36700.24
B0159 | Redbridge Masterplan | 0 | 138113 | 138113 | 683.19 | -137429.81 | 0 | 0 | 0 | 138113 | 0 | B0159 | Redbridge Masterplan | 0 | 69056.5 | 69056.5 | 18264.19 | -50792.31 | 0 | C3067 | Paris Payment System, Replacement / PCI DSS | 0 | 0 | 0 | 0
B0160 | Templars Square (GF Element) | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | B0160 | Templars Square (GF Element) | 0 | 3846.16 | 3846.16 | 404 | -3442.16 | 0 | C3068 | Windows 2008 Server Replacement | 0 | -109.99 | -109.99 | 13081.25
B0161 | Floyds Row (Feasibility2024) | 1050000 | -1000000 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 0 | B0161 | Floyds Row (Feasibility2024) | 525000 | -498076.92 | 26923.08 | 0 | -26923.08 | 0 | C3070 | Business Process Automation Full Rollout | 0 | 0 | 0 | 0
B0162 | Property Services Works to Town Hall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0162 | Property Services Works to Town Hall | -57692.31 | 0 | -57692.31 | 0 | 57692.31 | 0 | C3072 | Forms Engine Replacement | 0 | 9310.82 | 9310.82 | 21600
B0163 | Network infrastructure installations (utilities, Comms & Energy) | 40000 | 0 | 40000 | 0 | -40000 | 40000 | 40000 | 40000 | 160000 | 0 | B0163 | Network infrastructure installations (utilities, Comms & Energy) | 20000 | 0 | 20000 | 0 | -20000 | 0 | C3077 | Info@Work Enterprise Upgrade Rollout | 0 | -916.6 | -916.6 | 0
B0164 | Waterways investment | 500000 | -500000 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 0 | B0164 | Waterways investment | 250000 | -250000 | 0 | 0 | 0 | 0 | C3078 | Revs and Bens System Replacement | 0 | 0 | 0 | 0
B0165 | Stone walls & Railing programme | 100000 | 0 | 100000 | 0 | -100000 | 0 | 0 | 0 | 100000 | 0 | B0165 | Stone walls & Railing programme | 50000 | 0 | 50000 | 0 | -50000 | 0 | C3080 | Telephony Contract Replacement | 0 | 29297.29 | 29297.29 | 35199.5
B0166 | Broad street roofing & Façade project | 2000000 | -1800000 | 200000 | 0 | -200000 | 500000 | 1000000 | 300000 | 2000000 | 0 | B0166 | Broad street roofing & Façade project | 1000000 | -900000 | 100000 | 0 | -100000 | 0 | C3081 | Capitalised ICT Projects | 429152.12 | 202009.47 | 631161.59 | 483314.13
B0167 | Fire Risk Assessment programme works | 50000 | 0 | 50000 | 11800 | -38200 | 0 | 0 | 0 | 50000 | 0 | B0167 | Fire Risk Assessment programme works | 25000 | 0 | 25000 | 11800 | -13200 | 0 | C3082 | Website Redesign | 0 | 78231.81 | 78231.81 | 100893.75
B0168 | Bridge investment work | 500000 | -100000 | 400000 | 0 | -400000 | 300000 | 0 | 0 | 700000 | 0 | B0168 | Bridge investment work | 250000 | -50000 | 200000 | 0 | -200000 | 0 | C3083 | FOI System | 0 | 0 | 0 | -15750
B0169 | M&E Capital budget to fund capital replacement of assets including Fire Equipment, Bas Boilers, Electrical works and any components at End of Life (EoL) where there is statutory, H&S or Income need | 150000 | -150000 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000 | 0 | B0169 | M&E Capital budget to fund capital replacement of assets including Fire Equipment, Bas Boilers, Electrical works and any components at End of Life (EoL) where there is statutory, H&S or Income need | 75000 | -75000 | 0 | 0 | 0 | 0 | C3084 | Agresso Update | 0 | 84511.97 | 84511.97 | 108737.08
B0170 | Salary Costs across the Council to be capitalised | 323000 | -323000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | B0170 | Salary Costs across the Council to be capitalised | 161500 | -161500 | 0 | 0 | 0 | 0 | C3085 | ICT - I-trent replacement | 68745 | 0 | 68745 | 0
B0171 | Regeneration Property Purchase/Odeon | 0 | 212000 | 212000 | 713.2 | -211286.8 | 9880657 | 20821963 | 5466423 | 36381043 | 0 | B0171 | Regeneration Property Purchase/Odeon | 0 | 106000 | 106000 | 713.2 | -105286.8 | 0 | C3086 | ICT - QL Exploitation | 73328 | 67828.4 | 141156.4 | 174686.06
B0172 | Bury Knowle House | 0 | 41000 | 41000 | 0 | -41000 | 0 | 0 | 0 | 41000 | 0 | B0172 | Bury Knowle House | 0 | 22076.92 | 22076.92 | 0 | -22076.92 | 0 | C3087 | ICT - replacing Netcall contact centre telephony and resource management system | 68745 | 0 | 68745 | 47229.16
B0173 | Union Street Car Park | 0 | 65000 | 65000 | 0 | -65000 | 0 | 0 | 0 | 65000 | 0 | B0173 | Union Street Car Park | 0 | 35000 | 35000 | 731 | -34269 | 0 | C3088 | ICT - replacing Uniform (building control and planning) | 0 | 0 | 0 | 0
C3044 | Software Licences | 245000 | 0 | 245000 | 402356.99 | 157356.99 | 245000 | 245000 | 245000 | 980000 | 0 | C3044 | Software Licences | 122500 | 0 | 122500 | 402356.99 | 279856.99 | 0 | C3089 | ICT - Asset Management System | 274980 | 0 | 274980 | 18662
C3057 | Housing System Replacement | 0 | 0 | 0 | -9112.5 | -9112.5 | 0 | 0 | 0 | 0 | 0 | C3057 | Housing System Replacement | 0 | 0 | 0 | -9112.5 | -9112.5 | 0 | C3090 | ICT - Extension of existing Alemba case managmenet system | 18332 | 0 | 18332 | 15996
C3058 | CRM Lagan Replacement | 0 | 48264 | 48264 | 0 | -48264 | 0 | 0 | 0 | 48264 | 0 | C3058 | CRM Lagan Replacement | 0 | 24132 | 24132 | 0 | -24132 | 0 | C3091 | ICT - scanning of all paper planning files | 137490 | 0 | 137490 | 0
C3060 | End-Point Devices (Desktops/Laptops) | 150000 | 204366.83 | 354366.83 | 75167.81 | -279199.02 | 150000 | 150000 | 150000 | 804366.83 | 0 | C3060 | End-Point Devices (Desktops/Laptops) | 75000 | 102183.42 | 177183.42 | 42567.81 | -134615.61 | 0 | C3092 | ICT - Replacement of IKEN - L&G case management system | 68745 | 0 | 68745 | 7500
C3066 | Telephony Device Refresh | 60000 | -26309.57 | 33690.43 | 30411.79 | -3278.64 | 60000 | 60000 | 60000 | 213690.43 | 0 | C3066 | Telephony Device Refresh | 30000 | -13154.78 | 16845.22 | 30411.79 | 13566.57 | 0 | C3093 | ICT - Replacement of ArcGIS geospatial mapping system | 22915 | 0 | 22915 | 0
C3068 | Windows 2008 Server Replacement | 0 | 0 | 0 | -5125 | -5125 | 0 | 0 | 0 | 0 | 0 | C3068 | Windows 2008 Server Replacement | 0 | 0 | 0 | -3495 | -3495 | 0 | C3094 | ICT - Information @ Work major upgrade | 13749 | 0 | 13749 | 0
C3070 | Business Process Automation Full Rollout | 0 | 0 | 0 | 15666.67 | 15666.67 | 0 | 0 | 0 | 0 | #N/A | C3072 | Forms Engine Replacement | 0 | 0 | 0 | 10800 | 10800 | 0 | C3095 | ICT - Redesign of Council Website | 91660 | 0 | 91660 | 16915
C3072 | Forms Engine Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C3080 | Telephony Contract Replacement | 0 | 0 | 0 | 22599.5 | 22599.5 | 0 | C3096 | ICT - Open Revenue Cloud Migration | 0 | 0 | 0 | 0
C3080 | Telephony Contract Replacement | 0 | 0 | 0 | 22599.5 | 22599.5 | 0 | 0 | 0 | 0 | 0 | C3081 | Capitalised ICT Projects | 81600 | 226222.94 | 307822.94 | 487626.21 | 179803.27 | 0 | C3097 | ICT - Refresh of content and taxonomy of the Council Website | 22915 | 0 | 22915 | 3850
C3081 | Capitalised ICT Projects | 163200 | 452445.87 | 615645.87 | 487626.21 | -128019.66 | 163200 | 0 | 0 | 778845.87 | 0 | C3082 | Website Redesign | 0 | 1553.13 | 1553.13 | 627 | -926.13 | 0 | C3098 | ICT - Agresso upgrade and migration to Cloud | 320810 | 0 | 320810 | 119025.12
C3082 | Website Redesign | 0 | 3106.25 | 3106.25 | 627 | -2479.25 | 0 | 0 | 0 | 3106.25 | 0 | C3083 | FOI System | 0 | 0 | 0 | 7875 | 7875 | 0 | C6000 | ICT - feasibility | 164988 | 0 | 164988 | 0
C3083 | FOI System | 0 | 0 | 0 | 11812.5 | 11812.5 | 0 | 0 | 0 | 0 | 0 | C3084 | Agresso Update | 0 | 0 | 0 | 6167 | 6167 | 0 | E3511 | Essential Repair Grants | 41247 | 0 | 41247 | 22892.03
C3084 | Agresso Update | 0 | 0 | 0 | 6167 | 6167 | 0 | 0 | 0 | 0 | 0 | C3086 | ICT - QL Exploitation | 128000 | -12672.06 | 115327.94 | 212746.5 | 97418.56 | 0 | E3521 | Disabled Facilities Grants | 916600 | 498439.75 | 1415039.75 | 1118004.42
C3085 | ICT - I-trent replacement | 0 | 0 | 0 | 0 | 0 | 20000 | 55000 | 0 | 75000 | 0 | C3087 | ICT - replacing Netcall contact centre telephony and resource management system | 0 | 14734.31 | 14734.31 | 34283.92 | 19549.61 | 0 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | 0 | 0 | 0 | 3742.28
C3086 | ICT - QL Exploitation | 256000 | -25344.12 | 230655.88 | 216214 | -14441.88 | 78000 | 78000 | 78000 | 464655.88 | 0 | C3088 | ICT - replacing Uniform (building control and planning) | 50000 | 0 | 50000 | 0 | -50000 | 0 | E3558 | Go Ultra Low Oxford - On Street | 0 | 459904.4 | 459904.4 | 17043.35
C3087 | ICT - replacing Netcall contact centre telephony and resource management system | 0 | 29468.62 | 29468.62 | 34283.92 | 4815.3 | 0 | 0 | 0 | 29468.62 | 0 | C3089 | ICT - Asset Management System | 148510.3 | -18662 | 129848.3 | 12500 | -117348.3 | 0 | E3560 | Go Ultra Low Oxford - Taxis | 4780.07 | 31953.89 | 36733.96 | 969.76
C3088 | ICT - replacing Uniform (building control and planning) | 100000 | 0 | 100000 | 0 | -100000 | 0 | 0 | 0 | 100000 | 0 | C3090 | ICT - Extension of existing Alemba case managmenet system | 0 | 2002 | 2002 | 0 | -2002 | 0 | E3561 | Additional DFG Funding | 0 | 0 | 0 | -2484.24
C3089 | ICT - Asset Management System | 318662 | -37324 | 281338 | 30650 | -250688 | 300000 | 0 | 0 | 581338 | 0 | C3091 | ICT - scanning of all paper planning files | 0 | 75000 | 75000 | 10092 | -64908 | 0 | E3565 | Decarbonisation Fund - OCC element | 0 | 110238.01 | 110238.01 | 15126.04
C3090 | ICT - Extension of existing Alemba case managmenet system | 0 | 4004 | 4004 | 0 | -4004 | 0 | 0 | 0 | 4004 | 0 | C3092 | ICT - Replacement of IKEN - L&G case management system | 0 | 33750 | 33750 | 35125 | 1375 | 0 | E3568 | Leisure Centre LED Lighting Feasibility | 0 | 30247.8 | 30247.8 | 5390
C3091 | ICT - scanning of all paper planning files | 0 | 150000 | 150000 | 0 | -150000 | 0 | 0 | 0 | 150000 | 0 | C3093 | ICT - Replacement of ArcGIS geospatial mapping system | 0 | 12500 | 12500 | 0 | -12500 | 0 | F7024 | St Clements Environmental Improvements | 0 | -2.08 | -2.08 | 0
C3092 | ICT - Replacement of IKEN - L&G case management system | 0 | 67500 | 67500 | 35125 | -32375 | 0 | 0 | 0 | 67500 | 0 | C3094 | ICT - Information @ Work major upgrade | 1500 | 7500 | 9000 | 0 | -9000 | 0 | HT14 | South Oxfordshire Science Village | 0 | 0 | 0 | 0
C3093 | ICT - Replacement of ArcGIS geospatial mapping system | 0 | 25000 | 25000 | 0 | -25000 | 0 | 0 | 0 | 25000 | 0 | C3095 | ICT - Redesign of Council Website | 0 | 25829 | 25829 | 627 | -25202 | 0 | L1000 | Audio & Visual Equipment | 0 | 8145.82 | 8145.82 | -3895
C3094 | ICT - Information @ Work major upgrade | 3000 | 15000 | 18000 | 0 | -18000 | 0 | 0 | 0 | 18000 | 0 | C3096 | ICT - Open Revenue Cloud Migration | 25000 | 0 | 25000 | 0 | -25000 | 0 | M5023 | OxWED Loans | 1054090 | -1054090 | 0 | 0
C3095 | ICT - Redesign of Council Website | 0 | 51658 | 51658 | 627 | -51031 | 0 | 0 | 0 | 51658 | 0 | C3097 | ICT - Refresh of content and taxonomy of the Council Website | 12500 | 10575 | 23075 | 1500 | -21575 | 0 | M5024 | National Homelessness Property Fund | 0 | 581089.53 | 581089.53 | 0
C3096 | ICT - Open Revenue Cloud Migration | 50000 | 0 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 0 | C3098 | ICT - Agresso upgrade and migration to Cloud | 0 | 96609.8 | 96609.8 | 0 | -96609.8 | 0 | M5025 | Barton Park - purchase by Council | 9166000 | -3076109.6 | 6089890.4 | 3281620.2
C3097 | ICT - Refresh of content and taxonomy of the Council Website | 25000 | 21150 | 46150 | 1500 | -44650 | 0 | 0 | 0 | 46150 | 0 | C3099 | Third-party consultancy for Azure Active Directory and M365 migration from SCC, security setup and configuration. | 67500 | 0 | 67500 | 0 | -67500 | 0 | M5026 | Housing Company Loans (excl Barton Park) | 27498000 | -20432847.2 | 7065152.8 | 0
C3098 | ICT - Agresso upgrade and migration to Cloud | 0 | 193219.6 | 193219.6 | 0 | -193219.6 | 0 | 0 | 0 | 193219.6 | 0 | C3100 | Itrent system improvement | 15000 | 0 | 15000 | 0 | -15000 | 0 | M5032 | Barton Park - Loan to OCHL | 9166000 | -4275939 | 4890061 | 3298620.2
C3099 | Third-party consultancy for Azure Active Directory and M365 migration from SCC, security setup and configuration. | 135000 | 0 | 135000 | 0 | -135000 | 0 | 0 | 0 | 135000 | 0 | C3101 | I@W renewal or replacement | 150000 | 0 | 150000 | 0 | -150000 | 0 | M5033 | Blackbird Leys Regeneration (GF element) | 7907768.51 | -1745466.28 | 6162302.24 | 143680.6
C3100 | Itrent system improvement | 30000 | 0 | 30000 | 0 | -30000 | 0 | 0 | 0 | 30000 | 0 | C3102 | Cyber security monitoring and response service | 57500 | 0 | 57500 | 0 | -57500 | 0 | M5034 | Affordable Housing Supply | 995427.6 | -878102.8 | 117324.8 | 0
C3101 | I@W renewal or replacement | 300000 | 0 | 300000 | 0 | -300000 | 0 | 0 | 0 | 300000 | 0 | C3103 | Upgrade/replace Kirona DRS (this is an ODS system) | 37500 | 0 | 37500 | 0 | -37500 | 0 | M5035 | Growth Deal RP Funding | 647119.6 | -249315.2 | 397804.4 | 434000
C3102 | Cyber security monitoring and response service | 115000 | 0 | 115000 | 0 | -115000 | 0 | 0 | 0 | 115000 | 0 | C3104 | Windows security server upgrades | 37500 | 0 | 37500 | 0 | -37500 | 0 | M5037 | Northern Gateway (Oxford North HIF) | 9993538 | -8099497.34 | 1894040.66 | 4089
C3103 | Upgrade/replace Kirona DRS (this is an ODS system) | 75000 | 0 | 75000 | 0 | -75000 | 0 | 0 | 0 | 75000 | 0 | C3105 | Migration of Mod.gov | 45000 | 0 | 45000 | 0 | -45000 | 0 | M5038 | Roken House Aquisition and Refurbishment | 183320 | 415481.78 | 598801.78 | 433442.18
C3104 | Windows security server upgrades | 75000 | 0 | 75000 | 0 | -75000 | 0 | 0 | 0 | 75000 | 0 | C3106 | Migration of SCC to cloud hosted alternatives | 53500 | 0 | 53500 | 0 | -53500 | 0 | M5039 | UK Shared Prosperity Fund Invesment Plan | 64162 | 109992 | 174154 | 0
C3105 | Migration of Mod.gov | 90000 | 0 | 90000 | 0 | -90000 | 0 | 0 | 0 | 90000 | 0 | C3107 | Replacement of Uniform IDOX (additional funding) | 12500 | 0 | 12500 | 0 | -12500 | 0 | N6384 | Tower Blocks | 0 | 670465.19 | 670465.19 | 157559.63
C3106 | Migration of SCC to cloud hosted alternatives | 107000 | 0 | 107000 | 0 | -107000 | 0 | 0 | 0 | 107000 | 0 | C3108 | Online forms development (2x resources to accelerate) | 80000 | 0 | 80000 | 0 | -80000 | 0 | N6385 | Adaptations for disabled | 1033810.8 | 219190.4 | 1253001.2 | 1231636.08
C3107 | Replacement of Uniform IDOX (additional funding) | 25000 | 0 | 25000 | 0 | -25000 | 0 | 0 | 0 | 25000 | 0 | C6000 | ICT - feasibility | 0 | 90000 | 90000 | 0 | -90000 | 0 | N6386 | Structural | 1732500 | 251111.65 | 1983611.65 | 1822424.97
C3108 | Online forms development (2x resources to accelerate) | 160000 | 0 | 160000 | 0 | -160000 | 160000 | 0 | 0 | 320000 | 0 | E3511 | Essential Repair Grants | 7500 | 11053.99 | 18553.99 | 5000 | -13553.99 | 0 | N6387 | Controlled Entry Upgrades | 366769.8 | 19768.11 | 386537.91 | 13201.31
C6000 | ICT - feasibility | 0 | 180000 | 180000 | 0 | -180000 | 0 | 0 | 0 | 180000 | 0 | E3521 | Disabled Facilities Grants | 600000 | 176874.27 | 776874.27 | 941334.45 | 164460.18 | 0 | N6388 | Major Voids | 513296 | 219984.21 | 733280.21 | 1244011.22
E3511 | Essential Repair Grants | 15000 | 22107.97 | 37107.97 | 5000 | -32107.97 | 15000 | 15000 | 15000 | 82107.97 | 0 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | 0 | 0 | 0 | 2.44 | 2.44 | 0 | N6389 | Damp-proof works | 68745 | 389555.11 | 458300.11 | 58746.1
E3521 | Disabled Facilities Grants | 1200000 | 353748.55 | 1553748.55 | 887114.89 | -666633.66 | 1200000 | 1200000 | 1200000 | 5153748.55 | 0 | E3558 | Go Ultra Low Oxford - On Street | 0 | 247353.01 | 247353.01 | 0 | -247353.01 | 0 | N6390 | Kitchens & Bathrooms | 1209010 | -1209010 | 0 | 0
E3557 | Oxford and Abingdon Flood Alleviation Scheme | 0 | 0 | 0 | 2.44 | 2.44 | 250000 | 0 | 0 | 250000 | 0 | E3560 | Go Ultra Low Oxford - Taxis | 0 | 19163.28 | 19163.28 | 19015 | -148.28 | 0 | N6391 | Heating | 2026871 | -2026871 | 0 | 0
E3558 | Go Ultra Low Oxford - On Street | 0 | 494706.03 | 494706.03 | 0 | -494706.03 | 0 | 0 | 0 | 494706.03 | 0 | E3561 | Additional DFG Funding | 0 | 2484.24 | 2484.24 | -2438.75 | -4922.99 | 0 | N6392 | Roofing | 641620 | 90935.12 | 732555.12 | 620876.49
E3560 | Go Ultra Low Oxford - Taxis | 0 | 38326.56 | 38326.56 | 17515 | -20811.56 | 0 | 0 | 0 | 38326.56 | 0 | E3565 | Decarbonisation Fund - OCC element | 0 | 52571.18 | 52571.18 | 0 | -52571.18 | 0 | N6395 | Electrics | 680559.9 | 326887.97 | 1007447.87 | 966246.63
E3561 | Additional DFG Funding | 0 | 4968.48 | 4968.48 | -2438.75 | -7407.23 | 0 | 0 | 0 | 4968.48 | 0 | E3568 | Leisure Centre LED Lighting Feasibility | 0 | 3215 | 3215 | 3840 | 625 | 0 | N6434 | Doors and Windows | 470000 | 179562.12 | 649562.12 | 967689.05
E3565 | Decarbonisation Fund - OCC element | 0 | 105142.35 | 105142.35 | -1859.08 | -107001.43 | 0 | 0 | 0 | 105142.35 | 0 | E3569 | General Fund Capital Reserve (SCS works & Energy) | 500000 | -250000 | 250000 | 0 | -250000 | 0 | N7020 | Extensions & Major Adaptions | 1251679.56 | -868618.38 | 383061.18 | 243107.82
E3568 | Leisure Centre LED Lighting Feasibility | 0 | 6430 | 6430 | 3840 | -2590 | 0 | 0 | 0 | 6430 | 0 | E3570 | Biodiversity Net Gain (Feasibility) | 0 | 53846.16 | 53846.16 | 21264 | -32582.16 | 0 | N7031 | Homes at Barton | 0 | 0 | 0 | 0
E3569 | General Fund Capital Reserve (SCS works & Energy) | 1000000 | -500000 | 500000 | 0 | -500000 | 500000 | 0 | 0 | 1000000 | 0 | KS04 | Legal Services | 0 | 0 | 0 | 0 | 0 | #N/A | N7032 | Great Estates Programme | 1851254 | -1451254.49 | 399999.51 | 81842.56
E3570 | Biodiversity Net Gain (Feasibility) | 0 | 100000 | 100000 | 19720 | -80280 | 0 | 0 | 0 | 100000 | 0 | L1000 | Audio & Visual Equipment | 0 | 6391 | 6391 | 0 | -6391 | 0 | N7033 | Energy Efficiency Initiatives | 3637100 | -722980.28 | 2914119.72 | 572530.27
KS04 | Legal Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | M5023 | OxWED Loans | 1875000 | -1362500 | 512500 | 0 | -512500 | 0 | N7040 | Blackbird Leys Regeneration | 1052800 | -468854.9 | 583945.1 | 92095.7
L1000 | Audio & Visual Equipment | 0 | 12782 | 12782 | 0 | -12782 | 0 | 0 | 0 | 12782 | 0 | M5024 | National Homelessness Property Fund | 0 | 316980.98 | 316980.98 | 157663.93 | -159317.05 | 0 | N7042 | Barton Regeneration | 444000 | 1345.13 | 445345.13 | 3257.33
M5023 | OxWED Loans | 3750000 | -2725000 | 1025000 | 0 | -1025000 | 0 | 0 | 0 | 1025000 | 0 | M5025 | Barton Park - purchase by Council | 5525804.57 | 3359189.9 | 8884994.47 | 6646509.79 | -2238484.68 | 0 | N7044 | Lift Replacement & Refurbishment Programme | 488899 | -288898.66 | 200000.34 | 70452.65
M5024 | National Homelessness Property Fund | 0 | 633961.96 | 633961.96 | 157663.93 | -476298.03 | 0 | 0 | 0 | 633961.96 | 0 | M5026 | Housing Company Loans (excl Barton Park) | 7025804.57 | 4932195.5 | 11958000.07 | 5599810.04 | -6358190.03 | 0 | N7047 | Social Rented Housing Acquisitions | 0 | 2383160.02 | 2383160.02 | 2368930.94
M5025 | Barton Park - purchase by Council | 11051609.13 | 6718379.8 | 17769988.93 | 6646509.79 | -11123479.14 | 17848472.83 | 5789066.94 | 4962150.08 | 46369678.77 | 0 | M5032 | Barton Park - Loan to OCHL | 0 | 4607189.9 | 4607189.9 | 0 | -4607189.9 | 0 | N7048 | Fire Door Installations | 2175834.6 | -1365834.18 | 810000.42 | 575329.46
M5026 | Housing Company Loans (excl Barton Park) | 14051609.13 | 9864391 | 23916000.13 | 5599810.04 | -18316190.09 | 36634000 | 20762000 | 29739609 | 111051609.13 | 0 | M5033 | Blackbird Leys Regeneration (GF element) | 2793438 | 1384562.03 | 4178000.03 | 6258552.41 | 2080552.38 | 0 | N7049 | Compulsory purchase of property | 0 | 0 | 0 | 0
M5032 | Barton Park - Loan to OCHL | 0 | 9214379.8 | 9214379.8 | 0 | -9214379.8 | 0 | 5789066.94 | 4962150.08 | 19965596.81 | 0 | M5034 | Affordable Housing Supply | 979000 | 64000 | 1043000 | 0 | -1043000 | 0 | N7050 | East Oxford development | 5215504.5 | -4199332.13 | 1016172.38 | 189877
M5033 | Blackbird Leys Regeneration (GF element) | 5586876 | 2769124.05 | 8356000.05 | 6153403.92 | -2202596.13 | 4866000 | 5452000 | 4121439 | 22795439.05 | 0 | M5035 | Growth Deal RP Funding | 136000 | -136000 | 0 | 0 | 0 | 0 | N7051 | Acquisition of Additional Units | 1643835.6 | 0 | 1643835.6 | 0
M5034 | Affordable Housing Supply | 1958000 | 128000 | 2086000 | 0 | -2086000 | 0 | 0 | 0 | 2086000 | 0 | M5037 | Northern Gateway (Oxford North HIF) | 0 | 576708 | 576708 | 2218.05 | -574489.95 | 0 | N7052 | HRA Stock Condition Survey | 162532.5 | -8335.08 | 154197.42 | 170153.5
M5035 | Growth Deal RP Funding | 272000 | -272000 | 0 | 0 | 0 | 272000 | 0 | 0 | 272000 | 0 | M5038 | Roken House Aquisition and Refurbishment | 0 | 47778.18 | 47778.18 | 3019.9 | -44758.28 | 0 | N7054 | Properties Purchased From OCHL | 51519392.11 | -27973090.33 | 23546301.78 | 2956718.16
M5037 | Northern Gateway (Oxford North HIF) | 0 | 1153416 | 1153416 | 2218.05 | -1151197.95 | 0 | 0 | 0 | 1153416 | 0 | M5039 | UK Shared Prosperity Fund Invesment Plan | 32500 | 153408.5 | 185908.5 | 0 | -185908.5 | 0 | N7057 | Kitchens | 0 | 1035757.68 | 1035757.68 | 687451.99
M5038 | Roken House Aquisition and Refurbishment | 0 | 95556.35 | 95556.35 | -147482.41 | -243038.76 | 0 | 0 | 0 | 95556.35 | 0 | M5040 | Brownfield Land Release Fund (BLRF) | 0 | 0 | 0 | 12876.73 | 12876.73 | 0 | N7058 | Bathrooms | 0 | 522461.56 | 522461.56 | 311416.18
M5039 | UK Shared Prosperity Fund Invesment Plan | 65000 | 306817 | 371817 | 0 | -371817 | 0 | 0 | 0 | 371817 | 0 | N6384 | Tower Blocks | 500000 | -369806.51 | 130193.49 | 6630.02 | -123563.47 | 0 | N7059 | Boilers Only | 0 | 1777110.46 | 1777110.46 | 1236573.33
M5040 | Brownfield Land Release Fund (BLRF) | 0 | 0 | 0 | 60120.64 | 60120.64 | 0 | 0 | 0 | 0 | 0 | N6385 | Adaptations for disabled | 389360 | 0.02 | 389360.02 | 812853.47 | 423493.45 | 0 | N7060 | Heating Systems | 0 | 367290.79 | 367290.79 | 237497.36
N6384 | Tower Blocks | 1000000 | -739613.02 | 260386.98 | 6630.02 | -253756.96 | 1300000 | 0 | 0 | 1560386.98 | 0 | N6386 | Structural | 620000 | 93877.14 | 713877.14 | 42418.58 | -671458.56 | 0 | N7061 | Northfield Hostel | 12176272.06 | -9312605.59 | 2863666.47 | 1024153.68
N6385 | Adaptations for disabled | 800000 | 0.05 | 800000.05 | 601185.73 | -198814.32 | 750000 | 650000 | 650000 | 2850000.05 | 0 | N6387 | Controlled Entry Upgrades | 40000 | 108995.57 | 148995.57 | 3351.79 | -145643.78 | 0 | N7062 | Lanham Way | 3995002.01 | -3089171.67 | 905830.35 | 1389717.18
N6386 | Structural | 2000000 | 187754.28 | 2187754.28 | 15755.6 | -2171998.68 | 2000000 | 2000000 | 2000000 | 8187754.28 | 0 | N6388 | Major Voids | 500000 | -0.22 | 499999.78 | 732142.12 | 232142.34 | 0 | N7066 | Next Steps Accommodation Programme | 0 | 533228.49 | 533228.49 | 0
N6387 | Controlled Entry Upgrades | 100000 | 217991.14 | 317991.14 | 3351.79 | -314639.35 | 333000 | 75000 | 75000 | 800991.14 | 0 | N6389 | Damp-proof works | 0 | 21857.01 | 21857.01 | 0 | -21857.01 | 0 | N7067 | Renewal Of Fire Alarm Panels | 141156.4 | 20900.32 | 162056.72 | 29781
N6388 | Major Voids | 1000000 | -0.44 | 999999.56 | 775739.12 | -224260.44 | 1000000 | 1000000 | 1000000 | 3999999.56 | 0 | N6392 | Roofing | 0 | 95375.33 | 95375.33 | 0 | -95375.33 | 0 | N7068 | Juniper | 0 | 0 | 0 | 0
N6389 | Damp-proof works | 0 | 43714.02 | 43714.02 | 0 | -43714.02 | 0 | 0 | 0 | 43714.02 | 0 | N6395 | Electrics | 1078400 | -26038.07 | 1052361.93 | 300478.46 | -751883.47 | 0 | N7070 | Major Refurbishment Masons Road | 0 | 0 | 0 | 183157.35
N6392 | Roofing | 0 | 190750.66 | 190750.66 | 0 | -190750.66 | 0 | 0 | 0 | 190750.66 | 0 | N6434 | Doors and Windows | 0 | 0.25 | 0.25 | 0 | -0.25 | 0 | N7071 | Fencing | 366640 | 549960 | 916600 | 116646.12
N6395 | Electrics | 2000000 | -52076.13 | 1947923.87 | 213778.87 | -1734145 | 2000000 | 700000 | 500000 | 5147923.87 | 0 | N7020 | Extensions & Major Adaptions | 300000 | 463693.47 | 763693.47 | 189314.57 | -574378.9 | 0 | N7072 | QL Improvements | 224567 | 224567 | 449134 | 0
N6434 | Doors and Windows | 0 | 0.49 | 0.49 | 0 | -0.49 | 0 | 0 | 0 | 0.49 | 0 | N7026 | Communal Areas | 0 | 0.17 | 0.17 | 6533.1 | 6532.93 | 0 | N7073 | Southfield Park Leases | 1374900 | 0 | 1374900 | 0
N7020 | Extensions & Major Adaptions | 1000000 | 927386.93 | 1927386.93 | 77018.15 | -1850368.78 | 700000 | 700000 | 700000 | 4027386.93 | 0 | N7031 | Homes at Barton | 0 | 0 | 0 | 0 | 0 | #N/A | N7074 | Oxford North Develpment | 7658924.05 | 185.16 | 7659109.2 | 6498864.41
N7026 | Communal Areas | 0 | 0.33 | 0.33 | 11955.23 | 11954.9 | 0 | 0 | 0 | 0.33 | 0 | N7032 | Great Estates Programme | 0 | -0.01 | -0.01 | 0 | 0.01 | 0 | N7075 | LAHF Acquisitions | 0 | 1730602.21 | 1730602.21 | 1862001.04
N7031 | Homes at Barton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | N7033 | Energy Efficiency Initiatives | 3814400 | -287787.68 | 3526612.32 | 120865.01 | -3405747.31 | 0 | N7076 | Major Voids – Kitchens and Bathrooms | 0 | 0 | 0 | 379298.51
N7032 | Great Estates Programme | 0 | -0.03 | -0.03 | 0 | 0.03 | 0 | 0 | 0 | -0.03 | 0 | N7040 | Blackbird Leys Regeneration | 220185.6 | 424658.76 | 644844.36 | 1343998.75 | 699154.39 | 0 | N7077 | Climate Change | 0 | 0 | 0 | 0
N7033 | Energy Efficiency Initiatives | 7450000 | -575575.35 | 6874424.65 | 184461.65 | -6689963 | 12750000 | 2325000 | 2325000 | 24274424.65 | 0 | N7042 | Barton Regeneration | 0 | 299180.15 | 299180.15 | 0 | -299180.15 | 0 | N7078 | LAHF 2 Acquisitions | 0 | 882841.66 | 882841.66 | 824.5
N7040 | Blackbird Leys Regeneration | 1504000 | 849317.52 | 2353317.52 | 2000891.75 | -352425.77 | 172000 | 172000 | 172000 | 2869317.52 | 0 | N7044 | Lift Replacement & Refurbishment Programme | 0 | 1715.98 | 1715.98 | 34345.14 | 32629.16 | 0 | N7079 | SHAP Acquisitions | 0 | 0 | 0 | 599591.66
N7042 | Barton Regeneration | 0 | 598360.3 | 598360.3 | 0 | -598360.3 | 0 | 0 | 0 | 598360.3 | 0 | N7047 | Social Rented Housing Acquisitions | 0 | 0.08 | 0.08 | 97920.27 | 97920.19 | 0 | R0005 | MT Vehicles/Plant Replacement Programme. | 4954039.76 | -2948590.48 | 2005449.28 | 1473715.23
N7044 | Lift Replacement & Refurbishment Programme | 100000 | 3431.97 | 103431.97 | 34345.14 | -69086.83 | 550000 | 150000 | 150000 | 953431.97 | 0 | N7048 | Fire Door Installations | 555000 | 1035588.7 | 1590588.7 | 42766.86 | -1547821.84 | 0 | T2273 | Car Parks Resurfacing | 261600 | 0 | 261600 | 134091.34
N7047 | Social Rented Housing Acquisitions | 0 | 0.16 | 0.16 | 75628.29 | 75628.13 | 0 | 0 | 0 | 0.16 | 0 | N7049 | Compulsory purchase of property | 0 | 0 | 0 | 797.81 | 797.81 | 0 | T2299 | Controlled Parking Zones | 0 | 52239.8 | 52239.8 | 0
N7048 | Fire Door Installations | 1500000 | 2071177.4 | 3571177.4 | 18857.57 | -3552319.83 | 1500000 | 1500000 | 1500000 | 8071177.4 | 0 | N7050 | East Oxford development | 0 | 422185.25 | 422185.25 | 1445103.57 | 1022918.32 | 0 | T2301 | Depot Rationalisation | 206235 | 38396.37 | 244631.37 | 189170.21
N7049 | Compulsory purchase of property | 0 | 0 | 0 | 797.81 | 797.81 | 0 | 0 | 0 | 0 | 0 | N7051 | Acquisition of Additional Units | 0 | -1500000 | -1500000 | 0 | 1500000 | 0 | T2309 | Cowley Marsh Extension | 52246.2 | 23213.66 | 75459.86 | -142674.16
N7050 | East Oxford development | 6793288 | 844370.5 | 7637658.5 | 1814252.57 | -5823405.93 | 264385 | 0 | 0 | 7902043.5 | 0 | N7052 | HRA Stock Condition Survey | 133320 | 164286.45 | 297606.45 | 109947.18 | -187659.27 | 0
N7051 | Acquisition of Additional Units | 3000000 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N7054 | Properties Purchased From OCHL | 41842411 | -29886539.81 | 11955871.19 | 7943686.37 | -4012184.82 | 0
N7052 | HRA Stock Condition Survey | 400000 | 328572.9 | 728572.9 | 109947.18 | -618625.72 | 200000 | 0 | 0 | 928572.9 | 0 | N7057 | Kitchens | 0 | -0.1 | -0.1 | 0 | 0.1 | 0
N7054 | Properties Purchased From OCHL | 83684822 | -59773079.61 | 23911742.39 | 7943436.37 | -15968306.02 | 42139726 | 46264902 | 39787056 | 152103426.39 | 0 | N7058 | Bathrooms | 0 | -0.04 | -0.04 | 0 | 0.04 | 0
N7057 | Kitchens | 0 | -0.2 | -0.2 | 0 | 0.2 | 0 | 0 | 0 | -0.2 | 0 | N7059 | Boilers Only | 250000 | 412798.94 | 662798.94 | 854559.95 | 191761.01 | 0
N7058 | Bathrooms | 0 | -0.08 | -0.08 | 0 | 0.08 | 0 | 0 | 0 | -0.08 | 0 | N7060 | Heating Systems | 250000 | 23556.53 | 273556.53 | 21564.04 | -251992.49 | 0
N7059 | Boilers Only | 500000 | 825597.87 | 1325597.87 | 914162.93 | -411434.94 | 500000 | 500000 | 500000 | 2825597.87 | 0 | N7061 | Northfield Hostel | 4762061.5 | 6237820.24 | 10999881.74 | 1239045.19 | -9760836.55 | 0
N7060 | Heating Systems | 500000 | 47113.06 | 547113.06 | 21377.58 | -525735.48 | 500000 | 500000 | 500000 | 2047113.06 | 0 | N7062 | Lanham Way | 1592561 | 1763365.69 | 3355926.69 | 1952169.75 | -1403756.94 | 0
N7061 | Northfield Hostel | 9524123 | 12475640.48 | 21999763.48 | 1448834.52 | -20550928.96 | 10153801 | 701464 | 0 | 32855028.48 | 0 | N7066 | Next Steps Accommodation Programme | 0 | 290873.06 | 290873.06 | 0 | -290873.06 | 0
N7062 | Lanham Way | 3185122 | 3526731.38 | 6711853.38 | 1651487.57 | -5060365.81 | 1103548 | 0 | 0 | 7815401.38 | 0 | N7067 | Renewal Of Fire Alarm Panels | 30000 | 73510.5 | 103510.5 | 0 | -103510.5 | 0
N7066 | Next Steps Accommodation Programme | 0 | 581746.12 | 581746.12 | 0 | -581746.12 | 0 | 0 | 0 | 581746.12 | 0 | N7068 | Juniper | 0 | 192614.5 | 192614.5 | 0 | -192614.5 | 0
N7067 | Renewal Of Fire Alarm Panels | 60000 | 147021 | 207021 | 0 | -207021 | 60000 | 75000 | 60000 | 402021 | 0 | N7070 | Major Refurbishment Masons Road | 0 | 293089.26 | 293089.26 | -2818.23 | -295907.49 | 0
N7068 | Juniper | 0 | 385229 | 385229 | 0 | -385229 | 0 | 0 | 0 | 385229 | 0 | N7071 | Fencing | 0 | 125427.82 | 125427.82 | 0 | -125427.82 | 0
N7070 | Major Refurbishment Masons Road | 0 | 586178.52 | 586178.52 | -63509.61 | -649688.13 | 0 | 0 | 0 | 586178.52 | 0 | N7072 | QL Improvements | 0 | 122500 | 122500 | 0 | -122500 | 0
N7071 | Fencing | 0 | 250855.63 | 250855.63 | 0 | -250855.63 | 0 | 0 | 0 | 250855.63 | 0 | N7073 | Southfield Park Leases | 0 | 750000 | 750000 | 0 | -750000 | 0
N7072 | QL Improvements | 0 | 245000 | 245000 | 0 | -245000 | 0 | 0 | 0 | 245000 | 0 | N7074 | Oxford North Develpment | 6769252.5 | 578328.63 | 7347581.13 | 1017088.88 | -6330492.25 | 0
N7073 | Southfield Park Leases | 0 | 1500000 | 1500000 | 0 | -1500000 | 0 | 0 | 0 | 1500000 | 0 | N7075 | LAHF Acquisitions | 0 | 156352.17 | 156352.17 | -4426.18 | -160778.35 | 0
N7074 | Oxford North Develpment | 13538505 | 1156657.27 | 14695162.27 | 1018964.78 | -13676197.49 | 8114472 | 1525090 | 1283000 | 25617724.27 | 0 | N7076 | Major Voids – Kitchens and Bathrooms | 0 | 249999.98 | 249999.98 | 74609.77 | -175390.21 | 0
N7075 | LAHF Acquisitions | 0 | 312704.34 | 312704.34 | -2976.18 | -315680.52 | 0 | 0 | 0 | 312704.34 | 0 | N7077 | Climate Change | 0 | 0 | 0 | 0 | 0 | 0
N7076 | Major Voids – Kitchens and Bathrooms | 0 | 499999.96 | 499999.96 | 74609.77 | -425390.19 | 0 | 0 | 0 | 499999.96 | 0 | N7078 | LAHF 2 Acquisitions | 0 | 345339.26 | 345339.26 | 1020101.3 | 674762.04 | 0
N7077 | Climate Change | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 8000000 | 0 | N7079 | SHAP Acquisitions | 0 | 104999.9 | 104999.9 | 237881.41 | 132881.51 | 0
N7078 | LAHF 2 Acquisitions | 0 | 690678.52 | 690678.52 | 1019101.3 | 328422.78 | 0 | 0 | 0 | 690678.52 | 0 | N7080 | Retained Right to Buy Receipts (Acquisitions) | 0 | 1500000 | 1500000 | 1036973.3 | -463026.7 | 0
N7079 | SHAP Acquisitions | 0 | 209999.81 | 209999.81 | 239331.41 | 29331.6 | 0 | 0 | 0 | 209999.81 | 0 | N7081 | Retained Right to Buy Receipts (Additional) | 500000 | 0 | 500000 | 0 | -500000 | 0
N7080 | Retained Right to Buy Receipts (Acquisitions) | 0 | 3000000 | 3000000 | 1236431.95 | -1763568.05 | 3000000 | 3000000 | 15000000 | 24000000 | 0 | N7084 | Alice Smith (Heating) | 100000 | 0 | 100000 | 0 | -100000 | 0
N7081 | Retained Right to Buy Receipts (Additional) | 1000000 | 0 | 1000000 | 0 | -1000000 | 0 | 0 | 0 | 1000000 | 0 | N7085 | Renewal of Solar and Energy infrastructure | 7500 | 0 | 7500 | 0 | -7500 | 0
N7084 | Alice Smith (Heating) | 200000 | 0 | 200000 | 0 | -200000 | 0 | 0 | 0 | 200000 | 0 | N7086 | Extensions (5/6 Beds) | 150000 | -150000 | 0 | 0 | 0 | 0
N7085 | Renewal of Solar and Energy infrastructure | 15000 | 0 | 15000 | 0 | -15000 | 15000 | 0 | 15000 | 45000 | 0 | N7087 | SHWP Urgent Works | 250000 | 0 | 250000 | 0 | -250000 | 0
N7086 | Extensions (5/6 Beds) | 300000 | -300000 | 0 | 0 | 0 | 600000 | 0 | 0 | 600000 | 0 | N7088 | Tower Blocks Additional Works | 750000 | -750000 | 0 | 0 | 0 | 0
N7087 | SHWP Urgent Works | 500000 | 0 | 500000 | 0 | -500000 | 0 | 0 | 0 | 500000 | 0 | N7089 | Housing for Older People - white goods and communal areas | 25000 | 0 | 25000 | 0 | -25000 | 0
N7088 | Tower Blocks Additional Works | 1500000 | -1500000 | 0 | 0 | 0 | 2500000 | 1000000 | 0 | 3500000 | 0 | N7090 | Digital Noticeboards for towerblocks | 25000 | 0 | 25000 | 0 | -25000 | 0
N7089 | Housing for Older People - white goods and communal areas | 50000 | 0 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 0 | N7091 | Capital R&M Works Investment | 1250000 | 0 | 1250000 | 0 | -1250000 | 0
N7090 | Digital Noticeboards for towerblocks | 50000 | 0 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 0 | N7092 | Communal Capital investment works to Council Homes | 2250000 | 560269.5 | 2810269.5 | 67177.48 | -2743092.02 | 0
N7091 | Capital R&M Works Investment | 2500000 | 0 | 2500000 | 0 | -2500000 | 0 | 0 | 0 | 2500000 | 0 | N7093 | ExternalCapital investment works to Council Homes | 2250000 | -185980 | 2064020 | 1015000.41 | -1049019.59 | 0
N7092 | Communal Capital investment works to Council Homes | 4500000 | 1120539 | 5620539 | 26920.25 | -5593618.75 | 4500000 | 4500000 | 4500000 | 19120539 | 0 | N7094 | Internal Capital investment works to Council Homes | 1750000 | 188883.5 | 1938883.5 | 1639268.99 | -299614.51 | 0
N7093 | ExternalCapital investment works to Council Homes | 4500000 | -371960 | 4128040 | 942112.6 | -3185927.4 | 4500000 | 4000000 | 0 | 12628040 | 0 | N7095 | Tower Blocks - Fire Alarm System Replacement | 0 | 0 | 0 | 0 | 0 | 0
N7094 | Internal Capital investment works to Council Homes | 3500000 | 377767 | 3877767 | 1563687.71 | -2314079.29 | 3500000 | 3500000 | 7500000 | 18377767 | 0 | N7096 | Stock Decency Improvement Works (Legislative) | 0 | 0 | 0 | 0 | 0 | 0
N7095 | Tower Blocks - Fire Alarm System Replacement | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 800000 | 0 | N7097 | Leiden Road (c. 12 affordable homes) | 0 | 0 | 0 | 0 | 0 | 0
N7096 | Stock Decency Improvement Works (Legislative) | 0 | 0 | 0 | 0 | 0 | 5000000 | 10000000 | 10000000 | 25000000 | 0 | N7098 | Underhill Circus (c. 11 affordable homes) | 0 | 0 | 0 | 0 | 0 | 0
N7097 | Leiden Road (c. 12 affordable homes) | 0 | 0 | 0 | 0 | 0 | 898000 | 2705000 | 457000 | 4060000 | 0 | N7099 | Additional Units (RRTBR) | 0 | 0 | 0 | 0 | 0 | 0
N7098 | Underhill Circus (c. 11 affordable homes) | 0 | 0 | 0 | 0 | 0 | 698000 | 2193000 | 509000 | 3400000 | 0 | N7100 | Additonal Programme (RRTBRs) | 0 | 0 | 0 | 0 | 0 | 0
N7099 | Additional Units (RRTBR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | R0005 | MT Vehicles/Plant Replacement Programme. | 2887139.5 | -1137139.4 | 1750000.1 | 648122.35 | -1101877.75 | 0
N7100 | Additonal Programme (RRTBRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T2273 | Car Parks Resurfacing | 100000 | -25000.23 | 74999.77 | 42346.62 | -32653.15 | 0
R0005 | MT Vehicles/Plant Replacement Programme. | 5774279 | -2274278.81 | 3500000.19 | 559613.77 | -2940386.42 | 7301909 | 3256938 | 3000000 | 17058847.19 | 0 | T2299 | Controlled Parking Zones | 0 | 221500 | 221500 | 0 | -221500 | 0
T2273 | Car Parks Resurfacing | 200000 | -50000.46 | 149999.54 | 42346.62 | -107652.92 | 138692 | 0 | 0 | 288691.54 | 0 | T2301 | Depot Rationalisation | 0 | 133322.5 | 133322.5 | 0 | -133322.5 | 0
T2299 | Controlled Parking Zones | 0 | 443000 | 443000 | 0 | -443000 | 0 | 0 | 0 | 443000 | 0 | T2309 | Cowley Marsh Extension | 0 | 17329.39 | 17329.39 | 100 | -17229.39
T2301 | Depot Rationalisation | 0 | 266645 | 266645 | 0 | -266645 | 0 | 0 | 0 | 266645 |  |  |  | 111534859.04 | 1799733.91 | 113334592.95 | 50830555.79 | -62504037.17
T2309 | Cowley Marsh Extension | 0 | 34658.79 | 34658.79 | 100 | -34558.79 | 0 | 0 | 0 | 34658.79
|  | 235437316.26 | 3753313.98 | 239190630.24 | 49382866.8 | -189807763.44 | 204905716.83 | 165841194.87 | 153651418.15 | 763588960.1
Note on H50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sonal - previous approval to reduce £540k down to £100k for 24/25 - not actioned - ok to no action???

## Jan Budget Rec (hidden)
Cost Centre | Account | Batch | Transaction Date | Amount | Note
B0100 | Y000 | OX-1003892 | 2023-01-20 | 46000 | Correction to Budget to match approved sum
|  | OX-1003892 |  | 46000
B0152 | Y000 | OX-1003893 | 2023-01-23 | 117000 | Q3 Monitoring Adjustments
F7011 | Y000 | OX-1003893 | 2023-01-23 | -27731 | Q3 Monitoring Adjustments
F7024 | Y000 | OX-1003893 | 2023-01-23 | -18803 | Q3 Monitoring Adjustments
|  | OX-1003893 |  | 70466
B0081 | Y000 | OX-1003912 | 2023-02-06 | -103000 | Roken House Budget Increase
M5026 | Y000 | OX-1003912 | 2023-02-06 | -107000 | Roken House Budget Increase
M5038 | Y000 | OX-1003912 | 2023-02-06 | 210000 | Roken House Budget Increase
|  | OX-1003912 |  | 0
A4820 | Y000 | OX-1003913 | 2023-02-07 | -35000 | Q3 Slippage
A4853 | Y000 | OX-1003913 | 2023-02-07 | -27456 | Q3 Slippage
B0083 | Y000 | OX-1003913 | 2023-02-07 | -310000 | Q3 Slippage
B0116 | Y000 | OX-1003913 | 2023-02-07 | -100000 | Q3 Slippage
B0117 | Y000 | OX-1003913 | 2023-02-07 | 2200 | Q3 Slippage
B0119 | Y000 | OX-1003913 | 2023-02-07 | -66682 | Q3 Slippage
B0120 | Y000 | OX-1003913 | 2023-02-07 | -200000 | Q3 Slippage
B0122 | Y000 | OX-1003913 | 2023-02-07 | -729764 | Q3 Slippage
B0129 | Y000 | OX-1003913 | 2023-02-07 | -8000 | Q3 Slippage
B0138 | Y000 | OX-1003913 | 2023-02-07 | -400000 | Q3 Slippage
B0142 | Y000 | OX-1003913 | 2023-02-07 | -747500 | Q3 Slippage
B0144 | Y000 | OX-1003913 | 2023-02-07 | -180000 | Q3 Slippage
C3044 | Y000 | OX-1003913 | 2023-02-07 | -20000 | Q3 Slippage
C3060 | Y000 | OX-1003913 | 2023-02-07 | -164022 | Q3 Slippage
C3084 | Y000 | OX-1003913 | 2023-02-07 | -105000 | Q3 Slippage
E3521 | Y000 | OX-1003913 | 2023-02-07 | 200000 | Q3 Slippage
E3565 | Y000 | OX-1003913 | 2023-02-07 | -111000 | Q3 Slippage
F7024 | Y000 | OX-1003913 | 2023-02-07 | -31197 | Q3 Slippage
M5024 | Y000 | OX-1003913 | 2023-02-07 | -1000000 | Q3 Slippage
M5025 | Y000 | OX-1003913 | 2023-02-07 | -501865 | Q3 Slippage
M5032 | Y000 | OX-1003913 | 2023-02-07 | -501865 | Q3 Slippage
M5033 | Y000 | OX-1003913 | 2023-02-07 | -100001 | Q3 Slippage
M5037 | Y000 | OX-1003913 | 2023-02-07 | -1000000 | Q3 Slippage
N6384 | Y000 | OX-1003913 | 2023-02-07 | -353642 | Q3 Slippage
N6385 | Y000 | OX-1003913 | 2023-02-07 | 294000 | Q3 Slippage
N6386 | Y000 | OX-1003913 | 2023-02-07 | -1216475 | Q3 Slippage
N6387 | Y000 | OX-1003913 | 2023-02-07 | 80000 | Q3 Slippage
N6388 | Y000 | OX-1003913 | 2023-02-07 | -99650 | Q3 Slippage
N7047 | Y000 | OX-1003913 | 2023-02-07 | -368236 | Q3 Slippage
N7048 | Y000 | OX-1003913 | 2023-02-07 | 310000 | Q3 Slippage
N7050 | Y000 | OX-1003913 | 2023-02-07 | -81000 | Q3 Slippage
N7052 | Y000 | OX-1003913 | 2023-02-07 | -233753 | Q3 Slippage
N7054 | Y000 | OX-1003913 | 2023-02-07 | -219000 | Q3 Slippage
N7055 | Y000 | OX-1003913 | 2023-02-07 | 737 | Q3 Slippage
N7057 | Y000 | OX-1003913 | 2023-02-07 | -6096 | Q3 Slippage
N7058 | Y000 | OX-1003913 | 2023-02-07 | -12244 | Q3 Slippage
N7061 | Y000 | OX-1003913 | 2023-02-07 | -237000 | Q3 Slippage
R0005 | Y000 | OX-1003913 | 2023-02-07 | -381942 | Q3 Slippage
T2299 | Y000 | OX-1003913 | 2023-02-07 | -300000 | Q3 Slippage
T2309 | Y000 | OX-1003913 | 2023-02-07 | -57000 | Q3 Slippage
|  | OX-1003913 |  | -9018453
M5026 | Y000 | OX-1003915 | 2023-02-07 | -10722835 | Q3 Underspend Adj
|  | OX-1003915 |  | -10722835
-19624822

## Budget Reconcilliation (hidden)
Cost Centre | Account | Batch | Transaction Date | Amount | Note
B0092 | Y000 | OX-1003769 | 2022-11-07 | -315137 | P6 Slippage
B0112 | Y000 | OX-1003769 | 2022-11-07 | -71063 | P6 Slippage
B0127 | Y000 | OX-1003769 | 2022-11-07 | -141000 | P6 Slippage
B0133 | Y000 | OX-1003769 | 2022-11-07 | -50000 | P6 Slippage
B0141 | Y000 | OX-1003769 | 2022-11-07 | -130000 | P6 Slippage
B0147 | Y000 | OX-1003769 | 2022-11-07 | -270000 | P6 Slippage
N6387 | Y000 | OX-1003769 | 2022-11-07 | -274522 | P6 Slippage
N6390 | Y000 | OX-1003769 | 2022-11-07 | -606704 | N6390 Kitchens & Bathrooms Split
N6390 | Y000 | OX-1003769 | 2022-11-07 | -86592 | P6 Slippage
N6391 | Y000 | OX-1003769 | 2022-11-07 | -489372 | N6391 Heating Split
N6391 | Y000 | OX-1003769 | 2022-11-07 | -1404303 | P6 Slippage
N7020 | Y000 | OX-1003769 | 2022-11-07 | -1055892 | P6 Slippage
N7026 | Y000 | OX-1003769 | 2022-11-07 | -581773 | P6 Slippage
N7032 | Y000 | OX-1003769 | 2022-11-07 | -688254 | P6 Slippage
N7042 | Y000 | OX-1003769 | 2022-11-07 | -588150 | P6 Slippage
N7044 | Y000 | OX-1003769 | 2022-11-07 | -363899 | P6 Slippage
N7047 | Y000 | OX-1003769 | 2022-11-07 | 2050318 | N7051 Vire to N7048
N7048 | Y000 | OX-1003769 | 2022-11-07 | -1837594 | P6 Slippage
N7051 | Y000 | OX-1003769 | 2022-11-07 | -2050318 | N7051 Vire to N7047
N7055 | Y000 | OX-1003769 | 2022-11-07 | -737 | P6 Slippage
N7057 | Y000 | OX-1003769 | 2022-11-07 | 526486 | N6390 Kitchens & Bathrooms Split
N7058 | Y000 | OX-1003769 | 2022-11-07 | 80218 | N6390 Kitchens & Bathrooms Split
N7060 | Y000 | OX-1003769 | 2022-11-07 | 489372 | N6391 Heating Split
N7067 | Y000 | OX-1003769 | 2022-11-07 | -52000 | P6 Slippage
N7070 | Y000 | OX-1003769 | 2022-11-07 | -250000 | P6 Slippage
|  | OX-1003769 Total |  | -8160916
N6390 | Y000 | OX-1003771 | 2022-11-07 | -606704 | P6 Slippage | think this is wrong - should be £86,592 only
|  | OX-1003771 Total |  | -606704
C3068 | Y000 | OX-1003786 | 2022-11-14 | -88600 | Website Redesign
C3082 | Y000 | OX-1003786 | 2022-11-14 | 88600 | Website Redesign
|  | OX-1003786 Total |  | 0
C3082 | Y000 | OX-1003787 | 2022-11-14 | 20000 | Website Redesign
|  | OX-1003787 Total |  | 20000
B0074 | Y000 | OX-1003789 | 2022-11-15 | 4500 | P6 Feasibility Bfwd
|  | OX-1003789 Total |  | 4500
|  | Grand Total |  | -8743120

## HRA budget (hidden)
|  | Latest budget 21/22 | Final spend 21/22 | Budget Remaining 21/22 | C/fwd | under/overspend | Original Budget 2022/23 | Revised 22/23 with carry forwards | Proposed adjustments | reprofiling | Adj between MTFP and final latest budget | Revised 22/23 budget |  | Jason's reconciliation | Difference
as per App 6
N6384 | Tower Blocks | 998849 | 115207 | 883642 | 883642 |  | 0 | 883642 |  |  |  | 883642 |  | 883642 | 0
N6385 | Adaptations for disabled | 704000 | 1066103 | -362103 |  | -362103 | 756000 | 756000 | 400000 |  |  | 1156000 |  | 1156000 | 0
N6386 | Structural | 800000 | 516992 | 283008 | 283008 |  | 2000000 | 2283008 |  |  | 433466.62 | 2716474.62 |  | 2716475 | 0.38
N6387 | Controlled Entry | 221083 | 209561 | 11522 | 11522 |  | 133000 | 144522 |  |  | 150000 | 294522 |  | 294522 | 0
N6388 | Major Voids | 300000 | 372350 | -72350 | -72350 |  | 515000 | 442650 |  |  | 172000 | 614650 |  | 614650 | 0
N6389 | Damp-proof works (K&B) | 100006 | 96123 | 3883 | 3883 |  | 75000 | 78883 |  |  | 44000 | 122883 |  | 122883 | 0
N6390 | Kitchens and Bathrooms | 0 |  | 0 |  |  | 1300000 | 1300000 |  |  |  | 1300000 |  | 1300000 | 0
N6391 | Heating |  |  | 0 |  |  | 2352000 | 2352000 | -458325 |  |  | 1893675 |  | 1893675 | 0
N6392 | Roofing | 1040000 | 1278332 | -238332 | -238332 |  | 700000 | 461668 |  |  | 263521 | 725189 |  | 725189 | 0
N6395 | Electrics | 711296 | 732997 | -21701 | -21701 |  | 695000 | 673299 |  |  | 619175 | 1292474 |  | 1292474 | 0
N6434 | Doors and Windows | 490123 | 596036 | -105913 | -105913 |  | 500000 | 394087 |  |  | 113000 | 507087 |  | 507087 | 0
N7020 | Extensions & Major Adaptions | 424672 | 53780 | 370892 | 370892 |  | 735000 | 1105892 |  |  |  | 1105892 |  | 1105892 | 0
N7026 | Communal Areas | 60000 | 30116 | 29884 | 29884 |  | 213000 | 242884 |  |  | 488889 | 731773 |  | 731773 | 0
N7032 | Great Estates Programme | 1100000 | 747183 | 352817 | 352817 |  | 1109000 | 1461817 |  |  | 126437 | 1588254 |  | 1588255 | 1
N7033 | Energy Efficiency Initiatives | 802786 | 711871 | 90915 | 90915 |  | 1985000 | 2075915 |  |  |  | 2075915 |  | 2075915 | 0
N7040 | Blackbird Leys Regeneration (HRA) | 109716 | 173095 | -63379 | -63379 |  | 325000 | 261621 |  |  | 163450 | 425071 |  | 425071 | 0
N7042 | Barton Regeneration | 28277 | 10127 | 18150 | 18150 |  | 0 | 18150 |  |  | 600000 | 618150 |  | 618150 | 0
N7044 | Lift Replacement Programme | 285000 | 161287 | 123713 | 123713 |  | 125000 | 248713 |  |  | 125186 | 373899 |  | 373899 | 0
N7047 | Social Rented Housing Acquisitions | 3734246 | 3416328 | 317918 | 317918 |  | 0 | 317918 |  |  | 500000 | 817918 |  | 817918 | 0
N7048 | Fire doors | 260000 | 31385 | 228615 | 228615 |  | 1500000 | 1728615 |  |  | 608979 | 2337594 |  | 2337594 | 0
N7050 | East Oxford development | 610000 | 2940 | 607060 | 607060 |  | 2813000 | 3420060 |  |  |  | 3420060 |  | 3420060 | 0
N7051 | Acquisition of Additional Units | 3231081 | 3205763 | 25318 | 25318 |  | 2000000 | 2025318 |  |  | 25000 | 2050318 |  | 2050318 | 0
N7052 | HRA Stock Condition Survey | 142729 | 3976 | 138753 | 138753 |  | 195000 | 333753 |  |  |  | 333753 |  | 333753 | 0
N7054 | Properties Purchased From OCHL | 22467700 | 23935127 | -1467427 | -1467427 |  | 74698000 | 73230573 | -51170 | -31447512 |  | 41731891 |  | 41731891 | 0 | 12592961
N7055 | Use Of Recycled Capital Grants | 368000 | 340263 | 27737 | 27737 |  | 0 | 27737 |  |  |  | 27737 |  | 27737 | 0
N7057 | Kitchens | 1017495 | 985020 | 32475 | 32475 |  | 0 | 32475 |  |  | 641039 | 673514 |  | 673514 | 0
N7058 | Bathrooms | 726300 | 758249 | -31949 | -31949 |  | 0 | -31949 |  |  | 457731 | 425782 |  | 425782 | 0
N7059 | Boilers Only | 780804 | 837243 | -56439 | -56439 |  | 0 | -56439 |  |  | 816087 | 759648 |  | 680241 | -79407
N7060 | Heating Systems | 63336 | 521661 | -458325 | -458325 |  | 0 | -458325 | 458325 |  |  | 0 |  |  | 0
N7061 | Northfield Hostel | 1773000 | 38884 | 1734116 | 1734116 |  | 11740000 | 13474116 | 1868884 | -13396000 |  | 1947000 |  | 1947000 | 0
N7062 | Lanham Way | 985000 | 171970 | 813030 | 813030 |  | 3555000 | 4368030 |  |  |  | 4368030 |  | 4368030 | 0
N7068 | Juniper |  | 51170 | -51170 | -51170 |  | 1586000 | 1534830 | 51170 |  |  | 1586000 |  | 1586000 | 0
N7064 | Unallocated Site 1 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  |  | 0
N7065 | Unallocated Site 2 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  |  | 0
N7066 | Next Steps Accommodation Programme | 2992584 | 2281801 | 710783 | 710783 |  | 0 | 710783 |  |  |  | 710783 |  | 710783 | 0
N7067 | Renewal Of Fire Alarm Panels |  |  | 0 |  |  | 102000 | 102000 | -102000 |  | 102000 | 102000 |  | 102000 | 0
N7070 | Major Refurbishment Masons Road |  |  | 0 |  |  | 750000 | 750000 |  |  |  | 750000 |  | 750000 | 0
|  | 47328083 | 43452940 | 3875143 | 4237246 | -362103 | 112457000 | 116694246 | 2166884 | -44843512 | 6449960.62 | 80467578.62 | 0 | 80388173 | -79405.62
[5 empty] | 31142545.98 | [5 empty] | 0
119818

## Update Summary (hidden)
Smartsheet Updates by Service Area
Updates last month (December monitoring)
|  | Live Projects | Comments Updated |  | Forecasts Updated |  | Key Risks Updated |  | Milestones Updated
Development Directorate
| Planning | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0%
| Regeneration & Economy | 19 | 3 | 15.79% | 6 | 31.58% | 3 | 15.79% | 3 | 15.79%
| Corporate Property | 15 | 0 | 0% | 2 | 13.33% | 1 | 6.667% | 3 | 20%
| Housing Development | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
| Housing Services - GF | 3 | 1 | 33.33% | 0 | 0% | 1 | 33.33% | 0 | 0%
| Housing Services - HRA | 34 | 6 | 17.65% | 12 | 35.29% | 0 | 0% | 1 | 2.941%
Communities and People
| Community Services | 5 | 3 | 60% | 2 | 40% | 1 | 20% | 1 | 20%
| Regulatory & Community Safety | 4 | 0 | 0% | 1 | 25% | 0 | 0% | 1 | 25%
Chief Exec and Corporate Resources
| Environmental Sustainability | 8 | 5 | 62.5% | 2 | 25% | 3 | 37.5% | 3 | 37.5%
| Oxford Direct Services | 7 | 2 | 28.57% | 1 | 14.29% | 1 | 14.29% | 1 | 14.29%
| Financial Services | 5 | 1 | 20% | 0 | 0% | 1 | 20% | 0 | 0%
| Business Improvement | 6 | 3 | 50% | 0 | 0% | 0 | 0% | 0 | 0%
|  | 111 | 25 | 22.52% | 26 | 23.42% | 11 | 9.91% | 13 | 11.71%
Updates in last 3 months October to December
|  | Live Projects | Comments Updated |  | Forecasts Updated |  | Key Risks Updated |  | Milestones Updated
Development Directorate
| Planning | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0%
| Regeneration & Economy | 18 | 18 | 100% | 14 | 77.78% | 15 | 83.33% | 16 | 88.89%
| Corporate Property | 15 | 7 | 46.67% | 9 | 60% | 4 | 26.67% | 5 | 33.33%
| Housing Development | 3 | 0 | 0% | 1 | 33.33% | 0 | 0% | 0 | 0%
| Housing Services - GF | 4 | 0 | 0% | 1 | 25% | 0 | 0% | 0 | 0%
| Housing Services - HRA | 34 | 5 | 14.71% | 13 | 38.24% | 3 | 8.824% | 3 | 8.824%
Communities and People
| Community Services | 4 | 3 | 75% | 2 | 50% | 3 | 75% | 3 | 75%
| Regulatory & Community Safety | 4 | 2 | 50% | 1 | 25% | 0 | 0% | 1 | 25%
Chief Exec and Corporate Resources
| Environmental Sustainability | 7 | 7 | 100% | 1 | 14.29% | 6 | 85.71% | 7 | 100%
| Financial Services | 3 | 2 | 66.67% | 2 | 66.67% | 1 | 33.33% | 1 | 33.33%
| Oxford Direct Services | 9 | 9 | 100% | 2 | 22.22% | 4 | 44.44% | 3 | 33.33%
| Business Improvement | 6 | 5 | 83.33% | 4 | 66.67% | 0 | 0% | 5 | 83.33%
|  | 108 | 59 | 54.63% | 51 | 47.22% | 36 | 33.33% | 44 | 40.74%
Updates in 21/22 Financial Year April to November
|  | Live Projects | Comments Updated |  | Forecasts Updated |  | Key Risks Updated |  | Milestones Updated
Development Directorate
| Planning | 1 | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0%
| Regeneration & Economy | 19 | 19 | 100% | 17 | 89.47% | 14 | 73.68% | 18 | 94.74%
| Corporate Property | 15 | 12 | 80% | 8 | 53.33% | 8 | 53.33% | 8 | 53.33%
| Housing Services - need to split out | 41 | 39 | 95.12% | 34 | 82.93% | 18 | 43.9% | 18 | 43.9%
Communities and People
| Community Services | 4 | 3 | 75% | 3 | 75% | 5 | 125% | 3 | 75%
| Regulatory & Community Safety | 4 | 4 | 100% | 3 | 75% | 0 | 0% | 2 | 50%
Chief Exec and Corporate Resources
| Environmental Sustainability | 7 | 7 | 100% | 6 | 85.71% | 6 | 85.71% | 7 | 100%
| Financial Services | 3 | 3 | 100% | 3 | 100% | 2 | 66.67% | 2 | 66.67%
| Oxford Direct Services | 11 | 11 | 100% | 8 | 72.73% | 7 | 63.64% | 6 | 54.55%
| Business Improvement | 6 | 6 | 100% | 5 | 83.33% | 2 | 33.33% | 6 | 100%
|  | 111 | 105 | 94.59% | 88 | 79.28% | 63 | 56.76% | 70 | 63.06%

## Smartsheet Data 161024 (hidden)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 1900-01-17 | 19 | 20 | 21 | 22 | 1900-01-22 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308
Scheme Name | Scheme Description | Capital Code | Primary Reporting Board/Owning Group | Programme | Directorate | Service Area | DB Update Request Group | Type of Scheme | Senior Responsible Officer | Scheme Sponsor | Business Owner | Programme Manager | Project OR Client Manager | External Project Manager | Progress Update Provider (Contact field) | Capital Project Classification | Stage/Gateway | Project Update (latest progress overview) | Project Start Date | Target Completion Date | Next Key Milestone 1 - Description / Target Date | Key Milestone 2 - Description / Target Date | Key Milestone 3 - Description / Target Date | Next Key Milestone Target Date | Project Status | Cost / Budget Status | Time Status | Risk Status | Issue Status | Benefits Status | Key Activities completed LAST MONTH | Activities to be completed NEXT PERIOD | Off Target Reasons | Key Risks and Mitigations | Key Issues to Address (100 words) | Issues/Blockers for resolution by Programme Board | Action requested of CMT | Advise Carbon Reduction Measures (100 words) | Any unexpected or really good benefits to the coun | Budget | Original Budget 2024/25 | Latest Budget 2024/25 | Budget 2025/26 | Budget 2026/27 | Budget 2027/28 | Total Budget 24/25 to 27/28 | Actual 2024/25 Spend to Date | Project Manager Forecast 2024/25 Spend | Forecast Variance 2024/25 | 2024/25 Variance Category (where applicable) | Reason for Budget Variance (for public reporting) | Forecast total spend in year Apr 24/Mar 25 | Forecast total spend in year Apr 25/ Mar 26 | Forecast total spend in year Apr 27/28 onwards | Forecast Variance 25/26 | Forecast Variance 26/27 | Forecast Variance 27/28 | Future Years Variance Total | Forecast at Previous Quarter | Change in Forecast since Last Quarter | Reason for Movement in Forecast since last Quarter | Annual Contract Value | Likely Capital Expenditure | Likely New Bids Needed | Overall Project Budget | HL Report? | CDM Applicable? | Building Safety & Compliance Team Informed? | CDM - Pre Construction Phase | PM/Sponsor satisfied responsibilities being met? | Is there a plan in place to mitigate? | Detail the plan in place (see client checklist) | CDM - Construction Phase | PM/Sponsor satisfied requirements met/updated? | What requirement is un-met (see client checklist)? | What hasn't been updated (see client checklist)? | CDM - Principal Designer | CDM - Principal Contractor | CDM / Health & Safety Comments | ODS Opportunity (Yes, No, Unsure) | ODS Description - Work Type / Timing / Risks | Estimated Value of ODS Work in 2023/24 £ | Has the PM provided an update? | Request update | Priority | Period | Incumbent Supplier | Contract Expiry Date | Finance | ARG / DRG | Ward | Ward Councillor | Key Approvals Date | Key approval stage | Housing Supply Board Only Fields | Update Request Filter | Growth Deal Year | Growth Deal Y/N | Housing scheme Type | OX Place involvement | HELAA Reference | RP Name | Land Ownership | Homes England AH Programme | Total Units - Indicative Programme | Social Rent Units | Affordable Rent Units | Shared Ownership Units | First Homes | Market Sale | Market Rent | Other | Supported Accommodation | Total Affordable Units Forecast | Total Forecast Units | Total Units Delivered | Programme Milestone - Planning Submission Date | Programme Milestone - Planning Consent Date | Programme Milestone - CSOS Date | Programme Milestone - SOS Date | Programme Milestone - PC Date | Planning Stage | Planning App Ref | Forecast Planning Submission Date | Forecast Planning Consent Date | Forecast Tender Award Date | Forecast Build Contract Signed Date | Forecast Start on Site Date | Forecast Practical Completion Date | Actual Planning Submission Date | Actual Planning Consent Date | Actual CSOS Date | Actual SOS Date | Actual PC Date | Forecast Total Handovers 2023/24 | Forecast SR Handovers 2023/24 | Forecast AR Handovers 2023/24 | Forecast SO Handovers 2023/24 | Forecast FH Handovers 2023/24 | Forecast Supported/other Handovers 2023/24 | Forecast Total Handovers 2024/25 | Forecast SR Handovers 2024/25 | Forecast AR Handovers 2024/25 | Forecast SO Handovers 2024/25 | Forecast FH Handovers 2024/25 | Forecast Supported/other Handovers 2024/25 | Forecast Total Handovers 2025/26 | Forecast SR Handovers 2025/26 | Forecast AR Handovers 2025/26 | Forecast SO Handovers 2025/26 | Forecast FH Handovers 2025/26 | Forecast Supported/other Handovers 2025/26 | Forecast Total Handovers 2026/27 | Forecast SR Handovers 2026/27 | Forecast AR Handovers 2026/27 | Forecast SO Handovers 2026/27 | Forecast FH Handovers 2026/27 | Forecast Supported/other Handovers 2026/27 | Total units out of scope/comments | Housing Overall Status | Housing Financial risk | Housing Technical/ Build issues | Housing Environmental/ Infrastructure risk | Housing Planning risk | Housing Community Support issues | Housing Market risk | Housing Legal/ Land/ Title issues/ risk | Housing Time Delay | Housing - General comments | Housing Supply Board approval date | Site Latitude | Site Longitude | Flat 1b1p - Social Rent | Flat 1b2p - Social Rent | Flat 2b3p - Social Rent | Flat 2b4p - Social Rent | Flat 3b4p - Social Rent | Flat 3b5p - Social Rent | Flat 3b6p - Social Rent | Flat 4b5p - Social Rent | Flat 4b6p - Social Rent | Flat 4b7p - Social Rent | Flat 4b8p - Social Rent | House 1b2p - Social Rent | House 2b3p - Social Rent | House 2b4p - Social Rent | House 3b4p - Social Rent | House 3b5p - Social Rent | House 3b6p - Social Rent | House 4b5p - Social Rent | House 4b6p - Social Rent | House 4b7p - Social Rent | House 4b8p - Social Rent | House 5b6p - Social Rent | House 5b7p - Social Rent | House 5b8p - Social Rent | House 5b9p - Social Rent | House 6b10p - Social Rent | Bungalow 1b2p - Social Rent | Bungalow 2b3p - Social Rent | Bungalow 2b4p - Social Rent | Bungalow 3b5p - Social Rent | Flat 1b1p - Affordable Rent | Flat 1b2p - Affordable Rent | Flat 2b3p - Affordable Rent | Flat 2b4p - Affordable Rent | Flat 3b4p - Affordable Rent | Flat 3b5p - Affordable Rent | Flat 3b6p - Affordable Rent | Flat 4b5p - Affordable Rent | Flat 4b6p - Affordable Rent | Flat 4b7p - Affordable Rent | Flat 4b8p - Affordable Rent | House 1b2p - Affordable Rent | House 2b3p - Affordable Rent | House 2b4p - Affordable Rent | House 3b4p - Affordable Rent | House 3b5p - Affordable Rent | House 3b6p - Affordable Rent | House 4b5p - Affordable Rent | House 4b6p - Affordable Rent | House 4b7p - Affordable Rent | House 4b8p - Affordable Rent | House 5b6p - Affordable Rent | House 5b7p - Affordable Rent | House 5b8p - Affordable Rent | House 5b9p - Affordable Rent | House 6b10p - Affordable Rent | Bungalow 1b2p - Affordable Rent | Bungalow 2b3p - Affordable Rent | Bungalow 2b4p - Affordable Rent | Bungalow 3b5p - Affordable Rent | Flat 1b1p - Shared Ownership | Flat 1b2p - Shared Ownership | Flat 2b3p - Shared Ownership | Flat 2b4p - Shared Ownership | Flat 3b4p - Shared Ownership | Flat 3b5p - Shared Ownership | Flat 3b6p - Shared Ownership | Flat 4b5p - Shared Ownership | Flat 4b6p - Shared Ownership | Flat 4b7p - Shared Ownership | Flat 4b8p - Shared Ownership | House 1b2p - Shared Ownership | House 2b3p - Shared Ownership | House 2b4p - Shared Ownership | House 3b4p - Shared Ownership | House 3b5p - Shared Ownership | House 3b6p - Shared Ownership | House 4b5p - Shared Ownership | House 4b6p - Shared Ownership | House 4b7p - Shared Ownership | House 4b8p - Shared Ownership | House 5b6p - Shared Ownership | House 5b7p - Shared Ownership | House 5b8p - Shared Ownership | House 5b9p - Shared Ownership | House 6b10p - Shared Ownership | Bungalow 1b2p - Shared Ownership | Bungalow 2b3p - Shared Ownership | Bungalow 2b4p - Shared Ownership | Bungalow 3b5p - Shared Ownership | Flat 1b1p - First Homes | Flat 1b2p - First Homes | Flat 2b3p - First Homes | Flat 2b4p - First Homes | Flat 3b4p - First Homes | Flat 3b5p - First Homes | Flat 3b6p - First Homes | Flat 4b5p - First Homes | Flat 4b6p - First Homes | Flat 4b7p - First Homes | Flat 4b8p - First Homes | House 1b2p - First Homes | House 2b3p - First Homes | House 2b4p - First Homes | House 3b4p - First Homes | House 3b5p - First Homes | House 3b6p - First Homes | House 4b5p - First Homes | House 4b6p - First Homes | House 4b7p - First Homes | House 4b8p - First Homes | House 5b6p - First Homes | House 5b7p - First Homes | House 5b8p - First Homes | House 5b9p - First Homes | House 6b10p - First Homes | Bungalow 1b2p - First Homes | Bungalow 2b3p - First Homes | Bungalow 2b4p - First Homes | Bungalow 3b5p - First Homes | Out of Area | District Enabler | Affordable units allocated to OCC | Policy Ref | Developer | Marketing Name | Duty to Cooperate | Affordable Allocation to OC % | Delivery timescale | S106 required | S106 signed | S106 Additionality | DOV required | DOV signed | Modified | Modified By | DB Update Completed
Upgrade Existing Tennis Courts | Upgrade Existing Tennis Courts | A4820 | Development Board | Development Review Group | Communities | Community Services |  | Capital Delivery |  | Peter Matthew |  |  | tbc |  | Paul Backman |  | Rolling Programme | That works have completed at Hinksey Park and Botley Park, this has included resurfacing and repainting of the courts. We have worked closely with the cabinet member and local ward cllrs to promote this. At Bury Knowle Park resurfacing works have also been completed to now include tennis and multi use games area at the site. Planning permission has been granted and works are now complete for the refurbishment of the pavilion and associated outdoor spaces. We are currently reviewing potential for works at Cutteslowe Park and Alexandra Park to resurface the existing tennis courts utilising S106 contributions from the Wychwood School developments |  | 45199 | Work starts June 2023 | Completion of works at Bury Knowle - July 24 | Confirmation of scope of works at Cutteslowe Park and Alexandra Park - End of 2024 |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: We have been working with the LTA and Premier Tennis and have secured £100k to upgrade Hinksey and Botley Tennis Courts. As a second phase we are looking at Bury Knowle and Cuttelslowe. A report has been sent to asset review group and has also gone to development board. We have now undertaken a procurement exercise and works will start at the end of April. Stakeholder comms has also gone out.; 33: Charging scheme at Hinskey & Botley received some criticism locally and from members. We have worked closely with members to mitigate this and have addressed their concerns. Tennis courts at Alexandra Park have significantly deteriorated and are in need of resurfacing - proposal for works using S106 contributions. Cutteslowe Park is in need of significant improvements as court conditions are poor - proposals for utilising S106 contributions working in partnership with Courtside to review options for delivery; 34: Completion of lease and funding agreements for Bury Knowle. We are currently working with corporate property and legal to get both finalised and agreed ahead of the opening of the new facility; 40: 0; 41: 108190.83; 42: 0; 43: 0; 44: 0; 45: 108190.83; 46: 2568.62; 47: 148000; 48: 39809.17; 49: Bring budget forward (more spend in 24/25 using future budget); 50: £33,000 CIL contributions from Headington Action are not currently showing on current budget. Once this has been allocated the project should show a small overspend due to unforseen costs in delivery of Hinksey Park and Botley Park resurfacing.; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: In line with client checklist; 73: Yes; 74: Yes; 75: all in place; 76: N/A; 77: Chapel Hill Projects; 78: Oxford Direct Services; 79: Steve stansfield has signed off RAMS and checklist; 80: Yes; 81: Bury Knowle Hub project already delivered by ODS. Future court resurfacing works are unlikely to represent an opportunity as they require specialist contractors; 83: Already Awarded; 84: £600k; 92: DRG; 117: 0 | [12 empty] | 45580.2784 | pbackman@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Rose Hill Community Centre - Parking Management | Creating a traffic order for the car park. Installing ticket machines and signage to enforce a maximum stay period and stop the car park being used incorrectly. | A4847 | Development Board | Development Review Group | Communities | Community Services |  | Capital Delivery |  | Peter Matthew |  |  | Lydia Dixon |  | Natalie Oakley |  | Feasibility | We are currently working with colleagues within the car parking team to develop a clear scope for this. It is likely that the £10k capital allocation will slip to 24/25. |  | 2023-06-30 | Traffic order obtained. |  |  |  | 24: On target; 25: On Budget; 26: Off Target; 27: Medium; 28: Medium; 30: ARG approval from February. ODS commissioning Legal to create traffic order. Local Clllrs briefed.; 33: Timescales and budget if part of a wider project; 37: Will influence building users and tenants to use alternative methods of transport instead of cars.; 40: 0; 41: 10000; 42: 0; 43: 0; 44: 0; 45: 10000; 46: 0; 48: -10000; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 80: Yes; 82: engineering. Car Parks; 84: 10000; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1129 | rhaverson@oxford.gov.uk
Bodycams | Purchase of cameras and data storage for body worn camaeras | A4852 | Development Board |  | Communities | Regulatory & Community Safety |  | Capital Delivery |  | Richard Adams |  |  |  |  | Daniel Courtenay |  | Delivery | Project completed. Final spend approx £27K (under budged of £60K) Closure Report to be completed by Richard Adams |  | 2023-12-29 | NFA | NFA |  |  | 24: Completed; 25: Completed; 26: Completed; 27: Low; 28: Low; 30: "Procurement - RfQ and tender spec draft completed. Both documents will be forwardto stakeholders for appoval including ICT and Teams who have registered an interest in using BWVD ICT - Advice taken from ICT about intergrating BWVD into Council systems Front Door of Change - Project Proposal Form sent to Tim Martin"; 33: -; 34: NFA; 40: 0; 41: 23000; 42: 0; 43: 0; 44: 0; 45: 23000; 46: 22977.5; 48: -23000; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1129 | rhaverson@oxford.gov.uk
Cycling Infrastructure Matched Funding | Originally Councillor Upton fund covering 4 years. | A4853 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Miscellaneous Capital Spend |  | Carolyn Ploszynski |  |  |  |  | Mim Norvell |  | Other Capital Spend | 7 carriageway locations approved for installation at County CMD, 75 racks, 150 spaces. ODS to install after order is 'made'. Next set of racks proposals being progressed, including Cowley Rd. 'Latest Budget' not updated at time of data entry, in hand with Account Manager. |  | 2026-03-31 | Carriageway rack installs Nov-Dec 24 | Non-TRO rack approvals |  |  | 24: On target; 25: Under Budget; 26: On target; 27: Low; 28: Low; 30: 76 public racks installed by ODS, providing 152 additional spaces. A further 57 racks (114 spaces) approved on private land, being installed via the Park That Bike scheme. Four carriageway rack locations in progress. Press release 8 June for Bike Week. Some confusion to be unpicked between County/City/ODS regarding responsibility/ownership of racks across the city.; 33: >County/City/ODS under resourced leading to delays; 34: > progress next phase proposals.; 37: N:A; 40: 60000; 41: 55353.16; 42: 173681; 43: 0; 44: 0; 45: 229034.16; 46: 15282; 47: 82000; 48: 26646.84; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Additional time is probably required for processing upcoming location approvals, could take longer than previously expected.; 51: 147034.16; 52: 0; 53: 0; 54: -26646.84; 55: 0; 56: 0; 57: -26646.84; 66: N/A; 69: Yes; 70: Yes; 71: Yes; 72: As there is only one contractor CDM regs do not apply in terms of appointing a PD - not applicable. ODS are PC and have provided competency details.; 73: No; 74: Yes; 77: Confirmed not required (single contractor); 78: ODS; 80: Yes; 82: Public Bike Rack installations; 84: 90000; 92: DRG; 117: 0 | [12 empty] | 45580.3542 | mnorvell@oxford.gov.uk | Y | 45547.3786 | mnorvell@oxford.gov.uk
Leys Pool and Leisure Centre / Youth Hub (YIF) | The remodelling of the existing centre to create a Youth Hub | A4855 | Development Board | Development Review Group | Communities | Community Services |  | Capital Delivery |  | Peter Matthew |  |  | Hagan Lewisman | TBC | Rebecca Dedman | Project - Development | Delivery | Works commenced on site on 23 September 2024. Overall, good progress has been made on site with the commencement of the Phase 1 demolition / enabling works to the rear of the Leisure Centre. ODS have reported works are currently on programme with the completion date of the 25 March 2025 remaining achievable. The final RIBA Stage 4 architectural, structural and civil design package and fire strategy report and plans was issued on 25 September 2024. The final RIBA Stage 4 mechanical and electrical design was issued on 30 September 2024. A majority of the building contract between Oxford City Council and ODS has now been agreed. Schedule of Amendments have been finalised and the completed Stage 4 design. The items left to be confirmed are detailed below: - Contract Sum Analysis. - Contract Programme. - Contractor’s Proposals. The above information was expected back from ODS by the end of September 2024 as part of their Stage 2 tender submission. However, due to delays in finalising the M&E Stage 4 design and coordination with the other consultants, the final Stage 4 design pack was issued later than originally planned. This has resulted in ODS not being able to commence pricing until 30 September 2024 when the full pack was issued. ODS are currently completing their pricing for the Stage 2 tender and will submit this on 18 October 2024. |  | 2026-03-31 | Phase 2 Demolition to commence 14 October 2024 | Revised anticipated Design and Build Contract to be sealed 30 October 2024 | Revised anticipated completion date 25 March 2025 |  | 24: At Risk; 25: On budget; 26: At Risk; 27: Medium; 28: Medium; 33: RISK & MITIGATION: Recent demolition activities consisting of partition block wall removal raised possible stabilisation issues to an adjoining wall. All internal partitions (previously connected to the linear wall) has been removed leaving but a set of rack backs with the aim in maintaining lateral stability. The Structural Engineer attended site to confirm stability of the wall as it is currently, we received an initial response to say that it ‘seems safe’ and have requested a more definitive response and are awaiting this formal confirmation. It is worth noting that a CDM site audit was carried out on 4 October 2024, an extract from report follows: ‘Although this visit was to carry out a general CDM inspection across the site on behalf of the Client, focus was also to be made to the recent demolition activities consisting of partition block wall removal posing possible stabilisation issues to adjoining wall. At the time of visit, all internal partitions (previously connected to linear wall) has been removed leaving but a set of rack backs with the aim in maintaining lateral stability. New blockwork had started to be constructed to the and adjoined to linear wall via the use of steel starter kits. Although from a H&S perspective, in this scenario, there were no obvious and immediate concerns regarding stability, the Structural Engineer is attending site on Monday 7th October to carry out a check and to provide professional opinion. Following this visit, there may be a required change in approach regarding re-build. The CDM PD / CDM Advisor highlighted that there may be the requirement for a pier to be constructed in a suitable position along the linear wall to provide further stabilisation in support of normal use as the length of single skin blockwork (once rack backs are removed) would likely exceed 6m from adjoining walls. SE & Arch to confirm. Crack in block work noticed above central door however, needle has been installed and at the time of visit, infill block work was nearly complete.’ RISK: The costs within the budget estimate ODS provided, are all provisional until Stage 4 design & scope is complete, therefore there is a risk on the cost of the scheme even after having Value engineered the scheme at this stage. RISK: Programme extends beyond the funding deadline, 31 March 2025. MITIGATION: Weekly precontract meetings to monitor progress and mitigate any potential slippage to keep project on track. Review work that could potentially be bought forward i.e. site setup, demolition. The following risk (The Funding Agreement Clause 18.5) was raised at DB on 5/02/24 and the recommendation was – Proceed with signing grant funding agreement, recognising that the funding could be withdrawn with 3 months’ notice RISK: The Funding Agreement Clause 18.5 stipulates that The Funder may terminate (without cause) agreement by giving three months’ notice in writing, provided that the Recipient shall be entitled to claim Grant funds that it has already spent on Eligible Expenditure. MITIGATION: Either remove or agree in side letter that they do not apply probably side letter as unusual to amend GFA. (note: The funder have made clear that they cannot make changes, that there are many local authorities who have accepted and that the alternative is to not accept the funding.); 34: Potential drainage defect in reception area. Property team investigating. Potential risk to the project. There is an issue with the Professional Negligence Insurance (Professional Indemnity) ODSL currently holds which does not cover claims between the Council and ODSL. Because they are wholly owned, and part of the same group, the cover is dealt with as if the Council and ODSL are a single party. If the council needed to recover costs from ODSL, if that cost was of a significant amount and ODSL didn't have the resources to pay for it, the Council wouldn't be able to recover the costs because the insurance wouldn't have the mechanism to do so and would therefore have to bear those costs. The Council are due to award a Design and Build contract with ODSL (subject to value for money assessment) for the creation of a new Youth Hub and associated remodelling works at the Leys Pools & Leisure Centre in September 2024. Issue to be raised at DRG 19-06-2024.; 40: 0; 41: 1071594.07; 42: 0; 43: 0; 44: 0; 45: 1071594.07; 46: 77320.35; 47: 1051594.07; 48: -20000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Retention (remaining 2.5% of construction budget) to be paid 25/26.; 51: 20000; 54: 20000; 55: 0; 56: 0; 57: 20000; 65: HL; 66: Yes; 69: Yes; 73: Yes; 77: Baily Garner LLP; 78: Oxford Direct Services Ltd; 80: Yes; 82: PCSA (Managing Professional Services)/D&B Contract (Principal Contractor); 83: Already Awarded; 84: Initial Reports & Surveys £17,940.00 Pre-Construction Services Agreement £97,320.94 Construction budget £800,000.00; 117: 0 | [12 empty] | 45581.373 | rdedman@oxford.gov.uk | Y | 45548.3338 | rdedman@oxford.gov.uk
Cutteslowe Lower Pavilion | Conversion of stored water system to mains at Cutteslowe Lower Pavilion | A4856 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | James Viljoen | [9 empty] | 40: 130000; 41: 130000; 42: 0; 43: 0; 44: 0; 45: 130000; 46: 0; 48: -130000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1129 | rhaverson@oxford.gov.uk
Leisure infrastructure life cycle investment (dilaps) | Leisure infrastructure life cycle investment (dilaps) | A4857 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Regi Martin |  | Design & Specification | Dilaps draft JCT contract sent to Serco for review, aiming to commence works in September |  | 46022 | Define the packages of work | Sign JCT Contract | Deliver the works packages |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 840000; 42: 560000; 43: 0; 44: 0; 45: 1400000; 46: 168668; 48: -840000; 54: -560000; 55: 0; 56: 0; 57: -560000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Leisure Invest to Save - Leisure Contract | Leisure Invest to Save - Leisure Contract | A4858 | Development Board | Asset Review Group | Communities | Regulatory & Community Safety |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Hagan Lewisman |  | Delivery | Cabinet and Council approval has been given. A deed of variation has been drafted by our legal team, with the purpose to protect the Council in relation to repayment of the capital loaned to them. This is now with Serco for their approval and agreement is likely by return. Replacement and improvement of long lead in items such as Gym Equipment has been completed at Ferry, Barton and Leys. The feedback from customers has been very positive. The governance of the project is through the Maintenance meeting with Serco that also picks up the Dilapidations and is chaired by Property Services and Supported by Leisure. |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 2400000; 41: 3040000; 42: 0; 43: 0; 44: 0; 45: 3040000; 46: 0; 48: -3040000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3842 | hlewisman@oxford.gov.uk | Y | 45546.0545 | hlewisman@oxford.gov.uk
Leisure Centre Capital Works & Replacements | Leisure Centre Capital Works & Replacements | A4859 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Regi Martin |  | Design & Specification | Defining what capital projects will sit outside of the dilaps, working with Serco to understand the ask before proceeding. |  | 46022 | Define the packages by exclusion of the dilaps | Sign JCT Contract | Deliver the works packages |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 200000; 41: 200000; 42: 200000; 43: 200000; 44: 0; 45: 600000; 46: 8650; 48: -200000; 54: -200000; 55: -200000; 56: 0; 57: -400000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Community Centres Capital Works & Replacements | Community Centres Capital Works & Replacements | A4860 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Regi Martin |  | Design & Specification | Developing initial design |  |  | Define the packages of work | Sign JCT Contract | Deliver the works packages |  | 24: On target; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: Low; 28: Low; 40: 430000; 41: 150000; 42: 0; 43: 0; 44: 0; 45: 150000; 46: 0; 48: -150000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1129 | rhaverson@oxford.gov.uk
Hinksey Splash | Hinksey Splash | A4861 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Chris Bell |  | Delivery | Contract agreed - awaiting start date from contractor, but will be in September |  | 45731 | Work starts on site on 14th Oct 24 | Update on 1st Nov that works progressing to timescale and on budget | Update on 1st February that works are progressing to time and on budget |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: The project needs to be completed by 15th March to comply with the external funding deadline; 34: The time taken to complete the procurement process and agree the contact has left a tight deadline to complete construction on time but the contractor is currently confident they will still do it.; 40: 18385; 41: 80000; 42: 200000; 43: 0; 44: 0; 45: 280000; 46: 0; 47: 225822.13; 48: 145822.13; 49: Forecast Underspend at end of project; 50: Contingency was included which may not be required; 51: N/A; 52: Project to be completed in 2025/26; 53: N/A; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: ODS (Andy Wharton); 78: Ustigate Ltd; 80: Yes; 81: To manage to tender process and external contractor to deliver the refurbishment of the splash park at Hinskey Park; 82: Project Management; 83: Already Awarded; 84: £15,000 (2024/25 only); 117: 0 | [12 empty] | 45579.233 | cbell@oxford.gov.uk | Y | 45546.0282 | cbell@oxford.gov.uk
Planned Building Improvements | Capitalised Repairs and Maintenance | B0031 | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Completed | [7 empty] | 24: Completed; 25: On Budget; 26: Completed; 27: Low; 28: Low; 34: on going review of Capital items; 40: 750000; 41: 501982.31; 42: 1250000; 43: 750000; 44: 750000; 45: 3251982.31; 46: 11719.75; 48: -501982.31; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 80: No; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1129 | rhaverson@oxford.gov.uk
R & D Feasibility Fund | Feasibility Fund (Revenue) for use in the development of projects. | B0074 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Nigel Kennedy |  |  | N/A |  | Rachel Haverson |  | Feasibility | September 2024 Update - Allocations for 24/25 - Templars Square, BNG Feasibility, Floyds Row, HSBC Options, Bury Knowle House, Union Street Car Park, 42 & 46a George Street and Redbridge Masterplan - totalling £512,000. £401,815 budget remaining for 24/25. |  |  | N/A - budget is allocated to approved schemes at the feasibility stage. |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Medium; 28: Low; 33: RISKS * Funding is insufficient for the number of schemes requiring feasibility funding. * Continuing to commence further feasibility funded schemes may not be sustainable from a financing or resourcing perspective. MITIGATIONS * Review existing feasibility schemes on on-going basis to assess whether project profilied correctly or can be paused or stopped. * Introduce top up of feasibility budget when projects reach delivery stage and seek budget approval i.e. request gross budget and return the feasibility. * Potentially need to prioritise new bids arising against existing projects to assess options for reallocation of funding.; 40: 500000; 41: 462815; 42: 500000; 43: 200000; 44: 0; 45: 1162815; 46: 0; 47: 502815; 48: 40000; 49: N/A - On Budget; 51: 350000; 52: 200000; 53: 150000; 54: -150000; 55: 0; 56: 150000; 57: 0; 66: No; 77: N/A; 78: N/A; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45559.0291 | rhaverson@oxford.gov.uk
East Oxford Community Centre | Development of the existing East Oxford Community Centre including new build. A separate project (N7050) also includes the development of up to 32 housing units on Princes street, Catherine Street and Union street. | B0083 | Development Board | Development Review Group | Communities | Community Services |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Douglas Kerrigan |  | Delivery | Commence on site 6th March 2024 |  | 45838 | Complete roof works 11th November 2024 | Commence brickwork ground floor 18th November 2024 | Complete cladding 20th December 2024 |  | 24: Off Target; 25: On Budget; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 30: Demolition has commenced in Princes Street. A fixed price has been agreed with ODS and that is £5.9m inclusive of PCSA Cabinet on 14 June passed the request for a budget increase of £1.3m; 33: Access for Community Centre and Residential. Ongoing Coordination meetings in place to decide a mutually agreeable strategy. These are now planned on a weekly basis at site level and monthly for combined project teams. The logistics of completing shared sewers and paved areas between community centre and residential means completion of that area will not be until October 6th. EOCC is targeted as end of June 2025 but occupation will not be [possible till paving work is concluded to allow means of escape from the community centre.; 34: Delivery coordination and logistics in shared road space and space between community centre and residential site. Revised red line boundary now runs up to community centre and constant reviews of Health and Safety and CDM issues are paramount. The present methods in place of weekly site review and monthly whole team planning/coordination workshops are essential and effective.; 37: MMC and OSF across new build. Proposed non gas system throughout; 40: 4223967; 41: 3500000.27; 42: 2124657; 43: 0; 44: 0; 45: 5624657.27; 46: 2897949.9; 47: 3245000; 48: -255000.27; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Presently early design changes led to delays which have a mitigation strategy to meet original Practical Completion dates; 51: 2242500; 52: 134000; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: PD will sit with ODS and their designer under D and B; 73: Yes; 74: Yes; 75: None; 76: Nil; 77: ODS appointed designer will be PD; 78: Refurbishment and New build ODS under a D and B; 80: Yes; 81: ODS are main contractor for the works; 82: All elements of construction from groundworks through to finishes; 83: Already Awarded; 84: £5.9m; 92: DRG; 117: 0 | [12 empty] | 45579.9946 | dkerrigan@oxford.gov.uk | Y | 45546.2753 | dkerrigan@oxford.gov.uk
Jericho Community Centre | Jericho Community Centre | B0084 | Development Board | Development Review Group | Development | Regeneration & Economy | [18 empty] | 40: 0; 41: 0; 42: 200000; 43: 0; 44: 0; 45: 200000; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Cave Street | 26 Cave Street and the adjacent site at Standingford House is to be redeveloped as a mixed use development including affordable workspace as part of an inclusive economy. | B0092 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Jane Winfield / Carolyn Ploszynski |  |  |  |  | Douglas Kerrigan |  | Feasibility | Project is not meeting feasibility targets due to economic uncertainties and unstable build costs. It has been decided to 'mothball' the project and investigate meanwhile uses Line in cabinet paper December 2023 to explain The following statement has been issued to Ward Councillors Statement on Oxford City Council’s decision to pause Cave Street redevelopment: “Oxford City Council has taken the decision to pause the redevelopment of Standingford House, on Cave Street, due to the present challenging economic climate. “The Cave Street site will remain a City Council asset, allowing for meanwhile options to be explored that could bring the site back into temporary use. “The decision comes as significant cost increases – both in the construction and the cost of borrowing – mean the agreed budget for the Standingford House redevelopment is no longer sufficient. The Council is responsible for effectively managing its budget and assets and has considered various options to continue with the redevelopment. However, all would require an increased budget and a long-term payback period, putting increased pressure on the Council’s Medium Term Financial Plan. “Plans to replace Standingford House with modern small business units were approved by Cabinet in 2021 as the building did not comply with the required national legislation for Minimum Energy Efficiency Standards (MEES) for commercial properties and the building was in poor condition. It needed urgent repair and maintenance. “Demolition of the former building is complete, and the site has been secured. Consideration will be given to how the site might best be used in the short to medium term, until economic conditions support bringing forward the planned development of small business units.” ENDS The site will be secured (small budget held say £50k) and a handover made to properties w/c 4/12/2003. Housing services are investigating a meanwhile use as TA by installing pods. A project board dedicated to this will be held on a monthly basis. |  | 45282 | Meanwhile uses considered January 2023 |  |  |  | 24: On Hold; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: N/A; 28: Low; 30: Further cost reviews have produced a deficit of £3.5 against budget on full scheme as approved. Alternative schemes were presented at a Members Briefing on 12 June. The options presented are to be completed by end of June for a further meeting; 33: TBA on meanwhile uses; 37: BREEAM Excellent target confirmed and included in Options appraisal. Outstanding costed but likely to be unviable as result of market inflation.; 40: 0; 41: 194134.47; 42: 0; 43: 0; 44: 0; 45: 194134.47; 46: 263733.39; 48: -194134.47; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 69: Yes; 70: Yes; 73: No; 74: No - answer next two questions; 75: Project has not entered construction phase; 76: n/a; 77: AAP appointed - nothing to report.; 78: tba; 80: Yes; 82: Site security a; 92: DRG; 117: 0 | [12 empty] | 45576.1429 | dkerrigan@oxford.gov.uk | Y | 45546.2753 | dkerrigan@oxford.gov.uk
Bullingdon Community Centre | Demolition and rebuild of community centre | B0096 | Development Board | Development Review Group | Communities | Community Services |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Douglas Kerrigan |  | Completed | Practical Completion achieved |  | 2022-12-07 | Practical Completion achieved December 2022 together with Commission and handover |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Practical Completion achieved; 33: Cost report submitted for increase over budget to date Final account can now be submitted; 34: Extension of time considered and granted.; 37: OSF, ASHP, Low energy lighting, solar panels, air tightness, brise soleil; 40: 0; 41: 63135.94; 42: 0; 43: 0; 44: 0; 45: 63135.94; 46: 169417.41; 48: -63135.94; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 77: Jessop and Cook; 78: ODSL; 82: Main Contractor; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
George St 1-3 | Refurbishment of 1-3 George Street to provide affordable workspace as part of an inclusive economy. | B0098 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Karoline Soisalo De Mendonca |  | Delivery | - Works on site have been completed. - OCC/ODS agreed that LADs would be paused for 8 weeks to allow ODS the chance to gather all BREEAM information and finalise accreditation. We may be able to get a 'Good' rating, 'Very Good' very unlikely. - 14/08/24: Caroline/Carolyn/Simon met to discuss, as ODS not making any progress with BREEAM after 5 weeks. - Agreed way forward on 15/08/24: ODS/OCC to work together to finalise BREEAM, to meet to discuss variations line by line with ODS in September, and both sides to put together a qualitative narrative report to describe what they believe 'went wrong' or caused severe delays and financial loss. - ODS/OCC to meet 11/09/24 to discuss variations |  | 2024-09-27 | BREEAM Workshop 1 - 22/08/24 | Variations Meeting OCC/ODS - 11/09/24 | Practical Completion: Mid or late September |  | 24: Off Target; 25: On budget; 26: Off Target; 27: High; 28: High; 30: "- Internal works on all floors completed except for the following: • There are two large glazed panels to ground floor stair to external rooftop that require replacement due to condensation. Replacement programmed for w/c 19/06 • New solution for ground floor access to external stair to rooftop accepted by Building Control. The solution includes concrete steps, stainless steel handrails and automated doors. Works to carried out between 05/06/23 – 30/06/23 - ADP (architects) completed As-builts. OCC/ODS checked drawings on site and found discrepancies that needed correcting. ADP visited site on 19/05/23 for a site measure and should re-issue amended as-builts by 26/05/23. As builts still not sent to RWE due to lack of payment by ODS> - Rooftop Pergolas: There has been a significant delay with the Oak order for the rooftop – the original date for the 9no. oak columns and associated oak structural elements for the pergolas has been delayed by 6 weeks. This was disclosed to OCC on 16/05/23. - Steel elements including external fire stair and balustrades are being manufactured. - Rooftop works are programmed to happen between 03/07/23 and 28/07/23. - Runway East was selected as the operator and lease agreement is due to be executed 26/05/23. - There is a possibility for partial possession of the internal parts of the building so Runway East can commence their internal fitout works before practical completion. - ODS have issued a revised programme on 24/05/23 with practical completion date shown as 09/08/23. - - External Rooftop: Issues with drainage. ODS did not build to architects/drainage engineer drawings. ODS checking with engineer and BC to see what solution is acceptable to re,edy this. - RWE lease agreement ongoing. RWE requesting exclusivity for Cave St before signing on George."; 33: -The project still remains in significant delay, practical completion is now on hold until we can establish BREEAM status. - BREAAM: Risk that ODS will not complete BREEAM as agreed between OCC and ODS. To mitigate this risk, OCC have agreed to meet regularly and support in completing works. - OCC/ODS are in final accounts negotiations which can be lengthy. There are disagreements on contractual obligations on both sides. In order to understand all variations and their legitimacy, ODS have agreed to meet to run through them line by line. In this meeting, ODS will have to demonstrate two things: that the variations were legitimate client changes or instructions, and substantiation/evidence of works. - Risk of having to go to external mediation in case disagreements cannot be resolved. this will cause further delays and add cost. - risk of loss of income as the property sits empty, without an operator. OCC is working with Savills to arrange viewings. OCC Property has been in talks with potential tenants on possible lease agreements and rent. - risk of clawback for OxLEP funding. This is unlikely, but OCC/ODS working together to find a position both sides are comfortable to reach PC. OCC also working with Savills to ensure a tenant moves in asap.; 34: - Handover/ PC to be confirmed: date to be confirmed, dependent on BREEAM status - Final Accounts negotiations with ODSL ongoing - Premises is being marketed by Savills, visits, viewings ongoing.; 37: Approval agreed to additional spend to meet BREEAM Very Good including fabric improvement, triple glazing, air source heating and PV; 40: 0; 41: 166732.7; 42: 0; 43: 0; 44: 0; 45: 166732.7; 46: 2817522.57; 47: 5000; 48: -161732.7; 49: Bring budget forward (more spend in 24/25 using future budget); 50: Due to ongoing project delay - Ongoing OCC officer and legal costs relating to extended programme and delays - Late invoicing by ODS: ODS invoiced in 2024/25 for works completed in 2023/24 - Consultant payment: payments to consultants were left to the end of the project, so an estimated £10k will be invoiced to OCC for QS and contract admin services; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 73: Yes; 74: Yes; 77: AAP appointed, review monthly; 78: ODSL reporting monthly; 79: A health and safety audit is being carried out after a H&S incident, ODS external H&S consultant has now been to site after a while of not inspecting.; 80: Yes; 82: Enabling works, Office refurbishment; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Gloucester Green Car Park Ventilation (H&S) | Upgrade of the ventilation system | B0100 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  | Keith Reynolds |  | Luca Minetola |  | Completed | Works completed by ODS in September in line with revised programme. Awaiting Final account sign off |  | 2022-09-27 | Works are complete |  |  |  | 24: Completed; 25: Over Budget; 26: Completed; 27: N/A; 28: N/A; 30: Works completed by ODS in September in line with revised programme. Awaiting Final account sign off; 40: 300000; 41: 370730.14; 42: 0; 43: 0; 44: 0; 45: 370730.14; 46: 553788.82; 48: -370730.14; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 77: Heaton Design & Engineering; 78: ODS; 80: Yes; 82: Appointed.; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Covered Market - Major capital works at Covered Market | Repairs and maintenance | B0101 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Awaiting outcome of the covered market masterplan |  | 2025-03-31 |  |  |  |  | 24: On Hold; 25: Under Budget; 26: Awaiting new Schedule; 27: Low; 28: Low; 30: This is on hold while Covered Market Master Plan is defined and concluded.; 33: Changing priorities. Scope of proposed works will likely be reviewed now draft Master Plan report for the Covered Market has been received and fully reviewed.; 34: Awaiting Client's instructions.; 37: N/A; 40: 200000; 41: 888453.03; 42: 200000; 43: 200000; 44: 200000; 45: 1488453.03; 46: 12861.63; 47: 200395.36; 48: -688057.67; 51: 100000; 52: 100000; 54: -100000; 55: -100000; 56: -200000; 57: -400000; 65: HL; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Lift Maintenance Programme (GF) | Repairs and maintenance programme | B0102 | Development Board | Asset Review Group | Communities | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | On-going maintenance and inspections with repairs |  | 2025-03-31 | Requires budget approvals, Section 20, cabinet report,contract extension procurement | Contract extension required October 24 | Cabinet approval 24 |  | 24: At Risk; 25: On Budget with slippage; 26: Awaiting new Schedule; 27: High; 28: High; 30: Resource being sourced to manage installs is still in the process of being identified.; 34: Will require contrasct extension to allow for tendering/lift consultant sectioon 20 \and procurement; 40: 140000; 41: 109484; 42: 150000; 43: 0; 44: 0; 45: 259484; 46: 3733.62; 47: 109484; 48: 0; 51: 269484; 52: 50000; 54: 119484; 55: 50000; 56: 0; 57: 169484; 66: N/A; 80: No; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Gas Works Pipe Bridge Refurbishment | Repairs and maintenance | B0104 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Delivery | main works to bridge completed - Bearing replacement works underway pending approval from TA - Due to reopen on 31st Oct |  | 2024-10-31 | Temporary Bridge Opening - 31st July 24 | Bearing Replacement - September 24 | Project Completion Oct / Nov 24 |  | 24: On target; 25: Over budget; 26: Off Target; 27: Medium; 28: Medium; 30: Works to commence on site on the 1 April 23. There is a programme meeting takin place on 10th March to determine completion of the programme.; 33: "Bridge is due to be lifting with jacking taking place from underneath. Following this bridge being raised the bearings that the bridge rests on will be replaced. Once this has been completed the project will essentially be completed, other than snagging and demobilsaition. "; 40: 1000000; 41: 1770635.67; 42: 0; 43: 0; 44: 0; 45: 1770635.67; 46: 539092.22; 47: 1977544.45; 48: 206908.78; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 79: Satisfactory; 80: No; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Covered Market Re-Roofing Works (Planned Maintenance) | Repairs and maintenance programme - Repairs to the covered market roof | B0106 | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  | Richard Davison |  | Luca Minetola |  | Delivery | "Covered Market Roof Project was determined by procurement and legal. New project for phase 6c to be done by property services. Phase 7 has been passed over and added to the Masterplan for the Covered Market." |  | 2026-11-28 | Project initiation | Design and tender | Project delivery |  | 24: On Hold; 25: On Budget; 26: Awaiting new Schedule; 27: Low; 28: Low; 30: Phase 5a is proceeding well, and programme is due to complete at the end of September 23. Phase 6c will follow in October.; 33: Access to enable the delivery of Phase 6c of the works is provided. Working in conjunction with Master plan delivery, other major refurbishments at the same time. Ability to share welfare facilities. Deliveries to and from Market St, which is currently semi pedestrianised.; 34: Adequate funding for the delivery. Feasibility PiD required to establish total project cost.; 40: 525000; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 648057.67; 48: 648057.67; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 79: Satisfactory; 80: Yes; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
38-40 George St Redevelopment | Regeneration of 38-40 George St site | B0112 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Jane Winfield / Carolyn Ploszynski |  |  |  |  | Carri Unwin |  | Delivery | Planning application resolution to grant is on Agenda for the October Committee. This is a 1 month delay on project, and was due mainly to the request for additional work to the visual assessment information. Drafting of s106 being finalised, and Press release comms agreed in preparation for after Resolution to Grant achieved. Developer and operator requested a revision to lease boundaries to accommodate cycle parking area and store for community space. Acceptable and legals being progressed. |  | 2028-01-31 | Resolution to grant - Oct 24 | Planning approval Jan 25 | Investigations and trial pits - Nov Dec 24 |  | 24: On target; 25: On Budget; 26: On target; 27: Medium; 28: Low; 30: Final solutions received and preferred bidder selected. July Cabinet to approve contracting with the preferred bidder for an aparthotel scheme with community space on ground floor; 33: Agreement being reached with the LPA on s106 and visual information. Mitigations: additional meetings as required, and correctly articulating wide range of significant benefits and improved Gloucester Green elevation and maximised active frontages to benefit Gloucester Green - a key project and city centre aim. Right to Light injunction risk - mitigate through progressing appropriation process. Minimising future reputational risk to Council - in its public servant role by s106 ensuring community space is available in perpetuity to at least serve local city centre residents as well as other wider groups. Mitigation by liaison with communities and economic team. And list of approved uses in sub lease between Staycity and Makespace.; 34: Supporting MRE design team with regular Progress Meetings, and support and advice re key meetings with stakeholders, and PRs. As well as progressing appropriation to mitigate Right of Light injunction risk Support good communication between MRE and the Planning Authority; 37: Yes from more efficient building; 40: 0; 41: 130451.85; 42: 0; 43: 0; 44: 0; 45: 130451.85; 46: 24686.56; 47: 157000; 48: 26548.15; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Contingency unspent so far in 24/25 Note- £98K property payment due in Feb/Mar 25; 51: 9905657; 52: 20836963; 53: 6063427; 54: 9905657; 55: 20836963; 56: 6063427; 57: 36806047; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: Development partner is contracted, "as far as possible under CDM Regs" to carryout the Client responsibilities on behalf of the Council.; 73: No; 74: Yes; 75: To be done; 76: To be done; 77: Development partner's appointed company; 78: Development partner's appointed company; 79: Meeting with Theo this week; 80: No; 92: DRG; 117: 0 | [12 empty] | 45579.2525 | cunwin@oxford.gov.uk | Y | 45552.2066 | cunwin@oxford.gov.uk
Diamond Place (Redevelopment) | To create a concept Masterplan, supported by a business case to demonstrate that re-development is viable and deliverable and supported by the community. There will be two variants of the Masterplan: a comprehensive redevelopment and an option that enables us to proceed without the University as a partner | B0114 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  | Jane Norman |  | Jane Norman |  | Feasibility | OCC Client Brief approved at Development Board on the 4th March and has been sent to OX Place for consideration. Ox Place have now confirmed that they will not be able to provide any update until January 2025. The local GPs have now heard back from BOB ICB who have confirmed that no funding was approved by their Executive Board for the move to South Parade but this didn't rule out potential funding in the future due to the change of government. Officers met with Peter Redman from BOB ICB in September. He was unable to confirm whether funding would be available for Diamond Place in the future or not but has agreed to provide information regarding the size of health facility they would require at Diamond Place. This will be shared with Ox Place. |  | 2025-03-31 | Ox Place to provide update on feasibility work - January 2025 |  |  |  | 24: Off Target; 25: Closed; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 30: "The Stakeholder Workshops are continuing, the most recent held on the 23rd May. There are two more, one in June and the final one in July. OX place Board, on the 22nd May, agreed to proceed with initial appraisal work and to the development of a proposal for consideration by the Board and HSB. There has still be no response from the ICB to the many requests to meet to discuss a potential health centre and supporting funding."; 33: The Neighbourhood Forum have clear ideas about the redevelopment of the site. The Stakeholder workshops have helped to explore the key challenges of developing the site and the forum are now considering a review of the neighbourhood plan. The Neighbourhood Forum also have different expectations about the timescale for any potential redevelopment. We will continue to engage with them through the tri-partite meetings and involve Ox Place in these meetings in the new year.; 34: Oxford University timeline and community expectations are misaligned. Further work with the NF through the tripartite meetings and the stakeholder workshops have helped to reinforce the issues that still need to be resolved during the pre-development stage. BOB ICB still need to clarify what's required at Diamond Place and whether funding will be agreed for a new facility.; 37: The costs of a carbon zero scheme are c. £3m. This cost will need to be reviewed as part of detailed proposals for the site.; 40: 0; 41: 9999.5; 42: 74770; 43: 0; 44: 0; 45: 84769.5; 46: 2365; 48: -9999.5; 49: N/A - On Budget; 54: -74770; 55: 0; 56: 0; 57: -74770; 65: HL; 66: No; 69: No; 70: Yes; 80: Unsure; 81: This project is currently with OxPlace who are completing feasibility stage work so unable to confirm at this stage if it would be an opportunity for ODS or not.; 92: DRG; 117: 0 | [12 empty] | 45579.3148 | jnorman@oxford.gov.uk | Y | 45552.3706 | jnorman@oxford.gov.uk
Osney Mead Path Works | HIF funding for OFAS and Cycle infrastructure to unlock housing at Osney Mead | B0116 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Roland Parsloe |  | Design & Specification | It has been agreed that HIF funding allocated for Pathworks to be focused on the pathworks associated with the proposed Oxpens River bridge. The funding for the pathworks improvements to the west of the railway to Osney Mead would then need to be secured from elsewhere. Discussions have taken place with Homes England and Oxford University on the principles involved. Balfour Beatty have been appointed as contractor to deliver the bridge and pathworks. A Deed of Variation to the HIF Funding agreement was received from Homes England and returned with comments and a further version of the DofV has been received. Back to back funding agreements have been drafted re the OFAS element of the funding with the Environment Agency but are still subject to review and discussion. However, an agreement with University of Oxford has not been agreed which presents a risk to the drawdown of funding with regard to clawback by Homes England. This has been reported to Cabinet who have agreed to accept the risk. Funding has to be drawn down by March 25 (subject to signing the DofV) and details of spend evidenced and pre conditions and milestones met. |  | 2025-03-31 | Deed of Variation from Homes England for the HIF funding to be progressed - Requirement to conclude by 24 Sept 2024 | Complete back to back agreement with EA | Draft a recovery strategy as required by the DofV |  | 24: Off Target; 25: Budget to be agreed; 26: At Risk; 27: High; 28: High; 30: It has been agreed that HIF funding allocated for Pathworks to be focused on the pathworks between the railway bridge and proposed bridge. The funding for the pathworks improvements to the west of the railway to Osney Mead would then need to be secured from elsewhere. Discussions have taken place with Homes England and Oxford University on the principles involved. The Stantec Path Works Optioneering Report signed off and shared with Oxford University who may pick up when Osney Mead development moves forward. A Deed of Variation to the HIF Funding agreement has been received from Homes England and back to back funding agreements have been drafted re the OFAS element of the funding. However an agreement with University of Oxford has not been agreed which presents a risk to the drawdown of funding with regard to clawback by Homes England.; 33: There remain risks relating to the ability to claim the funding from Homes England. A Deed of Variation has been drafted to extend the period to claim funding up to March 25 and resolve other issues. Evidence of spend is required to make the claim and there is a risk that there will not be sufficient spend on the pathworks by March 25 as delivery is now delayed by the JR of the planning decision. Also if funding is spent without the University delivering housing at Osney Mead there is a risk of clawback.; 34: A Deed of variation has been received from Homes England for the HIF funding and final changes have been made and returned to Homes England. Agreement with Environment Agency to be completed and recovery strategy agreed with Homes England. Progress is also required on the bridge funding to enable programming and spend of the HIF for the pathworks.; 40: 564914; 41: 1398635.13; 42: 0; 43: 0; 44: 0; 45: 1398635.13; 46: 0; 47: 1398635.13; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: N/A; 69: N/A; 70: N/A; 71: N/A; 72: CDM being picked up under Oxpens River Bridge; 73: N/A; 74: N/A; 75: N/A; 76: N/A; 77: N/A; 78: N/A; 79: N/A; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45548.4125 | jbarker@oxford.gov.uk
Regeneration Property | Budget reflects desire to de-risk the existing portfolio, allowing the Council to be competitive if an attractive opportunity becomes available. Provides greater flexibility for the Council to address required regeneration post COVID 19 with its own property. | B0117 | Development Board | Asset Review Group | Development | Corporate Property |  | Miscellaneous Capital Spend |  | Jane Winfield |  |  |  |  | Emma Gubbins |  | Completed | Remainder of funds to be used within the capital programme due to changes in PWLB lending rules. Unlikely to make any further acquisitions |  | 2022-09-01 | Purchase complete. Remaining budget to be considered as part of the budget process |  |  |  | 24: On target; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: Medium; 28: High; 30: Purchase of industrial unit is now complete. Remainder of funds to be reprofiled over the MTFP as part of the budget process. Limited opportunities to acquire due to changes in PWLB lending rules.; 40: 0; 41: 3402.38; 42: 0; 43: 0; 44: 0; 45: 3402.38; 46: 3402.38; 48: -3402.38; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Ice Rink - Development options | To develop longer-term delivery options for Oxford Ice Rink | B0118 | Development Board | Development Review Group | Communities | Regeneration & Economy |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Jane Norman |  | Feasibility | Prior and Partners have completed the draft pre-app which was reviewed by the Project Board and Development Board in August. The pre-app was submitted on the 23rd August and the pre-app meeting will be held on the 14th October. Lead members were updated at the weekly leaders meeting in early September. The project board will be updated on the pre-app discussions at the end of October. |  | 2024-12-30 | First pre-app meeting with LPA - October 2024 | Second pre-app meeting with LPA- November 2024 |  |  | 24: On target; 25: On Budget; 26: On target; 27: Medium; 28: Medium; 30: A meeting took place with both architects (BDP and Hawkins Brown), Montagu Evans, OxWED and OCC on the 25th May to review BDP's Technical Assessment. The TA has confirmed that OxWED's A9 site can accommodate the new ice rink and supporting uses as well as providing the opportunity for significant enabling uses. BDP have produced example layouts that show student housing ranging from 180 to 400 units. OCC and OxWED are continuing to work on draft Heads Of Terms which we anticipate will only cover the land swap option and possibly joint planning( pre-app and application). OCC have confirmed to OxWED that they will only be in the position by the end of June to confirm the land swap option is worth considering. Further work over the next 6 to 8 months will confirm this.; 33: 1. Alternative locations may not be achievable within the timescale required for delivery of a new ice rink. 2. Alternative locations outside of the city centre may be politically unacceptable. Members briefings have confirmed that these options can be explored by officers. 2. Access to the new location and provision of sufficient parking for ice rink users is a key issue.; 34: To establish LPA support for relocating the OIR to an out of city centre location and their view on the potential development options for the current site.; 37: Carbon reduction programme is being worked up to be funded from Salex where it is modelled to be capable of payback within the medium term life of the rink.; 40: 0; 41: 36704; 42: 0; 43: 0; 44: 0; 45: 36704; 46: 25553.6; 48: -36704; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 69: No; 70: Yes; 80: No; 81: Currently going through pre-app to explore location options so specialist input required from consultants.; 92: DRG; 117: 0 | [12 empty] | 45579.3148 | jnorman@oxford.gov.uk | Y | 45552.3706 | jnorman@oxford.gov.uk
Oxford Station Masterplan | To create a concept Masterplan for Oxford train station and surrounding sites. The evidence-base and consultation must be to a standard that will allow the Masterplan to evolve to an SOBC. The Masterplan will take a holistic approach to the redevelopment of the whole station area including the delivery of a multi-modal transport interchange with rail service enhancements and capacity upgrades, improved station forecourt and commercial area, with better connectivity to Becket Street and wider integration to key developments in the city centre (Oxford West End), whilst ensuring delivery of East-West rail timetable requirements (a nationally significant infrastructure project). The Masterplan will fulfil the stakeholder priorities for the Station. | B0119 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Kate Beeching |  | Feasibility | Drafting materials to support input and decisions ahead of publication, including digital accessibility requirements. Response to LC17 sewer constraint in car park - did not object to land disposal |  | 2025-02-28 | Further engagement around alignment of rail strategy and OSM publication, including dates. Further engagement also needed with COMPF team. | NR developing case for car park reduction (NR targeting internal approval for the LC17 process sought end of Sep, circulate LC17 Oct/Nov. | NR - test market interest (no major progress from 1st development partner so engaging a 2nd) |  | 24: On Hold; 25: Under Budget; 26: On Hold; 27: Low; 28: Low; 30: Still running approximately 1 month behind schedule (as last time). Design Workshop 2 held 09/06/23 with Board/Team members. Phase 1 now concluding with Phase Report due 27/06/23. New programme will be created for Phase 2 onwards, following break/review clause.; 33: New Risk of sewer in becket St car park - impacts/mitigations considered and will now be a constraint. Draft risk register last updated with Board Nov 2023; to update next following stakeholder engagement sessions (date tbc) The RED risks are now: • DfT does not agree to fund Oxfordshire Connect or remains uncertain (now red, was amber) but masterplan is revenue generating towards rail costs • Highway modelling is not available to inform optimal crossing points and design and highway improvements to Becket St or Botley Rd - likelihood increased given no further data /resources being available, and increased potential impact given better understanding of pressures. • Delay reaching alignment on how to proceed with engagement. Public consultation remains uncertain until alignment around COMPF/rail strategy are understood . • Rail regulator does not agree parking reduction/ uncertainty how much parking would need to be re-provided – ORR are engaged at Oxfordshire Connect Programme Delivery Group. NR leading Connectivity Study update + LC17 process will require statutory consult local authorities + others on reduction; 34: Approach to publication and engagement Bus companies still favour off-street bus option, and rail industry prefer North car park location. Need to agree how to handle these compromises whilst not watering down the vision/perception of deliverability. Need to work via COMPF to demonstrate how buses move in the future. HB/JD agreed to engage on principles in the Rail Strategy and COMPF but decision to be reached on approach. Responses from stakeholder engagement - TBC but anticipate new issues will be raised. Issue with botley rd bridge ramp lengths is now understood and not as serious as first considered, though ramps may be 3-4m longer than shown. Assurance from consultants that forecout designs took correct CAD references (so forecourt reduction no longer considered an issue of being over-estimated) County/City - agreed city will seek to jointly support County's position on the LC17 car park reduction consultation. Strategy agreed that County will respond taking the reduction proposed by NR but say will seek more, however still potentially an issue if leadership/members do not align with this Officer proposal.; 37: Y; 40: 0; 41: 51563.3; 42: 0; 43: 0; 44: 0; 45: 51563.3; 46: 0; 47: 7261.32; 48: -44301.98; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Forecast spend is confirmed. Other budget may slip as stakeholder engagement approach needs to be confirmed.; 51: £44,301.68‬; 54: #INVALID OPERATION; 55: 0; 56: 0; 57: #INVALID OPERATION; 65: HL; 66: No; 69: No; 70: Yes; 71: No; 73: No; 74: Yes; 75: N/A not in construction phase; 76: N/A; 77: N/A; 78: N/a; 79: will need consideration alongside route to delivery - will be responsibility of the landowner and development partner. Council not currently taking on this stake.; 80: No; 81: Only at RIBA1; 92: DRG; 117: 0 | [12 empty] | 45580.42 | kbeeching@oxford.gov.uk | Y | 45558.3758 | kbeeching@oxford.gov.uk
Osney Bridge (Oxpens River Bridge) | Provision of a pedestrian/cycle bridge over the Thames linking Oxpens to Osney Mead | B0120 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Roland Parsloe |  | Design & Specification | Planning permission granted but subject to Judicial Review. Further submission has been made to County for Technical approvals: AIP, Section 38 & CAT 3 checks - near to conclusion - but still awaiting AiP sign off. S106(3) Highways Act notice published on 2nd May for 6 weeks, process due to conclude shortly. Initial priced packages received by BB - showing increase from previous estimates. Due to delays further funding to cover CEs and Risk is needed. Circa 1.35m. University being approached. OxWED have been approached re. Land behind ice rink for crane as this could reduce the above figure and reduce risks from flooding. Delays have made risk of completed by March 2025 very high so approach to County to seek agreement to extend funding to allow construction in 2025. |  | 2025-12-31 | Confirmation on extension of Growth Deal funding | JR decision, anticipated end of October | • Complete AiP and Technical approvals Clearance of planning conditions Agreement re crane position with OXWED PCSA ends at end of Oct 24 • Construction Contract entered end of 2024 • Works start March 25 • Bridge open to cycles/peds December 2025 | PCSA ends end of 23 May 24 | 24: At Risk; 25: Budget to be agreed; 26: At Risk; 27: High; 28: High; 30: "PCSA underway with the key VE workshops; The main ideas with an impact on the planning are: - Path width on bridge 4.0m to 3.5m - Path width adjoining bridge 4.0m to 3.5m - Change of handrail Material - Change from tensioned mesh to tensioned wire on the parapets - Change from half steel half concrete for the piers to a full steelwork pier - Change from a timber lean rail to a cheaper material with longer life OxWED unlikely to progress the enabling works in advance. Ongoing discussions to coordinate. Application due to be submitted August."; 33: Risk of JR proceeding delaying programme beyond 2025. Situation being monitored. Meeting the final Growth deal & HIF spending deadlines. Work underway to secure the funding for 2025. Negotiations with OXWED in relation to enabling works and land use. Further information to be provided re crane positioning. Risk budget will not be sufficient. On going work with BB re cost of PCSA and bridge construction.; 34: Technical approvals for the bridge, required to complete the PCSA. Clearance of planning conditions. Agreement with OXWED re crane position Receipt of S106(3) approval Securing of the funding for the bridge Firm up programme and agree delivery agreement.; 40: 7184694; 41: 7458420.26; 42: 0; 43: 0; 44: 0; 45: 7458420.26; 46: 406032.15; 47: 985961; 48: -6472459.26; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delay to programme; 51: 6472459; 52: 0; 53: 0; 54: 6472459; 55: 0; 56: 0; 57: 6472459; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: No; 72: BB to prepare at appropriate time (after RIBA 4 design complete).; 73: No; 74: Yes; 77: Balfour Beatty; 78: Balfour Beatty (later); 79: Still at design stage; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45548.4125 | jbarker@oxford.gov.uk
City Cycle Schemes (Growth Deal) | Four chosen cycle routes and crossing updates across the city to encourage walking and cycling | B0122 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Carri Unwin |  | Delivery | Donnington Rec shared cycleway / footway: Info for condition discharge, and updated landscape schemes on Agenda for October Planning Committee for approval. SIgnificant support letters from community in favour of path through park. Liaison with Cllrs, residents, and football club done, and ongoing. Subject to planning approval, works can start on site early November. Contract with ODS being finalised and signed. And ODS can mark out pitches during construction to preference of football club, while allowing cycle access through too. Legal finalising s106 wording. Marsh Lane Rec: completed, apart from Property completing agreement with Christchurch for preferred connection to the highway. Scheme functions without. |  | 2025-02-28 | Planning approval of conditions and updated landscape scheme - Oct 24 | Sign contract with ODS - Oct 24 | Works start on site - Nov 24 |  | 24: On target; 25: On budget with slippage; 26: On target; 27: Medium; 28: Low; 30: Boundary Brook completed King Georges scheme completed Marsh Lane Rec completed (except Christ church path in legals) Donnington tree removals mitigated; liaising with planning dept as planning application is submitted.; 33: Risk - not getting planning discharge of conditions and updated landscape scheme. Mitigation: - provided case officer with all info she needs; and generated positive consultation comments of support, incl from football club and residents association. Risk - Legal resurce at City and County not sufficientto produce s106 document on time. Mitigation: ongoing liaison with legal lead. Risk - ODS have delays in gearing up for work. Mitigation: worked is booked in diary, and keep close liaison ongoing. Risk: consultant CA and PD cause delays and extra costs. Mitigation: Managing good relationships and asking for input as early as possible; 34: Attend Planning Committee to answer any questions Manage Legal to get s106 signed promptly Sign contract with ODS post planning approval.; 37: None; 40: 0; 41: 431332.3; 42: 0; 43: 0; 44: 0; 45: 431332.3; 46: 23096; 47: 218000; 48: -213332.3; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delayed start to site works due to awaiting planning approval of updated scheme information and condition info.; 51: 213332.3; 54: 213332.3; 55: 0; 56: 0; 57: 213332.3; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: Prepared by Stantec on behalf of ODS.; 73: Yes; 74: Yes; 75: none; 76: none; 77: ODS - Stantec; 78: ODS; 79: CDM info has been compiled by Stantec on behalf of ODS as part of D&B project. Currently collating and filing/reviewing information.; 80: Yes; 82: D&B contractor; 84: £245,00.00; 92: DRG; 117: 0 | [12 empty] | 45579.2525 | cunwin@oxford.gov.uk | Y | 45552.2066 | cunwin@oxford.gov.uk
Port Meadow Moorings | Commercial Advice | B0124 | Development Board | Asset Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Emma Gubbins |  |  | TBC |  | Jane Norman |  | Feasibility | The last Project Board was held on the 5th August. It was agreed that this project would now be split: -Property to progress the tender for the new contract for managing the moorings with the target of April 2025 for the new contractor in place; -Regeneration to progress longer term feasibility work to include commissioning commercial advice. A new PID and report will be presented to ARG on the 1st October with a request for a budget to cover external advice and internal staff time. |  | 2025-04-30 | Report to ARG - 1st October 2024 | Procurement of specialist consultant to provide commercial advice- November 2024 |  |  | 24: Not started; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: Low; 28: Low; 30: Project paused due to capacity. To be assigned to the Regeneration Team.; 33: The site sits adjacent to an SSSI, SAC and SAM and has Freemen of the City of Oxford and the Wolvercote Commoners managing the area. The impact of any proposals on this sensitive landscape will need to be very carefully assessed and a clear communications strategy put in place. The timescale for considering future options may be longer than usual due to the above sensitivity and the need to work with the EA. Starting work now will ensure that sufficient time is available to accommodate other organisations timescales and governance.; 34: A new PID and report will be presented to ARG in October. Budget of £67,000 agreed at DB but will now need to be re-presented as budget will now only cover appointment of a specialist consultant as well as staff time and external legal advice.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: -5279.22; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 69: No; 70: Yes; 71: No; 73: No; 74: Yes; 75: none; 77: to be determined at later stage; 78: to be determined at later stage; 79: Inherent H&S issues to be dealt with when working in/adjacent to water.; 80: No; 81: Early stage project requiring specialist consultant input; 117: 0 | [12 empty] | 45579.3148 | jnorman@oxford.gov.uk | Y | 45552.3706 | jnorman@oxford.gov.uk
City Centre Restart (CIL) | Strategic CIL pot set aside for city restart in 2020-21 financial year, but ultimately not spent and rolled over to 2021-22 financial year. Linked to St Michael's Levelling | B0125 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Diana Fawcett |  | Delivery | My understanding is that CIL should show a total of £8,000 budget for city centre projects. This should be split to £1,368.49 for 2023/2024 and £6631.51 for 2024/2025. My understanding is that any extra shown against CIL, should have been allocated to the Covered Market. |  | 45747 |  |  |  |  | 24: On target; 25: Under Budget; 26: On target; 27: Low; 28: Low; 30: £60,000 allocated to St Michael's Street surface improvement in 2022-23 has been slipped to 2023-24 as part of overall £240,000 budget envelope (including SPF and s106 pots). Passing this cost centre over to Di Fawcett to oversee, but current headline is that there are cost inflation risks with the project, so there may need to be an ask to use remaining £40,000 of CIL pot too.; 40: 0; 41: 39324.01; 42: 0; 43: 0; 44: 0; 45: 39324.01; 46: 1109; 48: -39324.01; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: Yes; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Asset Condition Survey (Corporate, Commercial and Community) | Commission condition surveys on assets to determine future maintenance, expenditure and rationalisation of those assets. | B0126 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Running in conjunction with aquisition of new asset management sysytem to determine requirements and details needed to populate the system |  | 2024-03-29 | Asset Management System in place | Mini competition on Framework | Appoint to Carry out surveys |  | 24: On Hold; 25: Under Budget; 26: On target; 27: Low; 28: Low; 30: Scope for commercial surveys being defined and new tender process initiated. Going out to framework to find contractor to carry out surveys on General Fund Commercial buildings. Surveys on other assets (Bridges / Monuments etc.) to be completed internally.; 33: """Access will be the key risk. Flow of information to contractor Health & Safety Information for properties."""; 34: Program will be re-issued based once AMS is in place.; 37: The surveys will look at energy and social inclusivity at the core of recommendation to OCC; 40: 0; 41: 300000; 42: 0; 43: 0; 44: 0; 45: 300000; 46: 102.52; 47: 50000; 48: -250000; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 80: No; 82: N/A; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
ZEZ Phase 1 Feasibility | ZEZ Phase 1 feasibility | B0127 | Development Board | Development Review Group | Corporate Strategy | Environmental Sustainability |  | Capital Delivery |  | Mish Tullar |  |  |  |  | Mai Jarvis |  | Idea | Phase 1 complete and terms agreed on revenue share for phase 1 - legal agreement progressing. Phase 2 - Project on hold, but likely to un-pause soon, awaiting decision on City Council role in project. |  | 2023-12-31 | Complete legal agreement with County re. Phase 1 revenue share | Agree role in Phase 2 with County |  |  | 24: On Hold; 25: On Budget; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 30: June: 2023: Project still on hold, but likely to un-pause soon, awaiting decision on City Council role in project. April 2023: Project on hold. March 2023: Project on hold. Feb 2023: project still on hold. Jan 2023: No change on least month. Still awaiting confirmation on programme. Dec 2022: Project on pause while the programme for the project is reassessed and agreed between county and City Nov 2022: Project on pause while the programme for the project is reassessed and agreed between county and City October 2022: Funding will likely be needed in 23/24 Sep 2022: Awaiting spend programme from County Aug 2022: have gained overview of funding need from County, but awaiting spend programme. July 2022: No update on last month. Still no clarity from County on funding need. June 2022: No update on last month. Still no clarity from County on funding need. May 2022 Update: Currently in process of understanding need for OCC funding into this project, as the County has secured gov funding for the project. Update September 2021 This piece of work is being taken off pause and the feasability work is being restarted as such City Council will raising a PO to transfer of remaining money once confirmation of the work starting has been received from County and the work commissioned. No further update ( 13 October 2021) No further update 8 November 2021 No further update 13 December 2021 10 January 2022 - draft timetable emerging SOBC now out to tender; 33: Risk around ZEZ pilot being enforced while there is significant delay to the ZEZ and stakeholders in Pilot area likely to be vocal about the impacts on the; 34: manage stakeholders in pilot area when news of delay to ZEZ is announced; 40: 0; 41: 141000; 42: 0; 43: 0; 44: 0; 45: 141000; 46: 0; 48: -141000; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Cycle Greenways | Concept masterplan regarding cycle and walking routes from nearby places to Oxford's centre and key employment / retail / education sites. A joint project with the County and University. | B0128 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Simon Taylor |  | Feasibility | Project has now completed baseline analysis and route prioritization. Next steps is on the ground surveys and finalising first 50km of routes. |  | 2024-09-27 | Target contract start - 8 January 2024 | Target conclude stage 1 (baseline) - 5 April 2024 | Target conclude stage 2 (concept design) - 30 September 2024 |  | 24: Off Target; 25: On Budget; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 30: As per coach parking feasibility, this is being explored as a work stream within County "movement and place framework". Expecting more clarity in June / July. (Spend backstop is 2023-24 financial year, so this needs to be spent or agreement reached with County and University, and internally, to defer another year if required.); 33: Insufficient officer resource leads to project delays (now addressed by increasing capacity at City and stitching this project into wider Movement and Place Framework programme with County) Project completes without supporting delivery of schemes (should be addressed through successful scope and good clienting); 34: Extending spend backstop to end of 2024-25 financial year, reprofiling programme to reflect slippage. Anticipated completion Nov 2024; 40: 0; 41: 92250; 42: 0; 43: 0; 44: 0; 45: 92250; 46: 33007; 47: 92250; 48: 0; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 69: No; 70: Yes; 72: CDM responsibility written in to consultant commission; 77: n/a; 78: n/a; 80: No; 81: This is a feasibility study only, with an already appointed consultant.; 83: Already Awarded; 84: 0; 117: 0 | [12 empty] | 45579.3722 | staylor@oxford.gov.uk | Y | 45546.1528 | staylor@oxford.gov.uk
Town Hall Future Options (Lot 3) | Undertaking options studies which explore the future of the Town Hall. Key priorities include: - Enhancing OCC's workplace and operational footprint. - Maximizing the revenue generation of the building through unlocking the commercial potential of underutilized spaces and enhancing current offerings. - Proposed works to improve accessibility, inclusivity and sustainability whilst respecting the buildings heritage. Note: Previously this capital code (B0129) was previously used for considering the future options for relocation of OCC from SAC. Town Hall Projects are now split into 4 Lots: Lot 1 - works related to move from SAC - largely complete - B0143 Lot 2 - Ongoing maintenance and H&S works - led by property services team - B0157 Lot 3 - Options for the future of the Town Hall - B0129 Lot 4 - ICT Works - B0143 | B0129 | Development Board | Development Review Group | Development | Corporate Property |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Nathan Breeze |  | Idea | New Regeneration Manager (started July 2024) to progress project forward. Next steps are to: - develop PID for feasibility and viability studies (RIBA Stage 1) - develop and agree brief for feasibility and viability studies |  | 2025-08-01 | Develop and agree PID and brief for feasibility / viability study - February 2025 | Engage consultant teams - May 2025 | Complete Feasibility and Viability Study - August 2025 |  | 24: On target; 25: Under Budget; 26: Off Target; 27: Low; 28: Low; 30: Works are currently being reviewed with scope and brief to be defined following on from the initial works to enable office space to be released from SAC. An internal meeting has been held and feedback from the use of the building by staff is being collated. There is likely to be a need for some limited works to address initial issues from the relocation to the Town Hall, followed by a more comprehensive review of the use of the entire building. A development project manager is to be allocated when resource is available to take forward proposals that involve alteration to the building. A request for further feasibility funding will be made to support the project progressing.; 33: RISK 1. There are multiple planned and ongoing works in the Town Hall (Lots 1, 2 and 4). There is a risk that proposed design options do not align with these works and the investment that they have involved. MITIGATION 1: Work closely with the wider project team to understand the scope and timescales for works and raise any potential clashes / synergies with aims of future design options. Ensure the briefing information (including floorplans) provided to the consultant team for Lot 3 captures all relevant and up to date information for the building.; 34: Works associated with the fire risk assessment and fire compartmentation study. In particular the urgent removal of documents from the basement, part of the scanning project - C3091; 40: 0; 41: 25072; 42: 0; 43: 0; 44: 0; 45: 25072; 46: 1281; 47: 15000; 48: -10072; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delays to definition of brief for feasibility and viability studies leading to slippage of forecasted spend into next financial year.; 51: 100000; 54: 100000; 55: 0; 56: 0; 57: 100000; 65: HL; 66: N/A; 69: No; 70: Yes; 71: No; 72: N/A as project is at Idea Stage; 73: No; 74: Yes; 77: N/A; 78: N/A; 80: Unsure; 92: DRG; 117: 0 | [12 empty] | 45578.6395 | nbreeze@oxford.gov.uk | Y | 45548.3337 | nbreeze@oxford.gov.uk
CIL Feasibility |  | B0130 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski | [6 empty] | Feasibility | £50k budget remaining is ear-marked for Cowley Branch Line feasibility. £6,650 has been allocated to revenue spend in relation to Legal advice, however further Legal costs (c£20k) have now been incurred. After meeting Legal fees, remaining unallocated CIL budget can cfwd to 23/24 be reallocated to another project. | [6 empty] | 24: On target; 25: On Budget; 27: Low; 28: Low; 30: £50k budget remaining is ear-marked for Cowley Branch Line feasibility. £6,650 has been allocated to revenue spend in relation to Legal advice, however further Legal costs (c£20k) have now been incurred. After meeting Legal fees, remaining unallocated CIL budget can cfwd to 23/24 be reallocated to another project.; 40: 0; 41: 43350; 42: 0; 43: 0; 44: 0; 45: 43350; 46: 0; 48: -43350; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Meanwhile in Oxfordshire | Meanwhile use of vacant retail units in Oxford City Centre and Oxfordshire market towns. To tackle the predicted significant increase in vacant units in Oxford city centre and Oxfordshire’s market towns, by initiating a multi-authority ‘meanwhile use’ collaboration. | B0131 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Miscellaneous Capital Spend |  | Carolyn Ploszynski |  |  |  |  | Clayton Lavallin |  | Completed | Undertaken Facilitated meeting on how Makespace and OCC can work together in future. Ongoing Comms and TikToks for Market additions through Meanwhile Prepare for Lessons learnt meetings with operator and then with all project partners ( OXLEP & Districts) Prepare doc for LGC award submission. Ongoing Liaison with Makespace on progress of final schemes |  | 44864 | 17 Jan lessons learnt with MS 18 Jan lessons learnt with OXLEP & districts |  |  |  | 24: Completed; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Undertaken Facilitated meeting on how Makespace and OCC can work together in future. Ongoing Comms and TikToks for Market additions through Meanwhile Prepare for Lessons learnt meetings with operator and then with all project partners ( OXLEP & Districts) Prepare doc for LGC award submission. Ongoing Liaison with Makespace on progress of final schemes; 33: Viability of Phase 2, years 2 & 3 based on Revenue income.; 34: Prepare lessons learnt & Evaluation documents and share experience to "others"; 40: 0; 41: 82317; 42: 0; 43: 0; 44: 0; 45: 82317; 46: 2364; 48: -82317; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Coach Parking Feasibility | Coach parking in the city centre has caused a number of issues and there has been a desire to move coaches out of St Giles. As a result work has been undertaken to review options and in particular to consider the option of coach parking at Oxpens car park | B0132 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Simon Taylor |  | Feasibility | **Feasibility funding in place, with project having been on pause due to need to sequence with wider County strategic transport policies. Current intention between City and County officers is to progress study as part of new "Central Oxfordshire Movement & Place Framework" programme of work. Atkins consultants have now been commissioned to undertake this feasibility study. Target milestones remain TBC** |  | 2024-07-05 | June-Aug 2024: report commissioned and started / inception date planned | Sep-Nov 2024: report finalised and outputs incorporated into COMPF |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: "**No material change this month, although with County ""movement and place framework"" getting started means that there's more chance of this being picked up soon** No instruction to progress this work at present. Work to date has included working with Oxfordshire County Council on the opportunities to provide further drop off and layover spaces for coaches. A number of options were identified and these are summarised in the attached note together with the County comments in response. Oxpens car park was ruled out due to the temporary nature of the opportunity and the cost of bringing it forward."; 40: 0; 41: 20000; 42: 0; 43: 0; 44: 0; 45: 20000; 46: 0; 47: 20000; 48: 0; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 69: No; 70: Yes; 72: n/a; 73: No; 74: Yes; 77: N:A; 78: N:A; 80: No; 81: This is a feasibility study only with an already appointed consultant; 83: Already Awarded; 84: 0; 92: DRG; 117: 0 | [12 empty] | 45579.3722 | staylor@oxford.gov.uk | Y | 45546.2067 | tmaxwell@oxford.gov.uk
Burial Space | Development of a proposal for a new Cemetery | B0133 | Development Board | Development Review Group | Development | Corporate Property |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Carri Unwin |  | Design & Specification | Planning approval held up because access to field not secured by property, so archaeology and EA requested borehole ground investigations cannot be carried out. Final legal documents for VP are still with solicitors for signing. Property plan to get VP first then negotiate License with farmer, around ground investigations, for the maintenance of the land before construction works. Additional measures to ensure no adverse impact on parking available to sports clubs has been put back to them (and RFU and Sport England) with aim they can now remove their objection. Athletics Club agreeable, and Property team finalising agreements with Athletics Club, OPT, and ODS - those these latter two can only be concluded following planning approval. Landscape Officer confirmed no objection. EA Pre App advice confirmed suitability of site, but they now wanting more monitoring from boreholes. Proposed monitoring plan gone to them in April 24. Comments back received, and meeting now scheduled to agree a drainage design and monitoring plan to their satisfaction. County Highways unreasonably asking for large scale highway infrastructure of: road widening; bus stops, and pedestrian crossing from the very low traffic small burial meadow, that were not requested from the much larger adjacent sports pitches development. Good availability of reclaimed burial plots, and ODS making good progress exploring options for giving up to 3 years extra supply in existing cemeteries while property deals and planning are concluded. |  | 2026-07-31 | Property sign agreement with farmer, and gain access to field. Oct/Nov24 | Archaeology investigations and borehole works started after VP Nov 24 | EA Approval of drainage design and monitoring plan |  | 24: On target; 25: On budget with slippage; 26: On target; 27: Medium; 28: Medium; 30: Multi-disc consultants making good progress on their programme. Positive Pre App from South Ox received and highway pre app underway. Development Board approved commencing stakeholder and public consultation on outline designs, subject to positive highways pre app engagement. So month delay awaiting this. Consultation material - project page, online survey, press release all prepared for the outline designs, which are of a high standard. Negotiations with tenant farmer ongoing. Operator model being worked up with ODS and OCC and going to ODS Board once ODS, CMT and Members agree, Targetting June ODS Board; 33: Risk: signing agreement with farmer promptly to obtain VP and enable archaeology and borehole works and planning approval. Caused delays to programme - new programme now agreed at DB. Delays will cause extra resource and consultant cost budget pressure. Mitigations: property team prioritising finalising the terms he offered. Risk: County Highways could continue to ask for an unreasonable amount of additional highway improvements. Causing budget, and or time pressure if c278 takes a long while to agree with lawyers. Mitigations: OCC Director to meet County Budget has been included. Try to push for early agreement and drafting of 278 Risk: property negotiation progress with Athletics Club, OPT and ODS slow . Mitigation: monthly meetings to track and minute actions. Risk: ODS costing of works schedules comes in over budgetted market rates, but under 10% over and Directors require ODS to be instructed. Then budget pressure on works and resource costs and programme. Risk of gap in availability just of new (not reclaimed) burial plots from Spring 2025. Mitigations: Burial service are stretching the remaining burial space available, and there is always good reclaimed burial availability. Reactive comms agreed. ODS looking at feasibility of releasing other small areas of land in existing cemetries; 34: Property signing deal with tenant farmer, or agreeing access Getting EA to meet to agree drainage design and monitoring plan Rugby club liaison now burial meadow provides net parking gain for them, but they are still angling for more.; 37: Yes through tree planting on site; 40: 0; 41: 353999.87; 42: 1323000; 43: 420869; 44: 0; 45: 2097868.87; 46: 59769.61; 47: 293999.87; 48: -60000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delays on planning and property work; 51: 1148000; 52: 419968.87; 54: -175000; 55: -900.13; 56: 0; 57: -175900.13; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: CDM Pre Construction Info Checklist circulated to PB, and agreed with Project Sponsor; 73: No; 74: Yes; 75: To be done; 76: To be done; 77: TEP; 78: N:A Tbc; 79: Meeting with Theo next week; 80: Unsure; 82: Design consultants to advice on work type, and capacity, in house skills required. And QS done cost estimate. Pricing pack designed for parity between ODS pricing it, (first stage if time in programme), and then other tenderers as EDD advises, to ensure scheme gains market rates and best value from an experienced Contractor who will carry out the majority of work themselves. Critical on this project there are no delays, and work is delivered very promptly and to high standards.; 92: DRG; 117: 0 | [12 empty] | 45579.2525 | cunwin@oxford.gov.uk | Y | 45558.1559 | rhaverson@oxford.gov.uk
Enabling Works for Decarbonisation Project | Package of enabling works required to facilitate the decarbonisation project, consisting of both repair of the existing M&E plant where compatible, and upgrade of plant where compatibility would not be facilitated by repair. | B0138 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | TBC |  | Completed | 1. Hinksey Commissioning complete. 2. Project Handed over to Property 08/02/2023 3. Currently reviewing O&M manuals/ Health and safety files. |  | 2023-01-27 | Completion of Hinksey Commissioning work |  |  |  | 24: On target; 25: On Budget; 26: At Risk; 27: Medium; 28: Low; 30: 1. Hinksey Commissioning complete. 2. Project Handed over to Property 08/02/2023 3. Currently reviewing O&M manuals/ Health and safety files.; 33: Barton Leisure Centre PHX heat exchanger claim by Willmott Dixon due to the pool water high levels of chlorine alleged to have caused corrosin on the heat exchanger.; 34: Pool cover issues to be finalised. Report from the indipendant H/S inspector received OCC currently reviewing the report.; 40: 0; 41: 0.39; 42: 638576; 43: 0; 44: 0; 45: 638576.39; 46: 0; 48: -0.39; 54: -638576; 55: 0; 56: 0; 57: -638576; 65: HL; 66: Yes; 77: F&G; 78: Willmott Dixon; 80: Unsure; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Kiosk Project | Redevelopment of the Kiosks at Gloucester Green | B0141 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Carri Unwin |  | Delivery | Cabinet in place, and date obtained from SSE for them to connect it. Currently then arranging for supply comppany to fit meter following SSE work. Hoardings in place until new electric supply connected and working, then disconnection can be done for other power supply on 38 -40 George St, and paving works completed. |  | 2025-03-31 | SSE connect supply to new cabinet - Nov 24 | Npower fit new meter into cabinet - Nov 24 | SSE disconnect electric from boundary of 38-40 George St - Mar 25 |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Surrender deal and VP agreed with tenant of Kiosks 1, and 2&3. and VP now achieved now on Kiosk 4, court action dropped - good news.. Project Board instructed that ODS to do project works even though most of work can be done one demolition sub Contractor and likely quicker to engage and get on the ground. QS, PM, PD appointed now, and have most costs from ODS and had pre start meeting, but still no solid hoardings up. Recent urgent project meeting ODS said solid hoardings design will de done by 22 Jun 23, and then 2 week lead time to get hoardings up on site. Then some site strip can be done. Legal advice is to get kiosks down asap, but gas and electric need disconnecting first. (Safety non negotiable from demolition contractor) All applications in.; 33: Risk of delays due to SSE process to connect new Cabinet, and due to Npower lead times to fit meter. Mitigation: regular chasing and communication. Risks of ODS electrician work slow to progress connections of power bollards, and finish Cabinet to LSD market satisfaction. Risk of delays due to SSE process to carry out disconnections of Odeon wall infrastructure following new Cabinet live. Mitigation: schedule in time for all forms and chasing required; and OCC payments timescales.; 34: Chasing Npower for dates of fitting meter into Cabinet. Aiming to get other to do work promptly so hoardings can come down as approach Christmas trading. Ensuring paving work completed; 37: Minimal; 40: 179987; 41: 241034.3; 42: 0; 43: 0; 44: 0; 45: 241034.3; 46: 117505.14; 47: 191034.3; 48: -50000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delays from utility companies; 51: 50000; 54: 50000; 55: 0; 56: 0; 57: 50000; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: CDM Pre construction info checklist circulated to Project Board; 73: Yes; 74: Yes; 75: None; 76: To be done; 77: Ibis; 78: ODS; 79: Meeting Theo next week; 80: Yes; 82: Some site clearance, then they subcontract demolition works to other firm; 84: 60000; 92: DRG; 117: 0 | [12 empty] | 45579.2525 | cunwin@oxford.gov.uk | Y | 45552.2066 | cunwin@oxford.gov.uk
Capital R&M Works | Budget for Capital R&M works resulting from condition surveys to be allocated to specific projects as approved. | B0142 | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Delivery | Project demand via ARG and DB - funding includes 46 George st, South Park & Alexandra sports projects | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Medium; 30: Allocations made to former Jamie's works and Gas Works Pipe Bridge projects following Cabinet reports. Allocations retained in 22/23 for potential contributions to legacy projects relating to commercial property stock.; 33: Key risks: 1. Additional cost to meet the programme and bridge opening at the end of May 2024 2. Delays to appointment of Contractor; 3. Labour and material shortages; 4. Increased material prices; 5. Delays in obtaining work permits; 6. Delays due to adverse weather conditions; 40: 500000; 41: 619586.29; 42: 1200000; 43: 0; 44: 0; 45: 1819586.29; 46: 23140; 47: 1000000; 48: 380413.71; 54: -1200000; 55: 0; 56: 0; 57: -1200000; 65: HL; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
46 George Street | Capital R&M Works |  | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Delivery | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45548.3337 | nbreeze@oxford.gov.uk
South Park | Capital R&M Works |  | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Delivery | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Alexandra Sports Projects | Capital R&M Works |  | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Delivery | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45547.3786 | mnorvell@oxford.gov.uk
Town Hall Relocation (Lots 1 and 4) | Project to consolidate the Council’s office space within the Town Hall following decision to let the whole of SAC. Original £1m budget for works to SAC to enable letting re-purposed. Town Hall Projects are now split into 4 Lots: Lot 1 - works related to move from SAC - largely complete - B0143 Lot 2 - Ongoing maintenance and H&S works - led by property services team - B0157 Lot 3 - Options for the future of the Town Hall - B0129 Lot 4 - ICT Works - B0143 | B0143 | Development Board | Development Review Group | Development | Corporate Property |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Nathan Breeze |  | Delivery | Town Hall Projects have been reorganized from 3 Phases into 4 Lots. This Project was previously called Phase 1 and is now Lot 1. Phase 1 activities have been split between Lot 1 and newly created Lot 4 for ICT Works (overseen by Rocco Labellarte) Lot 1 and Lot 4 activities both have budget allocated from Phase 1 budget (B0143) Key works in Lot 1: - Signing off of historic building control application - ongoing - Old Museum Shop to Display Area - target start in January 2025 - Movement of Print and Post function - awaiting clarifications Key works in Lot 4: - WiFi Expansion - target installation 21/10/24 - 16/12/24 (w/e and out of hours working) - Upgrades to PBX (Server) Room - consists of enabling works to upgrade the room (ceiling, walls, doors, AC) followed by upgrades to cabinets. Target final installation June 2025. - IT Build Room - Basement room to surveyed to identify damp issues to be addressed. Target completion date is February 2025 |  | 2025-05-01 | WiFi Expansion part 1 - December 2024 | IT Build Room - February 2025 | Upgrade PBX Room - June 2025 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Project running in line with programme 2/12/2022 Completed on programme-snagging and in use changes ongoing; 33: Coordination of all projects related to Town Hall. Regular meetings with Property teams to ensure no conflicting work areas.; 34: Individual projects may need the input of a fire engineer to determine the require fire protection needed for compliance with statutory regulations.; 40: 0; 41: 479010.97; 42: 0; 43: 0; 44: 0; 45: 479010.97; 46: 39913.14; 47: 190000; 48: -289010.97; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Slight delays to start of PBX room upgrade and print and post room relocation will result in forecasted spend moving into next financial year.; 51: 289010.97; 54: 289010.97; 55: 0; 56: 0; 57: 289010.97; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: PD has been appointed to oversee Lot 1 projects; 73: No; 74: Yes; 77: n/a; 78: To be appointed for PBX room following IT commissioned report; 80: Yes; 81: There are fit out works to the server room required.; 82: This will involve some upgrades to walls and ceilings to improve fire compartmentation. There will also upgrades to incoming services.; 83: Direct Award; 84: 45000; 92: Both; 117: 0 | [12 empty] | 45583.1382 | nbreeze@oxford.gov.uk | Y | 45552.3706 | jnorman@oxford.gov.uk
Salary Costs across the Council to be capitalised |  | B0144 | Development Board | Development Review Group | Corporate Resources | Financial Services |  | Miscellaneous Capital Spend |  | Nigel Kennedy | [6 empty] | Other Capital Spend | 0 | [6 empty] | 24: Not started; 40: 380000; 41: 1760591; 42: 663000; 43: 663040; 44: 663040; 45: 3749671; 46: 0; 48: -1760591; 54: -663000; 55: -663040; 56: -663040; 57: -1989080; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
St Michael's Street Levelling Works and Feasibility | Street levelling works | B0145 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Mim Norvell |  | Delivery | Investigative trench survey confirmed an estimated £19.8k additional costs (main cost Virgin Media). Agreed with HoS/HoF to vire from unallocated City Restart CIL. Budget remains under £500k. Crossing £500k threshold would require Leader delegation (Brown/Hollingsworth) for decision to proceed. S278 progressing. Potential for COMPF/ZEZ/SPF underspend contribution for enhancements, potentially reintroducing removed elements. Construction planned for Jan-Mar 25. |  | 2025-03-31 | Proceeding to contract with ODS | County/Legal s278 approval Oct/Nov 24 |  |  | 24: On target; 25: On budget; 26: On target; 27: Medium; 28: Medium; 30: ">Working with consultants & ODS rescoping/value engineering to bring costs closer to budget. Awaiting weight bearing test w/c 19/6 to confirm that saving costs via reduced / adjusted build up is satisfactory. This and other measures will be required. Options to be presented at DB 20/7. >Construction shift from Autumn to Jan-Apr 24 will connect with additional SPF allocation 24-25 >Party Wall Act concluded by Legal/AAP as not applicable. Notifications/schedule of conditions will be actioned instead for due diligence. >County approved 13m extension of closure area (North Gate Hall)"; 33: > Works/Legal delay affecting SPF spend criteria deadline - construction programme reviewed and agreed with ODS, early engagement with Legal > Services cause unexpected delays - GPR survey / investigative trenches, increased budget, early engagement with utilities; 34: Agree chamber works detail with Virgin Media, S278 progression, adjust design approach to potential planters/seek commuted sum.; 40: 168817; 41: 408826.57; 42: 0; 43: 0; 44: 0; 45: 408826.57; 46: 23579.45; 47: 288019.57; 48: -120807; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Reprofiling of billing programme; 51: 120807; 54: 120807; 55: 0; 56: 0; 57: 120807; 65: HL; 66: Yes; 69: Yes; 70: No - answer next question; 71: Yes; 72: PCI requested; 73: No; 77: AA Projects; 78: ODS; 80: Yes; 81: Delivery of construction works Jan-Mar 25; 82: Delivery of construction works Jan-Mar 25; 83: Direct Award; 84: £208,666 24/25 - £120,807 25/26; 92: DRG; 117: 0 | [12 empty] | 45582.3711 | mnorvell@oxford.gov.uk | Y | 45548.4125 | jbarker@oxford.gov.uk
Ice Rink - Car Parking | Develop proposals to ensure there are approximately 25 spaces available to meet the needs of ice rink users when the Oxpens car park closes. | B0146 | Development Board | Development Review Group | Communities | Regeneration & Economy |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Jane Norman |  | Design & Specification | The latest proposal for 12 parking spaces has internal approval and consultants have prepared a planning application to reflect this. The project is on hold until there are sufficient staff resources within the regeneration team to support it. |  |  | Project on hold |  |  |  | 24: On Hold; 25: On budget; 26: On target; 27: Medium; 28: Medium; 30: Draft report to 16 June Cabinet approved. It is recommending parking at front option which will progress to full council in July for budget. Pre-app undertaken; recommended more planting which may compromise number of spaces. OxWED indicate car park will close earliest Summer 2025. Need to be ready for Summer 2025 as worst case. Implementation timing needs to be cognisant of the Ice Rink relocation timeframe. Si undertaken to advise that parking at front is technically feasible. Cost estimates upgraded to take account of larger contingencies to cover unknown time and rising construction inflation.; 33: Risk 1: New proposals not acceptable to planning & user groups Mitigation 1: Meeting with user group, pre-app discussions. Risk 2: Ice rink users unhappy with proposals leading to reputational risk. Mitigation 2: Reduce risk by open dialogue and good Comms; 34: Management of new car park by the new leisure operator & associated permissions. Consider impact of BNG/landscaping proposals Update scheme plans for reduced spaces scheme. Submit planning application. Discuss with Leisure disruption to operation of Ice rink during construction.; 40: 100000; 41: 16065.93; 42: 130000; 43: 0; 44: 0; 45: 146065.93; 46: 10415; 48: -16065.93; 54: -130000; 55: 0; 56: 0; 57: -130000; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: Glanville to prepare at appropriate time (after design); 73: Yes; 74: Yes; 77: Glanville Consultants; 78: TBC (ODS); 79: Still at design stage; 80: Yes; 82: ODS have completed Site Investigation work and could potentially undertake works once planning permission has been granted.; 83: Direct Award; 84: £100,000 plus( depending on timing of work); 92: DRG; 117: 0 | [12 empty] | 45579.3148 | jnorman@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Repairs to 24-26 George St (Fomer Jamie's) | Repairs to former Jamie's Italian restaurant site to enable re-letting | B0147 | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Completed | Project practical completion has been achieved, waiting for final accounts to be concluded with ODS. Possible further works required but negotiations with new tenant are underway and due to be concluded the coming weeks. |  | 2023-10-27 | Completion October 2023 | Final Accounts by end of Dec |  |  | 24: Completed; 25: On Budget; 26: Completed; 27: Low; 28: Low; 30: Project, although delayed, still looking to complete on time (end of June).; 33: Budget spend is being scrutinised by QS & CA for validity; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 847823.78; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 70: Yes; 73: Yes; 74: Yes; 77: Andrew Glossop; 78: ODS; 79: Satisfactory; 80: Yes; 82: External decoration & roof works project; 84: 616385.32; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
OFAS HIF Contribution | £4.35m contribution from HIF to the OFAS scheme. | B0148 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Jenny Barker |  | Feasibility | Homes England have provided a revise Deed of Variation to the funding agreement. This has addressed some significant issues with the original funding agreement including extending the period for the draw down of the funding to March 2025. Response has been sent and final version awaited. Capacity funding has been received for 22/23 and 23/24 to address some of the HIF internal costs to date. A bid has been made for capacity funding for 24/25 and HE have requested further details. |  | 49765 | Agreement of Deed of variation - October 24 | Agreement with the EA - October 24 | Clearance of pre drawdown conditions - Dec 24 |  | 24: Off Target; 25: On Budget; 26: Off Target; 27: Medium; 28: Medium; 30: "Work is progressing on a Deed of Variation to the funding agreement with Homes England and back to back agreements with Oxfordshire County Council/EA. These are necessary to enable the drawdown of funding and reduce the risk to the Council on transferring funds . A further report has been presented to the Cabinet and delegated approval has been agreed to enter the agreements. Oxfordshire County Council have sought to avoid taking on liability related to the HIF funded works. Agreement has been reached with the EA to take on the liability. The works to be funded are also behind schedule so there is some risk around the ability to drawdown the HIF based on County works once agreements are reached. UofO have raised concerns re meeting the HIF outputs. HE have provided a letter of comfort around the reclaiming of funding. This highlights the potential to work with Homes England should the milestones prove a problem. Capacity funding has been received to address some of the HIF costs to date."; 33: This HIF is particularly complex as there are two elements of works being funded separately from the housing delivery which is being facilitated by the funding. There remains a risk that it will not be possible to claim the funding, which requires pre conditions to be met and evidence of spend. A recovery strategy is sought related to housing delivery and this is subject to discussions with U of O. There is a risk that if housing is not delivered at Osney Mead that the funding could be clawed back by Homes England.; 34: The priority is to reach agreement with Homes England over the funding agreement to be able to move forward with confidence. An agreement with the EA is then required to enable funding to be passed to them.; 37: not directly; 40: 0; 41: 4350000; 42: 0; 43: 0; 44: 0; 45: 4350000; 46: 0; 47: 4350000; 48: 0; 50: Funding is going to be required to be drawn down by March 2025 and will then be passed to the EA.; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 74: Yes; 77: NA; 78: NA; 80: No; 81: OFAS is being delivered by the Environment Agency who have already procured a contractor.; 92: DRG; 117: 0 | [12 empty] | 45579.4896 | jbarker@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Tumbling Bay Embankment Works | Initial feasibility budget to carry out required surveys. Budget to carry out works to be included in 23/24 budget. | B0149 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  | James Axford |  | Luca Minetola |  | Design & Specification | Project is still in design stage awating permits for EA. Public engagement and planning once these stages are achieved. |  | 2025-10-28 | Design Completion / Tender | Planning / FRAP | Delivery June 2025 |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Surveys on bank to be undertaken once water levels have dropped. Budget for both Tumbling Bay and Long Bridges works included within 23/24 budget.; 33: Public access is now restricted with Heras Fencing & signage.; 34: Planning & FRAP; 40: 0; 41: 31185.5; 42: 250000; 43: 0; 44: 0; 45: 281185.5; 46: 5667.87; 47: 281185.5; 48: 250000; 54: -250000; 55: 0; 56: 0; 57: -250000; 65: HL; 80: Yes; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Hinksey Pool Liner | Replacement of damaged liner at deep end. | B0150 | Development Board | Asset Review Group | Communities | Community Services |  | Rolling Programme |  | Peter Matthew |  |  |  |  | Luca Minetola |  | Completed | 0 |  |  | Variation instructed to original order, now to include pool side repair |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 37: no; 40: 0; 41: 18385; 42: 0; 43: 0; 44: 0; 45: 18385; 46: 0; 48: -18385; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 77: Fusion; 80: No; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Bus Shelters | Procure new long term contract to manage city bus shelters | B0151 | Development Board | Development Review Group | Development | Corporate Property |  | Capital Delivery |  | Emma Gubbins |  |  |  |  | Jane Norman |  | Feasibility | The Bus Shelter Tender was launched on the 22nd July with a closing date of the 6th September. The bids will be evaluated during September/ early October with the contract commencing in November 2024. The tender has included the station and NHS shelters for information only to allow these to potentially be included in the contract in the future. Further discussion with Network Rails/GWR and the NHS will be required once the supplier has been appointed. |  | 45628 | Contract Award- November/December 2024 | Implementation Phase- January-Mar 2025 |  |  | 24: On target; 25: On budget; 26: On target; 27: Medium; 28: Low; 30: Project is still on schedule for the new contract to start on the 1st Dec 2023. 6 organisations are interested in bidding. having completed addition market engagement the potential income generated and the preferred contract length (15 years) means this will be going to Cabinet for sign off in July. The tender will be launched shortly after.; 33: Programme delay- the programme timeframe has slipped but the tender process is on target for the award of contract before the current contract ends in late November/early December. Lack of interest in the tendering opportunity - 6 suppliers were interested but only 2 bids were received, one being the current incumbant. Lack of resource to secure and manage new contract - PM has input from Property, Procurement, Legal and County to keep things on track Public opinion- negative press re replacement of bus shelters - explain the reasoning via positive promotion of the new contract and the opportunities it will bring in terms of improved services and the use of sustainable materials, fact that shelters will be recycled etc. Planning and highways issues - it will be the responsibility of the contractor to obtain necessary permissions for any new shelters etc. and this will be made clear during the market engagement.; 34: Evaluation of bids, selection and appointment of supplier implementation plan to replace shelters, exit strategy to be agreed with current provider Clear Channel if not appointed.; 37: Yes- with the use of sustainable materials and green roofs; 40: 0; 41: 15049.79; 42: 0; 43: 0; 44: 0; 45: 15049.79; 46: 9811; 48: -15049.79; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 69: No; 70: Yes; 71: Yes; 72: The existing contract in place maintains and cleans all bus shelters, this has been extended until DEC 24, with a roll over extension and one month notice agreed, until a new contract is in place.; 73: No; 74: Yes; 80: No; 81: This relates to the tender process for the Bus Shelter Infrastructure and Advertising Concession contract which has been completed and the preferred bidder published on the 11th October 2024.; 83: Already Awarded; 92: DRG; 117: 0 | [12 empty] | 45579.3148 | jnorman@oxford.gov.uk | Y | 45552.2647 | anhumpherson@oxford.gov.uk
Cowley Branch Line Full Business Case | Project to undertake the Approval in Principle design and Full Business Case and local connectivity studies for the reopening of the Cowley Branch Line to passengers. This includes the parameters for a financial contribution from Oxford City Council, including the ring-fencing of future Community Infrastructure Levy (CIL) contributions | B0152 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Rui Marcelino |  | Feasibility | Project is up and running. Programme Panel meetings taking place every 4 weeks as well as NwR progress meetings. Pedestrian and Cycle bridge design (Oxford Cowley station) RIBA stage 1 completed and RIBA stage 2 underway. commissioning of the Infrastructure Place Study (IPS) was completed just before Christmas, just subject to contract formal signing taking place Wed 17th Jan. Formal inception meeting to take place on Wed 17th Jan and IPS team already invited to attend several working groups and engagement meetings. Additional work has also been commissioned by County on Development of a developer contributions strategy for infrastructure to support the reopening of CBL, this has been completed and it is anticipated that the IPS team will pick this up and progress it further. Although CDM principal Designer was not part of the IPS commission, lead consultant has provided cost estimate for this should we wish to instruct it. |  | 2026-12-01 | Completion of RIBA stage 2 concept design Pedestrian and cycle bridge - End Feb 2024. | Contract start for Infrastructure Place Study - Contract signing Wed 17th Jan | Completion Full Business Case (PACE phase 2 part 1) - Nov 2024 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Collaboration Agreement, Development Services Agreement and MOU all signed at the end of March. Dedicated project manager started 17th April, and Project is up and running. Programme Panel and NwR progress meetings have taken place and currently developing the procurement specification for commissioning the Infrastructure Place Study.; 40: 1689183; 41: 2599669.13; 42: 653350; 43: 0; 44: 0; 45: 3253019.13; 46: 1420616.46; 48: -2599669.13; 54: -653350; 55: 0; 56: 0; 57: -653350; 65: HL; 66: Unsure; 77: Please see project update; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
HSBC Options | Building has a joint freehold, and options need to be considered should current tenant activate lease break clause. This budget allows exploration of preferred of option by carrying out an external valuation, legal and tax advice, and engaging in early conversation with joint freeholder. | B0153 | Development Board | Asset Review Group | Development | Corporate Property |  |  |  | Jane Winfield |  |  |  |  | Kate Protheroe |  | Feasibility | Initial and midway meetings have been carried out with consultant and now awaiting completion of draft report to consider for internal approval |  | 2024-10-25 | Receipt of draft report by 25th October | Discuss results of feasibility report at ARG/Development Board |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Medium; 33: Confirm once report received; 34: Maximising income/capital receipt and best future use of the building; 40: 0; 41: 55000; 42: 0; 43: 0; 44: 0; 45: 55000; 46: 0; 47: 12000; 48: -43000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Left time for internal approval before using rest of budget; 51: 43000; 54: 43000; 55: 0; 56: 0; 57: 43000; 66: N/A; 80: No; 81: Currently at options analysis/feasibility stage for future use of the building, so no opportunities until lease renewal expires in 2030.; 92: ARG; 117: 0 | [12 empty] | 45580.2808 | kprotheroe@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Covered Market refurbishment & regeneration | A preferred development option for supporting successful long-term future of the Covered Market & its surrounding streets was selected by leadership & cabinet in Feb '23 & next project stages are proceeding on basis of this decision. A new consultant team is now appointed to deliver the masterplan. The new team has completed a review of RIBA Stage 2 works. | B0154 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Andrew Humpherson |  | Delivery | Project management and design team consultants including Principal Designer now appointed. Key Stage One milestone works to review and revise the current masterplan and essential works proposals completed and under review by Project Board. Proposals to be finalised and supported by a revised business case for approval before progressing to detailed design in the new year. Property Services scope of remedial works to be identified separately. Consultation is on-going with All Souls College in respect of college proposals to extend and refurbish High Street properties including air rights development and market entrance improvements. Works will help offset OCC masterplan costs. |  | 46273 | Consultant team now working to September deadline to complete a project and budget review for delivery of the masterplan. Draft review tabled at OCM Board 17/09/2024 | Consultant completion Milestone One works Sept/Oct 2024. Initial review complete pending OCC feedback and decision on next steps. | RIBA Stage 3 works to commence on budget approval February 2025 |  | 24: On target; 25: On budget; 26: On target; 27: Medium; 28: Medium; 30: "Nat Delfino has taken over as project lead from Ted Maxwell in April '23 - transition has been well-managed, with good handover/background support & no perceived adverse effects to project delivery. Following cabinet approval in Feb '23, a workshop has been held in the same month to review the Feasibility phase & plan the next stages. Two monthly Project Boards have also been held since, in April & May '23. Next steps & key actions: - ND 121s to get to know team members/key stakeholders & key project aspects/challenges = continue - Building Services = NDe set up Working Group to encourage more collaboration between Regen & Property Services team. Input from property services team re MEPH surveys results is delayed & outstanding due to 3rd party service providers' lack of responsiveness; - Key market trader lease conditions that could block development = continue investigating new risk highlighted by Property colleagues at April '23 PB; - Market street part-pedestrianisation = lead consultant RFQ issued & budget increased due to lack of market interest. Offers due back 19/6. Working Group set up to engage with project team & key stakeholders & proceeding well. Workstream being led by Mim Norvell, reporting into ND; - Procurement strategy for consultants & contractor = finalise & approve in May/June '23 [Timeline extended re introduction of new Due Diligence phase by ND]; - Programme = ND will update provisional draft programme to include a new Due Diligence Phase, which is a new pre-construction stage which will take place prior to Detailed Design being undertaken. This new project phase is required given implications of Infrastructure/MEPH workstream need to be incorporated into the current feasibility/concept design & wider implications understood, prior to project being progressed to detailed design stage. Programme will remain in provisional draft form until the consultants + contractor are in place; - Heritage-led Asset Management & Maintenance Plan = development of this document is seen by Planning/Heritage team as a key output from the project to ensure long-term life of the market - TBC who is in charge of developing & managing this doc; - Project brief = develop & approve in May/June '23 [Timeline extended re introduction of new Due Diligence phase by ND]."; 33: Project concerns over additional budget to deliver essential utilities work now largely mitigated following completion of Stage 2 review. Proposals and business case under review including reduced scope within original masterplan budget and option for additional funding supported by a revised business case. Preferred option pending decision by project board. Revised proposals will require a revised business case with separation between essential works and masterplan works as part of a revised viability model. Central Government funding uncertainty = current SPF £300K funding allocation within project’s £6.5m budget could be at risk, as it may need to be used to fund other under-funded R&E projects. Loss of public/wider interest = possible member perception that project progress is taking too long to materialise & possible political/ reputational ramifications of this. Mitigation - consultants have completed Stage One review providing more certainty on deliverability.; 34: Stage 2 review has identified two main options for further consideration. Options include consideration for further investment subject to board approval and a revised business case. Final proposals will be dependent on wider council budget review. Options under consideration as risks and mitigation above.; 37: Environmental sustainability objectives part of project brief and will be part of decision-making process regarding preferred options at each stage.; 40: 1513991; 41: 797647.39; 42: 589820; 43: 2906795; 44: 3265551; 45: 7559813.39; 46: 369806.38; 47: 672979; 48: -124668.39; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Stage 3 approval to proceed pending approval to OCC MTFP and wider budgetary constraints; 51: 535790; 52: 2975992; 53: 2968047; 54: -54030; 55: 69197; 56: -297504; 57: -282337; 65: HL; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: Principle Designer (CDM & BSA) now appointed; 73: No; 74: Yes; 77: Now appointed together with Principal Designer BSA (Building & Safety Act); 78: Future appointment by Contractor; 80: Unsure; 81: Market Street works completed by ODS with a contract value of £163K. Further utilities works will be required within the market and potentially in Market Street to support the masterplan. These works will be subject to detailed design in 2025 at which point the potential scope for ODS may be clearer; 82: Future utilities replacement works and asset management works - roofs, redecoration etc. within the Covered Market as part of the masterplan and subject to detailed design in 2025.; 83: Tender; 84: 163294.7; 92: DRG; 117: 0 | [12 empty] | 45580.3012 | anhumpherson@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Waterways Condition Survey | Survey to ascertain condition of waterways | B0156 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Completed | Condition survey now completed. |  | 45212 | Project Initiation | Design & Tender | Project Delivery |  | 24: Completed; 25: On budget; 26: Completed; 27: Low; 28: Low; 40: 355000; 41: 354657.58; 42: 0; 43: 0; 44: 0; 45: 354657.58; 46: 121101.55; 48: -354657.58; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 68: No; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Town Hall Works | Refurbishment Programme | B0157 | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Works are being split into phases from Asset data and surveys |  |  | Appointment of design team | package of works out to tender | Project Completion |  | 24: Not started; 25: Budget to be agreed; 26: On target; 27: Low; 28: Low; 30: Works are being split into phases from Asset data and surveys; 40: 1500000; 41: 1521915.25; 42: 1500000; 43: 0; 44: 0; 45: 3021915.25; 46: 261039.05; 47: 1521915.25; 48: 0; 54: -1500000; 55: 0; 56: 0; 57: -1500000; 65: HL; 79: Satisfactory; 80: Yes; 84: 200000; 92: ARG; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2647 | anhumpherson@oxford.gov.uk
Ceilings (Phase 7) | Refurbishment Programme |  | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Works are progressing well and due for completion in November 24 |  | 2024-11-30 | Start on Site January 2024 | Early handover of Meeting Rooms August 2024 - Achieved. | Practical Completion/ November 2024 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: Variations to original Contract - Catch Deck Scaffolds installed in Boiler House. Servery Ceiling Repaired to enable business as usual. Boothole temp propping continues. Designs for Boothole in progress.; 34: Costed Designs required for Boothole and SW Turret. Mitigations in Boiler House must be tackled in Phase 8.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 300000; 48: 300000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45546.1351 | adorrington@oxford.gov.uk
Facade Clean | Refurbishment Programme |  | Development Board | Asset Review Group | Development | Corporate Property |  | Rolling Programme |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | "ODS on traffic management plan costs are over £150k pushing project costs over £500k. Cabinet paper now required for project to prgress to next steps in March 2025." |  | 45747 | Package price now over £500k | Traffic management plan to be approved by County & delayed until Mar 25 | Start on site |  | 24: Off Target; 25: Budget to be agreed; 26: Off Target; 27: Medium; 28: Low; 33: Project costs from ODS have pushed the budget proposal above deligated amount so will need to complete a cabinet report; 34: ODS traffic mangement costs over £150k pushing project costs over £500k, cabinet paper to follow.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 200000; 48: 200000; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45547.1653 | kprotheroe@oxford.gov.uk
Redbridge Masterplan | Redbridge Masterplan feasibility | B0159 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Andrew Humpherson | Project - Development | Feasibility | Consultants (commercial and reference masterplan) recommendation agreed pending review of Decision Notice. Infrastructure and Transport consultant tenders now active. |  | 2025-10-31 | Lead consultants to be appointed August 2024 Infrastructure & transport consultant tenders August 2024 | Outline Options appraisal to be complete February 2025 | Business Case & Report (subject to approval to options appraisal) Aug 2025 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: Comparative analysis of options and assessing preferred options will be difficult to agree with competing demands for site. Need to engage with County with regard to transport and alternate park & ride site adjacency Members concerned at transport limitations and impact on options appraisal. Review of existing transport studies proposed to confirm there are growth opportunities within existing transport infrastructure.; 34: Consultant appointments to be finalised to start works; 40: 0; 41: 138113; 42: 0; 43: 0; 44: 0; 45: 138113; 46: 17751; 47: 50010; 48: -88103; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Extended consultant procurement process including finalising contract terms.; 51: 71818; 52: 0; 53: 0; 54: 71818; 55: 0; 56: 0; 57: 71818; 65: HL; 66: No; 80: Unsure; 81: Works will be dependent on the outcome of the options appraisal currently being commissioned; 82: Potential Waste Recycling Centre to be considered as part of the development options; 83: Tender; 84: 0; 117: 0 | [12 empty] | 45580.3012 | anhumpherson@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Templars Square (GF Element) | Templars Square (GF Element) | B0160 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Andy Dorrington |  | Feasibility | [7 empty] | 40: 0; 41: 0; 42: 100000; 43: 0; 44: 0; 45: 100000; 46: 404; 48: 0; 54: -100000; 55: 0; 56: 0; 57: -100000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Floyds Row (Feasibility 2024) | Floyds Row (Feasibility 2024) | B0161 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Kate Protheroe |  | Feasibility | Draft report received and comments reverted back to Carter Jonas. Scope of project increased to include wider regeneration area. |  | 45607 | Instruct Carter Jonas for further feasibility on wider regeneration project | Report on wider regeneration received for internal review and approval |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Medium; 33: Property is vacant during process but is regularly inspected by vacant property team. Business rates will need to be mitigated.; 34: Issues addressed in options analysis to cover market conditions for both leasing and freehold/long leasehold sales and redevelopment potential; 40: 1050000; 41: 50000; 42: 0; 43: 0; 44: 0; 45: 50000; 46: 0; 47: 27000; 48: -23000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Allowance of time for internal approvals; 51: 23000; 52: 0; 53: 0; 54: 23000; 55: 0; 56: 0; 57: 23000; 66: N/A; 80: Unsure; 81: Options analysis being undertaken so depends on outcome - still at feasibility stage; 82: Potential for future refurbishment work of building, but depends on outcome of options analysis; 83: Quotes; 84: Unable to estimate at this stage; 117: 0 | [12 empty] | 45580.2808 | kprotheroe@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Property Services Works to Town Hall | Property Services Works to Town Hall | B0162 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Feasibility | Project Inititation |  |  | Project initiation |  | Project completion |  | 24: Not started; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Network infrastructure installations (Utilities, Comms & Energy) | Network infrastructure installations (Utilities, Comms & Energy) | B0163 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | In progress no spend in year - slip 40K to 25/26 | [6 empty] | 24: On Hold; 25: On budget; 26: On target; 27: N/A; 28: N/A; 40: 40000; 41: 40000; 42: 40000; 43: 40000; 44: 40000; 45: 160000; 46: 0; 48: -40000; 49: Slippage (Less spend in 24/25 now forecast in future years); 51: 40000; 52: 40000; 53: 80000; 54: 0; 55: 0; 56: 40000; 57: 40000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Waterways Investment | Waterways Investment | B0164 | Development Board | Asset Review Group | Development | Property Services |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Long Bridges |  | 45596 | Start on site 05/08/2024 | Start on site | Project Completion 31/10/2024 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 500000; 41: 500000; 42: 0; 43: 0; 44: 0; 45: 500000; 46: 0; 47: 500000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Stone Walls & Railing Programme | Stone Walls & Railing Programme | B0165 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Delivery | Budget code not on P2P and unable to raise orders - Issue raised with Finance (PS) orders ready to issue once code sorted out |  | 45777 | Project Initiation | Design & Tender | Project Delivery |  | 24: On target; 25: Budget to be agreed; 26: On target; 27: Low; 28: Low; 40: 100000; 41: 100000; 42: 0; 43: 0; 44: 0; 45: 100000; 46: 0; 47: 100000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Broad Street Roofing & Facade project | Broad Street Roofing & Facade project | B0166 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | 19 to 20 Broad Street are currently been surveyed by TMD and awaiting results at the end of October. The broader Broad Street project for the remaining properties is due to go onto intend W/C 7th October 2024 |  | 47208 | 19 to 20 Broad Street: Design and Tender, Broader scheme: Survey | 19 to 20 Broad Street: Start on site, Broader scheme: Design and Tender | 19 to 20 Broad Street: Delivery, Broader scheme: Start on site |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: Access for erecting scaffolding is restricted to specific days, seasonal markets and university exams.; 40: 2000000; 41: 500000; 42: 1500000; 43: 0; 44: 0; 45: 2000000; 46: 0; 47: 120000; 48: -380000; 54: -1500000; 55: 0; 56: 0; 57: -1500000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Fire Risk Assessment programme works | Fire Risk Assessment programme works | B0167 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Rolling Programme | Depending on survey outputs and specific action types. This budget is difficult to define, as works need to be categorised for delivery by Capital program first, however, where these do not coincide , this budget applies. |  | 45747 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 50000; 41: 50000; 42: 0; 43: 0; 44: 0; 45: 50000; 46: 11800; 47: 50000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45554.1383 | drutter@oxford.gov.uk
Bridge investment work | Bridge investment work | B0168 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Delivery | Tumbling Bay and Trill Mill bridges went to DB on the 7th of October 2024 and was approved to proceed. |  | 2026-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: None foreseen; 40: 500000; 41: 400000; 42: 300000; 43: 0; 44: 0; 45: 700000; 46: 0; 47: 80000; 48: -320000; 54: -300000; 55: 0; 56: 0; 57: -300000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45554.264 | bmcrobie@oxford.gov.uk
M&E Capital budget | Funding capital replacement of assets including Fire Equipment, Gas Boilers, Electrical works and any components at EoL where there is statutory, H&S or income need | B0169 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Rolling Programme | Hinksey pool boiler replacement feasibility and design underway |  | 2025-03-31 |  |  |  |  | 24: On target; 25: Under Budget; 27: Low; 28: Low; 33: Not enough detail on further equipment needs, currently exploring options with providers; 40: 150000; 41: 150000; 42: 150000; 43: 0; 44: 0; 45: 300000; 46: 0; 47: 70000; 48: -80000; 49: N/A - On Budget; 54: -150000; 55: 0; 56: 0; 57: -150000; 80: Unsure; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
Bury Knowle House | Feasibility study looking into potential options for the site | B0172 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | David Rutter |  | Feasibility | Design team out to RFQ, will then be appointed following review of returns. |  | 45869 | Appointment of design team - November 2024 | Package of works out to tender - February 2025 | Project completion - September 2025 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 41000; 42: 0; 43: 0; 44: 0; 45: 41000; 46: 0; 47: 41000; 48: 0; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 69: Yes; 73: Yes; 80: Unsure; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Union Street Car Park | Feasibility study looking into the potential development of the site | B0173 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Bruce McRobie |  | Feasibility | Awaiting further information on ownership of small area that could be incorporated into the site to increase the footprint of the proposed development. Prices for an outline massing study will be sought be the end of July 24. Tender for viability advice will be sought during August 24 |  | 45747 | Land ownership information - 30th September 2024 | Outline massing study - 30th November 2024 | Viability assessment and report - 31st January 2025 |  | 24: On target; 25: On budget; 26: Off Target; 27: Low; 28: Low; 34: Procurement of consultants; RfQ's to be completed by end of Sept/24.; 40: 0; 41: 65000; 42: 0; 43: 0; 44: 0; 45: 65000; 46: 731; 47: 65000; 48: 0; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 81: The project is only a feasibility study.; 117: 0 | [12 empty] | 45579.2653 | bmcrobie@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
ICT Software and Licences | ICT Software and Licences | C3044 | Development Board |  | Corporate Resources | Business Improvement |  | Rolling Programme |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Rolling Programme | NOT A PROJECT. NO TARGET COMPLETION THEREFORE. |  |  | Not a project |  |  |  | 24: Completed; 25: Under Budget; 27: Low; 28: Low; 30: NOT A PROJECT; 40: 245000; 41: 245000; 42: 245000; 43: 245000; 44: 245000; 45: 980000; 46: 402356.99; 48: -245000; 54: -245000; 55: -245000; 56: -245000; 57: -735000; 66: No; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Housing System Replacement (QL Project) | Replacement of the legacy Northgate Housing, Northgate Codeman asset management and Civica Servitor systems. Introduction of a mobile working platform. | C3057 | Development Board |  | Communities | Housing - Homelessness (GF) |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Alison Cornacchia |  | Delivery | Tenant Portal - The tenant portal was successfully made live on 11th September. A soft launch of the portal was made to Tenant Ambassadors. |  |  | Tenant Portal - Extend the launch to new tenants during sign-up |  |  |  | 24: Completed; 25: Completed; 26: Completed; 27: High; 28: High; 30: Tenant Portal - test cycle 3 nearing completion with issue resolution retesting being the main focus (currently 20 issue in progress which is down from 83 in the last reporting period). The tenant portal Live server environment is now setup in preparation for go-live migration scheduled for next week. We aim to get Tenant Ambassadors registered and reviewing the portal by end June/early July. Aareon will refund OCC for expenditure on Choice-Based Lettings portal development. The preferred partner (MRI) will be providing a demo of the CBL products so that OCC can carry out due dillegence checks (requirements fit, timescales, infrastructure implications, procurement implications). Defects Liability workstream (direct any repairs reported to the developer during the defects period)is now Live and handed over to BAU. Work continues on the the property data loaders for newly built homes and component updates. The Mobile Forms pilot (Versaa Forms) has been developed and will be demo'ed to Tenancy Management next week.; 33: - Resources and capacity are critical for managing the volume of work activities, which are continuously being prioritized. - Ensure the supplier's resources and capacity are booked and available when needed. Request and book resources as early as possible.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: -9112.5; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45580.4473 | acornacchia@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
CRM Lagan Replacement | Repacement of the legacy CRM system with ASM | C3058 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  | Purnima Gore |  | Rocco Labellarte |  | Design & Specification | This project has been renamed the ASM Replacement as Lagan was replaced by ASM. requirements have been gathered. Need to sense check them with ODS before going to market. |  | 2024-10-31 | Sense check business requirements with ODS | Procurement via GCloud or CCS 30/10/24 | Implementation 28/02/25 |  | 24: On target; 25: On Budget; 26: Off Target; 27: Medium; 28: Low; 30: Discussing procurement route for cloud version upgrade. Contract award likely to take place early in 2023/24 - slip budget to 2023/24.; 40: 0; 41: 48264; 42: 0; 43: 0; 44: 0; 45: 48264; 46: 0; 48: -48264; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
End-Point Devices (Desktops/Laptops) | End-Point Devices (Desktops/Laptops) | C3060 | Development Board |  | Corporate Resources | Business Improvement |  | Rolling Programme |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Rolling Programme | 0 |  | 2021-06-30 | Closed |  |  |  | 24: Not started; 25: Completed; 26: Completed; 27: N/A; 28: N/A; 40: 150000; 41: 354366.83; 42: 150000; 43: 150000; 44: 150000; 45: 804366.83; 46: 42567.81; 48: -354366.83; 54: -150000; 55: -150000; 56: -150000; 57: -450000; 66: No; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.906 | rlabellarte@oxford.gov.uk
Telephony Device refresh | Telephony Device refresh | C3066 | Development Board |  | Corporate Resources | Business Improvement |  | Rolling Programme |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Rolling Programme | Not a project. Funding for device replacements as needed. |  | 2021-08-27 | Not a project. Funding for device replacements as needed. NO TARGET COMPLETION THEREFORE. |  |  |  | 24: Not started; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Not a project. Funding for device replacements as needed.; 40: 60000; 41: 33690.43; 42: 60000; 43: 60000; 44: 60000; 45: 213690.43; 46: 30411.79; 48: -33690.43; 54: -60000; 55: -60000; 56: -60000; 57: -180000; 66: No; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Form Engine Replacement | Replace all website and Lagan forms with new versions using Jady Forms software | C3072 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  | Purnima Gore |  | Rocco Labellarte |  | Completed | Project is closed. Residual capital of £642. |  | 45016 | Implementing waste forms. |  |  |  | 24: Completed; 25: On Budget; 26: Off Target; 27: High; 28: Low; 30: Forms developed. Waste forms are outstanding and being worked on.; 33: No risks noted.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 10800; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Telephony Contract Replacement | BT telephony contract replacement | C3080 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  | Purnima Gore |  | Rocco Labellarte |  | Delivery | Additional requirements being processed via Procurement in March. In the region of £25k additional spend. PO raised in early May. Go live at end of October. |  | 2024-08-31 | Go Live / End of August, early September |  |  |  | 24: On target; 25: On Budget; 26: Off Target; 27: Medium; 28: Low; 30: Project in delivery.; 33: ODS to join the pilot test in June.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 22599.5; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Capitalised ICT Projects |  | C3081 | Development Board |  | Communities and People | Business Improvement |  | Miscellaneous Capital Spend |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Idea | NOT AN ICT PROJECT - FUNDING SET ASIDE FOR ADDITIONAL FUTURE PROJECTS IF REQUIRED. NO TARGET COMPLETION THEREFORE. | [6 empty] | 24: Not started; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: N/A; 28: N/A; 30: NOT AN ICT PROJECT - FUNDING SET ASIDE FOR ADDITIONAL FUTURE PROJECTS IF REQUIRED; 40: 163200; 41: 615645.87; 42: 163200; 43: 0; 44: 0; 45: 778845.87; 46: 487626.21; 48: -615645.87; 54: -163200; 55: 0; 56: 0; 57: -163200; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Website Refresh & content update (duplicate on this list of projects) | Duplicated in C3097 | C3082 | Development Board |  | Corporate Strategy | Corporate Strategy |  | Capital Delivery |  | Mish Tullar |  |  | Purnima Gore |  | Rocco Labellarte |  | Closed | Website has gone live (phase 1) |  | 2024-01-31 | Complete migration of pages (pahse 2) | Migrate content 31/12/23 | All content and microsites to be migrated / 30-05-24. Capital costs set against incorrect cost centre code for the microsites. To be adjusted. |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 3106.25; 42: 0; 43: 0; 44: 0; 45: 3106.25; 46: 627; 48: -3106.25; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
FOI System |  | C3083 | Development Board |  | Corporate Resources | Law & Governance |  | Capital Delivery |  | Emma Jackman |  |  |  |  | Grace Wigham |  | Completed | All key users have now been trained. System went live on 26/06/2023. Webform and disclosure log have gone live. The decision has been made to publish FOIs which are deemed to have some public interest. |  | 2023-10-31 | Contract to begin 31/03/2023 |  |  |  | 24: Completed; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Demo given to Caroline on the 1/06/23, due to present demo on the 15/06/23 to CMT and further training of key users between 15/06/23 and 21/06/23 with go live date expected to be w/c 26/06/23; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 7875; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Agresso Update |  | C3084 | Development Board |  | Corporate Resources | Financial Services |  | Capital Delivery |  | Nigel Kennedy |  |  | TBC |  | Sonal Khade |  | Delivery | Project Team and Board have now been formed and project has started |  | 45327 | Cycle 3 UAT- 24th December |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Project Team and Board have now been formed and project has started; 33: Working with Project team to complete Cycle 3 of UAT; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 6167; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - I-trent replacement | Need to go to market to procure a system at contract end. | C3085 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Gail Malkin |  |  | Current plan is to extend contract to 31.03.28. Current contract is to 31.03.25. We are not in a good position to specify our exact needs. We need to improve use of current system and be clear about business needs before starting a procurement exercise. We are currently investing to improve processes and application. |  | 2027-12-31 |  |  |  |  | 24: Not started; 25: Budget to be agreed; 27: N/A; 28: N/A; 40: 0; 41: 0; 42: 20000; 43: 55000; 44: 0; 45: 75000; 46: 0; 47: 0; 48: 0; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Project delayed; 54: -20000; 55: -55000; 56: 0; 57: -75000; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
QL Exploitation | Enhance the QL Implementation by advancing mobile functionality and self-service capabilities. | C3086 | Development Board |  | Communities | Housing - Homelessness (GF) |  | Capital Delivery |  | Peter Matthew |  |  |  |  | Alison Cornacchia |  | Delivery | Versaa Forms - PEEP Form (Pilot) : Technical issues have been resolved. The OCC and ODS Versaa environments have been rebuilt and all environments have been successfully upgraded. Versaa Forms - Tenancy Services : The off-the-shelf Tenancy Services product issues have also been resolved. The handover of the product was completed at the end of September. Predictive Arrears (MARS) : The MARS solution has been successfully implemented. Notice has been issued to Mobysoft, who are currently progressing the off-boarding process. OCC has completed it's decommissioning tasks. Sub-Account & Former Arrears Solution : Requirements have been agreed, development completed and test cycle 1 completed. Housing Needs System Solution - Work has now started on the ITT Supplier Contract. Contractor Portal : Requirements have been gathered and process maps developed |  | 45716 | Versaa Forms - PEEP Form (Pilot) - Complete UAT (Oct 24) - Pre Go-Live Activities (Oct 24) - Soft Launch (Pilot Users) (Nov 24) Versaa Forms - Tenancy Services - Product and process familiarisation (Oct 24) - Testing Phase (Nov 24) | Predictive Arrears (Sub Account & Former Arrears) - Testing Phase (Oct / Nov 24) - Training (Nov 24) - Go-Live (Dec 24) Housing Needs System Procurement Exercise - Finalise ITT (Nov 24) - Publish Tender (Dec 24) - Evaluate Tender Responses (Feb 25) | Contractor Portal - Initiation Phase (Oct 24) - Installation and Configuration (Nov 24) - Testing Phase (Dec 24) - Pilot Contractor Onboarding (Jan 25) |  | 24: At Risk; 25: On budget with slippage; 26: At Risk; 27: Medium; 28: Medium; 33: - Budget forecast predicts this project will be over budget by the end of the financial year. This is mitigated by N7072 being under budget (all expenditure has been captured in the primary capital budget. - The adoption of the new solution is being facilitated through engagement with Business Areas, with a prioritized focus on key areas. - Resource and capacity management are crucial for handling the volume of work activities, which are continuously being prioritised. - Unforseen delays are introduced due to timescales involved in investigating and resolving technically complex issues involving multiple 3rd Party Suppliers.; 40: 256000; 41: 230655.88; 42: 78000; 43: 78000; 44: 78000; 45: 464655.88; 46: 212746.5; 47: 385500; 48: 154844.12; 49: Forecast Overspend at end of project; 50: Although the forecast reflects an overspend, it is mitigated by the N7072 being under budget. Collectively the 2 budgets will reflect an underspend due to slippage on some elements of the programme.; 51: 463700; 54: 385700; 55: -78000; 56: -78000; 57: 229700; 117: 0 | [12 empty] | 45581.2095 | acornacchia@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
ICT - replacing Netcall contact centre telephony and resource management system |  | C3087 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  |  | Project concludes in November 2024 |  | 2024-10-31 | Publish RFQ - August 2024 | Award contract - 28/09/24 | Implement solution - 30/11/24 |  | 24: Off Target; 27: Low; 30: About to publish RFQ for replacement. Waiting for Crown Commercial Services to publish framework in July/August.; 33: Demand on ICT resources is high and whilst the business requirements have been identified, we are struggling with a higher-than-usual BAU demand, to provide resource and focus to moving this project forwards.; 40: 0; 41: 29468.62; 42: 0; 43: 0; 44: 0; 45: 29468.62; 46: 30976; 48: -29468.62; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Replacing Uniform (Planning and Regulatory Services) | Replacement of Planning and Regulatory services information management and document management systems | C3088 | Development Board |  | Corporate Resources | Business Improvement |  |  |  | David Butler |  |  |  |  | Lan Nguyen |  | Rolling Programme | This project is about replacing the Uniform information management system and related EDMS (unsupported) for a modern cloud-based solution. Current contract runs out end of March 2026 and coincides with decomissioning of on-prem hosting of current solution. Project is currently at a pre-procurement stage (phase 2). The Invitation to Tender is being written with a specification identified by consultants from feedback from the Council's Uniform users. This is being reviewed with input from the project board (ICT, Procurement, Finance, Legal, Data Governance, Planning and Regulatory Services). The related contract has also been drafted by legal, which is also being reviewed by the Project Board. When the ITT and contract have been completed, the procurement process can commence (Target November 24) Project resources (time, budget, team) for the full migration in phase 3 are uncertain at present and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the level of resourcing required for the next stage. |  | 2026-04-01 | Target November 24: ITT and contract to be sent out | Procurement and supplier awarded - December-March 2025 | Phase 3 - Project migration stage - 1st April 2025-Onwards |  | 24: On target; 25: Budget to be agreed; 26: On target; 27: Medium; 28: Medium; 33: The ITT and contract are being written to best protect the council's interests and ensure that suppliers will be able to deliver the required solution for the project. Project resources (time, budget, team) for the full solution and migration in phase 3 are uncertain and likely to depend on the supplier of the solution (i.e. incumbent or new). Therefore, there are questions embedded within the ITT which will help to identify the full level of resourcing required for the next stage.; 34: The technical aspects of the Invitiation to Tender, scoring and demos are to be worked out for the project in addition to the requirements of the legal contract. Due to the complexity of the task (66 requirements and 61 ICT requirements) and that input is required from officers across the Council for the contract and ITT, there may be some delays in compiling and reviewing an agreed approach before going to procurement.; 40: 100000; 41: 100000; 42: 0; 43: 0; 44: 0; 45: 100000; 46: 0; 47: 0; 48: 0; 49: Forecast Overspend at end of project; 50: Full costs of the solution, including resourcing and costs of migration to be identified in the procurement phase of the project and will depend on which supplier is chosen. See forecast spend for annual contract costs anticipated - current annual costs of contract and hosting to be redirected when new contract is planned to start (March 26).; 51: N/A; 52: 221245; 53: 221245; 54: #INVALID OPERATION; 55: 221245; 56: 221245; 57: #INVALID OPERATION; 66: N/A; 80: No; 117: 0 | [12 empty] | 45579.2877 | lnguyen@oxford.gov.uk | Y | 45548.3337 | nbreeze@oxford.gov.uk
ICT - Asset Management System | Budget to procure and implement a new Asset Management System | C3089 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Ted Bowler |  | Design & Specification | A scoping document has been issued to a long list of suppliers, the returns will be reviewed and from this a short list of suppliers will be selected and invited to tender for the contract. |  | 45716 | Agree and draft the specification to be used for Tender process. Late July - August 2024. | Agree which providers will invited to Tender, and undertake the Tender exercise. September - November 2024. | Award contract to successful provider. January/February -2025 |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: The project timeline is very tight and only minor delays will impact on the overall project timeline. Fortnightly project board meetings and weekly meetings with our external consultant are in place to ensure that the chance of any delays are kept to a minimum.; 40: 318662; 41: 281338; 42: 300000; 43: 0; 44: 0; 45: 581338; 46: 12500; 47: 150000; 48: -131338; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Due to the project timeline we will only just be starting system implementation during the current financial year.; 51: 300000; 52: 130000; 54: 0; 55: 130000; 56: 0; 57: 130000; 65: HL; 66: No; 80: No; 92: ARG; 117: 0 | [12 empty] | 45579.3259 | tbowler@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
ICT - Extension of existing Alemba case managment system |  | C3090 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Closed | Alemba system has been set up for use by the People Team. |  | 45169 |  |  |  |  | 24: Closed; 25: On Budget; 26: Off Target; 27: Low; 28: Low; 30: People team are completing the process mapping, after which the Alemba system will be configured to accommodate the team and testing can begin.; 40: 0; 41: 4004; 42: 0; 43: 0; 44: 0; 45: 4004; 46: 0; 48: -4004; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Scanning Project | Project to digitize physical documents currently stored in Town Hall Basement, Town Hall Flat and Horspath Road. Physical documents need to be urgently removed / reduced from the basement of the Town Hall. A fire risk assessment has deemed these combustible, paper-based documents to pose a significant fire risk. The project will involve the removal, cataloguing, scanning, digital storage, ongoing physical storage and disposal of documents. | C3091 | Development Board | Development Review Group | Development | Planning |  | Capital Delivery |  | David Butler |  |  |  |  | Nathan Breeze |  | Feasibility | BUDGET NOTE: It is currently understood that any budget not spent in this financial year 24/25 (forecast at £90k) will be folded into the 25/26 Town Hall Lot 2 budget (B0157) to contribute towards the overall costs of the scanning project, which will come out of this budget (B0157). The overall costs of the scanning project will be estimated and taken to Cabinet for approval in January 2025. The majority of the spend is likely to take place in the 25/26 financial year. PROJECT UPDATE: Two main options for a scanning project are being considered: - Option 1 - A business case for digitising the Councils archive was prepared in June 2024. It recommended an internal auditing / cataloguing process of files stored to be carried out by each Service area to set the requirements and specification for a digitisation project by a third-party supplier. - Option 2 - Following the recommendations of the Fire Risk assessment, an alternative option has been explored which accelerates the removal of files from the Town Hall Basement. In this option a third-party supplier removes and catalogues the files stored. This catalogue could then be used to set the requirements and specification for a digitisation project by a third-party supplier. - An update report was provided to the Town Hall Project Board 03.10.24 with a detailed comparison of estimate programmes and costs (internal and external) between the two options. - Option 1 is the recommended approach to the Scanning Project. The next step will be to speak to Heads of Services with files in the Town Hall Basement and refine the estimated internal resource needed to undertake the project. Following this the aim is to submit an updated Business Case to OCB 26.11.24 for approval to take to cabinet in January 2025. Horspath Road File relocation Files stored at Horspath Road were relocated 15/10/24 to allow the building to be converted for alternative use. These are now stored in the Town Hall Flat, whilst the planning for the overall digitisation project is progressed. |  | 46082 | Relocate Files from Horspath Road to Town Hall - October 2024 | Updated Business Case for Scanning Project to OCB - November 2024 | Request for Cabinet Approval - January 2025 |  | 24: Not started; 25: Budget to be agreed; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 33: RISK 1 - Fire risk of ongoing storage of combustible (paper-based) material in the town hall basement MITIGATION 1 - Limited and controlled access to Town Hall Basement Area. Prioritise removal / relocation of material in escape routes. Progressing Scanning Project will lead to removal of significant number of files from the Town Hall Basement. RISK 2 - Potential breach of legal requirements for retention of and access to archive material. MITIGATION 2 - Clarification of Records Retention and Disposal Schedule as well as public access requirements. Identification of documents that need to be retained will be part of initial part of the project.; 34: A Fire Risk Assessment has recommended the removal/significant reduction of combustible (paper-based) material stored in the Town Hall Basement in the next 6 months. The Council does not currently have a catalogue of all files stored in Town Hall Basement, Flat and Horspath Road. This is to needed to define requirements and cost certainty for a digitisation project. The majority of this cataloguing process could either be undertaken internally (resource from each Service Area) or externally (third-party supplier) with advantages and disadvantages to each.; 40: 0; 41: 150000; 42: 0; 43: 0; 44: 0; 45: 150000; 46: 10092; 47: 60000; 48: -90000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delays to the start of the scanning project whilst most suitable route is defined, leading to forecasted spend being moved into next financial year; 51: 90000; 54: 90000; 55: 0; 56: 0; 57: 90000; 66: Unsure; 80: No; 81: This project doesn't involve any construction work.; 117: 0 | [12 empty] | 45583.1382 | nbreeze@oxford.gov.uk | Y | 45546.906 | rlabellarte@oxford.gov.uk
ICT - Replacement of IKEN - L&G case management system |  | C3092 | Development Board |  | Corporate Resources | Law & Governance |  | Capital Delivery |  | Emma Jackman |  |  |  |  | Amanda Ball |  | Delivery | Implementation programme has been delayed because access for testers to MS365 is not yet available. Iken have suspended implementation pending confirmation from OCC of a workable solution. |  |  | Agreement of contract with Hable - 31 Jan 2024 | Completion of configuration of Sharepoint by Hable - 31 March 2024 | Completion of mobilisation of new Iken cloud-based case management system - 30 June 2024 |  | 24: Off Target; 25: Over budget; 26: Awaiting new Schedule; 27: N/A; 28: High; 33: Delay causing risk of delay to Council's transition to cloud-based Outlook application; 34: Resolution of internal ICT readiness issues to allow implementation programme to continue; 40: 0; 41: 67500; 42: 0; 43: 0; 44: 0; 45: 67500; 46: 35125; 48: -67500; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Replacement of ArcGIS geospatial mapping system |  | C3093 | Development Board |  | Development | Planning |  | Capital Delivery |  | David Butler |  |  |  |  | David Butler |  | Closed | Completed | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 30: Completed; 40: 0; 41: 25000; 42: 0; 43: 0; 44: 0; 45: 25000; 46: 0; 48: -25000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Information @ Work major upgrade |  | C3094 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Other Capital Spend | PO Signed in September. Go live in October. | [6 empty] | 24: Not started; 40: 3000; 41: 18000; 42: 0; 43: 0; 44: 0; 45: 18000; 46: 0; 48: -18000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Redesign of Council Website |  | C3095 | Development Board |  | Corporate Strategy | Corporate Strategy |  | Capital Delivery |  | Mish Tullar |  |  |  |  | Rocco Labellarte |  | Closed | Completed in May 2023 | [6 empty] | 24: Completed; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 30: Completed in May 2023; 40: 0; 41: 51658; 42: 0; 43: 0; 44: 0; 45: 51658; 46: 627; 48: -51658; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Open Revenue Cloud Migration |  | C3096 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Nigel Kennedy |  |  |  |  | Rocco Labellarte | [9 empty] | 40: 50000; 41: 50000; 42: 0; 43: 0; 44: 0; 45: 50000; 46: 0; 48: -50000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.906 | rlabellarte@oxford.gov.uk
ICT - Refresh of content and taxonomy of the Council Website | Duplicated in C3082 | C3097 | Development Board |  | Corporate Strategy | Corporate Strategy |  | Capital Delivery |  | Mish Tullar |  |  |  |  | Tom Jennings |  | Delivery | A project plan for 'phase two' is in place, which will see us systematically improve each area of the council's website. A pilot project has been carried out with the council tax team, which is due to complete in the next couple of weeks. We will then move on to improve the recycling and jobs sections of the website. Meanwhile, a website working group has been established to bring together content, digital, customer and citizen teams to work on the website improvements. Terms of reference have been drawn up and will be brought to OCB in October for approval. |  |  | Draft project plan for phase two of website |  |  |  | 24: On target; 26: On target; 30: Meeting with ODG on 8th June. Next steps are for service areas to provide timeline for making the updates.; 33: Risk that the website improvements end when the current additional resource is removed in November 2024, without having completed the process of optimising all high usage areas of the website for customer self-service. Mitigation: permanent increase in resourcing of web content management. October update: ICT is extending the resource until March 2025. A budget bid has been submitted to create a permanent resource from 2025/26.; 40: 25000; 41: 46150; 42: 0; 43: 0; 44: 0; 45: 46150; 46: 1500; 48: -46150; 54: 0; 55: 0; 56: 0; 57: 0; 70: Yes; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
ICT - Agresso upgrade and migration to Cloud |  | C3098 | Development Board |  | Corporate Resources | Financial Services |  | Capital Delivery |  | Nigel Kennedy |  |  |  |  | Rocco Labellarte |  | Closed | Project has gone live |  | 2024-02-29 | Post implementation intensive care | Year End Close on new system - 31st May 2024 |  |  | 24: On target; 25: On budget; 26: Completed; 40: 0; 41: 193219.6; 42: 0; 43: 0; 44: 0; 45: 193219.6; 46: 0; 48: -193219.6; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.906 | rlabellarte@oxford.gov.uk
Third-party consultancy for Azure Active Directory & M365 migration from SCC, security setup & configuration | Third-party consultancy for Azure Active Directory & M365 migration from SCC, security setup & configuration | C3099 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Delivery | Awaiting contract signature of main SCC contract. |  | 46081 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: N/A; 40: 135000; 41: 135000; 42: 0; 43: 0; 44: 0; 45: 135000; 46: 0; 48: -135000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
iTrent system improvement | iTrent system improvement | C3100 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Gail Malkin |  | Delivery | Work has started to implement data retention module, reporting module is being evaluated and recruitment process improvements taking place. |  | 2025-03-31 | data retention module implemented | new recruitment functionality launched |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 33: Team capacity to deliver improvements - setting clear priorities and need to limit new work; 34: Consultation with the business before implementing change and training for managers; 40: 30000; 41: 30000; 42: 0; 43: 0; 44: 0; 45: 30000; 46: 0; 47: 30000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 70: Yes; 80: Yes; 82: ODS use iTrent so will benefit from improvements; 84: n/a; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
I@W renewal or replacement | I@W renewal or replacement | C3101 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Feasibility | Requirements gathering underway as of 1st September |  | 45716 |  |  |  |  | 40: 300000; 41: 300000; 42: 0; 43: 0; 44: 0; 45: 300000; 46: 0; 48: -300000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.906 | rlabellarte@oxford.gov.uk
Cyber security monitoring and response service | Cyber security monitoring and response service | C3102 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Completed | Monitoring and response services in place |  | 2024-06-28 |  |  |  |  | 24: Completed; 25: On budget; 26: On target; 27: N/A; 40: 115000; 41: 115000; 42: 0; 43: 0; 44: 0; 45: 115000; 46: 0; 48: -115000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.059 | jmalton@oxford.gov.uk
Upgrade / replace Kirona DRS (ODS system) | Upgrade / replace Kirona DRS (ODS system) | C3103 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Ruth Wigham | [9 empty] | 40: 75000; 41: 75000; 42: 0; 43: 0; 44: 0; 45: 75000; 46: 0; 48: -75000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.906 | rlabellarte@oxford.gov.uk
Windows security server upgrades | Windows security server upgrades | C3104 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Rolling Programme | Project due to complete on time. |  | 2024-10-31 |  |  |  |  | 40: 75000; 41: 75000; 42: 0; 43: 0; 44: 0; 45: 75000; 46: 0; 48: -75000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Migration of Mod.gov | Migration of Mod.gov | C3105 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Jonathan Malton |  | Pipeline (Approved awaiting budget) | No change since last update |  | 45747 |  |  |  |  | 40: 90000; 41: 90000; 42: 0; 43: 0; 44: 0; 45: 90000; 46: 0; 48: -90000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.4548 | jmalton@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
Migration of SCC to cloud hosted alternatives | Migration of SCC to cloud hosted alternatives | C3106 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Design & Specification | Contract negotiations underway. |  | 46081 | Contract Signature delayed to September 2024 |  |  |  | 40: 107000; 41: 107000; 42: 0; 43: 0; 44: 0; 45: 107000; 46: 0; 48: -107000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Replacement of Uniform IDOX (additional funding) | Replacement of Uniform IDOX (additional funding) | C3107 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | David Butler | [9 empty] | 40: 25000; 41: 25000; 42: 0; 43: 0; 44: 0; 45: 25000; 46: 0; 48: -25000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Online forms development | Online forms development | C3108 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  | Rolling Programme | [7 empty] | 40: 160000; 41: 160000; 42: 160000; 43: 0; 44: 0; 45: 320000; 46: 0; 48: -160000; 54: -160000; 55: 0; 56: 0; 57: -160000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
ICT - feasibility | Not a project. Funds for various feasibility studies. NO TARGET COMPLETION THEREFORE. | C6000 | Development Board |  | Corporate Resources | Business Improvement |  | Capital Delivery |  | Helen Bishop |  |  |  |  | Rocco Labellarte |  |  | 0 | [6 empty] | 24: Closed; 40: 0; 41: 180000; 42: 0; 43: 0; 44: 0; 45: 180000; 46: 0; 48: -180000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Essential Repair Grants | Essential Repair Grants - E3511 | E3511 | Development Board |  | Communities | Regulatory & Community Safety |  | Miscellaneous Capital Spend |  | David Butler |  |  |  |  | Becky Walker |  | Other Capital Spend | Increased ERG budget has been approved in Council Budget to help waiting list of clients. | [6 empty] | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Increased ERG budget has been approved in Council Budget to help waiting list of clients.; 33: Not enough contractors for work type; 34: Invoices from ODS; 37: There would be as most interventions are helping to rectify severe safety issues with the structure of peoples homes.; 40: 15000; 41: 37107.97; 42: 15000; 43: 15000; 44: 15000; 45: 82107.97; 46: 5000; 47: 30000; 48: 0; 49: Forecast Underspend at end of project; 51: 15000; 52: 15000; 53: 15000; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: HIA Team are designers; 78: Various; 79: Each work has its own plan; 80: Yes; 82: Various Repair type works; 84: 0.8; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Disabled Facilities Grants | Disabled Facilities Grants | E3521 | Development Board |  | Communities | Regulatory & Community Safety |  | Miscellaneous Capital Spend |  | David Butler |  |  |  |  | Becky Walker |  | Other Capital Spend | BAU in HIA with referrals being progressed. | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: BAU in HIA with referrals being progressed.; 33: County Council Occupational Therapists are funded so there is no backlog and the service is actively promoting the availability of funding. Liaising with hospitals to enable discharge.; 34: We are starting to pay ODS as well to show spend. Still awaiting all correct invoices for compliance; 37: Most of our works are adaptations, but some of these do significantly improve the EE of a property, and we do undertake safety repairs as well which do the same.; 40: 1200000; 41: 1553748.55; 42: 1200000; 43: 1200000; 44: 1200000; 45: 5153748.55; 46: 941334.45; 47: 1553748.55; 48: 0; 51: Unknown until budget is known; 52: Unknown until budget is known; 53: Unknown until budget is known; 54: #INVALID OPERATION; 55: #INVALID OPERATION; 56: #INVALID OPERATION; 57: #INVALID OPERATION; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: HIA Team are designers; 78: Various; 79: Each project has its own individual plan; 80: Yes; 82: QL needs to work correctly and supply invoices that match quotes; 84: various; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45539.0611 | rhaverson@oxford.gov.uk
OFAS -additional contribution | The Council is a partner in the flood alleviation scheme. Internal project team costs are currently being reimbursed by the EA. The capital budget is for potential further contribution to the OFAS scheme rather than project team costs. | E3557 | Development Board | Asset Review Group | Development | Corporate Property |  | Miscellaneous Capital Spend |  | Jane Winfield |  |  |  |  | Emma Gubbins |  | Other Capital Spend | Have now entered into the Option Agreement. legal are providing advice and draft notices on the land which requires advertising prior to disposal (open space) Terms agreed for the disposal of the fields adjacent to Redbridge Hollow - Fisher German have confirmed values look reasonable. EA have provided HOTs but they confirm Council will need to provide VP - this doesn't reflect the agreement so have asked EA to confirm. |  |  | Agreement of Option Agreement September 2023. Planning permission late 2023. CPO to be confirmed December 2024. - complete | Advertising of land - May 2024 | Agreement of terms for additional BNG land transfer - May 2024 |  | 24: On target; 26: On target; 27: High; 28: Medium; 30: Project documentation is nearing completion. The EA has submitted its planning application in February 2022. County planners have made a Regulation 25 request for additional information. Planning permission is anticipated late 2023 and the CPO has been made March 2023 with confirmation 18 months later. This will require support from the following OCC departments: Planning Property Legal Work is progressing on the Draft Option Agreement for the land to be transferred at nil cost. Completion is anticipated end of September 2023. The 'notional' valuation of this land has been agreed with the EA along with Field 1 which is being sold to the EA at market value. This will require support from the following OCC departments: Property Legal; 33: Risk 1. Project Risks- Gaining Planning permission and CPO Inquiry Mitigation for these is being managed by the EA (OCC support on Project Board and Sponsoring Group) Risk 2. OCC Risk- overlap of OFAS with OCC plans for Seacourt and Redbridge P&R's Mitigation - Open dialogue & sharing of information and timetables for OFAS and OCC plans for Seacourt & Redbridge P&R. Risk 3. Originally, OCC agreed a contribution of kind of up to £1m, including internal staff resource as a key stakeholder/contribution to the project 4-5 years ago. The length of time the project has taken and changes in staff, alongside post covid impacts on Legal and Property resource meant there was insufficient internal staff resources to do this work. This has been resolved with a dedicated external Property Services contractor, Richard Waple, as Lead Officer and an external Legal Services contractor, Ian Goldsmith. Professional Fees have started to be reimbursed by the EA. To date, all of OCC's Professional Fees have been reimbursed to the end of November 2022. OCC remains a committed partner to the scheme.; 34: It is understood that the A243 Kennington Bridge improvement works are fully funded as is the OFAS project. Planning Permission and confirmation of CPO are still required for OFAS to proceed. Highways England has not objected to the 2022 planning application. Agreement still required for Option Agreement.; 35: 0; 40: 0; 41: 0; 42: 250000; 43: 0; 44: 0; 45: 250000; 46: 2.44; 48: 0; 54: -250000; 55: 0; 56: 0; 57: -250000; 65: No; 66: No; 80: No; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
O-GULO | Trialling and Delivering Onstreet charging solutions, at the right locations and for an affordable price, to enable Oxford Residents without access to offstreet parking to transition to Ultra Low Emission Vehicles and improve Air Quality and reduce Carbon Emissions in Oxford. | E3558 | Development Board | Development Review Group | Corporate Strategy | Environmental Sustainability |  | Capital Delivery |  | Mish Tullar |  |  |  |  | Vikki Robins |  | Design & Specification | >September 2024 - Agreement still not issued by County. Escalated to 151 Officer and Head of Corp Servs. This needs to be in place before the LEVI tender is published - planned end October 24 August 2024 - draft of agreement due from County but no date given for this yet. LEVI work taking priority for all Oxon Councils as tender due for this by September 2024. June 2024 - meetings taking place in June with County for the reimbursement method of the allocated funding as well as the transfer of the GULO assets to County control. May 2024 - no new progress, project remains paused. - City are seeking reimbursement of investment through revenue share, which has been agreed in principle >Project Paused- County is seeking full integration of GULO P2 into LEVI, with all new onstreet contracts entered into by County highways. Permission to enter into a back-to-back agreement now received from Funder (OZEV) .City are seeking reimbursement of investment through revenue share, which has been agreed in principle. Ongoing delays on LEVI timeline, GULO timelines likely to shift significantly backwards, to early 2025. |  | 2024-03-31 | Agreement on City to County transition - updated deadline Jul 2024 | LEVI tender (GULO integrated) November 2023 | Payment schedule and transition work concluded - September 2024 |  | 24: On Hold; 25: On Budget with slippage; 26: Awaiting new Schedule; 27: Medium; 28: Medium; 30: Phase 2 - now unpaused. > Procurement now being aligned with cross-district LEVI procurement, to benefit from the value benefit of the much larger procurement value which should enable us to achieve lower pricing and more equitable deployment due to the enhanced portfolio effect (procuring for both higher and lower risk sites to spread commercial risk). Full impact on deployment timeline to be confirmed once known, current procurement target date is August/September 2023. Preparing comms. Procurement prep is very advanced, so can turn around quickly once agreements are reached.; 33: OGP2ZR005 - Agreement with County not signed by end October for the GULO funds transfer. Mitigation - Escalate and if still no progress consider using the funds outside LEVI for alternative A/C charging in car parks. OGP2ZR004 - Substantial delay to GULO Infrastructure delivery in Oxford. County officers have stated intention to withdraw permission for city to take GULO forward on the highway, and demand full integration of GULO into LEVI under County contract ownership. Onstreet delivery timelines for LEVI are currently set to early 2025. Mitigation: Officers are seeking urgent confirmation on proposed GULO timelines, with the aim of securing a 2024 delivery.; 34: OGP2ZI002 - County highways now wish to contract new highways deployment directly under LEVI, and had challenged OxEVIS legitimacy. Sponsor and programme manager have escalated the issue up to executive level and unblocked successfully, with County now fully supporting OxEVIS, and work is in progress to agree on a transition work package for Oxford highways estate that retains Oxford's strategic leadership for EVI under OxEVIS and retains the existing quality of contract management. Issue will remain open until agreements have been reached.; 37: Not quantifiable until total number of delivered chargers is established.; 40: 0; 41: 494706.03; 42: 0; 43: 0; 44: 0; 45: 494706.03; 46: 0; 48: -494706.03; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: N/A; 74: Yes; 77: P2 not yet procured; 78: P2 not yet procured; 80: Yes; 82: ODS are a supplier on the DPS and are expected to bid for the contract. - Delivery of car park chargers in partnership with CPOs. - Adoption of legacy onstreet bollard chargers to test "connected energy assets" business case. - some of this has already taken place with ODS managing and operating 13 on-street charges from 1-10-24. - Opportunity for GUL-e installations - Opportunity to provide services to CPOs on maintenance.; 84: now unknown: ODS role in context of County GULO takeover tbc.; 92: DRG; 117: 0 | [12 empty] | 45576.4388 | vrobins@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
T-GULO | Delivering minium of 16 rapid charge points for taxis. | E3560 | Development Board | Development Review Group | Corporate Strategy | Environmental Sustainability |  | Capital Delivery |  | Mish Tullar |  |  |  |  | Vikki Robins |  | Delivery | update 1-10-24. Legal have now assigned someone to look at the leases. Supplier engagement for sign off will commence once we have the completed leases. Project delivery complete but close out still in progress.. Some minor transition items outstanding (as build-drawings, full lease signatures). |  | 2024-11-29 | Transition & handover sign-off | Lessons learned - April 2024 | Full Close-out - November 2024 |  | 24: Off Target; 25: On budget with slippage; 26: Off Target; 27: Low; 28: Low; 30: All works but bay lining defects complete, launch date 22nd of Jan. Full commissioning of two Old Greyfriars chargers today, awaiting confirmation.; 33: September 24 - Lease signing due before the end of October. Once completed, this project can be closed down as all deliverables will be completed. Leases for some sites off street sites to be finalised and signed by both parties. Nilesh and Sue progressing with legal during September Final invoice paid to Blink Charging (formerly EB Charging). As built drawings sent over for all sites. O&M documentation sent over- to be reviewed.; 34: Project ready for transition into close-out, pending lease completion; 37: As per previously submitted entries.; 40: 0; 41: 38326.56; 42: 0; 43: 0; 44: 0; 45: 38326.56; 46: 19015; 47: 0; 48: -38326.56; 49: N/A - On Budget; 50: N/A; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: EB Charging Ltd - Liam McDonnel; 78: EB Charging Ltd - Morgan Hands; 80: No; 82: Provision of bay linings/signage; 84: £1.5k; 92: DRG; 117: 0 | [12 empty] | 45576.4388 | vrobins@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Decarbonisation Fund (OCC Element) | OCC has been awarded £10.9m under the Public Sector Decarbonisation Scheme (PSDS). Includes £1,636,736.00 for heat pumps and solar at Hinksey Pool and £9,286,813 for solar farm investment and heat pumps at five of OCC’s operational buildings | E3565 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Luca Minetola |  | Completed | 1. Hinksey's completion date 27 with Practical Completion. issued 10 February 2023 by F&G due to outsanding documents. 2. Two trees completed still monitoring the health of the trees. 3. Salix Audit oustanding. To start after final account. 4. Pool Cover works outstanding completed on the 18 of January 2023. 5. Indipendant inspection for the pool cover complete. 6. Barton L Centre PHX to be send for testing by specilialst on the meturlugy of the heat exchanger. |  | 44957 | 1. Commmissioning complete 2. Pool Cover Cover works completion and indipendant inspection of safety issues. May include security. Complete 3. Report from Inspector complete and submitted to OCC from reveiw. |  |  |  | 24: On target; 25: On Budget; 26: At Risk; 27: High; 28: High; 30: "1. Hinksey's completion date 27 with Practical Completion. issued 10 February 2023 by F&G due to outsanding documents. 2. Two trees completed still monitoring the health of the trees. 3. Salix Audit oustanding. To start after final account. 4. Pool Cover works outstanding completed on the 18 of January 2023. 5. Indipendant inspection for the pool cover complete. 6. Barton L Centre PHX to be send for testing by specilialst on the meturlugy of the heat exchanger."; 33: Claim from WD on Barton Leisure Centre PHX damage due to what they allege as high levels of chlorine. Mitigation - OCC has sent the PHX; 34: 1. Hinksey Pool Cover (PC) has significant gaps, Fusion feels this may cause entrapment safety issues. A meeting was held on 11 December 2022. It was decided WD and Forge (subcontractor) should complete the Pool Cover works on the 18 January. 3.Thereafter the completion of outstanding works, an independant assessement will be undertaken at OCC's cost to review risks and recommendation identified by the Report. 4. Barton Leisure Centre PHX installed however WD want to recoup costs alleging that this was a problem cused by client that is the that corrosion that was caused by the end user's water salt and chlorine adminstration in the pool. 5. Financial Audit by Salix. 6. Agreeing final accout with WD.; 37: The projects will deliver two key benefits for the City Council: a) energy bill savings of up to £440/year (rough estimate with more detail to be provided at the next stage and b) carbon emissions reduction of c.1,570tCO2 each year which is equivalent to 3 years of carbon reduction required by the CMP.; 40: 0; 41: 105142.35; 42: 0; 43: 0; 44: 0; 45: 105142.35; 46: 0; 48: -105142.35; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 77: F&G appointed as Principal Designer (PD) and Clerk of Works for SSEN works; 78: Willmott Dixon appointed as Principal Contractor; 80: Yes; 82: Minor Repairs and Tree works monitoring; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45558.2855 | ldavis@oxford.gov.uk
LED Lighting Upgrade Survey | Measured Bldg Survey of 5 Leisure Centres incl. Lighting | E3568 | Development Board | Asset Review Group | Corporate Strategy | Environmental Sustainability |  | Capital Delivery |  | Mish Tullar |  |  |  |  | David Oldham |  | Completed | The survey drawing work completed. We are waiting on access to the Technician at Serco to populate the type and lux of light fittings surveyed. |  | 45473 | All visits completed except with Technician at Serco | short visit completed with Serco Technical person | Compiling of the lighting data sheets has been completed |  | 24: Completed; 25: Under Budget; 26: Completed; 27: High; 28: Low; 30: October; 33: The lighting data sheets have been sufficiently completed to fufill the requirements but not as full as initially hoped. The site support was not sufficient to do this due to ongoing commitments. It was not possible to extend the project further; 34: Project complete and all reports and files recieved; 40: 0; 41: 6430; 42: 0; 43: 0; 44: 0; 45: 6430; 46: 3840; 47: 3840; 48: -2590; 49: Forecast Underspend at end of project; 50: Managed a better deal - £2590 less than budgeted; 51: 3840; 52: 0; 53: 0; 54: 3840; 55: 0; 56: 0; 57: 3840; 65: HL; 66: No; 69: No; 70: Yes; 71: No; 72: Gathering data on this project. No CDM reporting required on survey work that is not intrusive. Changed from 'Yes' CDM Applicable to 'No'.; 73: No; 74: No - answer next two questions; 77: N/A; 78: N/A; 80: No; 82: No ODS work as part of this survey; 92: ARG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
General Fund Capital Reserve (SCS works & Energy) | General Fund Capital Reserve (SCS works & Energy) | E3569 | Development Board | Asset Review Group | Development | Corporate Property |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | To be used for SCS for GF in 25/26 - slip full amount into 25/26 & 26/27 |  | 45747 |  |  |  |  | 27: Low; 28: Low; 40: 1000000; 41: 1000000; 42: 0; 43: 0; 44: 0; 45: 1000000; 46: 0; 47: 0; 48: -1000000; 49: Slippage (Less spend in 24/25 now forecast in future years); 51: 1000000; 54: 1000000; 55: 0; 56: 0; 57: 1000000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
BNG Feasibility | Feasibility of biodiversity offsetting on OCC land | E3570 | Development Board | Development Review Group | Development | Environmental Sustainability |  | Capital Delivery |  | Jane Winfield |  |  |  |  | Laura Davis | Project - Development | Feasibility | TVERC ecological surveys completed. Legal review of Conservation Covenant v s.106. |  |  | Completion of habitat assessments, enhancement modelling & report. Final reports due from ecological consultant 15/11/24. | Completion of legal review. Jan 2025. |  |  | 24: On target; 25: On budget with slippage; 26: On target; 27: Low; 28: Low; 33: 1) If the project were to show that none of the candidate sites are cost effective/viable for BNG use. Mitigated by careful selection of sites using economical, maintenance, property and planning background knowledge. 2) If the project is unable to gather reliable information on Council pipeline BNG costs it may not be possible to make a financial case for the use of council-owned land for BNG offsetting. Mitigate by working with the development teams to gather useable information. 3) If the ecological survey season is missed in 2024, then that element of works would be delayed to summer 2025. This risk has been mitigated by the successful appointment of an ecological consultant and the survey works are now completed (as of August 2024).; 34: 1) Understanding pipeline BNG costs for the council development teams. 2) Establishing contact with legal teams in county and districts to discuss possibility of mutual BNG S.106 arrangements.; 40: 0; 41: 100000; 42: 0; 43: 0; 44: 0; 45: 100000; 46: 12744; 47: 53000; 48: -47000; 49: Slippage (Less spend in 24/25 now forecast in future years); 51: 47000; 52: 0; 53: 0; 54: 47000; 55: 0; 56: 0; 57: 47000; 66: No; 69: No; 73: No; 80: Unsure; 82: Still being assessed as part of the feasibility work. In conversation regarding current maintenance regimes on the candidate sites.; 84: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
OxWED Loans |  | M5023 | Development Board |  | Corporate Resources | Financial Services |  | Miscellaneous Capital Spend |  | Nigel Kennedy |  |  |  |  | n/a |  | Other Capital Spend | £325k loan payment approved in 2023/24 due to extended programme. Potential further release will be in future years subject to final business case. | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Approved £325k loan payment due to extended programme made. Further £275k release subject to final business case; 40: 3750000; 41: 1025000; 42: 0; 43: 0; 44: 0; 45: 1025000; 46: 0; 48: -1025000; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
National Homeless Property Fund and RSAP Bid | Rough Sleeping Accommodation Programme bid and the further £2m investment in the National Homelessness Property Fund by the Council. Includes £2m budget provision for RSAP match funding of £2m. | M5024 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Nerys Parry |  |  |  |  | TBC - Paul Wilding |  | Other Capital Spend | Further NHPF payment of £1,780k due in March 23, followed by a final payment of £976k in June 2023 | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: Further NHPF payment of £1,780k due in March 23, followed by a final payment of £976k in June 2023; 33: WRONG PM RECORDED - SHOULD BE RICHARD WOOD OR PAUL WILDING; 40: 0; 41: 633961.96; 42: 0; 43: 0; 44: 0; 45: 633961.96; 46: 157663.93; 48: -633961.96; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Barton Park - Purchase by Council (Phase 1 Affordable Housing at Barton Park) | Loan to OX PLACE for transfer of Barton Park properties to initially purchased by the Council under Phase 1 contract. Loan offset by capital receipt. | M5025 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | David Watt |  | Other Capital Spend | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. |  | 2024-03-31 |  |  |  |  | 24: Off Target; 25: Under Budget; 26: Off Target; 27: Medium; 28: Medium; 30: The OX Place Development Team reviewed their scheme appraisals at the beginning of the 2023/24 financial year. This suggested that the revised loan drawdown total for the financial year will be now be £12.513m (Q1 £3.440m, Q2 £1.226m, Q3 £4.440m, Q4 £3.407m); 33: There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years.; 34: None; 37: The homes are constructed to achieve the legacy Code for Sustainable Homes Standard, Level 4, which increases the energy efficiency levels above building regulations.; 40: 11051609.13; 41: 17769988.93; 42: 17848472.83; 43: 5789066.94; 44: 4962150.08; 45: 46369678.77; 46: 6646509.79; 47: 5844583; 48: -11925405.93; 49: Remainder of in year budget removed from programme; 50: Remainder of in year budget removed from programme; 51: 0; 52: 0; 53: 0; 54: -17848472.83; 55: -5789066.94; 56: -4962150.08; 57: -28599689.85; 66: No; 69: No; 70: Yes; 71: No; 73: No; 74: Yes; 80: No; 117: 0 | [12 empty] | 45580.1001 | dwatt@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Housing Company Loans (Development Company excl. Barton Park) | Loans to the Housing Company. | M5026 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | David Watt |  | Other Capital Spend | The programme has been updated in Sep24 following a review of the OX Place BP. |  | 2024-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: Off Target; 27: High; 28: High; 30: Due to the level of capital receipts received in 2023/24 (assisted by HRA stage payments for Lucy Faithful House and historical project management fees finally being agreed with the Council for 100% HRA developments) by OCH(D)L, together with prevailing cash balances in the company and the delayed activity of development activity in the programme, this has all meant that the drawdown loan activity has significantly been curtailed in 2023/24.; 33: The activity of loan drawdowns is completely development led and we have experienced delays and removed the optimum bias from the programme.; 40: 14051609.13; 41: 23916000.13; 42: 36634000; 43: 20762000; 44: 29739609; 45: 111051609.13; 46: 5599810.04; 47: 5046250; 48: -18869750.13; 49: Loan request now revised throughout the remaining programme; 50: Revised loan activity now adjusted due to updated HRA stage payments, better cash management and programme planning.; 51: 772040; 52: 4480140; 53: 85739590; 54: -35861960; 55: -16281860; 56: 55999981; 57: 3856161; 66: No; 69: Yes; 70: Yes; 71: Yes; 72: OX Place Business Plan; 80: Yes; 117: 0 | [12 empty] | 45580.1001 | dwatt@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
Loan to Housing Company re Barton Park (Loan to OCH(I)L) | Loan to OX PLACE for transfer of Barton Park properties to initially purchased by the Council under Phase 1 contract. Loan offset by capital receipt. | M5032 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Nigel Kennedy |  |  |  |  | David Watt |  | Other Capital Spend | There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years. |  | 2024-03-31 | Acquisition of social housing from next phase of development. |  |  |  | 24: Off Target; 25: Under Budget; 26: Off Target; 27: Medium; 28: Medium; 30: The OX Place Development Team reviewed their scheme appraisals at the beginning of the 2023/24 financial year. This suggested that the revised loan drawdown total for the financial year will be now be £12.513m (Q1 £3.440m, Q2 £1.226m, Q3 £4.440m, Q4 £3.407m); 33: There is a paper going to the company's Shareholder in November 2024 confirming the decision to transfer all the prevailing and future Barton Park dwellings to the Council's HRA. Thus, there will be no new loans provided to OCHL for this purpose for the remaining months of 2024/25 and future years.; 37: The homes are constructed to achieve the legacy Code for Sustainable Homes Standard, Level 4, which increases the energy efficiency levels above building regulations.; 40: 0; 41: 9214379.8; 42: 0; 43: 5789066.94; 44: 4962150.08; 45: 19965596.81; 46: 0; 47: 5844583; 48: -3369796.8; 49: Remainder of in year budget removed from programme; 50: Remainder of in year budget removed from programme; 51: 0; 52: 0; 53: 0; 54: 0; 55: -5789066.94; 56: -4962150.08; 57: -10751217.02; 66: No; 80: No; 117: 0 | [12 empty] | 45580.1001 | dwatt@oxford.gov.uk | Y | 45519.3625 | dscholes@oxford.gov.uk
Blackbird Leys Regeneration (GF element) | Regeneration of Blackbird Leys including the Retail Centre, Community Centre and Knights Road to provide approximately 294 new homes, retail units and community centre. The regeneration is in partnership with Catalyst Housing. | M5033 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Karoline Soisalo De Mendonca |  | Design & Specification | COMMUNITY CENTRE: Design/Planning: - Design freeze achieved, with minor coordination between disciplines still ongoing, design team working on planning submission - Energy consultants asking for 5 weeks to produce assessments and reports, which may delay submission date - OCC discussing fee and programme for Stage 4 drawings to be produced by Jessop & Cook for tender (both fitout and S&C) - OCC/PBT discussing procurement strategy for community centre. PBT preferred route is 1-stage D&B, with one single contractor delivering both shell & core and fitout. - OCC agrees that having one contractor delivering both scopes will simplify and expedite delivery, but is concerned with loss of control over design due to D&B contract. OCC to increase design control by requesting detailed Stage 4 drawings for tender and detailed ERs. Programme: - Programme has been affected by design development delays on externals. Planning submission date has now slipped to mid September 2024. - Design freeze anticipated for 16/08/24 - Final Exhibition: w/c 09/09/24 - Submission: 20/09/24 Budget: - design team has been working on VE exercises on shell & core, guided by PBT's QS. - S&C still over budget but PBT agreed they now have a viable/buildable design (JG at Procurement meeting) -D&S reviewing/revising cost plan for fitout to reflect latest design PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. |  | 2028-05-23 | Community Centre Design Freeze: 16/08/24 | Final Exhibition: w/c 09/09/24 | Outline Application submission: 20/09/24 |  | 24: At Risk; 25: On budget with slippage; 26: At Risk; 27: High; 28: High; 30: "PLANNING: - Planning application is undergoing determination. - Amendment including some changes to the design, ie – second stair core addition, submitted. Consultation for amendment ends on 19/06. - Highways had submitted an objections that has since been retracted following a meeting with LPA/Savills/Applicants - We are still aiming to go to July planning committee. - Parish Council have appointed a team of consultants including a regeneration consultant, who have helped Parish understand the application documents and write their comments. Parish have issue and concerns but their position was not an objection (when comments submitted to LPA 03/05/23 - Parish on 31/05 was contentious and both councillors and members of the public were voal against aspects of the project. The focus was on the community centre size, location and lack of engagement. - Parish had a meeting with the LPA w/c 05/06 to voice their concerns. OCC/PBY are meeting with Parish on 19/06 to further discuss. HIF: - We are still waiting to hear back from HE regarding the HIF extension. - We received another set of queries fro HE, which have now been answered. There are a couple of financial questions (of changes to costs/funding) that we are finding difficult to bottom out. KSM invited HE/PBY to a meeting to clarify/discuss outstanding items. - HE confirmed that funds cannot be drawn down prior to HIF Agreement DoV being signed. LEGAL: - Intent to appropriate report was approved at cabinet 14/06/23. KSM now working on the notice to be published in the Oxford Mail. - Ad to run for 14 days and comments allowed for 28 days. - Appropriation to go back to Cabinet once comments received (August Cabinet?) - DoV meetings are ongoing. Freeths/Devonshires met on 13/06/23 to discuss main items. Freeths/Devs to negotiate wording. Devs to send OCC the commercial terms for discussion. - DoV terms to go to Cabinet in Aug. COMMUNITY CENTRE: - PBY/OCC agreed to delivery model of PBY taking on DM role, OCC taking on financial risk. - PBY to appoint lead consultant/design team directly. JTP to design shell and core, with J&C to design interior fitout. - OCC to direct appoint J&C to work alongside Transition by Design, JTP and Hill on early engagement and design. This can come out of CC interior fees, where there is allowance for community engagement, Stages 0-1 works. - Parish, community unhappy with the cc being in outline application. Not enough explanation on why this was going in as hybrid? Community believe the cc won’t be given enough attention/ won’t be delivered. - This will hopefully be clarified at Parish/OCC/PBY meeting on 19/06. -Engagement work with TbD to start asap. OCC/PBY to meet TbD on 19/06. VIABILITY: - PCSA2 ongoing. Hill to finalise PCSA work end of July, Calford Seaden to write report in 2 weeks following. OCC to get Ridge to write a report on findings, ME to write up best case? COMMS: - Newsletter to go out after Parish meeting, but before Parish Council."; 33: - Community Centre delivery: This is still a major risk to the project, as it has the potential to delay the occupation of Block A. This planning condition is being questioned by PBT, and is relatively vague in wording. KSM to confirm. -The programme has slipped due to delays in design development, and planning submission has now been pushed to 20 Sept 2024. This means there will be slippage on completion date for the centre. - Community Centre Budget: After VE exercises, S&C still over budget, but PBT agrees there is no more scope for VE and are happy to proceed to tender. Revised cost report for fitout to be issued. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2. - OCC/PBT discussing Ph 2 options - Peabody confident they can get a viable Ph 2 scheme, which will de-risk the delivery of housing and therefore risk of claw back for HIF by Homes England. - Comms & Engagement: Still a risk to relations as this project gets more politically sensitive. Comms around Community Centre especially sensitive as the planning submission date has been moved back several times as the project faces delays at design development stage. Parish Council/Community have expressed concerns about delays and worries about housing being delivered without the community centre have returned. OCC to continue to attend Parish Council meetings and communicate with concerned parties to assuage concerns. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024.; 34: - Community Centre Design & Planning Submission: design finalised, design team now working with consultants on planning pack and reports, for September submission. - Community Centre Budgets: S&C still over budget after VE exercises, PBT/OCC to move forward to planning submission/ tender. Latest fitout cost report to be issued. - Community Centre Budget: the project currently does not have a budget or funding for furniture or ICT. OCC Communities to provide brief, KSM to look into FF&E schedule. - Comms & Engagement on outline application ongoing. Newsletter will be issued in August.; 37: Proposals as planning policy based on current 2022 building regs with additional fabric uplift. Note proposals to reduce standards considered by CHL as part of viability review but no longer proposed.; 40: 5586876; 41: 8356000.05; 42: 4866000; 43: 5452000; 44: 4121439; 45: 22795439.05; 46: 6256454.72; 47: 9141780; 48: 785779.95; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Delay to planning submission for outline application submission and therefore start on site. Current delay of 5 months from original submission date of end of March 2024. This has pushed construction costs for community centre shell & core to 25/26, 26/27. We are currently studying procurement options for the community centre - traditional, 1-stage D&B and 2-stage D&B. Each option has a slightly different programme but all show construction starting 25/26, whereas before, we had forecast SoS for 24/25. I'm unsure if I've missed something in my 24/25 forecast as £5.2m is substantial, but Jason J is away and I need to sit down with him and go over line by line to see what I've missed or if the 24/25 forecast was too high. Will be able to confirm these numbers when he gets back on 22/07.; 51: 8154389; 52: 4392329; 53: 1106941.05; 54: 3288389; 55: -1059671; 56: -3014497.95; 57: -785779.95; 65: HL; 66: Yes; 69: Yes; 70: No - answer next question; 71: Yes; 72: Peabody taken over all client CDM responsibilities for all project scope excluding the community centre fitout. - OCC have appointed AAP to carry out PM, QS and CDM roles for the fitout scope of the community centre project. This scope might change as OCC/PBT explore the possibility of delivering shell & core and fitout together by one contractor, so QS, CDM roles may be carried out by PBT consultants. - currently exploring procurement options for joint shell & core and fitout. EOIs have been received, PBT reviewing. OCC/PBT to meet to discuss w/c 22/07. - Once procurement strategy confirmed, CDM strategy to be reviewed.; 73: Yes; 74: No - answer next two questions; 75: CDM for construction not in place yet as it is still early, but CDM to be reviewed once procurement strategy confirmed. OCC has appointed consultants to take over CDM in any case.; 77: Currie & Brown (appointed by Peabody); 78: The Hill Group; 80: Yes; 82: Community Centre fit out and possible sub-contractor work packages; 84: Community Centre fitout: £2.3 build cost; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45548.4125 | jbarker@oxford.gov.uk
Affordable housing (supply) | Enabling/ Top-up grants to enable affordable housing supply using s.106 developer contributions | M5034 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Dave Scholes |  | Other Capital Spend | s106 Top-up/ Enabling grant. Dec 22 Delegated decision re £650k agreed to enable a 9 unit tenure switch to SR at Barton Park - with P4P. Grant Agreement to be finalised and detailed delivery programme awaited (July 24). Sept 23 Cabinet committed the remaining £1.3m as further funding into the BBL Regen project (for phase 2) if required - to ensure viability. July 24 update - Included in Peabody modelling and assumed to be required to make the scheme stack. |  | 2029-03-30 | Grant Agreement for P4P for additional affordable homes at Barton Park. | Grant Agreement for Peabody re BBL ph 2 funding contribution. |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: s106 Top-up/ Enabling grant. £1,308,000 yet to be committed to projects. Delegated decision re £650k agreed Dec 22 (9 unit tenure switch to SR at Barton Park - with P4P).; 34: £650k - 2025/26 (tbc). Remaining £1,308k - 2028/29 (tbc). Unable to identify projects for possible further spend, or to mitigate risks on current schemes in delivery at present, and without additional s.106 contributions to spend. 2024/25 budget is showing as £128k over expectation. Funding contribution to the LFH development has yet to be debited (was planned to be actioned in the 2023/24 closedown).; 40: 1958000; 41: 2086000; 42: 0; 43: 0; 44: 0; 45: 2086000; 46: 0; 47: 128000; 48: -1958000; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Reprofiling into future years; 51: 650000; 53: 1308000; 54: 650000; 55: 0; 56: 1308000; 57: 1958000; 66: No; 77: n/a; 78: n/a; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Oxford Growth Deal Registered Provider Funding | Redistribution of OGD funding to RP schemes on completion | M5035 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Dave Scholes |  | Other Capital Spend | Passing on grant received from County. No funding from the Capital Programme. All incoming funding received (£10,530,000) is paid out to the relevant projects as 90% on SoS and 10% at PC. £3,470k paid to L&G for William Morris Court £4,340k paid to Catalyst/ Peabody for Littlemore Park. £2,720k committed to A2Dominion for Gibbs Cres, with £2,448k paid to date. |  | 2025-03-31 | Continue to manage and monitor 'stalled site' with A2D at Gibbs Crescent. £272k due at PC. There is a risk that this will not be paid, and that the £2,448k already paid will need to be clawed back (and then repaid to County). A2D are seeking replacement funding direct from Homes England (with the claim currently held pending). |  |  |  | 24: On target; 25: On Budget; 26: Off Target; 27: Medium; 28: Medium; 30: Passing on grant received from County. No funding from the Capital Programme. All incoming funding received (£10,530,000) - Paid out at 90% on SoS and 10% at PC. July 22 - Budget now re-aligned by finance to reflect true position/ liabilities (overall this remains cost neutral to OCC). Oct 22 - Final grant paid to L&G on practical completion of William Morris Close. All funds from 22/23 (£2,795,000 paid).; 33: All agreements sealed. But see comment above about terminating the agreement with A2D.; 34: Gibbs Cres stalled due to contractor going into Administration. Re-tendered and A2D are ready to award the new build contract pending securing funding certainty to ensure viability.; 40: 272000; 41: 0; 42: 272000; 43: 0; 44: 0; 45: 272000; 46: 0; 47: 0; 48: 0; 51: 272000; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 77: NA; 78: NA; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3931 | mmcfarlane@oxford.gov.uk
Oxford North (Northern Gateway) | Drawdown of HIF funding to provide infrastructure for Oxford North and facilitate the provision of additional affordable housing as part of the development. | M5037 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Jenny Barker |  | Delivery | It has not been possible to agree the drawdown and spend of the HIF grant and a request has been made to Homes England to withdraw from the funding agreement. |  | 45380 | Confirmation from Homes England re the withdrawal from the Funding agreement and confirmation that funding held is to be returned. |  |  |  | 24: Off Target; 25: On Budget; 26: Off Target; 27: High; 28: High; 30: Further meeting with TWO and Homes England has taken place with a view to resolving the remaining issues with regard to the HIF agreement and agreement between OCC and TWO. Final version of the Deed of Variation has been received but TWO have concerns re the draft. HE have raised concerns re the ability to pay the funding. . First claim for funding submitted and paid and will be forwarded to TWO once agreements completed. Capacity Funding for 22/23 has been received.; 33: Homes England have advised they will be seeking repayment of the funding currently held; 37: no; 40: 0; 41: 1153416; 42: 0; 43: 0; 44: 0; 45: 1153416; 46: 2218.05; 47: 1153416; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 70: Yes; 77: NA; 78: NA; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Roken House | Acquisition and refurbishment to provide 9 x one bedroom flats for permanent lets at Social Rent (using RRTBRs) | M5038 | Development Board |  | Development | Housing Supply (GF) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | Andy Dorrington |  | Dave Scholes |  | Other Capital Spend | Jan 22 - Architects appointed. April 22 - Property purchased (£1.4m). Works Spec prepared. Asbestos Survey commissioned. Jun 22 - Planning App submitted. M&E consultants appointed. Full spec being prepared. Slight project delays due to additional surveys and reports having to be commissioned - M&E survey (inc Fire Strategy); Flood Risk Asst (for planning). Oct 22 - Planning approval secured. Building Control application in. Tender pack for works prepared and with ODS for pricing. Project currently has c. 5 weeks delay to programme. Nov 22 - Pricing to spec (with options) undertaken. Assessment (ahead of contract award) on 21st Nov 22. Dec 22 - M&E pricing still awaited. Jan 23 - ODS pricing confirmed and verified by indep QS. Decision made to increase the budget envelope by £200k and to award the contract - Now back on (enhanced) budget. May 23 - Contract Award (to ODS) June 23 - SoS Dec 23 (Budget) Cabinet recommendation to move project from GF to HRA - Approved at full Council in Jan 24. Mar 24 - Handover of 8 homes / PC (9th home - old office -pending final Building Control sign-off) Aug 24 - BC sign-off completed (Flat 9). PC achieved. All homes let. |  | 2024-08-02 | Finance to move entire project into HRA (2023/24 year end closedown) including RRTBR inclusion in the DLUHC 'pooling return' re spend. |  |  |  | 24: Completed; 25: On Budget; 26: Off Target; 27: Low; 28: Medium; 30: Jan 22 - Architects appointed. April 22 - Property purchased (£1.4m). Works Spec prepared. Asbestos Survey commissioned. Jun 22 - Planning App submitted. M&E consultants appointed. Full spec being prepared. Slight project delays due to additional surveys and reports having to be commissioned - M&E survey (inc Fire Strategy); Flood Risk Asst (for planning). Oct 22 - Planning approval secured. Building Control application in. Tender pack for works prepared and with ODS for pricing. Project currently has c. 5 weeks delay to programme. Nov 22 - Pricing to spec (with options) undertaken. Assessment (ahead of contract award) on 21st Nov 22. Dec 22 - M&E pricing still awaited. Jan 23 - ODS pricing confirmed and verified by indep QS. Decision made to increase the budget envelope by £200k and to award the contract - Now back on (enhanced) budget. May 23 - Contract Award (to ODS) June 23 - SoS; 33: Some additional items and Architects Instructions have been necessitated but negotiations underway to minimise costs (max expected overspend c.£63k); 34: TO MOVE ENTIRE PROJECT FROM GF TO HRA (as per Jan 24 Council); 40: 0; 41: 95556.35; 42: 0; 43: 0; 44: 0; 45: 95556.35; 46: 440789.38; 47: 157500; 48: 61943.65; 50: Final Account settlement underway; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 68: Yes; 69: No; 70: Yes; 72: Client pre-construction checklist complete and requirements met; 73: No; 74: Yes; 77: Jessop and Cook (architects); 78: ODS; 80: Yes; 82: Refurb project (£400k exc on-costs); 84: 425000; 117: 0; 277: N/A | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Roken House (HSB) | Redevelopment of former supported accommodation block - 9 units. | M5038 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 31: Awaiting handover of scheme before the end of FY; 40: 65000; 41: 255000; 42: 350000; 43: 0; 44: 0; 45: 605000; 46: 0; 48: -255000; 54: -350000; 55: 0; 56: 0; 57: -350000; 95: 44510; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: City Council; 106: N/A; 107: 9; 108: 9; 109: 0; 110: 0; 113: 0; 114: 0; 116: No; 117: 9; 118: 9; 120: 44681; 121: 44742; 122: 44773; 123: 44804; 124: 45016; 125: Planning approval; 133: 44693; 134: 44805; 135: 45041; 136: 45082; 137: 45529; 138: 8; 139: 8; 145: 1; 146: 1; 188: On target; 190: On target; 193: On target; 196: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: GENERAL FUND DIRECT DELIVERY. Acquired 01/04/22. Jessop and Cook architects commissioned. Planning application for one additional unit to be created from internal reconfiguration (May 22). 16/05/22 - Planning application approved with uplift of budget - Working towards client sign off and build programme. 28/09/23 - the office will now be converted to a flat so numbers to 9 social rent delivery 28/11/23 -- handover pushed back til end of Jan 24. 13/03/24 - 8 of the 9 units to be handed over by end of the month 03/06/24 - building control visited end of May. Final flat should handover next month 30/07/24 - the final (9th) unit of the scheme handed over on 25/07/24. Scheme moving to closed.; 217: 51.7401; 218: -1.2554; 219: 8; 277: N/A; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3812 | mmcfarlane@oxford.gov.uk
UK Shared Prosperity Fund (UKSPF) | Oversight and monitoring of UKSPF investment plan | M5039 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Matthew Broadbent |  | Rolling Programme | Following agreement at development board (17th July) UKSPF capital expenditure for this year will focus on the Market Street scheme design and delivery - up to £170k has been allocated for 23/24. The remaining £20k capital has been made available to progress St Michael's Street, ahead of delivery in 24/25. The focus for revenue expenditure this year is to cover the officer time in delivering the Match My Project trial to support community organisations and social value delivery. There is a small allocation (£35k) planned to deliver training and business development support through a third party. Advice from legal suggests this may be possible through direct grant award to a partnership of local providers - OSEP, CAG, Cooperative Futures. This will need Director sign off. Members have expressed concerns that the Wayfinding upgrade had been removed from the plan and we are exploring options to reintroduce in the programme's final year 24/25, using some of the funding allocated to skills. |  | 45747 | See Market Street project for latest dates | Social Economy Support provider appointed - December 2023 | Match My Project Launch - 7th November |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 65000; 41: 371817; 42: 0; 43: 0; 44: 0; 45: 371817; 46: 0; 48: -371817; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: No; 81: Whole programme - funding broken down into projects, all of which has now been allocated.; 83: Already Awarded; 117: 0 | [12 empty] | 45579.3416 | mbroadbent@oxford.gov.uk | Y | 45551.3812 | mmcfarlane@oxford.gov.uk
Brownfield Land Release Fund 2 (BLRF2) | Brownfield Land Release Fund 2 (BLRF2) | M5040 | Development Board | Housing Supply Board |  |  |  | Housing |  | Tom Bridgman |  |  | Anneri Gatial |  | Dave Scholes |  | Delivery | Two contracts signed (March 24) for survey work (Bailey Garner) and demolition and enabling works (ODS) - now programmed in during Q3 & 4 2024/25. Relates to 5 sites (Underhill, Leiden, BBL x3) |  | 45744 | Surveys; Planning App; and party wall info | Demolition works (garages on 3 sites and 2 x bungalows on one). |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 34: Working now to commission main build contracts; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 48908.78; 47: 340213; 48: 340213; 49: N/A - On Budget; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 69: Yes; 78: ODS; 80: Yes; 82: Demotion and enabling works; 84: 315000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3812 | mmcfarlane@oxford.gov.uk
Harebell Road (small sites) | Small sites scheme with BLRF and potential for four homes | M5040 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45315; 96: Cabinet Decision; 100: No; 101: Enabling RP Led; 104: OCLT; 105: City Council; 106: HE Programme; 107: 4; 108: 2; 110: 2; 117: 4; 125: Pre-Application; 127: 2024-10-27; 128: 45667; 130: 2025-05-20; 131: 2025-05-20; 132: 46112; 152: 4; 153: 2; 155: 2; 188: At Risk; 213: 07/09/23 Funding to prepare site available through BFLR. 06/06/24 - Milestones updated from BBL sites draft programme PDF; 215: 45264; 216: 45649; 217: 51.7208; 218: -1.192; 275: 5000; 276: Approval for a revolving feasibility budget of £50,000 (£5,000 per site).Agreed at HSB 25 July 2023 and Development Board on 17 August 2023; 300: TRUE; 305: 75260 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Balfour Road (small sites) | Small sites scheme with BLRF and potential for four homes | M5040 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45315; 96: Cabinet Decision; 100: No; 101: Enabling RP Led; 104: OCLT; 105: City Council; 106: HE Programme; 107: 4; 108: 2; 110: 2; 117: 4; 125: Pre-Application; 127: 45592; 128: 45667; 130: 45797; 131: 45797; 132: 46112; 152: 4; 153: 2; 155: 2; 188: At Risk; 213: 07/09/23 Funding to prepare site available through BFLR 06/06/24 - Milestones updated from BBL sites draft programme PDF; 215: 45264; 216: 45649; 217: 51.7226; 218: -1.2038; 275: 5000; 276: Approval for a revolving feasibility budget of £50,000 (£5,000 per site).Agreed at HSB 25 July 2023 and Development Board on 17 August 2023; 300: TRUE; 305: 44045 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Pegasus Road (small sites) | Small sites scheme with BLRF and potential for four homes | M5040 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45315; 96: Cabinet Decision; 100: No; 101: Enabling RP Led; 104: OCLT; 105: City Council; 106: HE Programme; 107: 4; 108: 2; 110: 2; 117: 4; 125: Pre-Application; 127: 45592; 128: 45667; 130: 45797; 131: 45797; 132: 46112; 152: 4; 153: 2; 155: 2; 188: At Risk; 213: 07/09/23 Funding to prepare site available through BFLR 06/06/24 - Milestones updated from BBL sites draft programme PDF; 215: 45264; 216: 45649; 217: 51.719; 218: -1.2028; 275: 5000; 276: Approval for a revolving feasibility budget of £50,000 (£5,000 per site).Agreed at HSB 25 July 2023 and Development Board on 17 August 2023; 300: TRUE; 305: 92595 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Barton Howards | Regeneration of the Howard housing at Barton | MD95 | Development Board | Development Review Group | Development | Housing - HRA (Supply) |  | Capital Delivery |  | Nerys Parry |  |  |  |  | TBC |  | Closed | Closure report presented to HSB 16 November. Pre-meeting held between property team and SW on 02/11/22. Malcolm Peek outlined proposed way forward in terms of remedial works to all steel framed houses in OCC stock. SW uploaded all data to property server. |  | 44616 |  |  |  |  | 24: On Hold; 25: Completed; 26: Completed; 27: N/A; 28: N/A; 30: Closure report presented to HSB 16 November. Pre-meeting held between property team and SW on 02/11/22. Malcolm Peek outlined proposed way forward in terms of remedial works to all steel framed houses in OCC stock. SW uploaded all data to property server.; 33: Remedial works to property to maintain minimum standards become very onerous in near future leading to unplanned loss of housing stock.; 34: SW to advice property if any outstanding issues arise.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Test for Rachel | Test for Rachel | N/A | Development Board | [11 empty] | Rachel Haverson |  | Idea | Test Test Test | [6 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Test for Rachel 1 | Test for Rachel |  | Development Board | [11 empty] | Rachel Haverson | [9 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Test for Rachel 2 | Test for Rachel |  | Development Board | [11 empty] | Rachel Haverson | [9 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Test for Rachel 3 | Test for Rachel |  | Development Board | [11 empty] | Rachel Haverson | [9 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Tower Blocks | Refurbishment of the tower blocks | N6384 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Capital Delivery |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Design & Specification | Negotiations in progress - slip 1.3M to 25/26 |  | 46477 |  |  |  |  | 24: On Hold; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 30: Work on Evenlode & Windrush will slip through into the 2023/24 financial years at the earliest, this being subject to statutory approvals, completion of the works and compliance with the Employers Requirements; 40: 1000000; 41: 260386.98; 42: 1300000; 43: 0; 44: 0; 45: 1560386.98; 46: 6630.02; 47: 260386.98; 48: 0; 49: Slippage (Less spend in 24/25 now forecast in future years); 51: 1310386.98; 52: 250000; 53: 0; 54: 10386.98; 55: 250000; 56: 0; 57: 260386.98; 80: No; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Adaptations for Disabled | Overspent last year, predicting overspend this year | N6385 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Miscellaneous Capital Spend |  | Nerys Parry |  |  | - |  | Luca Minetola |  | Rolling Programme | ODS budget demand led - 168K remaining at end of Feb |  | 45747 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Lack of visibility of work stream which lies with ODS; 40: 800000; 41: 800000.05; 42: 750000; 43: 650000; 44: 650000; 45: 2850000.05; 46: 812853.47; 48: -800000.05; 54: -750000; 55: -650000; 56: -650000; 57: -2050000; 80: Unsure; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Structural | Repairs and maintenance programme | N6386 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Bill Chamberlain |  | Luca Minetola |  | Rolling Programme | "Concrete works Work completed to 1 scheme, ongoing for 3 others and still to start at last. General subsidence and cracking. On demand budget - Update on 29/08 POs raised to the Sum of £137,112.50 for Phase 1, 10 properites completed to RIBA stage 2. Cabnet report in process for 1 Million spend" | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Medium; 28: N/A; 30: Concrete works Work completed to 1 scheme, ongoing for 3 others and still to start at last. General subsidence and cracking On demand budget; 40: 2000000; 41: 2187754.28; 42: 2000000; 43: 2000000; 44: 2000000; 45: 8187754.28; 46: 67485; 47: 2187754.28; 48: 0; 54: -2000000; 55: -2000000; 56: -2000000; 57: -6000000; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Controlled Entry | Repairs and maintenance programme | N6387 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Bill Chamberlain |  | Luca Minetola |  | Rolling Programme | Survey being completed in this year. First reports due back (priority blocks) week ending 11th Oct | [6 empty] | 24: On target; 25: On budget; 26: On target; 27: Low; 28: N/A; 30: Works still need to be identified for this financial year but all controlled entry systems needs to be updated from 3g to 5g to ensure ease of management of fobs; 40: 100000; 41: 317991.14; 42: 333000; 43: 75000; 44: 75000; 45: 800991.14; 46: 3351.79; 47: 100000; 48: -217991.14; 54: -333000; 55: -75000; 56: -75000; 57: -483000; 80: No; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Major Voids | Repairs and maintenance programme | N6388 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | - |  | Luca Minetola |  | Rolling Programme | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. This is also a delegated budget to ODS. Demand led. Orders for a number of major voids have recently been placed. |  | 45747 |  |  |  |  | 24: On target; 25: Over budget; 26: On target; 27: Medium; 28: N/A; 30: These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. This is also a delegated budget to ODS. Demand led. Orders for a number of major voids have recently been placed.; 40: 1000000; 41: 999999.56; 42: 1000000; 43: 1000000; 44: 1000000; 45: 3999999.56; 46: 728341.64; 47: 1000000; 48: 0.44; 49: N/A - On Budget; 54: -1000000; 55: -1000000; 56: -1000000; 57: -3000000; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Damp-proof works (K&B) | Repairs and maintenance programme | N6389 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Chris Scott |  | Luca Minetola |  | Rolling Programme | "A rolling programme where repairs are done as they come in. There has been an increase in the number of damp issues during autumn and winter months. Work needs to be done to identify persistent issues to make installations planned rather than re-active" | [6 empty] | 24: On target; 25: On budget; 26: On target; 27: Medium; 28: N/A; 30: A rolling programme where repairs are done as they come in. There has been an increase in the number of damp issues during autumn and winter months. Work needs to be done to identify persistent issues to make installations planned rather than re-active; 40: 0; 41: 43714.02; 42: 0; 43: 0; 44: 0; 45: 43714.02; 46: 0; 47: 43714.02; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Kitchens & Bathrooms (holding budget) | Holding budget awaiting allocation to individual headings | N6390 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme |  |  | 45747 |  |  |  |  | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 250000; 48: 250000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Heating (holding budget) | Holding budget awaiting allocation to individual headings (Heating Systems / Boilers only) | N6391 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme |  |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 107710; 48: 107710; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Roofing | Repairs and maintenance programme | N6392 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Rolling Programme | orders placed and 26 properties and properties still to be validated for remaining budget |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 30: orders placed and 26 properties and properties still to be validated for remaining budget; 40: 0; 41: 190750.66; 42: 0; 43: 0; 44: 0; 45: 190750.66; 46: 0; 47: 190750.66; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Electrics | Repairs and maintenance programme | N6395 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | ODS |  | Luca Minetola |  | Rolling Programme | Delegated budget to ODS and is on target to deliver. We have agreed to fund 165 properties |  | 45016 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: N/A; 28: N/A; 30: Delegated budget to ODS and is on target to deliver. Need agreement to fund 200 properties this year; 40: 2000000; 41: 1947923.87; 42: 2000000; 43: 700000; 44: 500000; 45: 5147923.87; 46: 300478.46; 47: 1947923.87; 48: 0; 49: N/A - On Budget; 54: -2000000; 55: -700000; 56: -500000; 57: -3200000; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Doors and Windows | Repairs and maintenance programme | N6434 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Rolling Programme | Nationwide are still completing properties from last years programme and have had access issues. A programme of works for this year has been identified and submitted for Nationwide to price. |  | 2021-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 30: Nationwide are still completing properties from last years programme and have had access issues. A programme of works for this year has been identified and submitted for Nationwide to price.; 40: 0; 41: 0.49; 42: 0; 43: 0; 44: 0; 45: 0.49; 46: 0; 48: -0.49; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Extensions & Major Adaptions | Extensions & Major Adaptions | N7020 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Rolling Programme | Commented as per each single project | [6 empty] | 24: On target; 25: On Budget; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 1000000; 41: 1927386.93; 42: 700000; 43: 700000; 44: 700000; 45: 4027386.93; 46: 371373.91; 47: 475265.95; 48: -1452120.98; 54: -700000; 55: -700000; 56: -700000; 57: -2100000; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
50 Oxford Road adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Delivery | Approved construction and architectural services (Stages 1-6) cost. Currently under construction |  | 45961 | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: Over budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 67756.16; 48: 67756.16; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
18 Lambourn Road adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Completed | Works completed | [6 empty] | 24: Completed; 25: Completed; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
12 Spindleberry Close adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Completed | Works completed | [6 empty] | 24: Completed; 25: Completed; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
34 Weldon adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Delivery | Approved construction and architectural services (Stages 1-6) cost. Currently under construction |  | 2025-06-30 | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 27920.35; 48: 27920.35; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
14 Heather adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Delivery | Approved construction and architectural services (Stages 1-6) cost. Construction on hold until decanting |  |  | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 25614.53; 48: 25614.53; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
2 Broadhead Place adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Design & Specification | Approved architectural services (Stages 1-6) cost. Tender cost approved by HRG. Currently under mobilisation period |  | 2026-03-31 | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 82737.5; 48: 82737.5; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
21 Kendall Crescent adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Feasibility | Approved architectural services (Stages 1-4) cost. On hold | [6 empty] | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 5586.33; 48: 5586.33; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
16 York Road adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Gary Long |  | Luca Minetola |  | Delivery | Approved construction and architectural services (Stages 1-6) cost. Currently under construction |  | 45838 | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: No projects on site but progress being made. Now have single point of contact in Francisco Gomez. Finishing one project and have approval for two more; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 30595.5; 48: 30595.5; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Major works team to price for all works; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
23 Brampton Road extension and adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Approved architectural services (Stages 1-3) cost. On hold |  |  | Appointment of design team completed | Package of works out to tender to be developed | Project Completion TBC |  | 24: On Hold; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 1726.34; 48: 1726.34; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
2 Green Hill extension and adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Design & Specification | Approved architectural services (Stages 1-6) cost. Tender cost approved by HRG. Currently under mobilisation period |  | 2026-03-30 | Appointment of design team | package of works out to tender | Project Completion |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 150024.6; 48: 150024.6; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
37 Peppercorn Avenue extension and adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Design & Specification | Approved architectural services (Stages 1-4) cost |  |  | Appointment of design team completed | Package of works out to tender completed | Project Completion reached |  | 24: On Hold; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 2845; 48: 2845; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
29 St Peter's Road extension and adaptation | Extensions & Major Adaptions |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Design & Specification | Approved architectural services (Stages 1-4) cost. On hold |  |  | Appointment of design team | package of works out to tender | Project Completion |  | 24: On Hold; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 10500; 48: 10500; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Communal Areas | Repairs and maintenance programme | N7026 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | Capital programme budget |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: N/A; 30: Ahead of schedule on FRA and on target for asbestos surveys. Additional resource gained from contractors to catch up on deficit. Work ongoing; 40: 0; 41: 0.33; 42: 0; 43: 0; 44: 0; 45: 0.33; 46: 6533.1; 47: 728491.33; 48: 728491; 50: Demand led budget; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: Decoration and repair works to stairwells; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Great Estates Programme | Development projects | N7032 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Sue Briscoe |  | Luca Minetola |  | Rolling Programme | Move 400K to FRA programme and put 500k reserve for bin store project |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: Projects waiting for approval. One project on site. Budget unlikely to be completely spent this year; 37: Planting of trees, hedges and wildlife habitat. Local sourcing of products were possible.; 40: 0; 41: -0.03; 42: 0; 43: 0; 44: 0; 45: -0.03; 46: 0; 47: 6180; 48: 6180.03; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 82: with Highways; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Energy Efficiency (Initiatives) |  | N7033 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Broken down into specific projects |  | 2025-03-31 |  |  |  |  | 24: Off Target; 25: On budget with slippage; 26: Off Target; 27: Low; 28: Low; 30: SHDF funding application proceeding well. LAD1B project. Breyer Group gave assurances that all lodgements will be completed by end of October enabling us to make final declaration and keep funding but were unable to do so. They then requested an extension until 19th October which was granted by BEIS; 40: 7450000; 41: 6874424.65; 42: 12750000; 43: 2325000; 44: 2325000; 45: 24274424.65; 46: 112269.59; 47: 6581510.21; 48: -292914.44; 51: 2325000; 52: 2325000; 53: 2325000; 54: -10425000; 55: 0; 56: 0; 57: -10425000; 68: Yes; 79: CPP being developed; 80: Yes; 84: TBC; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
SHDF Wave 2.1 |  |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Works on site have commenced and the project is now in delivery phase. The first completions are due imminently by ODS and Vinci are also due to complete installations shortly. 54 properties have commenced delivery. A review of number of properties deliverable is currently underway with DESNZ due to the 23/24 funding clawback (£200k TBC). |  | 2025-03-31 | Grant funding spent by 31/03/25 | Delivery completed by Sept 25 at latest |  |  | 24: Off Target; 25: On budget with slippage; 26: Off Target; 27: Medium; 28: Medium; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 4542472.35; 48: 4542472.35; 54: 0; 55: 0; 56: 0; 57: 0; 68: Yes; 79: CPP being developed; 80: Yes; 82: 100 properties; 84: TBC; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
23/24 ASHP Project |  |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Feasibilibility surveys are underway with engagement due to start. |  | 2025-03-31 |  |  |  |  | 24: Off Target; 25: On budget with slippage; 26: Off Target; 27: Low; 28: Low; 33: Delays to procurement due to legal consultants delaying contracts for framework. Working with legal and procurement to ensure this is sorted ASAP.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 789037.86; 48: 789037.86; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 68: Yes; 79: CPP being developed; 80: Yes; 82: TBC; 84: TBC; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
23/24 GSHP Project |  |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Feasibility completed and final designs drafted. |  | 2025-03-31 |  |  |  |  | 24: Off Target; 25: On budget with slippage; 26: Off Target; 27: Low; 28: Low; 33: Delays to procurement due to legal consultants delaying contracts for framework. Working with legal and procurement to ensure this is sorted ASAP.; 34: Grid Capacity could impact delivery programme as a sub station upgrade is likely needed.; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 1000000; 48: 1000000; 54: 0; 55: 0; 56: 0; 57: 0; 68: Yes; 79: CPP being developed; 80: Yes; 82: TBC; 84: TBC; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Other N7033 |  |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Not a project |  | 2025-03-31 | n/a | n/a | n/a |  | 24: Off Target; 25: On budget with slippage; 26: Completed; 27: Low; 28: Low; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 47: 250000; 48: 250000; 54: 0; 55: 0; 56: 0; 57: 0; 68: Yes; 79: CPP being developed; 80: No; 84: TBC; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Blackbird Leys Regeneration (HRA element) | Regeneration of Blackbird Leys including the Retail Centre, Community Centre and Knights Road to provide approximately 294 new homes, retail units and community centre. The regeneration is in partnership with Catalyst Housing. | N7040 | Development Board | Development Review Group | Development | Housing - HRA (Supply) |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Karoline Soisalo De Mendonca |  | Delivery | PHASE 1 UPDATE: - S278 still sits with County for approval/agreement. Street lighting design pending, but County has agreed to sign without technical approval for lighting. - Badger Issue: new badger sett built, now ecologist to check that badgers have gone to the new sett. This will de-risk the Knights Rd site development significantly. - Delays in going through safety gateway new Building Act for tall buildings. Issues in trying to get a case manager assigned, over 12 weeks delayed and ongoing. HIF: -Last HIF claim in August LEGAL: - Budget for internal capital charges set - JO, BM and KSM discussed legal works for Phase 2 should be c. £50k, with £30k uplift in case of CPO -JO to lead on procurement for legal consultants using framework PHASE 2: - BM and Property leading on engagement with residents and retail units for Phase 2 VP, move into Block A. - BG advised that residents to be moved earlier rather than later to avoid distress of living opposite construction, one tenant already moved. - CPO cabinet report to go on forward plan May/June, report to go to cabinet in October. This is to allow OCC to enact CPO powers if needed, although unlikely. VIABILITY: - Phase 2 viability: OCC/PBT meeting to discuss options - PBT presented options that looked at varying: tenure spite, accommodation, building height and frame to reduce costs and improve viability. - PBT presented two viable options with varying social rent/shared ownership numbers. Dave Scholes was present in the latest meeting to assess from AH point of view. - OCC has requested that PBT explore further options that look at more tenure/accommodation variation. - next meeting: 22/08/24 HOUSING: - Comms with residents happening, BG & housing team to assisting. - Housing rehomed one OCC tenant, aiming to move the rest early and have the housing units as temporary accommodation until Phase 2 VP. COMMS: - Comms ongoing, with Peabody consultants leading - Community Centre events and comms ongoing and led by TbD |  | 2028-05-23 | Signing of S278: 'imminent' (?) End of August | Badger relocation completed: Need to achieve by end of November | Phase 2 Strategy Agreed: End of September |  | 24: On target; 25: On budget; 26: On target; 27: Medium; 28: Medium; 30: "PLANNING: - Planning application is undergoing determination. - Amendment including some changes to the design, ie – second stair core addition, submitted. Consultation for amendment ends on 19/06. - Highways had submitted an objections that has since been retracted following a meeting with LPA/Savills/Applicants - We are still aiming to go to July planning committee. - Parish Council have appointed a team of consultants including a regeneration consultant, who have helped Parish understand the application documents and write their comments. Parish have issue and concerns but their position was not an objection (when comments submitted to LPA 03/05/23 - Parish on 31/05 was contentious and both councillors and members of the public were voal against aspects of the project. The focus was on the community centre size, location and lack of engagement. - Parish had a meeting with the LPA w/c 05/06 to voice their concerns. OCC/PBY are meeting with Parish on 19/06 to further discuss. HIF: - We are still waiting to hear back from HE regarding the HIF extension. - We received another set of queries fro HE, which have now been answered. There are a couple of financial questions (of changes to costs/funding) that we are finding difficult to bottom out. KSM invited HE/PBY to a meeting to clarify/discuss outstanding items. - HE confirmed that funds cannot be drawn down prior to HIF Agreement DoV being signed. LEGAL: - Intent to appropriate report was approved at cabinet 14/06/23. KSM now working on the notice to be published in the Oxford Mail. - Ad to run for 14 days and comments allowed for 28 days. - Appropriation to go back to Cabinet once comments received (August Cabinet?) - DoV meetings are ongoing. Freeths/Devonshires met on 13/06/23 to discuss main items. Freeths/Devs to negotiate wording. Devs to send OCC the commercial terms for discussion. - DoV terms to go to Cabinet in Aug. COMMUNITY CENTRE: - PBY/OCC agreed to delivery model of PBY taking on DM role, OCC taking on financial risk. - PBY to appoint lead consultant/design team directly. JTP to design shell and core, with J&C to design interior fitout. - OCC to direct appoint J&C to work alongside Transition by Design, JTP and Hill on early engagement and design. This can come out of CC interior fees, where there is allowance for community engagement, Stages 0-1 works. - Parish, community unhappy with the cc being in outline application. Not enough explanation on why this was going in as hybrid? Community believe the cc won’t be given enough attention/ won’t be delivered. - This will hopefully be clarified at Parish/OCC/PBY meeting on 19/06. -Engagement work with TbD to start asap. OCC/PBY to meet TbD on 19/06. VIABILITY: - PCSA2 ongoing. Hill to finalise PCSA work end of July, Calford Seaden to write report in 2 weeks following. OCC to get Ridge to write a report on findings, ME to write up best case? COMMS: - Newsletter to go out after Parish meeting, but before Parish Council."; 33: - S278: this is a risk to delay in programme and S278 works SoS. Signing of S278 is said to be imminent. - Phase 2 Viability: viability of Phase 2 at risk. Peabody have carried out a viability study to test delivery options to demonstrate the viability of Ph 2, strategy to be agreed. Delay risk as Ph 2 may need a new planning application. - Comms & Engagement: Still a risk. Need to send out comms especially to update on site works and conditions. - CPO risk for retail units and leaseholders: Property are currently engaging with leaseholders and retail tenants, and advise that CPO risk is low. Property to lead on cabinet report for potential CPO for Phase 2 properties, to go to cabinet Oct 2024.; 34: - S278 to be signed. - Badger sett relocation: sett built and installed, badgers to be monitored to confirm relocation. - Ph 2: OCC/PBT to agree on delivery strategy, then agree next steps: viability review, DoV to DA, Planning submission etc.; 37: Proposals as planning policy based on current 2022 building regs with additional fabric uplift. Note proposals to reduce standards considered by CHL as part of viability review but no longer proposed.; 40: 1504000; 41: 2353317.52; 42: 172000; 43: 172000; 44: 172000; 45: 2869317.52; 46: 1343765.67; 47: 2353317.52; 48: 0; 49: N/A - On Budget; 51: 172000; 52: 172000; 53: 172000; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: Yes; 69: Yes; 70: No - answer next question; 71: Yes; 72: Peabody taken over all client CDM responsibilities for all project scope excluding the community centre fitout.; 73: Yes; 74: Yes; 77: Currie & Brown (appointed by Peabody); 78: The Hill Group; 80: No; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Barton Regeneration | Development projects | N7042 | Development Board |  | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Sue Briscoe |  | Luca Minetola |  | Rolling Programme | Agreed works completed |  | 2025-03-31 |  |  |  |  | 30: Works complete; 40: 0; 41: 598360.3; 42: 0; 43: 0; 44: 0; 45: 598360.3; 46: 0; 48: -598360.3; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Lift Replacement (Programme) | Lift Replacement Programme | N7044 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | No further significant lifts replacments for this current year but planning 25/26 - Large number of stair lift replacments expected |  | 2025-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 28: Low; 30: Programme for 2022-2023 being developed; 33: Awaiting procurement of Lift consultant to develop upodated replacement program; 40: 100000; 41: 103431.97; 42: 550000; 43: 150000; 44: 150000; 45: 953431.97; 46: 34345.14; 47: 150000; 48: 46568.03; 49: N/A - On Budget; 51: 150000; 52: 150000; 54: -400000; 55: 0; 56: -150000; 57: -550000; 80: No; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
12 Field ave Stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
17 Albert Street | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
26 Chillingworth Stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
30 Blackbird Leys Stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
32 Harebell rd stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
42 St Bernards Rd stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
5 Nicholson rd stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
59 Druce way Stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
68 Bernwood Stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
7 Brook view Stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
7 Faber Close Stairlift | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
7 Penny Cres stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 44286 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
92 Foxwell stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 44286 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Albert hs lift refurbishment | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 44286 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Evenlode Lift car lighting upgrade and flooring | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Pennywell drive Stairlift replacement | Lift Replacement Programme |  | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Completed | Programme for 2024-2025 being reviewed |  | 2021-03-31 |  |  |  |  | 24: At Risk; 25: Under Budget; 26: At Risk; 27: Medium; 30: Programme for 2022-2023 being developed; 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Social Rented Housing (Acquisitions) | Acquisition of street properties into the HRA to let at Social Rent (using Retained RTB Receipts). Rolling activity across multiple years. | N7047 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | Will McKay/ Steve Northey |  | Dave Scholes |  | Completed | ODS void works from 20/21 to end 22/23 capitalised/ charged into this budget - so all reconciled to April 23. The £23k retention from the Abbey Homes acquisition (45 homes) is also due to be paid in 23/24 from this budget, after defects work is completed and certified. (Jan 24 update - Awaiting confirmation of completed defects work before payment.) 2023/24 programme: Target: 9 acquisitions. Year End: 11 homes. |  | 45382 | Settlement of all final ODS works costs for 23/24 acquisitions asap - but will go past year end. | RETIRING THIS COST CENTRE FROM END 2023/24 |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: "22/23 Completions: Qtr 1: 1; Qtr 2: 3; Qtr 3: 2; & Qtr 4 (to date): 2. Total 8 YTD. 2 further properties are in the conveyancing pipeline for Qtr 4. Forecast for the year is 10 homes. This is below the project target (of 13) due to downward budget adjustments and difficulty in buying suitable 1 bed and 4 bed homes. ODS void works from 20/21 & 21/22 now capitalised, where possible, and charged into this budget. Two OX buy-backs (under extension project) also charged, in-part, to this budget. The £23k retention from the Abbey Homes acquisition (45 homes) is also due to be paid in 22/23 from this budget. Budget after adjustments is £2.425m (£2m plus £424k c/f after adjustments)."; 33: RETIRING THIS COST CENTRE FROM END 2023/24; 34: RETIRING THIS COST CENTRE FROM END 2023/24 UNCLEAR WHAT THE NEGATIVE BUDGET IN 24/25 IS - NEEDS RECTIFYING. SOME MIX-UP WITH N7051 WHICH SHOULD BE CLOSED??; 37: Additional carbon reduction measures applied as part of property refurbishment; 40: 0; 41: 0.16; 42: 0; 43: 0; 44: 0; 45: 0.16; 46: 94284.78; 47: 0; 48: -0.16; 50: Budget to be reset by finance and closed at end of 2023/24 year. No longer to be used.; 51: 0; 52: 0; 53: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: Yes; 82: Refurb/ void works required on all acquisitions; 84: 128000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45555.0919 | mmcfarlane@oxford.gov.uk
Street Property Acquisitions 23/24 | RRTB annual programme delivering street properties through leaseholder buy-back and open market | N7047 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 40: 0; 41: 440771.8; 42: 0; 43: 0; 44: 0; 45: 440771.8; 46: 290558.46; 48: -440771.8; 54: 0; 55: 0; 56: 0; 57: 0; 100: No; 101: Direct Delivery HRA; 105: Mixed; 107: 11; 108: 11; 116: No; 117: 11; 118: 11; 119: 11; 124: 45382; 125: Not Applicable; 126: Not Applicable; 132: 45382; 138: 11; 139: 11; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: 19/09/23 - Potential to deliver 11 units in 23/24; 220: 7; 224: 2 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Fire Doors | Fire door replacement | N7048 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | Awaiting ODS to submit costs for five blocks - Then need quotes for QS to review |  | 45747 |  |  |  |  | 24: On target; 25: Under Budget; 26: On target; 27: Low; 28: Low; 30: Doors to Foresters complete and survey work for Plowmans underway with approval for remaining tower blocks awaiting cabinet approval; 33: Re-focusing on high risk buildings as per BSR requirements, project being priced; 40: 1500000; 41: 3571177.4; 42: 1500000; 43: 1500000; 44: 1500000; 45: 8071177.4; 46: 42766.86; 47: 3000000; 48: -571177.4; 50: Contract approval and resource.; 51: 500000; 52: 500000; 54: -1000000; 55: -1000000; 56: -1500000; 57: -3500000; 80: Yes; 82: With ODS undergoing assessment for BM Trada installation approval there will be scope to install the required specified doors.; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
East Oxford (Housing Development) | Links with East Oxford Community Centre. This is the development of housing across two sites - 26 affordable homes (12 @SR & 14 @SO). | N7050 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Capital Delivery |  | Tom Bridgman |  |  | Lila Haracz |  | Dave Scholes |  | Delivery | Planning consent (Ctte Jan 21). Conditions being met. Working with Arcadis to develop a delivery programme. Sept 21 - Agt on route to market (separate to community centre refurb) - Housing Devt now being mobilised. Jan 22 - Build contract tenders issued. Plan to award in Feb 22. ODS undertaking demolition of all sites May to July 22, then site handover to residential. SOS Q3 2022/23, completion Q4 2023/24 (tbc - after tenders assessed). Jun 23 - Mobilising for SoS Tender results were poor - going back out to market again. Cost risk, although consultants believe that the expected budget envelope should still be sufficient (Mar 22). Impact on SoS expected to delay from Jan 23 to Mar 23. Professional Services costs paid by General Fund and will be apportioned over into HRA at year end by Finance. Oct 22 - Tenders from open tender assessed (inc financial due diligence) and contract award decision made (Dec 22). To now reset budget and programme following this. End Dec update - Contract now with Legal - expect to sign/ seal in Feb 23. Jan 23 - Homes England have confirmed that grant application is now approved. Oct 23 - Demolitions Complete. Having to move to 2nd tenderer - contract discussions underway and targeting contract signing in Nov 23 for SoS in early 2024. Contract with Life Build now signed and mobilising for SoS in March 24. Technical SoS achieved in Mar 24. Collins Street - Build progressing well - Above foundation (Jul 24). Princes Street - LifeBuild unable to access site for main works due to ODS on EOCC site adjacent - meetings to try to resolve. Lifebuild may have to delay build start to Sept 24 - likely cost implications being assessed. DSA to sign (OCHL to OCC) Mar 23-Jul 24 |  | 45925 | Princes Street site - Resolving issues for Life Build to start and assessing additional cost liability (HRA & GF) as a result. Report expected to escalate to Devt Board/ CMT following EOCC Project Board meeting on 19th July 24. | Delivery phase/ tracking progress | HE AHP grant milestones and funding draw-downs/ PC - grant drawdown for SOS achieved - Regular updates provided. |  | 24: Off Target; 25: On budget; 26: Off Target; 27: Medium; 28: High; 30: "Planning consent (Ctte Jan 21). Conditions being met. Working with Arcadis to develop a delivery programme. Sept 21 - Agt on route to market (separate to community centre refurb) - Housing Devt now being mobilised. Jan 22 - Build contract tenders issued. Plan to award in Feb 22. ODS undertaking demolition of all sites May to July 22, then site handover to residential. SOS Q3 2022/23, completion Q4 2023/24 (tbc - after tenders assessed). Jun 23 - Mobilising for SoS Tender results were poor - going back out to market again. Cost risk, although consultants believe that the expected budget envelope should still be sufficient (Mar 22). Impact on SoS expected to delay from Jan 23 to Mar 23. Professional Services costs paid by General Fund and will be apportioned over into HRA at year end by Finance. Oct 22 - Tenders from open tender assessed (inc financial due diligence) and contract award decision made (Dec 22). To now reset budget and programme following this. End Dec update - Contract now with Legal - expect to sign/ seal in Feb 23. Jan 23 - Homes England have confirmed that grant application is now approved." ODS revised programme/logistics to be coordinated. Revised CTMP approved. Briefing paper to project sponsor on access/delay issues. Princes - Working towards SOS 23 Sept'24. Programme delay and additional costs will be incurred. Collins - superstructure brick and blockwork progressing between 1st and 2nd floors. Scaffolding in progress. Arcadis are now working as the project coordinator with positive impact.; 31: KEY ACTION: Outstanding finance decision on Lifebuild claim - review date 16 Oct KEY ACTION: Need to agree contingency for possible claim - review date 16 Oct; 33: Princes St works on site delayed due to access, levels issues, so will incur additional costs and time. 23wk delay as currently expecting to SOS 23 Sept'24. Significant issues re construction management plan and delay to Princes Street SOS ODS on target for completion of CC timber frame by 20th Sept, which will enable Lifebuild to SOS at Princes Street on 23rd. Difficult tight sites to develop, co-ordination required with community centre main contractor on Princes Street. Solutions to the levels and drainage issues in shared footpath between both developments have been reached, but need to be be approved. Finance: Delays to SOS at Princes and potential impact of level issue will incur loss & expense claim, therefore increased build costs and programme delay. Planning: No issues identified re conditions, except condition 4 at Collins Street. Looking like Collins will be finished before the Community Centre (CC), so Collins completed units may need to remain vacant until CC reaches PC - this has been taken up with Planners. Both projects now scheduled for completion Sept 25.; 34: To agree programme/ delivery plan and any design changes with expected new contractor appointment (2nd placed tenderer, as 1st was not able to fulfil all contractual requirements). c. £1m slippage from 2023/24 to 2024/25 - adjustment to forecast required. No change to overall project budget which is on-track (pending above).; 37: Fabric first approach - good insulation and air tightness The scheme will use monoblock Heat Pumps complimented by carbon reducing technologies, such as good quality insulation, triple glazed windows, Mechanical Ventilation Heat Reduction (improved air tightness and high efficiency lighting. Energy modelling has indicated that fabric and systems energy efficiency measures, low carbon heating, as well as PV systems have the potential to make an improvement on Building Regulations Part L1A 2013 of 84%.; 39: 10400000; 40: 6793288; 41: 7637658.5; 42: 264385; 43: 0; 44: 0; 45: 7902043.5; 46: 1445103.57; 47: 6337353; 48: -1300305.5; 51: 677032; 52: 807351; 53: 0; 54: 412647; 55: 807351; 56: 0; 57: 1219998; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 75: CDM checklist refreshed ahead of SoS (and after site compound established); 77: Arcadis; 78: Life Build; 80: Yes; 82: Demolition of existing assets (Underway - Oct 22 - but full demolition now delayed to Feb 23, and now Oct 23) - Oct 23 - Complete; 84: 100k (est. - demolition x 2); 95: 44510; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - 2 small sites. Many dependencies re community reprovision that risk delay; 105: City Council; 106: Application Approved; 107: 26; 108: 12; 110: 14; 116: No; 117: 26; 118: 26; 119: 1900-01-25; 120: 2020-03-27; 121: 2020-07-01; 122: 2022-11-14; 123: 2020-12-31; 124: 44804; 125: Planning approval; 126: 20/00994/CT3 (Collins Street) 22/01128/VAR (Princes Street); 132: 2025-09-26; 133: 2020-03-27; 134: 44573; 135: 45251; 136: 45373; 152: 26; 153: 12; 155: 14; 188: Off Target; 190: Off Target; 193: Off Target; 196: At Risk; 199: At Risk; 202: At Risk; 205: At Risk; 208: On target; 211: Off Target; 213: Tender responses have been received and are being evaluated. Aiming for contact award on 14th Nov 22. 18/01/23 - Contractor Selected 09/05/23 - Contractor selected, contract to be finalised. ODS revised demolition programme on track. May 2023 - Legal turnover so all JCT amendments remain ongoing. 22/06/23 - Arcadis and ODS working to commence/finish demolition asap. There is potential for delays to impact HE 1 October SOS milestone. 26/06/23 - HE SOS of 1 October. Nearly there with housing contract. Still a question mark over demolition timescales. 7/7/23 - change to forecast build contract now 28/07/23. Planning risk change to Amber - no issues identified re conditions (except condition 4 at Collins Street may need review at a later date). CIL exemption advanced (awaiting forecast commencement date to issue final proforma) and s73 initial preapplication advice provided. Application to register Collins Street as a community asset is being explored. 02/08/23 - ODS demolition completed at Princes Street - Collins Street to follow on 14th August subject to court proceedings outcome. 21/08/23 - some concerns around QBT as contractor 07/09/23 - ODS demolition completed at Princes Street - Collins Street underway. Contractor not yet in contract. 14/09/23 - change of milestone dates as per revised programme - these differ slightly from new IMS dates to allow a buffer. Change in contractor with contract forecast date at end of Sept. Conversation with Valerie at HE and change of dates on IMS. 03/10/23 - Switch of contractor, not yet in contract although contract negotiations underway. Site appropriated into HRA. Indemnity insurances put in place for historical restrictive covenant. 30/10/23 - 1st November target for build contract 3/11/23 - build contract for signing 15 Nov. ODS demolition completed at Princes Street - Collins Street delay given asbestos found in the ground (awaiting removal). 21/11/23 - Build contracts signed and sealed 27/11/23 resolution to compound/site issue 11/01/24 - Demolition on both sites complete. Pre-construction activities underway. Latest contractor report available and all going well. Expected to meet March 22 SOS. 29/02/24 - onsite in three weeks - confirmation re location of site compound and discharge of pre-commencement conditions. 05/05/24 - Start on site made for HE grant claim at both Princes Street - & Collins Street. Issue relating to logistics plan/site access at Princes Street needs to be resolved with ODS/highways otherwise there will be programme delays and additional prelim costs. Collins Street groundworks to commence 8th April onwards, compound location to be resolved. 29/05/24 - significant issues re rejection of construction management plan and delay to Princes Street SOS - change to RAG status/time delay now Red 26/06/24 - further delays to CC so Princes Street prob can't progress until 9 Sept. AS taking paper to DB- either housing or CC go ahead. Lifebuild and ODS providing costs and programme info. Potential 22 week delay. But PC date brought forward 3 months to June 2025 02/07/24 - Coordination meetings taking place between all parties and community centre development may stand-down to allow Princes St residential to start in July'24. 19/07/24 - change to Red RAG status 14/08/24 - Princes - Works on site are on hold due to logistics plan/site access issues in front of Community Centre (CC) development. Working towards SOS 23 Sept'24. Programme delay and additional costs will be incurred. Collins - works progressing on site. Brickwork is progressing well on site and up to 1st floor with PC floors in. 19/09/24 - works c.3 weeks behind at Collins Street due to inclement weather, Lifebuild making good progress. Botb projects f/c PC Sept 2025. Arcadis as Project Coordinator has improved things.; 214: 43958; 215: 44112; 216: 45274; 217: 51.7481; 218: -1.2398; 266: Alto; 277: N/A - SDS agreed; 278: 45383; 281: 1491000; 282: 7500000; 283: 0; 288: 1572000; 289: 1231995; 290: 7587005; 292: 1400000; 293: 10391000; 294: 292258; 295: 10683258; 296: 4191250; 297: 5.34; 298: 30; 299: 3184774; 300: TRUE; 305: 86781 | 1572000 |  |  | 70% reduction on 2013 Building Regs | B | 2013 | No | Car free | Yes | Yes | Yes | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Acquisition of Additional Housing Units | Purchase of additional housing (9 units) on a 'turn-key' basis from the developer (Cantay). | N7051 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | Will McKay |  | Dave Scholes |  | Completed | Acquisition of 9 units (off-plan) - Only £25k retention left in budget as required. |  | 44408 | Payment of final retention sum (£25k) in Qtr 2 22/23 - To be actioned (Oct 22) |  |  |  | 24: On target; 25: On Budget; 26: Completed; 27: Low; 28: Low; 30: Acquisition of 9 units (off-plan) - Only £25k retention left in budget as required.; 33: Construction issues mitigated by the employment of a Council clerk of works to regularly inspections and reports on issues and progress to the PM in the construction phase.; 34: None, other than financial adjustments required to reflect the position of the project being on track to budget and time. Overall Project Spend: 20/21: £553,500 21/22: £3,018,000 22/23: £25,000 Total: £3,596,000 Budget: £3,645,000 (original budget £3.2m plus £445k from N7047); 37: New Build - As per Building Regs; 40: 3000000; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45562.4967 | mmcfarlane@oxford.gov.uk
HRA Stock Condition Survey | Identify the condition of HRA stock along with analysis of the performance of the stock, to inform the Housing Asset strategy. | N7052 | Development Board |  | Communities | Housing - HRA (Property) |  | Capital Delivery |  | Nerys Parry |  |  | Mark Smart |  | Luca Minetola |  | Delivery | 4,118/7,888 (52.2%) of HRA dwellings surveyed |  | 45747 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: N/A; 28: N/A; 30: Tender awarded for first 3000 homes and all blocks. Please note that budget is stuill required for remaining 5000 homes which has not beeen allowed for; 40: 400000; 41: 728572.9; 42: 200000; 43: 0; 44: 0; 45: 928572.9; 46: 106772.59; 47: 728572.9; 48: 0; 54: -200000; 55: 0; 56: 0; 57: -200000; 80: No; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45557.5863 | mmcfarlane@oxford.gov.uk
Properties purchased from OCHL | All affordable homes purchased from OX Place into the HRA - This is currently a programme 10 schemes delivering c. 870 homes. | N7054 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Dave Scholes |  | Other Capital Spend | The June 24 appraisals show a significant increase in OX Place costs, but most of these increases have not been passed onto the HRA. The HRA appraisals show c. £14m more possible spend. Most significant is a c. £16m increase in costs (and numbers of units) at R/B, but Sandy Lane Rec has seen a £2m decrease. For the purpose of this monitoring however, the current (Feb 24) MTFP budget is used, so the spend forecasts at Redbridge have been decreased proportionately in each year to reduce the overall budget forecasts by £14m. There are high levels of spend certainty with 3 (of 10) schemes, comprising c.17% of the overall budget, that are in delivery or expected to be soon, and where delivery risks are low. These schemes comprise of 100% of the spend forecast in 24/25 and 75% of the forecast in 25/26, so slippage in these two years is expected to be minimal. 3 of the schemes are targeting planning committee approval in the next 4 months. 3 already have consent and one is awaiting the s.106 only. The remaining 3 schemes are the largest schemes in the programme - all forecast in the later years of the programme with £222m spend (62% of this budget). There has been considerable slippage in programme dates with many now revised. The larger schemes are now forecast to run to 2031/32. |  | 48299 | Collaboration Agreement and associated documents, esp Development Agreements and Delivery Strategy (per scheme); plus Payment Schedules to be developed and agreed. | Continued management of schemes (4 re remaining 23/24 completions/ payments) and then from April 2024 on, 10 schemes in programme. | Negotiation on schemes with OX P to ensure viability but also V4M for the HRA. |  | 24: On target; 25: On Budget with slippage; 26: On target; 27: Medium; 28: Medium; 30: ""• Slippage by the following schemes: Barton 3B; Meadow La; Railway La; Westlands; MLM; Bertie; Goose Grn: and 25 Westlands. • £6.5m in profiled spend re Marston Paddock is b/f from 24/25 in anticipation of the Golden Brick transaction in Mar 24 (so to note that this spend in due in the last month of the year). • Some spend still profiled in 23/24 is still as risk of further slippage: o High Risk: £6m from Meadow Lane (£5.2m) and Bertie Place (£763k) – both due to planning risk. o Medium Risk: £6m Railway Lane – delivery risk with developer (including discharge of all pre-commencement planning conditions)""; 33: Developing more rigour to the business plan re capital spends; 34: Meetings set up with OX P to review schemes where new appraisals give cause for concern, inc Westlands and Redbridge. Programme manages scheme delivery by exception through HSB (and then to Devt Board).; 40: 83684822; 41: 23911742.39; 42: 42139726; 43: 46264902; 44: 39787056; 45: 152103426.39; 46: 7943216.04; 47: 23911742; 48: -0.39; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Slippage of some schemes in programme into later years; 51: 42139726; 52: 46264902; 53: 39787056; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 70: No CDM Client role - Advance sale agreement (covered in Collaboration Agreement); 75: No CDM Client role - Advance sale agreement (covered in Collaboration Agreement); 77: NA - Programme of projects and sites; 78: NA - Programme of projects and sites; 80: No; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45557.5863 | mmcfarlane@oxford.gov.uk
Goose Green Close (land to rear) | 31-unit mixed scheme - now 28 units. Further reduced to 24. | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Vicky Treitline |  | Vicky Trietline |  | Design & Specification | [7 empty] | 30: Planning committee in Sept - consent subject to s106. PC date pushed into next financial year.; 31: KEY ACTION: Response to OCC on Thames Water sewage treatment works non-occupation clause - review date 28 Oct Aiming to finalise legal agreements Land transfer agreement remains under negotiation Access from TWO adjacent site subject to payment negotiation; 33: Technical risk being mitigated through a range of surveys Planning approved subject to s106 (Sept). EA has imposed a Grampian planning condition on the scheme limiting occupation until such time that the sewerage treatment works have been upgraded. Build cost inflation or sales values impacting commercial negotiation until DA is signed - prices to be fixed where possible. Potential for community support risk - adequate local engagement in planning process. Community/councillor engagement reducing risk, scheme generally supported Access issue with adjacent s106 - legal advisors appointed for all title and legal actions Associated delays from risks monitored closely - Delay risk as multiple legal contracts to be aligned at the same time. Land transfer must happen before planning consent - Ensure internal processes/ sequencing is managed and issues escalated where needed. Moved to Red following Grampian condition.; 37: TBC but anticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 39: 3440000; 40: 0; 41: 581746.12; 42: 0; 43: 0; 44: 0; 45: 581746.12; 46: 0; 48: -581746.12; 54: 0; 55: 0; 56: 0; 57: 0; 77: Thornton Firkin (until point of construction); 78: Hill; 95: 45000; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 1; 105: City Council; 106: N/A; 107: 24; 108: 9; 111: 3; 113: 12; 116: No; 117: 12; 118: 24; 119: 1900-01-23; 122: 2021-02-26; 123: 2021-04-08; 124: 44862; 125: Approval subject to s106; 126: 24/00318/FUL; 128: 2024-12-10; 129: 2024-07-17; 130: 2024-12-01; 131: 2025-04-01; 132: 2026-07-30; 133: 45329; 134: 45552; 159: 12; 160: 9; 163: 3; 188: Off Target; 190: At Risk; 193: At Risk; 199: Off Target; 202: At Risk; 205: At Risk; 208: At Risk; 211: Off Target; 213: Project on hold since Summer 2020. Nov 22 - Approved into AHP at HSB & into Capital Spend Programme at DB. 15/12/22 - no update 18/01/23 -Cabinet approval to land transfer and buy backs due March 2023 .Legal advisors appointed Dec 2022. 18/02/23 No update 5/6/23 HoT for DA signed w/Hill. Contract to be negotiated. Hill to Commence pre app work June 2023. Access agreement to be negotiated before Sept 2023. Land transfer agreement b/t OX Place and OCC.Hill understand planning matters on the GG site. They have a strategy for exceeding the 'cap'. Pre app starts June 2023 26/06/23 - Planning submission date may be revised back from Sept. First Homes remain in planning but being reviewed. 3/07/23 - no update 04/08/23 - F/c tender award/CSOS pushed back slightly in line with OX P. 10/09/23 - F/c planning submission date pushed back 2 months to Nov with f/c PC date also pushed back one month. 14/09/23 Forecast planning pushed back a month to Dec. Build contract pushed back a week, SOS pushed back a month and PC pushed back a quarter to End of March 2026. 03/10/23 - Milestones pushed back – numbers TBC as currently in discussions with planning. Hill doing pre app/consultation work currently. Pl app to be submitted by Dec 2023. Access agreement with TWO to be negotiated before Dec 2023. Land transfer agreement being negotiated between OX Place and OCC 23/11/23 - HOTs reissued Nov 23 (not signed yet). Pre-app consultation took place Nov 23. F/c build contract signing pushed back 4 months to 18/04/24 27/11/23 - Planning to be submitted shortly. Consultation event went well. Thomas White Oxford - issues with access to be resolved. Reflection on First Homes 9 Jan - Planning app pushed back to 12 Feb (from end of Nov) 11/01/24 - HoTs to be reagreed following unit number change. Access agreement/payment with TWO to be negotiated before Jan 24. F/C dates pushed back 3 months e.g. planning consent now end of Aug, SOS now end of Oct 24. But PC date brought forward to Dec 25. No further money required this year. Hill currently funding. Going into planning any day. Will need to secure land transfer in advance of planning consent. 29/02/24 - in planning - planners thought to be ok with it. Still negotiating re TWO - offer submitted 2 weeks ago. Hill have retracted their offer to TWO for land. Finance risk moved to At Risk. 06/03/24 - F/C SOS pushed back 4 months/F/C PC pushed back 4 months to Mar 2026. Pl app consultation currently ongoing. Access agreement/payment with TWO to be negotiated before end Mar 2024. Land transfer agreement being negotiated between OX Place and OCC to complete Mar/Apr 2024 25/03/24 - Build contract April 2024, SOS Jan 2025 (PG) 04/04/24 - f/c CSOS pushed 1 mon to end of May 24 03/06/24 - Planning app due to go to Committee July / Aug 2024. HoT agreed on DA with Hill - draft contract being progressed. Access agreement/payment with TWO agreed in principle - HoT to be negotiated by June 2024 Land transfer agreement being negotiated between OX Place and OCC, must happen June 2024. Tender award date (and other F/C dates) pushed back 26/06/24 - Land purchase anyday, F/C sos will come out when we issue the Abovo. Need to get legal docs agreed (steer from EG) before committee dates confirmed. 02/07/24 - Planning app due to go to Aug committee. HoT agreed with Hill, draft contract progressing. Draft legal contract by July. Land transfer ag being negotiated - must happen August. 19/07/24 - f/c build contract pushed back a month Sept 24. F/c SOS and PC pushed back 3 months to April and June 26. 28/09/24 - planning subject to grampian condition/sewage issue Thames Water. 04/10/24 - OXP presentation lists PC date as April 2026 - milestone aligned but waiting confirmation from VT 11/10/24 - approach to planning to remove non-occupation clause. Aiming for planning and CSOS by end of 2024. F/c CSOS and PC pushed back 3 months to Dec 24/Jul 25 but SOS remains the same. Approx 1 year build.; 214: 44881; 217: 51.7862; 218: -1.2869; 232: 6; 234: 3; 237: 2; 270: TRUE; 277: N/A - SDS agreed; 281: 560000; 282: 2750000; 283: 435000; 284: 1093500; 285: 220338; 288: 0; 289: 0; 290: 3340000; 291: 3340000; 292: 0; 293: 3340000; 294: 58266; 295: 3398266; 296: 5775000; 297: 5.03; 298: 39; 299: 1795132; 300: TRUE; 303: N/A |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 | Yes | No | Yes |  |  | 1 | 45576.0815 | mmcfarlane@oxford.gov.uk | Y | 45557.5863 | mmcfarlane@oxford.gov.uk
Mill Lane, Marston (Almonds Farm/ Land West of Mill Lane) | 80 unit housing development scheme | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Vicky Treitline |  | Vicky Trietline |  | Design & Specification | [7 empty] | 30: Work with EG and legal on securing legal agreements and tender process; 31: KEY ACTION: Tender to go live (was originally due Feb 24) - review date 16 Oct Revisiting Stamp Duty discussion Submissions to Homes England currently on hold - more detail mid-November Legal agreements between OCC and OCHL being progressed.; 33: HE aware of delay to submission - further information on site provided in Sept, no info expected from HE until end of Oct Inflation build costs are a risk until contract is confirmed Further surveys (subject to award of contract) needed to better inform costs and programme Planning: JR now quashed so planning consent not at risk, save for obtaining s73 consent.; 37: TBC but anticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 39: 37950000; 40: 60000; 41: 207021; 42: 60000; 43: 75000; 44: 60000; 45: 402021; 46: 0; 48: -207021; 54: -60000; 55: -75000; 56: -60000; 57: -195000; 77: Thornton Firkin - contractor takes this role once contract signed; 78: To be appointed; 95: 44664; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 112b1; 105: City Council; 106: Drafting Bid; 107: 80; 108: 32; 110: 48; 113: 0; 116: No; 117: 80; 118: 80; 119: 1900-03-20; 120: 2021-01-10; 121: 2021-06-13; 122: 2021-08-08; 123: 2023-07-01; 124: 45717; 125: Planning approval; 126: 21/01217/FUL; 128: 2024-11-29; 129: 2025-03-30; 130: 2025-03-29; 131: 2025-07-15; 132: 2027-07-26; 133: 2021-04-29; 134: 44645; 166: 80; 167: 32; 169: 48; 188: Off Target; 190: At Risk; 193: At Risk; 199: Off Target; 202: On target; 205: On target; 208: At Risk; 211: Off Target; 213: Planning 'resolution to grant' subject to s106 received October 2021, s106 being negotiated. Build contract procurement tenders received 15 Dec, and being evaluated. Legal advice being provided on termination of tenancy on land. Aim to award contract by end March 2022 and SOS Aug 2022 18/10/22 - Planning consent obtained March 2022, JR hearing due Autumn 2022. Contractor selected on hold due to JR. JR date - Feb 2023. Contract documents nearing agreement. Notice To Quit is currently in arbitration proceedings. 15/12/22 no update 18/01/23 - Contractor selected but award on hold due to JR. April 23 - change to Red RAG on planning and time delay. May 2023 - still on hold. Build price has increased - discussions ongoing. Not in contract. June 2023 - JR hearing 1 Feb 2023, but decision still awaited. Lease surrender agreed with tenant, and completed end Feb 2023. Contractor selected (Equans) but revised financial proposal being discussed with EA to ensure Value for Money. 26/06/23 - November SOS but JR remains issue. JR decision expected in Sept which will push back milestone and payment dates. 3/07/23 - milestone dates moved back a month. OXP board approval for Equans contract but revised financial offer made since, which is being evaluated and discussions held. RAG - Tech Amber: Contractor to do surveys if/when contract awarded. This will better inform the costs and programme. Time delay Red: JR held 1 Feb 2023 - but decision still awaited. Mitigation is trying to prepare all contracts both with Equans (and settle price) and OCC/ OCHL in the meantime. Also time risk if Equans cannot provide acceptable bid price, and further procurement of a contractor is required. 7/9/23 - JR in favour of development but with Court of Appeal. HE grant/s106 issue. 14/09/23 - F/c CSOS pushed back 2m to Dec 23. 22/09/23 - F/c PC pushed back 1m Dec 25 04/10/23 - F/c SOS pushed back 2m May 24. High court dismissed JR appeal. Scheme can progress subject to clearing/s106 obligations. 30/10/23 - dialogue w/Developer Thomas White Oxford 23/11/23 PCSA being prepared with Equans. Limited PCSA Oct - Dec, prior to planning to allow formal build contract to be signed/ F/c SOS brought forward to 01/05/23; f/c build contract pushed back 4 months to 1/4/24. Dec- Feb : PCSA activities Jan '24- April '24: Clear planning conditions Jan - March '24 : revisit old (Arcadis) JCT and agree terms Feb '24 - submit s73 Pl. App. end March '24 : Confirmed pricing April '24 : Enter JCT May '24 : On site 27/11/23 - PCSA imminent 03/12/23 - Concern around Equans 07/12/23 - F/c SOS & PC dates pushed back - PC date very close to end of HE AHP 11/01/24 - EA to run 12-week tender from Jan 24 following parting w/Equans due to changing bid terms. EA to run PCSA process Jan - May 2024. Tender go 'live' Feb 2024, close date April/May 2024. Needs PC Q4 25/26 for HE funding. Timelines on IMS bid to be confirmed once certain on price. 29/02/24 - retender next week-ish. Tender award in May. When price back/acceptable then change to amber. Equans may tender 25/03/24 - Sign contract in Aug (pushed back from Apr) then SOS in Dec (PG) 29/05/24 - standard tender docs under review. Tender for end June w/bids back early Sept. F/c dates pushed back with delay to SOS beyond HE programme dates. S73 consent to be obtained, submitted May 2024 04/06/24 - latest update on CSOS is Nov '24. SoS Mar 2025. 19/06/24 - F/C SOS pushed back 2 months to May 25 26/06/24 - Tender (July - Sept run by EA) and s73 needed (submitted May). Legal agreements needed (input from EG). Ivona involved. AS to flag if SDLT an issue. 2-year build- PC pushed back 3m to May 27. May drop out of AHP/OCHL proceed at risk. Need HE conversation on grant. 11/09 - F/C dates pushed 3m - tenders back Dec 24, CSOS Feb 25, SOS July 25 04/10/24 - awaiting update from VT - OXP presentation puts PC at Summer 27 11/10/24 - Tender live next week, s73 in 4 weeks, F/C dates pushed 1-2m. 21 month build. PC summer 2027. Land transfer happened.; 214: 44881; 217: 51.7825; 218: -1.2497; 232: 13; 234: 10; 235: 8; 238: 1; 250: 13; 270: TRUE; 271: 44645; 273: TRUE; 277: N/A - SDS agreed; 281: 4695547; 282: 23700000; 283: 350000; 284: 1295812; 285: 688942; 287: 6019699; 288: 5120000; 289: 5520000; 290: 26910000; 291: 36750000; 292: 800000; 293: 37550000; 294: 618349; 295: 38168349; 296: 32720000; 297: 4.41; 298: 37; 299: 6375605; 300: TRUE; 303: N/A |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 | Yes |  |  |  |  | 1 | 45576.0815 | mmcfarlane@oxford.gov.uk | Y | 45557.5863 | mmcfarlane@oxford.gov.uk
Tucker Road | Demolition of garages and construction 3 x 2-bed houses for rent | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Delivery | [7 empty] | 30: Homes are physically complete but awaiting necessary paperwork re window fittings (Sips panels/air tightness); 31: KEY ACTION: Secure outstanding collateral warranties and take handover - review date 16 Oct Handovers currently expected in November; 33: Time delay risks being closely monitored - currently completing Q3 2024/25; 37: MEV ventilation; 39: 996000; 40: 0; 41: 385229; 42: 0; 43: 0; 44: 0; 45: 385229; 46: 0; 48: -385229; 54: 0; 55: 0; 56: 0; 57: 0; 77: Ridge; 78: ODS; 95: 44083; 96: Cabinet Decision; 99: Year 4; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 106: N/A; 107: 3; 108: 2; 109: 1; 116: No; 117: 3; 118: 3; 120: 2020-09-01; 121: 2021-01-17; 122: 2021-03-01; 123: 2021-04-01; 124: 44655; 125: Planning approval; 126: 20/02653/CT3; 132: 2024-10-28; 133: 2020-10-21; 134: 44256; 135: 44500; 136: 44630; 145: 3; 146: 2; 147: 1; 188: Off Target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: Off Target; 213: Detailed design work is ready for approval, ground survey report due 7/2. Scheduled demolition is to start 28/2. CSOS AND SOS NOW ACHIEVED?? AH comments 30/05/22 - this row has been accidently deleted from the sheet and so info has been lost and not up to date. Put back in according to report from March. JG update 30/04/22: forecast completion in November 2024 due to a minor but unavoidable planning issue. JG update 31/05/22: Planning are still dealing with pre-commencement condition discharge, plus there was a discrepancy in the planning submission which I have spoken to Planners about today, and hope to resolve this week. 15/12/22 foundations are done with block and beam flooring next 17/02/23 No further Updates 05/05/23 Frames are up. Roof tiles due to be delivered 15/5. Solar panels fitted. Updated programme due. Notice of non completion to be issued. 26/06/23 - Handover moved back to end of October due to ODS issues. 01/08/23 - Change Time Delay to At Risk: Monthly meetings, significant delays due to supply chain issues, and labour shortages. 03/08/23 - Change to Forecast PC - pushed back one quarter as per OX P smartsheet 03/10/23 - Progress continues, albeit slowly. Waiting for windows to be delivered. 30/10/23 - Issue with windows remains, concerns being addressed. Still expected to deliver in 23/24 but potential to be pushed back again. 23/11/23 - Unmapped utilities causing further delay. 27/11/23 - ODS targeting January - ODS issue 18/01/24 - PC date pushed back to mid-Feb (from end of Jan) 5/2/24 - sewer resolved. Groundworks, externals and final internals. ASHP due this week. 29/02/24 - struggling to get info from ODS - don’t know when ASHP are coming in. Helen has raised with Simon. May have to do an accrual. JG visiting on Monday. 06/03/24 - Landlord supply for sewage pump due w/c 26.3. No update on ASHP which is all that is preventing handover this month. 19/04/24 - Snagging underway w/c 15/4. Still waiting for landlord supply meter. 19/05/24 - landlord supply now installed 29/05/24 - physically constructed but James unhappy with paperwork so working with ODS on this. Issue re window fittings (sips panels/air tightness) awaiting update from ODS, may need to take out windows. And collateral warranties needed. 26/06/24 - AS may need support from DS. Warranties not forthcoming but ODS didn't sign the contract. 19/09/24 - Still awaiting warranties through ODS. Revised date of 28 October for PC.; 217: 51.725; 218: -1.2017; 232: 2; 277: N/A - SDS agreed; 300: TRUE; 303: N/A; 308: 150000 |  |  |  | Zero carbon regulated energy | B |  |  | No | Yes | Yes | Yes |  | 45575.3175 | rhaverson@oxford.gov.uk | N | 45555.3492 | mmcfarlane@oxford.gov.uk
Meadow Lane/ Church Way, Iffley | 32 units for an a mixed tenure all affordable housing scheme | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Kenny Phillips |  | Kenny Phillips |  | Design & Specification | [7 empty] | 30: Awaiting update re ecology planning consultation Efforts to secure alternative land not successful; 31: KEY ACTION: Resolution to outstanding ecology conditions to secure planning consent - review date 16 Oct Planning committee now revised to December 24 Tender and s73 required Progressing collab agreement Ongoing efforts to seek alternative land for nature habitat; 33: Planning submitted in Dec 22 with expected committee date now December 24. Ongoing issues with ecology/loss of habitat. As directed by the LPA during the pre-planning consultation. Currently not supported by Ecology Officer and it is likely that it will not be supported. Build costs have risen since scheme approval. Planners requesting material changes - will impact costs: Recent Abovo has been updated to include an uplift in the build costs given this plus delays to the scheme. Risk re s106 all affordable/ HE grant Scheme does not have full community support but has changed to all-affordable and continued engagement planned. Likely to be community objection due to greenbelt/ecology concerns - Comms consultation to take place between May -Sept 24. Also a concern around Councillor support - ecology reports to mitigate against loss of habitat; 37: Not permitted solar PV by planning TBC but aniticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with panel heaters in flats and ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 39: 18338000; 40: 0; 41: 586178.52; 42: 0; 43: 0; 44: 0; 45: 586178.52; 46: -66509.61; 48: -586178.52; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45000; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 389; 105: Private; 106: HE Programme; 107: 32; 108: 19; 110: 13; 116: No; 117: 32; 118: 32; 119: 32; 124: 45373; 125: Planning application submitted; 126: 22/03078/FUL; 128: 45636; 129: 45777; 130: 45791; 131: 45900; 132: 46357; 133: 44923; 152: 20; 153: 12; 155: 8; 159: 12; 160: 7; 162: 5; 188: Off Target; 190: At Risk; 193: On target; 199: Off Target; 202: At Risk; 205: On target; 208: On target; 211: At Risk; 213: 100% AH agreed by OCC. New scheme to be prepared. The scheme is almost ready for a planning application submission. It is likely to be submitted before the end of October 22. Currently for 32 homes. *Planning App to be submitted before end of Nov 22 17/05/23 Cllrs may not support the scheme despite LPA rec. to approve due to opposition by local community. Aiming for July Cttee but may be later if LPA needs more consultation. More ecology reports are being prepared for Ecologist (Tristan) on loss of habitat and poss loss of wildlife. Red RAG on time. May 2023 - invertebrates need rehoming, more survey work ongoing. 18 July planning meeting (or poss August) 26/06/23 - SOS and PC dates pushed back at EOQ1 OXP meeting. Ecology remains an issue - possible to use Bertie Place site to locate some invertebrates. 04/08/23 - Aim for Oct Cttee but this may be pushed out if the LPA needs more consultation. More eco. reports being prepared in response to Ecologist comments on loss of habitat /dealing with poss loss of wildlife if dev. goes forward. 7/9/23 - Ecology issues remaining plus materials, RVIA and section 106 concerns/HE grant. New contract figure has been received resulting in a process of value engineering. 22/09/23 f/c PC date pushed back 2 months Dec 25 03/10/23 - most milestones pushed back 1 - months due to planning. Reduces spend in this financial year against forecast position. 30/10/23 - Resubmission of planning re AH requirements (option A/B) and ecology. £5m has been reprofiled to next year - in new budget. 07/11/23 - F/c pl. consent and CSOS dates pushed back 6 weeks to Dec/end of Jan 24 respectively. 23/11/23 - f/c build contract(/SOS and PC dates) pushed back 4 months to 30/04/23. 27/11/23 - planners unsure about moving invertebrates to Bertie Place - consider SSSI at Redbridge instead? Planning are very cautious about this site 05/12/23 - Now aiming for March 24 committee hearing but may be pushed back if further consultation needed from LPA. 11/01/24 - Pln consent F/C date pushed back a month to end of April. SOS pushed back a month to Oct 24. In resi consultation now. This is excluding ecology which is being looked at shortly. March Planning Committee expected. Planners re-consulting on ecology so another 2 week window. Tristan doesn’t agree with Bertie Site B as a mitigation site. 29/02/24 - Meadow Lane all revised surveys and plans submitted to M Kemp and Tristan – papers to be advertised for consultation next week until 27 March. Will go to 21 May planning committee. Don’t have ecologists support at this point. He will maintain objection but might be a soft objection. Council will progress s106 in background. Contractor already appointed. 21/03/24 - Another round of consultation after elections with planning authority. This will be the final scheme. Got mitigation sites for the wildlife - moving the badger sett and building a new one. June committee hearing. Cannot have PVs according to planners because of the heritage of the village but will be PV ready in case this changes in the future. 04/04/24 - F/C planning consent and build contract dates pushed back e.g. CSOS 31 July 24. 03/06/24 - ongoing ecology issues - planning pushed back to Aug (TBC) Ecology (invertebrates) remains an issue. AM to test new approach internally. Potential impact on dividend. 26/04/24 - Collab ag and looking at procurement strategy. Ecology gone as far as it can. Won't meet all objections. If it doesn't get planning, won't get developed. Prob Aug for Planning. 19/07/24 - pln determination likely Oct. More ecology report submitted July 26/07/24 - F/c milestones inc PC date pushed back 9-10 months (PC Dec 2026) 06/08/24 - f/c planning consent date pushed back 2 months to Dec 24 delivery. Nov planning com. Abovos have 2 options: w/wout JR. 2-yr build programme 13/10/24 - Sent update request to the LPA in Oct - they are still waiting for response from EA. Planning could be Dec/Jan 16/10/24 - Approved at Cabnet; 214: 44335; 217: 51.7324; 218: -1.2376; 220: 4; 222: 4; 234: 4; 238: 4; 243: 3; 250: 2; 251: 2; 252: 1; 270: TRUE; 277: Yes - draft SDS; 281: 4500000; 282: 9995000; 283: 60000; 284: 797215; 285: 291429; 287: 2441356; 288: 2455000; 289: 1023250; 290: 15254977; 291: 18085000; 292: 648227; 293: 18733227; 294: 346051; 295: 19079278; 296: 17344250; 297: 0; 298: 80; 299: -13247636; 300: TRUE; 303: N/A |  |  |  | 40% reduction on 2022 Building Regs |  | 2024 | Yes | No | Yes | Yes | No | 1 | 45582.0908 | mmcfarlane@oxford.gov.uk | Y | 45557.5863 | mmcfarlane@oxford.gov.uk
Marston Paddock | Developer-led opportunity with the Lucy Group to acquire 40 homes for affordable for the HRA in Old Marston | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  | TBC Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | [7 empty] | 30: Work onsite progressing well; 31: KEY ACTION: Close monitoring against handover date - review date 25 Nov; 33: Now in contract and on-site Unadopted road raised as possible issue Working to minimise community risk If the scheme is delayed it will postpone when payments from the HRA are received. Contractor currently reporting possible delay due to steelwork delivery issues, but PC has not to be altered yet.; 37: A ‘fabric first’ approach means enhanced insulation and air tightness standards and high-performance windows. Air source heat pumps will provide heating and hot water. Mechanical ventilation heat recovery will reduce energy use by recycling heat from stale moist air as it is extracted. Fishers Vale is expected to go 56% beyond national carbon reduction targets – exceeding our planning requirement for a 40% improvement on building regulations. Solar PV panels are not included. They would affect the character of the conservation area.; 39: 23228500; 40: 0; 41: 250855.63; 42: 0; 43: 0; 44: 0; 45: 250855.63; 46: 2897.61; 48: -250855.63; 54: 0; 55: 0; 56: 0; 57: 0; 77: Lucy Developments Ltd; 78: Lucy Developments Ltd; 95: 44909; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 114d; 105: Private; 106: Application Approved; 107: 40; 108: 21; 110: 19; 117: 40; 118: 40; 119: 40; 120: 44469; 123: 44835; 124: 45474; 125: Planning approval; 126: 21/02580/FUL; 132: 45930; 133: 44460; 134: 44764; 135: 45236; 136: 45425; 152: 40; 153: 21; 155: 19; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Full planning permission approved - 21/02580/FUL - MK Planning Officer) - Land Ownership is Aubrey-Fletcher/ Wick Farming Ltd. Resolution for approval passed at March committee, 50% affordable, S106 in draft at the moment,comments provided. Lucy's are the developers. All the affordable units are M4(2) compliant, and plot 12 is designed to M4(3). With regard to the market element, Plots 5,6 and 36 are M4(2) complian The latest estimate we had for a start on site (based on a section 106 in March) was October, this depends on the section 106 timings and the discharge of any conditions/obligations, but are preparing to be on site as soon as possible. Call Thomas Corbin at Priors, understood RP bids have been received by SOHA & Sovereign. 19.05 2022 - S106 APPROVED and signed 22.07.2022. Approved into programme as 100% affordable 40 homes at HSB (Nov 22) and into Capital Spend programme at Devt Board (Nov 22) Indicative commencement on site is Jul 23, Golden Brick Jan 24, with PC Dec / Feb 26. 10/05/23 - Ongoing work on legals and design of homes ahead of planning amendment submission. Progressing DOV with OCC lawyers re 100% affordable site. 23/05/23 - Concern about SSE issue, letter from CG and HH to SSE next week and impact on PC date and HE programme. 26/06/23 - Aiming to be in contract in next month or so. 3/07/23 - Forecast PC pushed back a month 21/08/23 - DOV has been drafted and is out for comment. Tenure plan has been requested. 05/09/23 - forecast SOS moved back from 1 March to end of May 24. No longer aligns with HE milestone date. 22/09/23 - F/c build date pushed back 2 months to Oct 23. 03/10/23 - Ongoing work on legals - contracts, DOV (100% affordable site), planning amendment close to agreement. Contract signing imminent. S73 expected 14 November. Paper required for delegated authority. 30/10/23 - SOS needed for end of March - should be ok and in discussion with EA on this point. s106 signed. 3/11/23 - Ongoing work on legals - contracts are imminent, DOV (100% affordable site), planning amendment close to agreement. 9/11/23 - contracts confirmed as signed/exchanged - contract completes at golden brick subject to conditions (including planning conditions) being met 17/11/23 - request submitted to Homes England to delay SOS/Golden Brick date until 1 July 2024. 27/11/23 - meeting on site taking place in December. S73 taking longer and needs to be in place to discharge planning conditions. 28/11/23 - DOV signed by City (17/11) but not County. Pre-GB site works started 11/23 18/12/23 - DOV agreed and being engrossed. Completion in Jan w/s73 to follow. 11/01/24 - On track to achieve HE Golden Brick. No change to cashflow. SSE needs long lease for a substation. 5/2/24 - Ground works started on site. 29/02/24 - DoV ready for signing but refers to OCHL not OCHDL. Has been returned to legal on that basis to seek new signatures. Change Community issues to Green. 13/03/24 - DOV to be signed March 2024 - awaiting delegated decision 25/03/24 - on site, pre-commencement works April - DOV signed and sealed, likely for GB date to be brought forward 05/06/24 - Works progressing well - foundations in, slabs, brickwork progressing well. Golden Brick achieved and land/development transferred to OCC - contract completed. HE grant drawn down. 26/06/24 - All good on site. F/C PC currently Sept/before longstop date. Query over which date to use. 14/08/24 - Works progressing well - brickwork progressing well to all blocks and up to 1st floor level with floor joists going in. Onsite mains laying complete, water and elec. Hoarding has been erected and Oxford Needs Homes boards to be added. 02/09/24 - Steels have been fitted to 25% of plots. Services offsite works complete and substation installed. 19/09/24 - still on programme for Q2 24/25 but may move to early Q3 24/25 - steel supply/mains water issues; 214: 44881; 216: 44893; 217: 51.7771; 218: -1.2356; 220: 6; 221: 8; 237: 2; 239: 5; 266: Fisher's Vale; 270: TRUE; 271: 44764; 273: TRUE; 274: 45400; 277: N/A - SDS agreed; 281: 6277872; 282: 11722128; 283: 0; 284: 1526967; 285: 33576; 287: 2439457; 288: 2520000; 289: 3127500; 290: 17581060; 291: 22000000; 292: 1228560; 293: 23228560; 294: 818708; 295: 24047268; 296: 74; 297: 4.05; 298: 46; 299: 2492874; 300: TRUE; 304: 45425 | 2520000 |  |  | 40% reduction on 2022 Building Regs |  | 2022 | Yes | TBC | Yes |  | No | 1 | 45576.1632 | mmcfarlane@oxford.gov.uk | Y | 45557.6099 | mmcfarlane@oxford.gov.uk
Bertie Place | 31 affordable homes on Bertie Lane recreation ground | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Stuart Moran |  | Stuart Moran |  | Design & Specification | [7 empty] | 30: Approvals for October Cabinet report LPA have indicated that if the current EA objections can be addressed/removed, the application could be considered at November planning committee meeting.; 31: KEY ACTION: Resoluton to outstanding EA concerns and securing planning consent - review date 16 Oct Working with Arcadis to get costs reduced - though likely to go back for re-tender after planning confirmed. October cabinet for land appropriation includes CMT/Group Leaders November planning committee expected; 33: Planning not confirmed - likely Nov planning committee. EA have raised objections to bridge which remains that last objection for resolution. Rising build costs - being monitored and working to keeps within budget. Equans PCSA cost plan construction costs c.£1m over budget - intention to retender through competitive process. Appropriation of land to a planning purpose going to Cabinet in Oct - appropriation GF to HRA to follow before handover. Community opposition and potential for JR - ongoing engagement (particularly on play equipment) with community and Councillors. Opposition could impact on time delay - ongoing engagement and monitoring of programme. No known legal/land/title risk. Temp footpath closure during construction. Possibly a land risk on public open space. Further discussions with ward Members on third party issues. Land appropriation risk regarding the process of transfer subject to Counsel's advice. Ground contamination also a major risk; 37: TBC but anticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with panel heaters in flats and ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 39: 11408000; 40: 0; 41: 245000; 42: 0; 43: 0; 44: 0; 45: 245000; 46: 0; 48: -245000; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45147; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 8; 105: City Council; 106: HE Programme; 107: 31; 108: 22; 109: 0; 110: 9; 116: No; 117: 31; 118: 31; 119: 31; 120: 44911; 121: 45015; 122: 44440; 123: 45169; 124: 45504; 125: Planning application submitted; 126: 23/00988/FUL; 128: 45615; 129: 45717; 130: 45778; 131: 45870; 132: 46395; 133: 45051; 159: 31; 160: 22; 162: 9; 188: Off Target; 190: Off Target; 193: At Risk; 199: Off Target; 202: Off Target; 205: On target; 208: On target; 211: Off Target; 213: Public Consultation for Sept 22. Planning subm Jan 23. Appr. to continue Project, select partner, submit planning. Consultation closes 18/11. Procurement closes 11/11 Tender clarifications underway. Appointment of contractor Jan 23. Updated Members on consultation outcomes. Two Pre-Apps completed. Planning App Feb 2023. 18/01/23 - Young people's playground consultation 28/1. Planning app for Feb 23. 18/02/23 Equans appointed. Planning app Mar 23. 05/05/23 - Planning App subm 5/23. Equans undertaking further GI Surveys May 23. PSCA signed w/Equans 4/23. Red on planning, finance, community, time May 2023 - in planning, Aug com. - query over no. of 4-beds/2-beds. Need planning app for bridge. Aug cabinet for consultation on appropriation for bye-laws issue, licence to OX Place/dev agreement/appropriation from GF to HRA. 26/06/23 - Planning submitted and PCSA signed in April. App for bridge will be separate. Paper for Aug cabinet. 7/7/23 - Second planning app being worked up for bridge. Third party issues - still receiving objections from community. OXP board paper submitted for April 23. Further OXP board paper required for Aug for additional funds. Ground contamination a major risk. Red RAG on comm, planning and finance 11/7/23 - SOS pushed back to Feb 24 11/08/23 - Planning app now likely Nov. Approvals/app process approved Aug cabinet. Appropriation notices to be published. Potential grant issue with HE/100% affordable. 03/10/23 - most milestone dates pushed back 2 months e.g. f/c PC now Nov 25. Appropriation notices published. Spend moved to 24/25 – will be staged payments. SM drafting response on BLRF. 30/10/23 - Appropriation paper for submission to November Cabinet. Query over planning/footbridge. 6/11/23 - Second Planning Application being worked up for the bridge to be submitted in November 23. Meeting held with Ward Members to discuss Third party issues. Still receiving objections from the community. Planning app now likely Dec/Jan 27/11/23 - f/c planning, CSOS and SOS pushed back 6 months with planning consent now 1 April 24. Three key issues: Appropriation, planning for bridge and Equans. Seeking legal advice. 07/12/23 - Land app risk due to the Com. Report being placed on hold, pending Counsels advice. OXP Board approved further funding on 2nd Aug. Updated BLRF in Oct 23. 11/01/24 - Planning app for bridge submitted (app ref TBC). Awaiting Counsel advice on appropriation. Planning meeting on contamination strategy & trees early Jan. Build contract f/c pushed back a month to Jul 24. SOS pushed back 3 months - Oct 24. PC pushed back 2 months to Jan 26. 11/01/24 - Scheme going to committee in Feb but unclear about bridge/root protection. Appropriation issues outstanding and will go back to Cabinet following external legal advice. No change to cash flow. Equans PCSA work finished on submission of additional documentation. 31/01/24 - Planning committee back one month to March. Appropriation paper likely to be June Cab 08/02/24 - F/C dates pushed back 5 months pushing PC date into new FY. 29/02/24 - Planning com. in June. New steer from legal on app – app only land with housing from GF to HRA. area that will be the new MUGA will remain open space GF. Shut that land during construction. Cab paper for June 06/03/24 - Fees agreed with with Equans re request for additional fees to cover Prolongation 1 and 2. F/c dates pushed back 4 months - PC Oct 26 29/05/24 - issue with EA objecting to replacement bridge - big impact on planning, Sept/Oct planning committee. Sewage issue needs County input. Holding off on retender. Cabinet paper now July 05/06/24 - Pl. com. likely Sept. FC SOS pushed back 2 months to Aug 25. F/C PC date back 3 months to Jan 27 - out of HE prog 26/06/24 - Sept planning? 06/08/24 - 4 EA objections - sewage is County issue. Bridge may bring water from A to B. Oct pl com. £1m over budget. Need retender/get new EA. Board approved further funding on 2nd August, further report required for September for addit; 214: 45132; 215: 45215; 216: 45588; 217: 51.7321; 218: -1.2519; 220: 11; 221: 1; 234: 10; 270: TRUE; 277: N/A - SDS agreed; 281: 1; 282: 9416199; 283: 150000; 284: 831167; 285: 296652; 287: 490982; 288: 2650000; 289: 888750; 290: 7869551; 291: 11185001; 292: 223300; 293: 11408301; 294: 150191; 295: 11558492; 296: 10296250; 297: 4.79; 298: 36; 299: 2648798; 300: TRUE; 305: 455000 |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 |  | Yes | Yes |  | Yes | 1 | 45578.6178 | mmcfarlane@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Halliday Hill/ Westlands Drive | 15 new homes, to be built partially on the green at Northway. | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Stuart Moran |  | Design & Specification | [7 empty] | 30: Update from County on s106 which is expected to conclude imminently then s278 (diversion) can progress. Road stopping order is complete - subject to sec of state letter. VE workshop in August; 31: KEY ACTION: Budget concerns to resolve (VE exercise) & poss HRA budget envelope change- review date 16 Oct Going to market - 7 interested contractors Road stopping order to follow s106. Procurement won't progress until 278 in place.; 33: Overheating/energy concerns - engaging with consultants to address through planning Risk re road closure Financial viability and rising build costs: Trying to identify a suitable contractor is challenging. Will go to open market tender because of the budget of £6.2m, which is £1.2m over scheme budget. VE cost plan to be received week ending 11/10 from Oxford Architects. Thornton Firkin to review costs independently. Community opposition unknown but little objection at consultation event - keep Councillors informed Legal risk around road closure - mitigation as above Road stopping order currently dependent on s106; 37: Whole house MEV Contractor is costing solar PV TBC but anticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with panel heaters in flats and ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 39: 6360000; 40: 0; 41: 1500000; 42: 0; 43: 0; 44: 0; 45: 1500000; 46: 0; 48: -1500000; 54: 0; 55: 0; 56: 0; 57: 0; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 602; 105: City Council; 106: N/A; 107: 15; 108: 6; 109: 5; 110: 4; 116: No; 117: 15; 118: 15; 119: 15; 120: 44814; 121: 44531; 122: 44713; 123: 45078; 124: 45444; 125: Approval subject to s106; 126: 22/01554/FUL; 128: 45688; 129: 45809; 130: 45901; 131: 45992; 132: 46419; 133: 44742; 134: 45097; 159: 15; 160: 6; 161: 5; 162: 4; 188: Off Target; 190: Off Target; 193: At Risk; 199: Off Target; 202: At Risk; 205: At Risk; 208: Off Target; 211: Off Target; 213: Planning app submitted. Need validation to start road closure app. Planning app validated. Discussions w/County on closure of highway. Solution agreed. Planners confirmed the app will be heard late Jan/Feb 23. 18/01/23 Ongoing discussions w/Ward members regarding green space at front of the dev. Meeting arranged for the w/c 13/01/23. Planning to be March/April following revisions to plans due to comments from highways and Secure by Design. Spke with Cllr Chapman re green space improvements. 05/05/23 - Planning June 23. Green space/bin recycling location for disc, Members & Localities. Proc. to start Aug 2023. Road closure fter Planning in Aug. Red RAG for planning, finance, legal, time. May 2023 - June pl. comm. Not listed in Bye-laws. After planning, then 6-12 month for road stop. SM/RJ may tender in summer. June 2023 - Planning now July 23 due to land transfer issues on green space. Procure. to start Aug 23. Soft mark testing of procurement shows little appetite from framework. Approved by planning com with some concerns around loss of green space. 26/06/23 request for clarity on timescale for road stopping order. SOS of summer 2024 confirmed. 7/7/23 - S106 being worked up to complete Aug 23. Procurement to start in Sept 23. Road closure to commence in Aug. Planning risk - road closure. More detail required around green space. Land transfer concerns. Rising build costs, may need open market tender. 22/09/23 - Revised f/c dates inc f/c PC date pushed back 1 financial year into 26/27. Procurement to start Oct 2023. Road closure to commence once the Planning notice issued. Approval (OXP board - £160,000) to take the project through to RIBA Stage 4. 29/09/23 - background paper sent to Homes England 03/10/23 - s106 exp Oct 2023. Procurement to start Nov 23. Need to understand roadstopping timeline/how it fits AHP as PC falls out of 21-26 timetable 30/10/34 - Potential for RTB rather than Homes England, DS to confirm. Greater flexibility on delivery timescale but March 2028 deadline is final. 6/11/23 - CSOS pushed back 2 months to March 24 27/11/23 - s106 expected 31/1/24 - held up at County 30/11/23 - road-stopping process started early Nov. Procurement starting November, soft market testing tenders in Jan 24. 01/12/23 - F/c CSOS pushed back 1m to 1 April 24. 11/01/24 - tendering soon - not through framework. Been through soft market testing - will be an ‘open’ tender of 6 companies. S106 outstanding w/County. Need clarity around practicalities on ownership of the road. F/C CSOS pushed back 2m to 1 June 24 16/01/24 - Commenced road closure on 1 Nov. Contractor procurement starting shortly. 08/02/24 - Tenders to go out Feb 24. 29/02/24 - CP chasing County. 06/03/24 - Advised s106 will complete April 24. Tenders go out Mar 24 25/03/24 - build contract in June (PG) 04/04/24 - Tenders to go out Apr 2024. F/C dates pushed back 3m inc PC date pushed to Sept 2026 14/04/24 - Potential to progress consent as subject to s106 - then stopping order can progress. 18/05/24 - s106 to complete in May. CSOS pushed back 2m to Dec 2024. 29/05/24 - with County still. After planning can move to stopping order - objections mean appeal to SoS. Going to market - 7 contractors interested 05/06/24 - S278 pending S106. F/c CSOS pushed back 2m to Feb 25 (tender award Nov 24). 06/08/24 - s106 to conclude then s278 (diversion) can progress. Road stopping order is complete - just need SOS letter. Procurement won't progress until 278 in place. Cost plan £1m over - value engineering. AD awaiting target date from County contact. VE workshop 8/8/24. F/C dates pushed back - CSOS Feb to Sep 25, SOS Jun to Dec 25, PC Sept 26 to Feb 27 16/09/24 - VE workshop being assessed, feed to Abovo still not viable. F/C Q2 25/26 SOS and 12-18m build period 13/10/24 - tenders to go out Dec 24/Jan 25. App from County to commence road closure. VE costings to be received from Oxford Architects 11/10. Thornton Firkin requested to undertake a cost plan review.; 217: 51.7691; 218: -1.2231; 224: 1; 227: 1; 234: 4; 270: TRUE; 277: N/A - SDS agreed; 281: 77104; 282: 5750000; 283: 150000; 284: 335508; 285: 433917; 287: -536529; 288: 3180000; 289: 425000; 290: 2755000; 291: 6210000; 292: 150000; 293: 6360000; 294: 57710; 295: 6417710; 296: 5785000; 297: 7.57; 298: 21; 299: 3514880; 303: N/A; 307: TBC |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 | Yes | TBC | Yes | Yes | TBC | 1 | 45578.6104 | mmcfarlane@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Railway Lane (Old Oil Depot site) | 90-home all-affordable development with Cantay Homes. | N7054 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Kenny Phillips |  | Kenny Phillips |  | Delivery | [7 empty] | 30: Homes England update re revised milestones and staggered Golden Brick dates; 31: KEY ACTION: Monitor contract and progress to SOS - review date 25 Nov; 33: Time delay - Golden Brick date moved back again to Dec 2024 and confirmed by HE. Contract discussions took longer than expected. Contract delays will need discussion with Homes England to push back GB date again - as update on PC dates which now extend past March 2026. SSEN have not made available enough power to the site to deliver all the EV charging. Ongoing discussions with SSEN. 7 EV spaces will be available across the site at completion The last remaining archaeological review has completed with no further findings noted to date. Off-the-shelf package deal so technical and BR regulations are at Developers risk - including BNG off-site contributions and contamination.; 37: Monobloc heat pump in houses and panel heaters/edel hot water heat punp in flats MEV ventilation; 39: 33864500; 40: 13538505; 41: 14695162.27; 42: 8114472; 43: 1525090; 44: 1283000; 45: 25617724.27; 46: 678059.26; 48: -14695162.27; 54: -8114472; 55: -1525090; 56: -1283000; 57: -10922562; 77: Cantay Estates; 78: Cantay Estates; 95: 44909; 96: Cabinet Decision; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - owner not currently planning to bring forward. SSSI issue and site not being identified in Local Plan may limit CPO options; 105: Private; 106: Application Approved; 107: 90; 108: 47; 110: 43; 116: No; 117: 90; 118: 90; 119: 1900-03-30; 121: 2022-07-19; 122: 2023-03-01; 123: 2023-06-01; 124: 46113; 125: Planning approval; 126: 21/01176/FUL; 131: 2025-02-28; 132: 2026-08-30; 133: 2021-04-27; 134: 44761; 135: 45534; 136: 45534; 152: 50; 153: 31; 155: 19; 159: 40; 160: 16; 162: 24; 188: At Risk; 190: On target; 193: At Risk; 199: On target; 202: On target; 205: On target; 208: On target; 211: At Risk; 213: Owned by WE Black/ Edge of SSSI site. Allocated in the Local Plan 2001-16 (Policy DS67). Discussions opened with Cantay for possible consideration for an entirely affordable housing scheme. Legals being drawn up for agreement. Planning submission has been validated as of June 21. Planning proving contentious with Cantay pushing for a decision but until we have a clear planning picture, the remaining dates are hard to predict. As at 16.5.22 Cantay awaiting update from Planning Dept. 27/6/22 - ongoing discussions with Cantay and planning department. Agreed by Planning Committee in July 2022 18/01/23 - no further update May 2023 - Cantay and KP continue to work on contract, s106 remains outstanding. Developing application via IMS - aim for June submission 26/06/23 - Dates align with OXP but slow worm issues may impact on this. 01/08/23 - The scheme went to Planning Committee on 19th July 2022 and was approved. Issues at time of planning were: BNG, Overlooking and provision for a bridge in the future. S106 finalised and out for signing (4th Aug 23). Work on legals underway with developer. Pre commencement conditions being revised due to lack of information by the LPA. These have been agreed by the LPA and Cantay. 08/09/23 - signing of build contract pushed back from August to October 03/10/23 - F/C build contract and PC dates pushed back 1 month. Homes England application resubmitted 07/11/23 - F/c SOS pushed back 7 months to July 24 and PC date pushed back 3 months to early March 2026 - caution re Homes England deadline. 23/11/23 - work on legals underway with developer/OCC. 05/12/23 - Build contract f/c date remains in Dec but pushed back a week 11/01/24 - Build contract f/c signed date pushed back to end of Jan. Contract with Cantay agreed. Agreement with OCHL and OCC to be agreed similar to Marston Paddock. DS meeting with Shona this week. Timescales for agreements by end of the month. Lead in time for electrical cables to site is currently 2028. There is voltage capacity for the homes but not EV chargers. Littlemore Park/SOSV impacting on this. Resolution required. Deposit required by the end of FY. SOS 3 months later. HE to be updated regarding delay to SOS. 29/02/24 - contract exchange aiming for March before f/y/e. Still awaiting valuation - expected tomorrow. Concern about legal capacity - Shona reviewing external support (Capsticks/Brown Jacobsen). 05/04/24 - Work on legals underway with developer/OCC but OCC have now outsourced the legal service to BJ. This is delaying the contract being agreed. CSOS pushed back to April 24. 11/04/24 - Anglo-saxon pottery found onsite. Likely delay of a month max as archaeologist excavates/surveys site. 25/04/24 - SOS date pushed back 3 months. Contract date now mid-May. 19/05/24 - SOS pushed back a month to Oct 24 3/06/24 - SOS (GB) pushed back a month to Nov 24 26/06/24 - Groundworks resolved, no further pottery issues. Change technical build risk to green. Need to update HE re staged golden brick dates. 26/07/24 - Work on legals underway with developer/OCC but OCC (BJ). Contracts to be signed w/c 12/08 06/08/24 - f/c SOS and PC date moved back 2 months to Jan 25 and Aug 26 16/09/24 - Contracts signed - changed payment terms include monthly valuations. Forecast SOS pushed 2m to Feb 25; 214: 44252; 215: 45351; 216: 45346; 217: 51.7203; 218: -1.2274; 220: 8; 222: 8; 232: 3; 234: 18; 237: 9; 242: 1; 251: 24; 266: Keeper's Place; 270: TRUE; 271: 45145; 277: N/A - SDS agreed; 278: 45533; 281: 8990000; 282: 20010000; 283: 0; 284: 1461375; 285: 710219; 287: 1970906; 288: 6165000; 289: 3738750; 290: 23960750; 291: 33142500; 292: 722000; 293: 33864500; 294: 972140; 295: 34836640; 296: 29403750; 297: 5.06; 298: 38; 299: 12891680; 300: TRUE; 303: 45627 | 6165000 |  |  |  | B |  | Yes | No | Yes | Yes | No | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Kitchens |  | N7057 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | "These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. 13 Complete June 23 expected 104" |  | 45747 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 30: These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. 75 completed October; 40: 0; 41: -0.2; 42: 0; 43: 0; 44: 0; 45: -0.2; 46: 0; 47: 440771.8; 48: 440772; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Bathrooms |  | N7058 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | Capital programme budget |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. 58 YTD 88 Predicted year end; 40: 0; 41: -0.08; 42: 0; 43: 0; 44: 0; 45: -0.08; 46: 0; 47: 186994.92; 48: 186995; 49: N/A - On Budget; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45554.3156 | mmcfarlane@oxford.gov.uk
Boilers Only |  | N7059 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | This is a demand led budget and is part of the ongoing Decent homes and compliance work required by OCC as a landlord. 75 complete YTD 130 Predicted year end. Projected £1,500,000k spend does not include CO which needs to be added in. No slippage reported yet |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: This is a delegated budget to ODS and is part of the ongoing Decent homes and compliance work required by OCC as a landlord. 75 complete YTD 130 Predicted year end. Projected £407k spend does not include CO which needs to be added in. No slippage reported yet; 40: 500000; 41: 1325597.87; 42: 500000; 43: 500000; 44: 500000; 45: 2825597.87; 46: 854559.95; 47: 1325597.87; 48: 0; 54: -500000; 55: -500000; 56: -500000; 57: -1500000; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45555.1057 | mmcfarlane@oxford.gov.uk
Heating Systems |  | N7060 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  | Mark Smart |  | Luca Minetola |  | Rolling Programme | This is delegated budget to ODS and is part of the Decent Homes works | [6 empty] | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: This is delegated budget to ODS and is part of the Decent Homes works. .; 40: 500000; 41: 547113.06; 42: 500000; 43: 500000; 44: 500000; 45: 2047113.06; 46: 21564.04; 47: 654823.06; 48: 107710; 54: -500000; 55: -500000; 56: -500000; 57: -1500000; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45555.0829 | mmcfarlane@oxford.gov.uk
Northfield Hostel | Development of 51 affordable homes (original scheme) - 27 @SR & 24 @SO) - PLUS an Additional Scheme of 10 further affordable houses on land being purchased (July 24) from the County - 6 @SR & 4 @SO (in-year budget change/ virement from N7054 agreed at Oct 23 Council. Total (All-years) capital budget for N/F (51) is £19,350,000 (gross exc interest) and for N/F (10) this is £6,300,000 (gross exc interest). The budget 24/25 is being reset to match this, but debiting off actual spends and forecast spend for the remainder of 2023/24 (as expected at end Sept 23). | N7061 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | James Graham |  | Dave Scholes |  | Design & Specification | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission to be made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Now confirmed as in Year 4 OGD. Requires land sale; build contract signing; & planning consent by end March 22. Due to go to Plg Ctte on 9th March. Other critical path work (land and build contract) to follow in March. 15 Mar 22 - Approved at Plg Ctte. s.106 being finalised now. End March - s.106 agreed and land sale being progressed. June 22 - Re-tender using OCHL Framework to secure best price. Land now acquired from County. Sept 22 - tenders back and being assessed. Oct 22 - PSCA expected late Nov 22 Nov 22 - Budget to be reviewed in Dec 22/Jan 23 once more price certainty is secured. Currently forecasting a TSC (exc interest) of £19.65m (if a £16m build cost can be achieved). This would give a budget pressure of £3,250k, but the scheme would still meet HRA financial parameters and the higher Abovo costs have been tested in the draft HRA BP preparation (Nov 22). New budget to go to March 23 Cabinet and then Council. PCSA due to be issued March 23. Homes England bid by end March 23 also. June 23 - PCSA sealed and work underway. Demolition Aug 23. Main contract SoS Dec 23. HE Grant issue - looking to purchase adjacent County site to over come this. Reports into HSB and Devt Board (June 23) and cabinet report for Aug 23. Sale by County Cabinet agreed end Sept 23. Oxford City full Council agreement budget in Oct 23. Solicitors instructed and sale expected to complete late Oct/ Nov 23. Jan 24 - decision not to award build contract and to re-tender. Above reversed and Equans to be appointed. Feb- July 24 Price and contract negotiations with Equans. Demolition works underway. |  | 2026-03-27 | Build tender result, then revised cost schedule and programme to be confirmed. To establish whether we have sufficient price certainty (and limited risk) re costings, as to whether to submit a Homes England AHP funding bid in early Jan 23. Early March 23 - PCSA to be signed Jun 23 - Sealed! Now PCSA work (to complete in Feb 24). Demolition contract to be let - to SoS for demolition phase May 24 - targeting demolition completion July 24. DSA to sign (OCHL to OCC) Jul 24 HE grant claim. | Land purchase (N/F 10) from the County - in Jul 24, and RMA submitted to planning - anticipated July 24. | Main Build contract let - New target Aug 24 |  | 24: Off Target; 25: On Budget; 26: Off Target; 27: Medium; 28: Medium; 30: ""Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission to be made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Now confirmed as in Year 4 OGD. Requires land sale; build contract signing; & planning consent by end March 22. Due to go to Plg Ctte on 9th March. Other critical path work (land and build contract) to follow in March. 15 Mar 22 - Approved at Plg Ctte. s.106 being finalised now. End March - s.106 agreed and land sale being progressed. June 22 - Re-tender using OCHL Framework to secure best price. Land now acquired from County. Sept 22 - tenders back and being assessed. Oct 22 - PSCA expected late Nov 22 Nov 22 - Budget to be reviewed in Dec 22/Jan 23 once more price certainty is secured. Currently forecasting a TSC (exc interest) of £19.65m (if a £16m build cost can be achieved). This would give a budget pressure of £3,250k, but the scheme would still meet HRA financial parameters and the higher Abovo costs have been tested in the draft HRA BP preparation (Nov 22). New budget to go to March 23 Cabinet and then Council. PCSA due to be issued March 23. Homes England bid by end March 23 also. June 23 - PCSA sealed and work underway. Demolition Aug 23. Main contract SoS Dec 23. HE Grant issue - looking to purchase adjacent County site to over come this. Reports into HSB and Devt Board (June 23) and cabinet report for Aug 23 being drafted."" Homes England application currently on hold Purchase of land completed Demolition completed 23 Aug 2024; 31: KEY ACTION: N/F 10: Appointment of architect & RMA submission - review date 16 Oct KEY ACTION: N/F 51: Budget concerns for resolution (Costs showing as over budget envelope & V4M concerns) - review date 16 Oct Build contract expected in autumn 2024 Resubmission to Homes England - currently on hold with update expected mid-November Confirmation of procurement exemptions report expected (Northfield 10); 33: Pre-Planning application and consultation used to mitigate planning risk. Tender for build contract re-run through new OCHL framework (Lot2). Risk to delivery completing by Homes England deadline/ Need to secure funding from the HE AHP programme. Legal risk: Contract issue over liability levels. Complexity about process to include other site.; 34: Requires a further re-tender (Jan 24).; 37: Solar PV to Sunamp Thermina PCM battery. Immersion back up. MVHR - hybrid cooling addition required Fabric first approach - good insulation and air tightness Solar panels on roof to support electricity generation and MVHR All electric with SunAmp Thermino Hot Water system, NuAire cooling system and panel heaters. 3 x EV chargers and a car club with 2 cars.; 39: 19350000; 40: 9524123; 41: 21999763.48; 42: 10153801; 43: 701464; 44: 0; 45: 32855028.48; 46: 1239045.19; 47: 5698890; 48: -16300873.48; 51: 15825280; 52: 2546915; 53: 5000; 54: 5671479; 55: 1845451; 56: 5000; 57: 7521930; 66: Yes; 69: Yes; 70: Yes; 71: Yes; 72: To refresh ahead of demolition contract SoS, and again ahead of main build contract SoS (after re-tender).; 73: No; 76: See above. SoS now delayed; 77: WSP; 78: Equans - TBC; 80: No; 84: 0; 95: 44083; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 39; 105: County Council; 106: Drafting Bid; 107: 51; 108: 27; 110: 24; 116: No; 117: 51; 118: 51; 119: 51; 120: 44300; 121: 44648; 122: 44895; 123: 44957; 124: 45473; 125: Planning approval; 126: 21/03328/OUTFUL; 129: 44896; 130: 45625; 131: 45663; 132: 46265; 133: 44533; 134: 44648; 159: 51; 160: 27; 162: 24; 188: Off Target; 190: At Risk; 193: At Risk; 199: On target; 202: On target; 205: On target; 208: At Risk; 211: Off Target; 213: Re-tender for contractor Sept 22. Tender Report issued. Legal/Procurement advice. 18/01/23 Meeting with Equans 17/02/23 Approval to appoint Equans 05/05/23 Del. approval Mar 23 to appoint Equans. PCSA for signing May 23. Aug for demo (bats nesting). Hoarding to go up. VE meeting -Planners unlikely to accept major changes. May 23 - IMS app submitted. 9/06/23 - additionality issue w/HE grant. Demolition in Aug & PCSA pre-commencement underway. 26/06/23 - PCSA signed. Discussion on demo dates/no clear programme. SOS pushed to Jan 24. Waiting info f/Equans on demo (ODS increased price). Dev. continuing with add 10 units. IMS app referred back to resubmit w/10 units. 7/7/23 - Aim to bring forward demo Oct 23 (Equans). Bat survey on 11. VE will mean S73 application to Planning. HE App unresolved. SOS pushed back to Feb 24. Planning risk - Currently not meeting planning cond. to build 24 units in 30 months. Missing target by 2 months. S73 needs to vary design. 21/08/23 S73 to be applied to vary pl. app/reduce costs. Drafting report for demo del. approval in Oct. PCSA for complt Mar 24. 22/09/23 - F/c CSOS pushed back a month to Dec 23. F/c SOS pushed back a month/March 24. PCSA for completion Oct 23. Demo likely Nov 23. s73 submitted. Further bat survey. 03/10/23 - demo plus enabling work maybe Equans in Oct/Nov 23. F/c SOS pushed back a month to Apr. 30/10/24 - IMS app. once RM submitted plus signing contract/land purchase (exp. imminently) 22/11/23 - Work on contract price, currently w/in parameters. Progress on design. Moving towards demo. Signing CSOS f/c milestone pushed back 2 months to end Jan 24. Also SOS pushed back 2 months to 31/05/24. Planning risk from A to G. Finance risk from R to A. Market risk from A to G. Legal risk changed G to A. Contract issue over liability levels. Complexity re process to include other site. 27/11/23 - work w/Equans on cap on liability for demo. 07/12/23 - Issue wEquans as contractor. Suspend IMS app until Jan 24. 11/01/24 - JG reprofiled cashflow DS on both sites. This ends PCSA and pauses everything else. Demo pushed back Mar to May. N10 land purchase for this month. Searches happened - will go to EG. 5/2/24 - Equans working to RIBA 4 (7/3/24). Contracts for minor works asap, main contract exp. March 24. SOS may change. 15/2/24 - SD picking up on land purchase. Equans have been asked for revised price and programme 29/02/24 - legal progressing work contract re Equans demolition. Sale at N10 moving forward. Will become one project. Change to f/c dates (pushed back 2 months) while updating SDS. 06/03/24 - Work ongoing to manage contract price, but currently w/in parameters. PCSA 99% complete, Equans working on comments and securing prices. Moving towards demolition work starting, waiting for Legal to conclude minor works contract. 25/03/24 - Build contract with Equans – demo going ahead. Approved for demo/minor works in Apr. Build contracts to be signed/start in June. 25/04/24 Managing contract price w/in parameters. PCSA 99% complete, Equans working on comments/securing prices. Minor works contract sealed, work to start w/c 8/5 19/05/24 - PCSA complete 29/05/24 - demo started. Finalising cost plan - Aug SOS for main works. Need procurement exemptions - then submit for planning (prob July). Purchase of add 10 this week. MM/JG to update IMS bid/grant rates. May 26 expecting completion but might be earlier 26/07/24 - enabling works ongoing. Costs from Equans – need to review with programme. Procurement happy with exemptions report. JG to finalise/circulate then VEEP report. Cost high - JG to summarise info from EA. IMS app for early Aug. 30/08/24 - CSOS/SOS milestones pushed back 2m with CSOS Oct. PC pushed back to Aug 24 beyond HE prog. 6/9/24 - JG starting tender process for architect 19/09/24 - demo complete, minor works complete soon. RoT from project EA re viability challenges. Poss retender TBC. 13/10/10 - final cost plan over budget, need approval for extra budget. SOS back 1m to Jan 25; 214: 43958; 215: 44956; 217: 51.7239; 218: -1.2153; 270: TRUE; 271: 44648; 277: N/A - SDS agreed; 278: 45383; 281: 1489000; 282: 17700000; 283: 21468; 288: 4217300; 289: 1960071; 290: 15351047; 292: 3372950; 293: 21528418; 294: 675378; 295: 22203796; 296: 15063213; 297: 3.58; 298: 59; 299: 358354; 300: TRUE; 305: 317300 |  | TRUE | Category 1 – Pre-Manufacturing - 3D primary structural systems [PCG - Roof trusses, precast concrete stairs] Category 2 – Pre-Manufacturing - 2D primary structural systems [PCG - Upper floor slabs, roof compartmentation spandrel panels] Category 5 – Pre-Manufacturing - Non-structural assemblies and sub-assemblies [PCG – Balcony, walkway and stair balustrade systems] Category 7 – Site process led labour reduction/productivity improvements [PCG - Adoption of Fieldview technology for verification of adherence to design, quality standards and materials specifications] | 70% reduction on 2013 Building Regs | B | 2013 | Yes |  | Yes | Panel heaters | Yes | 1 | 45578.597 | mmcfarlane@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Northfield Hostel additional site 10 units | Purchase of site adjacent to Northfield Hostel to develop 10 all-affordable homes | N7061 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Design & Specification | [7 empty] | 30: Confirmation of land acquisition Procurement strategy to appoint an architect to secure RM consent has been drafted and discussions underway with OCC to progress this ASAP; 31: KEY ACTION: N/F 10: Appointment of architect & RMA submission - review date 16 Oct Resubmission to Homes England - currently on hold with update expected mid-November Confirmation of procurement exemptions report expected (Northfield 10); 37: Fabric first approach - good insulation and air tightness Solar panels on roof to support electricity generation and MVHR; 39: 6265713; 40: 300000; 41: 0; 42: 600000; 43: 0; 44: 0; 45: 600000; 46: 0; 48: 0; 54: -600000; 55: 0; 56: 0; 57: -600000; 95: 45147; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 105: County Council; 106: Drafting Bid; 107: 10; 108: 6; 110: 4; 117: 10; 118: 10; 119: 10; 125: Application documentation being prepared; 127: 45636; 128: 45717; 130: 45717; 131: 45777; 132: 46244; 159: 10; 160: 6; 162: 4; 188: Off Target; 213: 22/08/23 Connells have completed their valuation which will be sent shortly. Procurement likely to issue a waiver to allow us to work with Equans and SM to undertake a Planning Pre-app with Equans standard house types. 28/11/23 - RM to be submitted and allow IMS application before end of year 11/01/24 - JG has reprofiled the cash flow for DS on both sites. This wraps up PCSA and pauses everything else. Demolition pushed back from March to May. Additional land purchase happening this month. Searches have happened and will go to EG. 29/02/24 - Sale moving forward. Will then be considered one site. 25/03/24 - minor works contract being let this month with Equans. PG to follow up and update. 10/06/24 - Awaiting exemptions approval from procurement - once has this will submit for planning (expecting July). Purchase of add 10 expected this week. 24/06/24 - exchange/completion of land purchase expected within 10 days. AS to update on reserved matter. 19/07/24 - completion of land purchase confirmed. awaiting RM submission. Homes England application on hold. 30/08/24 - pushed back planning submission date from August to December 24. OX Place to appoint architects to do this shortly. 19/09/24 - OCC has now acquired the site from the County Council. The procurement strategy to appoint an architect to secure detailed planning consent has been drafted and discussions underway with OCC colleagues with a view to progressing this ASAP. Not confirmed if the procurement will be separate to Northfield 51; 214: 45089; 215: 45132; 216: 45528; 234: 2; 237: 4; 270: TRUE; 275: 50000; 276: £10,000 – Agreed at HSB 12 June 2023 and Development Board on 15 June 2023; £40,000 – Agreed at HSB 25 July 2023 and Development Board on 17 August 2023; 277: Yes - draft SDS; 281: 1200000; 282: 3787311; 283: 1; 288: 808000; 289: 465000; 290: 4358995; 292: 644683; 293: 5631995; 294: 135005; 295: 5767000; 296: 4425000; 297: 4.56; 298: 31; 299: 1049065; 300: TRUE |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 | [6 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Lanham Way | This is the development of 10 affordable homes (5 @SR & 5 @SO). | N7062 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | Allison Dalton |  | Dave Scholes |  | Delivery | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Planning issues being resolved with architects and across teams. Mar 22 - Significant redesign required to reduce number of units. Sept 22 - Planning consent secured (at committee) for 10 homes. Conditions and s.106 pending Nov 22 - Build Contract tender out (on framework) - Due back Jan 23 Jan 23 - Tender back - being assessed. (Feb 23) s106 drafted and ready to sign Jun 23 - Land purchased. Build contract to be signed imminently. Final legals to build contract. Possible slight delay to SoS due to ecology (translocation window) Build contract signed and SoS achieved in Dec 23. DSA to sign (OCHL to OCC) Mar 24 - Jul 24 |  | 45630 | Tracking progress through site meetings and programme tracking | HE AHP Grant milestones and funding draw-downs - claims received for acquisition and SOS | PC Dec 25 |  | 24: On target; 25: Under Budget; 26: On target; 27: Low; 28: Low; 30: "Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission made this month. Land sale from County Council being actioned (internal delegated decision now made). Jan 22 - Planning issues being resolved with architects and across teams. Mar 22 - Significant redesign required to reduce number of units. Sept 22 - Planning consent secured (at committee) for 10 homes. Conditions and s.106 pending Nov 22 - Build Contract tender out (on framework) - Due back Jan 23 Jan 23 - Tender back - being assessed. (Feb 23) s106 drafted and ready to sign Jun 23 - Land purchased. Build contract to be signed imminently." Handovers anticipated Jan 2025 - need monitoring against 15 Jan Homes England expectation; 31: KEY ACTION: Close monitoring against handover date - review date 25 Nov IMS PC milestone 15 Jan 2025 Update on electricity connection issue - following late application from Feltham Marketing of SO units to begin early Autumn; 33: Build issues - Site Meetings and EA engaged Contractor has undertaken detailed technical risk analysis with none identified to date - contingency in budget After acquisition scheme will be private highway for OCC to maintain - adequate provisions in place Remove or minimise any provisional sums re finance - robust programme tracking; 34: Budget 2024/25 on (MTFP) should be £4,288,671 - £170k more than Oct 23 Abovo - but budget being held as was to ensue contingency. (This is also the forecast spend, assuming slippage in 2023/24). No change to overall project budget which is on-track.; 37: Fabric first approach - good insulation and air tightness Solar panels on roof to support electricity generation and MVHR; 39: 5555000; 40: 3185122; 41: 6711853.38; 42: 1103548; 43: 0; 44: 0; 45: 7815401.38; 46: 1952100.33; 47: 4136012; 48: -2575841.38; 51: 374413; 52: 0; 53: 0; 54: -729135; 55: 0; 56: 0; 57: -729135; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: Welling Partnership; 78: Feltham Construction; 80: No; 95: 44083; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - small site; 105: County Council; 106: Application Approved; 107: 10; 108: 5; 110: 5; 116: No; 117: 10; 118: 10; 119: 10; 120: 44189; 121: 44272; 122: 44378; 123: 44440; 124: 44896; 125: Planning approval; 126: 21/03114/CT3; 132: 45674; 133: 44593; 134: 45006; 135: 45224; 136: 45264; 145: 10; 146: 5; 148: 5; 188: On target; 190: At Risk; 193: On target; 199: On target; 202: On target; 205: At Risk; 208: On target; 211: On target; 213: In negotiation with contractor, aim to sign contact June / July 2022 subject to VP. Outstanding risks due to Judicial Review, Tenant Occupation, delay and absolute risk. Risks should be further crystallised by end June 2022 17.05.22 Update: Still in planning due to rejection. Now looking at 10 units ( 2 and 3 beds units) - likely to be 50:50 SR to SO. Update 18.10.22 Resolution to grant consent' given Sept 2022 for 10 homes (2 and 3 bed houses). S106 to be agreed. Project being tendered to contractors Oct - Dec 2022. Contract for County land completes when planning granted following s106 agreement, and when JR period expires. Hold off completion until tenders received to ensure cost is within budget 18/01/23 - One tender received Jan 2023. Figure is within budget but needs full evaluation. 17/02/23 No Update 23/05/23 Contract award made to Feltham subject to signing the detailed JCT contract docs (target end June) - all delegated decisions approved. Completion of purchase/transfer of site from County to City 25 May subject to clearance on pre-completion inspection. 19/5/23 Submission via IMS - going to bid clinic on 8 June. June - Pl consent with s106 granted 21 March 2023. Contractor award made May 2023 - JCT contract to be negotiated and signed June/ July 2023. Contract to acquire land from County completed in May 2023. HE funding confirmed. 26/06/23 - possibly moving away from Jessops for new EA, decision soon. On programme. 3/07/23 - Pl consent w/s106 granted 21 Mar '23. Contractor award made May 2023 - JCT contract to be negotiated and signed July 2023. Contract to acquire land from County completed in May 2023. HE funding award confirmed June 2023. 01/08/23 - first grant (acquisition milestone) requested from Homes England - due August 2023. 04/08/23 - EA services have been retendered and Welling Partnership to start work in Aug 23 with Jessop & Cooke falling away at the same time 22/08/23 - signing of build contract progressing but now likely early Sept (pushed back a few weeks) Some concerns about meeting Dec 23 SOS flagged but awaiting clarification. 14/09/23 F/c build contract pushed back a few weeks to end of Sept (similar with SOS) with forecast PC pushed back to end of March 2026 03/10/23 - pre SOS work ongoing e.g. clearing conditions/s106 30/10/23 - Awaiting confirmation that contract is signed - already signed by Feltham. All progressing with expectation of SOS in December ahead of HE SOS milestone in early Jan. 9/11/23 - contract confirmed as signed 23/11/23 - formal site handover and SOS Dec 23 04/12/23 - confirmation of SOS. Changed RAG to Green but note that OXP keep it as Amber. F/c PC date pushed back to Oct 2025 (beyond HE deadline). Clarification requested to allow update to HE. 11/01/24 - Progress report on 8 Jan 2024 - details TBC as necessary. EoQ meeting: on track. 7/2/24 - CDM checklist updated. Work continuing at good pace. Potential for slight delay with additional work to fit out SO units. 29/02/24 - onsite all good. Some changes to spec but contingency covered this. Sales are starting to market scheme. 05/04/24 - Site is making good progress against programme. Extreme wet weather making conditions difficult but not insurmountable. Internal finishes design work underway. Ecologist on board for BNG delivery. Service charge calculation in progress. PC date amended to early Dec 24. 29/05/24 - Cashflow slowing. AD to provide update. 27/06/24 - potential energy issue noted and flagged in RAG section: Feltham failed to complete an application in January subsequently picked up in May - Debbie trying to resolve. 19/09/24 - in budget but some delays, w handovers early 2025. Marketing starting early Autumn.; 214: 43958; 217: 51.7199; 218: -1.2271; 266: Young's Way; 270: TRUE; 271: 45005; 277: N/A - SDS agreed; 278: 45383; 281: 870000; 282: 3800000; 283: 30000; 288: 700000; 289: 598750; 290: 4081675; 292: 680425; 293: 5380425; 294: 63684; 295: 5444109; 296: 4191250; 297: 4.5; 298: 39; 299: 1146139; 300: TRUE | 700000 | TRUE | The scheme uses MMC for the houses, these are being fabricated offsite | 70% reduction on 2013 Building Regs - 83% with PV TBC | B | 2013 | Yes |  | Yes | Yes | Yes | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Next Steps Accommodation Programme |  | N7066 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Dave Scholes |  | Completed | Buying 5 one bed flats for rough sleepers in a Housing First model. Completed on 3 in March 21 (Q4) and remaining two will be in April 21 (Q1 21/22). 5 NSAP units completed. A new bid to buy 10 further units in 21/22 made in April 2021, and award of funding confirmed (June 21) - team mobilising and contacting agents. Sept 21 - 1st unit completed. Oct 21 - Additional grant ask from MHCLG (to replace £550k that was to be funded from OGD) now under consideration/ sign-off. Jan 22 - 4 RSAP units completed. Last 6 properties in conveyancing and expect to complete by end March 2022. 15th Mar 22 - Initial 8 completions (cost c. £1,540k plus min £50k refurb costs). 9 units now completed (9th one was today - £175k). 10th (last) home expected to complete on 28/3/22 (£135k). SDLT exempt. End Mar 22 - All 10 RSAP properties now purchased and void works are underway with ODS. First 2 tranches of grant per dwelling claimed. Now awaiting PC. July 2022 - All works now complete - Homes are lettable and are let. |  | 44742 | Expect void works spend to be capitalised into this project - Value TBC. Project can then close. Expect a £500k underspend |  |  |  | 24: Completed; 25: Under Budget; 26: Completed; 27: Low; 28: Low; 30: "Buying 5 one bed flats for rough sleepers in a Housing First model. Completed on 3 in March 21 (Q4) and remaining two will be in April 21 (Q1 21/22). 5 NSAP units completed. A new bid to buy 10 further units in 21/22 made in April 2021, and award of funding confirmed (June 21) - team mobilising and contacting agents. Sept 21 - 1st unit completed. Oct 21 - Additional grant ask from MHCLG (to replace £550k that was to be funded from OGD) now under consideration/ sign-off. Jan 22 - 4 RSAP units completed. Last 6 properties in conveyancing and expect to complete by end March 2022. 15th Mar 22 - Initial 8 completions (cost c. £1,540k plus min £50k refurb costs). 9 units now completed (9th one was today - £175k). 10th (last) home expected to complete on 28/3/22 (£135k). SDLT exempt. End Mar 22 - All 10 RSAP properties now purchased and void works are underway with ODS. First 2 tranches of grant per dwelling claimed. Now awaiting PC. July 2022 - All works now complete - Homes are lettable and are let."; 33: None; 34: Final account settlement (with ODS). Homes England Audit info submitted - BDO engaged to undertake this (OCC expense). Close budget and vire funds - as per Council decision March 2023; 40: 0; 41: 581746.12; 42: 0; 43: 0; 44: 0; 45: 581746.12; 46: 0; 48: -581746.12; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 77: n/a; 78: n/a; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Renewal of Fire Alarm Panels | Replacement of fire alarm panels and configuration of detection systems - initial sites are Pound House, Cardinal House, Atkyns Court, Birch House and George Moore House | N7067 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Capital Delivery |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Rolling Programme | Alarm and detection system at Headley House completed (June 2023), next site to be identified and procured. |  | 45747 |  |  |  |  | 24: On target; 25: Under Budget; 26: On target; 27: Medium; 28: N/A; 30: Exemption request submitted to enable replacement of the system at Headley House to be completed within the current years allocated budget. Awaiting confirmation from Procurement.; 33: Completion of this project affects Fire safety, thus important to maintain progress; 40: 60000; 41: 207021; 42: 60000; 43: 75000; 44: 60000; 45: 402021; 46: 0; 47: 207021; 48: 0; 51: 650000; 52: 650000; 54: 590000; 55: 575000; 56: -60000; 57: 1105000; 80: No; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Juniper | The direct delivery of homes by ODS into the HRA | N7068 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Dave Scholes |  | Closed | Now Juniper only - 2 units (with ODS). Tucker is being progressed by OCHL. Thomson was dropped in favour of a land deal to support the Railway Lane devt with OCHL/ Cantay. Still pending a proposal and cost from ODS (likely for one unit only now due to ground constraints). PROPOSE TO CLOSE THIS PROJECT AS UNVIABLE (and reallocate funding to support the Northfield scheme budget pressure through the 23/24 final budget process) |  | 2023-09-01 | Awaiting financial appraisal and programme. Issue concerning ground conditions pending (re statutory services running through the site). |  |  |  | 24: Not started; 26: Awaiting new Schedule; 27: High; 28: High; 30: "Now Juniper only - 2 units (with ODS). Tucker is being progressed by OCHL. Thomson was dropped in favour of a land deal to support the Railway Lane devt with OCHL/ Cantay. Still pending a proposal and cost from ODS (likely for one unit only now due to ground constraints). PROPOSE TO CLOSE THIS PROJECT AS UNVIABLE (and reallocate funding to support the Northfield scheme budget pressure through the 23/24 final budget process)"; 33: Requires planning submission and works programme.; 34: Requires budget from N7063 ODS to confirm price - esp re ground works issue - Due shortly (July 22) Now Oct 22 - Further delay (Nov 22) - it is possible that only one unit may now be feasible and this raises concerns re viability and V4M - TBC To consider closing this project as part of the 23/24 final budget process; 40: 0; 41: 385229; 42: 0; 43: 0; 44: 0; 45: 385229; 46: 0; 48: -385229; 54: 0; 55: 0; 56: 0; 57: 0; 66: Yes; 80: Unsure; 82: Building contract; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Masons Road - Major Refurbishment |  | N7070 | Development Board |  | Communities | Housing - HRA (Property) |  | Capital Delivery |  | Nerys Parry |  |  |  |  | Luca Minetola |  | Delivery | Orders have been placed with ODS and 3 properties remaining to be done with 4 underway |  | 2025-03-31 |  |  |  |  | 24: On target; 25: On Budget; 26: On target; 27: Medium; 28: N/A; 30: Orders have been placed with ODS and 3 properties remaining to be done with 4 underway; 40: 0; 41: 586178.52; 42: 0; 43: 0; 44: 0; 45: 586178.52; 46: 53382.08; 47: 586178.52; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 80: Yes; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Fencing |  | N7071 | Development Board | Asset Review Group | Communities | Housing - HRA (Property) |  | Rolling Programme |  | Nerys Parry |  |  |  |  | Luca Minetola |  |  | Demand led/ lower demand than previous years. |  | 45747 |  |  |  |  | 24: On target; 25: Under Budget; 26: On target; 27: Low; 28: N/A; 40: 0; 41: 250855.63; 42: 0; 43: 0; 44: 0; 45: 250855.63; 46: 0; 47: 250855.63; 48: 0; 50: Lower demand than expected; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45554.2158 | mmcfarlane@oxford.gov.uk
QL Improvements (HRA) |  | N7072 | Development Board |  | Communities | Housing - HRA (Property) |  | Capital Delivery |  | TBC |  |  |  |  | Alison Cornacchia |  | Delivery | Please see QL Exploitation | [6 empty] | 24: Not started; 40: 0; 41: 245000; 42: 0; 43: 0; 44: 0; 45: 245000; 46: 0; 48: -245000; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45580.4473 | acornacchia@oxford.gov.uk | Y | 45545.5416 | rhaverson@oxford.gov.uk
Southfield Park Leases | Southfield Park lease extension | N7073 | Development Board |  | Communities | Housing - HRA (Property) |  | Miscellaneous Capital Spend |  | Nerys Parry |  |  |  |  | Bill Graves |  | Delivery | Alex Miller (Corporate Assets) has made contact with Lincoln College regarding the proposal. Lincoln College have, in turn, contacted their solicitor and valuer to get initial input but are awaiting their response before having a conversation with us. |  |  | JLL providing valuation report - TBC | Corporate Assets to contact Lincoln College - Complete | Lincoln College to contact OCC once they have had a response from their solicitor and valuer. TBC |  | 24: Off Target; 25: On budget; 26: At Risk; 27: Low; 28: Low; 30: Alex Miller (Corporate Assets) to chase consultants JLL on estimate of valuation to inform informal discussions with Lincoln College, rather than enter directly into the statutory lease extension process.; 33: The key risk is that the valuation of the lease extension under the statutory process is higher than the budget envelope of £1.5m. The other risk is that Lincoln College may wish to decline informal discussions however there is a statutory process that we can fall back on as mitigation if necessary. The appointment of JLL (Real Estate & Property Consultancy) has to advise on valuation and negotiation has also provided assurance that best value will be obtained.; 34: Keep pushing Lincoln College for progress; 37: No; 40: 0; 41: 1500000; 42: 0; 43: 0; 44: 0; 45: 1500000; 46: 0; 48: -1500000; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 77: N/A; 78: N/A; 80: No; 82: N/A; 84: N/A; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Oxford North Develpment | 112 affordable homes (via the s.106) from this site. (1 additional) | N7074 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  | Andy Dorrington |  | Dave Scholes |  | Delivery | Cabinet approvals secured in March 2023. Moving to contract signing SoS achieved (June 23) |  | 46477 | Monitor site progress and staged payments | First handovers are expected Quarter 3 2025-2026. | PC (Jun 27) |  | 24: On target; 25: On Budget; 26: On target; 27: Low; 28: Low; 30: First handovers are now expected Quarter 3 2025-2026.; 31: Agreed additional unit is due to be formalised contractually with Hill via a DoV which is awaited; 33: The scheme has planning and the obligations of this will be picked up by Hill through the contract. However, appropriate due diligence will be done. s73 submitted in May 24 for 2 extra flats in the podium area of blocks 6&7. Scheme is in contract and on-site although query over the housing trajectory which does not align with the development agreement. Issue has been noted with careful monitoring on site. Reprofiling took place in April to move all units from 24/25 to 25/26 Technical risks will be the responsibility of Hill through the contract. Due diligence on going. Energy strategy negotiations taking place throughout first half of 2024; 34: DSA with OX P agreed - to be sealed (Jul 24); 37: Monobloc heat pumps to houses and communal heat pump to flats MVHR Solar panels to the flats Blocks 6& 7 fed from blocks 4 & 5.; 39: 33803250; 40: 13538505; 41: 14695162.27; 42: 8114472; 43: 1525090; 44: 1283000; 45: 25617724.27; 46: 1017088.88; 47: 5464131; 48: -9231031.27; 51: 13168936; 52: 8119326; 53: 200000; 54: 5054464; 55: 6594236; 56: -1083000; 57: 10565700; 66: Yes; 69: Yes; 70: Yes; 73: Yes; 74: Yes; 77: Hill Residential; 78: Hill Residential; 80: No; 95: 45000; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 1; 105: Mixed; 106: N/A; 107: 317; 108: 90; 110: 22; 116: No; 117: 112; 118: 112; 119: 112; 120: 44648; 125: Planning approval; 126: 22/00675/RES; 132: 46357; 133: 44698; 134: 44869; 135: 45107; 136: 45107; 152: 69; 153: 49; 155: 20; 159: 43; 160: 41; 162: 2; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: RM approved - 22/00675/RES / on 07/11/2022 / and Outline approved - 18/02065/OUTFUL on 21/03/2021 for the whole site 480 Units. S106 Agreed. This Project is part of large strategic site. RM Application validated on 28/03/2022 for the first for around 317 homes (35% affordable - 80/20 SR/SO Split) No current RP in contact with the developer. Currently awaiting the submission of revised plans and documents as planning requested amendments with regards to the height and design of the proposed blocks and a number of amendments to the supporting technical documents were required. The submission was due early April but there have been delays with a number of reports. It was aiming to present at June committee but this may need to be July given delays. The scheme is in line with policy H2 but within the original submission, 19.05.2022 - Savills to produce accommodation schedule and target dates for SOS & PC as there was no indication as to where the AH units would be located and the mix breakdown at present is 111 dwellings: One Bed Flat = 25 x SR + 6 x SO = 31 Two Bed Flat = 27 x SR + 9 x SO = 36 Three Bed Flat = 17 x SR + 5 x SO = 22 Three Bed House = 12 x SR + 1 x SO = 13 Four Bed House = 8 x SR + 1 x SO = 9 Total = 111 Update 28/11/22 : Currently in discussions with the planning team over the delivery. the start on Site is looking at 'early 2023' It will then take around 7 years to complete the entire scheme with 35% minimum AH requirement in each delivery phase with an Accommodation schedule received but NO housing trajectory. A lot could change, the applicant is preparing the housing trajectory that they are required to do this under the terms of the S106. Savills have not given a timescale on when this would be ready, they are aware of the requirement to submit this before starting on site. The milestones are based on what Hill had sent most recently to Sarah when they asked for the bid of the affordable units PC of last Affordable December 2026. 17/05/23 Aiming for contracts to be in final draft by mid June (if not sooner). Meetings are taking place on a weekly basis with both sides (legal, EA, Hill, Procurement). An update to Housing is taking place on the 17th May. 01/08/23 - Contracts signed and parcel 1 transfer undertaken 30th June 2023. On site monitoring and management now underway with first site meeting in September. 31/10/23 - housing trajectory agreed although difference between delivery profile in s106 and contract 27/11/23 - CDM checklist and all CDM related issues have been deferred to Hill. 11/01/24 - No site delays noted. 29/02/24 - all on target, developer has submitted planning change to add extra flats to undercroft. KP will do another BP appraisal (2 for social rent). Won’t affect the programme. Think planning will be ok. KP will know if it’s financially ok at the end of next week. 21/03/24 - DOV for extra 2 units. The proposals involve providing two additional three-bedroom flats within two of the blocks (6 and 7) by moving cycle parking into basement. Dev. proposes new flat in bl.6 would be SR, flat in bl.7 would be SO, whilst Plot 73 would be market sale rather than SO. 11/04/24 - Revised CDM info provided. 03/06/24 - F/C PC date pushed back 3 months to Dec 2026 10/06/24 - revised prog. has PC (single unit) in March 2027 25/07/24 - Deed of variation to be issued in last week of July 24 to include changes to the number and unit types. Monthly site meetings taking place every 5 weeks. 06/08/24 - PC date moved forward to Dec 26. Query early delivery of some units 19/09/24 - on programme and in budget. Additional agreed unit is being formalised with Hill through a DoV. First handovers expected Q3 25/26; 214: 44956; 215: 45432; 217: 51.7959; 218: -1.2822; 266: Canalside Quarter; 270: TRUE; 271: 44278; 273: TRUE; 277: N/A - SDS agreed; 278: 45383; 281: 8730000; 282: 20455000; 283: 0; 288: 0; 289: 2324500; 290: 31574398; 292: 4713898; 293: 33898898; 294: 1945426; 295: 35844324; 296: 49598500; 297: 4.09; 298: 46; 299: 5460440; 300: TRUE |  |  |  | 40% reduction on 2013 Building Regs | B | 2013 | Yes | No | Yes | Yes | Yes |  | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
LAHF Acquisitions (Round 1) | Property acquisition then conversation to social rent for Ukrainian & Afghan households | N7075 | Development Board |  | Development | Housing - HRA (Supply) |  | Miscellaneous Capital Spend |  | Tom Bridgman |  |  |  |  | Andy Dorrington |  | Completed | 7 of 7 properties purchased, void completed and let. |  | 45260 | Purchase of remaining 2 properties by 30/11/23 - complete | Registration of all properties on Council systems | Completion of void works of all properties, allocation & letting - on-going |  | 24: Completed; 25: Under Budget; 26: Completed; 27: Low; 28: Low; 33: Budget- overall budget allows for property purchase, associated costs & void works although final void costs confirmed once work is completed. Market price fluctuations - all properties either purchased or in conveyancing Sales fall through - accepted risk, OCC are cash buyers but cannot avoid chain sales Underspend - there may be budget left over following property purchases; 34: Project leads met with DLUHC in November who confirmed underspend can be brought forward to be used within LAHF Round 2 program which is on-going and more units to be purchased by March 2024. Final void costs TBC via ODS once void works are completed on program therefore spend allocated for 23/24 may increase but not to reach budget envelope.; 40: 0; 41: 312704.34; 42: 0; 43: 0; 44: 0; 45: 312704.34; 46: -5250.54; 48: -312704.34; 54: 0; 55: 0; 56: 0; 57: 0; 66: N/A; 80: Yes; 82: Void works for 7 properties to renovate to a lettable standard; 84: 233551; 117: 0 | [12 empty] | 45580.5546 | adorrington@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
LAHF 1 Ukrainian refugees acquisitions programme 22-24 | Local Authority Housing Fund programme delivering street properties through leaseholder buy-back and open market | N7075 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 40: 0; 41: 0; 42: 898000; 43: 2705000; 44: 457000; 45: 4060000; 46: 0; 48: 0; 54: -898000; 55: -2705000; 56: -457000; 57: -4060000; 100: No; 101: Direct Delivery HRA; 105: Private; 107: 7; 108: 7; 116: No; 117: 7; 118: 7; 119: 6; 125: Not Applicable; 132: 45260; 137: 45247; 138: 7; 139: 7; 188: Completed; 190: Completed; 193: Completed; 199: Completed; 202: Completed; 205: Completed; 208: Completed; 211: Completed; 213: 5 x Ukraine 2 & 3 bedroom properties & 1 x Syrian 4+ bedroom property. Funded by DLUCH; 222: 4; 224: 2; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3995 | mmcfarlane@oxford.gov.uk
Major Voids - Kitchens & Bathrooms | Major Voids - Kitchens & Bathrooms | N7076 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  |  |  | 45747 |  |  |  |  | 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Climate Change | Climate Change | N7077 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | Update will be shared as of next month |  | 46843 |  |  |  |  | 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45546.1351 | adorrington@oxford.gov.uk
LAHF 2 Ukrainian refugees acquisitions programme 22-24 | Local Authority Housing Fund programme delivering street properties through leaseholder buy-back and open market | N7078 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Dave Scholes |  | Delivery | [7 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45182; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Mixed; 106: N/A; 107: 5; 108: 5; 117: 5; 125: Not Applicable; 132: 45473; 138: 1; 139: 1; 145: 5; 146: 5; 188: On target; 190: On target; 193: On target; 196: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: 29/04/24 - four units completed by May 24. Final units complete in June - to conclude programme 03/06/24 - one more handover expected in June 24; 221: 4; 224: 1; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
LAHF 1/2 acquisitions programme | Additional units being acquired through underspend of LAHF programmes | N7078 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Dave Scholes |  | Delivery | [7 empty] | 95: 45035; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 3; 108: 3; 117: 3; 125: Not Applicable; 132: 2024-10-30; 145: 3; 146: 3; 188: On target; 213: 29/04/24 - programme completing June 24; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.1351 | adorrington@oxford.gov.uk
LAHF 2 Ukrainian refugees acquisitions programme 22-24 | Local Authority Housing Fund programme delivering street properties through leaseholder buy-back and open market | N7078 | Development Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | All units delivered and let. Awaiting final ODS invoices on 2/5 units in order to confirm total spend. | [6 empty] | 25: Under Budget; 26: On target; 40: 0; 41: 690678.52; 42: 0; 43: 0; 44: 0; 45: 690678.52; 46: 1019348.48; 47: 1376500; 49: N/A - On Budget; 66: No; 69: No; 70: Yes; 71: No; 73: No; 80: No; 82: HRA Void works to bring to HRA lettable standards.; 84: 62787.52; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.1351 | adorrington@oxford.gov.uk
SHAP Single Homelessness Accommodation Programme - Acquisitions 22-24 | Homes England-funded programme delivering street properties through leaseholder buy-back and open market | N7079 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Dave Scholes |  | Delivery | [7 empty] | 40: 5774279; 41: 3500000.19; 42: 7301909; 43: 3256938; 44: 3000000; 45: 17058847.19; 46: 258832.45; 48: -3500000.19; 54: -7301909; 55: -3256938; 56: -3000000; 57: -13558847; 95: 45147; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 12; 108: 13; 116: No; 117: 13; 118: 12; 119: 1; 125: Not Applicable; 132: 31/11/24; 138: 5; 139: 5; 145: 8; 146: 8; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: 6 x One Bed properties per financial year, Homes England grant funded 16/01/24 - reprofiled to show 5 units in 23/24 and 7 units in 24/25 July 24 - One additional unit to come into the programme - increasing delivery from 12 to 13; 220: 12; 300: TRUE | [12 empty] | 45579.2504 | mmcfarlane@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
SHAP Single Homelessness Accommodation Programme - Acquisitions 22-25 | Homes England-funded programme delivering street properties through leaseholder buy-back and open market | N7079 | Development Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | Delivery Total 6/12 homes met PC and LET, further 6 to be delivered by March 28th 2025. Next legal completion dates for remaining 6/12: 1) 17/10/2024 2) 18/10/2024 3) 22/10/2024 4) 22/10/2024 5) 29/10/2024 6) 05/11/2024 Void works estimated to complete by early February 2025 to enable letting and prgramme completion by end of March 2025. Projected Spend = £2,595,000 Actual Spend (To Date) = £1,254,963 ODS Projected Spend = £127,609.28 ODS Actual Spend (To Date) = 43,609.28 Forecast Remaining Budget = £293,000 |  | 45744 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 33: Key risk - Property in chain falling through with on-going economical pressures of mortgage rates and October budget uncertainty for portfolio holder, i.e., capital gains tax. Mitigations - Pipeline in RRTBR to transfer properties to SHAP (If needed), continue new business opportunities under enquiry to bring into the programme.; 40: 0; 41: 209999.81; 42: 0; 43: 0; 44: 0; 45: 209999.81; 46: 236380.16; 47: 1510000; 49: N/A - On Budget; 51: 0; 52: 0; 53: 0; 66: No; 69: No; 71: Yes; 82: HRA Void works; 84: 127609.28; 117: 0 | [12 empty] | 45580.5546 | adorrington@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
Street Property Acquisitions 24/25 | RRTB annual programme delivering street properties through leaseholder buy-back and open market | N7080 | Development Board | Housing Supply Board |  |  |  | Housing |  | Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | Delivery Total 3/18 homes met PC and LET, 4/17 legally completed with a further 15 to be delivered by March 28th 2025. Next legal completion dates for remaining 13/17: 1) 31/10/2024 2) 31/10/2024 3) 31/10/2024 4) 31/10/2024 5) 12/11/2024 6) 19/11/2024 7) 26/11/2024 8) 04/12/2024 9) 04/12/024 10) 14/01/2025 11) 14/01/2025 12 14/01/2025 13) 14/01/2025 Void works estimated to complete by early March 2025 to enable letting and prgramme completion by end of March 2025. Projected Spend = £4,060,450 Actual Spend (To Date) = £1,243,906.27 ODS Projected Spend = £196,743.18 ODS Actual Spend (To Date) = £18,743.18 Forecast Remaining Budget = -£1,060,450 (This will move into approved RRTBR budget for 2025/26 £3,0000) |  | 45744 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 0; 41: 3000000; 42: 3000000; 43: 3000000; 44: 15000000; 45: 24000000; 46: 1033053.12; 47: 4060450; 48: 1060450; 49: N/A - On Budget; 51: 0; 52: 0; 53: 0; 54: -3000000; 55: -3000000; 56: -15000000; 57: -21000000; 66: No; 69: No; 73: No; 80: Yes; 82: HRA Void costs to bring property to HRA lettable standards; 84: 195743.18; 95: 45399; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Mixed; 106: N/A; 107: 12; 108: 14; 116: No; 117: 14; 118: 6; 124: 45747; 125: Not Applicable; 126: Not Applicable; 132: 45747; 145: 14; 146: 14; 188: On target; 230: 5; 234: 1; 300: TRUE | [12 empty] | 45580.5546 | adorrington@oxford.gov.uk | Y | 45538.1339 | rhaverson@oxford.gov.uk
Street Property Acquisitions 25/26 | RRTB annual programme delivering street properties through leaseholder buy-back and open market | N7080 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 40: 200000; 41: 149999.54; 42: 138692; 43: 0; 44: 0; 45: 288691.54; 46: 0; 48: -149999.54; 54: -138692; 55: 0; 56: 0; 57: -138692; 95: 45399; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Mixed; 106: N/A; 107: 12; 108: 12; 117: 12; 132: 46112; 152: 12; 153: 12; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Street Property Acquisitions 26/27 | RRTB annual programme delivering street properties through leaseholder buy-back and open market | N7080 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Site Identification only | [7 empty] | 40: 0; 41: 500000; 42: 0; 43: 0; 44: 0; 45: 500000; 46: 0; 48: -500000; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45399; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Mixed; 106: N/A; 107: 12; 108: 12; 117: 12; 132: 46477; 159: 12; 160: 12; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45540.2343 | mmcfarlane@oxford.gov.uk
Street Property Acquisitions 27/28 | 12 affordable homes delivered through leaseholder buy-back and market purchase | N7080 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Site Identification only | [7 empty] | 40: 0; 41: 266645; 42: 0; 43: 0; 44: 0; 45: 266645; 46: 0; 48: -266645; 54: 0; 55: 0; 56: 0; 57: 0; 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 12; 108: 12; 117: 12; 132: 46843; 166: 12; 167: 12 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45538.1339 | rhaverson@oxford.gov.uk
Street Property Acquisitions 28/29 | 12 affordable homes delivered through leaseholder buy-back and market purchase | N7080 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Site Identification only | [7 empty] | 40: 0; 41: 34658.79; 42: 0; 43: 0; 44: 0; 45: 34658.79; 46: 0; 48: -34658.79; 54: 0; 55: 0; 56: 0; 57: 0; 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 12; 108: 12; 117: 12; 132: 47208; 173: 12; 174: 12; 187: Annual RRTB acquisition programme | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.1351 | adorrington@oxford.gov.uk
Additional Acquisitions (Sandy Lane) | 12 affordable homes delivered through RRTB | N7081 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Dave Scholes |  | Feasibility | [7 empty] | 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45399; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 12; 108: 12; 117: 12; 125: Planning application submitted; 126: 24/01397/FUL; 128: 45595; 130: 45626; 131: 45646; 132: 46112; 133: 45453; 152: 12; 153: 12; 188: On target; 190: On target; 193: On target; 196: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: 07/12/23 - This relates to The bungalow' site on Sandy Lane - potential to include further sites in future. 26/04/24 - HOT's drafted and with legal. Aiming to be 12 SR (changed from 50/50 split) Target Delivery Dates: - Planning Submission June 2024 - Planning Approval October 2024 - Enter contract November 2024 - Start on Site December 2024 - Practical Completion December 2025 - Defects Period End November 2026 03/06/24 - Planning expected to be submitted this week 01/08/24 - waiting for surveys to be completed before application can be validated. validation expected by end of August 05/09/2024 - planning submission validated 17/10/24 -The application is looking more promising, no further enquires raised by the Planning Officer and the ones that were raised are satisfied, this application has also passed its consultation deadline too. The upcoming committee dates are 19th November and 10th December, so hopeful for the earlier one and one to soon pencil into the calendars.; 300: TRUE; 307: TBC | [12 empty] | 45582.0891 | mmcfarlane@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Additional acquisitions (Maltfield House) | Off-market purchase from County Council to provide 10 x 1-bed flats. | N7081 | Housing Supply Board | Housing Supply Board |  | Regeneration & Economy |  | Housing |  |  |  |  | Andy Dorrington |  | Dave Scholes |  | Feasibility |  |  |  | All necessary Council-side budgets, delegations and approvals are in place for this project (HSB and Development Board approved the draft Cabinet report in Feb/ March 24) and it can proceed into RIBA Stages 3 & 4 as soon as the delivery approach and SDS are agreed. |  |  |  | 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 95: 45399; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 105: County Council; 106: N/A; 107: 10; 108: 5; 109: 5; 117: 10; 120: 45712; 121: 45873; 122: 45921; 123: 46069; 124: 46440; 125: Pre-Application; 127: 45768; 128: 45853; 130: 45910; 131: 46066; 132: 46431; 159: 10; 160: 5; 161: 5; 213: 3/5/24 - The development being commissioned is within the Retained RTB Receipts acquisition programme – with budget agreed in Feb 24 Council. Project approvals April cabinet. A Heads of Terms has been drafted to initiate internal approval processes at both Council’s and inform conveyancing. Legal have been instructed and title and statutory searches are underway as part of the due diligence on land acquisition. A planning application will be supported by the Affordable Housing Supply Team to deliver a 100% affordable housing scheme (through planning condition, not via a s.106 - to ensure full compliance with RRTBR regulations), with a one bed mix to directly address priority housing needs 08/08/26 - HOT going to County. Briefing paper from legal going to HSB in August. 01/10/24 - EOI for tender submissions has gone live with new milestones - planning milestones pushed back a few months e.g. planning submission from Feb to Apr 2025 and consent from May to July 2025; 214: 45413; 215: 45516; 216: 45475; 300: TRUE; 307: TBC | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Additional acquisitions (Sandy Lane & Maltfield House) | 12 affordable homes delivered through RRTB (Sandy Lane) & Off-market purchase from County Council to provide 10 x 1-bed flats (Maltfield House). | N7081 | Development Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Design & Specification | Sandly Lane - HoT's agreed & Planning application validated Maltfield House - HoT's tbc | [6 empty] | 40: 1000000; 41: 1000000; 42: 0; 43: 0; 44: 0; 45: 1000000; 46: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Alice Smith (Heating) | Alice Smith (Heating) | N7084 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | System replaced 2019. sustainability team opportunity for improvements to currnetl systme controls |  | 45747 |  |  |  |  | 40: 200000; 41: 200000; 42: 0; 43: 0; 44: 0; 45: 200000; 46: 0; 47: 200000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Renewal of Solar & Energy infrastructure | Renewal of Solar & Energy infrastructure | N7085 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Feasibility | Feasibility work to establish current conditions |  | 45747 |  |  |  |  | 24: Not started; 25: On budget; 26: On target; 27: Low; 28: Low; 40: 15000; 41: 15000; 42: 15000; 43: 0; 44: 15000; 45: 45000; 46: 0; 47: 5000; 48: -10000; 54: -15000; 55: 0; 56: -15000; 57: -30000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Extensions (5/6 beds) | Extensions (5/6 beds) | N7086 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola | [9 empty] | 40: 300000; 41: 0; 42: 600000; 43: 0; 44: 0; 45: 600000; 46: 0; 48: 0; 54: -600000; 55: 0; 56: 0; 57: -600000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
SHWP Urgent Works | SHWP Urgent Works | N7087 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | Projects being reviewed unlikely need in current year but may form part of D&M need in 25/26 - Slip 500K into 25/26 |  | 45747 |  |  |  |  | 27: Low; 28: Low; 40: 500000; 41: 500000; 42: 0; 43: 0; 44: 0; 45: 500000; 46: 0; 47: 0; 48: -500000; 51: 500000; 54: 500000; 55: 0; 56: 0; 57: 500000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Tower Blocks Additional Works | Tower Blocks Additional Works | N7088 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Multiple remedial works being planned by Fortem - Framework with procurement for Specialist services (PM/CM/CoW, etc) |  | 45747 |  |  |  |  | 27: Low; 28: Low; 40: 1500000; 41: 0; 42: 2500000; 43: 1000000; 44: 0; 45: 3500000; 46: 0; 47: 260000; 48: 260000; 49: N/A - On Budget; 54: -2500000; 55: -1000000; 56: 0; 57: -3500000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Housing for Older People - white goods & communal areas | Housing for Older People - white goods & communal areas | N7089 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Housing Management call demand led - no requests to date this year |  | 45747 |  |  |  |  | 24: On Hold; 25: On budget; 26: Awaiting new Schedule; 27: N/A; 28: N/A; 40: 50000; 41: 50000; 42: 0; 43: 0; 44: 0; 45: 50000; 46: 0; 47: 50000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Digital noticeboards for tower blocks | Digital noticeboards for tower blocks | N7090 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | Orders now being raised on QL for ODS (electrical works) and ITSL group (TV and anti-tamper case). ICT arranging data ports and broadband for all 5 blocks. |  | 45747 |  |  |  |  | 24: On target; 25: Under Budget; 26: On target; 27: N/A; 28: N/A; 40: 50000; 41: 50000; 42: 0; 43: 0; 44: 0; 45: 50000; 46: 0; 47: 50000; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45552.2898 | lminetola@oxford.gov.uk
Capital R&M works investment | Capital R&M works investment | N7091 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  |  | Slip full budget into 25/26 |  | 45747 |  |  |  |  | 40: 2500000; 41: 2500000; 42: 0; 43: 0; 44: 0; 45: 2500000; 46: 0; 47: 0; 48: -2500000; 51: 2500000; 54: 2500000; 55: 0; 56: 0; 57: 2500000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Communal Capital investment works to Council Homes | Communal Capital investment works to Council Homes | N7092 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola | [9 empty] | 40: 4500000; 41: 5620539; 42: 4500000; 43: 4500000; 44: 4500000; 45: 19120539; 46: 67177.48; 48: -5620539; 54: -4500000; 55: -4500000; 56: -4500000; 57: -13500000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
ExternalCapital investment works to Council Homes | ExternalCapital investment works to Council Homes | N7093 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola | [9 empty] | 40: 4500000; 41: 4128040; 42: 4500000; 43: 4000000; 44: 0; 45: 12628040; 46: 1000502.38; 48: -4128040; 54: -4500000; 55: -4000000; 56: 0; 57: -8500000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.2898 | lminetola@oxford.gov.uk
Internal Capital investment works to Council Homes | Internal Capital investment works to Council Homes | N7094 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola | [9 empty] | 40: 3500000; 41: 3877767; 42: 3500000; 43: 3500000; 44: 7500000; 45: 18377767; 46: 1315111.68; 48: -3877767; 54: -3500000; 55: -3500000; 56: -7500000; 57: -14500000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45554.3545 | mmcfarlane@oxford.gov.uk
Tower Blocks - Fire Alarm System Replacement | Tower Blocks - Fire Alarm System Replacement | N7095 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola |  | Design & Specification | Specification updated, PM allocated, soft market testing for prices will determine route of governance. |  | 2026-03-31 |  |  |  |  | 24: On target; 25: Budget to be agreed; 27: Medium; 28: Medium; 33: Staff changes have introduced slight delays, working to re-confirm design.; 40: 0; 41: 0; 42: 800000; 43: 0; 44: 0; 45: 800000; 46: 0; 48: 0; 54: -800000; 55: 0; 56: 0; 57: -800000; 117: 0 | [12 empty] | 45582.2506 | lminetola@oxford.gov.uk | Y | 45554.3545 | mmcfarlane@oxford.gov.uk
Stock Decency Improvement Works (Legislative) | Stock Decency Improvement Works (Legislative) | N7096 | Development Board | Asset Review Group | Development | Housing - HRA (Property) |  | Capital Delivery |  | Malcolm Peek |  |  |  |  | Luca Minetola | [9 empty] | 40: 0; 41: 0; 42: 5000000; 43: 10000000; 44: 10000000; 45: 25000000; 46: 0; 48: 0; 54: -5000000; 55: -10000000; 56: -10000000; 57: -25000000; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Leiden Road | 6 affordable homes | N7097 | Development Board | Housing Supply Board | Development |  |  | Housing |  | Tom Bridgman |  |  | Lila Haracz |  | Dave Scholes |  | Feasibility | Seeking to mobilise this project |  |  | Scheme devt appraisal review to drive expected costs down | OX P to appoint professional services team | Reset budget into budget round (down) |  | 24: Not started; 31: KEY ACTION: Rapid progress on costs and design req'd - review date 16 Oct KEY ACTION: Budget concerns for resolution (esp V4M) - review date 16 Oct; 33: No deliverable scheme yet demonstrated with a programme; 40: 0; 41: 0; 42: 898000; 43: 2705000; 44: 457000; 45: 4060000; 46: 0; 47: 50000; 48: 50000; 51: 450000; 52: 1000000; 53: 0; 54: -448000; 55: -1705000; 56: -457000; 57: -2610000; 66: Yes; 69: Yes; 80: Yes; 82: BLRF demolition - contracted; 95: 45315; 96: Cabinet Decision; 101: Direct Delivery HRA; 102: TRUE; 106: N/A; 107: 6; 108: 3; 109: 3; 117: 6; 118: 6; 119: 6; 125: Pre-Application; 127: 45688; 128: 45838; 130: 46022; 131: 46053; 132: 46477; 159: 6; 160: 3; 161: 3; 188: Off Target; 196: Off Target; 213: Early feasibility stage i.e. getting indicative proposals, surveys, costs; 214: 45348; 215: 45348; 216: 45355; 217: 51.7465; 218: -1.2009; 275: 15000; 276: Joint £30,000 for Leiden and Underhill Agreed at HSB on 13 December 2022 and Developoment Board on 13 February 2023; 281: 0; 282: 1250000; 283: 0; 288: 905535; 289: 0; 290: 812965; 292: 468500; 293: 1718500; 294: 15014; 295: 1733514; 296: 1650000; 297: 7.31; 298: 24; 299: 959777; 300: TRUE; 305: 74825 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Underhill Circus | c.12 affordable homes | N7098 | Development Board | Housing Supply Board | Development |  |  | Housing |  | Tom Bridgman |  |  | James Graham |  | Dave Scholes |  | Feasibility | Seeking to mobilise this project |  |  | Scheme devt appraisal review to drive expected costs down | OX P to appoint professional services team | Reset budget into budget round (down) |  | 24: Not started; 31: KEY ACTION: Rapid progress on costs and design req'd - review date 16 Oct KEY ACTION: Budget concerns for resolution (esp V4M) - review date 16 Oct; 33: No deliverable scheme yet demonstrated with a programme; 40: 0; 41: 0; 42: 698000; 43: 2193000; 44: 509000; 45: 3400000; 46: 0; 47: 50000; 48: 50000; 51: 950000; 52: 2000000; 53: 0; 54: 252000; 55: -193000; 56: -509000; 57: -450000; 66: Yes; 69: Yes; 73: No; 80: Yes; 82: BLRF demolition - contracted; 95: 45315; 96: Cabinet Decision; 101: Direct Delivery HRA; 102: TRUE; 106: N/A; 107: 12; 108: 6; 109: 6; 117: 12; 118: 12; 119: 12; 125: Pre-Application; 127: 45688; 128: 45838; 130: 46022; 131: 46053; 132: 46477; 159: 12; 160: 6; 161: 6; 188: Off Target; 196: Off Target; 213: Early feasibility stage i.e. getting indicative proposals, surveys, costs; 214: 45348; 215: 45348; 216: 45355; 217: 51.7674; 218: -1.196; 275: 15000; 276: Joint £30,000 for Leiden and Underhill Agreed at HSB on 13 December 2022 and Developoment Board on 13 February 2023; 281: 0; 282: 2800000; 283: 0; 284: 0; 288: 1687500; 289: 0; 290: 1687500; 292: 575000; 293: 3375000; 294: 38888; 295: 3413888; 296: 3040000; 297: 6.41; 298: 29; 299: 1496631; 300: TRUE; 305: 53496 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45552.3081 | owain.pearce@odsgroup.co.uk
Additional Units (RRTBR) | Additional Units (RRTBR) | N7099 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Dave Scholes | [9 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5416 | rhaverson@oxford.gov.uk
Additional Programme (RRTBRs) | Additional Programme (RRTBRs) | N7100 | Development Board | Housing Supply Board | Development | Housing - HRA (Supply) |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Dave Scholes | [9 empty] | 40: 0; 41: 0; 42: 0; 43: 0; 44: 0; 45: 0; 46: 0; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.3072 | rnixon@oxford.gov.uk
The MT Vehicles/Plant Replacement Programme | MT Vehicles/Plant Replacement Programme is a rolling programme, the purpose of which to provide a replacement for the Council and ODS fleet within economic lifespans. The current priority for the programme is dust carts, older vans & tippers and grounds maintenance plant as these are now at the end of their economic lifespan, with maintenance costs set to increase. | R0005 | Development Board |  | Corporate Resources | ODS |  | Rolling Programme |  | Jason Munro |  |  |  |  | Owain Pearce |  | Rolling Programme | We have made good progress in decarbonizing our fleet, however we are at the difficult stages of trying convert vehicles that have no suitable charging solution or are expensive to convert to electric. As such every vehicle needs assessing on a case by case basis. Where possible we are looking to extend the life of assets to keep the cost of fleet down for both ODS and OCC. This is to make most efficiency of the fleet whilst keep expenditure down versus trying to improve our green footprint of the fleet. The impact this will have on the Capital programme is a potential carry over every year as we will no longer be replacing on the typical fixed 7 year term. This also means a more detailed management of the running costs across the whole fleet on a continuous basis. Lead times on vehicles has come down so if vehicle running costs increase on a particular asset then we will look to replace asap. As well as a cost benefit to ODS and the Council by extending asset life, there may be scope to decarbonize more of the fleet as newer longer range assets come into the market, EV prices decrease due to the new ZEV mandate, and alternative solutions to infrastructure charging become available. Note that we are still following our previous replacement lifecycle for depreciation (usually 7 years) and the extend life will continue with no depreciation for any additional years beyond its normal life. As such I have reviewed the capital program and estimated a reduction in overall spend for this year. |  |  | There are still a number of electric vehicles outstanding on order, due to one supplier's production delays and space/charging constraints at depots. | The capital program has been reviewed for 2024-25 with carry over from 2023-24. There are many assets to be assessed individually and a continuous monitoring of running costs. However I have estimated the likely replacements for this year at a maximum and reduced the budget accordingly. | We have reviewed the utilization of the ODS & OCC fleet and reduced the fleet size by 10%. This will continue to be monitored and fleet vehicles cut where under utilized. |  | 24: On target; 25: On budget with slippage; 26: Off Target; 27: Low; 28: Low; 30: How this work will progress/will be funded is yet to be determined and agreed.; 33: The project is still subject to planning of replacement Electric vehicles across all services based on Net Zero targets. It is a very complex replacement due to many vehicles being taken home or calculating power requirements at depots and economic considerations. We would like to support OCC’s aim full decarbonization of the fleet by 2030 but this can only be achieved with new infrastructure and some high cost electric vehicles. If we buy diesel now then we are tied in for another 7 years. As such we are deferring replacement of some assets until decisions have been made on future replacement methods and strategy. The biggest risk is vehicles going wrong and the lead times being too long to replace the asset quickly. Therefore we are continuing to keep a fleet of pool vehicles to offset VOR and any unforeseen vehicle issues. The planning of the programme will no longer be as straightforward as it used to be and will require closer monitoring of asset running costs. That being said we have changed the budget to a fixed amount per year and plan to only replace fixed life assets and any assets that are starting to cost more for maintenance or reaching 10+ years.; 34: ODS/OCC strategy & financial model for replacement of vehicles to Electric is an ongoing process. Future budgets may fluctuate due to frequent price changes of orders and the uncertainty of what we might be replacing as diesel or EV or whether we extend the life of assets, however where possible we will fit within the new budget limit.; 37: The Electric Vehicles project, using ESO grant funding, will achieve the target of the electrification of 25% of the ODS fleet by 2023. The timeline for further electrification is dependent on the agreement of the ODS / OCC strategy and financial model currently under discussion. Replacement of ageing vehicles with more carbon efficient models (even if not electric) would contribute to carbon reduction targets.; 40: 5774279; 41: 3500000.19; 42: 7301909; 43: 3256938; 44: 3000000; 45: 17058847.19; 46: 648122.35; 47: 3500000; 48: -0.19; 49: Slippage (Less spend in 24/25 now forecast in future years); 50: Extending life of assets and rolling over budgets; 51: 3500000; 52: 3500000; 53: 10500000; 54: -3801909; 55: 243062; 56: 7500000; 57: 3941153; 66: No; 117: 0 | [12 empty] | 45579.2919 | owain.pearce@odsgroup.co.uk | Y | 45546.2753 | dkerrigan@oxford.gov.uk
Car Parks Resurfacing | Car Parks Resurfacing | T2273 | Development Board |  | Corporate Resources | ODS |  | Rolling Programme |  | Emma Gubbins |  |  |  |  | Oliver Hearn |  | Rolling Programme | Work underway at Ferry Pool Work planned for Gloucester Green and Walton Well Road CCTV upgrade required at Gloucester Green |  | 2025-03-31 | Ferry pool completion during July | Coordination begun for surface repairs to GG bus station - Feb |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 28: Low; 30: On site on Cutteslowe completing planned works. Meadow Lane carpark planning consent achieved with condition to reduce size of carpark. Work to go ahead within next two weeks. All remaining budget will be consumed by year end.; 33: No notable current risks to programme.; 34: Coordination with stakeholders has begun for surface repairs to GG bus station. This work is currently planned for Jan/Feb 25.; 40: 200000; 41: 149999.54; 42: 138692; 43: 0; 44: 0; 45: 288691.54; 46: 42346.62; 47: 288083.77; 48: 138084.23; 49: N/A - On Budget; 51: £120,000 - 130,000; 52: 0; 53: 0; 54: #INVALID OPERATION; 55: 0; 56: 0; 57: #INVALID OPERATION; 66: Yes; 69: No; 70: Yes; 73: No; 80: Yes; 81: Work awarded in line with car park management regime including inspections and reactive work.; 82: Safety repairs, refurfacing, improvements, signage, drainage; 83: Direct Award; 84: £288k; 117: 0 | [12 empty] | 45579.2232 | oliver.hearn@odsgroup.co.uk | Y | 45546.2753 | dkerrigan@oxford.gov.uk
Controlled Parking Zones | Controlled Parking Zones | T2299 | Development Board | Development Review Group | Development | Planning |  | Capital Delivery |  | Tom Bridgman |  |  |  |  | Rachel Nixon |  | Delivery | Paper presented to 7/10/24 Development Board (DB) indicating County Council is requesting the release of £358,080 to cover the review of 7 existing CPZ zones in the city. Recommendation from DB to check whether this would be a key decision and need to go to Cabinet, also to brief LU. DB also supportive of remaining funds (£84,920) being returned to the CIL pot and not re-profiled. Post DB Update - Confirmation that Cabinet decision is required - is on forward plan for December 2024. |  | 2025-03-31 | Release of £358,080 to County Council. |  |  |  | 24: Not started; 25: Budget to be agreed; 27: Low; 30: "13 December 2022 County have agreed to proceed with three of the four schemes on the priority 1 list and Iffley is to be redesigned and hopefully all members from both councils can support this scheme. Next prioritisation list has been agreed by both councils and a paper has been taken to DRB and DG and due at HSG on 13 July. County are now working up the business case to support the documentation for the release of CIL money £500K 14 Sept 2022 - there has been a change of view about the Rose Hill CPZ and as such that is likely to be removed from the prioritisation list 2. discussion are ongoing between County and City officers and members. 10 October 2022 - the agreed programme has been further delayed as city members have raised some concerns - discussions are ongoing so no confirmed programme as yet. 24 Nov decision has been made to progress 3 of the 4 priority 1 schemes no details as to when money needs to be released across to C 10 January 2022 - the County are still awaiting confirmation of the priority 1 schemes and plan to redesign Iffley CPZ as such no timetable as yet for the release of the CIL funding 9 Feb - confirmation has now been received that Upper Wolvercote and Donnington schemes are to be implemented and i am awaiting final prices prior to getting the business case circulated around members and officers. 3 March - I have chased County Colleagues as to what is happening with the business case for the release of CIL money but they are still awaiting final quotes from ODS for the costs of the two schemes that are to proceed. 24 April 2023 57K of the 500K is to be released across to the County Council for the implementation of the two CPZs for U Wolvercote and Donnington .Paper work has been completed and has been forwarded to Democratic Services Initial discussions have been held with County officers to discuss the priorities for the next phase of implementation. No recommendations have yet to be made 8th June 2023 Nothing to add as County are monitoring the implementation and then will review the next priority list"; 33: Cabinet does not agree to release the funds.; 40: 0; 41: 443000; 42: 0; 43: 0; 44: 0; 45: 443000; 46: 0; 47: 358080; 48: -84920; 49: Forecast Underspend at end of project; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 80: Unsure; 81: Oxfordshire County Council are leading on the project for the review of existing Controlled Parking Zones with funding towards this being sought from CIL monies held by the City Council. The release of these monies is subject to Cabinet approval (meeting scheduled for Dec 2024). There may be opportunity for ODS to be involved in the delivery of this review.; 82: See above; 84: Unknown; 117: 0 | [12 empty] | 45581.1089 | rnixon@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
ODS Depot Rationalisation | Consideration of a single depot to support Oxford Direct Services. Development of a recycling transfer station is linked to the Depot Rationalisation. Also the project is currently spread over various Cost Centres. | T2301 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Douglas Kerrigan |  | Feasibility | Work has continued during 2022 to explore using Horspath to accommodate the majority of ODS business to free up other depot sites and to allow for some growth in ODS business. This option was reliant on leasing extra land of a couple of hectares in size to store vehicles and other spill over activity that the existing Horspath depot site would not be big enough to accommodate. Several sites in the vicinity have been looked at but none can accommodate a long lease that would provide the business certainty ODS would need. The city work is now on pause with the agreement that ODS are going to scope out what staying on their existing sites mean and whether they could physically rationalise into the other depot sites freeing up Horspath to save them rental costs. Monitoring of other site opportunities will continue. We await update from ODS in order to feed into confidential scrutiny update requested as part of budget process. |  | 2025-12-19 | Update expected end of August from ODS |  |  |  | 24: On Hold; 25: Budget to be agreed; 26: Awaiting new schedule; 27: High; 28: High; 30: Work has continued during 2022 to explore using Horspath to accommodate the majority of ODS business to free up other depot sites and to allow for some growth in ODS business. This option was reliant on leasing extra land of a couple of hectares in size to store vehicles and other spill over activity that the existing Horspath depot site would not be big enough to accommodate. Several sites in the vicinity have been looked at but none can accommodate a long lease that would provide the business certainty ODS would need. The city work is now on pause with the agreement that ODS are going to scope out what staying on their existing sites mean and whether they could physically rationalise into the other depot sites freeing up Horspath to save them rental costs. Monitoring of other site opportunities will continue. We await update from ODS in order to feed into confidential scrutiny update requested as part of budget process.; 33: Identification of a suitable site to create parking for ODS operations. Feasibility - Review of ODSL operational requirements to include as tender document for RIBA 0-2 reports. Clear and robust gateways to be set for RIBA 0; RIBA 1 and RIBA 2; 34: Re-planning work for this project, with revised scope, will include refreshed timescales and costs; approval will then be sought for an updated Capital budget, as appropriate. Additional land to support potential development at Horspath is essential; 37: Anticipated that this will be a Net Zero Carbon Facility. Sustainability brief has been developed in collaboration with Paul Spencer.; 40: 0; 41: 266645; 42: 0; 43: 0; 44: 0; 45: 266645; 46: 0; 48: -266645; 54: 0; 55: 0; 56: 0; 57: 0; 65: HL; 66: No; 77: TBA; 78: N:A currently in feasibility stage.; 80: Yes; 82: Reinstatements and fit outs within main contract; 92: DRG; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3394 | vgalvin@oxford.gov.uk
Cowley Marsh Extension | Return of Cowley Marsh Depot to original footprint following temporary extension. | T2309 | Development Board | Development Review Group | Development | Regeneration & Economy |  | Capital Delivery |  | Carolyn Ploszynski |  |  |  |  | Douglas Kerrigan |  | Delivery | Area now in use by public Awaiting advice on hedge planting from ODS arboricultural services. The row of Cypress trees on the boundary with the CM yard have been removed as an additional cost to the project. These had been neglected and were in a dangerous condition. This was reported at a previous board several months ago and budgeted at £14k. The final account is due to be closed out once the hedging costs are know and if they can be planted this season |  | 2024-06-28 | Discharge of planning conditions can now proceed following completion of all works (subject to hedge planting) Stated as November so that will be the date on discharge | Hedge planting during November 2024 |  |  | 24: On target; 25: Over budget; 26: On target; 27: Low; 28: Low; 30: All preparation complete for wild flower meadow Agreement to over run by LPA to plant in Spring 2023; 33: None; 34: Dangerous trees were never in original budget-estimate for all works related is £15-20k Planting of hedgerows to be completed along with areas of planting damaged by wet weather; 40: 0; 41: 34658.79; 42: 0; 43: 0; 44: 0; 45: 34658.79; 46: 100; 47: 34658.79; 48: 0; 54: 0; 55: 0; 56: 0; 57: 0; 66: No; 69: No; 70: Yes; 73: No; 74: Yes; 77: n/a; 78: ODS; 80: Yes; 81: Dismantling of previous use fittings and paving and restoring to agreed planted area for public use; 82: main works; 83: Already Awarded; 84: 225000; 92: DRG; 117: 0 | [12 empty] | 45579.9946 | dkerrigan@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Business intelligence unit (BIU) | To set up a virtual BIU to allow for flexible use of our analytical capabilities in order to become a data driven, evidence based organisation |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - BIU | Mish Tullar |  |  | Sally Hicks | Sally Hicks |  | Sally Hicks |  | Completed |  | 2021-04-01 | 2023-12-31 |  |  |  | 2024-04-30 | 24: Completed; 25: Completed; 26: Completed; 27: Medium; 29: Completed; 30: 1. Full report of Residents’ Survey results completed and disseminated to members in December 2023. 2. Summary of Residents’ Survey results presented in a Let’s Talk session on 18th January and Locality Learning session on 7th February. 3. Draft Corporate KPIs taken to CMT on 8th January and 29th January for further discussion and feedback. 4. Corporate KPIs to be taken to Scrutiny on 22nd January for further discussion 5. Date confirmed for next Oxfordshire Analyst Networking event (28th February 2024). Preparation for event has started. 6. ArcGIS training commenced. ArcPro access has been granted to Corporate Data Analyst and BIU Lead. 7. Origin-destination, Vacant Dwellings and Socio-Economic Grade Census 2021 reports produced Census Teams channel. Additional Census reporting to follow shortly. 8. BIU input in the development of a paper relating to SED (socio-economic duty) and if this will be adopted by the council; 31: 1. Power BI dashboard development for Corporate KPIs to commence once Corporate KPIs have been determined. Proposal for front door of change submitted (some updates required). 2. Finalisation of Corporate KPIs – baselines and targets to be determined. 3. Service Area level KPIs development has commenced with Service Areas asked for feedback by March/April 2024). KPIs to incorporate Oflog updates where relevant 4. Data for the Corporate Strategy to be collated in February. 5. BIU to support with CEX channel shift programme (Council Tax and Benefits) to understand who/where to target and to measure the impact of this work. Details of exactly what is required currently TBC. 6. Landlord data segmentation project request from Environmental Sustainability team. Details and timings TBC. 7. LGA Inform tools review to inform use of tools across the organisation – January/February.; 34: Capacity has now been received for all analysts and is extremely limited for the rest of this year. Risk that the core team (Sally Hicks and Carlos Barrero) will start to go over capacity as more projects come on board. November and December will be a particularly busy time for the BIU as census data is released. Additional support from Business Analysts on BIU projects agreed in light of limited capacity from analysts. An additional analyst from sustainable cities has also been confirmed and will become part of the virtual analyst team.; 35: • Capacity of analysts remains very limited. Corporate Data Analyst will go on maternity leave at end of March. Cover is currently being recruited for but capacity of BIU Lead could become stretched over the next few months.; 97: Right; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Citizen Experience Strategy and Programme | Citizen Experience workstream |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Helen Bishop |  |  | Vicki Galvin | Vicki Galvin |  | Vicki Galvin |  |  |  | 2022-06-06 | [5 empty] | 24: At Risk; 25: On budget; 26: At Risk; 27: Medium; 29: Off Target; 30: Strategy - Press release re: progress made against strategy in first year submitted. Readiness actions and culture maturity assessment actions now merged with CEX programme tracker with monthly update requests issued. Culture - CEX Culture Maturity assessments completed with Corporate Property and booked for Law & Governance. Artificial Intelligence - Supporting development of Corporate AI Policy. Procurement Exemption agreed for Sabio to complete Intent Capture & Analysis in the Contact Centre to help determine any further efficiencies that could be fed into the budget. Channel Management Plan - outline drafted with support from Customer Services and Comms. Comms - FftF Comms Plan agreed and campaign to raise awareness of FftF and the programmes within it launching 23rd September. Video introducing the Change Support Team created and on the intranet. CEX Projects: Building Control - Exploration of online booking system paused until Service have capacity. Online payment to be included in phase 3 Civica Pay development. Jadu forms developed and ready to go live - just need links adding to appropriate webpages. Housing Needs - General Register application Jadu form project complete. Have agreed to support Service with a TO BE map for the new Housing Needs system so Service can suggest savings the new system may bring. Bulky Waste - ODS Board awaiting resource to complete feasibility for the online booking proposal from the web developer. Have agreed that in the meantime a Lead from OCC and ODS will work together with support of a BA to review our original feasibility report and the other options outlined and draft a one page report on whether any of these can/should be taken forward in the meantime or as an alternative.; 31: Culture - CEX Culture Maturity Assessment completed by Law & Governance (3rd Oct). Artificial Intelligence - Intent Capture & Analysis work underway in the Contact Centre. Channel Management Plan - report brought to OCB to agree next steps. Comms - Let's Talk and Leadership Conversation delivered with weekly articles in Connected Council underway. CEX Projects: Building Control - Webforms live. Housing Needs - Re-map GR process to determine interim efficiencies. TO BE map for new Housing Needs system. Bulky Waste - Agreement reached on how to progress webform on ODS or OCC website.; 32: Benefits status remains off target due to delays out of our control re: the implementation of the online Housing General Register application form, QL Tenants Portal, promotion of the online Revs and Bens forms and ICT capacity to build new online forms.; 35: Benefits Tracker being updated correctly and on a monthly basis.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Taxi Licensing | Work with the Licensing and Applications team to implement Victoria Forms and understand how else the process of applying for and renewing a taxi license can be improved for both the customer and staff through simplification and automation. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Ian Wright |  |  | Vicki Galvin | Vicki Galvin |  | Vicki Galvin |  |  | Will report at the Workstream level | 2022-06-13 |  |  |  |  | 2023-04-01 | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Tactical changes | - Gather baseline information on progress made against the tactical changes that were generated from the Customer Experience workshops delivered 2021-22. - Establish an ongoing reporting method for these and any new tactical changes agreed. - Share learning and successes as appropriate and provide support with blockers where relevant. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Ian Wright |  |  | Vicki Galvin | Vicki Galvin |  | Vicki Galvin |  |  | Will report at the Workstream level | 2022-08-23 | 2024-05-01 |  |  |  |  | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 30: None.; 31: Monthly review of tracker at CEX Delivery Board.; 33: 1. Monthly reminder email to be sent out. Any ongoing outstanding updates to be flagged to OCB. 2. VG to review updates monthly, monitor issues/blockers highlighted and look at how we can support where possible.; 34: 1. Update requests not completed. 2. Progress not being made against tactical changes and therefore benefits not realised."1. Monthly reminder email to be sent out. Any ongoing outstanding updates to be flagged to OCB. 2. VG to review updates monthly, monitor issues/blockers highlighted and look at how we can support where possible."; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Building Control | Work with the Building Control team (and relevant Applications and Contact Centre Officers) to understand how the process of customers submitting Full Plans or Building Notice applications can be improved for both the customer and staff through simplification and automation. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Ian Wright |  |  | Vicki Galvin | Vicki Galvin |  | Vicki Galvin |  |  | Will report at the Workstream level | 2022-07-18 | [5 empty] | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 30: Revised Business Case approved at OCB. Specification for CivicaPay drafted and being shared with Anna W for comment and progressing. Jadu form due to be developed - ICT resource allocated.; 31: Specification shared with CiviaPay for quote. Jadu form development underway.; 32: Back and forth with Business Case caused delays. Agreed Option in Business Case provides minimal savings.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.088 | rlabellarte@oxford.gov.uk
Freedom of Information Requests | Reviewing how Freedom of information requests are handled and making recommendations about improvements through simplification and automation. Process mapping, analysing FOI requests and reviewing current IAG provided. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Ian Wright |  |  | Vicki Galvin | Vicki Galvin |  | Vicki Galvin |  |  | Will report at the Workstream level | 2022-05-25 | [5 empty] | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 30: None. Project completed.; 31: None.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
M365 Programme | Implementation of Microsoft 365 - full capability |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Isaac Durno |  | Isaac Durno |  |  |  | 2022-06-08 | 2024-12-31 |  |  |  | 2024-04-01 | 24: At Risk; 25: Budget to be agreed; 26: Off Target; 27: Medium; 29: At Risk; 30: M365 has now seen the successful implementation of Outlook, OneDrive and associated products. Learning Pathways continues to be updated and FAQs updated to reflect organisation questions.; 31: IT - working on options to hide U drive / minimse access Onboarding of supplier to support the organisation with SharePoint Organisation to tidy up M drives, and reduce down data.; 32: Due to resources being unavailable within IT, as well as technical issues upon delivery and adoption resourcing shortage, there has been significant delay in the delivery of the project. There is also the reliance on a third party support for the next stage of the programme; 33: IT resources / Adoption Resources; 34: That moving large batches does not work and we need to try lower numbers. Escalation with third party supplier; 35: None at this time; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Telephony replacement | Replacement of the Council's telephony solution |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Rocco Labellarte |  | Rocco Labellarte |  |  |  | 2020-09-08 | 2024-11-30 |  |  |  | 2024-10-18 | 24: Off Target; 25: On budget; 26: Off Target; 27: Low; 30: Extended UAT completed; 31: Prep for go live; 32: The project was delayed due to 8 month wait to get all approvals to award contract. A subsequent issue with BT disabling 01865 numbers has caused further delays. We are working through this issue as of 16th September. This should complete by mid October.; 34: Delays in signing contract. Accept; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
GIS replacement | Replacement of the Council's GIS solution |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Rocco Labellarte |  | Rocco Labellarte |  |  |  | 2021-09-16 | 2023-07-28 |  |  |  | 2023-07-28 | 24: Completed; 25: On budget; 26: On Target; 27: Low; 30: Project delivered.; 31: Close project; 34: That services that do not propose evaluators will not have input into the scoring of the tenders. Provide list of evaluators to CTIO and ask provide opportunity to services to support the evaluation; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Forms replacement | Replacement of the Council's web form solution |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Rocco Labellarte |  | Rocco Labellarte |  |  |  | 2022-03-03 | 2023-03-31 |  |  |  | 2023-04-28 | 24: Closed; 25: Completed; 26: Completed; 27: N/A; 29: Completed; 30: Project completed; 34: That if forms are not signed off, when Lagan is decommissioned citizens will not be able to contact the council for their services. "Ask that all service areas provide names of staff that can support the 1. sign off of forms after testing 2. Confirm what to do with forms that have not been used for a year 3. Confirm the change of content required if forms are to be removed"; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Lagan replacement | Replacement of the Lagan CRM solution. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Rocco Labellarte |  | Rocco Labellarte |  |  |  | 2022-07-01 | 44958 |  |  |  | 44957 | 24: Completed; 25: Completed; 26: Completed; 27: N/A; 29: Completed; 30: Lagan Decommissioned. Project completed.; 32: Getting approval for the contract type has taken some time.; 34: Engagement from resources for the project. Continue communication and accept risk; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Netcall Replacement | Replacement of Contact Centre Telephony (Netcall) |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Rocco Labellarte |  | Rocco Labellarte |  |  |  | 2022-07-01 | 45107 |  |  |  | 45535 | 24: Off Target; 25: On budget; 26: Off Target; 27: Medium; 29: On target; 30: RFQ Published in early October; 31: Tenders to be assessed and contract awarded.; 32: Delays waiting for Procurement to advise on route to market and Crown Commercial Services being late with Network Services 3 framework.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Flexible Working: Technology, People, and Workplace | This programme is to implement a long term Flexible Working approach for Oxford City Council. It has three workstreams; People, Workplace and Technology. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Jane Winfield |  |  | Isaac Durno | Isaac Durno |  | Isaac Durno |  |  |  | 2022-02-07 | 45142 |  |  |  | 44974 | 24: Completed; 25: Completed; 26: Completed; 27: N/A; 29: Completed; 30: Closure of Flexible Working programme, as this has now moved into various business areas: Team Principles and associated work - now sits within the People Team Move to the Town Hall, phase 2 and associated work - now sits with Tom Bridgeman; 31: Scanning report to go to OCB - February 2024. This will be the last element of the former programme.; 32: N/A; 33: People Programme - H&S, Future Workplace Programme; 34: "1.Technical resource in IT to support with full-scale M365 adoption and analysis of requirements ahead of roll-out 2. Delay in Microsoft 365 programme will result in poor perception of IT and/or programme 3. Lack of change management resources to support roll-out in timescale required for M365 this may impact adoption and understanding across OCC 4. Limited resources in People workstream to complete contract and policy recommendation which may result in complaints from staff 5. H&S - roll-out of new DSE assessment will likely lead to requests from staff for equipment for remote working" "6. Assurance and due diligence technical architect supporting and reviewing approach 7. Further communications to be published with update when migration plan is established 8. Keep project board updated and discuss adoption plans and limitations 9. Re-prioritise projects and workloads and discuss OCC priorities 10. Clear DSE guidance and cost of remote working kit and package"; 35: N/A; 36: N/A; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Integrated Business Planning - service reviews | Embedding a new process integrating budget setting, business planning, service planning and the change programme, enabling members to make informed decisions about how to balance the budget in the Medium Term Financial Plan. 2 review meetings with each Service, health check meetings, information gathering and budget reporting, consultation and scrutiny. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Nigel Kennedy |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-04-01 | 2023-02-28 |  |  |  | 2022-07-26 | 24: At Risk; 25: On budget; 26: On Target; 27: Medium; 30: Service review meetings; 31: Continue service review meetings; 32: Budget balanced for 4 years however risk of adverse variances from budget monitoring, for example income from companies, commercial rents and carparks.; 34: Adverse variances from budget monitoring, for example income from companies, commercial rents and carparks.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Assets Review | To drive and profile additional income from our assets and services within the next four-year Medium Term Financial Plan, balanced against an assessment of risk and resource |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Nigel Kennedy |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-06-01 | [5 empty] | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 30: Update to OCB and CMT; 31: Move reporting of this programme to Development Board; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Reducing Third Party Spend | Improving contract management within the organisation, creating a contracts register, reviewing all contracts in phases, staff training, information and guidance, trialing prompt payment |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Nigel Kennedy |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2021-08-02 | 2022-12-31 |  |  |  | 2022-06-30 | 24: On Target; 25: Over budget; 26: On Target; 27: Medium; 29: At Risk; 30: Third round of contract reviews; 31: Continue contract reviews; 32: Savings associated with Reducing Third Party Spend project for 23/24 may not be achievable due to economic climate and inclusion of sustainability, equality and diversity (including Oxford living wage) and social value in contracts. Savings targets will be reviewed in the next budget round.; 34: Some services not challenging price increases in contracts. Comms around contract management. Promote free online contract manangement training course; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Commercial Framework | Creating a commerical framework to strengthen our income generation/commercial activity, in OCC, in a way that supports our design principles, wider economic and environmental objectives and our mixed service delivery |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Nigel Kennedy |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-06-01 | 2023-12-31 |  |  |  | 2022-10-18 | 24: Off Target; 25: On budget; 26: On target; 27: High; 30: Commercial Framework to ODG; 31: Leadership Conversation 19th September. Build into service reviews; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Freedom of Information Requests - discovery | Reviewing how Freedom of information requests are handled and making recommendations about improvements through simplification and automation. Process mapping, analysing FOI requests and reviewing current IAG provided. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Citizen Experience | Ian Wright |  |  | Vicki Galvin |  |  | Vicki Galvin |  |  | Will report at the Workstream level | 2022-05-25 | 2022-07-31 |  |  |  | 44742 | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 30: None; 31: None; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Agresso Upgrade | Replacing Agresso on premises with cloud version. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Digital & Technology | Ian Brooke |  |  | Rocco Labellarte | Anna Winship |  | Anna Winship |  |  |  | 2022-03-01 | 2024-02-05 |  |  |  | 44926 | 24: On target; 25: On budget; 26: On target; 27: Low; 29: On target; 30: cycle 3 of UAT preparation to begin in November. three issues now resolved to allow us to proceed; 31: cycle 3 of UAT, training; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Operating model reviews | People Team Operating Model |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Vanessa Wilson |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-08-24 | 2023-10-31 |  |  |  | 2022-10-04 | 24: Completed; 25: Completed; 26: Completed; 27: N/A; 29: On target; 30: People operating model benefits reviewed and added to tracker (under operating model and People programme); 31: Implement actions and track benefits; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Operating model reviews | ICT operating model |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Finance | Vanessa Wilson |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-06-24 | [5 empty] | 24: Off Target; 25: On budget; 26: On Target; 27: Off Target; 30: Draft operating model slide deck prepared and shared with Tom and Helen for feedback. Changes made; 31: Paused; 32: Paused by Tom Hook; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Demand Management | Understanding our customers and what drives demand. Delivering demand management interventions. Building expertise in demand management. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - Smart Council | Carolyn Ploszynski |  |  | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-06-01 | [5 empty] | 24: On Target; 25: On budget; 26: On target; 27: Low; 30: Wrap up sessions pilot teams. Began work with planning (focus webpages), CSO managers (focus CSO conversations about cost of living support), Locality Operating Managers (focus people in OCC understanding and engaging with the localities network), Tenancy Management (focus call about tenancy issues going to the right place). Sorting out handover; 31: Continue work with new project teams. Follow up pilot groups recommendations and further tracking. Investigate wider use of text messages instead of letters. Scope demand management work going forward following change of PM.; 35: Team capacity; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Benefits Realisation Tracking | Putting in place a benefits realisation tracking mechanism and process, in collaboration with the Senior BA, for reporting to governance boards. |  | Organisational Change Board | Organisational Change Board | [7 empty] | Lauren Doggett | Lauren Doggett |  | Lauren Doggett |  |  |  | 2022-05-03 | [5 empty] | 24: On Target; 26: On Target; 27: Low; 30: Tracker updated following audit recommendations. Tracker updated monthly and reviewed at OCB quarterly; 31: Tracker to be updated monthly and reviewed at OCB quarterly; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
People Programme - Onboarding & Induction | Review and improve corporate induction and onboarding process |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 2023-03-31 |  |  |  | 2023-01-31 | 24: Completed; 25: On budget; 26: Off Target; 27: Low; 29: Completed; 30: New Corporate Induction was launched in May 2023. This workstream is now complete.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
People Programme - Recruitment | - Develop inclusive recruitment processes and practices to improve the diversity of candidates and recruits. - Develop training for managers to improve capability and selection decisions. - Improve recruitment processes to deliver efficiencies and service quality improvements through better use of iTrent's recruitment module |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2024-04-01 | 2025-03-31 |  |  |  |  | 24: On target; 25: On budget; 26: On target; 27: Low; 29: On target; 30: Recruitment audit completed and findings reviewed. Drafting inclusive recruitment training and guidance.; 31: Schedule inclusive recruitment training July to October 2024. Launch Hiring Managers Network. Explore iTrent new recruitment module.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Flexible Working [& Digital Skills] | - Support the move to flexible working - review contracts and policies and develop guidance. - [New for 2023-4]: Develop support, training and materials to enable staff to use technology effectively in the hybrid working environment, and to support customers to self-serve. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 2024-03-31 |  |  |  | 45382 | 24: Completed; 25: Completed; 26: Completed; 27: Low; 29: Completed; 30: Initial Flexible Working workstream completed.; 31: Finalise details of flexible working workstream 2024-25, incorporating elements of the former Smart Council programme.; 33: Flexible Working Programme - workplaces and technology workstreams.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
HR policy & guidance - Introduce new accessible, customer-focused approach | Review of HR policy format/approach, starting with Disciplinary Policy. This will then become the template for other policies that can be rolled out as they are each updated and reviewed |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-04-01 | 2023-03-31 |  |  |  | 2023-03-31 | 24: Completed; 25: On budget; 26: On Target; 27: Low; 30: Disciplinary Documents and new policy approach approved and published.; 31: A schedule of policy reviews has been agreed for 2023-24 and is now Business As Usual.; 34: 1. Disagreement around proposed approach with the TU's 2. Capacity within the team given volume of work 3. Working to agree outcome of consultation with Unison and Unite by 25th October 4. Working to complete reports for November Council meeting. Review priorities for remaining policies."; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Support a healthy working environment | Build on work to date to raise awareness and promote well-being |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-04-01 | 2023-03-31 |  |  |  |  | 24: Completed; 26: Completed; 27: Low; 29: On target; 30: Wellbeing Week delivered in May, follow-up survey analysed and shared with CMT and Partnership Working Group. Activities for the remainder of 2023-24 will be incorporated into the Diversity & Inclusion workstream.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Operational effectiveness of People Services | Embed and maximise effectiveness of People Team Service Desk. Review and simplify Job Evaluation Process, Payroll and Operational Support Service processes. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 45383 | 2025-03-31 |  |  |  |  | 24: Off Target; 25: Budget to be agreed; 26: On target; 27: Medium; 29: Off Target; 30: Majority of staff now using People Team Service Desk. Working to iron out issues faced with ASM and investigating alternative options.; 31: Contributing to ASM retender. Exploring iTrent alternatives to ASM.; 32: ASM not delivering efficiency, demands on the admin team are increasing and demands of operational recruitment support delaying recruitment process improvements. Working on options to mitigate.​; 33: ICT and Alemba capacity for implementation.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Build People Team capability | Implement new People Team structure |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 44652 | 44773 |  |  |  | 44743 | 24: Completed; 25: On budget; 26: On Target; 27: Low; 30: No further updates this month.; 31: Close this workstream 31/3/23 and move it into business as usual.; 34: competitive recruitment market. using a new recruitment supplier; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Leadership Development | Design & deliver Leadership Development Programme focusing on one area of people management practice - managing and motivating performance |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 45382 |  |  |  | 2024-03-31 | 24: Completed; 25: On budget; 26: On target; 27: Low; 29: On target; 30: 14 managers completed coaching accreditations. Leadership Challenge Groups have been putting together recommendations. Candid and Caring training updated, trialed with Law & Governance Team, and opened to all employees for bookings. Aspiring Management Programme and mentoring scheme launched.; 31: Complete procurement and onboarding of provider for Aspiring Managers training.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Performance Management - establish an effective approach | Establish an effective approach to performance management and equip managers to have meaningful conversations about performance |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 2023-03-31 |  |  |  | 2022-12-31 | 24: Closed; 25: Closed; 26: Closed; 27: N/A; 29: Closed; 30: This workstream has been merged with the leadership development workstream.; 31: See Leadership Development workstream; 32: Capacity in team. Difficulties recruiting Talent Business Partner.; 33: Engagement of heads of service and management teams; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Career and workforce development | Support career and workforce development |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 2024-03-31 |  |  |  |  | 24: Completed; 25: Completed; 26: Completed; 27: Low; 29: Completed; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Pay and reward | Review and re-design pay framework to meet organisation needs. Implement new pay structure and improve the benefits offering. |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-05-01 | 2025-03-31 |  |  |  | 45596 | 24: On target; 25: On budget; 26: Off Target; 27: Medium; 29: On target; 30: Detailed project plan in place. Meetings with Heads of Service complete. Now aiming to take to Council October.​; 31: Finalise pay structure design. Further consultation with union reps.​ Make recommendation on Microsoft discount offer​; 32: Running 3 months behind schedule as extra data review was required, adjustments to design made following feedback from unions, and other work pressures; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Develop culture of equality, diversity and inclusion | Encourage services to build an inclusive culture and improve our diversity & inclusion capability: - complete Disability Confident actions - design and deliver EDI training at 3 levels - development of staff networks |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2024-04-01 | 2025-03-31 |  |  |  |  | 24: On Target; 25: On budget; 26: On target; 27: Low; 29: On target; 30: EDI training level 1 – dates set and available for booking on iTrent.; 31: First meeting on Disability and neurodiversity network; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Values & Behaviours | Embed the organisation's values and behaviours across all areas of work |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-03-01 | 2023-03-31 |  |  |  |  | 24: Completed; 25: On budget; 26: On Target; 27: Low; 30: Banner on organisational values ordered for Town Hall. Values & behaviours incorporated into recruitment campaigns.; 31: This workstream will be incorporated into Business as Usual and all other workstreams from 31st March 2023.; 34: Competitive recruitment market.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Layers and spans | Assess current position and identify opportunities by addressing layers and spans across the orgnisation |  | Organisational Change Board | Organisational Change Board |  |  |  | Change - People | Nerys Parry |  |  | Becky Willis | Becky Willis |  | Becky Willis |  |  |  | 2022-09-01 | 2023-03-31 |  |  |  | 2023-03-31 | 24: On target; 25: On budget; 26: At Risk; 27: Low; 30: No further update.; 31: With Tom Hook for updates.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Leisure and Health Inequalities | “A service which puts the needs of communities at its heart, providing a range of accessible and inclusive activities, plays an important role in tackling the climate emergency, reducing health inequalities, and supports the delivery of a multitude of policy objectives.” working vision Strengthening our relationships with health to address health inequalities |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Change | Stephen Gabriel | Ian Brooke |  | Ian Brooke | Ian Brooke |  | Ian Brooke |  |  |  | 2021-12-01 | 2024-03-01 |  |  |  | 2022-09-30 | 24: Completed; 25: Completed; 26: Completed; 27: Medium; 29: Completed; 30: - Leisure contract successfully mobilised - Client meetings set in calendar going forward - Future Active Lifestyles Commissioning set; 31: - Although this doesnt fall under this project we have a meeting with Fusion to deal with moneys owed and dilaps.; 35: None at the time of reporting; 36: None at the time of reporting; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Countywide rough sleeping |  |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Change | Stpehen Gabriel | Nerys Parry |  | Nerys Parry | Richard Wood |  | Richard Wood |  |  |  |  | 2024-03-01 |  |  |  |  | 24: On Target; 25: On budget; 26: On Target; 27: Low; 29: On target; 30: New Alliance of providers with experience of delivering locally in place. Contract commenced 1/4/22. Alliance has constituted working groups to oversee and deliver transformation. Housing First units and other accommodation for move on progressing. RSI funding outcome delivered for next 3 years, with majority of Countywide ask received. Floyds unable to return to pre-covid head count is posing a major funding challenge, with work to find a one year solution for 23-24, ahead of a long term solution from 24-25. Difficult conversations have been ongoing on the Alliance budget between the Alliance, City, County and Districts throughout January and February to inform budget priorities, as we aim to support the Alliance to set a balanced budget for 23-24. We have now reached agreement and the Alliance Budget signed off, this will see service reductions in light of a flat budget and rising costs, with most service reductions impacting prevention services provided by Aspire and Connections, as we sought to protect Accommodation services, with us only losing 5 units that were due to transfer to the Alliance that no longer will go ahead, down from an earlier proposal that would have saw us lose 28.; 31: While providing short term flexibilities at Floyds Row to allow for sustainability in 23-24, DLUCH have confirmed they will not fund communal accommodation including Floyds Row from 24-25, meaning our model for the Floyds Row assessment centre is no longer viable. In regard 23-24, we have been working closely with DLUHC and St Mungo’s to increase capacity in FR to help make the model more sustainable, alongside additional contributions from RSI funding and our County and District partners. All but two partners have now confirmed their contributions, and we have now escalated with them both. A new lease agreement with St Mungos is outstanding due to reassurance wanted from them on us sharing risk on Housing Benefit income, but will be signed imminently. We are now focused on the longer term challenges with Floyds, and designing a sustainable model for the services it offers such as SStS from 24-25. A working group is being put together involving the City Council, St Mungos and Homelessness Oxfordshire to lead this work.; 33: Continued close monitoring of progress at countywide steering group of the progress the Alliance is making, and of the supply of homes for Housing First. Close working with DLUHC and St Mungoes on options for FR. Manager within Housing Needs sits within the Allaince leadership team that is working on the Allaince budget.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Housing needs Transformation |  |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Nerys Parry |  | Nerys Parry | Richard Wood |  | Richard Wood | [9 empty] | 24: Completed; 25: Completed; 26: Completed; 27: N/A; 29: Completed; 30: All transformation learning strands have now delivered their findings. These have informed an agreed plan on implementation across 4 strands and supported by a restructure within Housing Needs. New Housing Needs Structure launched on the 14th of November. Staff have moved to new roles, and new teams are working with clients.​ The considerable risk of the launch impacting statutory homelessness services was managed effectively, with no significant issues experienced.​ Housing Needs staff had an away day event at the Town Hall on the 16th to mark the launch, and support training and culture change. Significant amount of work carried out through December to update process and working practice to align with new approach.; 31: Following launch of new structure, work continues to embed new ways of working and new procedures, and will continue into the new year. Strong ongoing emphasis on establishing right culture. Work will carry on for next few months to further develop the new teams process, procedure and working practice. Significant amounts of work needed to bring together new prevention and rapid rehousing teams. The new management team has overall ownership of delivering the transformation beyond the new structure with new process, policy, approach and culture, supported by 3 key task and finish groups covering homelessness prevention, TA and PRS. Lessons learnt to be completed with HR and Trade Unions following restructure, with learning for the organisation for future similar processes in other areas; 33: HN management monitoring demand closely to see if December was a one off bad month, or part of a new trend (with possible links to strain in other parts of public sector, such as NHS leading to more urgent discharges, or issues with young people’s accommodation services at County). Changes are being made to our Housing Options service to increase capacity to take more presentations, and to utilize new structure which better enables resources to be moved between teams based on changing demand.; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Home Improvement Agency delivery model | Compare service delivery provided by HIA in RS&CS with service provided to tenants in Council stock |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Wright |  |  | Becky Walker |  | Becky Walker |  | Completed |  | 44652 |  |  |  |  | 44834 | 24: Completed; 25: Completed; 26: Completed; 27: Low; 29: Completed; 30: This is still completed - Please Close; 31: This is completed - Please Close; 32: N/A; 33: None identified; 35: None; 36: Please close as completed; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Landlord Services Transformation / Tenant and Leaseholder Survey | The primary objective is to secure both legislative compliance and service improvements to Council tenants and leaseholders which involves more efficient joint working across a whole variety of teams across the Council and ODS delivering a more coherent service Follow the publication of the governments SHWP in November 2020, Simon Warde was seconded in March 2022 to become the SHWP Project Lead with a primary focus in ensuring OCC achieve compliance. The 2022 Tenant & Leaseholder (perception) survey is a criteria of the SHWP and will be run by Simon's backfill (Wendy Hind) |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Change | Stephen Gabriel | Nerys Parry |  | Bill Graves | Simon Warde |  | Simon Warde |  |  |  | 44683 | 45016 |  |  |  | 44739 | 24: On target; 25: On budget; 26: On target; 27: N/A; 29: On target; 30: SHWP # Approx 13 properties remain that require a carbon monoxide alarm install (all properties are capped) # Building Safety Engagement Officer started in post. # Resident Engagement Plan for the Tower Blocks (including time line) has been drafted. # Project Involvement Brief for the Tower Blocks has been completed. # Self-assessment of OCC’s compliance against the Consumer Standards ongoing. # Social Housing Regulation Bill remains in Final Stage at House of Commons.; 31: SHWP # Self-assessment of OCC’s compliance against the Consumer Standards and full Landlord webpage review. # Start the Resident Engagement Program for the tower blocks.; 36: Note the above; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Selective Licencing | Implementation of Selective Licensing |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Wright |  |  | Katherine Coney |  | Katherine Coney |  | Completed |  | 44672 | 45254 |  |  |  | 45169 | 24: Completed; 25: Completed; 26: Completed; 27: Low; 29: Completed; 30: Closure report presented to OCB; 31: BAU; 33: Key risks still exist around recruitment to allow BAU; 36: Closure report to be noted; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Face-to-Face at Westgate Library | Relocation of face to face co-locating at Westgate Library with CAB. |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Helen Bishop |  |  | Mark Chandler |  | Mark Chandler |  |  |  | 44531 | 45169 |  |  |  | NA | 24: Closed; 25: On budget; 26: On Target; 27: Low; 29: Closed; 30: "- Report being refined for submission to CMT - Customer satisfaction has remained strong with 99% of customers surveyed YTD rating the service in Westgate as Good or Average"; 31: as above; 33: - There is a scanner available in the library which we can use if necessary for urgent scanning requests. We have explored with the library whether they could provide us with a "private space" to have 1-1 conversations with customers but unfortunately, they do not have anything available at the moment. Nerys Hughes has secured a private meeting room in the Town Hall for Housing customers to use. We will also be asking the library the costs for a "Pod" to use as a private space when we look to renew our agreement with them in January - The issue with connectivity has been flagged to ICT who have a solution to boost the signal which will be put in place as part of the move to the new space - We continue conversations with Property Services, County and the library with the intention of extending the contract to use the library for our Face to Face service for another year at least. They have offered a room to use but after reviewing the size it is clear that OCC and Citizens Advice will not be able to use the space at the same time. However we are keen to continue the collaboration between OCC and CAO which has been successful over the last year. A new proposal has now been agreed to use a space in the library to the right of the Reception area as you walk in to the 2nd floor. A plan of the area has been drawn up and all parties are in agreement for us to proceed. Costs have now been received to clear the space in the library, re-decorate, source furniture and ICT for both CAO and OCC. An extension to our agreement up until the end of July. Costs have now been agreed with CAO and as CMT have now approved it has been agreed that works will commence on 17th July over a period of 2 weeks. Throughout this period OCC and CAO provided a limited service with a representative triaging customers at reception. Furniture is yet to be ordered but this will be completed by 11th July. I am pleased to report that we moved into the new space on Monday 31st July and normal service was resumed. We are now just waiting for a "fixed" line to be connected which will provide us with our own access to wi-fi which will give us a more stable connection. Works have been agreed and costs approved for this, just waiting on the telephony provider. Housing have launched a pilot for 3 months utilising the space in the library from 14th September to have housing officers present who will see customers who have made an appointment. Naomi Winnifrith is producing a report to review the service Fixed line to access our own wi-fi has now been connected and is working fine All actions completed - project can now be closed; 35: There was a reduced service for 2 weeks from 17th July - internal and external comms were sent out advising our customers and staff We are still trying to get the scanner up and running, this has been escalated to Anthony Felman in ICT We now have a solution for getting the scanner up and running so I think this project can now be signed off as completed; 36: CMT approved the continuing service provision from the library and the associated costs; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45546.281 | dkerrigan@oxford.gov.uk
Service integration | Purposeful collaboration Moving to a more connected and collaborative approach to locality working |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Brooke |  | Stephen Gabriel | Ian Brooke |  | Ian Brooke |  |  |  | 44684 | 45688 |  |  |  | 45254 | 24: On Target; 25: On budget; 26: On Target; 27: Medium; 29: On target; 30: Completed recruitment for Locality Manager – Dee Gabbidon Start in Dec Continue to support resident support fund. Jasmin Carne providing admin support Cost of Living, continue to link into events such as Black History Month. Projects, paper on what's going well – building on what's strong Workshop to design a full list of collaborative tools and identify how these tools can be used to impact on our Corporate Plan objectives HSF and Resident Support Scheme promoted, increased focus on the Resident Support Scheme; 31: Short video being developed from the behavioural insights video Continued work on our approach to projects reflected in an updated paper Follow up conversation with CMT to refine approach Oxford Uni student commission underway to demonstrate the quantitative impact of the work CMT – quarterly session (East Oxford) Jan 2024 (design underway) Continued CoL support as we head into winter; 32: Need to improve communication; 33: More short videos; 35: Continue good communication; 36: Note progress; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
HIA - South & Vale Bid | Submit a bid to run South & Vale HIA if and when their contract is renewed |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Wright |  |  | Becky Walker |  | Becky Walker |  | Completed |  | 44834 | 45016 |  |  |  | 44834 | 24: Completed; 25: Completed; 26: Completed; 27: Low; 29: On target; 30: Completed - Please close; 31: Completed - Please close; 32: N/A; 36: Please close - Completed; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
East oxford community centre | Refurbishment and Extension of East Oxford Community Centre |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Brooke |  | Hagan Lewisman | Douglas Kerrigan |  | Douglas Kerrigan |  |  |  | 43472 | 45836 |  |  |  | 45593 | 24: Off Target; 25: On budget; 26: Off Target; 27: Low; 29: On target; 30: Roof structure erected. Internal partitions 95% Internal openings in existing building 90%; 31: Scaffold adjustments Complete brickwork Complete roof covering Complete partitions; 32: 8 week delay due to redesign of timber frame and subsequently substructure. Laying of ground floor screed early by adapting scaffold will work to mitigating the 8 week delay and attain 26/9/2025 completion date.; 33: Completion of timber frame to allow reduced access widths ensuring housing commence 23rd Septemebr 2024; 36: None at this moment till claims are substantiated; 117: 0 | [12 empty] | 45581.238 | dkerrigan@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Bullingdon | Demolition and Rebuild of new Community Centre |  | Communities Change Board | Communities Change Board |  |  |  | CCB - Directorate | Stephen Gabriel | Ian Brooke |  | Hagan Lewisman | Douglas Kerrigan |  | Douglas Kerrigan |  |  |  | 43591 | 44902 |  |  |  | 45282 | 24: Completed; 25: On budget; 26: On Target; 27: N/A; 29: Completed; 31: Final account to be issued and retention sum released.; 35: None; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
DAHA | DAHA Accreditation |  | Communities Change Board | Communities Change Board | [5 empty] | Ian Wright |  |  | Liz Jones |  | Liz Jones |  |  |  | 44713 | 44902 |  |  |  | 44772 | 24: On Target; 25: On budget; 26: Off Target; 27: Low; 29: On target; 30: Clarified DLUHC funding for the next 2 years. Recruitment for the DAHA Project Worker is set Prevention and Rapid Rehousing Service Audit has begun Landlord Services Audit has begun; 31: Scrutinising the audits Extend the audits to other service areas; 33: If internal recruitment is not successful will go out externally; 117: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Friars Wharf |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | Further cost reviews have produced a deficit of £4.63m against budget on full scheme as approved incusive of lost LEP funding. Alternative schemes were presented at a Members Briefing on 12 June and are being worked through. Update to be provided to DB on 20th July. Alternatives being looked at include new planning application for simplified design with steel frame and a housing option being reassessed. A decision will need Council if it is to seek further funding so that would be November. |  |  | 0 | 0 | 0 |  | 33: 0; 34: 0; 50: 0; 100: No; 101: Regeneration; 103: n/a - Initial consideration not yet undertaken; 105: Mixed; 106: N/A; 117: 0; 118: 0; 213: Scheme proposed by A2D (mixed land ownerships with Council owning most); 217: 51.7474; 218: -1.2619 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Grandpont Car Park |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | £60,000 allocated to St Michael's Street surface improvement in 2022-23 has been slipped to 2023-24 as part of overall £240,000 budget envelope (including SPF and s106 pots). Passing this cost centre over to Di Fawcett to oversee, but current headline is that there are cost inflation risks with the project, so there may need to be an ask to use remaining £40,000 of CIL pot too. |  |  | 0 | 0 | 0 |  | 33: 0; 34: 0; 50: Budget should be £1,421,433; 100: No; 101: Not Yet Known; 103: 106; 105: County Council; 107: 10; 117: 0; 118: 0; 213: County Site - Being addressed through meetings with the County (June 2019) - estimated capacity of 9 units. Oct 19 - County not presently intending to bring forward as still in 'operational use'. Named in the Local Plan 2036 as a site for possible Employer-linked housing. Policy SP39 relates; 217: 51.7448; 218: -1.2623 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Low-density HRA housing stock |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | Boundary Brook: completed King Georges scheme: completed Marsh Lane Rec: completed (preferred connection to the highway refused by Christ church; involved to County to try and resolve if possible. Will work without but preferred with direct connection to crossing point) Donnington: been delayed in planning and we are currently waiting for the outcome of the planning application for Donnington Rec, hoping to start construction in September ’23 after nesting season. Working with Comms to improve / create web content and tie in with ODS website. |  |  | Go out to tender - September | Create appropriate trianing package for staff | Consult with Mili Kalia around the impact on equalities |  | 33: County Council Occupational Therapists are funded so there is no backlog and the service is actively promoting the availability of funding. Liaising with hospitals to enable discharge.; 34: We are starting to pay ODS as well to show spend. Still awaiting all correct invoices for compliance; 50: Budget is £45K, spend is due to ODS not submitting invoices; 100: No; 101: Not Yet Known; 103: n/a - regen sites (not yet identified); 105: City Council; 117: 0; 118: 0; 213: Various sites may get identified in this process (being commissioned with external consultants ARC June 2019) as potential regen sites, inc current housing sites on large site footprints. For information only at this stage. Initial schemes with low scores identified for further work (Oct 20). Consultants to be re-engaged to consider schemes that may have higher scores, but sit on large land footprints; 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Slade House |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | **County is in principle supportive of including this theme within the wider programme of work under "movement and place framework". Details TBC** No instruction to progress this work at present. Work to date has included working with Oxfordshire County Council on the opportunities to provide further drop off and layover spaces for coaches. A number of options were identified and these are summarised in the attached note together with the County comments in response. Oxpens car park was ruled out due to the temporary nature of the opportunity and the cost of bringing it forward. | [6 empty] | 33: 0; 34: Invoices from ODS; 50: 0; 100: No; 101: Not Yet Known; 103: 124; 105: Mixed; 107: 50; 117: 0; 118: 0; 213: See note re Manzil Way (poss linked site). Named in the Local Plan 2036 as a site for possible Employer-linked housing. Policy SP57 relates; 217: 51.7426; 218: -1.1982 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Rymers Lane |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | - Project leadership = since taking over as project lead in April ‘23, ND has been meeting the project team & key stakeholders in collective + 121 meetings, undertaking a Due Diligence review of progress to date & carrying out a gap analysis – with the aim of then developing a strategy to take the project forward. ND will be leaving the role sometime around September/October '23 – plans are progressing for a replacement, who will take over at date TBC - Internal engagement = following cabinet approval in Feb '23, a workshop has been held in the same month to review the Feasibility phase & plan the next stages. Three monthly PBs have also been held since, in April, May & July '23 - MEPH/Building Services workstream = a key information gap has been found so far within the MEPH workstream. After various meetings with Property Services colleagues, a series of survey reports carried out by Ridge on behalf of the PS team have been issued to ND on 12.07.23. The Options Appraisal report that interprets those results & offers options on the way forward with relative costs were yet to be shared, but have now come through on 18/07/23 following TB intervention with MP. This workstream is currently blocking the tender process for the consultant team from progressing, given the scope of the team’s work needs to be defined - Programme = lack of MEPH discipline input into the Masterplan means a new Due Diligence project phase will be required between the previous Feasibility & Concept Design stage (RIBA Stage 1 + 2) & the next Detailed Design stage (RIBA Stage 3) – MEPH input is essential in order to understand whether the design option presented to cabinet in Feb ’23 is viable & it’s not possible to progress into detailed design without carrying out this new project phase. Current provisional programme is dated 17.04.23 - following M365 impact, ND will update programme to include new Due Diligence phase. Programme will remain in provisional draft form until the consultants + contractor are in place. Programme RAG has been upgraded to Over Schedule this month, given the likely impact of the MEPH workstream delays; - Market Street part-pedestrianisation workstream = good progress has been made, despite a few setbacks. The lead consultant tender was issued in May through the In-Tend portal. Following a doubling of the budget to £50K, 3 tenderers returned an offer. Interviews were held on 29/6 with the 3 companies – the tender was won by Urban Movement [confidential until contract is signed] - Market street part-pedestrianisation = sign contract with Urban Movement & start services delivery; - Project brief = will likely need to be revised following understanding of MEPH implications - timeline TBC - Budget - RAG has been indicated as Over Budget as of this month, given the costs related to MEPH upgrades will go up, but it's currently unclear from Property Services by how much. Ballpark currently indicated by Property Services colleagues is between £2.3Mil & £3.5Mil, with a cost of £5Mil also being mentioned to future-proof the building. | [6 empty] | 33: - Storage of BWVD in the town hall - Contact made with David Hunt to explore options. 4 location have been identified - Upload of data from BWVD for staff working from home - this may not be possible. Data will have to be uploaded once docked; 34: Create appropriate training package for staff. This will need to cover - Use of hardware/software - Legislation governing surveillance - Equality training - ensure staff consider the equality (9 Protected characteristic); 100: No; 101: Enabling RP Led; 103: 605; 104: A2 Dominion; 105: RP; 107: 37; 115: 37; 116: Yes; 117: 0; 118: 37; 119: 37; 123: 43252; 124: 43677; 125: Planning approval; 126: 17/02813/FUL; 136: 43252; 137: 43677; 188: Completed; 213: Cantay/ A2D development. 17/02813/FUL Scheme completed end of July 2019. Fit-out during Aug 19 and let to first residents in w/c 2nd Sept 2019.; 217: 51.7347; 218: -1.2234 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
1 Pullens Lane |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | Collaboration Agreement, Development Services Agreement and MOU all signed at the end of March. Dedicated project manager started 17th April, and Project is up and running. Programme Panel and NwR progress meetings have taken place and currently developing the procurement specification for commissioning the Infrastructure Place Study. | [6 empty] | 100: No; 101: Not Yet Known; 103: 440; 105: Private; 107: 11; 117: 0; 118: 0; 213: Landowner recorded as G&S Brown. Says an option has expired. Plg App for a care home refused. Planning estimate site capacity at 11 units (0.42 hec); 217: 51.7576; 218: -1.227 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barnards Hill Primary School playing fields |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | As per coach parking feasibility, this is being explored as a work stream within County "movement and place framework". Expecting more clarity in July / Aug. (Spend backstop is 2023-24 financial year, so this needs to be spent or agreement reached with County and University, and internally, to defer another year if required.) | [6 empty] | 100: No; 101: Not Yet Known; 103: 173; 105: County Council; 117: 0; 118: 0; 213: Freeholder is Oxon CC and they are not minded to release covenants to allow the school to develop land for a non-educational use at present (Oct 19). Local Plan SP63 relates however - min 30 dwellings. Named in the Local Plan 2036 as a site for possible Employer-linked housing.; 217: 51.7633; 218: -1.1926 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Between Towns Road (non-student element of student site - inc Cons Club) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | Work is progressing on a Deed of Variation to the funding agreement with Homes England and back to back agreements with Oxfordshire County Council/EA. These are necessary to enable the drawdown of funding and reduce the risk to the Council on transferring funds . A further report has been presented to the Cabinet and delegated approval has been agreed to enter the agreements. Oxfordshire County Council have sought to avoid taking on liability related to the HIF funded works. Agreement has been reached with the EA to take on the liability. The works to be funded are also behind schedule so there is some risk around the ability to drawdown the HIF based on County works once agreements are reached. UofO have raised concerns re meeting the HIF outputs. HE have provided a letter of comfort around the reclaiming of funding. This highlights the potential to work with Homes England should the milestones prove a problem but the Council remains at risk of clawback. Capacity funding has been received to address some of the HIF costs to date. | [6 empty] | 100: No; 101: Developer Led; 103: 95; 105: Private; 117: 0; 118: 0; 213: Cantay has the options for this site and is developing plans for student units across the whole corner site (Dec 19 update); 217: 51.7331; 218: -1.2129 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Edge of Playing Fields, Oxford Academy |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | Homes England have declined to offer the grant that we have spent over four years trying to agree. I think you would agree that we have been extremely patient and tried to cooperate as best we could during this whole process. TWO considering consequences. We have outlined an alternative approach in the from of a loan but will need a decision from TWO needed urgently as spend would need to complete by March 2024. | [6 empty] | 100: No; 101: Not Yet Known; 103: 467; 105: County Council; 117: 0; 118: 0; 213: Owned by Oxon CC - Leased to Oxford Academy Trust on a 125 yr lease - Unlikely to release for non-educational use at the current time (Oct 19). Named in the Local Plan 2036 as a site for possible Employer-linked housing. SP13 relates.; 217: 51.72; 218: -1.2142 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Government Buildings/ Harcourt House, Marston Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | 0 | [6 empty] | 100: No; 101: Not Yet Known; 103: 24; 105: Private; 107: 70; 117: 0; 118: 0; 213: Owned by the Oxford Centre for Islamic Studies (OCIS) opposite; 217: 51.7551; 218: -1.2357 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Island Site (From Oxford Hotel to Canal by Worcester St) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | £50k budget remaining is ear-marked for Cowley Branch Line feasibility. £6,650 has been allocated to revenue spend in relation to Legal advice, however further Legal costs (c£20k) have now been incurred. After meeting Legal fees, remaining unallocated CIL budget can cfwd to 23/24 be reallocated to another project. | [6 empty] | 100: No; 101: Not Yet Known; 103: 70; 105: Private; 107: 40; 117: 0; 118: 0; 217: 51.7529; 218: -1.2662 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Jesus College Sports Ground |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | BAU in HIA with referrals being progressed. | [6 empty] | 100: No; 101: Not Yet Known; 103: 26; 105: Private; 107: 28; 117: 0; 118: 0; 213: Owned by Jesus College. Possible capacity for 28 units (Plg). Site not planning policy compliant for student accommodation so if brought forward, should include affordable housing.; 217: 51.7452; 218: -1.2244 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land Surrounding St Clements Church |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | Increased ERG budget has been approved in Council Budget to help waiting list of clients. | [6 empty] | 100: No; 101: Not Yet Known; 103: 117; 105: Private; 107: 50; 117: 0; 118: 0; 213: Owned by Magdalen College. Possible capacity for 50 units (Plg). Site not planning policy compliant for student accommodation so if brought forward, should include affordable housing.; 217: 51.7537; 218: -1.2376 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Southfield Golf Course (or parts thereof) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | Procurement - RfQ and tender spec draft completed. Both documents will be forwardto stakeholders for appoval including ICT and Teams who have registered an interest in using BWVD ICT - Advice taken from ICT about intergrating BWVD into Council systems Front Door of Change - ODG approved project on the 11th July 2023 | [6 empty] | 100: No; 101: Not Yet Known; 103: n/a - owners not expected to b/f at present time; 105: Private; 117: 0; 118: 0; 213: Sites for possible consideration in next Local Plan/ HELAA for 2031 on? Partial use possible? Re-provision options to green belt sites possible? College owned (tbc)?; 217: 51.7413; 218: -1.2056 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Speedwell House |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: n/a; 105: County Council; 117: 0; 118: 0; 213: County Site - Being addressed through meetings with the County (June 2019). Old HELAA Ref 110 - Removed from list in 2019 though as County Council have started to reoccupy the building and have indicated it is not likely to be brought forward as a site within the next 5 years. Noted here for info and future reference only.; 217: 51.7485; 218: -1.2575 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Florence Park depot site |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 105: City Council; 107: 10; 117: 0; 118: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Northbrook House |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 103: n/a - regen to be considered further (net unit gain unlikely); 105: City Council; 107: 10; 117: 0; 118: 0; 213: OCC Cat 2 sheltered scheme - to be de-commissioned. Expectation is that the BBL central area regen project may generate some flats that will be a perm decant option for residents. Holding until then (new lets on short term agreements only). Provisional start date of redevelopment mid 2025/26, decants starting in early 2025; 217: 51.7194; 218: -1.2041 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Windale House |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 103: n/a - regen to be considered further (net unit gain unlikely); 105: City Council; 107: 40; 117: 0; 118: 0; 213: OCC Cat 2 sheltered scheme - that could be de-commissioned if the BBL central area regen project generates some flats that could be one perm decant option for residents. Large site footprint - esp inc Andromeda Close garages and land. Provisional start date of redevelopment mid 2025/26, decants starting in early 2025; 217: 51.7188; 218: -1.1983 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Iffley Mead |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 104; 105: County Council; 107: 80; 117: 0; 118: 0; 213: County Site - Being addressed through meetings with the County (June 2019) - estimated capacity of 60 units; 217: 51.7337; 218: -1.2355 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Kassam Stadium |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 28; 105: City Council; 107: 150; 117: 0; 118: 0; 213: 6 June 2023 update from David Browne - stadium site (freehold) was sold by OCC on 5 October 2001 to Firoka (Oxford Leisure). OCC has no freehold/leasehold interest in the stadium/car park or leisure complex. The agreement for the stadium site if between Firoka and Ox United FC (no OCC interest). Only OCC interest in this area is for The Priory, off Grenoble Road, leased by OCC to Firoka.; 217: 51.7165; 218: -1.2101 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Lincoln College Sports Ground |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 32; 105: Private; 107: 90; 117: 0; 118: 0; 213: Owned by Lincoln College. Possible capacity for 90 units (Plg). Site not planning policy compliant for student accommodation so if brought forward, should include affordable housing. Oxford co-housing group may have explored this site already (tbc)?; 217: 51.745; 218: -1.2263 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Osney Mead |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 586; 105: Private; 117: 0; 118: 0; 213: University assembling land for future campus quarter. Named in the Local Plan 2036 as a site for possible Employer-linked housing. Policy SP2 relates; 217: 51.7486; 218: -1.2764 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Oxford (Greyhound) Stadium |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 111; 105: Private; 107: 100; 117: 0; 118: 0; 213: Housing units listed in the emerging HELAA/ Local Plan as a way to make the redevelopment of the site viable. June 21 Oxford Mail reports that, "Kevin Boothby, who runs two other greyhound tracks, has secured a 10-year lease from Oxford Stadium owners Galliard Homes"; 217: 51.7257; 218: -1.2002 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Oxford Retail Park |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 289; 105: Private; 117: 0; 118: 0; 213: Dependency is Cowley Branch line halt - viability likely to start April19; 217: 51.7292; 218: -1.2017 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Oxford Station (inc Beckett St car park) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 75; 105: Private; 107: 20; 117: 0; 118: 0; 217: 51.7535; 218: -1.2721 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Pear Tree Farm |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 590; 105: Private; 107: 122; 117: 0; 118: 0; 213: Ownership: Merton College; 217: 51.7956; 218: -1.2811 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Temple Cowley Pool |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 100: No; 101: Enabling RP Led; 103: 58; 104: Catalyst; 105: RP; 107: 48; 108: 0; 109: 19; 110: 29; 113: 0; 114: 0; 116: No; 117: 48; 118: 48; 119: 48; 121: 43131; 123: 2018-02-28; 124: 43768; 125: Planning approval; 126: 16/01225/FUL; 134: 43131; 136: 2018-02-28; 137: 43768; 188: Completed; 213: Final 11 SO flats completed - scheme completed; 217: 51.7355; 218: -1.2154 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Park Farm, Marston |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 462; 105: Private; 107: 60; 117: 0; 118: 0; 213: Owned by the University of Oxford (rather than a college). Possible capacity for 60 units (Plg). Site not planning policy compliant for student accommodation so if brought forward, should include affordable housing. Considered by Planning Inspectors in consideration of the Local Plan (2019). Allocated as a site in the Local Plan 2036 (adopted June 20) Policy SP27. 14/02/22 - Planning have met agents - Unsure if to continue to include in next Local Plan (LP 2040) as a site - Will need to consider new Strategic Flood Risk Asst (SFRA) docs - University appears to have little appetite to take this site forward; 217: 51.7628; 218: -1.2411 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Summerfield School |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 125; 105: Private; 107: 120; 117: 0; 118: 0; 213: 14th Feb 22 - Planners report that the school has little appetite to bring forward this site in the next five years; 217: 51.7782; 218: -1.2634 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Summertown Strategic Site |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: n/a - owners not expected to b/f at present time; 105: Private; 117: 0; 118: 0; 213: Site for possible future consideration. Land is adjacent to the Summerfields School athletics track site - Owned by Wadham college, but they have not indicated any intention to bring forward within a 5 year period, so removed from the 2019 Planning Trajectory list. Only the Summerfields school site is identified with a HELAA ref now.; 217: 51.7807; 218: -1.2592 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandy Lane Bowls Club |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 103: n/a - Scheme yet to be developed/ inter-dependencies re community re-provision on-site prior to any likely housing completions, so these may be too far out to consider within current planning trajectory.; 105: City Council; 107: 30; 117: 0; 118: 0; 213: Feasibility work due to report to OCHL Board. Scheme unlikely to be proceedable due to viability issues re the reprovision of the indoor bowls club. Removed from OGD programme (2019).; 217: 51.7237; 218: -1.2128 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.3812 | mmcfarlane@oxford.gov.uk
NSAP - Next Steps Accom Prog Acquisitions (20/21) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 99: Year 3; 100: Yes; 101: Direct Delivery HRA; 103: n/a - single units - No net gain; 105: Private; 107: 5; 108: 5; 116: No; 117: 5; 118: 5; 119: 5; 122: 44199; 123: 44199; 124: 44286; 125: Not Applicable; 136: 44199; 137: 44378; 188: Completed; 213: MHCLG indicated bid success (Sept 20). Bid entered into Homes England IMS system (Oct 20) for formal V4M checks. HE approved (Nov 20) & contract entered into (Nov 20). Mobilised workstream (Oct 20) for 5 x 1 bed acquisition completions in Qtr 4 20/21. Cabinet & Council approved project and budget (Nov 20). Property market searches/ valuations initiated for suitable properties to be used for 'Housing First' allocations. Challenging market conditions at present - few units unencumbered by private leaseholds, at the right value, and complications during lockdown with buyer-chains, and vendors securing vacant possession, and securing mortgage finance in usual timescales. Request to MHCLG for potential variation to proposal or a time extension broadly declined (late Dec 20/ Jan 21). Jan 21 update - 2 properties have accepted offers and 1 further one has an offer in place. Mar 21 update - 5 units in conveyancing and aiming for completions by end March. Homes England are allowing a 3 month extension to this, and we have applied as a backstop in case of delay. End May 21 - All 5 properties now purchased and are in the process of being made ready for first lettings (June 21 target for this). All 5 properties now sat with Paul Wilding for occupation with help from A2. (20/10); 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandford Road (phase 1) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 100: No; 101: Developer Led; 103: 29; 104: OCC; 105: Private; 107: 140; 108: 45; 109: 0; 110: 0; 113: 70; 114: 0; 115: 0; 116: No; 117: 45; 118: 115; 119: 45; 121: 43348; 123: 43527; 124: 44407; 125: Planning approval; 134: 43348; 135: 43983; 136: 43527; 137: 44481; 188: Completed; 213: OCH purchasing 45 social rent units. 6x3 beds handed over in July 2x4 beds expected Dec-20 and 11x2 beds in Feb-21 with remainder in 21/22. Jan 2021 - on-track in accordance with the (Covid) revised programme. Mar 21 update - on track for Dec 21 completion. On track for Oct 21 PC.; 217: 51.7176; 218: -1.2304 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Oxwed (Without Student) | Mixed-use scheme of 450 including student accom. |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 31: s106 being drafted; 100: No; 101: Regeneration; 103: 76; 105: Mixed; 106: N/A; 107: 234; 108: 82; 110: 6; 111: 29; 113: 117; 116: No; 117: 117; 118: 234; 120: 2022-12-13; 121: 2023-12-01; 122: 2023-11-30; 123: 2023-12-31; 124: 45747; 125: Planning application submitted; 126: 22/02954/OUT; 128: 45599; 130: 2024-09-01; 131: 2024-09-01; 132: 2027-06-01; 133: 2022-12-08; 166: 117; 167: 82; 169: 6; 170: 29; 188: On target; 190: On target; 193: On target; 196: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Initial master planning and pre-app work underway through OXWED. (Early 2021). Summer 2021 - discussion on housing options expected. Expect to procure a development partner after outline planning consent is secured. (Devt Partner c. mid-2022). Delivery not expected until 2024 on. The total scheme residential number of 450 includes student accom (c.25% tbc) - with off-site contribution expected. AD Notes - Outline planning application received 08/12/2022 31/10/23 - Awaiting outline planning consent - November planning committee 28/11/23 - AD chasing progress on this - scheme gone quiet. Planning consent f/c pushed back 2 months to Jan 2024. And f/c SOS pushed back 3 months to April 2024. 08/02/24 - OxWed delivery strategy being drafted by Priors and moving towards drafting of s106. 08/03/24 - More info next week, draft s106 circulated to the applicant. F/c dates pushed back to 3-4 months with planning expected March 24 and CSOS Sept 2024 - PC date slipped from 26/27 to 27/28 13/03/24 - update from planning that consent likely by June 2024 26/03/24 - s106 in draft. 03/06/24 - outline planning expected this month 06/08/24 - still drafting s106. Moved to a new planning officer; 217: 51.7498; 218: -1.2669; 220: 57; 221: 25; 251: 6; 270: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Small Council Sites (inc garages) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: n/a - regen sites (not yet identified); 105: City Council; 107: 40; 117: 0; 118: 0; 213: HAP report on garage sites issued - potential for further feasibility work subject to funding being available. Report has fed into the wider work on small sites - Cabinet paper now in June.; 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Valentia Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Enabling RP Led; 103: 329; 105: City Council; 107: 12; 116: No; 117: 0; 118: 0; 213: Site brought forward in new adopted Local Plan 2036. OCHL not considering and suggest discussions with a CLH group through enabling work. New CLH group forming (lead Andy Edwards) interested in potential for site development - discussion planned with OCHL re possible partnership approach.; 217: 51.7545; 218: -1.2189 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Market Purchases - Acquisition Programme (2017/18 to 2018/19) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Direct Delivery HRA; 103: n/a - single units - No net gain; 105: Private; 107: 14; 108: 14; 109: 0; 110: 0; 113: 0; 114: 0; 116: No; 117: 14; 118: 14; 119: 14; 124: 43495; 125: Not Applicable; 137: 43495; 188: Completed; 213: Acquisitions for HRA permanent letting ( 10 units Great Western Park & 4 x 3bed & 5bed street properties). Project to acquire units into the GF for Temp Accom use excluded.; 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
RSAP - Rough Sleepers Accommodation Programme - Acquisitions (21/22) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Direct Delivery HRA; 103: n/a - single units - No net gain; 105: Private; 107: 10; 108: 10; 116: No; 117: 10; 118: 10; 119: 10; 122: 44287; 123: 44287; 124: 44651; 125: Not Applicable; 135: 44650; 136: 44285; 137: 44680; 188: Completed; 213: Subject to HE bid in IMS in 21/22. Indicative approval in the MHCLG NSAP programme given (Sept 20) with revenue funding attached to the NSAP prog units across 20/21 and 21/22. Units to be used as perm use under 'Housing First'. Cabinet report for Project Approval given in Nov 20. Budget to be allocated in main budget reports (Dec 20 to Feb 21). Apr 21 update - Capital & Revenue Bid submitted (MHCLG & Homes England IMS) for these 10 units under RSAP. June 21 - Confirmation of funding award. Project mobilised and acquisitions underway (end July 21 - 3 in conveyancing, and up to 4 more entering the pipeline with offers made). Sept 21 - 9 units in conveyancing. Request with MHCLG for an additional £550k to replace OGD funding. 30/09/21 - MHCLG say "positive, but dependent on Ministerial sign-off that is likely to take a few weeks". Expect to have to slow conveyancing work down accordingly to minimise risk. DLUHC confirmed funding of £550k in addition to HE claim (to replace lost OGD funding) (26/10). All 10 units completed and handed over to ODS by 30/03/22. Most require minimal / no works with 3 requiring more extensive upgrading. Grant claims submitted on IMS and monies for 1st 2 tranches received. Final 5% tranche to be claimed for all by 29/04/22 on confirmation of unit handover from ODS.; 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Lakefield Road (RBL) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 604; 105: County Council; 107: 20; 117: 0; 118: 0; 213: County Site - Being addressed through meetings with the County (June 2019) - estimated capacity of 20 units; 217: 51.7179; 218: -1.2198 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Glanville Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 100: No; 101: Direct Delivery HRA; 103: n/a - small site; 105: Private; 107: 9; 108: 5; 109: 4; 116: No; 117: 9; 118: 9; 119: 9; 121: 43803; 122: 44095; 123: 2020-10-01; 124: 44440; 125: Planning approval; 134: 43803; 135: 44095; 136: 2020-10-01; 137: 44407; 188: Completed; 217: 51.7417; 218: -1.2256 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Canterbury House, Glanville Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 107: 10; 115: 10; 116: Yes; 117: 0; 118: 10; 213: Supported housing scheme. Currently has 10 units + offices | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Jericho Canalside |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Site Identification only | [7 empty] | 100: No; 101: Developer Led; 103: 11; 105: Mixed; 107: 0; 108: 0; 109: 0; 110: 0; 113: 0; 114: 0; 116: No; 117: 0; 118: 0; 125: Planning Refusal; 133: 2020-06-02; 188: At Risk; 213: Mixed Ownerships - poss inc: Administrators; Oxford City Council; British Waterways; Church of England. Proposed to provide affordable units off-site from conversion of the existing community centre building once new community centre in operation. 10.03.2022 - The situation with the application has progressed. The financial viability assessment has now robustly demonstrated it is not viable to provide on-site provision of affordable housing or contribution towards off site provision. Ongoing - Review mechanism that could secure any surplus profit as a contribution towards affordable in future. PLANNING APPLICATION REFUSED FOR 24 OM UNITS- 22.04.2022; 217: 51.7576; 218: -1.2701 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Crescent Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 105: City Council; 107: 12; 108: 6; 110: 6; 117: 12; 118: 12; 213: Brookes Univ | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45547.1696 | mmcfarlane@oxford.gov.uk
Champion Way |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Closed | [7 empty] | 100: No; 101: Enabling RP Led; 103: n/a - small site; 104: OCLT; 105: City Council; 107: 0; 108: 4; 109: 0; 110: 0; 113: 0; 114: 0; 116: No; 117: 4; 118: 4; 120: 2020-04-01; 121: 2020-07-06; 122: 2021-06-01; 123: 2021-07-01; 124: 44651; 125: Planning approval; 131: 2021-07-01; 132: 2022-03-31; 133: 2020-04-01; 134: 2020-11-25; 213: Possible Community-Led Housing devt - currently led by TbD (community architects). An application to the Homes England Community Housing Fund by TbD to cover initial consultancy/ feasibility costs was successful (Dec 18) and work progressed accordingly, inc decision over a poss RP partnership if OCLT application for RP is not given - Detailed application submitted to the regulator in Sept 19. External valuation of land interest received - to inform decision re authority for a lease (at nil value). Cabinet (13 Nov 19) report agreed. Likely to also need to consider funding regime options - ODG/ s106 funds. Discussions with Soha re an RP partner (poss for Dean Ct site in VoWHDC also). Request for a small loan/ grant to assist moving forward with feasibility work to be considered further (Cabinet report on AH top-up grants being drafted for January 2020 Cabinet). Pre-app plg discussions inc a meeting of TbD, planning consultant, highways, tree officer and urban designer (13 Nov 19). Following up with neighbour around access issues (met Dec 19). Feb 2020: Neighbour has agreed to move and had Band 1 priority for a decant. This will overcome easement issue and improve scheme viability. TbD drawing up two sets of plans for a revised garden layout and will consult highways on these. Pre-App process successfully concluded (4 Mar 20). Neighbour moving which improves access issues. Full Planning App submitted (1 Apr 20). Joint meetings now being held with OCLT also. Planning consent - expected Jun 20. Heads of Terms for land sale to OCLT to be agreed. Business Case for use of s.106 top-up funding being developed. (Jul 20) and included in OGD additional funding asks list (Sep 20). ODS works under 'great estates' to close off easement and change garden arrangements for neighboring 2 flats completed. (Nov 20). Planning Consent agreed (Nov 20). External legal advice on the HRA parcel of land received re appropriation/ transfer options and draft lease agt now being drafted. (Dec 20). SITE PAUSED (Dec 20) - Further site investigation work shows a major water trunk main running through the site and potentially under the building footprint - that cannot be built over, and a 5m buffer zone either side that would require Thames Water's consent. Re-routing cost expected to be prohibitive. Further exploration work with TW/ survey company to be explored, but major redesign/ loss of units/ another plg app expected (£20k+ cost). Next CHF could help support this work, but 'meanwhile uses' to now also be explored. Latest (Jan 21) OGD/ HE position is also to require a CLT to be advanced with RP status or RP partner for SoS. Mar 21 update - A survey to definitively map the water mains pipe through the site is to be commissioned. To drop from OGD (Yr4). Champion Way closed due to Thames Water main issue.; 217: 51.7235; 218: -1.2213 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Jericho Health Centre / St Pauls House | Redevelopment of former health centre with OCC retaining five SR units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Developer Led; 103: none; 105: Mixed; 107: 17; 108: 5; 114: 12; 116: No; 117: 5; 118: 17; 119: 17; 120: 43739; 121: 44001; 122: 44494; 123: 44859; 124: 45015; 125: Planning approval; 126: 19/02531/FUL; 132: 45265; 133: 43739; 134: 44001; 136: 44494; 137: 45265; 138: 5; 139: 5; 188: Completed; 190: Completed; 193: Completed; 199: Completed; 202: Completed; 205: Completed; 208: Completed; 211: Completed; 213: Full planning permission granted - 19/02531/FUL - SOS Achieved, Lucy Group Lucy Group provided build programme, working with Bill Chamberlaine to get updates. Change of use of extended ground floor to Class A1 (retail), Class A2 (professional and financial services) and Class B1 (office), and provision of nine new Class C3 dwellings (including 4x2 bedroom flats and 5x3 bedroom flats. The next meeting is May, looking to attend to get details. Update from site, the removal of flat roof to the existing block will commence on the 13th June with the additional floor/roof completed in the late summer and works to OCC 5 properties commencing in October/November with the programme for completion in March 2023. Pictures and conveyancing plans recieved of current progress and saved on file. 18.05.2022 - Chasing for accomodation schedule, have raised importance to Mark Smart who has picked this up. OCC have 2 x 2b + 3 x 3b; 5 x OCC = Flat 2 – 3B Flat 3 – 2B Flat 5 – 3B Flat 6 – 3B Flat 7 – 2B 2 x existing units Lucy Group 1 x private leaseholder 9 x new units retained by Lucy Group - Project suffered some slippage with cladding and incoming services which has delayed our external works. Flats will be physically complete internally at end of May, but due to ongoing external works we will be unable to achieve B Regs sign off until 16th June. We are allowing a 2 week programme contingency and therefore flats will be ready for occupation 3rd July. Viewings and access for preparation for tenancies will be possible from end May. Programme in scheme file 3/08/23 Agreeing handover dates - update expected week of 7 Aug 22/11/23 - Completion of units confirmed 05/12/23 - Handover confirmed today; 217: 51.7602; 218: -1.2678; 221: 2; 223: 3 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Gibbs Crescent - OGD ONLY | 140-all affordable scheme delivered by A2Dominion |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | [7 empty] | 30: Tender pr; 31: Ongoing discussions with A2D Proposal going to Homes England﻿ to secure grant funding; 33: Construction contractors have gone into liquidation - awaiting further confirmation of new contract, to be signed June 2024 - Homes England proposal to secure grant funding Time delay from construction issues; 99: Year 4; 100: Yes; 101: Enabling RP Led; 103: 603; 104: A2 Dominion; 105: RP; 106: N/A; 107: 0; 108: 1; 109: 0; 110: 54; 113: 0; 114: 0; 116: No; 117: 55; 118: 55; 120: 43458; 121: 43746; 122: 44561; 123: 44865; 124: 45657; 125: Planning approval; 126: 18/03369/FUL; 131: 45778; 132: 47087; 133: 43458; 134: 43746; 135: 44644; 136: 44788; 173: 55; 174: 1; 176: 54; 187: Scheme pushed out of scope until confirmation of funding. Currently anticipated to come back into programme.; 188: Off Target; 211: Off Target; 213: 12 units (switched from market rent added into Growth Deal programme and grant rates confirmed). See commentary for main schemes (Paradise St and Gibbs Cres) re development progress (170 units in total). Feb 22 - A further 43 flats to be tenure switched from market to SO (in OGD) - see note in main scheme entry 8 June 23 - site closed from midday onwards, changed to Amber RAG (Henry Construction have gone into Administration. A2D are seeking legal control of the site back and developing contingency plans) 28/11/23 - A2 are in breach of the s106 due to delays on the site, AD will meet with them soon. s106 gives them 54 month period to complete scheme. 18/12/23 - Scheme delivery moved back one year from Dec 24 to Dec 25. 13/03/24 - update from RP on tender exercise/impact on programme expected in April 24 29/04/24 - this week A2D recommending which contractor (out of two) to progress with the new contract. Should be able to approve and sign tender award contract in June. SOS will be May 2025. PC Nov 2026. 08/05/24 - A2 Went out for Tender in October. 8th March was the tender return date. Two contractors bid; price return between both contractors is 6k apart.£600k A2 will be able to recommend tender award internally on 30th April to then progress internally towards appointment. Mid - May Tender to be internally approval and contracts signed in June. Mid July SOS May 2025 / November 2026.SOS end of July Estimated 24 month build programme. 3/6/24 - tender info has been returned. Two submissions - awaiting contractor appointment following tender. Poss contract in June. 17/06/24 - Update from A2D: Report will now be going to EMT on 9th July and it’s hoped we will have a response regarding grant funding before that, so there will be no waiting on anything else. As soon as we have a decision, we will agree a programme with the chosen Contractor and our Planning Manager is already briefed to start the process to vary the s106 on those two points. If the decision is not to proceed, tenancies at Paradise Street will not be renewed so that the 15 units can be provided there, although we all hope that’s not the route that is chosen. 01/08/24 - A2D confirmed that Homes England have declined their funding bid due to high grant ask and regulatory rating. Now seeking funding report through DLUHC and/or RCGF. 04/10/24 - Waiting for feedback (expected Jan) re potential funding routes. Expected to submit bid for funding in March with almost immediate SOS again. Then a 2-year build so SOS approx April 2025 to April 2027 - change dto Amber RAG.; 217: 51.7487; 218: -1.272; 250: 31; 252: 24; 270: TRUE; 271: 44014; 273: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Existing Barton (Howards) phase 1 |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Steve Weitzel |  | Steve Weitzel |  | Site Identification only | [7 empty] | 100: No; 101: Regeneration; 103: n/a - regen to be considered further; 105: City Council; 107: 60; 109: 0; 110: 8; 113: 30; 114: 0; 115: 0; 116: No; 117: 8; 118: 60; 124: 45108; 125: Pre-Application; 213: The decision has been made to pause scheme due to informatio received from surveys. Initially it was agreed to proceed with Phase 1 as a Pilot. [Demolish 26 units 26 OCC owned and 6 RTB’s & Rebuild c60-70 new homes; current masterplan shows 63 home; 27 new Houses and 36 new flats. Initial estimates suggest we would require an initial capital expenditure of c£2.5m to assemble the land with a build cost of c£12.5m including fees and costs.] Alan Wylde prepared the viabilities, prior to his departure, for Barton Phase 1 assuming OCHL deliver it. It is still marginally viable, but, not in a way that OCHL would find acceptable in terms of the return. We are exploring alternative options for delivery. Planning pre-app meeting held 11/05. Speaking with SOHA who own land to south as this provides opportunities for more units which may improve viability. Structural surveys delayed over 15 months due to lack of available properties causing delay to scheme delivered in January 2022 (instructed Nov 2020). These surveys are critical to the evidence base for undertaking the project. Their delay caused delay to the whole project. The results of the survey are underwhelming and do not support the business case. Subsequent discussions have centred on the possibility of returning the phase 1 pilot to OCHL to undertake and close out report.; 217: 51.7645; 218: -1.2028 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Existing Barton (Howards) phase 2 |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Steve Weitzel |  | Steve Weitzel |  | Site Identification only | [7 empty] | 100: No; 101: Regeneration; 103: n/a - regen to be considered further; 105: City Council; 107: 340; 108: 0; 109: 0; 110: 0; 113: 0; 114: 0; 116: No; 117: 0; 118: 0; 125: Not Applicable; 213: The decision has been made to pause Phase 2 in October 2021. Previous discussions had centred on the possibility of returning the phase 1 pilot to OCHL to undertake feasibility and close out the report. Following a recent request to update the “Barton” page on the council website, Dave Scholes has highlighted the Barton Howards Project is still "open” and should be taken to HSB & DB to be closed, as recommended in my October 2021 briefing note for DB. The briefing note was pulled from the DB on 29/11/21 by agreement between Stephen Clarke and Tom Bridgman. The detailed survey report was forwarded to the PM on 27 January 2022 and did not support the assumptions previously made about the seriousness of the steel frame corrosion etc. In the meantime, SAP scores were evaluated on properties within the overall scheme giving higher than expected ratings of band C & D; higher than expected. These survey results further undermine the case for proceeding.; 217: 51.7645; 218: -1.2028 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Union Street Car Park |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Regeneration; 103: 61; 105: City Council; 107: 20; 117: 0; 118: 0; 213: Request from HSB (May 21) to re-look at the opportunities from the wider site (inc school/ adult education center, & Boots and flats above (in part in OCC ownership). Contact to be made with the school and County to progress discussions. No interest from County on site re-development. Report updated to reflect development area and recommendations for next steps. JW has had an approach for the site for student accommodation and ZedPod also carrying out desk top feasibility for units and retaining parking spaces. Report will need to go to next Development Board Mtg. 27/06/22: AD working on draft paper to obtain funding for feasibility study; 217: 51.7482; 218: -1.2355 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Street Property Acquisitions 22/23 |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Direct Delivery HRA; 105: Mixed; 107: 10; 108: 10; 116: No; 117: 10; 118: 10; 119: 1900-01-06; 124: 45016; 125: Not Applicable; 132: 45016; 137: 45016; 188: Completed; 213: Record of Street Acquisitions recorded on file here: M:\Housing-Services\AH Supply Programme\SITES & SCHEMES (inc Monthly Reports)\7 - Acquisitions & Street Purchases\Street Purchases - 2022-23\HRA Purchase Scheme - Delivery Schedule 2022-23.xlsx | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Street Property Acquisitions (2020/21 to 2021/22) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Direct Delivery HRA; 103: n/a - single units - No net gain; 105: Private; 107: 34; 108: 34; 116: No; 117: 34; 118: 34; 119: 1900-02-02; 123: 2020-04-05; 124: 44651; 125: Not Applicable; 136: 43926; 137: 44651; 188: Completed; 213: Using RRTBRs - Targets: 20/21: 25 units. 21/22: 8 units, plus 1 unit using RCGF funding. Total: 34. (Also, to note 1 x HRA perm acquisition in 2019/20 at 51 Littlebury). Completions: 20/21 22 units; 21/22 11 homes (to end Mar 22) plus 1 using RCGF = 34. Next Steps Accommodation Programme –Target: 5 x 1 beds 20/21. Completions 20/21 3 units; 21/22 2 units. RSAP 21/22 prog – 10 x 1beds (reported separately ) Further 2 street property purchases 2 x 2 bed completed 30/03/2022 from the top up fund. Further 2 x 2 bed acquisitions delayed in conveyancing and expected to complete Q1 22/23.; 217: 51.7515; 218: -1.2574 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45547.1696 | mmcfarlane@oxford.gov.uk
Northern Gateway/ Oxford North HSB | Purchase of 111 S106 affordable homes with Hill |  | Housing Supply Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | [7 empty] | 30: Scheme is in contract and on-site; 31: Monitoring site for delivery according to current schedule Potential for two extra units going through planning and requiring financial assessment; 33: Scheme is in contract and on-site although query over the housing trajectory which does not align with the development agreement. Issue has been raised and noted with careful monitoring on site. Reprofiling took place in April to drop 16 units from 24/25 to 25/26 - potentially more will need to be slipped; 77: Hill Residential; 78: Hill Residential; 95: 45000; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 1; 105: Mixed; 106: N/A; 107: 317; 108: 89; 110: 22; 116: No; 117: 111; 118: 111; 120: 2022-03-28; 125: Planning approval; 126: 22/00675/RES; 132: 2027-03-02; 133: 2022-05-17; 134: 2022-11-04; 135: 2023-06-30; 136: 2023-06-30; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: RM approved - 22/00675/RES / on 07/11/2022 / and Outline approved - 18/02065/OUTFUL on 21/03/2021 for the whole site 480 Units. S106 Agreed. This Project is part of large strategic site. RM Application validated on 28/03/2022 for the first for around 317 homes (35% affordable - 80/20 SR/SO Split) No current RP in contact with the developer. Currently awaiting the submission of revised plans and documents as planning requested amendments with regards to the height and design of the proposed blocks and a number of amendments to the supporting technical documents were required. The submission was due early April but there have been delays with a number of reports. It was aiming to present at June committee but this may need to be July given delays. The scheme is in line with policy H2 but within the original submission, 19.05.2022 - Savills to produce accommodation schedule and target dates for SOS & PC as there was no indication as to where the AH units would be located and the mix breakdown at present is 111 dwellings: One Bed Flat = 25 x SR + 6 x SO = 31 Two Bed Flat = 27 x SR + 9 x SO = 36 Three Bed Flat = 17 x SR + 5 x SO = 22 Three Bed House = 12 x SR + 1 x SO = 13 Four Bed House = 8 x SR + 1 x SO = 9 Total = 111 Update 28/11/22 : Currently in discussions with the planning team over the delivery. the start on Site is looking at 'early 2023' It will then take around 7 years to complete the entire scheme with 35% minimum AH requirement in each delivery phase with an Accommodation schedule received but NO housing trajectory. A lot could change, the applicant is preparing the housing trajectory that they are required to do this under the terms of the S106. Savills have not given a timescale on when this would be ready, they are aware of the requirement to submit this before starting on site. The milestones are based on what Hill had sent most recently to Sarah when they asked for the bid of the affordable units PC of last Affordable December 2026. 17/05/23 Aiming for contracts to be in final draft by mid June (if not sooner). Meetings are taking place on a weekly basis with both sides (legal, EA, Hill, Procurement). An update to Housing is taking place on the 17th May. 01/08/23 - Contracts signed and parcel 1 transfer undertaken 30th June 2023. On site monitoring and management now underway with first site meeting in September. 31/10/23 - housing trajectory agreed although difference between delivery profile in s106 and contract 27/11/23 - CDM checklist and all CDM related issues have been deferred to Hill. 11/01/24 - No site delays noted. 29/02/24 - all on target, developer has submitted planning change to add extra flats to undercroft. KP will do another BP appraisal (2 for social rent). Won’t affect the programme. Think planning will be ok. KP will know if it’s financially ok at the end of next week. 21/03/24 - DOV required for additional 2 units. The proposals involve providing two additional three-bedroom flats within two of the apartment blocks (6 and 7) by moving cycle parking into the basement. The developer has proposed that the new flat in block 6 would be social rent and the new flat in block 7 would be shared ownership, whilst Plot 73 would be market sale rather than shared ownership. 11/04/24 - Revised CDM info provided. 03/06/24 - F/C PC date pushed back 3 months to Dec 2026 10/06/24 - revised programme has final completion (single unit) in March 2027; 214: 44956; 215: 45432; 217: 51.7959; 218: -1.2822; 220: 25; 221: 2; 222: 25; 223: 8; 224: 7; 225: 2; 234: 12; 237: 8; 250: 6; 252: 9; 253: 5; 270: TRUE; 271: 44278; 273: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Littlemore Park (phase 2) | All-affordable scheme delivering 273 homes across 2 phases - part Growth-Deal funded |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 99: Year 3; 100: Yes; 101: Enabling RP Led; 103: 34; 104: Catalyst; 105: RP; 107: 106; 108: 56; 110: 50; 113: 0; 114: 0; 116: No; 117: 106; 118: 106; 119: 106; 120: 2018-08-29; 121: 2019-05-01; 122: 2020-09-30; 123: 2021-01-17; 124: 45195; 125: Planning approval; 126: 14/02940/OUT; 133: 2018-08-29; 134: 2019-05-01; 135: 2020-09-01; 136: 2020-11-01; 137: 45247; 138: 32; 139: 13; 141: 19; 188: Completed; 213: Phase 2 (106 units) - Also contracted with Hills - Funding in OGD - Accommodation schedule within scheme folder to track handovers as well as OGD Grant funding schedule. Working with Catalyst to monitor handover performance, tracking handovers with Catalyst. 22/11/23 - Confirmation of completion of all units. Awaiting PC certificate.; 217: 51.7225; 218: -1.2275; 220: 4; 222: 24; 235: 18; 237: 9; 241: 1; 270: TRUE; 271: 42453 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Gibbs Crescent/ Paradise St - EXC OGD UNITS | 140-all affordable scheme delivered by A2Dominion |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | [7 empty] | 100: No; 101: Enabling RP Led; 103: 603; 104: A2 Dominion; 105: RP; 106: N/A; 107: 170; 108: 68; 109: 0; 110: 17; 113: 0; 114: 30; 116: No; 117: 85; 118: 115; 120: 2018-12-24; 121: 2019-10-08; 122: 2021-12-31; 123: 2022-10-31; 124: 45657; 125: Planning approval; 126: 18/03369/FUL; 132: 47087; 133: 2018-12-24; 134: 2019-10-08; 135: 2022-03-24; 136: 2022-08-15; 173: 85; 174: 68; 176: 17; 187: Scheme pushed out of scope until confirmation of funding. Currently anticipated to come back into programme.; 188: Off Target; 213: Planning consent. Demolition works commenced at Paradise St. After demolition - Paradise St build 20 mnths/ Gibbs Cres build 4 years. 11 tenants left to decant out (as at end Sept 2020). Also see note re OGD - 12 units. 170 units across the full scheme (140 at Gibbs and 30 at Paradise Street). Nov 21 Update - Paradise Street has now achieved SoS following demolition. Gibbs Cres - A2D in negotiation with successful tenderer from their framework. Expect to formally sign contract once final decant timeline is confirmed (Jan 22). c. 6 decants remaining. Feb 22 update: Remaining market units at Gibbs (43 flats) to switch from market to SO (and be included in OGD Yr 4 - agreed by OGD, pending A2D Board approval on 24/2). Build contract ready to sign in March (confirmed). 14/02/22 - 3 remaining tenants to decant/ evict. 01/06/22 - Possession of last flat given by Court for 5th July, with tenant agreeing to accept another tenancy (out of area) in advance of this. Nov 22 - demolition is now complete and piling is due to start in Dec 22 - held up by SSE works to de-commission the existing substation and upgrade to the new one. 8 June 23 - site closed - RAG changed to Amber.- Henry Construction have gone into Administration (13/6). A2D are seeking legal control of the site back and developing contingency plans. 28/11/23 - A2 are in breach of the s106 due to delays on the site, AD will meet with them soon. s106 gives them 54 month period to complete scheme. 18/12/23 - Scheme delivery moved back one year from Dec 24 to Dec 25. 13/03/24 - update from RP on tender exercise/impact on programme expected in April 24 3/6/24 - tender info has been returned. Two submissions - awaiting contractor appointment following tender. Poss contract in June. 01/08/24 - A2D confirmed that Homes England have declined their funding bid due to high grant ask and regulatory rating. Now seeking funding report through DLUHC and/or RCGF. 04/10/24 - Waiting for feedback (expected Jan) re potential funding routes. Expected to submit bid for funding in March with almost immediate SOS again. Then a 2-year build so SOS approx April 2025 to April 2027 - change dto Amber RAG.; 217: 51.7487; 218: -1.272; 220: 29; 222: 36; 224: 4; 249: 3; 250: 13; 270: TRUE; 271: 44014 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barns Road allotments east |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Rebecca Jacob |  | Rebecca Jacob |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 216; 105: City Council; 107: 30; 108: 10; 110: 20; 117: 30; 118: 30; 213: Allotment potentially still in use and therefore site not available. Use to be monitored.; 217: 51.7302; 218: -1.2156 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Cowley Marsh Depot |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Rebecca Jacob |  | Rebecca Jacob |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 16; 105: City Council; 107: 80; 108: 32; 110: 8; 113: 40; 114: 0; 116: No; 117: 40; 118: 80; 125: Pre-Application; 213: Milestones dependent on ODS relocation-confirmation of delayed programme awaited. Professional Services team appointed for RIBA stages Jessop & Cook led & surveys being undertaken for feasibility stage only. Report on Title prepared. BLRF application unsuccessful.; 217: 51.7389; 218: -1.2195 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Ruskin Field |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Rebecca Jacob |  | Rebecca Jacob |  | Site Identification only | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 463; 105: Private; 107: 40; 117: 0; 118: 0; 213: Site acquisition heads of terms have not been agreed with college. College has not engaged for some time as under pressure with the implications of covid. Feasibility undertaken to inform these discussions. Key risks include planning allocation limiting site size, conservation, ecology, community objection and site access. Not possible to programme at this stage without having a interest in the land. To be followed up in due course. June 2023 - College has been taken over and is now likely to submit an application for student accommodation.; 217: 51.7675; 218: -1.2115 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Alice Smith House | Demolition of existing TA block, and construction new supported housing scheme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Closed | [7 empty] | 31: - Scheme currently on hold; 33: - High design costs - currently looking to retender - Does not yet have planning - pre-app underway - Community support risk not confirmed but consultation will take place when appropriate - Grant options are limited - Significantly delayed - awaiting approval to progress (vacant possession April 2025); 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - regen to be considered further (net unit gain unlikely); 105: City Council; 107: 27; 108: 0; 109: 27; 110: 0; 113: 0; 114: 0; 115: 0; 116: Yes; 117: 27; 118: 27; 120: 2023-01-31; 121: 2023-02-28; 122: 2023-05-31; 123: 2024-09-01; 124: 46113; 125: Pre-Application; 127: 45536; 128: 45658; 129: 45261; 130: 45261; 131: 45778; 132: 2027-04-01; 187: Supported accommodation; 188: Off Target; 190: At Risk; 193: At Risk; 199: At Risk; 202: At Risk; 205: At Risk; 208: On target; 211: Off Target; 213: Propose as GENERAL FUND DIRECT DELIVERY. Temporary Accommodation at present. Pre-app is being finalised, with consultation due to start in May, and 1st part of 2 stage tender prior to identify a contractor prior to submission. JG update 30/05/22 - Alice Smith is currently forecast to be 27 units, and completion is programmed for April 2025 Update 18/10/2022 - Completion Is now Programmed for April 26 15/11/22 no Update 15/12/2022 No update 18/01/23 Decision is with Housing, is this a GF or HRA scheme? Can they release the TA given demand pressures 17/02/23 - No Further update Currently awaiting update 26/06/23 - Vacant possession date is April 2025. May need to go back to market for an architect as costs are high. Need to make business case - no grant options for TA. 03/08/23 - Proposal to re-tender design due to high cost of Ridge. 03/10/23 - Not currently in the programme. Alice Smith House difficult because of business case for funding as temporary accommodation. 12/01/24 -Scheme has been shut down for AHS as commissioners/ clients – Main driver was unable to secure grant to use for TA and needing this as TA dud to high demand (past the date originally planned to hand it over as vacant). Work in hand now to review planned maintenance needs of the building – esp a new heating/ hot water system. Closing report Jan 2024 HSB. Officer decision report required at March HSB. 06/03/24 - This site will not be developed for the foreseeable future, new heating system being installed.; 217: 51.7209; 218: -1.2176 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Eastern House | Demolition of outdated TA block and contruction of 11 houses |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Site Identification only | [7 empty] | 31: - Scheme currently on hold; 33: - Progress dependent on development of Alice Smith House; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - regen to be considered further (net unit gain unlikely); 105: City Council; 107: 12; 108: 6; 110: 5; 117: 11; 118: 11; 120: 2022-06-03; 121: 2022-09-30; 122: 2024-04-26; 123: 2024-06-28; 124: 45961; 125: Pre-Application; 127: 45901; 128: 46023; 129: 45261; 130: 45261; 131: 46569; 132: 46966; 187: Dependency of decanting across into completed ASH scheme as replacement TA. Can be developed without this when TA demand drops. Will look to bring scheme back in programme at that time.; 188: Off Target; 213: Temporary Accommodation at present. Could be released late 2019 if new GF TA block can be commissioned on one of these two sites, with the other being released for new build (general needs) after the new TA is occupied. Design process commenced on the two options. Final pre-app meeting due early July 2021. JG Update 30/05/22: Eastern House is forecast to be 11 units, and completion is programmed for June 2026 18/10/2022 Completion is now Programmed for August 2027 15/12/2022 No Update 18/01/23 Waiting for GF decision on Alice Smith House 17/02/23 - No Further Update April - change to Red RAG on time delay 03/10/23 - Not currently in the programme. Possibility of returning to Eastern House depending on HRA work around budget envelope. 12/01/23 - Scheme re-profiled to Site ID (after achieving D and S stage). Dependency of decanting across into the completed ASH scheme as replacement TA. Can be developed without this though, once TA demand drops from the current level and other move-on options present. Will look to bring the scheme back into programme at that time.; 217: 51.7262; 218: -1.2201 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Juniper Drive |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Closed | [7 empty] | 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 2; 108: 2; 116: No; 117: 2; 118: 2; 120: 2023-01-31; 121: 2023-04-28; 122: 2023-05-01; 123: 2024-01-02; 124: 45658; 125: Application documentation being prepared; 127: 45019; 128: 45231; 131: 45293; 132: 2025-01-01; 188: On Hold; 213: Thames Water have identified a larger than expected pipe under the site which requires diversion. Cost implications being investigated before proceeding. JG update 30/05/22: Juniper is still 2 units, but there is a problem with the utilities, so it is now not due to complete until April 2024 update 18/10/22 - Large sewer identified which means only 1 unit can be built. Being re-priced by ODS - not due for completion until Jan 2025 15/12/22 - no further update 18/01/23 - no further update 17/02/2023 - Scheme close down agreed - report at Jan 2023 HSB; 217: 51.7225; 218: -1.1945 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Lanham Way HSB | 10-unit 100 per cent affordable housing scheme |  | Housing Supply Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Allison Dalton |  | adalton@oxford.gov.uk |  | Delivery | [7 empty] | 30: Scheme making good process Potential for PC to be brought forward - need close monitoring against Homes England expectations; 31: Close monitoring on site and against PC date for Homes England Ongoing monitoring re energy concerns; 33: Contractor has undertaken detailed technical risk analysis with none identified to date - contingency in budget After acquisition scheme will be private highway for OCC to maintain - adequate provisions in place Remove or minimise any provisional sums re finance - robust programme tracking Potential energy issue noted as risk June 2023 - mitigations in place and monitoring; 69: Yes; 77: Jessop and Cook (pre-contract)/Welling Partnership (from contract stage); 78: Feltham Construction; 95: 44083; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - small site; 105: County Council; 106: Application Approved; 107: 10; 108: 5; 110: 5; 116: No; 117: 10; 118: 10; 120: 44189; 121: 44272; 122: 44378; 123: 2021-09-01; 124: 44896; 125: Planning approval; 126: 21/03114/CT3; 132: 45630; 133: 44593; 134: 45006; 135: 45224; 136: 45264; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: In negotiation with contractor, aim to sign contact June / July 2022 subject to VP. Outstanding risks due to Judicial Review, Tenant Occupation, delay and absolute risk. Risks should be further crystallised by end June 2022 17.05.22 Update: Still in planning due to rejection. Now looking at 10 units ( 2 and 3 beds units) - likely to be 50:50 SR to SO. Update 18.10.22 Resolution to grant consent' given Sept 2022 for 10 homes (2 and 3 bed houses). S106 to be agreed. Project being tendered to contractors Oct - Dec 2022. Contract to acquire land from County completes when planning had been granted following s106 agreement, and when JR period has expired. Hold off completion until tenders received to ensure cost is within budget 18/01/23 - One tender received Jan 2023. Figure is within budget but needs full evaluation. 17/02/23 No Further Update 23/05/23 Contract award made to Feltham subject to signing the detailed JCT contract docs (target end June) - all delegated decisions approved. Completion of purchase/transfer of site from County to City 25 May subject to clearance on pre-completion inspection. 19/5/23 Submission via IMS - going to bid clinic on 8 June. June - Pl consent with s106 granted 21 March 2023. Contractor award made May 2023 - JCT contract to be negotiated and signed June/ July 2023. Contract to acquire land from County completed in May 2023. HE funding confirmed. 26/06/23 - possibly moving away from Jessops for new EA, decision soon. On programme. 3/07/23 - Pl consent with s106 granted 21 March 2023. Contractor award made May 2023 - JCT contract to be negotiated and signed July 2023. Contract to acquire land from County completed in May 2023. HE funding award confirmed June 2023. 01/08/23 - first grant (acquisition milestone) requested from Homes England - due August 2023. 04/08/23 - EA services have been retendered and Welling Partnership to start work in August 23 with Jessop & Cooke falling away at the same time 22/08/23 - signing of build contract progressing but now likely to be early Sept (pushed back a few weeks) Some concerns about meeting Dec 23 SOS flagged but awaiting clarification. 14/09/23 Forecast build contract pushed back a few weeks to end of Sept (similar with SOS) with forecast PC pushed back to end of March 2026 03/10/23 - pre SOS work ongoing e.g. clearing conditions/s106 30/10/23 - Awaiting confirmation that contract is signed - already signed by Feltham. All progressing with expectation of SOS in December ahead of HE SOS milestone in early Jan. 9/11/23 - contract confirmed as signed 23/11/23 - formal site handover and SOS Dec 23 04/12/23 - confirmation of SOS. Changed RAG to Green but note that OXP keep it as Amber. F/c PC date pushed back to Oct 2025 (beyond HE deadline). Clarification requested to allow update to HE. 11/01/24 - Progress report on 8 Jan 2024 - details TBC as necessary. EoQ meeting: on track. 7/2/24 - CDM checklist updated. Work continuing at good pace. Potential for slight delay with additional work to fit out SO units. 29/02/24 - onsite all good. Some changes to spec but contingency covered this. Sales are starting to market scheme. 05/04/24 - Site is making good progress against programme. Extreme wet weather making conditions difficult but not insurmountable. Internal finishes design work underway. Ecologist on board for BNG delivery. Service charge calculation in progress. PC date amended to early Dec 24. 29/05/24 - Cashflow slowing. AD to provide update.; 214: 43958; 217: 51.7199; 218: -1.2271; 232: 3; 235: 2; 266: Young's Way; 270: TRUE; 271: 45005 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
74a Foxwell Drive - New Unit | Single property from extensions programme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Completed | [7 empty] | 99: Year 4; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 1; 108: 1; 116: No; 117: 1; 118: 1; 119: 1; 120: 44075; 121: 44136; 122: 44206; 123: 44256; 124: 44621; 125: Planning approval; 126: 21/01757/CT3; 132: 45195; 133: 44370; 134: 44435; 135: 44650; 136: 44700; 137: 45198; 138: 1; 139: 1; 188: Completed; 190: Completed; 193: Completed; 199: Completed; 202: Completed; 205: Completed; 208: Completed; 211: Completed; 213: Part of a package of smaller OCHL-owned sites - intend to be built by ODS. Planning awarded September 2021, Contract going award March 22 with start on site Q4. End March 2022 - Build contract signed with ODS. OGD grant claim submitted within Year 4 deadline. The design has been adversley affected by cost and funding constraints. New build (74a) is timber frame, GSHP for heat and hot water. Refurb works to original house (74) to bring up to lettable standard only. As with other sites in this programme progress to site has been delayed by shortage of resources and materials Currently onsite and all works underway. Some delays because of utilities connections etc. Revised programme pending from ODS. 15/12/2022 no further update 18/01/23 - No Further Update 17/02/203 - No Further Update 10/05/2023 - All identified risks assessed, mitigated and removed to date exception of water supply pipework. Thames water design submitted and pending installation date. Ongoing pressure from increasing materials costs and availability. Working closely with EA and QS to value engineer wherever possible. Thames water design cost received and is within contingency. Monitor construction phase - undertaking design review to simplify the plans and make savings where possible. Making sure only essential works are carried out. Thames Water design and installation costs now confirmed. Pending installation date. 21 June - Currently onsite and all works underway. Timber frame and external brickwork complete. New Thames Water connection for new home is causing some concern although proposal now received along with agreement to proceed. May cause completion/handover delay. 07/09/12 - Properties are completed pending water connection to 74a on 06.09.24. Building Control will then issue completion. 28/09/23 - completed just not legally transferred yet - paperwork is with housing. 03/10/23 - Legal Transfer to OCC completed 29.09.23. Keys to OCC 04.10.23.; 217: 51.7513; 218: -1.2602; 234: 1 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
66 Sandy Lane - New units |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 2; 108: 2; 116: No; 117: 2; 118: 2; 119: 1900-01-01; 121: 2019-07-31; 122: 2020-08-03; 123: 2020-10-01; 124: 44501; 125: Planning approval; 134: 43677; 135: 44046; 136: 44088; 137: 44431; 188: Completed; 213: Progress against programme delayed by industry wide materials shortages and statutory utilities connections. Should still complete within forecast. PC achieved 23 August 2021 but yet to be handed over. Handover completed 17.11.21.; 217: 51.7513; 218: -1.2602 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
9 Pauling Road - New Unit |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Completed | [7 empty] | 99: Year 3; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 1; 108: 1; 116: No; 117: 1; 118: 1; 119: 1; 121: 43866; 122: 43983; 123: 44013; 124: 44439; 125: Planning approval; 134: 43866; 135: 43983; 136: 44013; 137: 44498; 188: Completed; 213: Progress against programme delayed by industry wide specialist materials shortages and statutory utilities connections. Should still complete within forecast. Thames Water connected 20.08.21. Bldg Control certification due 27.09.21 to enable handover. Building Control not achieved - delayed (29/09). Handed over 29.10.21.; 217: 51.7513; 218: -1.2602 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barton Park (Phase 1) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Completed | [7 empty] | 100: No; 101: Direct Delivery OCHL; 102: TRUE; 103: 2; 105: City Council; 107: 237; 108: 95; 109: 0; 110: 0; 113: 142; 114: 0; 116: No; 117: 95; 118: 237; 119: 95; 124: 43920; 125: Planning approval; 137: 44169; 188: Completed; 213: All 95 homes should be transferred by the end of 2020.; 217: 51.7716; 218: -1.2196 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
2 Dynham Place - New Units |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Closed | [7 empty] | 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 0; 108: 0; 116: No; 117: 0; 118: 0; 120: 2020-12-01; 121: 2021-02-01; 122: 2021-04-11; 123: 2021-06-01; 124: 44713; 125: Planning approval; 128: 44386; 129: 44585; 130: 44599; 131: 44624; 132: 2022-10-28; 133: 2020-02-19; 213: Part of a package of smaller OCHL-owned sites - intended to be delivered through ODS. Site investigations have identified difficult ground conditions. Site may now be unviable due to the excessive cost to remediate land. Additional OGD funding requested to support this still being delivered. Planning approval granted. Scheme may be unviable to deliver without additional subsidy. ODS tasked with providing build cost plan. Possible HUG site, possible sell off. REMOVED FROM PROGRAMME - ADDED TO SMALL SITES.; 217: 51.7513; 218: -1.2602 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Warren Crescent | Construction of 10 3-bed houses for rent. Site is adjacent to Lye Valley fen. |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Completed | [7 empty] | 99: Year 1; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 64; 105: City Council; 107: 10; 108: 4; 109: 6; 116: No; 117: 10; 118: 10; 119: 1900-01-09; 120: 2013-06-24; 121: 42639; 122: 2019-03-29; 123: 2019-09-25; 124: 45169; 125: Planning approval; 126: 13/01555/CT3; 132: 2023-07-13; 133: 2013-06-24; 134: 42639; 135: 43553; 136: 43733; 137: 45120; 138: 10; 139: 4; 140: 6; 188: Completed; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: All footpath diversion order issues are resolved. Final remaining hurdle is a s104 with Thames Water to allow work on the sewer. Work has commenced update* 18/10 /22 On site, up to first floor joists 16/12/22 On site, roof trusses on roofs to be done next 18/01/23 - No Update 17.02.23 No Further Update 05/05/23 - Finishing work being done. Snagging starts 17/4 May 2023 - getting to snagging. Issue of s278 being picked up by legal (Shona). 26/06/23 - Handover expected on time in July. Handover likely to be 11 July. PC achieved 13 July - PC certificate requested 03/08/23 - site complete, in defects/ Outstanding legal issues being addressed.; 217: 51.7504; 218: -1.2107; 234: 4 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Rose Hill |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Completed | [7 empty] | 99: Year 1; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 606; 105: City Council; 107: 43; 108: 18; 110: 25; 116: No; 117: 43; 118: 43; 119: 1900-02-11; 120: 2018-10-26; 121: 43481; 122: 2019-03-29; 123: 2019-09-16; 124: 44501; 125: Planning approval; 133: 43399; 134: 43481; 135: 43553; 136: 43724; 137: 44432; 188: Completed; 217: 51.7325; 218: -1.2375 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Edgecombe Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 7; 108: 4; 109: 3; 110: 0; 116: No; 117: 7; 118: 7; 119: 1900-01-06; 121: 2020-01-15; 122: 2020-08-03; 123: 2020-08-03; 124: 44473; 125: Planning approval; 134: 43845; 135: 44046; 136: 44046; 137: 44538; 188: Completed; 213: Scheme is progressing well, units are weathertight. Bad weather during bricklaying delayed completion by 1 week. Risk of further delays due to supply constraints.; 217: 51.7646; 218: -1.1984 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Harts Close |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - out of area; 105: City Council; 107: 2; 108: 1; 109: 1; 110: 0; 116: No; 117: 2; 118: 2; 119: 2; 120: 43301; 121: 43424; 122: 43886; 123: 2020-06-01; 124: 44348; 125: Planning approval; 133: 43301; 134: 43424; 135: 43886; 136: 43983; 137: 44294; 188: Completed; 213: Development complete.; 217: 51.8196; 218: -1.2977 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45554.3545 | mmcfarlane@oxford.gov.uk
East Oxford Community Sites 2 (Catherine Street) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Rebecca Jacob |  | Rebecca Jacob |  | Closed | [7 empty] | 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - small site. Many dependencies re community reprovision that risk delay; 105: City Council; 107: 6; 116: No; 117: 0; 118: 0; 124: 45108; 125: Pre-Application; 132: 2023-07-01; 213: Options for delivery to be considered, site potentially earmarked for disposal. Land receipt to fund community centre redevelopment.; 217: 51.7481; 218: -1.2398 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
OUP Sports Ground, Jordan Hill |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 49; 105: Private; 107: 130; 117: 0; 118: 0; 213: Landowner recorded in HELAA as University of Oxford (Could be acting as agent for OUP?) Possible capacity for 130 units (Plg). Site not planning policy compliant for student accommodation so if brought forward, should include affordable housing.; 217: 51.793; 218: -1.2754 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandy Lane Recreation Ground | Scheme to deliver up to 340 units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Stuart Moran |  | Stuart Moran |  | Feasibility | [7 empty] | 30: A recent meeting has taken place between OCHL and OCC officers in relation to the inter-dependencies with the Cowley Branch Line project.; 31: KEY ACTION: Collaboration agreement (re moving two adult pitches to Hershall Crec) with Littlemore Parish signed in order to make site developable - review date 16 Oct KEY ACTION: Need to model mixed & affordable scheme options - review date 16 Oct The procurement strategy is ongoing with the priority to appoint the consultancy team thereafter, once the Collaboration Agreement has been formally entered into between all parties Reprofiling expected in response to energy issues Planning reviewing need for any further investigations Proposal to tie into the wider governance arrangements for the Cowley Branch line project are to be taken forward to ensure coordination and oversight on an ongoing basis, to be discussed between OCC and OCHL on 18th September.; 33: Emerging issues re energy requirements - no more than one third site energy before 2030 Feasibility report identifies technical issues - these will be managed subsequent to confirmation of site capacity Planning risk around relocation of pitch - Impact on masterplan of Cowley Branchline station facilities/bridge currently unresolved. Escalating build costs/costs of relocating pitches/other potential s106 costs/Cowley Branch line - regular monitoring Community risk particularly around pitches - ongoing engagement Title issues to be further explored Time delay also particularly likely to be impacted by relocation of pitches; 37: TBC but aniticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 289; 105: City Council; 106: N/A; 107: 342; 108: 137; 110: 205; 116: No; 117: 342; 118: 342; 119: 342; 120: 45352; 121: 45537; 122: 45702; 123: 2025-03-03; 124: 47543; 125: Pre-Application; 127: 45927; 128: 2026-01-31; 129: 2026-01-31; 130: 2026-09-01; 131: 2027-04-01; 132: 2032-04-01; 187: Scheme active in feasibility stage - likely to need reprofiling due to energy issues; 188: Off Target; 190: At Risk; 193: At Risk; 199: At Risk; 202: At Risk; 205: At Risk; 208: At Risk; 211: Off Target; 213: Principle of relocating pitches to be agreed. Preparing a response to Littlemore PC. Pitch relocation disc. ongoing w/Littlemore Parish Council. 18/01/23 Preapplication advice sought from LPA. 09/05/23 - OX Place board approved update/next steps 26/06/23 - Change to SOS to Jan 2026 02/08/23 - Pitch relocation disc ongoing w/Littlemore PC and site feasibility underway before consultation with Sport England. 12 week preapp process underway w/LPA to seek agreement on scale, layout and heights of buildings. HSB agreed w/recommendations in June/July 23 paper 03/10/23 - Masterplan, agreement reached with LPA on scale, layout and heights, next steps ODRP. Cowley Branch line disc at early stages. 30/10/23 - RJ and Tom to review whether to lose homes to secure desire lines across the site for Business Park. Going to Design Review Panel in December. 3/11/23 - HoTs for pitch relocation agreed by Littlemore PC at Oct Parish meeting. Pitch site feasibility underway before consultation with Sport England/Planning team. Masterplan agreement reached with LPA on scale, layout and heights, next steps ODRP. Milestone dates pushed back several months. 27/11/23 - RJ working on Littlemore legal agreements (for Jan ODPR). Sport England are supportive. Meeting w/Ted & Rory re CBL to take place. 01/12/23 early stage CBL discussions 11/01/24 - ODRP Feb 24. No cashflow changes. Bridge project in touch with OXP - for Jan HSB. 05/02/24 - CBL discussions have led to redesign of area next to Tesco. 29/01/24 - Scheme on target. Re agreement with parish council, comments have come back through their solicitor. 4 comments on collab agreement – 2 are fine, 2 will get push back. 06/03/24 - Collab agreement and DoV to be agreed. Delays with legal - now targeting after the May elections. 04/04/24 - ODRP report received, seek a response from planning on what should be further investigated. April OXP Board paper to agree funding of £250k to appoint an EA and Architect and procure a contractor. Joint instruction from Ds and EG as well as SM instructing legal for OXP to commence the land transfer. 19/04/24 - Feedback from planning on improvements to the masterplan. CBL disc. have led to redesign of area next to Tesco, further work maybe required after next stakeholder meeting. 29/05/24 - awaiting collab agreement on moving football pitches. It's agreed by OX P and parish - needs input from property. Aiming for project appointments in June/early July. Big issues though on access to energy. SSE can't commit to more than a third of site before 2030. Programme needs to be totally reprofiled with SOS now likely to be 2028 (we have it 2026/27 now). Potential flex with solar/battery and any schemes (e.g. labs) which have already secured their energy but don't come forward. 26/06/24 - review to decide if B3M kept on (they did feasibility). Need EA and QS. New proc. strategy under review. Need a developable site first which is Collab Agreement w/Parish Council. Principles on parking, moorings, CBL, needed. AS will share info with AG. Design panel meeting took place - BM3 working up to planning submission. 01/07/24 - F/c dates pushed back inc planning sub 6m to Mar 2025, consent date pushed 8m to Sept 25, CSOS/PC pushed back 10/12 months to Nov 25/April 32. 14/08/24 - Masterplan agreement reached with LPA on scale, layout and heights. ODRP report received. Feedback from planning on what improvements should be made to MP. CBL disc. led to a redesign of area by Tesco, further work maybe required after stakeholder meeting. No app to appnt consultants until collab ag. signed. 16/09/24 - OXP Board paper needed Sept 24 for architect funding and pitch relocation 13/10/24 - Collaboration agreement and DoV to be agreed. Draft currently with Littlemore PC. Board approved Sept 24 £2.8m to appoint Architect/cost of pitch relocation to Herschal Crescent. Collab agreement still w/OX Place Legal needs to go back to OCC lawyers and LPC poss in Nov 24/ F/c dates pushed 9-12m eg planning sub; 214: 44252; 215: 45089; 216: 45466; 217: 51.725; 218: -1.2079; 270: TRUE; 275: 150000; 276: Agreed at HSB 12 June 2023 and Development Board on 15 June 2023; 277: Yes - draft SDS; 281: 1; 282: 92319500; 283: 4600000; 284: 11078340; 285: 3655083; 287: 7292076; 288: 23950000; 289: 17917500; 290: 80292146; 291: 118945000; 292: 3214646; 293: 122159646; 294: 5991689; 295: 128151335; 296: 101027500; 297: 5.17; 298: 30; 299: 34884554 |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 | Yes |  | Yes | Yes | Yes |  | 45578.6306 | mmcfarlane@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Grenoble Road/ South Oxon Science Village |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Jenny Barker |  | Jenny Barker |  | Pipeline (Approved awaiting budget) | [7 empty] | 100: No; 101: Regeneration; 103: n/a - out of area; 105: Mixed; 107: 3000; 108: 420; 109: 300; 110: 180; 111: 300; 117: 1200; 118: 0; 125: Pre-Application; 188: Off Target; 213: The SODC Local Plan was adopted in December 2020. The SODC LP includes the allocation of the land South of Grenoble Road for approximately 3000 homes as part of a mixed use development. The Council owns approximately 25% of the site. The local plan policy seeks 50% affordable housing (40% affordable rent, 35% social rent, 25% other affordable). SODC have published guidance on First Homes seeking a revised housing mix of 25% First Homes, 35% social rent, 15% low cost home ownership and 25% affordable rent. SODC have commenced a review of their Local Plan and have withdrawn from the Oxfordshire Plan 2050. It is not clear what this will mean for housing numbers required in the plan period. The development of the site is being progressed through a partnership between the Council, Magdalen College and Thames Water. The current focus of work has been on formation of a delivery vehicle between the partners and then the process for the appointment of a master developer as a development partner. Cabinet considered a report in October 2021 and a further report in February 2022 seeking to delegate the final agreement to the LLP and option agreements for the development approach. Review of the capacity of the site and financial modelling has been undertaken due to the constraints now known about the site. Due to a number of changes a further report to Cabinet is proposed to be taken in 2023. 40% allocation on 3,000 unit scheme. Delivery timescale down as 26/27; 214: 44335; 217: 51.7115; 218: -1.1995; 260: Yes; 261: South Oxfordshire DC; 262: 1200; 264: Strat 11; 266: South Oxfordshire Science Village (SOSV); 267: Yes; 268: 40; 269: 2026/27 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Bartlemas Nursery (former site) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing | [8 empty] | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 346; 105: Private; 117: 0; 118: 0; 213: Oriel College owned - Have indicated a desire to still bring forward (as student or resi) in land supply work with planning (Aug 22) - Further contact info requested (DS) | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45554.3545 | mmcfarlane@oxford.gov.uk
Between Towns Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Lila Haracz |  | Lila Haracz |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 599; 105: City Council; 107: 38; 108: 16; 109: 2; 110: 20; 113: 0; 116: No; 117: 38; 118: 38; 120: 43448; 121: 43572; 122: 2020-07-01; 123: 2020-11-01; 124: 44774; 125: Planning approval; 133: 43448; 134: 43572; 135: 44018; 136: 44144; 137: 44944; 188: Completed; 213: Progress on site last month - Brickwork to Church party wall has been completed with only bike store outstanding. Window installation has been completed. Plastering to the communal areas and window reveals is ongoing. M&E 2nd fix in flats is 95% complete. Kitchen installation are 100% complete, with snagging awaited in some areas. Internal door installation to flats is complete, including architraves and skirtings. Front door installations are 100% complete. Decorating Team are working their way through the development. Works to street frontage drainage and electrical mains feed have been completed into the building. Gas, water and comms have been installed to the courtyard and run to the connection points. NHBC and planning yet to approve alternative material selected in lieu of cladding. 15/12/22 - almost completed 18/01/23 - handover is imminent Handed over 18/01/23, currently in 12mths defects period; 217: 51.7327; 218: -1.2183 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Hill View Farm, Mill Lane, Marston | Large mixed scheme of around 150 units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Design & Specification | [7 empty] | 30: Site contamination concerns impacting on land negotiations; 31: Continued liaison landowner; 33: Ground contamination query Landowner not committed; 100: No; 101: Developer Led; 103: 112a1; 105: Private; 106: N/A; 107: 124; 108: 63; 110: 16; 113: 45; 116: No; 117: 79; 118: 159; 120: 2020-09-01; 121: 44188; 123: 2022-06-01; 124: 45809; 125: Planning approval; 126: 20/03034/FUL; 130: 45626; 131: 45641; 132: 46204; 133: 2020-12-02; 134: 2022-03-25; 159: 79; 160: 63; 162: 16; 188: At Risk; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Full planning permission granted - 20/03034/FUL Ownership: Dogar (could be linked with OCC site). Landowner-led scheme. Proposes to submit pre- Owner is tendering for a developer. Has already marketed the s.106 units and OCC made a bid (on the shortlist). Application approved at Planning Ctte on 26 May 21. S106 Signed, Sovereign are having RP units- May 22 - JR Planning have received a pre-action protocol letter for a proposed judicial review outlining a number of grounds of potential challenge, they are consulting a barrister regarding whether the claims are a legitimate threat. The claims are not principally related to highways, although one of the points relates to how the agreement is structured in terms of the contribution to cycling infrastructure, there are a number of other grounds though. Planning are required to respond by 3rd May, at which point the claimants have until 6th May to decide whether to pursue a JR. They may not do so, if this is the case then the development can proceed. If they do proceed then this could delay things considerably. Target Dates - SOS: June 22, 1st PC of affordable housing: June 23, Last PC of affordable housing: June 25. Sovereign are the active RP delivering on this scheme, no other RP delivery at present and Sovereign are NOT contractually on board. The court hearing took place on 1st February, update as of 05/05/2023 Still waiting for a decision from the judge on both on the JR - Persimmon Homes have walked away, the RP are still interested in the site ut milestones and programme TBC. 03/08/23 - the judicial review has been dismissed although there is potential for an appeal - awaiting confirmation. Possible 35 additional units via a DOV and CIL exemption application. 04/10/23 - the high court has dismissed the JR appeal. Scheme can progress subject to clearing/s106 obligations. 30/10/23 - scheme to be delivered by OX Place subject to single cabinet member decision 27/11/23 - landowner has gone back to market. Countryside still in conversation. Jan 24 - issues on ground contamination impacting negotiations 13/03/24 - currently this scheme is not progressing - no developer involvement 29/04/24 - Sovereign no longer involved. Ongoing work to discuss with landowner 03/06/24 - AD working directly with landowner on enabling works. Developer has signed MoU with landowner and RP - now working towards discharging pre-commencement conditions 02/07/24 - confirmation of scheme progress expected 5 August when Sovereign go to their board 01/08/24 - contract to be signed by all parties by end of August. Developer will not be varying the MIP clause so no risk of planning changes. Scheme RAG changed to green. Potential for additional once contracts are signed but unlikely. 04/10/24 - current scheme fell through - renegotiations underway. Scheme moved to Amber. 18 months left on planning to SOS. 15/10/24 - SNG have confirmed they are going to target board approval on the 4th November to then exchange contracts on the 7th November with Bellway. They are agreeing HoT’s to confirm this at present.; 217: 51.7825; 218: -1.2497; 220: 15; 221: 11; 222: 8; 232: 4; 234: 16; 237: 6; 239: 3; 250: 4; 251: 6; 252: 6; 270: TRUE; 271: 44645; 273: TRUE | [12 empty] | 45580.1881 | mmcfarlane@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Redbridge Paddock | Proposal to build 295 new homes on a former brownfield site in the green belt, which is included in the current Local Plan. Plus residential moorings and custom build/self build. |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Stuart Moran |  | Stuart Moran |  | Feasibility | [7 empty] | 30: Updated cost plan recently received from Hill and the viability has been reviewed - very complex. ME appointed to support viability considerations.; 31: KEY ACTION: Resolution to County ransom strip issue to make site developable - review date 16 Oct KEY ACTION: Re-engagement of architects to move to Planning submission (detailed programme to be provided) - review date 16 Oct KEY ACTION: Need to agree mix and units > budget envelope - review date 16 Oct Ongoing discussions re car free status, rights of moorers and wider planning considerations Still awaiting feedback from Homes England on proposed Brownfield/Infrastructure and Land funding; 33: Technical risks include contamination, sewerage and flooding - early engagement with contractor to identify and resolve. New issue around access to energy requirements identified High planning risk around density, landscape and moorings - early engagement with consultants, contractors, planning to overcome risks. Issue of car-free stance from County will make family homes 'unsellable'. A Landscape Architect has been appointed to address the ecology and design. Priors Planning consultant have been asked to give advice on BNG and current site maintenance. Access is a risk with the possibility of a County ransom strip negotiations to take place with the County on 17/10/24. Access is a risk with the possibility of a County ransom strip negotiations to take place with the County in August 24. Legal advice is taking place re BNG baseline and new legislation. Financial viability risks and agreement on PCSA - exploring range of financial models Possible community objection due to former greenfield designation/impact on ecology - working with planners, Members, consultants. It is a brownfeld site. Community consultation 12-14 Oct. Possible time delay due to planning, market conditions, PCSA and contamination - Working with contractors to develop a programme and a risk register to mitigate the constraints. Awaiting Hills cost plan May 24. Legal/land: Section of river owned by 3rd party, so drainage cannot discharge into that section. Clarity of access rights to be resolved. There was a title risk round the footpath ownership and ransom strip, still on going with advice from Capsticks and valuation advice from Carter Jonas. New RoT produced in Nov 23 to reflect advice received, currently being updated in June/July 24, searches now taking place. There has been a question raised by BPTW about the red edge site boundary not matching with the plan. Now resolved. Section of river owned by 3rd party, so drainage cannot discharge into that section. Clarity of access rights to be resolved meeting taking place to address OCC access across the County's land at the end of August 24. June 24 noticed served on boatowners who are in the process of moving. Time: Working with contractors to develop a programme and a risk register to mitigate the constraints. Hills cost plan received 11th July 24. Currently the cost plan is under review.; 37: Scheme to be a sustainability exemplar - targeting EPC A if possible Low/no car challenge under discussion TBC but aniticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 113; 105: City Council; 106: N/A; 107: 295; 108: 92; 110: 24; 113: 146; 116: No; 117: 116; 118: 295; 119: 295; 120: 2023-10-01; 121: 2024-03-01; 123: 2024-08-01; 124: 46143; 125: Pre-Application; 127: 45717; 128: 45901; 129: 45748; 130: 45962; 131: 46478; 132: 47574; 187: Scheme active in feasibility stage - 2029/30 - energy issue also likely to impact current delivery timescale Includes 146 market sale; 188: Off Target; 190: At Risk; 193: At Risk; 199: At Risk; 202: At Risk; 205: At Risk; 208: At Risk; 211: Off Target; 213: Allocation from Green Belt. Feasibility bids submitted - Arcadis appt. Work since Feb 2019. Site investigations complete. Pre-app started. Council's desire to more actively client has led to work pausing to decide dev objectives. Main risk CPZ/on site parking. Project re-started as low car. Soft market testing Jul 22 to select a Contractor, further procure. exp in Sep w/update to OCHL for more funds. Possession action being resolved (Court hearing Sep 22). Tenant to leave. Disc. with Asset Management on security. Tender documents issued. 18/01/23 - Procurement started for EA/Solicitor. EA & solic appoint. pending Feb 2023. Ecology survey Mar 2023. 10/05/23 - Tender docs returned from Equans and Hills, appt pending. Potter and Raper reviewed. Tenant left site 22/12. Boundary fence erected by Asset Man. P&R appointed as EA. Capsticks appt solicitor. Ecology complete. Board report approved more funding. Procurement for Arch & Plan. Consultant. Working w/ Hills pre PCSA. Hills identifying surveys req'd. June 2023: Client-side conv w/planners, housing need and finance needed. 26/06/23 - Client response in development. First meeting with arch's next week. 7/7/23 - Procur. complete for Arch. and Planning Consultant. Hills undertaking site surveys. Site walk through July. Pre-app in Sep. Contractor is Hills subject to PCSA. Working w/consultants, planners and early appt of a contractor to overcome planning risks. Priors Planning Consultant apptd. Landscape Architect being procured on ecology/design. 11/08/23 - Current scheme 377 units. Working up cost options. 22/09/23 - various f/c pushed back inc planning con by 6 mths to Apr 25. Hills undertaking ecology in Sept, site surveys to follow. Landscape Maintenance commenced. Pre-App completed on 26 Sept. Options and costings underway. 30/10/23 - Finance risks clarified b/t OXP and OCC 06/11/23 - working w/Hills pre PCSA, PCSA to be signed w/c 6/11/23. Option of 255 units being considered. 27/11/23 - PCSA signed w/Hill - also Dev Manager and Contractor. Survey work ongoing. Planning sub pushed back 2 mths to Aug 24. SK to meet w/plan (MK) re access. Hill working on cohousing case - SM spoke to Fran. 11/01/23 - Survey work complete (LVIA, Ground, Ecology, consultation with transport) Highways planning pre-app complete Dec23, concerns raised re no car req from County. More pre-apps Feb 24. County confirmed ownership of road/cycle path. Further paper for OCC gov Mar/Apr 24. Land transaction in train. 08/02/24 - Working with Co-Ho on parking. 29/02/24 - Pre-app next week. Design work ongoing (inc C.Smith) in April. 06/03/24 - Updated RoT received to reflect highways/access. Working on a solution for Co-Ho w/evidence on why scheme should have parking. Successful Design meeting for c.316 new homes. Consultants addressing no car v low car. 05/04/24 2nd Pre-Apps took completed 12/03/24 with ODRP, planning risks to be addressed by design changes - poss pause on planning. Updated RoT received to reflect highways/access. Hoardings/Comms strategy post election. 19/04/24 - design meeting now 316 homes. Poss planning pause (6 weeks) to improve masterplan/look at ODRP feedback. Presentation to Members Apr. Hills cost plan due 31/04. Apr Board paper to complete PCSA/request funds 19/05/24 Updated master plan presentation 10 May. May 24 discussions regarding access to County land. Milestones pushed back 2-3m 29/05/24 Likely energy issue 09/07/24 - comms strategy prepared. F/c pl. subm. pushed back 1m to Mar 25. 06/08/24 - Heras fencing erected around site July 24. Notice served on boatowners, 2 have left. Milestones pushed back e.g. SOS 1 year to April 27, PC pushed 4m. 14/08/24 - Community consultation now Oct 24. Soft market testing took place July 24. Clarifications on underwriting of fees by HRA approved at board June 24 to continue 16/09/24 - RIBA Stage 3 due to commence Sept 24. Community consultation 12-14 Oct. Planning on target for Mar 25 13/10/24 - Heras fencing and RIBA3 to start in Nov; 214: 44084; 215: 45215; 216: 45588; 217: 51.729; 218: -1.2515; 270: TRUE; 277: Yes - draft SDS; 281: 0; 282: 80000000; 283: 2695045; 284: 5058452; 285: 6928004; 287: -38841501; 288: 100000; 289: 6580000; 290: 50835080; 291: 55840000; 292: 1675080; 293: 57515080; 294: 2771121; 295: 60286201; 296: 46308000; 297: 4.64; 298: 38; 299: 15991409 |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 |  |  | Yes | Yes | Yes | 1 | 45578.6322 | mmcfarlane@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
Northfield Hostel HSB | 51 homes built on the former Northfield Hostel site. The land was formerly owned by Oxfordshire County Council. The development is being delivered through the HRA. |  | Housing Supply Board |  |  |  |  | Housing |  |  |  |  | James Graham |  | Stuart Moran |  | Delivery | [7 empty] | 30: Ongoing discussions with Equans following their change of direction; 31: Hoarding expected to be put up in April subject to legal confirmation re purdah Demolition/minor works (with Equans) expected to start in April Build contract expected in summer 2024 Resubmission to Homes England in due course; 33: Bats nesting, s278 work - demolition plus other enabling works targeted for October 23 Discharge of planning conditions in time - continue to review and consult Financial viability, rising build costs and access to HE grant - working to mitigate cost increases. New adjacent site to secure access to full grant, HE aware of delay to submission - now targeting late summer 2024 Time delay due to agreeing PCSA/contract price - aim to bring demolition forward and manage cost increases; 77: Dobson Grey; 95: 44510; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 39; 105: County Council; 106: Drafting Bid; 107: 51; 108: 27; 109: 0; 110: 24; 116: No; 117: 51; 118: 51; 120: 44300; 121: 44648; 122: 44895; 123: 44957; 124: 45473; 125: Planning approval; 126: 21/03328/OUTFUL; 129: 44896; 130: 45412; 131: 45443; 132: 46054; 133: 44533; 134: 44648; 188: At Risk; 190: At Risk; 193: At Risk; 199: On target; 202: On target; 205: On target; 208: At Risk; 211: At Risk; 213: Re-tender for contractor Sept 22. Tender Report issued. Legal/Procurement advice. 18/01/23 Meeting with Equans 17/02/23 Delegated approval report to appoint Equans 05/05/23 Delegated approval Mar 23 to appoint Equans. PCSA for signing May 23. August for demo (bats nesting in building). Hoarding to be erected. Value engineering update meeting w/Planners completed unlikely to accept major changes. May 23 - IMS app submitted. 9/06/23 - additionality issue w/HE grant. Demolition in Aug & PCSA pre-commencement underway. 26/06/23 - PCSA signed. Discussion on demolition dates/no clear programme. SOS pushed to Jan 2024. Waiting info f/Equans on demo (ODS increased price). Dev. continuing to progress with add 10 units. IMS application referred back to resubmit w/10 units. 7/7/23 - Discussion to bring forward demo in Oct 23 (Equans). Bat survey on 11/7. Hoarding requested. Value engineering will mean S73 application to Planning. HE App unresolved. SOS pushed back to Feb 24. Planning risk - Currently not meeting planning condition to build 24 units in 30 months from Planning. Missing target by 2 months. S73 to be made to vary the design. 21/08/23 S73 to be applied to vary planning app/reduce costs. Drafting report for demolition delegated approval in Oct. PCSA for completion Mar 24. 22/09/23 - F/c build contract pushed back a month to Dec 23. F/c SOS pushed back a month/March 24. PCSA contract for completion Oct 23. Demo likely Nov 23. s73 submitted. Further bat survey Sept 2023. 03/10/23 - demolition plus enabling work maybe undertaken by Equans in Oct/Nov 23. F/c SOS pushed back a month to Apr. 30/10/24 - IMS application once RM submitted plus signing contract and land purchase (expected imminently) 22/11/23 - Work on contract price, currently w/in parameters. Progress on design. Moving towards demo work. Signing build contract f/c milestone pushed back 2 months to end of Jan 24. Also SOS pushed back 2 months to 31/05/24. Planning risk changed from A to G. Finance risk change from R to A. Market risk changed from A to G. Legal risk changed from G to A. Contract issue over liability levels. Complexity about process to include other site. 27/11/23 - issue around cap on liability for demolition need to work out with Equans. 07/12/23 - Issue with Equans as potential contractor. Need to suspend IMS application until at least Jan 2024. 11/01/24 - JG reprofiled cash flow for DS on both sites. This wraps up PCSA and pauses everything else. Demolition pushed back March to May. Additional land purchase expected this month. Searches have happened and will go to EG. 5/2/24 - Equans working to RIBA 4 (7/3/24). Contracts for minor works asap and main contract expected March 2024. SOS may change. 15/2/24 - SD picking up on land purchase. Equans have been asked for revised price and programme 29/02/24 - legal progressing work contract re Equans demolition. Sale at Northfield 10 moving forward. Will become one project. Change to f/c dates (pushed back 2 months) while updating SDS. 06/03/24 - Work ongoing to manage contract price, but currently within parameters. PCSA 99% complete, Equans working on comments and securing prices. Moving towards demolition work starting, waiting for Legal to conclude minor works contract. 25/03/24 - Build contract with Equans – demolition going ahead. Been approved for demolition/minor works in April. Build contracts due to be signed/start in June. 25/04/24 Working to manage contract price, but currently within parameters. PCSA 99% complete, Equans working on comments/securing prices. Minor works contract sealed, work to start w/c 8/5 19/05/24 - PCSA complete 29/05/24 - demolition started. Finalising cost plan/programme - August SOS for main works. Awaiting exemptions approval from procurement - once has this will submit for planning (expecting July). Believes purchase of add 10 this week. I'll be picking up with James to review/update IMS bid/grant rates. May 2026 expecting completion date but might be earlier; 214: 43958; 215: 44956; 217: 51.7239; 218: -1.2153; 220: 8; 221: 3; 222: 11; 224: 5; 250: 10; 251: 3; 252: 11; 270: TRUE; 271: 44648 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Diamond Place | Diamond Place redevelopment |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Pipeline (Approved awaiting budget) | [7 empty] | 30: Testing scenarios re loss of income/parking being commissioned but surveys to take place after school holidays; 31: KEY ACTION: OCHL response on delivery - review date 28 Oct KEY ACTION: Need to also model mixed housing schemes - review date 28 Oct; 33: Site has a 1m slope. No adverse historical site use recorded. Other tenures to be explored to manage market risk; contractual obligations re non-resi-elements; need experienced architect Finance - abnormal costs largely unscoped. Testing of a range of scenarios re retaining elements of parking to cover potential loss of income. Issues identified re land ownership, currently with legal including considering insurances Time delays expected but progress will be closely managed - need to clarify non-resi details Community risk - high expectations for design/build; 37: TBC but aniticipated Fabric first approach - good insulation and air tightness. This will minimise energy consumption and cost. Electric site with ASHP in houses MVHR Solar panels A target of zero carbon for regulated energy is the target.; 100: No; 101: Regeneration; 102: TRUE; 103: 18; 105: City Council; 106: N/A; 107: 104; 108: 41; 110: 63; 117: 104; 118: 104; 119: 104; 124: 46728; 125: Pre-Application; 127: 46868; 128: 47088; 129: 45748; 130: 46692; 131: 47362; 132: 47942; 187: Scheme active in pipeline phase (approved awaiting budget); 213: Carter Jonas commissioned to work on concept Masterplan (RIBA 1) with supporting business case. Expected to complete by Summer 2021. University of Oxford timelines are still 2-3 years away from development although they haven't begun even schedule of accommodation. The Council are developing an option on how to proceed without the University. DS update 30/05/22: no change – very early stages & paused (Univ) - Regen team to report back to HSB on this in June/ July 26/06/23 - inception visit being arranged by OXP 25/08/23 - requested greater info on delivery timeframes/AH units but due to process with Ox Place which may impact on the timing and numbers it's not possible to commit anything yet. JN should have a better idea in October - but likely to be pushed back to 28/29 PC. 22/09/23 - All f/c dates pushed back between 6 months and over a year 03/10/23 - OXPlace to appoint design team subject to receiving a client brief from OCC. Early work demonstrates that the site is feasible. Coming to HSB in October. Alternative to GP practice if this does not remain. Query over leisure centre. First payment in 26/27. 30/10/23 - SK met with HLM, Montagu Evans architect. 27/11/23 - for discussion at HSB December meeting. Need to know what is planned. 01/11/24 - No feasibility spend at the moment. Awaiting client brief in the next month. 25/02/24 - PC date moved back 2 years based on OX P alignment - although JN unable to confirm PC date until scheme is within OXP BP 06/03/24 - client brief presented at Feb HSB/Mar DB. Initial feasibility is ok, ready to procure design team. OCC require time to finalise land assembly, issues outstanding about amount of parking required, whether there will be a tenant for a medical practice, appetite from OUD for master-planning. Design issues include whether to demolish & rebuild community centre, there is a small strip of white land within the red line. Milestone dates (exc PC) pushed back 2 years. 25/03/24 - Design - negotiate with the uni on masterplan. JG says planners are insisting on masterplan. Can go to HSB/DB with a brief masterplan and confirmed with uni. 19/04/24 - Initial feasibility is ok, ready to procure design team. OCC brief received. Needs OXP Board approval to proceed. 25/04/24 - parking options report required, with corresponding capacity & cost plan 19/05/24 - RoT needs to be finalised 29/05/24 - James taking this. Issue in covering off the potential lost income. JG testing scenarios of retaining different levels of parking. High expectations from community in design and build. Revised dates pushing back 12-18 months: Planning - April 2028, consent - Dec 2028, PCSA before planning - Nov 2027, SOS - Sept 2029 - 3 year build. 06/08/24 - no change - dates differ from OCHL b/c they have not yet been pushed back 13/10/24 - Parking consultant appointed; 214: 45005; 215: 45348; 216: 45346; 217: 51.7762; 218: -1.266; 270: TRUE; 277: Yes; 281: 9000000; 282: 34000000; 283: 2000000; 284: 2446000; 285: 1468102; 287: 5965898; 288: 6635000; 289: 8268750; 290: 41576250; 291: 54880000; 292: 1600000; 293: 56480000; 294: 2584614; 295: 59064614; 296: 46611250; 297: 3.9; 298: 39; 299: 3744590 |  |  |  | 40% reduction on 2022 Building Regs | B | 2022 |  |  | Yes | Yes |  |  | 45578.6086 | mmcfarlane@oxford.gov.uk | Y | 45545.5281 | rhaverson@oxford.gov.uk
BBL District Centre Regen Phase 1 | Blackbird Leys redevelopment delivering 294 new affordable homes over two sites - SR units only on this site with SO on Knights Road |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Karoline Soisalo De Mendonca |  | Karoline Soisalo De Mendonca |  | Delivery | [7 empty] | 30: Scheme has now started on site Weekly site updates being provided; 31: Ongoing monitoring of badger sett and programme implications at Knights Road; 33: 29/04/24 - Discovered a badger sett at Knights Road. This may delay commencement of programme at Knights Road.; 100: No; 101: Enabling RP Led; 103: 9 & 593; 104: Catalyst; 105: City Council; 106: N/A; 107: 112; 108: 112; 116: No; 117: 112; 118: 112; 123: 2022-01-18; 124: 46258; 125: Planning approval; 126: 23/00405/OUTFUL; 129: 45231; 132: 2026-04-30; 133: 2023-02-17; 134: 2023-08-16; 135: 2023-11-20; 136: 2023-12-11; 152: 61; 153: 61; 159: 51; 160: 51; 188: On target; 213: Project viability under review - decision to proceed at risk. Finalising Stage Two Gateway negotiations with Catalyst. Key issue is financial viability risk share and HIF programme. Planning application ready for submission pending approval to proceed. RAG to Red due to delivery risk re viability. Alternative delivery options and changes to development agreement between Catalyst and OCC under review Some Block A 2-beds likely to be converted to 1-beds due to bulding regs 11/08/23 - The project is still at risk due to external funding which is time sensitive and we haven't had planning consent. We are expecting to be granted consent after 15/08/23, which is our planning committee date. Once we have consent and Peabody have been able to demonstrate project viability, the RAG status should be able to be lowered from red. Planning confirmed at August 2023 committee. 7/9/23 - HE grant issue 13/10/23 - Draft s106 with legal 31/10/23 - Phase 1 split out to identify Knights Road. District centre refers to Blocks A (51 units) and D (61 units). All units confirmed as social rent. Current target PC is Block D - July 25 and Block A - March 26 - units moved into 25/26 delivery. PC dates will be reconfirmed once in contract 6/11/23 - query reducing total numbers by 6 for the replacement units 8/11/23 - DoV to Development Agreement between OCC/Peabody to be signed on 10 Nov (may slip to subsequent week but we are keeping this date as projected date) with Building Contract to be signed between Peabody and Hill Contractors anticipated for 20/11/23 28/11/23 - Note that there are 8 units that will be replacements. Leave within the programme at the moment. 16/01/24 - Block D – July 25 (53 SR + 8 SR OCC = 61 units and expected on one handover date) Block A – April 26 (51 SR units and expected on one handover date) Knights Road – last PC April 26 – phased handovers over a 12-month period (84 SO) 26/01/24 - KM - Phase 1 has started. Hoarding is up and they are currently carrying out enabling works. The hoarding went up on the second week of December 2023 opposite Evenlode Tower (Block D site), but I'm not sure of the exact date. They started demolition works around 8th Jan 2024. 29/04/24 - Discovered a badger sett at Knights Road. This may delay commencement of programme at Knights Road. 14/06/24 - No change to programme, delivery as expected; 217: 51.7209; 218: -1.2044; 220: 36; 222: 20; 252: 66; 254: 18; 270: TRUE; 271: 45225 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
BBL Knights Road Phase 1 | Blackbird Leys redevelopment delivering 294 new affordable homes over two sites - SO units only on this site and SR units on BBL District Centre Phase 1 |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Karoline Soisalo De Mendonca |  | Karoline Soisalo De Mendonca |  | Delivery | [7 empty] | 30: Related to BBL Phase 1 development; 31: Awaiting confirmation of new RAG status, likely this scheme can move to Amber/Green; 100: No; 101: Enabling RP Led; 104: Catalyst; 105: City Council; 106: N/A; 107: 84; 110: 84; 117: 84; 118: 84; 123: 2022-01-18; 124: 46258; 125: Planning approval; 126: 23/00405/OUTFUL; 129: 45231; 132: 2026-04-30; 133: 2023-02-17; 134: 2023-08-16; 135: 2023-11-20; 136: 2023-12-11; 159: 84; 162: 84; 188: On target; 213: 31/10/23 Knights Road split out from Phase 1 to help scheme monitoring. Target PC date currently March 2026 for all units with delivery phased over the preceding year. Target delivery now in 25/26 - PC dates will be reconfirmed once in contract 16/01/24 - Knights Road – last PC April 26 – phased handovers over a 12-month period (84 SO) 26/01/24 - KM - Phase 1 has started. Hoarding is up and they are currently carrying out enabling works. The hoarding went up on the second week of December 2023 opposite Evenlode Tower (Block D site), but I'm not sure of the exact date. They started demolition works around 8th Jan 2024. 14/06/24 - No change to programme, delivery as expected; 217: 51.7205; 218: -1.2014 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
BBL District Centre Regen Phase 2 | Blackbird Leys redevelopment delivering 294 new affordable homes over two sites. |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Karoline Soisalo De Mendonca |  | Karoline Soisalo De Mendonca |  | Design & Specification | [7 empty] | 33: Risk in access to external funding which is time sensitive - legal and AHS in discussions to secure funding; 100: No; 101: Regeneration; 103: 9 & 593; 104: Catalyst; 105: City Council; 106: N/A; 107: 98; 108: 62; 110: 36; 116: No; 117: 98; 118: 98; 124: 46861; 125: Planning approval; 129: 45231; 130: 45270; 131: 46204; 132: 2028-05-20; 133: 44974; 134: 45154; 173: 98; 174: 62; 176: 36; 187: Active scheme - awaiting confirmation of viability/funding; 188: Off Target; 213: Project viability under review - decision to proceed at risk. Finalising Stage Two Gateway negotiations with Catalyst. Key issue is financial viability risk share and HIF programme. Planning application ready for submission pending approval to proceed. RAG to Red due to delivery risk re viability. Alternative delivery options and changes to development agreement between Catalyst and OCC under review. PC date pushed back from Dec 27 to May 2028. 26/01/24 - Phase 2 milestones: Vacant Possession: Feb 2026 Completion: May 2028 20/05/24 - Potential to become Amber once agreed dates are formalised. Planning amendment required. 14/06/24 - Phase 2 meeting with Peabody on 17th June to discuss viability, and they will present a strategy for Ph2 delivery. This strategy, I suspect, may have changes to the housing offering or adding more units. 05/08/24 - Phase 2 is still red - we still haven't agreed a delivery strategy, so in theory that phase is not yet viable in its current form.; 220: 21; 221: 3; 222: 29; 224: 9; 250: 14; 251: 1; 252: 21; 270: TRUE; 271: 45225; 300: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land at St Frideswide Farm | Developer-led mixed scheme of 134 units of which 67 are affordable |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Delivery | [7 empty] | 30: Ongoing discussions with RP; 100: No; 101: Developer Led; 103: 107; 104: Sovereign; 105: Private; 106: N/A; 107: 134; 108: 54; 110: 13; 113: 67; 117: 67; 118: 134; 120: 2021-05-24; 121: 44463; 123: 44835; 124: 45809; 125: Planning approval; 126: 21/01449/FUL; 132: 45894; 133: 2021-05-24; 134: 44991; 135: 44988; 136: 2023-03-03; 145: 50; 146: 44; 148: 6; 152: 17; 153: 10; 155: 7; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Full planning permission submitted - 21/01449/FUL - Planning achieved 24/09/21,The scheme includes 67 affordable homes, being 54 social rented and 13 shared ownership units (accommodation schedule saved in scheme folder) priority is on getting the S106 agreed and the permission issued to finalise the land purchase. SOS anticipated autumn 22. Phased handovers expected with first completions around Summer 2023, I would anticipate final completion of the whole site approximately two years after that – Summer 2025. 02/09/2022 - S106 Completed - Developer has now sent out a request for updated bids to the registered providers who were the leading bidders in our pre-planning market testing. The Section 106 requires tje developer to have the affordable housing under contract prior to implementing the planning permission, so it is now a priority for them to get the affordable contract secured. Separately, they also need to finalise the land purchase transaction, which was conditional upon their grant of planning permission. The hope is that they will be able to secure the land purchase and affordable housing contract by the end of 2022, allowing our build team to start on site early in 2023. Soverign have agreed HOT and wish to convert 2 x SO 4B6P units to 2 X SR units which we support and is going through the planning enquiry process for a variation. The land purchase completed just before Christmas, and subject to getting the pre-commencement conditions and S106 pre-implementation requirements addressed the hope is to start on site in May 2023. Sovereign contractually on board, 06/03/2023 SOS – Mid May 23 - Waiting on confirmation SOS has taken place First PC – latest programme has the first PC on the affordable in Dec 2024 PC – latest programme has the final PC on the affordable in Oct 2026 31/10/23 - onsite and progressing 28/11/23 - DOV on two points -tenure change and MIP clause. No issues reported. 13/03/24 - progressing fine - awaiting DOV to be confirmed 29/04/24 - Two DOVs - one for MIP clause: one for tenures switch: 03/06/24 - Site progressing - awaiting confirmation of first handover. Still awaiting confirmation of DOV (submitted May 2024). Update: no handovers yet there is a delay caused by the service connections and so currently waiting on an update on the timing but it is likely these will be August handovers. AD has requested site visit/comms liaison 13/06/24 - There are some changes to delivery but this doesn't affect the year. Current delays are caused by delays in the connection to mains water which will mean the build can progress but we cannot take possession of the units unit the connection is achieved. Changes updated.; 217: 51.7977; 218: -1.2659; 220: 17; 222: 17; 233: 8; 234: 6; 237: 6; 250: 2; 252: 5; 266: Priory Grove; 270: TRUE; 271: 44798; 273: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Templars Square | Redevelopment of shopping centre to include residential units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 30: A consultant has been selected for the Templars Square scheme with Council on-boarding to lead to formal appointment shortly.; 100: No; 101: Developer Led; 103: 14; 105: Private; 106: N/A; 107: 850; 108: 0; 109: TBC 166; 110: 0; 112: TBC 170; 114: 886; 116: No; 117: 0; 118: 0; 125: Pre-Application; 127: 45747; 128: 46021; 131: 2026-07-30; 132: 2033-12-31; 187: Active scheme in feasibility stage; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Planning permission granted - 16/03006/FUL - S106 was agreed. 22.03.2022 - Unfortunately the Applicant sold the site after planning permission was issued. Planning have been informed that the new owners want to do something much bigger across the whole shopping centre, including residential, but that’s all we know at this stage. and would expect a new planing application to be submitted. In contact with the new land owners Redevco to understand new plans, meeting is to be arranged. 17.05.2022 Currently overlaying OCC stock to OS Plan, to arrange visit with area manager to understand the site in more details. New planning consent being sought. 7 June 2023 - Lease interest now with Redevco for larger scheme 28/11/23 - In pre-app process for RM. Current milestones: Planning submission: Q4 2024 Planning approval Q3: 2025. SOS: Q2: 2026. Build programme of 7 years so end of 2033 for PC. 08/03/24 - schemes numbers roughly 650 in total. A consultant has been selected for the scheme with Council on-boarding to lead to formal appointment shortly. 29/04/24 - Montague Evans appointed for commercial advice. Looking at possible Homes England support. Developer advising scheme currently unviable. 08/05/24 - a total of 850 units, the Affordable Housing provision is 20% that totals 170 for a tenure of Affordable Private Rent (APR), this is confirmed that the 170 units will be retained by the freeholder and will not be managed by a Registered Provider 03/06/24 - Analysis review and summary expected this month - continued discussion with Homes England on funding options 01/08/24 - on way to MOU. draft s106 is with applicants and then on to county.; 217: 51.7326; 218: -1.2169; 275: 100000; 276: Agreed at HSB 12 June 2023 and Development Board on 15 June 2023. This represents 50% of a £200,000 commitment for feasibility | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Thornhill Park | 201 affordable units within mixed developer-led scheme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Design & Specification | [7 empty] | 30: Successful discussions with RPs have led to three RPs indicating interest in the site; 31: Ongoing work to secure an RP Review of potential changes to affordable housing numbers; 100: No; 101: Developer Led; 103: 38; 105: Private; 106: N/A; 107: 402; 108: 161; 112: 40; 113: 201; 116: No; 117: 161; 118: 402; 119: 402; 120: 44364; 123: 2023-11-01; 124: 46692; 125: Planning approval; 126: 21/01695/FUL; 131: 2024-11-24; 132: 2030-04-19; 133: 2021-06-17; 134: 2024-09-27; 166: 70; 167: 70; 173: 98; 174: 77; 178: 21; 187: Reprofiling in line with delivery programme following s106. 98 units expected in 28/29 and 33 units in 30/31; 188: On target; 190: On target; 193: On target; 196: On target; 199: On target; 202: On target; 205: At Risk; 208: On target; 211: At Risk; 213: Full planning permission submitted - 21/01695/FUL - Aapplication was validated on 05/07/2021 - The proposed distribution of affordable units in the forthcoming revision to the current application for 402 flats, a hotel and Innovation Centre. Planning Application on going, nothing confirmed by planning as of yet. The proposals are consistent with Policy H2 of the adopted Local Plan regarding quantum of affordable housing (50%) and tenure mix of the affordable element (80% social rented and 20% intermediate).Savills confirm intentions of 201 affordable dwellings containing 1 bed – 88 dwellings 2 bed – 66 dwellings 3 bed – 32 dwellings 4 bed – 15 dwellings Total = 201 affordable dwellings, the break down into the 80% SR & 20% Intermidate split still TBC. NO provisoon of First Homes or self build units, Savills note that the TAN does not refer to Paragraph 65 of the NPPF which states that Build to Rent proposals are not required to provide affordable home ownership. on the assumption of an average of circa 100 dwelling completions per annum, this could allow the scheme to be completed over a four year period from with a SOS in 2023 & First PC (INC affordable units in 2023) and a final PC of 2027. Not policy compliant but on balance, the planning officer is minded to approve the application as proposed given that the scheme is 100% flatted and, arguably, more appropriate for smaller 1 bed units. Further, the reason that the scheme can no longer meet a H4 compliant mix is due to the significant decrease in heights which I requested in order to mitigate harm on neighbouring amenity and to better respond to the local context. The design improvement more weight than the mix of affordable housing. This scheme is an important site allocation for us and I consider that the compromises that have been made are acceptable in this instance. It is positive that we are achieving 50% affordable with an even split between the mix of private and affordable. Planning application awaiting decision after being presented to committee on 14/12/2022 to grant planning permission subject to S106 completing. Currently in progress with S106 agreement and AH delivery. 19/09/23 - Forecast SOS pushed back 6 months to May 2023 - still seeking RP 28/11/23 - Still waiting on RP appointment to agree s106. 02/04/24 - move from Red to Amber as there has been progress in relation to RP - programme still to be agreed. 05/04/24 - potentially a change to delivery numbers to reduce ah by 2 and change tenure mix. Needs to go through planning TBC. New mix proposes 153 social rent and 46 affordable rent - total ah of 199. 29/04/24 Draft 106 resuming - phasing plans expected May 24. SOS pushed back 6 months 15/05/24 Change to tenure/units sizes across the scheme - to be updated when confirmed. No change to overall units/tenure mix 03/06/24 - Position agreed to progress s106 01/08/24 - draft s106 is with applicants and then on to county. 06/08/24 - s106 expected by 13 Sept. Then SOS likely Dec 2024. Delivery phasing to be confirmed but will be 270 SR in Ph1 and 76 SR in Ph 2 and 14 SR in Ph3. The Affordable rent units are likely to be made affordable private rent - this is an affordable tenure as per capital funding guide. 4- year build programme with final year delivery most likeley in 2028/29 - final handovers expected by Dec 2028. A up to date handover schedule is anticipated immediately after s106.; 217: 51.7616; 218: -1.1843; 220: 70; 221: 33; 222: 20; 224: 26; 229: 12; 270: TRUE; 271: 45561 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandford Road (phase 2) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Enabling RP Led; 103: 29; 104: Green Square Accord; 105: Private; 107: 0; 108: 14; 109: 0; 110: 11; 113: 0; 114: 0; 115: 0; 116: No; 117: 25; 118: 25; 119: 1900-01-24; 121: 2018-09-05; 123: 2019-03-03; 124: 44742; 125: Planning approval; 134: 2018-09-05; 135: 2020-06-01; 136: 2019-03-03; 137: 44893; 188: Completed; 213: 25 Equity-Share Key Worker units not able to be delivered as intended (lender issues) - so units to be delivered as per the default in the s106 - to go back to the usual planning compliant mix on the scheme as a whole - this would be 11 @SR and 14 @SO - but the agreement with Green Square Accord is able to deliver 11@SO now (Dec 21) and 14 @SR (Jun 22) instead. Andrew Murdoch to confirm plans with Abbey - Agreed with Andrew (Plg DM) and Sally F (Legal) that we are minded to agree to this approach (DS) - pending further info requested from Abbey (Dec 21). Jan 22 - Info received back to AM from Abbey. 11.03.2022 - The SO block is finished, snagged but GSA need to get into contract and check all the certs and then PC will follow soon after. The target was March but realistically anticipated to slip into April. 29/11/2022 Handovers completed.; 217: 51.7176; 218: -1.2304 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Bracegirdle, Mortimer, Broad Oak |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: n/a - small site; 105: City Council; 107: 8; 108: 8; 116: No; 117: 8; 118: 8; 121: 43445; 122: 43885; 123: 2020-04-01; 124: 44439; 125: Planning approval; 134: 43445; 135: 43885; 136: 43922; 137: 44887; 188: Completed; 213: Warranties outstanding issue with ODS (July 22). s.278 works issue resolved. Handover scheduled for 17/10. Works required by building control to secure sign off are being undertaken. We expect handover to take place on the 10th November; 217: 51.7465; 218: -1.2006 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Manzil Way |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: 574; 105: Mixed; 107: 10; 117: 0; 118: 0; 213: Leased by Health from City Council - approx 30 years left on lease only. Named in the Local Plan 2036 as a site for possible Employer-linked housing. Policy SP46 relates - But Council as landowner should be able to negotiate general needs housing also at this site or via a swap with Slade House site; 217: 51.7469; 218: -1.2317 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Wolvercote Paper Mill |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Enabling RP Led; 103: 67; 104: Catalyst; 105: Private; 107: 191; 108: 77; 109: 0; 110: 19; 113: 95; 114: 0; 116: No; 117: 96; 118: 191; 119: 1900-04-05; 121: 2018-09-25; 124: 44614; 125: Planning approval; 126: 13/01861/OUT; 134: 2018-09-25; 137: 44804; 188: Completed; 213: Completions:Oct-20 14 SO flats; Dec-20 7 SR houses; Mar-21 23 SR flats; May-21 12 SRflats ; 21 SR flats expected Jan-22; 22/23 7 SR houses 1 x 2 bed SR flat added through conversion of commercial unit - S106 in negotiation (Aug 21). Mar 22 update: Confirmed now one extra SR unit, so 77 @SR & 19 @SO. Total affordable 96. 88 units now handed over plots 195 & 143 – 146 will be on 28th July. Plots 140 & 141 have now slipped to August as there is a supply issue with internal doors. The final 2 plots were handed over on 31st August, plots 140 & 141.; 217: 51.784; 218: -1.2935 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Cumberlege/ Elsfield |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Lila Haracz |  | Lila Haracz |  | Completed | [7 empty] | 99: Year 2; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: 20; 105: City Council; 107: 35; 108: 20; 109: 3; 110: 12; 113: 0; 116: No; 117: 35; 118: 35; 119: 1900-02-03; 120: 2018-12-24; 121: 2019-03-20; 122: 2020-07-01; 123: 2020-11-01; 124: 44774; 125: Planning approval; 133: 2018-12-21; 134: 2019-03-20; 135: 2020-07-01; 136: 44053; 137: 44798; 188: Completed; 213: Cumberlege completed in Oct '21 (9 x SR units) Floor tiling in the entrance cores has been completed throughout. Boiler and radiator installations are complete and have been commissioned. Mechanical & Electrical meters have now all been installed. Bathroom installations have all been completed. Painting (snagging items) throughout the internals is still ongoing. Flooring to kitchens and timber flooring is now complete. Courtyard architectural installation to balconies has been completed. Soft and hard landscaping has been completed. Block paving to parking area has been completed, as has the tarmac to the new access road. Snagging of all homes has been completed and making good is progressing. The completion date has slipped as is scheduled for end of August.; 217: 51.7776; 218: -1.243 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Littlemore Park (phase 1) | All-affordable scheme delivering 273 homes across 2 phases - part Growth-Deal funded |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Completed | [7 empty] | 100: No; 101: Enabling RP Led; 103: 34; 104: Catalyst; 105: RP; 107: 167; 108: 55; 110: 112; 113: 0; 114: 0; 116: No; 117: 167; 118: 167; 119: 167; 120: 43341; 121: 43586; 122: 44104; 123: 44213; 124: 45036; 125: Planning approval; 126: 14/02940/OUT; 133: 43341; 134: 43586; 135: 43862; 136: 43884; 137: 45247; 188: Completed; 213: Phase 1 167 Units - Was 164 and now 167 Units 52 SR & 115 SO with the 3 additional. 3 additional units (SR) that are due to obtain planning. These are HE funded are HE. Accommodation schedule obtaining and tracking handovers with Catalyst. 22/11/23 - Confirmation of completion of all units. Awaiting PC certificate.; 217: 51.7225; 218: -1.2275; 220: 5; 221: 5; 222: 31; 235: 12; 237: 2; 250: 16; 251: 9; 252: 87; 270: TRUE; 271: 42453 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45557.6303 | mmcfarlane@oxford.gov.uk
Blackbird Leys Church |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 103: n/a; 105: Private; 107: 20; 117: 0; 118: 0; 120: 43903; 121: 44034; 125: Planning application submitted; 128: 44284; 133: 43903; 213: Proposal for possible off-plan purchase of this development following the demolition of the church. 20 residential flats. Early discussion re a possible HRA off-plan acquisition. Planning Application Dec 18 (18/03405/FUL) / Additional Info Mar 20 (20/00688/LBC). Awaiting planning approval (Jan 21). Mar 21 - Planning Consent still awaited. Further comments received in Feb 21. Consultation period now closed. May 21 - Application approved pending Sec of State approval re demolition of the existing listed building. Conversation opened up again with developer over potential sale, and provisional offer made - being considered by the Trustees. End July 21 update - Trustees seek to seek competitive offers from the market. Nov 21 - Marketing underway. OCC to not bid at the current time. (OCHL MD may wish to consider for OCHL if price expectation reduces). June 22 - Diocese may buy the units into it's investment portfolio. If this doesn’t happen Carter Jonas will take it to the wider market in Autumn 22. Tender for build not yet out, waiting for market to settle re pricing. Plg app status (17/06/22) - still having the S106 agreed.; 217: 51.7211; 218: -1.2014 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45557.6216 | mmcfarlane@oxford.gov.uk
Salford Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 100: No; 101: Developer Led; 103: 601; 105: Private; 107: 16; 113: 16; 116: No; 117: 0; 118: 16; 121: 42802; 125: Planning approval; 134: 42802; 137: 44854; 188: Completed; 213: Application to vary affordable housing requirement because of problems in securing an RP partner - variation to a financial contribution for offsite housing agreed at October 19 EPC. S106 completed for £300k off-site contribution instead of affordable housing on-site. Progress monitoring - windows installed (Aug-21) TRACKING PROGRESS OF SITE ONLY - NO DELIVERY OF AFFORDABLE UNITS. 24.10.22 Confirmation of completion of site and receipt of funds.; 217: 51.7682; 218: -1.2436 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barton Park (Phases 2 and 4) | S106 scheme with Barton Oxford LLP and Countryside Homes |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Delivery | [7 empty] | 30: Recent changes to delivery programme but scheme on track to deliver units from next financial year. Cabinet papers and SMD approved for future HRA acquisitions.; 31: The project is on budget and programme. Properties will now be acquired direct into the HRA, with the report seeking formal approval for OCH(I)L to transfer the existing stock, and future acquisitions, into the HRA, to be considered at Cabinet (October) and Full Council (November).; 33: Time delay due to recession and labour issues - monitoring of programme delivery and dialogue with Vistry; 37: ASHP in later stage - gas in earlier phase; 95: 41465; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 2; 105: Other; 106: N/A; 107: 423; 108: 174; 116: No; 117: 174; 118: 174; 119: 0; 124: 45992; 125: Planning approval; 132: 2027-11-24; 133: 44701; 134: 44705; 135: 44713; 136: 44713; 145: 39; 146: 39; 152: 52; 153: 52; 159: 54; 160: 54; 166: 29; 167: 29; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: Future phases of Barton Park - completed transfer to Developer (Countryside) on 29.06.21. Planning Application complete. AH changed PC date to 01/12/25 to be in line with other Barton ParK Ph 2&4 entry. Reserved Matters Application = full planning consent obtained on 24/05/22 Planning committee (21/02776/RES). Also see line re additional affordable units from this phase (debited from totals here). Overall Ph2&4 is 434 total homes (so 174 @SR = 40%) as per the RMA. Site set up under way. No further details at present. 18/01/23 - No further update 17/02/23 - Will initiate contact with new team to push for programme details. 10/05/23 - awaiting update from Vistry, monitoring scheme closely. Clerk of Works and employers agent appointed. First meeting with Vistry to take place on site on 23 May 2023 17/05/23 - Site set up under way. No further details at present. Merger of Countryside with Vistry has led to project team changes. First site meeting 23.05.2023. June - waiting for handover schedule and confirmation of units. 26/06/23 - Awaiting Countryside to get going with programme. 51 this year seems too high. Need a new programme to revise figures. 01/08/23 - Site set up under way. No further details at present. Merger of Countryside with Vistry has led to project team changes. Vistry engaged with EA etc and documentation becoming available. Waiting for handover schedule and confirmation of units. 31/08/23 - Amended delivery forecast figures to match OX Place. Not quite the same as latest spreadsheet but this is likely to change so OX P figures probably more realistic. 24/25 - 31, 25/26 - 55, 26/27 - 45, 27/28 - 43 07/09/23 - Site set up under way. Vistry engaged with EA etc and documentation becoming available. Partial handover schedule provided - units to complete from March 2024. 7/09/23 - Change to OXP delivery programme now reflected on smartsheet. 20/09/23 - changes to programme again - picked up with AD who is realigning OXP schedule. Now 8 in 23/24; 44 in 24/25; 35 in 25/26; 49 in 26/27 and 38 in 27/28 03/10/23 - Site set up under way. Vistry engaged with EA and documentation becoming available. Partial handover schedule provided - units to complete from March 2024. Site team now established and providing detail around units. 30/10/23 - units delivering in 2024/25 reduced from 44 to 37 07/12/23 - seeking clarification on delivery dates. Next site meeting 12/12/23. 11/01/24 - Next progress meeting on 15/1/24. 15/03/24 - confirmed programme with AD: Developer profiling has changed a little to: 24/25: 62 25/26: 29 26/27: 58 27/28 (final handover November 2027): 25 But reporting on Smartsheet builds in some flexibility on this as units on other phases have often slipped. 05/04/24 - Works progressing on Phase 2. Design for final sub phase 4B2 due w/c 18 March 2024 19/09/24 - Programme on track - some slight delays to first handovers. Cabinet papers and SMD approved for future HRA acquisitions.; 217: 51.7699; 218: -1.212; 220: 19; 221: 22; 222: 26; 224: 3; 233: 5; 234: 53; 237: 21; 238: 19; 241: 5; 242: 1; 270: TRUE | [6 empty] | Yes |  |  | Yes | Yes | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barton Park (Phase 3) | Barton Park development with current and ongoing delivery of affordable units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Allison Dalton |  | Allison Dalton |  | Delivery | [7 empty] | 30: Changes to programme but final PC date remains the same with scheme completing next year Cabinet papers and SMD approved for future HRA acquisitions.; 31: Ongoing monitoring The project is on budget and programme. Next handovers in Sept and Nov. Properties will now be acquired direct into the HRA, with the report seeking formal approval for OCH(I)L to transfer the existing stock, and future acquisitions, into the HRA, to be considered at Cabinet (October) and Full Council (November).; 95: 41465; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: 2; 105: City Council; 106: N/A; 107: 207; 108: 83; 113: 124; 116: No; 117: 83; 118: 207; 124: 45565; 125: Planning approval; 132: 45626; 133: 43549; 134: 43693; 135: 43090; 136: 44075; 138: 17; 139: 17; 145: 35; 146: 35; 188: On target; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: This is a S106. OCC is purchasing completed units from the Phase Developer. Redrow have suffered Covid delays. Progress against programme delayed by industry wide materials shortages and pandemic. Schedule of handovers available. 18/01/23 - No Further Update 17/02/23 - Recent discussions with site team stressed that we expect to receive the current forecast of 37 units in 23/24 and final 15 in 24/25. June 2023 - Expecting handover of 17 units on 30th June. The new site team seems to be working well with the subcontractors and work is progressing across the site. 26/06/23 - Still seeking up to date programme and figures. Not sure about handovers and final PC date. 30/06/23 - 17 units handed over 03/12/23 - Next handovers in January 2024. Redrow has closed it's Thames Valley offices and made staff redundant. Management is now with South Midlands regional office in Northampton. Revised handover now set to complete in October 24. 07/12/23 - Seeking clarification on Handover dates. 11/01/24 - Site meeting and progress report on 9 Jan. Next handovers March 2024 with final handover October 2024. 14/03/24 - Email confirmation with AD to confirm slippage so 17 handovers for 23/24 and delivery in 24/25 now 35. 05/04/24 - Redrow Team making good progress to programme. Must be offsite by 31 December 2024 because compound land is owned by another developer. 19/09/24 - Cabinet papers and SMD approved for future HRA acquisitions.; 217: 51.7716; 218: -1.2196; 222: 12; 234: 38; 235: 5; 237: 18; 238: 10; 270: TRUE | [11 empty] | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45551.1236 | mmcfarlane@oxford.gov.uk
William Morris Close |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Completed | [7 empty] | 99: Year 3; 100: Yes; 101: Enabling RP Led; 103: 341; 104: Legal & General; 105: Private; 107: 86; 108: 38; 109: 12; 110: 36; 113: 0; 114: 0; 116: No; 117: 86; 118: 86; 119: 86; 120: 43454; 121: 43789; 122: 44103; 123: 44207; 124: 44621; 125: Planning approval; 126: 18/03330/OUT; 133: 43454; 134: 43789; 135: 44103; 136: 44116; 137: 44818; 188: Completed; 213: Planning Consent Nov 19. L&G proposed a switch to make the scheme 100% affordable in July 20. As a 'land-led' scheme it was therefore agreed as eligible for OGD. Funding agreements being developed (Sept 20) and Cabinet project approval sought (14 Oct 20). Head of Finance to approve initial 90% OGD grant award on 15 Oct 20 using delegations ahead of Council change to budget (30 Nov 20). Contracts (Cantay & L&G signed 29 Sept 20). Contractor has now started on site. Projected handovers: Mar 22 Blocks E & F (24 SR flats) & 8 SR houses; 22/23 May-22 Block B (12 AR flats) & Block A,C&D (36 SO flats); Jul-22 6 SR houses. Nov 21 update: Units 7-14 & 63-86 (32 Social Rented units) expected to handover early March 2022 (7 months ahead of programme). Other handovers in May 22 and July 22. L&G update 09/06/22: developer at William Morris Close is slightly behind programme and the next plots (48 plots) are now due 5th August with final 6 plots on 15th August. This has slipped from our original PC forecast for July 2022. 11th July update - PC to slip to mid-Sept now (slight delays re flooring finishes and then snagging); 217: 51.7388; 218: -1.2089 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barton Park (Phase 2 &4) ADDITIONAL UNITS | 96 additional units on Barton Park with Places for People |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Megan McFarlane |  | Megan McFarlane |  | Delivery | [7 empty] | 30: Meeting with P4P to confirm progress on-site; 31: Confirmation of delivery programme Work to confirm OCC/P4P contract re tenure change; 33: Work on site has started and scheme progressing as expected; 100: No; 101: Enabling RP Led; 103: 2; 104: Places for People; 105: Other; 106: N/A; 107: 95; 108: 9; 109: 31; 110: 56; 116: No; 117: 96; 118: 96; 124: 45992; 125: Planning approval; 130: 44804; 131: 44918; 132: 46059; 133: 44701; 134: 44705; 145: 39; 147: 7; 148: 32; 152: 57; 153: 9; 154: 24; 155: 24; 188: At Risk; 190: On target; 193: On target; 199: On target; 202: On target; 205: On target; 208: On target; 211: On target; 213: 95 Homes taken off Barton Ph 2 & 4 OMS and moved to this new line. 1B x 31; 2B x 36; 3B x 21; & 4B x 7. Total: 95. Tenure Switch with sale to Places For People RP. Dec 21 - Purchase contract exchanged between PfP and Countryside subject to planning. Reserved matters application (from Countryside is submitted) - see details re main ph 2&4 entry. PfP are assessing what top-up grant might be required to make the 9 AR three and four bed homes into SR. Grant funding is from HE under the SP route. Jan 22 - funding reqt provided re AR to SR tenure switch - to assess V4M against s.106 funds. AH on 14.04.22 - Places for People confirmed additional purchase of 3 SO units. Jun 22 - Meeting with Head of Planning re option to use s106 grant to change tenure of 9 larger houses (3 & 4 bed) from AR to SR due on 15/06/22. Re-arranged (15 Aug 22) - Agreed subject to lead member approval. Now 96 homes - expect to exchange contracts with Countryside shortly. (5 Aug 22 - Accom'n Schedule provided) Aug 22 - Alex H approved s.106 spend. Nov 22 - Delegated decision agreed. Dec & Jan 23 - Chased for key prog dates and to progress grant agt March 2023 - confirmation of SOS and legal completion has been achieved. May - chased again for new programme and template funding agreement 07/09/23 - Meeting with Nigel. Further work on confirming SR units. Some indication of handovers dates with some delivery possible in 23/24 and some running beyond current dates to 26/27 although unclear on number of units in each phase. Requested detailed breakdown of accommodation schedule/tenure/housing type 15/07/24 - Meeting with Nigel and updated programme provided - handovers taking place between November 2024 and February 2026. Info re 10 additional shared ownership units being bought by Sage. Funding agreement being reviewed by P4P. Quarterly update review meeting scheduled. Aiming for site visit in September on affordable housing block. Awaiting detailed breakdown with addresses/M43 information from Nigel.; 217: 51.7699; 218: -1.212; 270: TRUE; 306: 650000 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Barton Park (Phase 3b) | 22 units all for affordable with Greencore |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | James Graham |  | James Graham |  | Site Identification only | [7 empty] | 33: - Greencore no longer progressing site - options to progress being considered - PROW to be address under planning - contract is subject to planning so PROW being dealt with under this clause - Finance risk due to design not yet finalised - Time delay around planning risk and stopping requirement - advice being sought; 100: No; 101: Direct Delivery OCHL/HRA; 102: TRUE; 105: City Council; 107: 22; 108: 9; 110: 13; 117: 22; 118: 22; 123: 45016; 124: 45565; 125: Pre-Application; 127: 45201; 128: 45474; 129: 45352; 130: 45352; 131: 45688; 187: Scheme paused pending a decision on how/when it can be brought forward again. Awaiting a decision from LLP based on planning advice.; 188: At Risk; 190: At Risk; 193: On target; 199: At Risk; 202: On target; 205: On target; 208: On target; 211: At Risk; 213: Site being looked at by OCHL but no firm scheme at present. Barton phase 3 is being re-marketed by the LLP (no time scale given) and OCHL will have the opportunity to bid. The site is not suitable for an inexperienced Community Led housing group. Exchange due soon. 1st pre-app due January 2022. OCHL in early discussions with Greencore about the scheme. Greencore have submitted a pre-app for the scheme and are awaiting discussions with Planning. 12/05/22 - Update on tenure switch - 2 additional shared ownership units with 11 market sale houses shifted to shared ownership additionality (OCHL retaining ownership). 17/6/22 - work ongoing with Greencore in pre app to evolve scheme along with negs with Greencore on structure of deal between OCHL and Greencore. ODRP 8/12, added some questions and challenges which I will adddress w/c 12/12. The scheme is being revised by Greencore and their architects prior to any planning application submission. Contract are being agreed and will be exchanged with a subject to planning clause 18/01/23 No further update 17/02/23 - No Further Update May 2023 - May 2023 - LLP are reviewing the Planning arrangements with OCC planners - from LLPs perspective this is holding up land sale. Greencore are holding off until land issue resolved. 26/06/23 - Might need to slip SOS. No updates on LLP position which is source of hold-up. Some pre-app work done but lots to go. Really needs planning to be in this year/early next year. Should be possible but might need reprofiling - monitor until next month. 03/08/23 - forecast dates pushed back approx one quarter in line with OX P dates. The LLP are reviewing the Planning arrangements with OCC Planners. Greencore have pulled out. Discussions required for OCHL to step in ac developer. 03/10/23 - Not currently progressing - needs narrative for HSB. 11/01/24 - Scheme paused pending a decision on how/when it can be brought forward again. Last update - awaiting a decision from LLP based on planning advice.; 217: 51.7716; 218: -1.2196; 232: 5; 233: 5 | [11 empty] | 1 | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Lucy Faithfull House | Mixed scheme of 36 x 1, 2 and 3-bed flats |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Lila Haracz |  | Lila Haracz |  | Completed | [7 empty] | 31: - Handover expected imminently; 33: - Time delay due to utility meter delivery and commissioning services - being closely monitored; 99: Year 4; 100: Yes; 101: Direct Delivery OCHL/HRA; 102: TRUE; 103: TBC; 105: City Council; 107: 36; 108: 15; 109: 3; 110: 8; 113: 10; 116: No; 117: 26; 118: 36; 120: 43790; 121: 43908; 122: 44377; 123: 44388; 124: 45078; 125: Planning approval; 126: 19/03106/FUL; 133: 43803; 134: 43999; 135: 44424; 136: 44424; 137: 45251; 138: 26; 139: 15; 140: 3; 141: 8; 188: Completed; 190: Completed; 193: Completed; 199: Completed; 202: Completed; 205: Completed; 208: Completed; 211: Completed; 213: Progress on site last month - In Block A, external brickwork and scaffold are continuing up to the first and second floors. Dry lining and M&E have commenced. Windows to the first floor are being installed also. In Block B, the Structural Frame System (SFS) and external boarding have been completed. Window installation has been completed to the first floor and the second floor window installation has begun. Dry lining metal work to the first floor has been installed, with boarding due to start shortly. M&E containment works started in the period. Brickwork has continued around block B, with the second lift and door and window openings being formed. nstalled, with boarding due to start shortly. M&E containment works started in the period. Brickwork has continued around block B, with the second lift and door and window openings being formed. 18/01/23 - The period has seen a lot of progress; however, inclement weather conditions has impacted progress on site. Brickwork, plastering, screed and decorations have all been impacted by the extreme cold which is having a detrimental effect to the critical path of the programme. 17/02/23 - The freezing temperatures also impacted internal trades such as plastering, screed, tape and jointing and mist coat. This will result in a delay to the contract completion date, with the programme indicating a likely May finish. 01/06/23 - some slippage to programme due to utility delays indicating a likely August finish. Piece of work on lease went to board in early May. Now agreed that DevCo are retaining a long lease 26/06/23 Developers believe 18 Aug PC date is achievable although there remains a lot to do. 3/07/23 - PC date moved back to end of August 01/08/23 - Works are progressing well, but further slippage to programme due to Thames Water connection delay, indicating a likely Oct/Nov finish. 30/10/23 - Water connected on 24 October, awaiting handover any time 21/10/23 - Confirmation of completion of units. Awaiting PC certificate and confirmed accommodation schedule.; 217: 51.7485; 218: -1.2615; 220: 10; 222: 5; 250: 8; 270: TRUE | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45558.2266 | mmcfarlane@oxford.gov.uk
East Oxford Community Sites 1 (Princes St and Collins St) | 12 social rent at Princes Street and 14 shared ownership at Collins Street |  | Housing Supply Board |  |  |  |  | Housing |  | Tom Bridgman |  |  | Lila Haracz |  | Lila Haracz |  | Delivery | [7 empty] | 30: Discharge of pre-commencement planning conditions on both sites Achievement Start on site (both sites) to comply with Homes England milestones; 31: Review of contractor obligations and balance of risk profile Awaiting confirmation re site compound.; 33: Challenging site - ongoing liaison with contractor Potential for community opposition once construction begins (opposition to the project was identified) use considerate contractor scheme and positive communications Market risks - being monitored due to risk of housing market contracting/impact on shared ownership Time delay - Princes St works on site delayed due to access issues, so will incur additional costs and time - ODS revised programme/logistics to be co-ordinated; revised CTMP submitted Provisional sums on matters such as ground conditions etc. may lead to increased build costs Technical risk - Difficult tight sites, co-ordination required with CC Princes Street contractor. Ongoing discussions relating to access and crane impact. Level difference of Solution yet to be agreed re level difference between CC and residential schemes. Planning risk - No issues identified re conditions (except condition 4 at Collins Street may need review at a later date). Finance risk - Delays to SOS at Princes and potential impact of level issue will incur increased build costs and programme delay.; 77: Arcadis; 78: Lifebuild; 95: 44083; 96: Cabinet Decision; 100: No; 101: Direct Delivery HRA; 102: TRUE; 103: n/a - 2 small sites. Many dependencies re community reprovision that risk delay; 105: City Council; 106: Application Approved; 107: 26; 108: 12; 110: 14; 116: No; 117: 26; 118: 26; 120: 43917; 121: 44013; 122: 44879; 123: 44196; 124: 44804; 125: Planning approval; 126: 20/00994/CT3 (Collins Street) 22/01128/VAR (Princes Street); 129: 45245; 132: 45925; 133: 43917; 134: 44573; 135: 45251; 136: 45373; 188: At Risk; 190: At Risk; 193: Off Target; 196: At Risk; 199: At Risk; 202: At Risk; 205: At Risk; 208: On target; 211: Off Target; 213: Tender responses have been received and are being evaluated. Aiming for contact award on 14th Nov 22. 18/01/23 - Contractor Selected 09/05/23 - Contractor selected, contract to be finalised. ODS revised demolition programme on track. May 2023 - Legal turnover so all JCT amendments remain ongoing. 22/06/23 - Arcadis and ODS working to commence/finish demolition asap. There is potential for delays to impact HE 1 October SOS milestone. 26/06/23 - HE SOS of 1 October. Nearly there with housing contract. Still a question mark over demolition timescales. 7/7/23 - change to forecast build contract now 28/07/23. Planning risk change to Amber - no issues identified re conditions (except condition 4 at Collins Street may need review at a later date). CIL exemption advanced (awaiting forecast commencement date to issue final proforma) and s73 initial preapplication advice provided. Application to register Collins Street as a community asset is being explored. 02/08/23 - ODS demolition completed at Princes Street - Collins Street to follow on 14th August subject to court proceedings outcome. 21/08/23 - some concerns around QBT as contractor 07/09/23 - ODS demolition completed at Princes Street - Collins Street underway. Contractor not yet in contract. 14/09/23 - change of milestone dates as per revised programme - these differ slightly from new IMS dates to allow a buffer. Change in contractor with contract forecast date at end of Sept. Conversation with Valerie at HE and change of dates on IMS. 03/10/23 - Switch of contractor, not yet in contract although contract negotiations underway. Site appropriated into HRA. Indemnity insurances put in place for historical restrictive covenant. 30/10/23 - 1st November target for build contract 3/11/23 - build contract for signing 15 Nov. ODS demolition completed at Princes Street - Collins Street delay given asbestos found in the ground (awaiting removal). 21/11/23 - Build contracts signed and sealed 27/11/23 resolution to compound/site issue 11/01/24 - Demolition on both sites complete. Pre-construction activities underway. Latest contractor report available and all going well. Expected to meet March 22 SOS. 29/02/24 - onsite in three weeks - confirmation re location of site compound and discharge of pre-commencement conditions. 05/05/24 - Start on site made for HE grant claim at both Princes Street - & Collins Street. Issue relating to logistics plan/site access at Princes Street needs to be resolved with ODS/highways otherwise there will be programme delays and additional prelim costs. Collins Street groundworks to commence 8th April onwards, compound location to be resolved. 29/05/24 - significant issues re rejection of construction management plan and delay to Princes Street SOS - change to RAG status/time delay now Red; 214: 43958; 217: 51.7481; 218: -1.2398; 220: 6; 221: 2; 222: 4; 250: 8; 252: 6 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land East of Oxford Road, North Oxford |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 690; 109: 259; 111: 86; 117: 345; 118: 0; 125: Planning application submitted; 126: 23/01233/OUT; 128: 45163; 132: 2030-08-08; 133: 2023-05-05; 188: Off Target; 213: 50% affordable housing allocations of 690 homes in total.; 260: Yes; 261: Cherwell DC; 262: 345; 264: PR6a; 265: Savills; 266: Water Eaton; 267: Yes; 268: 50; 269: 2021/22 - 2030/31 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land West of Oxford Road, North Oxford |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Pipeline (Approved awaiting budget) | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 670; 109: 251; 111: 84; 117: 335; 118: 0; 125: Pre-Application; 132: 2030-08-22; 188: Off Target; 213: 50% affordable housing allocation. 670 units in total. Delivery timescale from 21/22 to 30/31. No planning submitted yet.; 260: Yes; 261: Cherwell DC; 262: 335; 264: PR6b; 265: Turnberry; 267: Yes; 268: 50; 269: 2021/22 - 2030/31 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land South East of Kidlington - East Bicester Road |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Design & Specification | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 430; 109: 161; 111: 54; 117: 215; 118: 0; 125: Planning application submitted; 126: 22/00747/OUT; 128: 44784; 132: 2030-08-22; 133: 44631; 188: On target; 213: 50% affordable housing allocation. Total homes 430. A secondary planning app also submitted but no info on this one. Delivery timescale from 26/26 to 30/31; 260: Yes; 261: Cherwell DC; 262: 215; 264: PR7a; 267: Yes; 268: 50; 269: 2026/27 - 2030/31 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land at Startfield Farm - an extension to the South of Kidlington |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 100: No; 101: Not Yet Known; 107: 120; 109: 45; 111: 15; 117: 60; 118: 0; 125: Planning application submitted; 126: 22/01611/OUT; 128: 45033; 133: 2022-05-30; 188: At Risk; 213: 50% affordable allocation on 120 home site. Delivery timescale between 23/24 and 26/27.; 260: Yes; 261: Cherwell DC; 262: 60; 264: PR7b; 265: Manor Oak Homes; 267: Yes; 268: 50; 269: 2023/24 - 2026/27 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land East of the A44 - new urban neighbourhood near Begbroke |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Feasibility | [7 empty] | 100: No; 101: Not Yet Known; 105: Other; 107: 1950; 109: 731; 111: 244; 117: 975; 118: 0; 125: Pre-Application; 132: 47717; 188: Off Target; 213: 50% affordable allocation on site for 1,950. Delivery timescale from 21/22 - 30/31; 260: Yes; 261: Cherwell DC; 262: 975; 264: PR8; 265: Oxford University Development; 266: Begbroke Innovation District; 267: Yes; 268: 50; 269: 2021/22 - 2030/31 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45558.2266 | mmcfarlane@oxford.gov.uk
Land West of Yarnton - village extension |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Design & Specification | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 540; 109: 202; 111: 68; 117: 270; 118: 0; 125: Planning application submitted; 126: 21/03522/OUT; 128: 45016; 132: 47359; 133: 44483; 188: Off Target; 213: 50% affordable allocation on site with 540. Delivery timescale from 21/22 t0 29/30; 260: Yes; 261: Cherwell DC; 262: 270; 264: PR9; 265: Touchstone P&D; 267: Yes; 268: 50; 269: 2021/22 - 2029/30 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Balance from Voids SODC (Re-lets) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 107: 115; 108: 40; 109: 29; 110: 17; 111: 29; 117: 115; 118: 0; 260: Yes; 261: South Oxfordshire DC; 262: 115; 267: Yes; 268: 100 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land at Northfields |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Pipeline (Approved awaiting budget) | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 1800; 108: 252; 109: 180; 110: 108; 111: 180; 117: 720; 118: 0; 125: Planning application submitted; 188: On target; 213: 40% allocation on 1,800 unit scheme. Delivery timescale is 26/27.; 260: Yes; 261: South Oxfordshire DC; 262: 720; 264: Strat 12; 265: L&Q Estates; 267: Yes; 268: 40; 269: 2025/26 - 2027/28 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Land North of Bayswater Brook |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Design & Specification | [7 empty] | 100: No; 101: Not Yet Known; 105: Private; 107: 1100; 108: 154; 109: 110; 110: 66; 111: 110; 117: 440; 118: 0; 125: Planning application submitted; 126: P22/S4618/O; 128: 45048; 133: 44917; 188: At Risk; 213: 40% affordable allocation on 1,100 site. Delivery timescale is 26/27. No decision yet on outline planning; 260: Yes; 261: South Oxfordshire DC; 262: 440; 264: Strat 13; 265: Dorchester Residential Management (DRM); 266: Bayswater; 267: Yes; 268: 40; 269: 2023/24 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Balance from Voids VoWH (Re-lets) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 107: 385; 109: 216; 110: 73; 111: 96; 117: 385; 118: 0; 260: Yes; 261: Vale of White Horse DC; 262: 385; 267: Yes; 268: 100 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
North Abingdon-on-Thames |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 107: 950; 109: 132; 110: 45; 111: 60; 117: 237; 118: 0; 125: Planning approval; 126: P17/V0050/O; P19/V1998/RM ; P19/V2588/RM; 133: 43689; 134: 44281; 188: At Risk; 213: 25% affordable allocation on site of 238. Delivery timescale noted as 2022 onwards. Outline planning achieved in 2017 with RM in 2021.; 260: Yes; 261: Vale of White Horse DC; 262: 237; 264: LPP1; 265: David Wilson & Barratt Homes; 267: Yes; 268: 25; 269: 2022 onwards | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
North-west Abingdon-on-Thames |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 104: Sovereign; 107: 200; 109: 28; 110: 9; 111: 13; 117: 50; 118: 0; 125: Planning approval; 126: P17/V1336/O; P20/V3227/DIS; 133: 44185; 134: 44264; 188: At Risk; 213: 25% affordable allocation on 200 unit site. Outline planning achieved in 2018. Planning decision partially discharged in 21. Delivery timescale noted as 2022 onwards; 260: Yes; 261: Vale of White Horse DC; 262: 50; 264: LPP1; 265: David Wilson & Barratt Homes; 267: Yes; 268: 25; 269: 2022 onwards | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45558.2266 | mmcfarlane@oxford.gov.uk
North-west Radley |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 104: Sovereign; 107: 240; 109: 34; 110: 11; 111: 15; 117: 60; 118: 0; 125: Planning application submitted; 126: P17/V1894/O; P20/V2990/DIS; 128: 44194; 133: 44152; 188: At Risk; 213: 25% affordable housing allocation on 240 unit scheme. Delivery timescale from 2022. Second application no decision yet. Outline planning in 2018.; 260: Yes; 261: Vale of White Horse DC; 262: 60; 264: LPP1; 265: Pye Homes; 267: Yes; 268: 25; 269: 2022 onwards | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
South of Kennington |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 107: 270; 109: 38; 110: 13; 111: 17; 117: 68; 118: 0; 125: Planning approval; 126: P17/V2961/FUL; 133: 43034; 134: 43553; 188: On target; 213: 25% affordable housing allocation on 270 unit scheme. Planning achieved. Delivery timescale 24/25 - 25/26; 260: Yes; 261: Vale of White Horse DC; 262: 68; 264: LPP1; 265: Redrow; 267: Yes; 268: 25; 269: 2024/25 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Dalton Barracks |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | Kira Ariskina |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 105: Other; 107: 1200; 109: 168; 110: 57; 111: 75; 117: 300; 118: 0; 125: Pre-Application; 188: On target; 213: 25% affordable housing allocation on 1,200 unit scheme. Delivery timescale 2025 and onwards. Ministry of Defence site. No planning submitted as yet.; 260: Yes; 261: Vale of White Horse DC; 262: 300; 264: LPP2; 266: Dalton Barracks Garden Village; 267: Yes; 268: 25; 269: 2025 onwards | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Balance from Voids WODC (Re-lets) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Delivery | [7 empty] | 100: No; 101: Not Yet Known; 107: 450; 108: 157; 109: 157; 110: 23; 111: 113; 117: 450; 118: 0; 260: Yes; 261: West Oxfordshire DC; 262: 450; 267: Yes; 268: 100 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Salt Cross Garden Village | Large WODC garden village development |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Design & Specification | [7 empty] | 100: No; 101: Not Yet Known; 107: 2200; 108: 227; 109: 227; 110: 33; 111: 163; 117: 650; 118: 0; 125: Planning application submitted; 126: 20/01734/OUT; 128: 44504; 133: 44015; 188: On target; 213: Outline planning still under consideration. Delivery timescales 24/25 - 33/34. 29.55% affordable allocation on 2,200 unit scheme.; 260: Yes; 261: West Oxfordshire DC; 262: 650; 264: EW1; 265: Grosvenor Developments Ltd; 266: Salt Cross; 267: Yes; 268: 29.55; 269: 2024/25 - 2033/34 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
West Eynsham |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Anneri Gatial |  | agatial@oxford.gov.uk |  | Design & Specification | [7 empty] | 100: No; 101: Not Yet Known; 107: 1000; 108: 96; 109: 96; 110: 14; 111: 69; 117: 275; 118: 0; 125: Planning approval; 126: 20/03379/OUT; 128: 44769; 133: 44182; 188: At Risk; 213: 27.5% affordable allocation on 1,000 unit scheme. Delivery timescale 20/21 - 28/29. Planning outstanding.; 260: Yes; 261: West Oxfordshire DC; 262: 275; 264: EW2; 265: Jensons Property; Berkley Strategic; Thomas Homes; Oxfordshire CC; Vanderbilt Homes; 267: Yes; 268: 27.5; 269: 2020/21 - 2028/29 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Powells Timber Yard |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 117: 0; 118: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Oxford Road (Cowley Road) |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 117: 0; 118: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Rectory Road Health Trust Facility |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 117: 0; 118: 0 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandford Site A |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 102: TRUE; 108: 30; 110: 62; 117: 92 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Sandford Site B |  |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Dave Scholes |  | Dave Scholes |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 102: TRUE; 108: 54; 110: 18; 117: 72 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
Garden House | Site with potential for 12 x 1-bed units |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Site Identification only | [7 empty] | 100: No; 101: Not Yet Known; 107: 12; 115: 12; 116: Yes; 117: 0; 187: Currently no site; 213: 03/06/24 - looking for a suitable site (TA); 219: 12 | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N | 45545.5281 | rhaverson@oxford.gov.uk
OxPens | Mixed-use residential scheme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Design & Specification | [7 empty] | 101: Developer Led; 106: N/A; 117: 0; 125: Planning application submitted; 132: 47574; 187: Active scheme in Design and Specification stage; 213: 26/03/24 - outline planning expected by June 2024 29/04/24 - outline planning still expected June 24. 11/06/24 - Richard Grey Court is within this site 01/08/24 - draft 106 is with county. Permission not yet granted. | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N
Hill View Farm - additionality | 35 additional units to the Hill View Farm scheme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 31: Not moving forward at present - actively trying to engage landowner; 100: No; 101: Developer Led; 105: Private; 106: N/A; 107: 35; 108: 15; 110: 20; 117: 35; 131: 45626; 132: 46204; 159: 35; 160: 15; 162: 20; 188: At Risk; 190: At Risk; 193: At Risk; 199: On target; 202: At Risk; 205: At Risk; 208: At Risk; 211: Off Target; 213: 31/10/23 Additionality as per Sovereign proposals. 28/11/23 - potentially at risk dependent on how scheme progresses 13/03/24 - currently this scheme is not progressing - no developer involvement 03/06/24 - AD working with RP to try and secure 35 additional units 15/10/24 - SNG have confirmed they are going to target board approval on the 4th November to then exchange contracts on the 7th November with Bellway. They are agreeing HoT’s to confirm this at present.; 217: 51.7825; 218: -1.2497; 273: TRUE | [12 empty] | 45580.1881 | mmcfarlane@oxford.gov.uk | Y
LAHF 3 acquisitions programme | 14 affordable homes delivered through Local Authority Housing Fund programme |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 100: No; 101: Direct Delivery HRA; 106: N/A; 107: 5; 108: 5; 117: 5; 125: Not Applicable; 132: 45747; 145: 5; 146: 5; 188: At Risk; 213: 28/03/24 - submission of LAFH 3 eoi, awaiting grant approval, will need Cabinet consent 01/08/24 - confirmed 5 properties to be delivered in programme and needs to go to cabinet/council | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N
Paradise Street (Gibbs Crescent s106 units) | 15 private units at Paradise Street to become social rent in the event that Gibbs Crescent does not come forward |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 100: No; 101: Enabling RP Led; 105: Private; 106: N/A; 107: 15; 108: 15; 117: 15; 125: Planning approval; 132: 46112; 152: 15; 153: 15; 213: 04/10/24 - now included in programme as mitigation for Gibbs Crescent units which have currently dropped out of the 4-year programme | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N
Street Property Acquisitions 29/30 | 12 affordable homes delivered through leaseholder buy-back and market purchase | N7080 | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 100: No; 101: Direct Delivery HRA; 105: Private; 106: N/A; 107: 12; 108: 12; 117: 12; 125: Not Applicable; 132: 47573; 187: Annual RRTB acquisition programme | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N
Additional acquisitions/RRTB (24 units) | 24 additional units financed using RRTB - currently seeking suitable sites |  | Housing Supply Board | Housing Supply Board | [8 empty] | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 100: No; 101: Direct Delivery HRA; 106: N/A; 107: 24; 108: 12; 109: 12; 117: 24; 125: Planning required in due course; 132: 47208; 173: 24; 174: 12; 175: 12; 187: 24 units being delivered through RRTB funding - tenure/timescale TBC; 213: 03/10/24 - scheme added into out of scope programme | [12 empty] | 45575.3175 | rhaverson@oxford.gov.uk | N
Barton Park (Vistry/Sage) tenure switch | 10 units to be switched from private to shared ownership on Barton Park Ph 2 and 4 |  | Housing Supply Board | Housing Supply Board |  |  |  | Housing |  |  |  |  | Andy Dorrington |  | Andy Dorrington |  | Feasibility | [7 empty] | 105: Private; 106: N/A; 107: 10; 110: 10; 117: 10; 125: Planning approval; 132: 47208; 173: 10; 176: 10; 187: Switch of private units (Vistry) to shared ownership (Sage) TBC | [12 empty] | 45579.1421 | mmcfarlane@oxford.gov.uk | Y

## Comparison Last Month (hidden)
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 1900-02-20 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Cost Centre | Capital Scheme Name | HOS | Service Area | Cost Centre | Capital Scheme Name | Description | Classification | Progress Update Provider | Project Status (select one option) | Owning Group | Directorate | Director | Internal Project Manager and/or Client Manager | External Project Manager | Project Sponsor | Contact | Project Update (current month) | Budget RAG Status | Schedule RAG Status | Risks RAG Status | Issues RAG Status | Key Risks and Mitigations | Key Issues to Address (100 words) | Gateway Stage | Next Key Milestone and when it will be achieved | Current Completion Date | Revised Completion Date (enter where applicable) | Original Budget 2021/22 | Budget 2022/23 | Budget 2023/24 | Budget 2024/25 | Total Budget 21/22 to 24/25 | Latest Budget 2021/22 | Actual 2021/22 Spend to Date | Project Manager Forecast 2021/22 Spend | Forecast Variance 2021/22 | 2021/22 Variance Reason (where applicable) | Reason for under/overspend or slippage to budget | Forecast total spend in year Apr 22/Mar 23 | Forecast total spend in year Apr 23/ Mar 24 | Forecast total spend in year Apr 24 onwards | Forecast Variance 22/23 | Forecast Variance 23/24 | Forecast Variance 24/25 | Future Years Variance Total (22/23 to 24/25) | Action requested from Project Board | Advise Carbon Reduction Measures (100 words) | ODS Opportunity (Yes, No, Unsure) | ODS Description | CDM - Principal Designer | CDM - Principal Contractor | Has the PM provided an update? | Request update | Modified By | Modified | Blank 1 | Cost Centre | Capital Scheme Name | Description | Classification | Progress Update Provider | Project Status (select one option) | Owning Group | Directorate | Director | Internal Project Manager and/or Client Manager | External Project Manager | Project Sponsor | Contact | Project Update (current month) | Budget RAG Status | Schedule RAG Status | Risks RAG Status | Issues RAG Status | Key Risks and Mitigations | Key Issues to Address (100 words) | Gateway Stage | Next Key Milestone and when it will be achieved | Current Completion Date | Revised Completion Date (enter where applicable) | Original Budget 2021/22 | Budget 2022/23 | Budget 2023/24 | Budget 2024/25 | Total Budget 21/22 to 24/25 | Latest Budget 2021/22 | Actual 2021/22 Spend to Date | Project Manager Forecast 2021/22 Spend | Forecast Variance 2021/22 | 2021/22 Variance Reason (where applicable) | Reason for under/overspend or slippage to budget | Forecast total spend in year Apr 22/Mar 23 | Forecast total spend in year Apr 23/ Mar 24 | Forecast total spend in year Apr 24 onwards | Forecast Variance 22/23 | Forecast Variance 23/24 | Forecast Variance 24/25 | Future Years Variance Total (22/23 to 24/25) | Action requested from Project Board | Advise Carbon Reduction Measures (100 words) | ODS Opportunity (Yes, No, Unsure) | ODS Description | CDM - Principal Designer | CDM - Principal Contractor | Has the PM provided an update? | Request update | Modified By | Modified | Blank 2 | Comment Updated | Blank 3 | Budget RAG Status | Schedule RAG Status | Risks RAG Status | Issues RAG Status | Key Risks and Mitigations | Key Issues to Address (100 words) | Gateway Stage | Next Key Milestone and when it will be achieved | Revised Completion Date (enter where applicable) | Blank 4 | Project Manager Forecast Updated
F7024 | St Clements Environmental Improvements | AA | Planning | F7024 | St Clements Environmental Improvements | S106 funded schemes | Project - Other | Lorraine Freeman | Paused | Development Board | Development | Tom Bridgman | - | 0 | - | lfreeman@oxford.gov.uk | There is currently £31197 not £50k left of this contribution as some was spent in 19/20. Discussions are currently taking place in respect on a project to include a new pathway and entrance gates to South Park - discussions are still taking place but it is hoped that the project will commence this financial year but may need to slip if project not agreed - discussions still on-going with leisure/county re location. The project may now change slightly but I am awaiting outcome of further discussions - there is a current scheme to upgrade the entrance to the park at the bottom of Morrell Ave. ODS will need to carry out consultation before project to commence. Still under discussion as OPT have not approved the current scheme - futher discussions taking place | On Budget | Awaiting new programme | Low | Low | No risks as S106 funded so can be carried over. | 0 | 1. Idea | 0 | 0 | 0 | 20000 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | -50000 | 0 | 0 | Yes | 0 | 0 | ODS | 0 | 0 | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5033 | Blackbird Leys Regeneration (GF element) | CP | Regeneration & Economy | M5033 | Blackbird Leys Regeneration (GF element) | Regeneration of Blackbird Leys including the Retail Centre, Community Centre and Knights Road to provide approximately 294 new homes, retail units and community centre. The regeneration is in partnership with Catalyst Housing. | Project - Development | Andrew Humpherson | Running | Development Board | Development | Tom Bridgman | Andrew Humpherson | N/A | 0 | Roo Humpherson | Changes to 100% affordable housing agreed and viability confirmed by CHL to address planning risk and viability issues around First Homes. Draft planning proposals received and discussed at Pre-App. Proposed Knights Road masterplan to be revised to avoid the Nature Reserve. Viability reviewed by OCC consultant - no significant concerns. Comments raised with CHL. Gateway Two delayed to February/ March to accommodate changes to layouts. Leaders briefing required on receipt of final proposals from CHL - proposed for end Jan. Development Agreement with CHL now signed by CHL and wet copy issued to OCC solicitors to enable exchange. | On Budget with slippage | Over Schedule | Medium | Medium | CHL grant transferred to RCGF - to be confirmed by HE. HIF grant extension to be confirmed - report submitted awaiting comment and review by HE. Revised proposals to be reviewed with Members. Knights Road development to be re-planned at avoid building on a small section of the nature reserve. Planning review required. Workshop confirmed for 20th Jan. Bio-diversity proposals currently not compliant with planning policy. Further calculations require following changes to Knights Road layout. Negotiations with County Highways required to allow for increased tree provision. Costs of s106 and s278 agreements at risk of increased external demands. Viability budget increased by c.£100K in response. Community objections to reduction in size of community centre to be addressed by new consultant team. Consultant Team appointments agreed subject to legal contracts - needs to be completed urgently. Further Councillors' briefing required prior to planning. State Aid funding subject to Legal Review. VP strategy and programme to be reviewed. Freeths appointed to support OCC Legal. Loss of CIL to Parish through conversion to 100% affordable housing to be addressed. Funding to be made available to support community proposals with Parish to be engaged in distributing funds (mechanism to be agreed). Comm's to be reviewed prior to planning submission. Purdah implications for planning submission date require urgent review | Revised planning proposals required. Planning statement required and OCC review. Development Agreement to be signed, sealed by both CHL and OCC. Legal review on-going for VP including land appropriation, CPO, State Aid. Negotiation with HE for HIF funding programme to be prolonged to March 2024 in hand and including Catalyst. Comm's to be reviewed prior to planning submission. | 3. Design & Technical Specification | Development Agreement to be signed/ sealed. Commencement of Community Centre design work and engagement urgent - January 2021. Request for extension to HIF funding with HE for review and approval. Gateway Two delayed further to February/ March 2022 to accommodate scheme revisions. Planning application delayed to February/ March 2022 | 46664 | 46861 | 452790 | 13795292 | 1235172 | 1835841 | 17202313 | 336008 | 27051 | 294880 | -41128 | Slippage (Underspend in 21/22 - slip budget back) | Catalyst prolongation of design and cost-planning and review of affordable housing proposals. | 7232696 | 7489817 | 1314119 | -6562596 | 6254645 | -521722 | -829673 | Legal support including review of VP process. Other Legal advice required for viability, CPO assistance | Housing and Community Facilities to meet emerging Local Plan standards with further opportunities to improve standards to be investigated during Detailed Design. Catalyst has prepared proposals for alternative additional carbon reduction measures currently being costed fro review as part of teh Stage Two Gateway | Some | Community Centre and retail fit out and possible sub-contractor work packages | Catalyst Housing Limited | tba | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0092 | Cave Street | CP | Regeneration & Economy | B0092 | Cave Street | 26 Cave Street and the adjacent site at Standingford House is to be redeveloped as a mixed use development including affordable workspace as part of an inclusive economy. | Project - Development | Andrew Humpherson | Running | Development Board | Development | Tom Bridgman | Andrew Humpherson | 0 | Tom Bridgman | Roo Humpherson | Review of planning proposals following written pre-app report. Tenant engagement on-going with comm's team support. date for VP under review and subject to further planning consultation. Project programme under review. Alternative accommodation options being considered but noted lack of viable alternatives to date. Planning proposals being developed and second pre-app consultation undertaken. | On Budget | Over Schedule | Medium | Medium | Planning concerns at scale of development requires further consultation with planning. Planning meeting proposed 18th Jan. Planning programme to be extended. OxLEP to be updated on programme and grant spend programme. Lack of suitable alternative accommodation for tenants still of concern. Risk of adverse publicity from tenant location requires more aggressive search for alternate facilities and particularly in respect of community tenants | Design revisions required to respond to planning pre-app feedback - impact on nett-lettable area under review with operator. BREEAM detailed design development affects operator office layouts. Under review with operator. Tenant relocation options required. Support from property/communities ongoing. Decision required on when to serve notice on tenants and under review with members. Title report ordered. State Aid review requested by OxLEP | 2. Feasibility | Planning consultation end January to assess potential impact on proposals.. Notice to be served on tenants | 45274 | 45524 | 1407500 | 3901465 | 1277500 | 0 | 5508450 | 329485 | 118590.25 | 152120 | -177365 | Slippage (Underspend in 21/22 - slip budget back) | Planning comments on second pre-app requires further design changes | 2366387 | 4075595 | 3110772 | -1535078 | 2798095 | 3110772 | 4373789 | HoS and Director review of SOBC (June). | BREEAM Excellent target confirmed and included in Options appraisal. Zero carbon options being costed as part of feasibility. | Yes | New build workspace and possible mixed use including housing development | AAP appointed - nothing to report. | tba | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0125 | City Centre Restart | CP | Regeneration & Economy | B0125 | City Centre Restart | Strategic CIL pot set aside for city restart in 2020-21 financial year, but ultimately not spent and rolled over to 2021-22 financial year | Project - Development | Ted Maxwell | Paused | 0 | Development | 0 | 0 | 0 | Tom Bridgman | Ted Maxwell | **Suggest re-allocated to Matt Peachey or Carolyn Ploszynski as I've not been close to this budget for a long time** Original allocation of CIL was that were allocated to this pot were subsequently paid by COMF. As part of the Welcome Back funding recommendations that was agreed by CMT and Leaders some of the CIL feasibility has been provisionally re-allocated. Current allocations are £20k to Murals and Boarding project, £15k street trading project and £15k night time economy infrastructure. The remainder has been kept as a buffer in case there is overspend or other costs that emerge given the changing timetable of city restart. | On Budget with slippage | Awaiting new programme | Low | Low | 0 | 0 | 0 | Proposals for the 3 workstreams being led by community safety to be confirmed - timetable dependent on Government roadmap. | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Forecast spending is being reviewed. CIL feasibility has been provisionally re-allocated. Current allocations are £20k to Murals and Boarding project, £15k street trading project and £15k night time economy infrastructure. The remainder has been kept as a buffer in case there is overspend or other costs that emerge given the changing timetable of city restart. | 0 | 0 | 0 | -100000 | 0 | 0 | -100000 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0122 | City Cycle Schemes (Growth Deal) | CP | Regeneration & Economy | B0122 | City Cycle Schemes (Growth Deal) | Four chosen cycle routes and crossing updates across the city to encourage walking and cycling | Project - Other | Douglas Kerrigan | Running | Development Board | Development | 0 | Douglas Kerrigan | 0 | Tom Bridgman | Doug Kerrigan | £140k for return of funds agreed. This accounts for ODS and PMO time alongside abortive consultant costs. A review of alternative schemes has taken place and schemes are to be reviewed on 17th January with a view to pushing funds to them. The project must complete by March 2023 | On Budget with slippage | Over Schedule | Medium | Medium | These have been reduced by considering other schemes | Review has lookeed at schemes mainly on City land to reduce the issues previously encountered | 3. Design and Technical Specification | January 17th 2022 Review of New Schemes Proposed | 44618 | 44986 | 450000 | 751662 | 0 | 0 | 901662 | 150000 | -94503.81 | 150000 | 0 | Forecast Underspend at end of project | This will be reduced due to cancellation of Marston Road and possibly Boults Lane | 750000 | 17000 | 0 | -1662 | 17000 | 0 | 15338 | none | 0 | Yes | D and B contractor | Stantec | ODSL | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0132 | Coach Parking Feasibility | CP | Regeneration & Economy | B0132 | Coach Parking Feasibility | Coach parking in the city centre has caused a number of issues and there has been a desire to move coaches out of St Giles. As a result work has been undertaken to review options and in particular to consider the option of coach parking at Oxpens car park | Project - Other | Ted Maxwell | Paused | Development Review Group | Development | 0 | 0 | 0 | 0 | Ted Maxwell | **No change this month - suggest budget is slipped to next financial year** No instruction to progress this work at present. Work to date has included working with Oxfordshire County Council on the opportunities to provide further drop off and layover spaces for coaches. A number of options were identified and these are summarised in the attached note together with the County comments in response. Oxpens car park was ruled out due to the temporary nature of the opportunity and the cost of bringing it forward. | On Budget | On Schedule | Low | Low | 0 | 0 | 2. Feasibility | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 0 | 20000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | No instruction to progress this work at present. | N:A | N:A | N:A | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 0 | 0 | 0 | 0 | N:A | N:A | 0 | 0 | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0137 | Court Place Farm Changing Rooms and Blackbird Leys Bowling Club Asset review | CP | Regeneration & Economy | B0137 | Court Place Farm Changing Rooms and Blackbird Leys Bowling Club Asset review | 0 | Project - Other | Emma Gubbins | Paused | 0 | Development | 0 | Emma Gubbins | 0 | 0 | Emma Gubbins | External lobbying by Hindu Community. Outline proposals for initial feasibility work and consultant appointments on hold. Alternative disposal or development routes to be considered. Updated report required to table option of direct disposal to community groups (with conditions). project transferred to Property | Budget to be agreed | Awaiting new programme | High | High | Adverse publicity from Hindu Community Group at lack of action. resourcing - project transferred to Property Team | Additional resourcing and budget will be required if the project s to move forward - to be set out in DRG report | 2. Feasibility | Report to propose alternative routes to deliver community facilities required to table direct disposal to community groups. date tba | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Project paused | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | Y | N |  | N | bar: 1 to 52
B0115 | Covered Market Masterplan | CP | Regeneration & Economy | B0115 | Covered Market Masterplan | Oxford City Council has procured a multi-disciplinary team to produce a Concept Masterplan (RIBA Stages 0 to 2) and heritage-led Asset Management & Maintenance Plan for Oxford’s Covered Market. The masterplan work will identify ways to support the successful long term future of the Covered Market and its surrounding streets. | Project - Development | Ted Maxwell | Running | Development Board | Development | Tom Bridgman | Ted Maxwell | 0 | Tom Bridgman | Ted Maxwell | 7th Jan project board included some agreements: > The project is aiming for revised programme – working back from autumn 2022 budget setting process and cabinet paper > Some options were removed from ongoing discussion entirely (new central communal area) > Technical review by officers and consultants during January and early February will support a recommendation about whether to pursue a "higher risk / full masterplan" or a "lower risk / high impact" scaled back option > Approval for GS’s change control #5 (to check our work revising scopes, costs, and Asset Management & Maintenance Plan, and the impact of new scopes on ongoing maintenance costs) at £2,656.25. This uses some of the project budget contingency, within the overall £155,000 budget approved by DRG and DB. After this spend, we will have £14,750 left in contingency | On Budget | On Schedule | Low | Low | __Short term risks and mitigations__: Programme slippage due to uncovering more complicated info at February project board and due to purdah in late-March / April. --> at Jan project board we agreed a revised programme in principle which already takes into account purdah Project could be paused / stopped soon due to uncertain viability --> ongoing work before and after January project board to show high risk / high reward and lower risk / lower reward options are inherently viable. __Ongoing risks and mitigations__: New risk identified: Latest info from EAV trial in CM is that there is not much uptake from traders (no uses in last three weeks). If the trial is not deemed to be some form of success by the traders, then the masterplan (with all options relying on a shift towards EAVs and away from vans) risks not being as compelling or plausible for traders as we would like. Transformation of servicing and market street could be off the table. --> Awaiting guidance from Elaine Philip regarding progress of EAV pilot, with potential for Pedal & Post to play a role. All officers understand importance of showing some progress on this theme. Project reliance on officers could mean insufficient buy-in is achieved from key stakeholders ---> Ongoing - Good communication between officers and TM so that there early warning regarding specific issues due to capacity and there is a chance to find alternative people or solutions Jesus College Northgate House development impact on Market Street public realm clashing with masterplan vision ---> Ongoing - info sharing with Planning and Northgate House dev team so the overall masterplan vision for Market Street is facilitated or not hindered by Northgate House's discharge of its planning conditions and vice versa. Project completes without being deliverable (another report on the shelf) ---> Ongoing - Incorporating biz process alongside masterplan project. Design ideas should not progress through initial and full options appraisal phases without having deliverability factored in clearly. Also seeking clarity re Gort Scott’s confidence in “RIBA Stage 2-” information There is no Principal Designer appointed for the project, which means the project doesn't conform to CDM 2015. This was not included in the original procurement brief of Gort Scott and was just raised by them as an issue. As a legal issue, it presents deliverability and public relations risks to the project too. ---> Factor in Principal Designer services as a requirement for any future phase of the project (after the masterplan) | Key actions raised at 7th Jan project board: > TM creating a new "pared down as possible" KM2 option and setting out qualitative and quantitative comparison of different options for all five 'key moves' > Officers, consultants and sub-consultants reviewing and updating summary technical work, including revised cash flow forecasts by Finance > TM create new simpler narrative-focused slide deck as basis for DRG / DB / Cabinet Member briefing in Feb and March | 3. Design & Technical Specification | Completing elongated "initial options appraisal" - targeting 1st March 2022 DB | 44544 | 44865 | 41560 | 31131 | 0 | 0 | 141131 | 110000 | 66072.75 | 110000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Most up to date 2021-22 spend is £105,000 due to slight re-profiling | 36000 | 0 | 0 | 4869 | 0 | 0 | 4869 | Steer re KS2 options, project scope, information gaps, quick wins | Environmental sustainability objectives part of project brief and will be part of decision-making process regarding preferred options at each stage. | Unsure | 0 | N/A Tom Bridgman guidance to exclude from this phase of project | n/a as project is a concept masterplan | 0 | TRUE | tmaxwell@oxford.gov.uk | 2022-01-12 18:01 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | N | N |  | N | bar: 1 to 52
B0128 | Cycle Greenways | CP | Regeneration & Economy | B0128 | Cycle Greenways | Concept masterplan regarding cycle and walking routes from nearby places to Oxford's centre and key employment / retail / education sites. A joint project with the County and University. | Project - Development | Pete Brunskill | Paused | 0 | Development | Tom Bridgman | Pete Brunskill | 0 | 0 | Pete Brunskill | Project remains on hold as partner organisations review options. County Council is pursuing a related strategy called Strategic Active Travel Network (SATN), but it remains to be seen how Oxford is adequately prioritised within the SATN and how Greenways funding can still play a useful role in going from lines on a map to implemented high quality schemes in Oxford. County and University funds sitting with City for Greenways technically have a long-stop date whereby they need to be spend before the end of the 21-22 financial year, so officers are working towards an exchange of letters regarding an extension and possible reallocation before then. | On Budget | Over Schedule | Medium | Medium | 0 | 0 | 2. Feasibility | Review as part of wider active travel programme review in Autumn 2021. | 0 | 0 | 0 | 0 | 0 | 0 | 106000 | 106000 | 0 | 0 | -106000 | Slippage (Underspend in 21/22 - slip budget back) | Currently targeting 31 March 2024 as the longstop for spending all the 106,000 so a current best guess would be for 25% of that in 22-23 and 75% in 23-24. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-17 13:32 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
A4853 | Cycling Infrastructure Matched Funding | CP | Regeneration & Economy | A4853 | Cycling Infrastructure Matched Funding | Originally Councillor Upton fund covering 4 years. | Other Capital Spend | Pete Brunskill | Paused | Development Board | Development | Tom Bridgman | Pete Brunskill | 0 | Cllr Louise Upton | Pete Brunskill |  Activity paused for 21/22  Scoping report with recommended route for using budget in 22/23 has been finalised.  City Centre site visits have taken place to understand what spaces may be available for additional cycle parking  Discussion with Craig Rossington about cycle parking highlighted issue of removing abandoned bikes  Councillor Hunt (City Cycling Champion) enquiring about the scope for bike hangers in Jericho/Summertown/Cowley  Briefing session with Councillor Gant (County Cycling Champion) for Councillor Hunt has also taken place  Cycling Infrastructure Fund work deprioritised given officer capacity and focus on other transport priorities | On Budget | Awaiting new programme | Low | Low | 0 | 0 | 9. Other Capital Spend | Intention to start devising some proposals for the fund during spring 2022 in collaboration with Craig Rossington at Oxfordshire County Council and deliver schemes during 2022-2023. | 0 | 0 | 60000 | 109956 | 60000 | 60000 | 242456 | 12500 | 13857 | 12500 | 0 | Slippage (Underspend in 21/22 - slip budget back) | For 2021-22, £12,500 has been transfered from this budget to Communities in order to co-fund the Shotover cycling infrastructure feasibility study. There is a decision notice in Ian Brooke's name, produced by Michael Woods. For the remainder of the £60,000 budget in 2021-22, there is a tentative plan for this cost centre, however it needs to be developed and presented to DRG as proposal(s). As per Greenways project, this budget awaits the new Principal Green Transport Planner starting in order to have officer resource to run with the project. | 60000 | 60000 | 60000 | -49956 | 0 | 0 | -49956 | 0 | N:A | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-17 09:16 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0114 | Diamond Place (redevelopment) | CP | Regeneration & Economy | B0114 | Diamond Place (redevelopment) | To create a concept Masterplan, supported by a business case to demonstrate that re-development is viable and deliverable and supported by the community. There will be two variants of the Masterplan: a comprehensive redevelopment and an option that enables us to proceed without the University as a partner | Project - Development | Jane Norman | Running | Development Board | Development | Tom Bridgman | Trudy Godfrey | 0 | Stephen Gabriel | Trudy Godfrey | Together with OUD we met the Neighbourhood Forum (NF) to relay the highlights from the Carter Jonas study. We have agreed to work with the NF and OUD on some Masterpan principes over the next year. Officers are finalising the report as it is likely to be sent to the NF. | On Budget | On Schedule | Medium | Medium | Oxford University have explained they are unable to progress designs for Ewart House until the Wellington Square scheme is sufficiently progressed. The Neighbourhood Forum are very concerned that the project will be delayed as there is an urgent need to co-locate GPs into a new medical centre. We agreed to meet NF reps to explain the issues and to work with them on Masterplan principles Community expectations around medical centre is high. The council are working with the CCG to try to deliver a new medical facility on site. However the CCG have to consider best value and are exploring a number of options including and at John Radcliffe. We need to understand CCG intent and have a series of meetings to firm up their requirements. Land ownership / unregistered land - need to progress our application with Land Registry. However Land Registry have indicated this is not a priority for them at the current time as they are dealing with a backlog. | Oxford University timeline and community expectations are misaligned. The NF, City Council and OUD need to work together to resolve this. We need to firm up the intent of the CCG and explain the immediacy expressed by the community. We need to work with OUD and the community to try and improve the emerging designs initially proposed by OUD which do impact on connectivity throughout the scheme. | 2. Feasibility | Meet the CCG to explore their options report and explain the community position. The NF would like to meet with the CCG and both City Council and OUD. Finalise the CJ report and release to the NF | 44438 | 44591 | 0 | 0 | 0 | 0 | 36268 | 36268 | 32148.64 | 36268 | 0 | 0 | Total budget is spent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stakeholder engagement with Oxford University | The costs of a carbon zero scheme are c. £3m - we hope to be able to secure grant. | No | 0 | 0 | 0 | 0 | TRUE | tgodfrey@oxford.gov.uk | 2022-01-17 10:00 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | Y | Y |  | N | bar: 1 to 52
B0098 | George St 1-3 | CP | Regeneration & Economy | B0098 | George St 1-3 | Refurbishment of 1-3 George Street to provide affordable workspace as part of an inclusive economy. | Project - Development | Lisa Smith | Running | 0 | Development | Tom Bridgman | Lisa Smith | 0 | Tom Bridgman | Lisa Smith | ODS are currently reporting an anticipated completion date of 6th July 2022, 7 months after the contract completion date, 14th December 2022. Piling works have completed with some works to the Grd floor having started, albeit in significant delay. Works to the upper floors are still in delay due to programme mismanagement. ODS are being pushed to complete works to the upper floors to enable the new operator to take occupation to complete the CAT B fit out whilst works to the lower floors continues. ODSL tender for D&B contract did not allow for any exclusions or clarifications and as such are liable for risks in the delivery of all works that fall outside of the contract works. OCC have reviewed anticipated costs and have determined who and how the additional costs are to be paid. The requests for additional funds is now subject to cabinet approval. | Over Budget | Awaiting new programme | Medium | Medium | The current financial status of the project is now starting to cause further problems, namely with concern regarding expenditure being met to claim against OxLEP funding. George Street has been allocated £800k of OxLEP funding, of which we need to have claimed against by March 2022. The combination of slow progress on site and down valuing of valuations is leaving us in a situation where we are currently projecting that we will not meet this deadline. An extension of time has already been granted with regards to George Street works and it is looking extremely unlikely that another extension will be available, however this will be broached at the next meeting with OxLEP. A meeting has been arranged to review this, it is hoped that money can be claimed against works completed instead of works billed for, this will remove the risk and ensure that the March deadline is met. This is still being reviewed and an update will be available accordingly. ODS have stated that the terms of engagement between OCC and the project consultants were requested by the ODS legal team at the point of signing the contract, however it wasn’t forthcoming. So as a result ODS claim that the design team were never novated, meaning that ODS have no ‘contractual responsibility’ to cover the costs of those services. However, ODS have been paying some of these fees as they are aware of the pressures to keep momentum on the project and will continue to do so. A meeting has been arranged for 18/01/2022 to review this. | Continued review and progression of budget review. Finalising agreement of legal documents to enable operator lease to be signed. Continued review of works on site and construction programme to improve on ODS completion date. | 4. Pipeline | Operator Lease including SLA to be agreed / signed. Additional Budget review - potentially Cabinet Feb 2022. Revised construction programme required from ODS - ASAP | 44544 | 44748 | 1635200 | 906660 | 0 | 0 | 1606660 | 700000 | 278502.12 | 700000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Programme has extended due to problems on site and poor contract management, with the completion date now falling within the next financial year. The cashflow will be prolonged over an additional 6 months from Dec’ to June, with the need for additional funds to cover additional works. | 340000 | 0 | 0 | -566660 | 0 | 0 | -566660 | Legal (property) support required for Lease/ SLA negotiations. ODSL revised management proposals required. | Approval agreed to additional spend to meet BREEAM Very Good including fabric improvement, triple glazing, air source heating and PV | Yes | Enabling works, Office refurbishment, Office fit out | AAP appointed, review monthly | ODSL reporting monthly | 0 | TRUE | lsmith@oxford.gov.uk | 2022-01-17 11:17 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N/A 1 | George St 42 - 46 | CP | Regeneration & Economy | N/A 1 | George St 42 - 46 | Ground floor retail units with vacant residential upper parts. Feasibility project to seek options including letting, refurbishment or identify an alternative use. | Project - Other | TBC | Paused | 0 | 0 | 0 | TBC | 0 | Tom Bridgman | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Idea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | confirmation of project commencement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2021-08-05 13:56 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0118 | Ice Rink - development options | CP | Regeneration & Economy | B0118 | Ice Rink - development options | To develop a 5 year maintenance programme, and longer-term delivery options for Oxford Ice Rink | Project - Development | Jenny Barker | Running | Development Board | Development | Tom Bridgman | Trudy Godfrey | 0 | Tom Bridgman | Trudy Godfrey | Hawkins Brown presented their initial findings to the project team. Montagu Evans presented their business case. The preferred location is on the railway edge however it has not been possible to design the scheme to avoid the floodzone, which would have implications for risk of delivery, programme risk for OxWED and cost implications. Officers are meeting Kevin Minns to discuss these implications and how best to raise with OxWED. Glanvilles have been appointed to advise on highway matters and provide construction drawings (for parking, public realm, vehicle servicing) to allow the ice rink to continue to operate whilst Oxpens is under construction. | On Budget | On Schedule | Medium | Medium | 1. The preferred option - to relocate the ice rink on Oxpens - comes with risk and cost challenges. Officers are discussing this with OxWED at the earliest opportunity. 2. Other options for the ice rink are limited. Co-location with OUFC may need to be re-explored. Even though this option is sub-optimal, we will need to take forward "refurbish existing" as an option at the next stage. 3. Commercial risk - Current appetites to invest in new or refurbished ice rinks by the ice market are going to be limited over the next few years due to covid and social distancing. | Need to explore appetite of OxWED to take forward relocation of the ice rink. Need to produce construction drawings to allow the ice rink to continue to operate during the Oxpens construction phase | 2. Feasibility | officers to meet with OxWED during January to explore relocation of ice rink. Glanvilles inception meeting in w/c 24 Jan OxWED workshop being arranged for early February, ideally Tom Bridgman should be present. Dates are being put forward. Need an additional £54k funding from Dev Board for Glanvilles design work. | 44311 | 44620 | 32000 | 0 | 0 | 0 | 115550 | 115550 | 17946 | 70000 | -45550 | Slippage (Underspend in 21/22 - slip budget back) | Slippage of consultancy work to 22/23, but total project budget is now over-committed. Need additional £54k from Dev Board for Glanvilles design work on parking / access options. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Are OUFC still interested in co-locating with the ice rink? | Carbon reduction programme is being worked up to be funded from Salex but whether or not this is undertaken will depend on which option is pursued. | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-19 15:13 | [54 empty] | N |  | N | N | N | N | Y | Y | N | Y | N |  | N | bar: 1 to 52
B0131 | Meanwhile in Oxfordshire | CP | Regeneration & Economy | B0131 | Meanwhile in Oxfordshire | Meanwhile use of vacant retail units in Oxford City Centre and Oxfordshire market towns. To tackle the predicted significant increase in vacant units in Oxford city centre and Oxfordshire’s market towns, by initiating a multi-authority ‘meanwhile use’ collaboration. | Other Capital Spend | Steve Weitzel | Running | Development Board | Development | Tom Bridgman | Steve Weitzel | 0 | Tom Bridgman | Steve Weitzel | The contract with MakeSpace has been signed . The contract with Makespace is a pre-condition to getting into contract with OXLEP and claiming OxLEP to cover the funding spent to date. Makespace have completed 14 leases in the County, and are currently liaising with Landlords to acquire more space and to accomodate many on the long list of interested potential tenants. 4 organaisations have been housed, over 18,900sq ft secured and 48 new jobs created by the project to the end of September 2021. We hope to have secured many more leases in next 2 months and are projecting to meet the scheme targets on Organaisations housed, sq ft secured and new jobs created. | On Budget | On Schedule | Low | Medium | Limited building options in some council areas (south, west). Landlord engagement and LA engagement increased Delay due to COVID and complexity of multiple projects. Building costs rising rapidly, long-term approach needed and larger projects preferred. Reduction in income from occupation delays means reduced revenue funds for Makespace. Mitigate by cutting some costs/seeking wider revenue funds/loans. | Contracting OXLEP Business rates costs on larger buildings Managing occupier expectations Securing fit outs at acceptable costs Future funding for Makespace, expected from rental revenues, currently forecast less than expected due to lower rent deals. Pressure being applied as Makespace are focusing on socail enterprises and not enough on commercial operations wich tend to generate higher revenue to fund future years. | 5. Delivery | Get into contract with OxLEP and make claim – end of November. Steeper ramp up in Leases agreed and organisations housed. | 44592 | 44742 | 1875000 | 253874 | 0 | 0 | 1844850 | 1590976 | 1407691 | 1590976 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Market conditions slowed leases acquired. Extension sought from OXLEP and achieved, now on new programme | 253874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Possible | Potential Contractor | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0113 | New Theatre (refurbishment) | CP | Regeneration & Economy | B0113 | New Theatre (refurbishment) | Feasibility for alteration and improvement of New Theatre | Project - Development | Jenny Barker | Paused | Development Board | Development | Tom Bridgman | Jenny Barker | tbc | Tom Bridgman | Jenny Barker | Agreement was reached with ATG to jointly fund feasibility work that was looking to improve the functioning of the theatre. A brief was agreed but appointment was stopped when the theatre had to close for the Covid 19 pandemic. Although the theatre has reopened discussions re the lease and the need for improvements have been taking place. Project is Paused. | Under Budget | Awaiting new programme | Medium | Medium | Project currently on hold. ATG are in discussions with the Property Team re lease renewal and investment proposals. A short lease extension was offered but this would limit any investment by ATG into the building. A longer lease is being sought. | Retention of and reopening of the theatre has been the priority. The conclusion of lease negotiations is needed before there is likely to be any progress on feasibility work with ATG. | 2. Feasibility | Discussions over the potential to extend the lease, linked to creation of a fund to invest in the building, have taken place. Further clarity is needed over the lease negotiations and the approach to the maintenance and upgrade of the building before feasibility can be progressed with clear objectives. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Project has been paused whilst the theatre was shut and there was uncertainty around reopening. The current lease on the theatre is short and discussions are on going with the Property Team with regard to increasing the length of the lease. Until there is progress on this matter any feasibility is likely to remain paused. Given the time that it is likely to take for the lease negotiations to progress and any agreement around the brief for feasibility work the budget has been slipped to 22/23. | 60657 | 0 | 0 | 60657 | 0 | 0 | 60657 | 0 | TBA | Unsure | 0 | 0 | 0 | 0 | 0 | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0112 | Odeon Redevelopment | CP | Regeneration & Economy | B0112 | Odeon Redevelopment | Feasibility for redevelopment of the Odeon | Project - Development | Carri Unwin | Running | Development Board | Development | Tom Bridgman | Carri Unwin | 0 | Tom Bridgman | Carri Unwin | Additional Legal advice has been obtained which advises on plans to demolish and landscape kiosk area to address antisocial behavious concerns and improve the visual amenity of Gloucester Green. Advice being sought on whether demolition will require Conservation Area Consent. Architects appointed to look at options to improve the visual amenity of Gloucester Green. A Commercial Agent JLL has been appointed and is carrying out Workstage 1 works on recommended delivery and marketing routes for the Odeon site. A report has been prepared for January 22 Cabinet for authority to market the site, and for JLL to begin Workstage 2 with Site Marketing Stage 1 planned for the start of May. | On Budget with slippage | On Schedule | Medium | Medium | The cinema has a limited lease remaining and it is unclear what the Odeon's intentions are. Pre pandemic they proposed investment in the building but did not pursue it. The pandemic has severely impacted their parent company. The development of options for the site is a mitigation for the uncertainty of the use going forward. The loss of a cinema may impact on the viability of business in George Street. This will be considered in developing proposals for the site. The loss of the cinema may raise adverse publicity and planning advice is that to replace the Odeon a cultural use should be provided of equal or greater value. There are separate plans to improve the visual amenity of Gloucester Green by demolition of the kiosks and landscaping the area. | The existing tenant is unable to commit currently to any extension of the lease and therefore to protect the Council’s investments options for alternative use and redevelopment need to be considered to avoid an empty building if the lease is not renewed. The Council does want to address the anti social behavior issues in Gloucester Green and is exploring options to demolish the kiosks and landscape that area of Gloucester Green. Some of the kiosks are in arrears and so the Council is not receiving the full rent for these units. Though there would be loss of income it is felt this can be made up for by increased longer term income from other Council investment projects in the City Centre. | 2. Feasibility | Cabinet report Jan 22 | 0 | 45169 | 40657 | 130000 | 125000 | 0 | 415657 | 160657 | 22831.35 | 160657 | 0 | N/A - On Budget | 0 | 65000 | 0 | 0 | -65000 | -125000 | 0 | -190000 | 0 | TBA | Unsure | 0 | 0 | 0 | 0 | TRUE | cunwin@oxford.gov.uk | 2022-01-20 11:21 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0141 | Kiosk Project | CP | Regeneration & Economy | #N/A | #N/A | #N/A | #N/A | Carri Unwin | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | N | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
B0120 | Osney Bridge (Oxpens River Bridge) | CP | Regeneration & Economy | B0120 | Osney Bridge (Oxpens River Bridge) | Provision of a pedestrian cycle bridge over the Thames linking Oxpens to Osney | Project - Development | Steve Weitzel | Running | Development Board | Development | Tom Bridgman | Steve Weitzel | 0 | Tom Bridgman | Steve Weitzel | The RIBA stage 1 report was produced and discussed widely at project meeting. It showed 4 options for bridge location and these were discussed at length and shared with County, University and OxWED. OxWED asked us to fix on one before their public consultation, however, this was too early in the process. We had initial archaeology and heritage OCC conversation and highlighted the urgent need to progress additional topographical survey, Site investigation and ore ecological surveys. The first two are tendered and awaiting start. The remainder are being discussed whether to appoint independent consultants or progress with Stantec to streamline operation. Liaison with EA has been tortuous due to staff changes, impacting on approval of SI and flooding discussions. New staff now appointed and trying to make up lost time. Work on RIBA 2 progressing and initial meeting held. Report due soon. Tending to favour Eastern route, contrary to OxWED currently preferred western route. Meeting arranged with property and OXWED to discuss. Also, held meeting with Levitt Bernstein to update on RIBA 1 and keep talking, next meeting end of November 2021. Knights keen to release press release. Discussed with Councillor Hollingsworth and agreed too early, partly due to Gasworks Bridge being closed. | On Budget | On Schedule | Medium | High | Key risks are delivery within the timescales, consents required, ground contamination affecting location of abutments, flood risk, coordination with Oxpens development and legal resources to support the work required including landowner agreements. These will be mitigated through the design process. A further risk is with regard to the transfer of ownership and adoption by the County Council and the close involvement of County Officers in the project is to mitigate the risk. | Liaison with EA over Flooding, compensation and scope of SI works. Agreement from OxWED to location of the bridge. Discussions on going. Flood risk and mitigation - consultant working scheme. Bridge connection to the north. The design of the connecting path works to the north needs to be progressed and may need to include an interim solution if Oxpens development has not progressed. Timing of delivery and co ordination with the Oxpens development will be required with on going dialogue with OxWED necessary Potential costs associated with contamination south of the river. SI tendered and in hand to determine. Clarity over standard for bridge and path works needed and to be obtained through engagement with County highways. Authorization to spend £300k and reports and approvals required to increase spend on design stages. | 2. Feasibility | Get SI undertaken, tenders eceived back and awaiting approvals from EA. Further meetings with stakeholders. DRG, DB & member briefing for the next stage of works in next cycle. | 45016 | 0 | 1100000 | 4583745 | 1340000 | 0 | 6223745 | 300000 | 40413.56 | 300000 | 0 | N/A - On Budget | Delay in consultant appointment has delayed draw down of budget. | 4000000 | 1600000 | 0 | -583745 | 260000 | 0 | -323745 | 0 | 0 | Unsure | 0 | Stantec - Simon Hudson | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0116 | Osney Mead Pathworks (Innovation Quarter) | CP | Regeneration & Economy | B0116 | Osney Mead Pathworks (Innovation Quarter) | HIF funding for OFAS and Cycle infrastructure to unlock housing at Osney Mead | Project - Development | Steve Weitzel | Running | Development Board | Development | Tom Bridgman | Steve Weitzel | 0 | Tom Bridgman | Steve Weitzel | Stantec have produced options for dealing with Flooding which apears to be over engineered so trying to agree variant standards to come up with acceptable scheme. Bridge over Bullstake stream needs re,ocating and exending. This will increase budget but not yet able to quantify as too early to options process. | On Budget | Over Schedule | High | High | Working through RIBA stage 1 has already highlighted some possible issues/risks relating to land and scope of the works. Environment Agency approval and resolution of the adoption issues for the works is necessary. EA engaged. Unregistered land may also be required and the University are pursuing a claim. Flood risk associated with delivering a dry route and the need for flood mitigation emains complicated. Consultant engaged to ensure flood risk mitigation is allowed for in the Oxpens proposals. Further work will be undertaken as part of the consultants work. The works will need a number of consents and the timing of achieving these represent a risk to delivery and programme. | Consultant appointment to enable feasibility and design work to progress. Progress agreement with EA re funding and agreement to enable works to progress. Clarification of path standard and adoption requirements with County Highways. Network Rail engaged and happy with proposals and lower level of BAPA agreed. Geotechnical investigation required and now scoped. EA engagement is now lined u and critical to design and hence scope of works. Scantec confident. More surveys required, some in scope and some not. | 2. Feasibility | RIBA stage 2 gateway review mid November 2021. Stakeholder consutations happening and planned leading to public event in December 2021. This will lead to design and planning submission in March 2022. | 44926 | 44945 | 900000 | 5300000 | 540000 | 0 | 6090000 | 250000 | 21864.68 | 250000 | 0 | N/A - On Budget | 0 | £4,590,000 includes funding for OFAS | 540000 | 0 | #INVALID OPERATION | 0 | 0 | #INVALID OPERATION | Confirmation whether OCC is prepared to appoint the consultants prior to a revised HIF funding agreement is signed? Encouragement of HE to progress revised agreement with OCC. | 0 | Unsure | 0 | Stantec - Simon Hudson | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
M5037 | Oxford North (Northern Gateway) | CP | Regeneration & Economy | M5037 | Oxford North (Northern Gateway) | Drawdown of HIF funding to provide infrastructure for Oxford North and facilitate the provision of additional affordable housing as part of the development. | Project - Development | Jenny Barker | Running | 0 | Development | Tom Bridgman | Jenny Barker | 0 | Tom Bridgman | Jenny Barker | Amended agreement with HE and agreement with TWO, to enable the HIF to be drawn down, was subject to on going discussion re subsidy control. This has now been resolved and drafting of agreements is underway. Work is ongoing with TWO to meet funding conditions and milestones. TWO keen to do first payment but amended agreement required. Homes England and Thomas White relationship requires OCC resource. Homes England have confirmed capacity funding for 21/22. | On Budget | Over Schedule | Low | Medium | Oxford North development is progressing but there remains risks around the timing of infrastructure delivery. Amended HE agreement and approval of repayment mechanism required. Whilst these have been agreed in principle formal amendment of the funding agreement is required and not yet been forthcoming from Homes England. Capacity funding for 21/22 has now been received to address budget pressures and a claim is being prepared. | A delegated decision is now being prepared to secure formal sign off for the terms of the agreements with Homes England and TWO. This include the assessment of profit being undertaken using the S106 mechanism and additional affordable housing being counted against the repayment of HIF. | 5. Delivery | Amended funding agreement with Homes England to enable the finalisation of the Agreement with TWO. Report om title being received. | 47057 | 0 | 0 | 9300000 | 0 | 0 | 10000000 | 700000 | 3577 | 750000 | 50000 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Delay in completing legal agreements has delayed the drawdown of funding. Early drawdown of £750k HIF currently anticipated in 21/22, to be passed on to TWO once in contract. | 5000000 | 4250000 | 0 | -4300000 | 4250000 | 0 | -50000 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0119 | Oxford Station Masterplan | CP | Regeneration & Economy | B0119 | Oxford Station Masterplan | To create a concept Masterplan for Oxford train station and surrounding sites. The evidence-base and consultation must be to a standard that will allow the Masterplan to be later adopted as an SPD. The Masterplan will take a holistic approach to the redevelopment of the whole station area including the delivery of a multi-modal transport interchange with rail service enhancements and capacity upgrades, improved station forecourt and commercial area, with better connectivity to Beckett Street and wider integration to key developments in the city centre (Oxpens and Osney), whilst ensuring delivery of East-West rail timetable requirements (a nationally significant infrastructure project). The Masterplan will fulfil the stakeholder priorities for the Station. | Project - Development | Kate Beeching | Running | Development Review Group | Development | Tom Bridgman | Kate Beeching | 0 | Tom Bridgman | Kate Beeching | Client team have agreed the revised brief for Atkins. Atkins will submit their proposal by end November. A clarification calll is being scheduled for last week in November. | Over Budget | Awaiting new programme | Medium | Medium | R: R: Ongoing Programme extension and risk to budget. M: Agree payment schedule linked to deliverables and diligent contract management. R: Sub-optimal Masterplan (inc crossing across Botley Road) because of need to deliver EWR first. In March 2021, NR revealed because of funding issues they may not be able to pursue the preferred Railhead solution. M: OCC and City are preparing a number of scenarios for consideration by NR to explore the funding and phasing of the different options. R: Elements of the public consultation may be controversial and result in reputational damage M: Atkins are spending more time on improving the evidence base to support the optioneering. We have agreed with the client group that we will use the consultation to gather feedback on the scenarios, rather than to select a preferred option. | Need to agree how Atkins will deliver the remaining contract; and impact on programme. To enable us to tie in with the West End SPD consultation, it is preferable for Atkins to finish their work by end Feb 2022. It is acknowledged this is tight. Competing demands for space on forecourt means that all asks will not be met in full. The evidence base needs to rationalize these decisions and the Masterplan narrative explain the trade-offs. Need to secure agreement with NR / ORR to reduce Car Parking. This will require and additional study to examine how people will access the station in the future when CO comes on-stream. Establish how much Funding NR can put towards the scheme to identify gap funding. | 2. Feasibility | Atkins to respond to revised brief by end November. Need to agree a new programme with the client team in early December. Report back to DRG in early December. | 44498 | 44834 | 70000 | 0 | 0 | 0 | 138571 | 138571 | 99016.88 | TBD - awaiting Atkins proposa | #INVALID OPERATION | Forecast Overspend at end of project | Atkins submitted contract variations due to extension to programme. Paper for additional CIL feasibility being drafted tracking to Sept DRG. Atkins contract being revised to finish at RIBA 1a rather than 1b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | May require Senior Management to discuss with DfT/ORR to reduce car parking at Station. May require Senior management to discuss with NR their intentions for the quality of development at Oxford at a senior level. May need to use the Landowners WELOG to help with evidence bases. | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-12 13:16 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0081 | Oxpens Carpark Decking | CP | Regeneration & Economy | B0081 | Oxpens Carpark Decking | Removal of deck car park at Oxpens | Project - Development | Lisa Smith | Running | Development Board | Development | Tom Bridgman | Lisa Smith | 0 | Tom Bridgman | Lisa Smith | Original remit was to remove, store and re-use decking within new depot rationalisation project, which is now not looking likely to happen resulting on budget for the project being reduced. LS prepared Cabinet report, Cabinet 26th Jan 2022. | On Budget with slippage | Awaiting new programme | Medium | Medium | Determining a suitable timeframe to commence works on site that do not impact Ice Rink Operations or the Decarbonisation project. Review of terms of lease with OXWED at Oxpens Car Park – Lisa to review with Emma Gubbins upon her return from annual leave. Cabinet and stakeholder engagements to continue. Cabinet decision awaited - 26/01/2022 | Key risk that we are in breach of contract with OXWED and liable for costs of the removal, mitigation is ongoing discussions and agreement via the OCC property team. The structure is in breach of planning approval, the public have previously been made aware of the removal, so the ongoing presence of the structure may be controversial, equally the Coach parking at St Giles is a nuisance to the neighbouring area and there is political pressure to re-order the City Centre Coach provision to address issues of Air Quality, noise and over crowding etc in the short term, options have been developed to address this in the short term, some will require discussion with the Bus operators to agree. | 2. Feasibility | Lease review with EG. Continued stakeholder engagement. Cabinet Jan 2022 | 44712 | 44771 | 43000 | 225355 | 0 | 0 | 235355 | 10000 | 9234 | 10000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Unsure why the Decking removal consultant fees have not been populated within the Agresso actual spend for 20/21. Finance to update. There is currently no fixed date for completion at present, removal of the decking is listed in the lease with OXWED for May 2022, which is required to be instructed no less than 6 months prior to the date where the decking is to be removed. Subject to further agreement with OXWED the backstop for this date is at the termination of the lease, which is currently March 2025, there is a rolling break on the lease with 6 months’ notice. Options were taken to DRG on 18th August and paper to DB is being drafted that may result in underspend from varying approach, but will require Cabinet decision. | 0 | 0 | 0 | -225355 | 0 | 0 | -225355 | N:A | Not applicable. | Yes | Active engagement with ODS for proposal to remove and store. | Carter Jonas (Giles Martin) | Not appointed yet, but likely to be ODS | 0 | TRUE | lsmith@oxford.gov.uk | 2022-01-17 11:17 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0086 | Seacourt Park & Ride (Extension) | CP | Regeneration & Economy | B0086 | Seacourt Park & Ride (Extension) | Creation of 600 space extension to existing Seacourt Park and Ride to include new terminal and facilities | Project - Development | Douglas Kerrigan | Running | Development Board | Development | Tom Bridgman | Douglas Kerrigan | Paul Walker | Tom Bridgman | Doug Kerrigan | Snagging issued and in progress O and M manual presented New works fenced off and lighting turned off to minimise rolling costs whilst overall underuse continues. | On Budget | Completed | N/A | Low | 0 | Snagging car park surface (minor). | 6. Completed | Discharge Conditions related to EV charging end of August | 44344 | 0 | 0 | 0 | 0 | 0 | 262499 | 262499 | -250212 | 262499 | 0 | N/A - On Budget | Not spent in 20/21 due to completing late. | 97500 | 0 | 0 | 97500 | 0 | 0 | 97500 | Final account due May 2021. Capitalise any surplus to cover PMO time. | All aspects of the works particularly terminal building have been designed to incorporate latest low energy technology. | Yes | 0 | WYG / Tetratech | ODSL | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:54 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
HT14 | South Oxford Science Village | CP | Regeneration & Economy | HT14 | South Oxford Science Village | Securing the allocation of and planning permission for South Oxford Science Village. Identification of and securing of proposals to enable the delivery of the development on the site. | Project - OtherLocal | Jenny Barker | Running | 0 | Development | Tom Bridgman | Jenny Barker | 0 | Tom Bridgman | Jenny Barker | Recommendations to Cabinet in October 21 have been agreed providing agreement to the development of the site using a master developer and the key principles for collaboration. Discussions underway re the delivery vehicle and a further report prepared for Cabinet Feb 22. | On Budget | On Schedule with Risks | Medium | Medium | Lack of formal collaboration agreement with partners is being addressed to provide certainty around the joint working taking place. Key principles established to inform the Heads of Terms. This will reduce the risk that a partner could walk away. Uncertainty remains over the final land available for development. TW will not confirm land availability until the AMP7 for the STW has been agreed (programmed for Jan 22) and MDC are yet to confirm if the lease for part of their land has been surrendered. These issues could alter the land owner share of costs and revenue. Previous work on the preparation of a planning application is becoming increasingly dated and will need to be refreshed for a future submission. It is intended to delay submission until a development partner is on board who will bring expertise and funding. However attempts to engage SODC planning have struggled to gain traction with risk that it has not been possible to reduce uncertainty around planning. Lease over OCC land needs to be addressed to provide certainty over the OCC land value. Other sites are progressing proposals and this could impact on the SOSV site infrastructure requirements. The progress on sites is being monitored. | Key issues relating to odour are due to report in January 22. Engagement with SODC to inform work required to prepare a planning application for the site is ongoing. The issue of overhead lines and removal/compensation is progressing but National Grid have been engaged and an initial approach for compensation has been made. Thames Water lease of OCC land and the potential to end the lease and the cost is being explored. A revised program has been prepared and the partners have agreed that planning will not be progressed until a development partner is on board. Preparation for master developer procurement is underway and the drafting of an LLP document. Details of both need to be agreed with a target to do so this quarter. | 2. Feasibility | Agreement of Delivery Vehicle - FEB 22 | 49674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | jbarker@oxford.gov.uk | 2022-01-11 09:57 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3070 | Business Process Automation Full Rollout | HB | Business Improvement | C3070 | Business Process Automation Full Rollout | 0 | Project - ICT | Rocco Labellarte | Completed | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Rocco Labellarte | 0 | Helen Bishop | Rocco Labellarte | The project is closed. RPA is now "business as usual" with individual service areas engaging in automation projects. | Completed | Completed | N/A | N/A | 0 | 0 | 5. Delivery | Closed. This was reported last month and before. It continues to be closed. | 0 | 44508 | 0 | 0 | 0 | 0 | 19515 | 19515 | 19687.5 | 19515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | rlabellarte@oxford.gov.uk | 2021-12-29 07:37 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3072 | Council website and partner portals refresh / redesign, including forms improvements | HB | Business Improvement | C3072 | Council website and partner portals refresh / redesign, including forms improvements | If the Council considers it appropriate or necessary, we can consider refreshing the design of the public facing website and portals (33 in total). | Project - ICT | Rocco Labellarte | Running | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Purnima Gore | 0 | Helen Bishop | Rocco Labellarte | Three suppliers shortlisted. Presentations w/k 17th January | On Budget with slippage | On Schedule | Low | Low | 0 | 0 | 5. Delivery | Award of contract - January 2021 | 0 | 44651 | 0 | 0 | 0 | 0 | 109000 | 109000 | 11154.96 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3058 | CRM Lagan Replacement | HB | Business Improvement | C3058 | CRM Lagan Replacement | Repacement of the legacy CRM system | Project - ICT | Rocco Labellarte | Paused | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Purnima Gore | 0 | Helen Bishop | Rocco Labellarte | Project deprioritised to allow for the implementation of Aareon. Procurement potentially in Febuary, subject to QL, Open Revenues and M365. | On Budget | Awaiting new programme | Low | Low | The key risks are: * the continued operation of unsupported software for the council's CRM and forms engine * the requirement to replace a number of dependent solutions simultaneously whilst ensuring continuity of service * uncertainty over the correct approach to market to take to enable a swift replacement of key systems and to make best use of existing technology Mitigations * reappraising the use of Aareon QL as a potential CRM replacement * use of the ICT Review for advice on approach to market * consideration of a short-term commission of technical expertise to advice on best route to market | 0 | 3. Design & Technical Specification | No change. To restart in December. | 0 | 0 | 0 | 50275 | 0 | 0 | 70275 | 20000 | 13633.84 | 20000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | 0 | 135000 | 0 | 0 | 84725 | 0 | 0 | 84725 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rlabellarte@oxford.gov.uk | 2021-12-29 07:37 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3060 | End-Point Devices (Desktops/Laptops) | HB | Business Improvement | C3060 | End-Point Devices (Desktops/Laptops) | End-Point Devices (Desktops/Laptops) | Rolling Programme | Rocco Labellarte | Completed | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Purnima Gore | 0 | Helen Bishop | Rocco Labellarte | Closed | Completed | Completed | N/A | N/A | 0 | 0 | 5. Delivery | Closed !!! | 44377 | 0 | 60000 | 150000 | 150000 | 150000 | 512290 | 62290 | 26658.83 | 62290 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rlabellarte@oxford.gov.uk | 2022-01-10 16:58 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3044 | ICT Software and Licences | HB | Business Improvement | C3044 | ICT Software and Licences | ICT Software and Licences | Rolling Programme | Rocco Labellarte | Running | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Rocco Labellarte | 0 | Helen Bishop | Rocco Labellarte | Not a project! Pays for Microsoft licenses on an annual basis. Still not a project. | Over Budget | On Schedule | Low | Low | 0 | 0 | 8. Rolling Programme | Not a project !!! | 0 | 0 | 245000 | 245000 | 245000 | 245000 | 980000 | 245000 | 233158.75 | 245000 | 0 | 0 | 0 | 245000 | 245000 | 245000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2021-11-03 17:14 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3066 | Telephony Device refresh | HB | Business Improvement | C3066 | Telephony Device refresh | Telephony Device refresh | Rolling Programme | Rocco Labellarte | Running | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Rocco Labellarte | 0 | Helen Bishop | Rocco Labellarte | Not a project. Funding for device replacements as needed. | On Budget | On Schedule | Low | Low | 0 | 0 | 8. Rolling Programme | Not a project. Funding for device replacements as needed. | 44377 | 44368 | 0 | 60000 | 60000 | 60000 | 189271 | 9271 | 8091.77 | 9271 | 0 | 0 | 0 | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rlabellarte@oxford.gov.uk | 2022-01-10 16:58 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3068 | Windows 2008 Server Replacement | HB | Business Improvement | C3068 | Windows 2008 Server Replacement | The existing Windows 2008 server estate is due to go out of support in the coming months. This project is to replace the server estate with one that is in support and assures security updates will be applied. | Project - ICT | Rocco Labellarte | Paused | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Kevin Wigham | 0 | Helen Bishop | Rocco Labellarte | Due to complete in mid 2022 with the replacement of Lagan and ARC-GIS. | On Budget | Awaiting new programme | Medium | Low | Risks / mitigation Arc-gis upgrade and PA mapping options becoming a significant risk to go lives. Issue with PA mapping and Arc gis being investigated and assistance gained from ESRI. | All Idox application dates are now subject to consultation to ensure they don’t create undue pressure on departments and ensure no clash with Aareon go live. No current dates for Aareon go live so agreeing IDOX dates difficult. Local view / Idox Uniform / public access compatibility with Arc-Gis. and Mapping Version compatibility issues to be resolved. | 5. Delivery | Due to be completed with the replacement of ARC GIS and the decomissioning of Lagan. | 44377 | 44651 | 121128 | 90000 | 0 | 0 | 149459 | 59459 | 42329.49 | 59000 | -459 | Forecast Underspend at end of project | 0 | 0 | 0 | 0 | -90000 | 0 | 0 | -90000 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rlabellarte@oxford.gov.uk | 2022-01-10 16:58 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3079 | Town Hall WiFi | HB | Business Improvement | C3079 | Town Hall WiFi | Feasibility funding for improvements to Town Hall visitor WiFi to support full business case | Project - ICT | Rocco Labellarte | Running | 0 | Communities and Customers | Stephen Gabriel | 0 | 0 | Helen Bishop | Rocco Labellarte | Feasibility study due in January 2022. | 0 | 0 | 0 | 0 | 0 | 0 | 2. Feasibility | Awaiting feasibility quotes from 2 suppliers. Will then be presented to the relevant board for approval in November. | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rlabellarte@oxford.gov.uk | 2021-12-29 07:37 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3080 | Telephony Contract Replacement | HB | Business Improvement | C3080 | Telephony Contract Replacement | BT telephony contract replacement | Project - ICT | Rocco Labellarte | Running | Operational Delivery Group | Communities and Customers | 0 | 0 | 0 | Helen Bishop | Rocco Labellarte | Tender signed off for issue in January to begin the procurement exercise. | On Budget | On Schedule | Low | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0096 | Bullingdon Community Centre | IB | Community Services | B0096 | Bullingdon Community Centre | Demolition and rebuild of community centre | Project - Development | Douglas Kerrigan | Running | Development Review Group | Communities and Customers | Stephen Gabriel | Douglas Kerrigan | 0 | Ian Brooke | Doug Kerrigan | Demolition complete. Groundworks commence January 2022 | On Budget | On Schedule | Medium | Low | BOQ pricing has led to better cost surety GI complete so ground risk low | Planning conditions discharge. | 3. Design & Technical Specification | Groundworks complete for erection of timber frame April 2022 | 44680 | 44864 | 1481151 | 1064578 | 0 | 0 | 1514578 | 450000 | 112342.35 | 200000 | -250000 | Slippage (Underspend in 21/22 - slip budget back) | Completion in 22/23 | ££1.2m | 32000 | 0 | #INVALID OPERATION | 32000 | 0 | #INVALID OPERATION | Agree to procurement route | 0 | Yes | 0 | Jessop and Cook | ODSL | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:54 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0083 | East Oxford Community Centre | IB | Community Services | B0083 | East Oxford Community Centre | Development of the existing East Oxford Community Centre including new build. A separate project (N7050) also includes the development of up to 32 housing units on Princes street, Catherine Street and Union street. | Project - Development | Douglas Kerrigan | Running | Development Board | Communities and Customers | Stephen Gabriel | Douglas Kerrigan / Hagan Lewisman | Arcadis | Stephen Gabriel | Doug Kerrigan | Stage 1 pricing complete and in budget Stage 2 started to complete by January 2022 Programme to be issued by ODS by January 2022 | On Budget | Awaiting new programme | Medium | Medium | Tender returns not as forecast with allowance for Brexit etc. Tender ASAP and VE Early tender to allow VE/Design alteration. | Finalise OSF Framework to meet tender dates that focus on signing contracts in January to gain access to Growth Deal Funding for housing and overall feasibility. Programme reissue to ensure this happens | 3. Design & Technical Specification | Agree final cost under CSA and fees under D and B arrangement Issue contractor programme by January | 44932 | 45114 | 4212439 | 5280487 | 0 | 0 | 5430487 | 150000 | 13293 | 150000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Vacant Posession not available till end of March. Start on site with surveys April 2022. Programme and fee review ongoing. Alternative methds of construction | 3500000 | 1750000 | 100000 | -1780487 | 1750000 | 100000 | 69513 | Sign off to proceed | Sustainability plan to be developed after stage 3 | Yes | Community centre works are in scope with ODS capabilities. Programme and phasing will need to match capacity. OSF package on new build will reduce management requirement | Arcadis UK | ODS on refurbishment. New build highly likely ODS under a D and B | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:54 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N/A 2 | Florence Park Community Centre | IB | Community Services | N/A 2 | Florence Park Community Centre | Redevelopment of the existing community centre. The existing community centre building is reaching the end of its life and redevelopment is being considered by the community. | Project - Other | Andrew Humpherson | Paused | Development Board | Communities and Customers | Stephen Gabriel | Andrew Humpherson | 0 | Stephen Gabriel | Roo Humpherson | No action this month. Project pending approval to proceed. The community association have said that they will fund a replacement new build. Engagement required with Community to review progress. Community group proposing to restart meetings with Council. Resourcing and budget to be agreed. | Budget to be agreed | Awaiting new programme | Low | Low | 0 | Resourcing and budget to be agreed. | Idea | Feasibility proposal now pending new discussions with Community Group to review proposals post-Covid. | tbc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Project Proposal by AH | 0 | Yes | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-05 15:48 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
A4833 | Horspath Sports Park | IB | Community Services | A4833 | Horspath Sports Park | Building a sports park at Horspath Road. | Project - Development | Hagan Lewisman | Completed | Development Board | Communities and Customers | Stephen Gabriel | Hagan Lewisman | Fusion Lifestyle | Ian Brooke | Hagan Lewisman | We are waiting for the County to return 80% of our security deposit. Everything has now been approved by the County and legal fees paid we expect payment before the end of March 21. | 0 | 0 | Low | 0 | 1: Fusion try to claim late variations due to delay. M: Confirm to Fusion on writing the contractual position. 3: Reputational risk from 'settling in' issues with the new operator OUFC. E.g Community clubs such as Horspath Youth FC pressing for unreasonable requirements. M: Community use agreement and regular meeting with clubs. 4: OUFC try to remove cricket from the site. M: Meet with OCB and OUFC, community use agreement developed. 5: Fusion become insolvent meaning that the making good works are not completed. M: Press Fusion to undertake and badge up in existing negotiations. | Awaiting County Council sign off of the S278 to release 80% of our security deposit. 2 Fusion final account. | 5. Delivery | 0 | end of March 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1295.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The budget available has changed. We need to reflect the previously set budget. | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | Y |  | Y | N | Y | Y | N | Y | N | N | N |  | N | bar: 1 to 52
A4847 | Rose Hill Community Centre - Parking Management | IB | Community Services | A4847 | Rose Hill Community Centre - Parking Management | creating a traffic order for the car park. Installing ticket machines and signage to enforce a maximum stay period and stop the car park being used incorrectly. | Project - Other | Dave Morrell | Paused | Development Board | Communities and Customers | Stephen Gabriel | Lydia Dixon | N/A | Ian Brooke | Dave Morrell | Project paused due to corona virus. Aim to start project again in Autumn 2021 | 0 | 0 | High | 0 | 0 | Project paused due to corona virus | 2. Feasibility | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Understand corporate steer whether this has been un-paused. | project paused due to corona virus | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2021-11-03 17:14 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0134 | Shotover SSSI Management Plan | IB | Community Services | B0134 | Shotover SSSI Management Plan | 0 | Other Capital Spend | Michael Woods | Running | Development Review Group | 0 | 0 | Michael Woods | 0 | Hagan Lewisman | Michael Woods | 0 | On Budget | On Schedule | Low | Low | 0 | 0 | 2. Feasibility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 5865.4 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0075 | Town Hall Museum | IB | Community Services | B0075 | Town Hall Museum | Development of the museum space within the Town Hall, extension to the contract with ODS to incorporate Ceiling repairs, Courtyard. | Project - Development | David Hunt | Completed | Development Board | Communities and Customers | Stephen Gabriel | David Hunt | Amanda Newman | Ian Brooke | David Hunt | The museum opened in October and be greatly received by their customers with lost of positive feedback received. The main areas being worked on now are the outstanding snagging items and the final account. Accounts are not finalised as we are reviewing the EOT claim made by ODS on the w/c 4th Jan. Worst case scenario is £100k over budget. This is due to the project delays and the extra professional fees, the EOT value being reviewed within this possible £100k is £23k | Over Budget | Over Schedule | Medium | Medium | Financial Overspend - Currently working on final accounts & EOT | Review EOT submitted by ODS, this is being done by Purcell & F&G ODS invoicing, both finance departments are working on this. Complete final items on the snagging | 5. Delivery | January – Agree final account and ODS to submit invoices (last one received in September) 17th January - Lessons Learnt Meeting Ongoing - Snagging | 44439 | 44455 | 2653148 | 0 | 0 | 0 | 1051395 | 1051395 | 1113403.33 | 1151395 | 100000 | Forecast Overspend at end of project | Finance are currently working with ODS due to invoicing issues effecting project spend. | 35000 | 0 | 0 | 35000 | 0 | 0 | 35000 | Review opportunity for money to be re-profiled from the building maintenance or compliance budgets to pay for additional work to the roof. | HLF sustainability Statement awaited from project team. | Yes | ODS are appointed for the base build. Specialist fit-out by others. | Ridge - Tom Bloxsom | ODSL | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-20 10:43 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | Y | N |  | N | bar: 1 to 52
A4820 | Upgrade Existing Tennis Courts | IB | Community Services | A4820 | Upgrade Existing Tennis Courts | Upgrade Existing Tennis Courts | Project - Other | Hagan Lewisman | Running | Development Board | Communities and Customers | Stephen Gabriel | tbc | 0 | Ian Brooke | Hagan Lewisman | The project is paused and there will be no spend in this financial year. Aim to draft paper to DRG in May. | 0 | 0 | High | 0 | There is a risk that the tennis courts at Bury Knowle deteriorate and become unsafe meaning closure after this year, ODS do regular checks and targeted cleaning but this will only last so long. | Decide whether we are to progress with this project and consider that we would still need to find match funding for it which is not guaranteed. | 8. Rolling Programme | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Decide whether the Council is in a position to fund the gap of circa £50k, or whether we must still try to find the gap with external funding. Noting the risk of court deterioration and closure. | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2021-12-07 10:52 | [54 empty] | Y |  | Y | Y | Y | Y | N | Y | N | N | N |  | N | bar: 1 to 52
E3561 | Additional DFG Funding 2020/21 | IW | Regulatory & Community Safety | E3561 | Additional DFG Funding 2020/21 | Additional Disabled Facilities Grant for 20/21 | Other Capital Spend | Becky Walker | Completed | Development Board | Communities and Customers | Stephen Gabriel | Ian Wright | 0 | Ian Wright | Becky Walker | Funding was £168,687.00, it was not budgeted as it was one-off additional DFG funding. I have chosen On budget above as there is not a N/A option. Majority of funds are spent, few jobs awaiting invoices. | Completed | Completed | N/A | N/A | 0 | Pay final contractors and close account. | 7. Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98682 | 98682 | 68727.77 | 98682 | 0 | 0 | PLEASE NOTE THERE IS NO BUDGET FOR 21/22 or any future years this is one-off funding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2021-12-08 12:37 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
A4852 | Bodycams for Community Safety team | IW | Regulatory & Community Safety | A4852 | Bodycams for Community Safety team | Purchase of cameras and data storage for body worn camaeras within the Community Safety Team | Project - Other | Dan Courtenay | Running Slowly | Development Board | Communities and Customers | Stephen Gabriel | Dan Courtenay | 0 | Richard Adams | Dan Courtenay | Project has started. The following work has been carried out - Contact with Data Protection to understand impact of body worn. data protection impact assessment and procedure submitted for review - Email sent to HR with regards to a Policy enquiry - Teams have been identified for BW use - John Radcliff have been engaged with about their usage of BWVD - Companies have been contacted for demonstations | On Budget | On Schedule | Low | Low | Legal hurdles and political concerns. Secure IT storage arrangements. Mitigations include ensuring compliance with personal data requirements and secure storage. | Need to identify a suitable supplier and establish what the IT requirements are for secure storage and management of data. | 4. Pipeline | Contact with ICT to check BWC suitability with OCC systems. Obtain confirmation from HR with regards to impact on Policy | 44651 | 44427 | 60450 | 0 | 0 | 0 | 60450 | 60450 | 0 | 60450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note project will be carried out in 21/22 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2021-11-03 17:14 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
A4845 | CCTV Suite Upgrade | IW | Regulatory & Community Safety | A4845 | CCTV Suite Upgrade | CCTV Suite Upgrade | Project - Other | Richard Adams | Running | Development Board | Regulatory Services | Stephen Gabriel | Richard Adams | Roger Hardiman RJH Consultancy | Ian Wright | Richard Adams | The suite installation at St Aldates police station and infrastructure work has commenced and should be completed by the end of January. This project is no longer linked to a centralised hub within ODS which is still in feasibility stage. If that project materialises, the kit can be moved from the suite to a new location. | On Budget | On Schedule | Low | Low | 1. Increases in costs, not currently accounted for. 2. Other district councils do not wish to commit to the single county hub - South, Vale and West Oxfordshire have confirmed that they will sign the partnership agreement. Cherwell have yet to commit. They invested in their own suite a few years ago. 3. Decision on whether the single hub can be moved to Horspath Depot and then to the new building proposed at Redbridge. - ODS have confirmed that the Hub can be situated in Horspath Road and facilities can be created in the new development. Olly Hearne is the ODS lead on this aspect. 4. HR issues may result in Hub project delay. Therefore proceeding with upgrading existing Suite in St Aldates Police station with technology that allows a lift and shift to a new Hub location. 5. We are upgrading our existing Suite now as it is close to obsolete. The joint CCTV Hub for Oxfordshire is still in development but equipment purchased now can be transferred as part of our contribution to the new Hub if it materialises. | Tendering process completed for upgrade of the existing suite, HRA funded CCTV projects and fibre upgrades. Procurement involved and framework development. Supply change problems have delayed some kit implementation. Network upgrades completed. Partial install of the suite - remaining to be completed in January alongside new cameras. | 4. Pipeline | Installation of CCTV suite to commence in October and finish by end of January. | 44337 | 44592 | 68688 | 0 | 0 | 0 | 68688 | 68688 | 0 | 68688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None | Yes | Ollie Hearn is ODS lead contact. | 0 | 0 | 0 | TRUE | radams@oxford.gov.uk | 2022-01-11 11:25 | [54 empty] | N |  | N | N | N | N | N | Y | N | Y | Y |  | N | bar: 1 to 52
E3521 | Disabled Facilities Grants | IW | Regulatory & Community Safety | E3521 | Disabled Facilities Grants | Disabled Facilities Grants | Other Capital Spend | Becky Walker | Running | Development Board | Communities and Customers | Stephen Gabriel | Ian Wright | 0 | Ian Wright | Becky Walker | BAU in HIA with referrals being progressed. | On Budget | On Schedule | Low | Low | County Council Occupational Therapists are funded so there is no backlog and the service is actively promoting the availability of funding. Liaising with hospitals to enable discharge. | We need to Pay ODS by April to show spend | 9. Other Capital Spend | 0 | 0 | 0 | 1282378 | 1400000 | 1200000 | 1200000 | 5017378 | 1217378 | 507673.79 | 1000000 | -217378 | 0 | Lack on Contractors and ODS being unable to invoice at present | £1.2M provisional | £1.2M provisional | Unknown | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | None | Most of our works are adaptations, but some of these do significantly improve the EE of a property, and we do undertake safety repairs as well which do the same. | Yes | 0 | HIA Team | Various | 0 | TRUE | bwalker@oxford.gov.uk | 2022-01-13 12:25 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
E3511 | Essential Repair Grants | IW | Regulatory & Community Safety | E3511 | Essential Repair Grants | Essential Repair Grants - E3511 | Other Capital Spend | Becky Walker | Running | Development Board | Communities and Customers | Stephen Gabriel | Ian Wright | 0 | Ian Wright | Becky Walker | Budget Confirmed and all budget for current year allocated, new funds needed Requested a PMB for budget increase | On Budget | On Schedule with Risks | Low | Low | 0 | New additional funding needed, bid submitted | 9. Other Capital Spend | 0 | 0 | 0 | 24948 | 15000 | 15000 | 15000 | 76520.61 | 31520.61 | 23546.08 | 31520.61 | 0 | 0 | 0 | Unknown | Unknown | Unknown | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | Confirmation of budget for next few years | There would be as most interventions are helping to rectify severe safety issues with the structure of peoples homes. | Yes | 0 | HIA Team | Various | 0 | TRUE | bwalker@oxford.gov.uk | 2021-12-08 16:21 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
E3562 | OxPops (Electric Vehicle Charging) | MT | Environmental Sustainability | E3562 | OxPops (Electric Vehicle Charging) | Testing suitability of pop-up charging points for EV. | Project - Other | Rose Dickinson | Completed | Development Board | Transition | Caroline Green | Rose Dickenson | 0 | Mish Tullar | Rose Dickinson | 0 | Completed | Completed | N/A | N/A | Achieving project close-out. PM resources have been allocated to secure project close-out. Stakeholder management. Set-up video call for stakeholder ahead of project closedown. Payback of grant. Accept the risk – the project was 100% and does not have a match requirement. | IAR to be completed. | 7. Closed | 0 | 0 | 0 | 35806 | 0 | 0 | 0 | 0 | 0 | -6349.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The project is a trial project to assess the viability of an onstreet vehicle charging solution. If successful, there is potential. | No | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0126 | Asset Condition Survey (Corporate, Commercial and Community) | JW | Corporate Property | B0126 | Asset Condition Survey (Corporate, Commercial and Community) | Commission condition surveys on 604 assets to determine future maintenance, expenditure and rationalisation of those assets. | Project - Development | Jonathan Wright | Running Slowly | Development Board | Development | Tom Bridgman | 0 | 0 | Malcolm Peek | Jonathan Wright | In the process of ending relationship with contractor RLB originally appointed due to a number of issues. Scope for required surveys to be redefined and new tender process initiated. Significant slippage likely - TBC | Under Budget | Awaiting new programme | Medium | Medium | Access will be the key risk. Flow of information to contractor Health & Safety Information for properties. | OCC surveyors pre-visiting properties to ensure tenants are aware of the surveys and will allow access for RLB to complete the surveys. Program re-issued based on contact with large sample of tenants across the City rather than postcode oriented. | 3. Design & Technical Specification | 0 | 44435 | TBC | 0 | 0 | 0 | 0 | 300000 | 300000 | 7642.82 | 120000 | -180000 | Slippage (Underspend in 21/22 - slip budget back) | In process of ending relationship with original contractor RLB before revising scope and re-tendering. Compensation due to RLB to be determined, so forecast currently represents a high end of estimate. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The surveys will look at energy and social inclusivity at the core of recommendation to OCC | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-21 18:06 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0123 | Boswells (Phase 1) | JW | Corporate Property | B0123 | Boswells (Phase 1) | The developer Reef proposes to redevelop Boswells department store to provide a quality hotel with restaurant and work space at GF level . From a planning perspective this is well advanced and generally well received . | Project - Other | Emma Gubbins | Completed | Asset Review | 0 | Tom Bridgman | Emma Gubbins | 0 | Tom Bridgman | Emma Gubbins | Two week delay due to waiting external parties. This may cause slippage into next financial year. Working with Finance to ensure as much can be paid this year as possible. Final legal stage at the moment working through all lease documents. s106 is out. Looking to agree turnover clause in the leases. ** June Update - Phase 1 of project is now complete - no further update requests until commencement of Phase 2 ** | On Budget with slippage | Over Schedule | Low | Low | Timelines, as we are working with third parties these could slip but we are all in agreement to aim for exchange by end of April. | None at present | 6. Completed | 0 | 44255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17814.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2021-12-08 12:37 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0135 | CCTV Gloucester Green Car Park | JW | Corporate Property | B0135 | CCTV Gloucester Green Car Park | 0 | Project - Compliance | Emma Gubbins | Running | Asset Review | 0 | Tom Bridgman | Emma Gubbins | 0 | Jane Winfield | Emma Gubbins | Fire escape survey complete - no alternative routes can be established. The survey has not been undertaken by the CCTV contractor and a new supplier will be sought if possible. We have approached Procurement for alternative suppliers and will be requesting quotes. | On Budget | Over Schedule | Low | Low | Difficulties with the CCTV contractor, discussions with procurement to see if there is an alternative supplier. | 0 | 2. Feasibility | 0 | 0 | 44470 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | N/A - On Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | N |  | N | N | N | N | N | N | N | Y | N |  | N | bar: 1 to 52
B0133 | Cemetery | JW | Corporate Property | B0133 | Cemetery | Development of a proposal for a new Cemetery | Project - Development | Carri Unwin | Running | Development Board | Development | Tom Bridgman | Carri Unwin | 0 | Jane Winfield | Carri Unwin | November 2021 DB approved the OBC to secure approval of the detailed feasibility funding. A financial model for recouping the capital from ODS has been agreed with Jane Winfield and Paul Swaffield. Also possiblility of small scale partnering opportunities with neighbouring authorities. Project Steering Group set up and met in Dec 2021. Separate task meeting on the Westhill Farm money relating to question asked by OPT at a separate Council meeting. Stephen hunt from OPT attended Stakeholder meeting 1 of Shotover management plan. It was clear the OPT understand Shotover as the whole of their covenant area, not just the Country Park. Carri agreed with Michael Woods that LDA who are doing Management Plan include an internal Appendix 1 to look at opportunities in the wider land south of the Council managed Country Park. Peter Geach provided legal briefing meeting and follow up note to Jane WInfield and Carri on the OPT Covenant, and strategy developed for emphasizing the landscape improvement potential of the cemetery. Cemeteries are now considered public open spaces by government and so would be in line with the covenant which stipulates the land is to be used for "open space or a park .. which the public is allowed access to" In that sense our Council plans are more in line with covenant than existing agricultural field. This case for a new public greenspace and cemetery was presented to OPT at a meeting with Ian Brooke and Emma Gubbins also present; and OPT are willing to explore a landscape led cemetery proposal. Carri to meet on site with Charlie Jackson - OPT's Green Spaces officer. | On Budget | On Schedule | Low | Low | Risk that the Management Plan being managed by Michael Woods does not deliver what the OPT want it to, and requested it for. Mitigating this by trying to communicating essential link to Cemetery to Michael Woods. Cemetery feasibility and outline design work can hopefully start to overtake Management Plan in any event. | Ensuring Management Plan being done by LDA contains enough on wider opportunities, and is acceptable to OPT. They have inputted to Stakeholder Meeting 1 so that's useful. Agreeing site constraints and opportunities with OPT green Spaces Officer, and then getting OPT Trustees to agree and sign off on Debbie Dance's verbal agreement to explore cemetery and other landscape improvements in Shotover area. | 2. Feasibility | OPT Trustees meeting agree to exploring cemetery. Formulate Brief with site analysis plan, and draft Management principles | 44620 | 45535 | 0 | 120000 | 0 | 0 | 240000 | 120000 | 41984 | 45000 | -75000 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Please note £75k approved budget temporarily advanced to another scheme and will be reinstated in 22/23 | 155000 | 650375 | 650375 | 35000 | 650375 | 650375 | 1335750 | N:A | 0 | 0 | 0 | N:A - currently at the initial feasibility stage, this will be in the next stage. | N:A | 0 | TRUE | cunwin@oxford.gov.uk | 2022-01-20 11:55 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0101 | Covered Market - Major capital works at Covered Market | JW | Corporate Property | B0101 | Covered Market - Major capital works at Covered Market | Repairs and maintenance | Project - Development | Jonathan Wright | Running | Development Board | Development | Stephen Gabriel | Katharine Gould | 0 | Tom Bridgman | Jonathan Wright | Internal high level redecorations completed. Refurbishment of Ladies Trader's toilets and rest room completed. Refurbishment of Gents Trader's toilets completed. Works to the external decorations underway, in phases, in conjunction with roof works. Removing perspex covering to an apex above Avenue 4 and infilling with glass completed. Awaiting instructions before proceeding with further activities, so no progress this month. | Under Budget | Awaiting new programme | Medium | Medium | Changing priorities. Scope of proposed works will likely be reviewed now draft Master Plan report for the Covered Market has been received and fully reviewed. | Awaiting Client's instructions. | 5. Delivery | Not known, as awaiting instructions. | 45747 | 0 | 1012790 | 839127 | 0 | 0 | 974098 | 134971 | 85210.93 | 135210.93 | 239.93 | Slippage (Underspend in 21/22 - slip budget back) | Works on hold until finalisation of Masterplan. Budget to be slipped to 24/25. | Monies slipped from past/current years | Monies slipped from past/current years | Monies slipped from past/current years | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | None | N/A | Some | 0 | Property Services | Oxford Direct Services | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0136 | Covered Market CCTV | JW | Corporate Property | B0136 | Covered Market CCTV | To procure a specialist CCTV professional to advise OCC on the specification requirement to install CCTV at the covered market. Subsequently to procure a supplier to install a suitable system. Manage delivery | Project - ICT | Elaine Phillips | Running | Asset Review | Development | Tom Bridgman | Elaine Phillips | 0 | Tom Bridgman | Elaine Phillips | CCTV contractor has been appointed. Samples of cameras, brackets and fixings received and being reviewed with planning. A conservation architect selected from our framework to submit a planning application, just awaiting their quote which they estimate under £2,500 and will then instruct to submit planning. | On Budget | Over Schedule | Medium | Low | 0 | 0 | 3. Design & Technical Specification | 0 | 44269 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 1352 | 75000 | 0 | 0 | 0 | Up to £100,000 | 0 | 0 | #INVALID OPERATION | 0 | 0 | #INVALID OPERATION | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2021-09-07 15:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0106 | Covered Market Roof Works (Planned Maintenance) | JW | Corporate Property | B0106 | Covered Market Roof Works (Planned Maintenance) | Repairs and maintenance programme - Repairs to the covered market roof | Rolling Programme | Richard Davison | Running | Development Board | Development | Tom Bridgman | Richard Davison | 0 | Stephen Clarke | rdavison@oxford.gov.uk | Phase 6B. Works Start 10.1.22. Erection of Scaffolding for enabling works prior to main works commencing. Current Programme for this phase of the works is 39 weeks. Current Order £350,336. 8047979 to Croft B.C. dated 10.12.21. | On Budget | On Schedule | Low | Low | Unforeseen works as the structure is opened up mitigated by experience from previous phases and a the contingency sum allowed for within the project. | 0 | 8. Rolling Programme | Completion of phase 6B, October 2022. Phase 6c 9 further months' work; Phase 5a 9 further months' work. Phase 7 removed. | 0 | October 2022 | 240000 | 177023 | 325000 | 325000 | 1337023 | 510000 | 329881.2 | 510000 | 0 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | 0 | £455k | £455k | 0 | #INVALID OPERATION | #INVALID OPERATION | -325000 | #INVALID OPERATION | 0 | 0 | Yes | 0 | OCC Property Services | Croft Building and Conservation Ltd. | 0 | TRUE | rdavison@oxford.gov.uk | 2022-01-14 16:09 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0110 | Covered Market Vacant Unit Works | JW | Corporate Property | B0110 | Covered Market Vacant Unit Works | No demand for larger, vacant units. Splitting large units to meet small unit demand. | Project - Development | Emma Gubbins | Running Slowly | Development Board | Development | Tom Bridgman | Emma Gubbins | 0 | Tom Bridgman | Emma Gubbins | Works delayed due to unforeseen issues with the flooring, fire system and structure of the shop front. Now resolved and anticipation May 2021. Making good, pest proofing and installation of final Perspex arranged for August. Handover anticipated 23rd August. | On Budget | Over Schedule | Low | Low | Scope of works increases due to unforeseen circumstances due to age and condition of market. Mitigated by ongoing investigation and collaboration with ODS over works. Works with architectural input to Bonners fruit and veg stall to improve storage and circulation have started. | 0 | 5. Delivery | 0 | 44339 | 44431 | 0 | 0 | 0 | 0 | 23938 | 23938 | -19336.26 | 23938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | wider measures within the market. lighting to be low energy, no heating in any of the units | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | N |  | N | N | N | N | N | N | N | Y | N |  | N | bar: 1 to 52
B0111 | Town Hall Dry Risers | JW | Corporate Property | B0111 | Town Hall Dry Risers | Replacement of the dry riser system in the Town Hall | Project - Compliance | Jonathan Wright | Running | Development Board | Development | Tom Bridgman | Keith Reynolds | Heaton Design & Engineering | Tom Bridgman | Jonathan Wright | Listed building consent and planning for the 30's Extension has been obtained. ODS have now been instructed to prepare for works on site. | On Budget | Awaiting new programme | Low | Low | Lack of fire fighting cover for 30's Extension. | Preparations for works on site. | 5. Delivery | Start on site. | 44489 | 44681 | 37282 | 0 | 0 | 0 | 141473 | 141473 | 95457.35 | 141473 | 0 | N/A - On Budget | The budgets and spends are not up to date. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Correct budget figures. | 0 | Yes | 0 | Heaton Design & Engineering | ODS | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 10:04 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0138 | Enabling Works for Decarbanisation Project | JW | Corporate Property | B0138 | Enabling Works for Decarbanisation Project | Package of enabling works required to facilitate the decarbonisation project, consisting of both repair of the existing M&E plant where compatible, and upgrade of plant where compatibility would not be facilitated by repair. | Project - Other | Oni Mazanzi | Running | Asset Review | Development | Tom Bridgman | Oni Mazanzi | Faithful & Gould | Jane Winfield | omazanzi@oxford.gov.uk | 0 | On Budget | On Schedule | Medium | Medium | 0 | 0 | 3. Design & Technical Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3066000 | 3066000 | 1181853.98 | 3066000 | 0 | N/A - On Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-19 12:15 | [54 empty] | N |  | N | N | N | N | Y | Y | N | Y | Y |  | N | bar: 1 to 52
B0100 | Gloucester Green Car Park Ventilation (H&S) | JW | Corporate Property | B0100 | Gloucester Green Car Park Ventilation (H&S) | Upgrade of the ventilation system | Project - Compliance | Jonathan Wright | Running | Development Board | Development | Tom Bridgman | Keith Reynolds | Kieran Gibbons (Heaton Design) | Jane Winfield | Jonathan Wright | ODS are now pursuing a price from an alternative main sub-contractor. Computer modelling and site survey being carried out by alternative main sub-contractor to enable fixed price. | On Budget | Over Schedule | Medium | Low | Awaiting fixed price from alternative main sub-contractor. | ODS and sub-contractor mobilisation. | 5. Delivery | Awaiting re-pricing and revised program. | 0 | 44708 | 74979 | 262123 | 0 | 0 | 262123 | 0 | -14590 | 262123 | 262123 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Working being accelerated in order to spend SALIX funded element given spending deadline of 31 March | 262123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Appointed. | Heaton Design & Engineering | ODS | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-21 17:57 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
F7011 | Headington Environmental Improvements | JW | Corporate Property | F7011 | Headington Environmental Improvements | s106 funded schemes | Project - Other | Jonathan Wright | Running Slowly | Development Board | Development | Tom Bridgman | James Axford | 0 | - | Jonathan Wright | A Stakeholder meeting is being held on 21/01/2022 to finalise the design for planters, cycle racks, shrubs and trees in various locations in Headington. ODS will provide revised costs for the final design and work in planned to start on site at the end of January. | 0 | 0 | Low | 0 | The project forecast dates from ODS require more consideration as delays have led to further issues on site. | 0 | 5. Delivery | Installation of Planters, Cycle Racks and Trees - 01/31/22 | 44592 | 0 | 29629 | 30781 | 0 | 0 | 30781 | 0 | 0 | 30781 | 30781 | N/A - On Budget | 0 | 0 | 0 | 0 | -30781 | 0 | 0 | -30781 | 0 | 0 | Yes | 0 | Oxford City Council | 0 | 0 | 0 | jaxford@oxford.gov.uk | 2022-01-17 18:16 | [54 empty] | N |  | Y | Y | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0084 | Jericho Community Centre | JW | Corporate Property | B0084 | Jericho Community Centre | Council funding to support a community project | Other Capital Spend | Hagan Lewisman | Paused | Development Board | Communities and Customers | Stephen Gabriel | Hagan Lewisman | - | Tom Bridgman | Hagan Lewisman | Awaiting DB instruction to proceed with the project. | Budget to be agreed | Awaiting new programme | Low | Low | Project spend is identified in the current financial year, but project brief is yet to be received. SC will liaise with Team Leader to ascertain project commitments. | Covid 19 pandemic related delay and costs. | 4. Pipeline | Not applicable, no instruction to proceed. | 44651 | 0 | 200000 | 195000 | 0 | 0 | 200000 | 5000 | 6276 | 0 | -5000 | Slippage (Underspend in 21/22 - slip budget back) | 0 | 0 | 0 | 0 | -195000 | 0 | 0 | -195000 | N:A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0104 | Old Gas Works Bridges | JW | Corporate Property | B0104 | Old Gas Works Bridges | Repairs and maintenance | Project - Compliance | James Axford | Running | Development Board | Development | Tom Bridgman | James Axford | County | Stephen Clarke | James Axford | Gasworks Pipe Bridge - Refurbishment Oxfordshire County Council (the technical approval authority) have provided their intial comments on the AIP (Approval in principle). Stantec have reviewed these comments and will be responding with an updated AIP this week. Solar Stud lighting has been installed throughout the Gasworks Railway Bridge diversion route by ODS and additional lighting in River Gardens and towards Folly bridge is being considered. | On Budget | On Schedule | Low | Low | Key risks; If Oxfordshire County Council do not approve Stantec's design then we will have to review our options on the bridge. | 0 | 2. Feasibility | Approval in principle - January | 0 | 0 | 0 | 0 | 0 | 0 | 194911 | 194911 | 126284.09 | 194911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unsure | 0 | Stantec | 0 | 0 | TRUE | jaxford@oxford.gov.uk | 2022-01-17 18:11 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0124 | Port Meadow Moorings | JW | Corporate Property | B0124 | Port Meadow Moorings | Health & Safety review and options appraisal. | Project - Development | Carri Unwin | Completed | Development Board | Development | Tom Bridgman | Carri Uniwn | 0 | Jane Winefield | Carri Unwin | Following Carris investigations of existing lease terms; condition of moorings; views of other boaters not mediated by Bossoms; procurement concerns; and nature and scale of the package of urgent safety/investment/associated upgrade work required and desirable by all parties; ASG has concluded that the project should go back to Property to take forward the immediate works required before a wider review of future options is begun. | Completed | Completed | N/A | N/A | N/a | N/a | 1. Idea | n/a | 44361 | 44439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | Forecast Underspend at end of project | Development aspect of project paused | Not defined as yet | Not defined as yet | Not defined as yet | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | Nothing | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 12:43 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0117 | Regeneration Property Purchase | JW | Corporate Property | B0117 | Regeneration Property Purchase | Budget reflects desire to de-risk the existing portfolio, allowing the Council to be competitive if an attractive opportunity becomes available. Provides greater flexibility for the Council to address required regeneration post COVID 19 with its own property. | Other Capital Spend | Jane Winfield | Running | Development Board | Development | Tom Bridgman | 0 | 0 | Tom Bridgman | Jane Winfield | One only opportunity has come forward for consideration, which has been broadly approved by Investment Committee subject to more work on income flows, Councillor Turner yet to be fully updated. Demand for property has increased during 2021 and prices are increasing. Options remain limited. | Budget to be agreed | Awaiting new programme | Medium | High | 0 | 0 | 1. Idea | Still on target to complete a purchase during current financial year | 44651 | 0 | 20000000 | 20000000 | 0 | 0 | 20000000 | 0 | 0 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | No longer on target to complete a purchase in 21/22 | 0 | 0 | 0 | -20000000 | 0 | 0 | -20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 12:43 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0129 | Town Hall Options | JW | Corporate Property | B0129 | Town Hall Options | Undertaking option studies to be completed for underused spaces within the Town Hall, SAC and adjacent retail units. Work is focused on three work streams - 1) OCC Business Requirements 2) Customer Experience Requirements 3) Commercial Opportunities | Project - Development | Carri Unwin | Running | Development Board | Development | Tom Bridgman | Carri Unwin | 0 | Jane Winfield | Carri Unwin | The Architects have produced their Report to RIBA Stage 0 looking at the feasibility of future use of the Town Hall in order to best maximise income and protect the long term future of this important Council and heritage asset. The Report has been reviewed. The PM is now working with key stakeholders to provide a Brief for the Architects to do the next RIBA stages of work on a Phase 1 work package that will include creating usable office space in part of the basement, ground floor, and part of some upper floors of the Town Hall. This office space can be separately accessed off Blue Boar St, and flexibly used in different proportions, either by the Council as staff offices, or rented out to other organisations. All as office space requirements are refined or changed over the coming months and years, as SAC is partially rented out. | On Budget | On Schedule | Low | Low | Undefined project brief - mitigation is to undertake a review of the current project brief inline with the SAC strategy, and scope of a realistic and cost efficient work package based on a optimal cost : potential income ratio. . Refined the current brief to omit unnecessary spaces and a reduced consultant team. | An additional funding bid to the Development Review Group for the Architects to progress the next Work Stages is to be made. | 2. Feasibility | March 2022: Submit request for additional feasibility to DRG and then Development Board | 44469 | 45016 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 62257 | 56000 | 6000 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Refinement of brief based on the updated OCC Business Model and estate rationalisation requirements. Bid for additional funding for next stages to be requested. | 80000 | 0 | 0 | 80000 | 0 | 0 | 80000 | None | 0 | 0 | 0 | N:A this is a feasibility desktop exercise, the PD will be appointed in the next stage. | N:A | 0 | TRUE | cunwin@oxford.gov.uk | 2022-01-20 09:58 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0139 | SAC Project | JW | Corporate Property | B0139 | SAC Project | 0 | Project - Development | Lisa Smith | Running | Development Review Group | Development | Tom Bridgman | 0 | 0 | Jane Winfield | Lisa Smith | It has been identified what works need to be carried out to get SAC into a position to let the grd and 1st floors. These works are currently being reviewed to determine what is necessary and what can be achieved to meet the June 22 deadline. Architectural appointment it to happen ASAP, to enable design package completion and for local authority applications to be made. ICT and M&E works and designs are currebtly being reviewed and appraised. ODS have been engaged with, to carry out communal / M&E works to the building. Following production of design documents, ODS are to price works to Grd and 1st floor let-able areas, providing OCC with commercially costed figure’s that will formulate the basis of any Capital Contribution for new tenants taking over the spaces. The agents, Cartar Jonas have been instructed to formally advertise the space, draft brochures are being put together for review. | Budget to be agreed | On Schedule with Risks | Medium | Medium | Delayed completion leading to delays with tenant occupation - Regular programme and risk review to de-risk project as it progresses. Close liaison with design team, OCC departments and ODS. Customer Services relocation to County Library - Space identified with Town Hall and LBC applications made to rehouse if needed. | 0 | 2. Feasibility | Budget estimate cost Feb 2022 | 0 | 44742 | 0 | 0 | 0 | 0 | 100000 | 100000 | 2970 | 100000 | 0 | N/A - On Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | lsmith@oxford.gov.uk | 2022-01-17 11:17 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
F7007 | Woodfarm / Headington (Headington Community Centre) | JW | Corporate Property | F7007 | Woodfarm / Headington (Headington Community Centre) | s106 funded schemes | Project - Other | Jonathan Wright | Completed | Development Board | Communities and Customers | Stephen Gabriel | Katharine Gould | Ian Bridge Surveyors | Adrian Arnold | Jonathan Wright | Work completed. | On Budget | Completed | Low | Low | 0 | Works completed. Additional budget from B2003 / B7044 | 3. Design & Technical Specification | Work completed | 44806 | 44470 | 8000 | 0 | 0 | 0 | 16397 | 16397 | 2351.75 | 16397 | 0 | N/A - On Budget | Note that £16,397 is the Section 106 monies. All costs incurred to date have all been set against B2003/B7044. The PO has been raised against B2003/B7044. The Section 106 monies need to be transferred to B2003/B7044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None | N/A | Yes | ODS have been advised that works need to be undertaken in August 2021 | Ian Bridge Surveyors | Oxford Direct Services | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
E3563 | Clean Bus Technology Grants | MT | Environmental Sustainability | E3563 | Clean Bus Technology Grants | Top up grant fund | Other Capital Spend | Amanda Ford | Running Slowly | Development Board | Transition | Caroline Green | Amanda Ford | 0 | Mish Tullar | Amanda Ford | Update from OBC Payment made of £212K June 2021. Ongoing problems with the retrofitted buses The latest update is that the replacement controllers were fitted to all three of the buses on 16/07, following which road testing re-commenced on 19/07. Two further issues have been identified: 1) The air compressors now fitted to the vehicle run continuously, creating an excessive drain on the battery and reducing range (as noted in my email below). There should be an air pressure switch which turns them off once sufficient air build up has taken place. We have been advised that to do this requires a software update to the compressors which Magtec have now written, as well as an additional component which is due to be delivered on 11/08. 2) We are experiencing an issue whereby the chassis batteries discharge overnight while the main vehicle battery is being charged, resulting in breakdowns. The Magtec head of software has investigated this and concluded that the charging rate from the vehicle battery to the chassis battery, through the DC / DC converter requires a software update to charge at 28.8V rather than 27V, which is causing the current gradual discharge issue. The software for this is currently being written and Magtec are targeting visiting the vehicles on 16/08 to install these software updates, as well as the compressor system upgrades required. This means that, all being well we should be able to re-start road testing in week commencing 16/08. All being well we should then be able to get the buses into service soon after that... but let's see how things go. Update from Stagecoach received 17th August 20 out of 21 vehicles now retrofitted. Stagecoach are looking to resolve final but by swapping one from elsewhere into this fleet so it can be retrofitted according to the terms of the grant requirements. No further update ( Sept 9th 2021) since the one above No further update ( October 13th 2021) since the one above No further update ( November 8th 2021) since the one above Update 10 January 2022 Stagecoach retrofits all completed and money paid across £178,290 Oxford Bus Company Latest update is as follows: Vehicle #1 entered our service fleet on 27 November and managed to successfully complete several part days of in service operation before suffering a chassis fault. This requires welding work to repair, and we are awaiting attendance from Magtec to decommission and subsequently re-commission the electric drive system, at a cost of £1,500 to allow us to complete this welding. Once done we envisage this vehicle will return to the in-service fleet once again. Vehicle #2 is awaiting a footbrake valve which Magtec have advised us is imminent. Once supplied this vehicle should be ready for testing. Vehicle #3 is still awaiting parts for the modification to the compressor air pressure switch which I advised you about back in September. This modification has been done successfully to the other two buses, but this one is outstanding currently. So we have made progress, but still a lot slower than we would like to see. The response times from Magtec as a supplier continue to be very slow and they continue to need a lot of chasing. We are targeting having the three vehicles tested and ready for regular everyday service by March 2022. At the current time we have advised Magtec that we will not be proceeding with any further bus conversions until the first three vehicles have demonstrated a sustained period of reliable operation, and have formally cancelled the orders for buses 4 and 5. | On Budget | Over Schedule | Low | Low | Risk Consequence Countermeasure RAG Status Comment Commitment of bus operators to retrofit buses Failure to identify suitable buses for retrofit We have already worked closely with operators in our local authority area to identify buses which they have committed for retrofit if successful in our grant application Legal agreements signed with operators Lack of suitable Accredited Technology Inability to identify suitable Accredited Technology available to complete the project We have spoken to a range of technology providers of whom only one is fully accredited at this stage. However, we are assured by the remaining providers that they are either in the process of accreditation already or will shortly apply to become accredited. Technology procured and orders placed Inability of technology provider to deliver within the required project timeline Dependent on the final number of accredited providers there is a risk that technology providers will have a significant amount of orders which they might be unable to fulfil within the required project timeline. We will require evidence of ability to deliver within project timeline as a requirement of our procurement process. MagTech as above | Some progress from OBC see update above. Retrofits happening, but slowly. Delay due to C19 having considerable impact on programme. Now need to check reliability before moving to final 2 buses. Stagecoach are commencing the last stages of the retrofitting - there has been a change of personnel but new project manager at Stagecoach has updated me " there were some further design issues, then some supplier delivery delays and installation is taking longer than thought it would. Aiming for completion end of August although this was not achieved or still waiting confirmation - chase email sent 8 Sept 2021 See notes above | 9. Other Capital Spend | March 2022 tbc depends upon the performance of the retrofitted buses as to whether OBC will proceed with buses 4 & 5 | 0 | 44651 | 0 | 0 | 0 | 0 | 564350 | 564350 | 390290 | 564350 | 0 | N/A - On Budget | N/A | N/A | 0 | 0 | #INVALID OPERATION | 0 | 0 | #INVALID OPERATION | 0 | None. Significant NOx reductions however | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | N | bar: 1 to 52
E3565 | Decarbonisation Fund (OCC Element) | MT | Environmental Sustainability | E3565 | Decarbonisation Fund (OCC Element) | OCC has been awarded £10.9m under the Public Sector Decarbonisation Scheme (PSDS). Includes £1,636,736.00 for heat pumps and solar at Hinksey Pool and £9,286,813 for solar farm investment and heat pumps at five of OCC’s operational buildings | Project - Development | Onsmus Mazanzi | Running | Development Board | Transition | Caroline Green | Onsmus Mazanzi | Faithful and Gould | Mish Tullar | omazanzi@oxford.gov.uk | -Negotiataions with Fusion on compensation claim still in progress. - Planning application was submitted 13/10/2021. Payment made via internal transfer. - Two heat pumps for Rosshill and Ice Rink delivered to the Contractors premises. OCC to sell on the pumps if buyer is found. Cabridge Council nolonger inetersted in the pump. - Mannufacturer accepted for the ASHP to be returned at 35% recharge. -Works ( tree removal and Excavations) at Hinksey pool to started 16/11/21 in parrellel with the planning application. - Contract with WD signed and saeled | On Budget | On Schedule | Low | Low | -SSEN completion of Hinksey Substationworks may delay beyond 31 March 2022 and continous engagement with SSEN in progress. - Planning application being denied. Continued engagement with Planners and consultees has taken place and in progress. | -Costs - costs have come higher than anticipated. F&G currently looking at figures in detail and challenging WD where necessary. -Possidble SSEN further costs -Substation to be a GRP thefroe under GPDO - Approval of additional costs | 1. Idea | 7 Decemeber- Planning Permission | 44469 | 44651 | 7538547 | 0 | 0 | 0 | 7527297 | 7527297 | 3297475.8 | 7527297 | 0 | N/A - On Budget | 0 | £10.9million | 0 | 0 | #INVALID OPERATION | 0 | 0 | #INVALID OPERATION | Explore further installation PVs on Ferry and Barton Leisure Centre | The projects will deliver two key benefits for the City Council: a) energy bill savings of up to £440/year (rough estimate with more detail to be provided at the next stage and b) carbon emissions reduction of c.1,570tCO2 each year which is equivalent to 3 years of carbon reduction required by the CMP. | Possible | 0 | F&G appointed as Principal Designer (PD) | Willmott Dixon appointed as Principal Contractor | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | Y | Y | Y | Y | N | Y | N |  | Y | bar: 1 to 52
E3566 | Decarbonisation Fund (Solar Farm Investment) | MT | Environmental Sustainability | E3566 | Decarbonisation Fund (Solar Farm Investment) | OCC has been awarded £10.9m under the Public Sector Decarbonisation Scheme (PSDS). Includes £1,636,736.00 for heat pumps and solar at Hinksey Pool and £9,286,813 for solar farm investment and heat pumps at five of OCC’s operational buildings | Other Capital Spend | Onsmus Mazanzi | Running | Development Board | 0 | 0 | Onsmus Mazanzi | Faithful and Gould | Mish Tullar | omazanzi@oxford.gov.uk | We are still waiting confirmation and finalisation loan agreement from OCC legal. The amount of the loan remains to be re-confirmed following reductions in the amounts available to the Council. Possible Salix loan £2,054,652 Council Loan £2m total £4,055 million. | On Budget | Awaiting new programme | Medium | Medium | Delay in the finalisation of the loan agreement | Loan Contract agreement with LCH | 1. Idea | Cabinet report 10 Novemeber 2021 seeking approval for the payment for the 1 December 2021 processing | 44469 | 44651 | 3385000 | 0 | 0 | 0 | 3385000 | 3385000 | 0 | 3385000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Removal of Ross Hill and Ice Rink from the programme | 2054000 | 0 | 0 | 2054000 | 0 | 0 | 2054000 | Follow up with Salix on our proposal and agree heads of terms. | 0 | 0 | 0 | N/A | LCH | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-20 16:06 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
ES21 | Energy SuperHub Oxford | MT | Environmental Sustainability | ES21 | Energy SuperHub Oxford | Innovate grant funded project, supporting decarbonisation of the grid, electrification of vehicles, creation of an EV charging Superhub at Redbridge P&R and Hackney taxi – electric Try b4 you Buy Scheme to break down barriers to EV adoption | Project - Development | Tina Mould | Running | Development Board | Development Board | Caroline Green | Tina Mould | Pivot Power | Mish Tullar | Tina Mould | Construction has started, Solar Canopy & Pivot substation almost completed. Remaining design work on the shared compound area needs to be completed promptly. Good relations & communication between all parties. ODS EV fleet all ordered and delivered. Taxi Try b4 you Buy re-starting post Covid. £5k grants for Hackney Trade have been well taken up by the trade. 6 x additional EV black cabs taxi's on the road | On Budget | Over Schedule | High | High | OCC have appointed an overarching CDM advisor/PD to support with CDM co-ordination across site and the co-ordination of multiple contractors. The shared compound design is progressing. Fastned will undertake the civils design and construction works on behalf of Fastned, Tesla and OCC - as this can only be done by one contractor. Contracting with Fastned needs to be done via the simplest methodology and should be concluded by end of first week of Feb. An outline methodology has been sent to Fastned's legal team to check through. | Tesla contract to be signed and returned - action for Tesla Gamma Redbridge contract to be finalised - in progress. Final design of compound to be completed and construction progressed - contracting methodology needs to be agreed . If this hits any hurdles we will need some support from director level to unblock. | 5. Delivery | Fastned compound construction contract agreed Construction able to start | 45016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Please see above | 0 | Possible | 0 | Each Stakeholder has their own design, OCC are taking an overarching co-ordination role | Each Stakeholder has their Contractor | 0 | TRUE | tmould@oxford.gov.uk | 2022-01-21 17:22 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
E3558 | O-GULO | MT | Environmental Sustainability | E3558 | O-GULO | Trialling and Delivering Onstreet charging solutions, at the right locations and for an affordable price, to enable Oxford Residents without access to offstreet parking to transition to Ultra Low Emission Vehicles and improve Air Quality and reduce Carbon Emissions in Oxford. | Project - Other | Vikki Robins | Paused | 0 | 0 | 0 | Vikki Robins | 0 | Rose Dickenson | Vikki Robins | >Project remains on Pause. >EV Strategy work will inform phase 2 scope, stakeholder engagement and data gathering stage in progress. > Feasibility for provision of additional enforced EV bays on the existing estate in progress, to improve access to local EV users. > RAW contract novation in progress, ongoing issues in regard to existing legacy charging estate due to lack of parts, labour shortage being managed. Project restart dependent on EV Strategy outputs. Completion date TBC. | On Budget with slippage | Awaiting new programme | High | High | OGP2R035 Lack of onward CPNO with Franklin going into administration. Mitigation: Raw have now purchased the Franklin estate. Mobilisation conversations with RAW are in progress over the coming weeks. LiveEV SLA has been frustrated, and is now void. Legal support in place, awaiting close down report. OGP2R020 - budgeted revenue insufficient to cover cost for full number of committed conditioned chargers. Mitigation: Project on hold, pending new funding agreement with OZEV and alternative funding sources for bollard/lamp post chargers (ORCS or LEVI) | OGP1I022 - Vandalism on the 3 ( poss 4 chargers) - access due to agnostic cabinet key locks. Repairs scheduled, new locking system pursued. OGP2R036 - ORCS timeline very short - decision required in December, EST engagement in January, locations feasibility needs to be carried out within this window. Mitigation: ORCS bid not likely feasible on original timeline, but may be extended. Explore other options (LEVI) as safeguard. | 3. Design & Technical Specification | Full, formal P1 close down and handover into BAU, enabling P1 close down and transition. Initial recruitment for Contract Management facility unsuccessful, now scheduled for end of Jan. TRO proposals to add enforced EV bays to existing sites to improve access: feasibility in progress, project decision estimated Feb. | 44819 | 0 | 4545 | 500000 | 0 | 0 | 561150 | 61150 | 42999.36 | 61150 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Slippage is still likely, but likelihood decreasing. Multiple issues contributed the slippage from the previous financial year, incl. staff sickness, staff shortages in supporting teams, lack of capital only solutions available in the market, lack of BAU provision. | 0 | 0 | 0 | -500000 | 0 | 0 | -500000 | Support Rose Dickinson and ODS in producing and funding a BAU solution that allows handover of sites into professional and qualified contract management. Support Rose Dickinson in funding bid to cover ongoing revenue costs in line with EV charging targets in for the city. Facilitate development of commercialisation strategy at heads of department level between Env Sus and Procurement to maximise commercial and revenue generating opportunities deriving from the first dynamic purchasing system for EV charging in the UK. | Not quantifiable until total number of delivered chargers is established. | Yes | As per discussion at transport steering board | N/A - P2 not procured | N/A - P2 not procured | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-17 09:03 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | Y | N |  | N | bar: 1 to 52
E3557 | OFAS -additional costs | MT | Environmental Sustainability | E3557 | OFAS -additional costs | Additional funding for OFAS scheme | Other Capital Spend | Tina Mould | Running | Development Board | Transition | Caroline Green | Tina Mould | 0 | Mish Tullar | Tina Mould | Project pace increasing. Planning permission will be applied for this year, and CPO shortly after. This will require support from the following OCC departments: Planning Property Legal | 0 | On Schedule | High | Medium | Risk 1. Project Risks- Gaining Planning permission and CPO Enquiry Mitigation for these is being managed by the EA (OCC support on Project Board and Sponsoring Group) Risk 2. OCC Risk- overlap of OFAS with OCC plans for Seacourt and Redbridge P&R's Mitigation - Open dialogue & sharing of information and timetables for OFAS and OCC plans for Seacourt & Redbridge P&R. Risk 3. OCC agreed a contribution of kind of up to £1m, including internal staff resource as a key stakeholder/contribution to the project 4-5 years ago. The length of time the project has taken and changes in staff, alongside alongside post covid impacts on Legal and Property resource mean that there is insufficient internal resource to do this work. Peter Geach joining legal has been a major support to the project. Property resources have also now been formalised. The EA have been sent hourly and day rates for staff. We are just waiting for their approval. OCC is a committed partner to the scheme. | Kennington Bridge need to be fully funded, to allow OFAS to progress. Planning Permission required for OFAS. Highways England still not supporting scheme, until traffic management solution found for Hinksey junctions. Working with EA to establish exact resource requirements needed by OCC. Budget bid for staff resource costs to be covered has been made to EA. | 9. Other Capital Spend | Planning Submission - Oct '21, delayed | 2030 | 0 | 0 | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | £250K | -250000 | 0 | #INVALID OPERATION | #INVALID OPERATION | see above | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
E3560 | T-GULO | MT | Environmental Sustainability | E3560 | T-GULO | Delivering minium of 16 rapid charge points for taxis. | Project - Other | Sarah Hassenpflug | Running | 0 | 0 | 0 | Sarah Hassenpflug | 0 | Rose Dickenson | shassenpflug@oxford.gov.uk | In deployment. Rewley Rd leasing term issue unresolved, further delay anticipated with slippage into FY2022/23 now very likely. Mitigation paper complete and communicated, emergency board meeting scheduled 28th of January. Civils and unit installations complete in Headington Car Park and Blackbird Leys Leisure Centre, but DNO connection delayed, Meter adoption scheduled January 2022. Manzil Way and Keble Rd well used. Back office transition from Hubeleon to Greenflux causing some new issues. Communications planned this week. Headington and Blackbird Leys and Old Greyfriar's fully commissioned early February 22. | On Budget with slippage | Over Schedule | Medium | Medium | TGP2R017 -External legal support required due to lack of internal staff resource. Risk of cost escalation. Mitigation: Property to model new leases on ESO and existing commercial contract, minimise legal input requirement. If cost exceeds contingency, review internal resource access. | TGP2I021 - Rewley Rd - Fire Service unexpectedly announced plans to move from site, insufficient lease length for the business case to stack up. Mitigation in progress: escalation to director level to progress negotiations, compensation offer for EB Charging Ltd under exploration, to enable lease options at <than commercial terms. Feasibility to install additional chargers at existing sites in Old Greyfriars and Keble Rd to replace Rewley site in progress. Engagement with regeneration officers to explore longer-term opportunities for replacement of Rewley Rd, if the site is lost early. Issue impact: Likely overspill of commissioning into FY 22/23. TGP2I022 - DNO connection delays due to incorrect plans being issued to the ICP by the DNO. Mitigation activity in progress. New meter connection scheduled for 18th and 19th January. On track for OG and BL, further delay to end of Jan possible for Headington. | 3. Design & Technical Specification | Headington and Blackbird Leys and Old Greyfriar's fully commissioned February. Mitigation decision Rewley Rd. | 44151 | 44742 | 0 | 0 | 0 | 0 | 203220 | 203220 | 1800 | 203220 | 0 | N/A - On Budget | Slippage now likely, due to Rewley Rd lease issue. Detail tbc pending board decision. | 177472 | 0 | 0 | 177472 | 0 | 0 | 177472 | Support Rose Dickinson in determining a Contract Management solution for all our EV estates. Supporting the budget bid to fund this solution. | As per previously submitted entries. | Yes | ODS involvement in Contract Management pursued, contractor has asked ODS for quotes for highways works, bay lining. | EB Charging Ltd - Mark Stilwell | EB Charging Ltd - Mark Stilwell | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | Y | N |  | N | bar: 1 to 52
E3567 | Town Hall Lighting Upgrade (SALIX) | MT | Environmental Sustainability | E3567 | Town Hall Lighting Upgrade (SALIX) | 0 | Project - Other | Keith Reynolds | Running | Asset Review | 0 | 0 | 0 | 0 | 0 | Keith Reynolds | Listed Building Consent has been granted. LBC Consent and approvals still to be firmed up. This project is in 4 phases, phase 1 is almost complete, awaiting ceiling works in Room G23. Phase 2 is complete. Phases 3 and 4 are on order and awaiting lighting delivery. | On Budget | On Schedule | Medium | Medium | Listed Building Consent has been granted conditions have been addressed. | Phase 3&4 has started on site but awaiting further materials. | 3. Design & Technical Specification | See Key Issues to Address. | 0 | 44651 | 0 | 0 | 0 | 0 | 90000 | 90000 | 0 | 90000 | 0 | N/A - On Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OCC | ODS | 0 | TRUE | kreynolds@oxford.gov.uk | 2022-01-17 09:51 | [54 empty] | Y |  | N | Y | N | N | N | N | N | N | Y |  | N | bar: 1 to 52
B0127 | ZEZ Phase 1 Feasibility | MT | Environmental Sustainability | B0127 | ZEZ Phase 1 Feasibility | 0 | Project - Development | Amanda Ford | Running | 0 | 0 | 0 | 0 | 0 | 0 | Amanda Ford | Update September 2021 This piece of work is being taken off pause and the feasability work is being restarted as such City Council will raising a PO to transfer of remaining money once confirmation of the work starting has been received from County and the work commissioned. No further update ( 13 October 2021) No further update 8 November 2021 No further update 13 December 2021 10 January 2022 - draft timetable emerging SOBC now out to tender | On Budget | Awaiting new programme | Low | Low | 0 | 0 | 1. Idea | Unclear awaiting timetable of tasks from the County Council | 44561 | 45291 | - | 0 | 0 | 0 | 141000 | 141000 | 0 | 141000 | 0 | 0 | explained above | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | aford@oxford.gov.uk | 2022-01-10 16:19 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3067 | Paris Payment System, Replacement / PCI DSS | NK | Financial Services | C3067 | Paris Payment System, Replacement / PCI DSS | To replace the Paris Payments system which goes out of support in December 2019 and to ensure the compliance of the PCI – DSS system, as per audit recommendations. | Project - ICT | Tim Martin | Running | Operational Delivery Group | Communities and Customers | Stephen Gabriel | Tim Martin | 0 | Nigel Kennedy | Tim Martin | This programme of works is separated into 3 strands. PCI DSS Policy being revised/updated. Once completed/adopted, Self Assessment Questionnaires will be completed. CivicaPay CivicaPay Phase 1 (Payments Only) went live Monday 10/01/2022. Some early user-related issues being managed. Phase 2 needs to be planned but this cannot begin until April 2022 for a potential completion July 2022 pending other project and capacity constraints MidCall telephone payments Go Live completed 10/01/2022. Contact Centre unable to Go Live with inbound payments as the Council's use of Mitel and Netcall break the functionality. Awaiting results of Netcall testing a solution. | Over Budget | Awaiting new programme | Medium | Low | Go Live issues and mitigations are relatively small and are manageable through Council resource. Lagan may be withdrawn, and so the integration with CivicaPay may cease to work. Alternate processing method being specified. Netcall telephone solution has been deferred and an alternate approach is to be taken with the Contact Centre. | Additional integration for Parking Fines required. Quotations being sought. Integration myst be completed by FCA deadline of 14/03/2022. Telephony configuration will result in an alternate approach being taken with the Contact Centre. Further costs arising (integrations, additional phone lines) | 5. Delivery | Phase 2 - Planning April 2022 conclude end July 2022 (estimate) | 44530 | 44771 | 17924 | 0 | 0 | 0 | 102684 | 102684 | 980 | 125274 | 22590 | Forecast Overspend at end of project | We currently have a shortfall of around £23k against the £185,675 budget. This is based on the committed capital figure of £155,474 plus the costs incurred for Niall Barker’s (original project manager) time at c£54k that’s coded to the budget. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | No | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | N | N |  | N | bar: 1 to 52
B0074 | R & D Feasibility Fund | NK | Financial Services | B0074 | R & D Feasibility Fund | Feasibility Fund (Revenue) for use in the development of projects. | Project - Development | Anna Winship | 0 | Development Board | Development | Tom Bridgman | N/A | N/A | Nigel Kennedy | James Marriott | 21/22 Feasibility pot potentially overcommitted, with just £67k remaining following approved allocations to the Ice Rink and Roken House. Potential commitments yet to be allocated include Town Hall options, Odeon, and further feasibility to get Cemetery Project the planning stage. important to note that the 2022/23 budget only has £150k remaining following advance to 2021/22. | 0 | 0 | Low | 0 | Funding is insufficient for the number of schemes requiring feasibility funding. | * 21/22 pot now allocated in full. * Need to identify suitable CIL feasibility schemes or remove budget from programme | 2. Feasibility | 0 | 0 | 0 | 325180 | 6862 | 400000 | 400000 | 829324 | 22462 | 6124 | 22462 | 0 | 0 | 0 | 150000 | 400000 | 400000 | 143138 | 0 | 0 | 143138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 12:43 | [54 empty] | N |  | Y | Y | N | Y | N | N | N | N | N |  | N | bar: 1 to 52
C3078 | Revs and Bens System Replacement | NK | Financial Services | C3078 | Revs and Bens System Replacement | 0 | Project - ICT | Shaun Butler | Running | Development Board | Development | Stephen Gabriel | 0 | 0 | Nigel Kennedy | Shaun Butler | In live - working through snags to get to steady state. | On Budget | On Schedule | Medium | Low | Risk register available on request. | Snag list Year End Training Outstanding workload | 5. Delivery | Steady State 31/3/22 | 44469 | 0 | 245000 | 0 | 0 | 0 | 463737 | 463737 | 379005.28 | 463737 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes - Tanya Bandekar updated on 18/01/22 | TRUE | rhaverson@oxford.gov.uk | 2022-01-18 15:30 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5023 | OxWED Loans | NK | Financial Services | #N/A | #N/A | #N/A | #N/A | Bill Lewis | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | N | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
M5036 | Low Carbon Hub Loans | NK | Financial Services | #N/A | #N/A | #N/A | #N/A | Bill Lewis | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | N | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
N7051 | Acquisition of Additional Housing Units | SC | Housing Services - HRA | N7051 | Acquisition of Additional Housing Units | Purchase of additional housing (9 units) on a 'turn-key' basis from the developer (Cantay). | Other Capital Spend | Dave Scholes | Completed | 0 | Communities and Customers | Stephen Gabriel | Will McKay | 0 | Dave Scholes | Dave Scholes | Acquisition of 9 units (off-plan). Milestones and budget reprofiled (Summer 2020) but now on site and on track for completion by Sept 2021. 13 Aug Update: Handover achieved early on 31st July 21 (i.e. earlier in Qtr 2 than forecast). Budget to be reconciled at end Qtr 2 - only £25k retention to be left as required. | On Budget | Completed | Low | Low | Delay to construction. Mitigated by the employment of a Council clerk of works who make regular inspections and reports on issues and progress to the PM. | None, other than financial adjustments required to reflect the position of the project being on track to budget and time. Overall Project Spend: 20/21: £553,500 21/22: £3,018,000 22/23: £25,000 Total: £3,596,000 Budget: £3,645,000 (original budget £3.2m plus £445k from N7047) | 5. Delivery | Sept 21 handover - possibly being b/f to August 2021 | 44466 | 44408 | #INCORRECT ARGUMENT SET | 0 | 0 | 0 | 3256081 | 3256081 | 3204495.68 | 3231081 | -25000 | 0 | Final settlement and Financial adjustment expected to leave only £25k for 22/23. | 25000 | 0 | 0 | 25000 | 0 | 0 | 25000 | None | New Build - As per Building Regs | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-10 15:05 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N6385 | Adaptations for Disabled | SC | Housing Services - HRA | N6385 | Adaptations for Disabled | 0 | Other Capital Spend | Mark Smart | Running | Development Board | Assistant Chief Executive | Stephen Gabriel | - | ODS | Stephen Clarke | Mark Smart | Full spend anticipated, current overspend being addressed by ODS. | On Budget | On Schedule | Low | 0 | 0 | 0 | 9. Other Capital Spend | 0 | 0 | 0 | 704000 | 756000 | 810000 | 810000 | 3080000 | 704000 | 5463.83 | 704000 | 0 | 0 | 0 | 756000 | 810000 | 810000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5034 | Affordable housing (supply) | SC | Housing Services - GF | M5034 | Affordable housing (supply) | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Stephen Gabriel | Dave Scholes | 0 | Tom Bridgman | Dave Scholes | s106 top-up/ enabling grant. Funding is being committed to projects (c.£2.5m to match-fund additional OGD funding) but will only be spent on the completion of the units, in each scheme, so the budget requires profiling once agreed, with much for the 22/23 financial year. Oct 21 - To be re-profiled in response to changes to Oxon Growth Deal programme. | On Budget | On Schedule | Low | Low | 0 | Assembling information site by sites re scheme abnormals and costs/ benefits for approval by Head of Planning (expect all information to be available and complied by end Jun 21 now - delayed while new DSAs were run in Abovo. July 21 update - Report now assembled ready for meeting with HoS for Plg. Oct 21 - Two schemes (with full details) submitted to Head of Plg for decision (Total request: £594k + £320k = £914,000) | 9. Other Capital Spend | TBC | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Re-profiling into years when buy-backs expected to occur - based on current programme and expected completion dates | 914000 | 1086000 | 1000000 | -2086000 | 1086000 | 1000000 | 0 | None | 0 | 0 | 0 | n/a | n/a | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | Y | N | N | N |  | N | bar: 1 to 52
MD95 | Barton Howards | SC | Housing Development | MD95 | Barton Howards | Regeneration of the Howard housing at Barton | Project - Development | Steve Weitzel | Paused | Development Board | Development | Stephen Gabriel | Steve Weitzel | Currently N/A | Stephen Clarke | Steve Weitzel | The decision has been made to pause Phase 2. Initially it was agreed to proceed with Phase 1 as a Pilot. [Demolish 26 units 26 OCC owned and 6 RTB’s & Rebuild c60-70 new homes; current masterplan shows 63 home; 27 new Houses and 36 new flats. Initial estimates suggest we would require an initial capital expenditure of c£2.5m to assemble the land with a build cost of c£12.5m including fees and costs.] Alan Wylde prepared the viabilities, prior to his departure, for Barton Phase 1 assuming OCHL deliver it. It is still marginally viable, but, not in a way that OCHL would find acceptable in terms of the return. We are exploring alternative options for delivery. Planning pre-app meeting held 11/05. Speaking with SOHA who own land to south as this provides opportunities for more units which may improve viability. Structural surveys delayed over 8 months due to lack of available properties causing delay to scheme are still not complete. These surveys are critical to the evidence base for undertaking the project. Their delay causes delay to the whole project. Phase 1 schemes have been assessed by Arcadis to improve viability. Further surveys have been undertaken [Topographical & Arboricultural] It is important the structural and asbestos surveys are undertaken before returning to HSB. and DB. Subsequent discussions have centred on the possibility of returning the phase 1 pilot to OCHL to undertake and this decison is pending the completion of the survey and close out report. | On Budget | Awaiting new programme | High | High | Outcome of structural and asbestos surveys. Decision on whether to proceed and if so; through PMO or OCHL. | Viability of Phase 1 , as a pilot, has become key risk. Public consultation is likely to be difficult, as is the land assembly and associated CPO legal process. It is likely that OCC will require a development partner for the later Phases of the Barton redevelopment. This could be by either negotiation with OCHL or via a procurement and a Development Agreement. Funding through OCHL, may come from the Council although grant would be sought from Government either through MHCLG/Homes England programmes. The Build project may be undertaken in 2-5 phases, Phase 1 approximately 26 Homes demolished, c60 new build would require capital expenditure of c£2m to assemble the land with a build cost of c£12m. | 1. Idea | Undertake Structural survey when property is free and then take to HSB before going to DB. | 46843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69575 | 69575 | 0 | 0 | - | - | - | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | TBC following receipt of Strategic Outline Business Case | TBC. Early discussions have taken place with Energy Efficiency Projects Officer from Sustainable Development & Regulatory Services. | Unsure | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 16:33 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5025 | Barton Park - Purchase by Council (Phase 1 Affordable Housing at Barton Park) | SC | Housing Development | M5025 | Barton Park - Purchase by Council (Phase 1 Affordable Housing at Barton Park) | Purchase of properties | Other Capital Spend | David Watt | Running | Development Board | Assistant Chief Executive | Stephen Gabriel | David Watt | 0 | Stephen Clarke | David Watt | Number of properties to be acquired by OCH(I)L in 2021/22 will now be 22 and cost an estimated £3.093m. Purchase will be spread across October, November and December of 2021 as opposed to all happening in June as previously anticipated. | On Budget | On Schedule | Low | N/A | 0 | None | 9. Other Capital Spend | End of all defects periods in December 2021. Final retention payments in January 2022. | 44535 | 0 | 5736037 | 12738996 | 8250000 | 8300000 | 32381856 | 3092860 | 2045391.16 | 3541000 | 448140 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Updated forecast following the Oct21 BP re-fresh recently approved | 8455017 | 10750000 | 7600000 | -4283979 | 2500000 | -700000 | -2483979 | None | The homes are constructed to achieve the legacy Code for Sustainable Homes Standard, Level 4, which increases the energy efficiency levels above building regulations. | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 10:14 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7042 | Barton Regeneration | SC | Housing Services - HRA | N7042 | Barton Regeneration | Development projects | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Stephen Gabriel | Sue Briscoe | ODS | Stephen Clarke | Mark Smart | the only work is now the Fettiplace frontage works, an order is sat on P2P for £20k. This is the only work we are now carrying out in Barton this financial year. | Under Budget | Awaiting new programme | Low | Low | The main priorities have been actioned. | ODS to carry out the works. | 5. Delivery | ODS now on site, works to be completed by end December 2021. | 44499 | 44560 | 600000 | 0 | 0 | 0 | 628276.92 | 628276.92 | -1218.34 | 28276.92 | -600000 | Slippage (Underspend in 21/22 - slip budget back) | there is no further work to do in this locality | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Leave £25k for Fettiplace, ODS to confirm date of project works. Allow a budget for communal doors, which will be processed and actioned once quotes are in. | Sourcing local products were possible. Planting of trees and wildlife habitat to offset some of the carbon. | Yes | We have now agreed the works progression with ODS. | Sue Briscoe/TBC (still awaiting a technician) | OXFORD DIRECT SERVICES | 0 | TRUE | sbriscoe@oxford.gov.uk | 2021-12-15 14:55 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7058 | Bathrooms | SC | Housing Services - HRA | N7058 | Bathrooms | 0 | Rolling Programme | Mark Smart | Running | 0 | 0 | 0 | 0 | 0 | Stephen Clarke | Mark Smart | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. | Under Budget | On Schedule | Low | N/A | 0 | 0 | 8. Rolling Programme | 0 | 44286 | 0 | 907266 | 0 | 0 | 0 | 1184031 | 1184031 | 323616.07 | 907266 | -276765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7040 | Blackbird Leys Regeneration | SC | Housing Services - HRA | N7040 | Blackbird Leys Regeneration | Regeneration of Blackbird Leys including the Retail Centre, Community Centre and Knights Road to provide approximately 294 new homes, retail units and community centre. The regeneration is in partnership with Catalyst Housing. | Project - Development | Andrew Humpherson | Running | Development Board | Assistant Chief Executive | Tom Bridgman | Andrew Humpherson | N/A | Tom Bridgman | Roo Humpherson | Changes to 100% affordable housing agreed and viability confirmed by CHL to address planning risk and viability issues around First Homes. Draft planning proposals received and discussed at Pre-App. Proposed Knights Road masterplan to be revised to avoid the Nature Reserve. Viability reviewed by OCC consultant - no significant concerns. Comments raised with CHL. Gateway Two delayed to February/ March to accommodate changes to layouts. Leaders briefing required on receipt of final proposals from CHL - proposed for end Jan. Development Agreement with CHL now signed by CHL and wet copy issued to OCC solicitors to enable exchange. | On Budget with slippage | Over Schedule | Medium | Medium | CHL grant transferred to RCGF - to be confirmed by HE. HIF grant extension to be confirmed - report submitted awaiting comment and review by HE. Revised proposals to be reviewed with Members. Knights Road development to be re-planned at avoid building on a small section of the nature reserve. Planning review required. Workshop confirmed for 20th Jan. Bio-diversity proposals currently not compliant with planning policy. Further calculations require following changes to Knights Road layout. Negotiations with County Highways required to allow for increased tree provision. Costs of s106 and s278 agreements at risk of increased external demands. Viability budget increased by c.£100K in response. Further Councillors' briefing required prior to planning. State Aid funding subject to Legal Review. VP strategy and programme to be reviewed. Freeths appointed to support OCC Legal. Loss of CIL to Parish through conversion to 100% affordable housing to be addressed. Funding to be made available to support community proposals with Parish to be engaged in distributing funds (mechanism to be agreed). Comm's to be reviewed prior to planning submission. Purdah implications for planning submission date require urgent review | Key decision on 100% affordable housing alternate proposals required. Viability under review by CHL with decision expected this month by CHL and to be tabled to members in the New Year. Development Agreement to be signed, sealed by both CHL and OCC. Legal review required for VP including land appropriation, CPO, State Aid. Negotiation with HE for HIF funding programme to be prolonged to March 2024 in hand and including Catalyst. Planning proposals to be reviewed as part of Stage Two Gateway proposals. | 3. Design & Technical Specification | Revised planning proposals required. Planning statement required and OCC review. Development Agreement to be signed, sealed by both CHL and OCC. Legal review on-going for VP including land appropriation, CPO, State Aid. Negotiation with HE for HIF funding programme to be prolonged to March 2024 in hand and including Catalyst. Comm's to be reviewed prior to planning submission. | 46664 | 46861 | 209000 | 152000 | 3259000 | 296000 | 3980166 | 273166 | 40885.96 | 109716 | -163450 | Slippage (Underspend in 21/22 - slip budget back) | Catalyst prolongation of design and cost-planning and review of affordable housing proposals. | 324835 | 1504085 | 1676420 | 172835 | -1754915 | 1380420 | -201660 | Legal support including review of appropriation. Other Legal advice required for viability, CPO assistance. | Housing and Community Facilities to meet emerging Local Plan standards with further opportunities to improve standards to be investigated during Detailed Design. Catalyst has now appointed a sustainability specialist to take a holistic view of the development. CHL considering BBL as exemplar Zero Carbon development | Some | Community Centre and retail fit out and possible sub-contractor work packages | Catalyst Housing Limited | tba | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7059 | Boilers Only | SC | Housing Services - HRA | N7059 | Boilers Only | 0 | Rolling Programme | Mark Smart | Running | 0 | 0 | Tom Bridgman | Mark Smart | 0 | Stephen Clarke | Mark Smart | This is a delegated budget to ODS and is part of the ongoing Decent homes and compliance work required by OCC as a landlord. | On Budget | On Schedule | Low | Low | 0 | 0 | 5. Delivery | 0 | 44286 | 0 | 1512780 | 0 | 0 | 0 | 1596891 | 1596891 | 649551.56 | 1596891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7026 | Communal Areas | SC | Housing Services - HRA | N7026 | Communal Areas | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | Mark Smart | 0 | Stephen Clarke | Mark Smart | Ahead of schedule on FRA and on target for asbestos surveys. Additional resource gained from contractors to catch up on deficit. | Under Budget | Over Schedule | Low | 0 | COVID-19 has caused delays to our FRA schedule on communal areas. We were already well ahead of target for the year and have secured additional resource to catch up sufficiently and will still deliver. | 0 | 8. Rolling Programme | 0 | 0 | 0 | 198000 | 213000 | 229000 | 229000 | 1219889 | 548889 | 30159.57 | 548889 | 0 | 0 | 0 | 213000 | 229000 | 229000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N6387 | Controlled Entry | SC | Housing Services - HRA | N6387 | Controlled Entry | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running | 0 | Assistant Chief Executive | Tom Bridgman | Bill Chamberlain | Baydale Control Systems Contract Manager - Gerard Atherton | Stephen Clarke | Mark Smart | Baydale have provided a program for the identified 27 blocks, orders have been raised and on site from the 19 April 2021.Total raised orders for the controlled entry works £80,000. | On Budget | On Schedule | Medium | 0 | The key risks are the requirement to have competent engineer to respond, to date there as been no issues with call out and an additional engineer has been allocated by the contractor to cover OCC blocks. | Identification of defective older models for control entry systems will be a priority with the additional allocated funding. | 8. Rolling Programme | 0 | 0 | 0 | 312500 | 83000 | 87000 | 87000 | 628083.43 | 371083.43 | 164533.31 | 371083.43 | 0 | 0 | 0 | 83000 | 87000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N6389 | Damp-proof works (K&B) | SC | Housing Services - HRA | N6389 | Damp-proof works (K&B) | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | Chris Scott | ODS | Stephen Clarke | Mark Smart | A rolling programme where repairs are done as they come in. Covid has impacted this plus with pausing of Kitchen and Bathroom works. Although in December we felt that spend would increase as works to do upgrades, with the latest lockdown this has not happened. There has been an increase in the number of damp issues during autumn and winter months. | Under Budget | On Schedule | Low | 0 | Others also have access due to staff changes Previous staff using code no longer with occ Access issue resulting in lack of spending No work took place during the month of May Site inspections are now taking place ( June)and orders are now being raised Once lock down to property is eased work will then commence | 0 | 8. Rolling Programme | 0 | 0 | 0 | 119000 | 122000 | 137000 | 137000 | 540006 | 144006 | 63810 | 144006 | 0 | 0 | 0 | 122000 | 137000 | 137000 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N6434 | Doors and Windows | SC | Housing Services - HRA | N6434 | Doors and Windows | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | Gary Long | 0 | Stephen Clarke | Mark Smart | On site and Nationwide will deliver the current program of works. | On Budget | On Schedule | Low | Low | COVID-19 | Possible access issues with COVID-19 | 8. Rolling Programme | 0 | 44286 | 0 | 579200 | 500000 | 500000 | 500000 | 2103123.19 | 603123.19 | 389187.11 | 603123.19 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7050 | East Oxford (Housing Development) | SC | Housing Services - HRA | N7050 | East Oxford (Housing Development) | Combined with East Oxford Community Centre. This is the development of housing across two sites. | Project - Development | Dave Scholes | Running | Development Board | Communities and Customers | Tom Bridgman | Dave Scholes | 0 | Stephen Clarke | Dave Scholes | Planning consent (Ctte Jan 21). Conditions being met. Working with Arcadis to develop a delivery programme. Sept 21 - Agt on route to market (separate to community centre refurb) - Housing Devt now being mobilised. | On Budget | Awaiting new programme | N/A | N/A | Link to timely delivery of community centre project to free up housing sites. | Tender and Contract Award for housing devt across 2 sites | 3. Design & Technical Specification | Contract Award | 45016 | 0 | 3533000 | 9697353 | 0 | 0 | 10307353 | 610000 | 2940 | 610000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Expected SoS for resi-development is now May 2022 | 7067000 | 0 | 0 | -2630353 | 0 | 0 | -2630353 | 0 | The scheme is anticipated to include Air Source Heat Pumps complimented by carbon reducing technologies, such as good quality insulation, triple glazed windows, Mechanical Ventilation Heat Reduction (improved air tightness and high efficiency lighting. Energy modelling has indicated that fabric and systems energy efficiency measures, low carbon heating, as well as PV systems have the potential to make an improvement on Building Regulations Part L1A 2013 of 84%. | No | 0 | tbc | tbc | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | Y |  | N | bar: 1 to 52
N6395 | Electrics | SC | Housing Services - HRA | N6395 | Electrics | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Tom Bridgman | ODS | ODS - Steven Hainge | Stephen Clarke | Mark Smart | Delegated budget to ODS and is on target to deliver. | On Budget | On Schedule | Low | Medium | ODS ability to resource the increase in rewires to deal with number of unsatisfactory EICR certs. Back log spread over two years. | Resources and tenants allowing us access to do the works. | 8. Rolling Programme | 0 | 44286 | 0 | 625000 | 554920 | 653000 | 653000 | 3191391 | 1330471 | 382094.18 | 1330471 | 0 | 0 | 0 | 625000 | 653000 | 653000 | 70080 | 0 | 0 | 70080 | Monitor the program | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7033 | Energy Efficiency (Initiatives) | SC | Housing Services - HRA | N7033 | Energy Efficiency (Initiatives) | 0 | Rolling Programme | Mark Smart | 0 | 0 | Assistant Chief Executive | Tom Bridgman | TBC | 0 | TBC | Mark Smart | Budget is incorrect. £100k agreed to be rolled over in 2020/21 HOWEVER BUDGET IS NOW REQUIRED TO BE ROLLED BACK INTO CURRENT FINANCIAL YEAR - This is to aid the overspend on Fire Doors within the HRA. | On Budget | On Schedule | Low | 0 | 0 | 0 | 8. Rolling Programme | 0 | 0 | 0 | 1252200 | 2735000 | 2000000 | 2000000 | 7537786.04 | 802786.04 | 191661.54 | 802786.04 | 0 | 0 | 0 | 1985000 | 2000000 | 2000000 | -750000 | 0 | 0 | -750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:10 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7020 | Extensions & Major Adaptions | SC | Housing Services - HRA | N7020 | Extensions & Major Adaptions | Extensions & Major Adaptions | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Tom Bridgman | Gary Long | 0 | Stephen Clarke | Mark Smart | 3 Projects Completed and 2 projects on site and one on hold. There are further 4 schemes which are in feasibility and discussion with OT and residents, but these will be delivered 2021/22. | On Budget | On Schedule | Low | Low | Budget being compromised on number of properties being proposed, delays in planning and OT changes to specification. More properties and recommendation with insufficient budget to cover the works. | 0 | 8. Rolling Programme | 0 | 44286 | 0 | 265000 | 278000 | 290000 | 290000 | 1282672 | 424672 | 30636.24 | 424672 | 0 | 0 | 0 | 278000 | 290000 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7048 | Fire Doors | SC | Housing Services - HRA | N7048 | Fire Doors | Fire door replacement | Rolling Programme | Paul Worts | Running | Development Board | Assistant Chief Executive | Tom Bridgman | 0 | ODS / CLC | Stephen Clarke | Paul Worts | Total spend for at the end of March £ 18,295.15 Reduced spend due to stoppage of works. Budget will be carried forward and delivered in 21/22. | On Budget | On Schedule | Low | 0 | Risks to future expenditure will be through procurement and Building Control applications. | Additonal works required, confirmation of specification to new schemes and Blocks. | 8. Rolling Programme | 0 | 44286 | 0 | 530000 | 580000 | 580000 | 580000 | 2608979 | 868979 | 13465.66 | 868979 | 0 | 0 | 0 | 580000 | 580000 | 580000 | 0 | 0 | 0 | 0 | 0 | 0 | Some | With ODS undergoing assessment for BM Trada installation approval there will be scope to install the required specified doors. | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
B0108 | Floyds Row (Refurbishment) | SC | Housing Services - HRA | B0108 | Floyds Row (Refurbishment) | 2 Phases of Homeless Shelter and Assesment Hub Operated by St Mungos | Project - Development | Douglas Kerrigan | Completed | Development Board | Communities and Customers | Tom Bridgman | Douglas Kerrigan | Jessop and Cooke Architects | Dave Scholes | Doug Kerrigan | Project complete and formally handed over following Building Control sign off. Exploration of possible further works to allow usage of the building during covid restrictions completed and concluding that alterations were not feasible. | Over Budget | Over Schedule | Low | Low | 0 | Ascertain costings for additional works following recent appointment of Jessop and Cook | 6. Completed | 0 | 44228 | 0 | 41400 | 0 | 0 | 0 | 41400 | 41400 | -109919.37 | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sign off of additional repairs through GF | Full adherence to new Building Regs - refurb includes additional insulation, double glazing, and replacement boilers and air handling units, etc. Significant reduction in on-site car parking. | Yes | 0 | 0 | 0 | Yes - Update from Stephen Clarke on 18/01/22 | TRUE | rhaverson@oxford.gov.uk | 2022-01-20 15:44 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7032 | Great Estates Programme | SC | Housing Services - HRA | N7032 | Great Estates Programme | Development projects | Rolling Programme | Mark Smart | Paused | Development Board | Assistant Chief Executive | Tom Bridgman | Sue Briscoe | ODS | Stephen Clarke | Mark Smart | Great Estates projects now commencing for 2021/22. PRIORY ROAD - site in process of being handed over to Client LINNET CLOSE - commenced July - held up for reportable asbestos - on site at present, due to complete end Nov 2021 FIELD AVENUE - drawing with Planning- on target CROWBERRY RD - AT RISK ! - now abandoned for this year due to resourcing issues Client side. Carry forward of spend into 2022/23 requested. | On Budget with slippage | Over Schedule | High | High | Due to staffing issue we are not able to obtain the drawings and this has delayed our Crowberry Road project comms and put this project behind schedule which has resulted in this project being carried over into 2022. The prices have increased for materials and this has had a detrimental effect on what we can provide this year. We will need to carry over funds into 2022 to allow Crowberry Road to commence next financial year, subject to planning approval. | The main difficulties are still: DRAWINGS - no technical availability has been provided since March 2021. We are now 8 months behind schedule for works this year. Crowberry road has had to be abandoned and no doors or bin stores can be installed. We ARE AT RISK in 2022 and beyond if we do not have a technician in the Great Estates. This has been put forward to Management as a grave concern. | 5. Delivery | SEE SUMMARY PRIORY ROAD - COMPLETED LINNET CLOSE - COMPLETED FIELD AVENUE - IN PROGRESS CROWBERRY ROAD - ABANDONED UNTIL 2022 DUE TO LACK OF TECHNICAL RESOURCE. | 44546 | 0 | 1300000 | 1109000 | 1163000 | 1163000 | 4661437 | 1226437 | 233374.77 | 1226437 | 0 | Slippage (Underspend in 21/22 - slip budget back) | The last main project of the year, Crowberry Road, has had to be moved into the 2022 budget line, due to delays with drawings and planning applications not being submitted (no technical drawing person). This has been discussed with Management and delays in 2022 are now inevitable and put the whole 2022 program at risk. | 1109000 | 1163000 | 1163000 | 0 | 0 | 0 | 0 | Release servitor spend on a monthly basis to the PM. Release P2P spend on a monthly basis to the PM. For checking/clarification purposes. Be aware that this spend is for 4 projects plus min-projects when requesting end dates. | Planting of trees, hedges and wildlife habitat. Local sourcing of products were possible. | Yes | with Highways | Sue Briscoe/TBC (resource to be found) | ODS - Highways | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7060 | Heating Systems | SC | Housing Services - HRA | N7060 | Heating Systems | 0 | Rolling Programme | Mark Smart | Running | 0 | 0 | Tom Bridgman | Mark Smart | 0 | 0 | Mark Smart | This is delegated budget to ODS and is part of the Decent Homes works. Reason this underspent is due to Covid, plus there are limited number of system which need upgrading. | Under Budget | On Schedule | Low | N/A | 0 | 0 | 5. Delivery | 0 | 44286 | 0 | 272100 | 0 | 0 | 0 | 63336 | 63336 | 25443.11 | 63336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5026 | Housing Company Loans (Development Company ex Barton Park) | SC | Housing Development | M5026 | Housing Company Loans (Development Company ex Barton Park) | Loan to the Housing Company. | Housing Company Loans | David Watt | Running | Development Board | Assistant Chief Executive | Tom Bridgman | David Watt | 0 | Stephen Clarke | David Watt | Capital spend for OCH(D)L in 2021/22 will cumulatively be as the Revised Estimate reported to the Shareholder in July 2021 as part of the BP re-fresh. Thus, gross OCH(D)L capital spend will be £46.448m, capital receipts are estimated at £30.235m, thus a net capital spend for the year is £16.213m. The corresponding total cumulative borrowing estimate for OCH(D)L remains at £17.808m. The reason the loans are higher than the in-year spend is due to funding cumulative interest from previous lending. | On Budget with slippage | Awaiting new programme | High | High | Clearly the current lockdown and pandemic restrictions have had an impact on programme delivery but it is the relationship with the local Planning Authority and Housing Enabling Team that is key to delivering a successful programme to meet the Council's MTFP dividend expectations from OCHL. | COVID-19 Brexit Sales and Marketing Strategy | 9. Other Capital Spend | The OCHL BP is undergoing a re-fresh that will be presented to the OCHL Board and Shareholder over the next month or two. | On-going Rolling Programme | 0 | 32200000 | 38926580 | 45500000 | 15000000 | 117234169 | 17807589 | 2021159.67 | 12345000 | -5462589 | Slippage (Underspend in 21/22 - slip budget back) | Loan Schedule updated in line with Business Plan Refresh. Although there has been a relatively large reduction in anticipated (development) capital spend for the year, there hasn’t been a reciprocal reduction in borrowing associated requirements. This is due to the in-year cash flows for the company and how the balance of capital spend is funded. Be it from existing credit cash flow balances c/fwd. from the previous financial year and/or in-year capital receipts/HRA stage payments arising from the much reviewed capital programme. | 5234291 | 0 | 32571067 | -33692289 | -45500000 | 17571067 | -61621222 | Take note of BP re-fresh and monitor performance. | The Bracegirdle scheme is expected to deliver a 100% Energy Reduction Target, with all the other schemes at 20% carbon reduction estimates. | Yes (Extensions Programme) | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 10:15 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
C3057 | Housing System Replacement | SC | Housing Services - HRA | C3057 | Housing System Replacement | Replacement of the legacy Northgate Housing, Northgate Codeman asset management and Civica Servitor systems. Introduction of a mobile working platform. | Project - ICT | Dave Shaw | 0 | Operational Delivery Group | Chief Executive | 0 | David Shaw | 0 | Stephen Clarke | dshaw@oxford.gov.uk | 0 | 0 | 0 | High | 0 | The key risks to Go Live remain the Finance Interfaces and CBL functionality. | 0 | 5. Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278595 | 278595 | 390624.95 | 278595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7052 | HRA Stock Condition Survey | SC | Housing Services - HRA | N7052 | HRA Stock Condition Survey | Identify the condition of HRA stock along with analysis of the performance of the stock, to inform the Housing Asset strategy. | Project - Other | Mark Smart | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | Darowen Jones | ARK | Stephen Clarke | Mark Smart | Further funding identified for 22-23, 21-22 budget rolled forward, project to commence 22-23. | Under Budget | Awaiting new programme | Low | 0 | Timescale for works to fit in with budget setting process, outputs and priorities to be agreed at initial meeting. | 0 | 2. Feasibility | 0 | 0 | 0 | 169200 | 0 | 0 | 0 | 142729 | 142729 | 0 | 142729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:48 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7057 | Kitchens | SC | Housing Services - HRA | N7057 | Kitchens | 0 | Rolling Programme | Mark Smart | Running | 0 | 0 | Tom Bridgman | 0 | 0 | 0 | Mark Smart | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Budget also delegate to ODS. Due to Covid and the government lockdown put in place from 4th January 2021 all internal works were paused. Covid restrictions have slowed the programme. | Under Budget | Over Schedule | Low | Low | Tenant refusal and sufficient kitchens at an age that will required to be upgraded. | Currently looking to procure 20% stock condition survey to evaluate the condition of kitchens install in the asset and budget and numbers will be adjusted. | 8. Rolling Programme | 0 | 44286 | 0 | 1228080 | 0 | 0 | 0 | 1658534 | 1658534 | 556928.53 | 1658534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:48 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7062 | Lanham Way | SC | Housing Services - HRA | N7062 | Lanham Way | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Tom Bridgman | 0 | 0 | Stephen Gabriel | Dave Scholes | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission made this month. Land sale from County Council being actioned (internal delegated decision now made). | On Budget | On Schedule | Low | Low | 0 | 0 | 3. Design & Technical Specification | Land purchase from County being actioned. (Jun 21) Contract Award - TBC (date) | 0 | 0 | 3050000 | 4525000 | 459000 | 0 | 5969000 | 985000 | 98743.05 | 985000 | 0 | N/A - On Budget | Expected start on site is now May 2022 with land purchase from County Council anticipated in March 22 subject to planning committee approval. | 2460000 | 459000 | 0 | -2065000 | 0 | 0 | -2065000 | None | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7044 | Lift Replacement (Programme) | SC | Housing Services - HRA | N7044 | Lift Replacement (Programme) | Lift Replacement Programme | Rolling Programme | Mark Smart | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | Mark Smart | Cotswold (+ others) | Stephen Clarke | Mark Smart | All works for the 2020/21 have been completed and program for 2021/22 being prepared and works will need to be procured. | Over Budget | On Schedule with Risks | Medium | Medium | Resources to procure the works. Tenant consultation and involvement in the program. | 0 | 8. Rolling Programme | 0 | 44286 | 0 | 306500 | 0 | 0 | 0 | 410186 | 410186 | 66158.5 | 410186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
M5032 | Loan to Housing Company re Barton Park (Loan to OCH(I)L) | SC | Housing Development | M5032 | Loan to Housing Company re Barton Park (Loan to OCH(I)L) | 0 | Housing Company Loans | David Watt | Running | 0 | Communities and Customers | Tom Bridgman | David Watt | 0 | tbc | David Watt | Loan schedule reflects properties to be acquired in M5025, now 22 properties with an estimated cost of £3.093m. | On Budget with slippage | On Schedule | Low | Low | The programme is completely development led and therefore we have no influence on when properties will be acquired. We can only monitor progress against previously submitted handover schedules. | 0 | 9. Other Capital Spend | Acquisition of social housing from next phase of development. | 44286 | 0 | 5736037 | 12705996 | 8250000 | 8300000 | 32348856 | 3092860 | 0 | 3541000 | 448140 | Bring budget forward (Overspend in 21/22 - bring future budget forward) | Updated forecast following Oct-21 BP re-fresh | 8455017 | 10750000 | 7600000 | -4250979 | 2500000 | -700000 | -2450979 | Take note of BP re-fresh and monitor performance | All part of the development specifications. | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 10:14 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N6388 | Major Voids | SC | Housing Services - HRA | N6388 | Major Voids | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Tom Bridgman | - | ODS - Steve Carter | Stephen Clarke | Mark Smart | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. This is also a delegated budget to ODS. | Under Budget | On Schedule | Low | N/A | Any voids with major expenditure in current financial year. | 0 | 8. Rolling Programme | 0 | 44286 | 0 | 472000 | 515000 | 560000 | 560000 | 2107000 | 472000 | 49626.86 | 472000 | 0 | 0 | 0 | 515000 | 560000 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7066 | Next Steps Accommodation Programme | SC | Housing Services - HRA | N7066 | Next Steps Accommodation Programme | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Tom Bridgman | Dave Scholes | 0 | 0 | Dave Scholes | Buying 5 one bed flats for rough sleepers in a Housing First model. Completed on 3 in March 21 (Q4) and remaining two will be in April 21 (Q1 21/22). 5 NSAP units completed. A new bid to buy 10 further units in 21/22 made in April 2021, and award of funding confirmed (June 21) - team mobilising and contacting agents. Sept 21 - 1st unit completed. Oct 21 - Additional grant ask from MHCLG (to replace £550k that was to be funded from OGD) now under consideration/ sign-off. | On Budget | On Schedule | Low | Low | Mitigating risk by working through problems with leaseholders etc. A very flat sale market in Oxford at present for one bed units. Oct 21 - 8 further units in the conveyancing pipeline. | Homes England deadline has now been extended to mid May 21 (from end March 21) - end June for PC. Refurb works to basic relet standard required by end June to claim funding from PC stage - working with ODS to have this prioritised and actioned to time. July 21 update - 5 x one beds from NSAP bid completed. Acquisitions mobilised for next 10 (RSAP bid) - 4 homes in conveyancing pipeline and offers made on 4 others to date. | 5. Delivery | Practical Completion and handover of initial 5 flats (by end Jun 21). Some new acquisitions entering the conveyancing pipeline (by end July 21). | 0 | 0 | 2392000 | 0 | 0 | 0 | 2992584.33 | 2992584.33 | 959557.32 | 2992584.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | none | 0 | 0 | 0 | n/a | n/a | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | Y | N | N | N | N | N | N | Y | Y |  | Y | bar: 1 to 52
N7061 | Northfield Hostel | SC | Housing Services - HRA | N7061 | Northfield Hostel | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Tom Bridgman | 0 | 0 | Stephen Gabriel | Dave Scholes | Pre-Planning public consultation due July 21, and planning submission Aug/ early Sept 21. Oct 21 - Planning submission to be made this month. Land sale from County Council being actioned (internal delegated decision now made). | On Budget | On Schedule | Low | Low | Pre-Planning application and consultation used to mitigate planning risk. Land sale underway. Tender for build contract to be actioned. | 0 | 3. Design & Technical Specification | Land purchase from County being actioned (Jun 21) Build tender - programme tbc - expect to be in contract by end Mar 22 | 0 | 0 | 7900000 | 11727000 | 0 | 0 | 13500000 | 1773000 | 32943 | 1773000 | 0 | N/A - On Budget | Expected start on site is now May 2022. 21/22 spend represents land purchase from County Council in March 2022 subject to approval at Planning Cttee. | 5600000 | 0 | 0 | -6127000 | 0 | 0 | -6127000 | None | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | N | bar: 1 to 52
M5035 | Oxford Growth Deal Registered Provider Funding | SC | Housing Services - GF | M5035 | Oxford Growth Deal Registered Provider Funding | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Tom Bridgman | 0 | 0 | 0 | Dave Scholes | We are passing on grant we have received from County. There is no money coming from the Capital Programme. We will receive more grant than that to be paid out in 21/22, as we will receive 100% of the funding, but retain 10% until scheme completions, so will finish in credit at 21/22 year end. July 21 update - WMC Agt with L&G due for sealing (Jul 21). Agt with Catalyst (Littlemore Pk) finalised and with Catalyst lawyer for engrossment/ Cabinet & Council approval for this one due 21/ 26 July 21. Sealed Oct 21. Payment (90%) due to Catalyst Oct 21. Grant Agt issued to A2D for Gibbs Cresc also. | On Budget | On Schedule | Low | Low | Legal agreements not signed yet but working with legal to complete this (expectded by end June 21). All agreements bar the new one for A2D sealed. | 0 | 9. Other Capital Spend | June - Payment receipts up to end Qtr 3 20/21. 1st payment out due to Catalyst. | 0 | 0 | 6900000 | 330000 | 0 | 0 | 5017000 | 4687000 | 3906000 | 4687000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Gibbs Crescent Payment slipped to 22/23. Looking into possible excess budget for Littlemore Park. | 0 | 0 | 0 | -330000 | 0 | 0 | -330000 | None | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | Y | N | N | N | N |  | N | bar: 1 to 52
M5038 | Roken House | SC | Housing Services - GF | M5038 | Roken House | Acquisition and refurbishment to provide one bedroom flat Temporary Accommodation | Other Capital Spend | Dave Scholes | Running | Housing Supply Board | 0 | Tom Bridgman | Dave Scholes | 0 | 0 | Dave Scholes | 0 | On Budget | On Schedule | Low | Low | 0 | 0 | 9. Other Capital Spend | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 1660000 | 1430000 | 0 | 1430000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Refurbishment costs to take place in 22/23 following acquisition, surveys and legal costs | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | N | bar: 1 to 52
N7054 | Properties purchased from OCHL | SC | Housing Services - HRA | N7054 | Properties purchased from OCHL | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | Tom Bridgman | Dave Scholes | 0 | Stephen Gabriel | dscholes@oxford.gov.uk | c.75 units expected as buy-backs from OCHL in 21/22 Finance are adjusting spend profiles accordingly. | On Budget with slippage | On Schedule | Low | Low | 0 | Improved noticed of handover date changes - esp phased handovers within larger schemes | 9. Other Capital Spend | Cumberlege; 66 Sandy; Pauling Rd handovers. Cross-checking BPs and MTFP programme for budget round (Oct 21). | 0 | 0 | 31418629 | 50136900 | 45064900 | 69977000 | 200239461 | 35060661 | 21444795 | 35060661 | 0 | Slippage (Underspend in 21/22 - slip budget back) | Estimated spend only - still needs to reflect the detailed profiling in the HRA BP | 39613500 | 45064900 | 69977000 | -10523400 | 0 | 0 | -10523400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N7067 | Renewal of Fire Alarm Panels | SC | Housing Services - HRA | N7067 | Renewal of Fire Alarm Panels | Replacement of fire alarm panels and configuration of detection systems - initial sites are Pound House, Cardinal House, Atkyns Court, Birch House and George Moore House | Project - Compliance | Paul Worts | Not started | 0 | 0 | Tom Bridgman | Paul Worts | 0 | Stephen Clarke | Paul Worts | Project Planning taking place. | On Budget | Awaiting new programme | Medium | N/A | Key risks relate to the age of the systems and associated equipment hence the need for an updated survey and assessment of options. | Key issues are ensuring the system is open protocol, is able to service the requirements of the evacuation strategy and is suitable for the building type and occupancy. Account will need to be taken of the age of the detectors and whether these require replacement. Systems should be fully addressable and installed to current British Standards BS5839 Pts 1 and 6 by a contractor accredited to BAFE SP203-1 for design, installation, commissioning and handover. | 8. Rolling Programme | 0 | 44651 | 0 | 102000 | 0 | 0 | 0 | 102000 | 102000 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0102 | Replace or refurbish lifts | SC | Housing Services - HRA | B0102 | Replace or refurbish lifts | Repairs and maintenance programme | Rolling Programme | Paul Worts | Running Slowly | Development Board | Assistant Chief Executive | Tom Bridgman | tbc | 0 | Stephen Clarke | Paul Worts | Currently in procurement via secured framework. Resource being sourced to manage installs. | 0 | 0 | High | 0 | Due to resource issues and staff being furlough has been progress. | 0 | 8. Rolling Programme | 0 | 0 | 0 | 43294 | 76190 | 0 | 0 | 119484 | 43294 | 0 | 43294 | 0 | 0 | 0 | 0 | 0 | 0 | -76190 | 0 | 0 | -76190 | 0 | 0 | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-18 10:04 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N6392 | Roofing | SC | Housing Services - HRA | N6392 | Roofing | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Tom Bridgman | Gary Long | ODS | Stephen Clarke | Mark Smart | These are part of OCC statutory requirement to ensure that all properties meet Decent Homes and are part of the 30 year investment plan and report elsewhere. Hope that works will start on September 2020. Issues with supply of concrete products and the leading time has meant 20/21 program will now not be completed till April 21. | Under Budget | Over Schedule | Low | 0 | COVID-19 Shortage of materials due to COVID-19. ODS pricing and mobilization of sub-contractors but supply chain now in pace. | ODS ability to deliver the volume of roofing for 2021/22. | 8. Rolling Programme | 0 | 44316 | 0 | 1040000 | 700000 | 700000 | 700000 | 3403521 | 1303521 | 392053.46 | 1040000 | -263521 | 0 | 0 | 700000 | 700000 | 700000 | 0 | 0 | 0 | 0 | monitor program | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7047 | Social Rented Housing (Acquisitions) | SC | Housing Services - HRA | N7047 | Social Rented Housing (Acquisitions) | Social Rented Housing Acquisitions - c. £15.7m budget. Spend is across three projects: (1) Abbey Homes Acquisition off-plan £6.5m budget envelope; (2) top-up into Glanville Rd N7051 £0.5m; & (3) Street Purchases project c.£8.4m across 20/21 & 21/22. | Other Capital Spend | Dave Scholes | Running | Development Board | 0 | Tom Bridgman | Julia Castle/ Will McKay/ Steve Northey | 0 | Dave Scholes | dscholes@oxford.gov.uk | Abbey Homes - 2 month slippage to programme. Completion now expected Dec 21 (instead of Oct 21). Street Purchases - Considerable completion activity in Qtr 4 which brings this scheme close to target. 13 homes completed in Qtr4 (Qtr4 spend on acquisitions was £3.65m). 22 homes acquired from street acquisition work in 20/21. 21/22 work also now underway - 5 completions to date (2 in Qtr 1 and 3 so far in Qtr 2). 5 other homes under offer. | On Budget | On Schedule | Low | Medium | Risks continue to be mitigated as planned, with low turnover of suitably priced large units, at the right price point in the private sale market, being the main limiting factor. Risks diminish as the project nears close. | MHCLG have recently extended the 3 year deadline for the spend of Retained RTB receipts. Under-spends can be carried forward if this is agreed. Abbey: 20/21 spend: £5,263k. 21/22 forecast: £965k. 22/23: £23k Str Acq: 20/21 spend: £5,719k c/f to 21/22 c.£344k plus an additional budget already profiled in 21/22 of £2,350k. | 5. Delivery | Summer 21 handovers / Cabinet report re spends from Qtr 3 21/22 on to be prepared for Nov 21 Cabinet/ Council | 44651 | 0 | 2946872 | 0 | 0 | 0 | 4234246 | 4234246 | 2756138.38 | 4234246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | none | Additional carbon reduction measures applied as part of property refurbishment | Yes | Refurb/ void works required on all acquisitions | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | Y | bar: 1 to 52
N6386 | Structural | SC | Housing Services - HRA | N6386 | Structural | Repairs and maintenance programme | Rolling Programme | Mark Smart | Running | Development Board | Assistant Chief Executive | Tom Bridgman | Mark Burch / Bill Chamberlain | 0 | Stephen Clarke | Mark Smart | Programme of works currently under C/F to 2020/21 financial year. | Under Budget | Over Schedule | 0 | 0 | ARK have completed their assessment of all the properties and properties have been classified as repair and monitor, further investigation or full option appraisal. Additional budget has been requested via other lines underspend With the Balcony repairs there will be an essential requirement to carry out concrete testing realising the impact on measurement costs where we have leaseholders. Approx cost to leaseholders to Blocks with Balconies circa £7000.00. APA Concrete Repairs have been successful with the RFQ tender for £77,399.00 and awarded contract, will start mobilisation to site. | Balcony concrete repairs require concrete testing to identify the exact amount of cost and measurement for procurement. Also requirement to address the handrails during repairs, this will be an unknown factor during repairs and required to give the project certainty with expectations of the repairs. With the final RfQ preparation and 9 sites identified for Concrete Assessment this will identify the required works and cost to indicate required budgets. APA Concrete repairs are on site and have completed 7 Blocks in total and samples sent to laboratory for analysis and awaiting reports. | 8. Rolling Programme | 0 | 0 | 0 | 846600 | 666000 | 232000 | 232000 | 2363466.62 | 1233466.62 | 193511.75 | 1233466.62 | 0 | 0 | 0 | 666000 | 232000 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-21 11:48 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | Y | bar: 1 to 52
N6384 | Tower Blocks | SC | Housing Services - HRA | N6384 | Tower Blocks | Refurbishment of the tower blocks | Project - Development | Darowen Jones | Running | Development Board | Assistant Chief Executive | Tom Bridgman | Darowen Jones | Fortem | Stephen Clarke | darowen@kinverbusiness.co.uk | Evenlode & Windrush are now physically complete and we await the Building Control Certification so Sectional Completion can be issued. Hockmore Tower continues and is on programme with no cost variations. | On Budget | On Schedule | Low | Low | 0 | 0 | 5. Delivery | Physical Works Complete | 44530 | 44592 | 200200 | 0 | 0 | 0 | 998849 | 998849 | 61822.6 | 998849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | Fortem Energy Services Ltd | Fortem Energy Services Ltd | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7068 | Juniper | SC | Housing Services - HRA | N7068 | Juniper | The direct delivery of homes by ODS into the HRA | Other Capital Spend | Dave Scholes | Not started | 0 | 0 | Tom Bridgman | 0 | 0 | Stephen Clarke | Dave Scholes | At feasibility stage. TUCKER ROAD: 3 affordable homes (2@SR & 1@AR tenures). Planning Consent achieved. Development Team are considering final Development Scheme Appraisal (w/c 24th May 21) as a possible OCHL scheme. If not, approved for HRA only. JCT contract to be issued to ODS by end June 21. THOMPSON TERRACE: Scheme removed from programme in favour of using the land to help bring forward the larger Railway Lane scheme. JUNIPER DRIVE: 2 affordable homes (@SR). Planning approval awaited. | 0 | 0 | 0 | 0 | 0 | Moving schemes from feasibility into delivery. Bringing Tucker to contractual start in Qtr 1 of 21/22 to meet profile in the OGD programme. | 3. Design & Technical Specification | TUCKER: Contract Award - Confirmed 30/09/21 - but now moved into OCHL programme (/buy-back into HRA). JUNIPER: Planning submission due in July 2021 - TBC if this also switched into OCHL. | 44712 | 0 | 2607000 | 2607000 | 0 | 0 | 2607000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2607000 | 0 | 0 | -2607000 | 0 | 0 | Yes | Building contract | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | Y |  | N | bar: 1 to 52
N7064 | Unallocated Site 1 | SC | Housing Services - HRA | N7064 | Unallocated Site 1 | 0 | Other Capital Spend | Dave Scholes | Completed | 0 | 0 | 0 | 0 | 0 | Stephen Clarke | Dave Scholes | Budget was removed completely as part of budget setting Oct 2021 | Completed | Completed | N/A | N/A | 0 | Actions pending a response re offer. July 21 - Update still awaited, as is the Sec of State consent to demolish the (listed) church. | 7. Closed | Pending | 0 | 0 | 5026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7065 | Unallocated Site 2 | SC | Housing Services - HRA | N7065 | Unallocated Site 2 | 0 | Other Capital Spend | Dave Scholes | Completed | 0 | 0 | 0 | 0 | 0 | Stephen Clarke | Dave Scholes | Budget was moved to OCHL development, this line needs to be removed from the capital programme | Completed | Completed | N/A | N/A | 0 | On site/ Delivery underway. | 7. Closed | on -site and underway | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
N7055 | Use of Recycled Capital Grants (for Social Rented Acquistions) | SC | Housing Services - HRA | N7055 | Use of Recycled Capital Grants (for Social Rented Acquistions) | 0 | Other Capital Spend | Dave Scholes | Running | 0 | 0 | 0 | 0 | 0 | Stephen Clarke | Dave Scholes | Deadline has been extended by Homes England. Unpausing next financial year (21/22) - Priority given to alternative spends using (more time limited) Retained RTB Receipts in 20/21. | On Budget | On Schedule | Low | Low | 0 | Searching for a suitable (and suitably priced) large house to acquire - 4 beds or more, or a 3 bed easy to convert/ extend. | 9. Other Capital Spend | Property into conveyancing pipeline by end Aug 21. Oct 21 - property identified and expect to complete in Qtr 3. | 0 | 0 | 0 | 0 | 0 | 0 | 368000 | 368000 | 324000 | 368000 | 0 | 0 | 0 | 368000 | 0 | 0 | 368000 | 0 | 0 | 368000 | None | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | N | bar: 1 to 52
T2273 | Car Parks Resurfacing | SH | Oxford Direct Services | T2273 | Car Parks Resurfacing | Car Parks Resurfacing | Rolling Programme | Jason Munro/ Suzanne White | Running | Development Board | Transition | Caroline Green | TBC | 0 | Simon Howick | Zena.Ellis@odsgroup.co.uk | Next projects to complete from prioritised list of re-surfacing works for 2021 are: • Worcester St car park • Godstow Road car park • Marsh Road car park All on track for completion by 31/03/22 Note - Funding for Godstow Road was carried forward in this budget to FY 21/22. | On Budget | On Schedule | Low | Low | Dates for the agreed car park works could change due to weather conditions There is an ongoing risk that sub-contractors could cancel due to Covid issues however to mitigate this risk frameworks are in place with the ability to call on other contractors if needed. | 0 | 8. Rolling Programme | Further dates for programme of work yet to be agreed | 44377 | 44651 | 468231 | 335864 | 300000 | 300000 | 1404095 | 468231 | 0 | 468231 | 0 | 0 | Funding for Godstow Road has been carried forward in this budget to FY 21/22. | 300000 | 300000 | 300000 | -35864 | 0 | 0 | -35864 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | zena.ellis@odsgroup.co.uk | 2022-01-14 16:55 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2299 | Controlled Parking Zones | SH | Oxford Direct Services | T2299 | Controlled Parking Zones | Controlled Parking Zones | Project - Other | Shaun Hatton | Running Slowly | Development Board | Transition | Caroline Green | Shaun Hatton | 0 | Simon Howick | shaun.hatton@oxfordds.co.uk | Received confirmation from County to proceed with Old Marston, South Oxford, Holloway South + Temple Cowley Awaiting further details for Florence Park | On Budget | On Schedule | Low | Low | 0 | Awaiting details for Florence Park - With an anticipated completion date of early March | 5. Delivery | 0 | 0 | 0 | 400000 | 250000 | 0 | 0 | 500000 | 250000 | 0 | 250000 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | N | Y | N | N | Y |  | N | bar: 1 to 52
R0010 | Electric Vehicles | SH | Oxford Direct Services | R0010 | Electric Vehicles | Electric vehicle purchase | Project - Other | Owain Pearce / Suzanne White | Completed | Development Board | Transition | Caroline Green | TBC | 0 | Simon Howick | Zena.Ellis@odsgroup.co.uk | Project complete and accepted into BAU. | On Budget | On Schedule with Risks | Low | Low | N/A - in BAU | 0 | 7. Closed | Commencement of data reporting to funding body to be managed under BAU | 0 | 44408 | 424000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - On Budget | 0 | 575350 | 0 | 0 | 575350 | 0 | 0 | 575350 | 0 | Achieves target of 25% of the ODS fleet being electrified by 2023. | 0 | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-17 13:52 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2308 | ODS Additional Technology Requirements | SH | Oxford Direct Services | T2308 | ODS Additional Technology Requirements | Capital investment in ICT | Project - ICT | Suzanne White | Running | Operational Delivery Group | Transition | Caroline Green | Suzanne White | 0 | Jane Lubbock | Zena.Ellis@odsgroup.co.uk | CRM – Planning activity ongoing, current forecast completion date is targeting Jun ’22 however this is on the assumption that: i) other projects do not take precedence & ii) OCC are able to release staff to work with ODS on integration. VWS - Current focus is on obtaining contract signature by 21/02/22. Assuming this is achieved, system go-live will be w/c 16/05/22 in line with current project plan. Work continues on revised roadmap. There are numerous moving parts to be considered in terms of CRM interfaces and requirements needed to secure specific contracts, good progress is being made and award of the CRM contract enables activity to help firm up the plan. | On Budget | On Schedule with Risks | Medium | Low | Timescale Risks: Work on QL IT issues continues. This risk is reducing as work progresses however there is still a risk issues may be more complex than anticipated which could result in more time and effort being required to ensure fixes are permanent and fit for purpose. This would impact resource availability for other IT projects/work. | 0 | 8. Rolling Programme | CRM - Implementation of new CRM solution - specific plan/dates tbc, Phase 2 targeting February 2022 VWS - contract signature by 21/02/22 | 44651 | 44742 | 1144326 | 537000 | 0 | 0 | 1144326 | 607326 | 0 | 607326 | 0 | N/A - On Budget | Additional Technology items associated with Depot project has been pushed back. | 0 | 0 | 0 | -537000 | 0 | 0 | -537000 | 0 | Route optimization will reduce mileage and therefore carbon emissions due to more efficient journeys. | No | 0 | 0 | 0 | 0 | TRUE | zena.ellis@odsgroup.co.uk | 2022-01-14 16:55 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2301 | ODS Depot Rationalisation (/Redbridge Masterplan) | SH | Oxford Direct Services | T2301 | ODS Depot Rationalisation (/Redbridge Masterplan) | Consideration of a single depot to support Oxford Direct Services. Development of a recycling transfer station is linked to the Depot Rationalisation. Also the project is currently spread over various Cost Centres. | Project - Development | Douglas Kerrigan, Oliver Hearn | Running Slowly | Development Board | Transition | Tom Bridgman | Douglas Kerrigan | 0 | Tom Bridgma | Doug Kerrigan | Work to assess cost impact of Redbridge Park & Ride option has shown that it is NOT financially viable for ODS to move there; it has therefore been agreed that one new super depot at Redbridge will not happen. ODS are committed to reducing our land take, driving out cost savings and supporting future growth through more co-location. We will be looking again at our existing sites during the coming period to determine how we could organise them differently, taking into account the changes Covid has brought about to ourselves and indeed other organisations - maybe there is a suitable space out there somewhere, which was not available in the past. ODS now plan to remain at Cowley Marsh, Horspath Road and Cutteslowe Park for the foreseeable future. How this work will progress/will be funded is yet to be determined and agreed. | On Budget | Awaiting new schedule | Medium | Low | Risk business case - there is a risk that the business case will not be released in a timely manner by ODS and considered viable in the current climate and the project will not be authorized to proceed. Key risks to note on the quality of the information provided by Stantec and the demonstration of ODS and Project related efficiencies made. Mitigation - Present a series of options for evaluation in the outline business case. Ensure that the business case can be appraised alongside as much information as can be made available at that point in relation to the financial position of the Council, ODS plans, and the opportunity that would be provided to the Housing Company through the redevelopment potential of Cowley Marsh. It was acknowledged that the current delay to the programme associated to the OBC and Redbridge sites, may push the completion of a new depot facility beyond the deadline of the funding in March 2024 release of land and put the funding at risk. At present the OBC Option is due to be released circa Autumn 2023 and Redbridge option is circa Spring 2024. Unless a decking is constructed, potentially adding a further 9-12 months to the programme, along with the depot construction, the OFAS and Kennington Bridge, the culmination of the works would mean shutting the Park and Ride down for circa 2-3 years to facilitate development. The actions from the members briefing for the Redbridge co-ordination slide, ie. 1) communication plan. 2) transport risks. 3) site risks. 4) project coordination. 5) planning policy. 6) occ governance steps. . Risk Travel and Traffic - There is a risk that the combined impact of group of Redbridge projects will not be able to be supported. Mitigation - coordination of the Redbridge group of projects and submission of a joint proposal. Early engagement with Highways England. This is frustrated by the lack of RIBA Stage 1 Depot transport statement from ODS. There is a risk that the brief requirements for Sustainability and Financial Efficiencies requirements will conflict with each other. Mitigation - Technical analysis is required in order to quantify the risk. | The decision not to proceed with depot rationalisation to one new super depot at Redbridge will have a significant impact on the timescales and budget for this project. Re-planning work for this project, with revised scope, will need to include refreshed timescales and costs; approval will then be sought for an updated Capital budget, as appropriate. It is not yet clear how Covid-19 and the rapid changes to the work environment might impact the programme requirements and ODS business requirements. | 2. Feasibility | We were due to receive the RIBA Stage 1 submission by 11th June, but this is now overdue. We anticipated the following dates: 1) Issued for Stakeholder virtual review (i.e. planning/ property/ sustainability etc) – wk.16th August 2) Depot Board Review - TBC 3) Case For Change Workshop (To include Tom Bridgman and Simon Howick) – 19th July 2021 4) Development Review Group – Sept 2021 5) Development Board – Sept 2021 6) Cabinet - November 2021? This is unlikely | 45382 | 46203 | 700000 | 6996663 | 5179718 | 0 | 12676381 | 500000 | 20022 | 500000 | 0 | Slippage (Underspend in 21/22 - slip budget back) | The decision not to proceed with depot rationalisation to one new super depot at Redbridge will have a significant impact on the timescales and budget for this project. Costs incurred in respect of all activities to date will need to be reviewed and agreed. Re-planning work for this project, with revised scope, will need to include refreshed timescales and costs; approval will then be sought for an updated Capital budget, as appropriate. | 6200000 | 5179718 | 0 | -796663 | 0 | 0 | -796663 | Timely release of ODS RIBA stage 1 information has not been forthcoming, awaiting issue. | Anticipated that this will be a Net Zero Carbon Facility. Sustainability brief has been developed in collaboration with Paul Spencer. | Yes | At some point we will likely require pre-construction services to develop the construction phase plan and a costed bill of quantities (possibly 2 stage tender). | Stantec | N:A currently in feasibility stage. | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2306 | ODS Mobile Working and Handhelds | SH | Oxford Direct Services | T2306 | ODS Mobile Working and Handhelds | ODS requirement for mobile working and handhelds | Project - ICT | Suzanne White | Running Slowly | 0 | Transition | Caroline Green | TBC | 0 | Jane Lubbock | Oliver Hearn | 0 | On Budget | Over Schedule | Low | Low | Risk Resource - availability of staff to deliver and receive training due to Covid 19 limiting pace of delivery. Mitigation - designate collection point for remaining devices, schedule 121 sessions observing social distancing rules to complete training. | Staff isolating due to vulnerability means that they cannot collect devices or complete training. Approximately 10 remaining. | 5. Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140778 | 140778 | 0 | 140777.72 | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Enabling mobile working reduces trips back and forth to depots. | No | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | Y |  | N | N | N | N | Y | Y | N | Y | Y |  | Y | bar: 1 to 52
T2307 | ODS Transformation Funding | SH | Oxford Direct Services | T2307 | ODS Transformation Funding | Capital investments required to deilver additional return. | Project - ICT | Suzanne White | Running Slowly | Development Board | Transition | Caroline Green | TBC | 0 | Helen Bishop | Zena.Ellis@odsgroup.co.uk | QL - work continuing & good progress has been made in recent weeks: Servitor Closing / QL Opening Balances have now been corrected for Stock, Labour and Subcontractors. Payment Interface testing is in progress. A copy of QL Live will be copied 14/01/22 and further tests carried out on 17/01/22. In parallel, work on the Sales Order Process is progressing with the correction of worktypes and job setup being corrected with the aim of Running a small batch through the Test environment w/c 17/01/22. 1st Touch Rollout has now reached 46 operatives incl Gas, EQC, Carpentry, Glaziers and Plumbers with another 12 piloting for their areas with plans to go live w/c 24/01/22. Work has slowed down due to GE commitments on the Interface and opening balance work. CRM – Planning activity ongoing, current forecast completion date is targeting Jun ’22 however this is on the assumption that: i) other projects do not take precedence & ii) OCC are able to release staff to work with ODS on integration VWS - Current focus is on obtaining contract signature by 21/02/22. Assuming this is achieved, system go-live will be w/c 16/05/22 in line with current project plan. | On Budget | Over Schedule | Medium | Medium | Timescale Risk - Work on QL IT issues continues. This risk is reducing as work progresses however there is still a risk issues may be more complex than anticipated which could result in more time and effort being required to ensure fixes are permanent and fit for purpose. This would impact resource availability for other IT projects/work. | 0 | 5. Delivery | Jan 2022 - QL Upgrade work to commence in parallel with continuing work to fix existing issues May 2022 - Upgrade to QL 4.10 in place. | 44407 | 44681 | 400000 | 130798 | 0 | 0 | 242298 | 111500 | 0 | 111500 | 0 | 0 | 0 | 0 | 0 | 0 | -130798 | 0 | 0 | -130798 | 0 | These remain as set out in the original plan – and can start to be measured once the new Planner software is operational and repair work can be scheduled around locations. | No | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2287 | P0024-D-2019 : Recycling Transfer Station | SH | Oxford Direct Services | T2287 | P0024-D-2019 : Recycling Transfer Station | Development of a recycling transfer station. Linked to the Depot Rationalisation Project for ODS | Project - Other | Oliver Hearn and Jane Lubbock | Paused | Development Board | Transition | Caroline Green | Oliver Hearn | 0 | Simon Howick | Oliver Hearn | 0 | 0 | 0 | 0 | 0 | Cost risks from market conditions. Mitigation by market testing key work packages. Cost risks from ground conditions. Mitigation through ground investigations. Avoiding major groundworks in the winter. | See above | 1. Idea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18752 | 18752 | 8970.75 | 18752 | 0 | 0 | 0 | TBC | TBC | TBC | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 0 | TBC | Yes | 0 | 0 | 0 | 0 | TRUE | jmarriott@oxford.gov.uk | 2022-01-11 15:31 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2302 | P0025-D-2019 : Recommissioning of temporary car parking at Redbridge | SH | Oxford Direct Services | T2302 | P0025-D-2019 : Recommissioning of temporary car parking at Redbridge | Recommissioning of temporary car parking at Redbridge | Project - Development | Steven Clews | Paused | Development Board | Transition | Caroline Green | Doug Kerrigan | 0 | Simon Howick | N/a | ODS now plan to remain at Cowley Marsh, Horspath Road and Cutteslowe Park for the foreseeable future. | Budget to be agreed | Awaiting new programme | N/A | N/A | 1/ Revenue from parking provided from decking. Consider meantime use at Oxpens Extend permission to use deck as car parking again till OXWED need site 2/ No decision on position of deck. Agree ODS and RTS positions | N:A | 7. Closed | Review Depot Rationalisation Outline Business Proposal circa May 2021. | 45658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not currently identified as a project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N:A | TBC | Unsure | 0 | 0 | 0 | 0 | 0 | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
T2305 | Parks Paths | SH | Oxford Direct Services | T2305 | Parks Paths | There are a large number of hoggin paths across the Council’s Parks and Open Spaces. A number of these are in need of resurfacing and have fallen into disrepair and will become a safety hazard. | Project - Other | Laura Harlock | Running | Development Board | Transition | Stephen Gabriel | tbc | 0 | Laura Harlock | lharlock@oxford.gov.uk | 0 | On Budget | On Schedule | Low | Low | Agresso spend should be £77,6770 for 20/21 and £33,840 will be spent in 21/22 financial year. | Please see above in reason under/ overspend against budget | 5. Delivery | 0 | 44621 | 44651 | 0 | 0 | 0 | 0 | 33840 | 33840 | 0 | 33840 | 0 | N/A - On Budget | 0 | 33480 | 0 | 0 | 33480 | 0 | 0 | 33480 | 0 | Delivering materials to site. | Yes | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2021-11-22 11:34 | [54 empty] | N |  | N | N | N | N | N | N | N | Y | Y |  | N | bar: 1 to 52
R0005 | The MT Vehicles/Plant Replacement Programme | SH | Oxford Direct Services | R0005 | The MT Vehicles/Plant Replacement Programme | MT Vehicles/Plant Replacement Programme is a rolling programme, the purpose of which to provide a replacement for the Council and ODS fleet within economic lifespans. The current priority for the programme is dust carts and grounds maintenance plant as these are now at the end of their economic lifespan, with maintenance costs set to increase. | Rolling Programme | Owain Pearce | Running | Development Board | Transition | Caroline Green | Owain Pearce | 0 | Simon Howick | Owain Pearce | How this work will progress/will be funded is yet to be determined and agreed. | On Budget with slippage | On Schedule | Low | Low | The project is subject to planning of replacement Electric vehicles across all services. This is a complex replacement due to many vehicles being taken home or calculating power requirements at depots. Due to severe supply chain issues across the globe the lead times on vehicles has extended by months. This may require us to bring forward orders for 2023 replacement as well to actually get them within the next FY replacement dates. It has also put delivery in jeopardy for this FY replacement vehicles. An additional step for vehicle replacement has been added requiring business cases for all diesel vehicle replacements. This is slowing down the ordering process. OCC are pushing for full decarbonisation of the fleet by 2030 but this can only be achieved with new infrastructure and some high cost electric vehicles. Leasing is being investigated but this has not been finalised. If we buy diesel now then we are tied in for another 7 years. As such it may be that some assets are rolled over until decisions have been made on future replacement methods and strategy. As many vehicles will slip from FY2021 into arrival during FY2022 then we will need to give them a replacement of 6 years instead of 7 to keep the capital programme smoothed. This will increase the annual cost for these assets to pay back to OCC. | ODS/OCC strategy & financial model for replacement of vehicles to Electric is an ongoing process. Much of this may come down to support from OCC. Capital funding will still be required regardless of strategy selected. We have had a number of non-priority vehicles due to be replaced this FY [which had been previously extended] requiring additional maintenance or needing to be disposed of - any smoothed into subsequent years may also require additional maintenance or rapid replacement, based on this trend. Decisions to be made from OCC on decarbonisation targets and leasing options. | 8. Rolling Programme | Some specs have been signed off with others outstanding. Surveys are outstanding but once complete Electric vehicles orders can be confirmed. | 0 | 0 | 2929845 | 4693893 | 2665952 | 2134220 | 12661023 | 3166958 | 1193231.03 | 2863713 | -303245 | Slippage (Underspend in 21/22 - slip budget back) | Slippage - a number of assets have been extended. This is in addition to delays in ordering due to outstanding home surveys & infrastructure options and delays in supply chain | 3285127 | 2665952 | 2134220 | -1408766 | 0 | 0 | -1408766 | 0 | The Electric Vehicles project, using ESO grant funding, will achieve the target of the electrification of 25% of the ODS fleet by 2023. The timeline for further electrification is dependent on the agreement of the ODS / OCC strategy and financial model currently under discussion. Replacement of ageing vehicles with more carbon efficient models (even if not electric) would contribute to carbon reduction targets. | 0 | 0 | 0 | 0 | 0 | TRUE | rhaverson@oxford.gov.uk | 2022-01-17 15:42 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
B0130 | CIL Feasibility |  |  | B0130 | CIL Feasibility | 0 | Project - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 150000 | 150000 | 0 | 150000 | 0 | 0 | Possible slippage as £100k currently unassigned to projects. £100k is ear-marked for projects yet to allocated budgets (£50k Cowley Branchline, £50k for West End Development). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | jmarriott@oxford.gov.uk | 2021-11-08 09:30 | [54 empty] | N |  | N | N | N | N | N | N | N | N | N |  | N | bar: 1 to 52
[110 empty] | 25 |  | 5 | 4 | 3 | 4 | 11 | 20 | 0 | 13 | 14 |  | 26
[23 empty] | 1. Idea | 9 | [32 empty] | 50: Projects; 51: Excluded; 52: Updates Expected |  | 21.01% |  | 4.202% | 3.361% | 2.521% | 3.361% | 9.244% | 16.81% | 0% | 10.92% | 11.76% |  | 21.85%
Development Directorate | [22 empty] | Idea | 1 | [85 empty] | Comments | [5 empty] | Risk |  |  | Milestones |  |  | Forecasts
AA | Planning | [21 empty] | 2. Feasibility | 24 | [85 empty] | 1 | 100% |  |  |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | bar: 50; 52
CP | Regeneration & Economy | [21 empty] | 3. Design & Technical Specification | 17 | [32 empty] | 50: 24; 51: 5; 52: 19 |  | 3 | 15.79% |  |  |  |  | 3 | 15.79% |  | 3 | 15.79% |  | 6 | 31.58%
JW | Corporate Property | [21 empty] | 3. Design and Technical Specification | 1 | [32 empty] | 50: 19; 51: 4; 52: 15 |  | 0 | 0% |  |  |  |  | 1 | 6.667% |  | 3 | 20% |  | 2 | 13.33%
SC | Housing Services - HRA | [21 empty] | 4. Pipeline | 4 | [32 empty] | 50: 37; 51: 3; 52: 34 |  | 6 | 17.65% |  |  |  |  | 0 | 0% |  | 1 | 2.941% |  | 12 | 35.29%
SC | Housing Services - GF | [21 empty] | 5. Delivery | 28 | [32 empty] | 50: 3; 52: 3 |  | 1 | 33.33% |  |  |  |  | 1 | 33.33% |  | 0 | 0% |  | 0 | 0%
SC | Housing Development | [21 empty] | 6. Completed | 3 | [32 empty] | 50: 4; 52: 4 |  | 0 | 0% |  |  |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
Communities and People | [22 empty] | 7. Closed | 6
IB | Community Services | [21 empty] | 8. Rolling Programme | 22 | [32 empty] | 50: 8; 51: 3; 52: 5 |  | 3 | 37.5% |  |  |  |  | 1 | 20% |  | 1 | 20% |  | 2 | 40%
IW | Regulatory & Community Safety | [21 empty] | 9. Other Capital Spend | 14 | [32 empty] | 50: 5; 51: 1; 52: 4 |  | 0 | 0% |  |  |  |  | 0 | 0% |  | 1 | 25% |  | 1 | 25%
Chief Exec and Corporate Resources | [22 empty] | 0 | 2
MT | Environmental Sustainability | [21 empty] | #N/A | 3 | [32 empty] | 50: 10; 51: 2; 52: 8 |  | 5 | 50% |  |  |  |  | 3 | 37.5% |  | 3 | 37.5% |  | 2 | 25%
NK | Financial Services | [22 empty] | 131 | [32 empty] | 50: 5; 52: 5 |  | 1 | 20% |  |  |  |  | 1 | 20% |  | 0 | 0% |  | 0 | 0%
SH | Oxford Direct Services | [20 empty] | New Projects | [34 empty] | 50: 9; 51: 2; 52: 7 |  | 2 | 22.22% |  |  |  |  | 1 | 14.29% |  | 1 | 14.29% |  | 1 | 14.29%
HB | Business Improvement | [21 empty] | Expected Updates | 119 | [32 empty] | 50: 9; 51: 3; 52: 6 |  | 3 | 33.33% |  |  |  |  | 0 | 0% |  | 0 | 0% |  | 0 | 0%
[57 empty] | 50: 134; 51: 23; 52: 111 |  | 25
Note on DD149: jmarriott: New Projects + Completed / Closed + no update requested (Paused) UPDATE MANUALLY

## Historic Spend (hidden)
Cost Centre | Cost Centre | GF / HRA | Category | Category & Fund | 18/19 Original | 18/19 Spend | 19/20 Original | 19/20 Amount | 20/21 Original | 20/21 Amount | 21/22 Approved Budget | 21/22 Amount
A3129 | A3129 - Donnington Recreation Ground Improvements | GF | Rolling Programme | Rolling Programme GF |  |  | 0 | 0
A4808 | A4808 - Blackbird Leys LC Improvements | GF | #N/A | #N/A | 0 | 0
A4816 | A4816 - Sports Pavillions | GF | Rolling Programme | Rolling Programme GF | 0 | 0
A4820 | A4820 - Upgrade Existing Tennis Courts | GF | Project - Other | Project - Other GF | 0 | 0 | 35000 | 0 | 35000 | 0 | 0 | 0
A4833 | A4833 - Horspath Sports Park | GF | Project - Development | Project - Development GF | 619116 | 651665.33 | 46600 | 61608.44 | 0 | 295.9
A4841 | A4841 - Skate Parks (Manzil Way Gardens) | GF | Rolling Programme | Rolling Programme GF | 52860 | 52699.05 | 0 | 2286.28
A4845 | A4845 - CCTV Suite Upgrade | GF | Project - Other | Project - Other GF | 0 | 9990 | 80000 | 1321.6 | 68688 | 58104.9 | 0 | 0
A4847 | A4847 - Rose Hill Community Centre - Parking Management | GF | Project - Other | Project - Other GF | 10000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0
A4848 | A4848 - Barton Fit Trail | GF | Project - Development | Project - Development GF |  |  | 7085 | 0
A4849 | A4849 - Five Mile Drive Pavilion | GF | Rolling Programme | Rolling Programme GF | 70000 | 89421.33
A4852 | A4852 - Bodycams for Community Safety Team | GF | Project - Other | Project - Other GF |  |  | 0 | 0 | 60450 | 0 | 0 | 0
A4853 | A4853 - City Wide Cycling Infrastructure Contribution | GF | Other Capital Spend | Other Capital Spend GF | 30000 | 0 | 30000 | 24543.58 | 60000 | 0 | 109956 | 0
B0027 | B0027 - Covered Market - Improvements & Upgrade to Roof | GF | #N/A | #N/A | 0 | 0
B0031 | B0031 - Planned Building Improvements | GF | Rolling Programme | Rolling Programme GF | 0 | 1047766.99 | 0 | 192045.35 | 0 | 504759.09
B0034 | B0034 - Rose Hill Community Centre | GF | #N/A | #N/A | 0 | 0
B0041 | B0041 - Investment - Misc City Centre Properties | GF | #N/A | #N/A | 0 | 0
B0074 | B0074 - R & D Feasibility Fund | GF | Project - Development | Project - Development GF | 111000 | 9734.25 | 1115914 | 0 | 325180 | 6124 | 740576 | 0
B0075 | B0075 - Stage 2 Museum of Oxford Development | GF | Project - Development | Project - Development GF | 1700000 | 479983.98 | 665000 | 1137932.53 | 35000 | 1368250.62 | 0 | -269940.81
B0081 | B0081 - Car Parking Oxpens | GF | Project - Development | Project - Development GF | 0 | 0 | 243000 | 7645 | 43000 | 10516.54 | 225355 | -2450
B0083 | B0083 - East Oxford Community Centre | GF | Project - Development | Project - Development GF | 250000 | 172641.56 | 1500000 | 144952 | 4212439 | 27114.5 | 3547154 | 51829.83
B0084 | B0084 - Jericho Community Centre | GF | Other Capital Spend | Other Capital Spend GF | 0 | 0 | 0 | 0 | 200000 | 6276
B0086 | B0086 - Seacourt Park & Ride Extension | GF | Project - Development | Project - Development GF | 2987000 | 1104514.63 | 1426933 | 3266919.1 | 0 | 124653.31 | 0 | -411356.99
B0092 | B0092 - Cave Street Development (Standingford House) | GF | Project - Development | Project - Development GF | 0 | -51390.42 | 0 | 56550.01 | 1407500 | 227209.7 | 2948824 | 57863.09
B0095 | B0095 - Barton Community Centre | GF | Project - Development | Project - Development GF | 70859 | 102942.94 | 0 | -14527.74
B0096 | B0096 - Bullingdon Community Centre | GF | Project - Development | Project - Development GF | 50000 | 62625.7 | 1273776.67 | -13427 | 1481151 | 562654.86 | 1064578 | -464198.36
B0098 | B0098 - 1-3 George Street | GF | Project - Development | Project - Development GF | 151909 | 188036.87 | 0 | 162430.85 | 1635200 | 869923.65 | 1226769 | -419215.57
B0099 | B0099 - Ship Street & New Road | GF | Rolling Programme | Rolling Programme GF | 494 | 374.29 | 0 | 0
B0100 | B0100 - Gloucester Green Car Park (H&S) | GF | Project - Compliance | Project - Compliance GF | 230000 | 6463.06 | 76350 | 37764 | 74979 | 20207.41 | 262123 | -168162.6
B0101 | B0101 - Capital works at Covered Market | GF | Project - Development | Project - Development GF | 314000 | 169210.09 | 918000 | 413691.89 | 1012790 | 106107.63 | 0 | 2500
B0102 | B0102 - Replace or refurbish Lifts | GF | Rolling Programme | Rolling Programme GF | 154000 | 34515.93 | 0 | 0 | 43294 | 0 | 76190 | 0
B0103 | B0103 - 6 Queen Street works | GF | Project - Compliance | Project - Compliance GF | 0 | 35193.71
B0104 | B0104 - Old Gas Works Bridges | GF | Project - Compliance | Project - Compliance GF | 30000 | 22991.91 | 0 | 25246 | 0 | 174460.3 | 0 | 66153.71
B0105 | B0105 - Westhill Barns (Shotover) | GF | Project - Other | Project - Other GF | 0 | 0
B0106 | B0106 - Covered Market Planned Maintenance - Roof | GF | Rolling Programme | Rolling Programme GF | 555623 | 514125.15 | 325000 | 329475.37 | 240000 | 378593.51 | 426000 | 172389.04
B0108 | B0108 - Floyds Row Refurbishment | GF | Project - Development | Project - Development GF | 1845000 | 1563425.61 | 47300 | 334936.69 | 41400 | -57817.13 | 0 | -47581.93
B0110 | B0110 - Covered Market Vacant Unit Works | GF | Project - Development | Project - Development GF | 170000 | 178040.77 | 116000 | 84021.3 | 0 | 39235.79 | 0 | -18528.15
B0111 | B0111 - Town Hall Dry Risers | GF | Project - Compliance | Project - Compliance GF | 0 | 17480 | 0 | 48527.19 | 37282 | 129362.79 | 0 | -29298.65
B0112 | B0112 - City Centre Land Redevelopment (Cinema Project) | GF | Project - Development | Project - Development GF | 0 | 24343.46 | 0 | 0 | 40657 | 44594.35 | 0 | 76355.6
B0113 | B0113 - New Theatre Improvements | GF | Project - Development | Project - Development GF | 0 | 24343.46 | 0 | 0 | 0 | 0
B0114 | B0114 - Diamond Place Redevelopment | GF | Project - Development | Project - Development GF | 0 | 34343.46 | 0 | 80231.63 | 0 | 32148.64 | 0 | 2640
B0115 | B0115 - Covered Market Masterplan | GF | Project - Development | Project - Development GF | 0 | 14368.58 | 0 | 0 | 41560 | 106904.84 | 0 | 4046.2
B0116 | B0116 - Osney Path Works (HIF funded) | GF | Project - Development | Project - Development GF |  |  | 1086250 | 0 | 900000 | 127085.97 | 5300000 | 37488.15
B0117 | B0117 - Regeneration Property Purchase | GF | Other Capital Spend | Other Capital Spend GF |  |  | 42000000 | 0 | 20000000 | 0 | 20000000 | 3023402.57
B0118 | B0118 - Oxford Ice Rink Development | GF | Project - Development | Project - Development GF |  |  | 0 | 47100 | 32000 | 59953 | 0 | 850
B0119 | B0119 - Oxford Station Feasibility | GF | Project - Development | Project - Development GF |  |  | 0 | 61428.52 | 70000 | 55208.4 | 0 | 0
B0120 | B0120 - Osney Bridge (Growth Deal) | GF | Project - Development | Project - Development GF |  |  | 0 | 16255 | 1100000 | 189050.62 | 4583745 | 70722.08
B0121 | B0121 - Redbridge Masterplan Feasibility | GF | Project - Development | Project - Development GF |  |  | 0 | 15000
B0122 | B0122 - City Cycle Schemes (Growth Deal) | GF | Project - Other | Project - Other GF |  |  | 0 | 98337.81 | 450000 | 31897.85 | 751662 | 0
B0123 | B0123 - Boswells Feasibility | GF | Project - Development | Project - Development GF |  |  | 0 | 60000 | 0 | 17814.73
B0124 | B0124 - Port Meadow Moorings | GF | Project - Development | Project - Development GF |  |  | 0 | 27520.22 | 0 | 0 | 0 | -5279.22
B0125 | B0125 - City Centre Restart | GF | Project - Development | Project - Development GF |  |  | 0 | 0 | 0 | 0 | 50000 | 0
B0126 | B0126 - Asset Surveys | GF | Project - Development | Project - Development GF |  |  | 0 | 0 | 0 | 0 | 0 | 0
B0127 | B0127 - ZEZ Phase 1 Feasibility | GF | Project - Development | Project - Development GF |  |  | 0 | 5000 | 0 | 0 | 0 | 0
B0128 | B0128 - Greenways Cycling Project | GF | Project - Development | Project - Development GF |  |  | 0 | 0 | 0 | 0 | 0 | 0
B0129 | B0129 - Town Hall Options | GF | Project - Development | Project - Development GF |  |  | 0 | 0 | 0 | 56146 | 0 | 0
B0130 | B0130 - CIL Feasibility | GF | Project - Other | Project - Other GF |  |  |  |  | 200000 | 0 | 0 | 0
B0131 | B0131 - Meanwhile In Oxfordshire | GF | Other Capital Spend | Other Capital Spend GF |  |  | 0 | 30150 | 1875000 | 1309480 | 253874 | 219528
B0132 | B0132 - Coach Parking Feasibility | GF | Project - Other | Project - Other GF |  |  |  |  | 20000 | 0 | 0 | 0
B0133 | B0133 - Cemetery Feasibility | GF | Project - Development | Project - Development GF |  |  |  |  | 0 | 48978 | 0 | -630
B0134 | B0134 - Shotover SSI Management Plan | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 0 | 0 | 623
B0135 | B0135 - CCTV Gloucester Green Car Park | GF | Project - Compliance | Project - Compliance GF |  |  |  |  | 0 | 300
B0136 | B0136 - Covered Market CCTV | GF | Project - ICT | Project - ICT GF |  |  |  |  | 0 | 1352 | 0 | 39549.49
B0137 | B0137 - Court Place Farm and Blackbird Leys Bowling Club Asset Review | GF | Project - Development | Project - Development GF |  |  |  |  | 0 | 0
B0138 | B0138 - Enabling works - Decarbonisation Project | GF | Project - Development | Project - Development GF |  |  |  |  | 0 | 2367389.53 | 0 | 91510.13
B0139 | B0139 - SAC Works to enable letting (Feasibility) | GF | Project - Development | Project - Development GF |  |  |  |  | 0 | 62035 | 0 | 42753.28
B0141 | B0141 - City Centre Public Realm (Kiosks Project) | GF | Project - Development | Project - Development GF |  |  |  |  | 0 | 1723 | 0 | 6245.92
B0142 | B0142 - Stock condition surveys (including bridge works) | GF | Project - Development | Project - Development GF | [6 empty] | 2362500 | 0
B0143 | B0143 - Air conditioning and other works to enable letting of SAC | GF | Project - Development | Project - Development GF | [6 empty] | 1000000 | 0
B0144 | B0144 - Salary Costs across the Council to be capitalised | GF | Project - Development | Project - Development GF | [6 empty] | 480000 | 0
B0145 | B0145 - St Michael´s Street Levelling Works | GF | Project - Development | Project - Development GF | [6 empty] | 0 | 0
B0146 | B0146 - Ice Rink Car Parking Feasibility | GF | Project - Development | Project - Development GF | [6 empty] | 0 | 3350
B0147 | B0147 - Repairs to 2-4 Gloucester Street and 24-26 George St | GF | Project - Development | Project - Development GF | [6 empty] | 0 | 0
B0148 | B0148 - Oxford Flood Alleviation Scheme (OFAS) HIF Contribution | GF | Project - Development | Project - Development GF | [6 empty] | 0 | 0
C3039 | C3039 - ICT Infrastructure - minor costs | GF | Project - ICT | Project - ICT GF | 55582 | 30542.54 | 0 | -2608.99 |  |  | 0 | 228.99
C3044 | C3044 - Software Licences | GF | Project - ICT | Project - ICT GF | 220000 | 213920.98 | 220000 | 233018.4 | 245000 | 233158.75 | 245000 | 224430
C3055 | C3055 - Waste Management System | GF | Project - ICT | Project - ICT GF | 8400 | 13400.01 | 0 | 0
C3057 | C3057 - Housing System Replacement | GF | Project - ICT | Project - ICT GF | 718045 | 641470.4 | 0 | 321404.54 | 0 | 699967.15 | 0 | 335857.18
C3058 | C3058 - CRM Lagan Replacement | GF | Project - ICT | Project - ICT GF | 0 | 14191.59 | 200000 | 65533.2 | 0 | 19344.94 | 100275 | 0
C3060 | C3060 - End-Point Devices (Desktops/Laptops) | GF | Rolling Programme | Rolling Programme GF | 590546 | 707529.79 | 0 | 84225 | 60000 | 38268.4 | 153485 | 1399.6
C3065 | C3065 - ODS Network Upgrade | GF | Project - ICT | Project - ICT GF | 88000 | 102425.2 | 0 | 0
C3066 | C3066 - Telephony Device Refresh | GF | Rolling Programme | Rolling Programme GF | 127320 | 126868.91 | 0 | 50729 | 0 | 26257.92 | 60000 | 5586.71
C3067 | C3067 - Paris Payment System, Replacement / PCI DSS | GF | Project - ICT | Project - ICT GF | 78705 | 49191.28 | 36970 | 33800 | 17924 | 4380 | 0 | 111064
C3068 | C3068 - Windows 2008 Server Replacement | GF | Project - ICT | Project - ICT GF | 110450 | 83521.79 | 209200 | 67323.79 | 121128 | 41189.49 | 109345 | 0
C3069 | C3069 - Infrastructure Monitoring Enhancements - Icinga & Orion | GF | Project - ICT | Project - ICT GF |  |  | 0 | 0
C3070 | C3070 - Business Process Automation Full Rollout | GF | Project - ICT | Project - ICT GF | 35225 | 9735.7 | 0 | 5974.72 | 0 | 19687.5
C3071 | C3071 - Idox / Uniform Improvement Project | GF | Project - ICT | Project - ICT GF | 70000 | 68455.66 | 0 | 11950
C3072 | C3072 - Forms Engine Replacement | GF | Project - ICT | Project - ICT GF | 22375 | 15870 | 0 | 8367.35 | 0 | 21891.6 | 0 | 0
C3073 | C3073 - CorVu Reporting System Replacement | GF | Project - ICT | Project - ICT GF |  |  |  |  | 0 | 0
C3074 | C3074 - Asset Database | GF | Project - ICT | Project - ICT GF |  |  | 0 | 0
C3075 | C3075 - Netcall | GF | Project - ICT | Project - ICT GF |  |  | 60450 | 7092.15
C3076 | C3076 - Computer Systems Backup | GF | Project - ICT | Project - ICT GF |  |  | 0 | 1528.1
C3077 | C3077 - Info@Work Enterprise Upgrade Rollout | GF | Project - ICT | Project - ICT GF | 17000 | 15853.9 | 0 | 4800
C3078 | C3078 - Revs and Bens System Replacement | GF | Project - ICT | Project - ICT GF |  |  | 0 | 271263.5 | 245000 | 456115.28 | 0 | 21985.64
C3079 | C3079 - Town Hall Visitor WiFi Feasibility | GF | Project - ICT | Project - ICT GF |  |  |  |  | 0 | 4400 | 0 | 1900
C3080 | C3080 - Telephony Contract Replacement | GF | Project - ICT | Project - ICT GF |  |  |  |  | 0 | 8325 | 0 | 9712
C3081 | C3081 - Capitalised ICT Projects | GF | Project - ICT | Project - ICT GF | [6 empty] | 386600 | 0
E3511 | E3511 - Essential Repair Grants | GF | Other Capital Spend | Other Capital Spend GF | 30000 | 5021.92 | 15000 | 23457.39 | 24948 | 26505.58 | 15000 | -96.94
E3521 | E3521 - Disabled Facilities Grants | GF | Other Capital Spend | Other Capital Spend GF | 1481529 | 1399150.94 | 1200000 | 1065000.08 | 1282378 | 1038830.25 | 1400000 | 255788.24
E3557 | E3557 - Oxford and Abingdon Flood Alleviation Scheme | GF | Other Capital Spend | Other Capital Spend GF | 250000 | 0 | 0 | -2305.5 | 0 | 0 | 0 | 0
E3558 | E3558 - Go Ultra Low Oxford - On Street | GF | Project - Other | Project - Other GF | 53175 | 765.5 | 530021 | 21281 | 4545 | 42530.16 | 500000 | 72.8
E3560 | E3560 - Go Ultra Low Oxford - Taxis | GF | Project - Other | Project - Other GF | 339440 | 129348.39 | 106968 | 113839.44 | 0 | 65728.76 | 0 | 10051
E3561 | E3561 - Additional DFG Funding | GF | Project - Other | Project - Other GF | 0 | 0 | 0 | 69317.6 | 0 | 68727.77 | 0 | 893.25
E3562 | E3562 - OxPops (Electric Vehicle Charging) | GF | Project - Other | Project - Other GF | 116743 | 68239.46 | 0 | 6349.2 | 35806 | -6349.2
E3563 | E3563 - Clean Bus Technology Grants | GF | Other Capital Spend | Other Capital Spend GF | 731760 | 232698.67 | 0 | 517445 | 0 | 390290 | 0 | 0
E3564 | E3564 - Energy Superhub Oxford | GF | Project - Other | Project - Other GF |  |  | 0 | 0
E3565 | E3565 - Decarbonisation Fund - OCC element | GF | Project - Development | Project - Development GF |  |  | 0 | 11250 | 7538547 | 7910118.01 | 0 | 209473.45
E3566 | E3566 - Decarbonisation Fund - Low Carbon Hub Loan Element | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 3385000 | 2054652
E3567 | E3567 - Town Hall Lighting Upgrade (SALIX) | GF | Project - Other | Project - Other GF |  |  |  |  | 0 | 114741.16 | 0 | -24412.01
F0026 | F0026 - Pedestrianisation of Queen Street | GF | Project - Development | Project - Development GF | 0 | 0 | 0 | 0
F7007 | F7007 - Woodfarm / Headington Community Centre | GF | Project - Other | Project - Other GF |  |  | 20000 | 3603.25 | 8000 | 2351.75
F7011 | F7011 - Headington Environmental Improvements | GF | Project - Other | Project - Other GF | 59004 | 950 | 0 | 27273.14 | 29629 | 27731 | 60781 | -27731
F7020 | F7020 - Work of Art Littlemore | GF | Project - Other | Project - Other GF |  |  | 0 | 0
F7024 | F7024 - St Clements Environmental Improvements | GF | Project - Other | Project - Other GF |  |  | 50000 | 0 | 20000 | 0 | 20000 | 0
G6013 | G6013 - Superconnected Cities | GF | Project - Other | Project - Other GF |  |  | 0 | 0
L1000 | L1000 - Audio & Visual Equipment | GF | Project - ICT | Project - ICT GF | [6 empty] | 0 | 0
M5019 | M5019 - Purchase Of Homeless Properties | GF | Other Capital Spend | Other Capital Spend GF | 238494 | 137990.64 | 0 | 0 | 0 | 0 | 0 | -719.79
M5020 | M5020 - Empty Homes CPO Revolving Fund | GF | #N/A | #N/A | 0 | 0
M5021 | M5021 - Equity Loan Scheme for Teachers | GF | Other Capital Spend | Other Capital Spend GF | 32813 | 32412.5 | 0 | 0
M5023 | M5023 - OxWED Loans | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 1080093 | 0 | 0
M5024 | M5024 - National Homelessness Property Fund | GF | Other Capital Spend | Other Capital Spend GF | 0 | 0
M5025 | M5025 - Barton Park - purchase by Council | GF | Other Capital Spend | Other Capital Spend GF | 6561000 | 6029744.28 | 9869000 | 3481034.82 | 5736037 | 2045391.16 | 8455017 | 1851976.69
M5026 | M5026 - Housing Company Loans (excl Barton Park) | GF | Housing Company Loans | Housing Company Loans GF | 9423000 | 3632336.49 | 16595316 | 23567067.2 | 32200000 | 305000 | 5234291 | 1863976.69
M5028 | M5028 - Property Rationalisation (Depot Project) | GF | Project - Development | Project - Development GF | 215280 | 213126.93 | -2153 | 0 | 0 | -247846.93
M5030 | M5030 - Loan to Housing Company - Lucy Faithful House | GF | #N/A | #N/A | 0 | 0
M5031 | M5031 - Barton Phase 2 - Loan To Housing Company | GF | #N/A | #N/A |  |  | 0 | 0 | 0 | 0
M5032 | M5032 - Barton Park - Loan to OCHL | GF | Housing Company Loans | Housing Company Loans GF | 6561000 | 6069746.27 | 9869000 | 3514034.82 | 5736037 | 2059391.6 | 8455017 | 0
M5033 | M5033 - Blackbird Leys Regeneration (GF element) | GF | Project - Development | Project - Development GF |  |  | 0 | 0 | 226395 | 43743 | 8387991 | 10501
M5034 | M5034 - Affordable Housing Supply | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 0 | 914000 | 0
M5035 | M5035 - Growth Deal RP Funding | GF | Other Capital Spend | Other Capital Spend GF |  |  | 0 | 3123000 | 6900000 | 3906000 | 2560000 | 0
M5036 | M5036 - Low Carbon Hub Loans | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 2000000
M5037 | M5037 - Northern Gateway (Oxford North HIF) | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 6462 | 9300000 | 0
M5038 | M5038 - Roken House Aquisition and Refurbishment | GF | Other Capital Spend | Other Capital Spend GF |  |  |  |  | 0 | 500 | 230000 | 1405980.5
N6384 | N6384 - Tower Blocks | HRA | Project - Development | Project - Development HRA | 1530000 | 199359.35 | 0 | 481750.55 | 200200 | 115206.6 | 0 | -404509.71
N6385 | N6385 - Adaptations for disabled | HRA | Other Capital Spend | Other Capital Spend HRA | 783000 | 793899.55 | 687000 | 695941.14 | 704000 | 1066765.94 | 756000 | 300608.49
N6386 | N6386 - Structural | HRA | Rolling Programme | Rolling Programme HRA | 450000 | 243246.34 | 636000 | 245199.38 | 846600 | 516992.47 | 2000000 | 56054.8
N6387 | N6387 - Controlled Entry | HRA | Rolling Programme | Rolling Programme HRA | 0 | 0 | 345000 | 53916.57 | 312500 | 209561.01 | 133000 | 12279.86
N6388 | N6388 - Major Voids | HRA | Rolling Programme | Rolling Programme HRA | 409000 | 153295.05 | 453000 | 138752.47 | 472000 | 372350.34 | 515000 | -6644.83
N6389 | N6389 - Damp-proof works | HRA | Rolling Programme | Rolling Programme HRA | 107000 | 129514 | 117000 | 81993.6 | 119000 | 96123 | 75000 | 26474
N6390 | N6390 - Kitchens & Bathrooms | HRA | Rolling Programme | Rolling Programme HRA | 2423000 | 2189532.91 | 2538000 | 0 | 0 | 0 | 1300000 | 0
N6391 | N6391 - Heating | HRA | Rolling Programme | Rolling Programme HRA | 2160000 | 2216089.91 | 2487000 | 0 | 0 | 0 | 2352000 | 0
N6392 | N6392 - Roofing | HRA | Rolling Programme | Rolling Programme HRA | 278000 | 173857.03 | 194000 | 441073 | 1040000 | 1278332.27 | 700000 | -216333.86
N6395 | N6395 - Electrics | HRA | Rolling Programme | Rolling Programme HRA | 593000 | 661130.62 | 629000 | 513837.25 | 625000 | 732996.71 | 695000 | 234915.83
N6434 | N6434 - Doors and Windows | HRA | Rolling Programme | Rolling Programme HRA | 280000 | 123767.29 | 312000 | 256876.81 | 579200 | 596035.86 | 500000 | 38897.55
N7020 | N7020 - Extensions & Major Adaptions | HRA | Rolling Programme | Rolling Programme HRA | 1005000 | 650389.56 | 265000 | 709938.24 | 265000 | 53779.79 | 735000 | 1469
N7026 | N7026 - Communal Areas | HRA | Rolling Programme | Rolling Programme HRA | 358000 | 138987.15 | 194000 | 47834.24 | 198000 | 30116.04 | 213000 | 16993.44
N7029 | N7029 - HCA New Build | HRA | #N/A | #N/A | 0 | 0 | 0 | 0
N7031 | N7031 - Homes at Barton | HRA | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | 0
N7032 | N7032 - Great Estates Programme | HRA | Rolling Programme | Rolling Programme HRA | 850000 | 1018052.02 | 1764000 | 2208586.25 | 1300000 | 747182.5 | 1109000 | -146545.18
N7033 | N7033 - Energy Efficiency Initiatives | HRA | Rolling Programme | Rolling Programme HRA | 300000 | 159744.02 | 568000 | 100213.96 | 1252200 | 711871.09 | 1985000 | 208060.34
N7038 | N7038 - Insulation Works | HRA | Rolling Programme | Rolling Programme HRA | 0 | 0 | 0 | 0
N7040 | N7040 - Blackbird Leys Regeneration | HRA | Project - Development | Project - Development HRA | 200000 | 83696.05 | 605000 | 19833.42 | 209000 | 173094.78 | 325000 | 42660.81
N7041 | N7041 - Electric Heating Conversion to Gas | HRA | #N/A | #N/A |  |  | 0 | 0 | 0 | 0
N7042 | N7042 - Barton Regeneration | HRA | Rolling Programme | Rolling Programme HRA | 1986535 | 1779874.25 | 1286000 | 233979.83 | 600000 | 10127.12 | 0 | 20890.33
N7044 | N7044 - Lift Replacement Programme | HRA | Rolling Programme | Rolling Programme HRA | 240000 | 0 | 0 | 53814.4 | 306500 | 161287.13 | 125000 | 2822.33
N7046 | N7046 - Development at Mortimer Drive | HRA | Other Capital Spend | Other Capital Spend HRA | 0 | 7875.94 | 0 | 0
N7047 | N7047 - Social Rented Housing Acquisitions | HRA | Other Capital Spend | Other Capital Spend HRA | 398629 | 335923.39 | 10298000 | 10950047.61 | 2946872 | 3416327.75 | 0 | 699514.87
N7048 | N7048 - Fire doors | HRA | Rolling Programme | Rolling Programme HRA | 450000 | 870581.77 | 424000 | 85020.91 | 530000 | 31384.66 | 1500000 | 0
N7049 | N7049 - Compulsory purchase of property | HRA | Other Capital Spend | Other Capital Spend HRA | 112114 | 3512.73 | 0 | 0
N7050 | N7050 - East Oxford development | HRA | Project - Development | Project - Development HRA | 0 | 0 | 3533000 | 292647 | 3533000 | 2940 | 2813000 | 490
N7051 | N7051 - Acquisition of Additional Units | HRA | Other Capital Spend | Other Capital Spend HRA | 500000 | 0 | 2700000 | 364624.6 | 3103606 | 3205763.18 | 2000000 | -25000
N7052 | N7052 - HRA Stock Condition Survey | HRA | Project - Other | Project - Other HRA | 250000 | 80799.36 | 0 | 26470.89 | 169200 | 3976.44 | 195000 | 0
N7053 | N7053 - Development Schemes | HRA | #N/A | #N/A |  |  | 0 | 0
N7054 | N7054 - Properties Purchased From OCHL | HRA | Other Capital Spend | Other Capital Spend HRA |  |  | 11600000 | 0 | 31418629 | 23935127.19 | 74698000 | 10917255.81
N7055 | N7055 - Use Of Recycled Capital Grants | HRA | Other Capital Spend | Other Capital Spend HRA |  |  | 368000 | 0 | 0 | 340262.83 | 0 | 0
N7056 | N7056 - Affordable Housing Supply | HRA | Other Capital Spend | Other Capital Spend HRA |  |  | 3000000 | 0
N7057 | N7057 - Kitchens | HRA | Rolling Programme | Rolling Programme HRA |  |  | 0 | 809908.58 | 1228080 | 985019.57 | 0 | 93693.11
N7058 | N7058 - Bathrooms | HRA | Rolling Programme | Rolling Programme HRA |  |  | 0 | 501841.12 | 907266 | 758248.75 | 0 | 24311.86
N7059 | N7059 - Boilers Only | HRA | Rolling Programme | Rolling Programme HRA |  |  | 0 | 989083.35 | 1512780 | 837243.12 | 0 | 123112.47
N7060 | N7060 - Heating Systems | HRA | Rolling Programme | Rolling Programme HRA |  |  | 0 | 283652.74 | 272100 | 521661.03 | 0 | 55528.65
N7061 | N7061 - Northfield Hostel | HRA | Other Capital Spend | Other Capital Spend HRA |  |  |  |  | 7900000 | 38884 | 11740000 | 1415030
N7062 | N7062 - Lanham Way | HRA | Other Capital Spend | Other Capital Spend HRA |  |  |  |  | 3050000 | 171970.24 | 3555000 | 15104.76
N7063 | N7063 - Tucker / Thomson / Juniper | HRA | Other Capital Spend | Other Capital Spend HRA | [6 empty] | 1586000 | 0
N7064 | N7064 - Unallocated Site 1 | HRA | Other Capital Spend | Other Capital Spend HRA |  |  |  |  | 5026000 | 0
N7065 | N7065 - Unallocated Site 2 | HRA | Other Capital Spend | Other Capital Spend HRA |  |  |  |  | 4000000 | 0
N7066 | N7066 - Next Steps Accommodation Programme | HRA | Other Capital Spend | Other Capital Spend HRA |  |  | 0 | 595165.67 | 2392000 | 2281801.24 | 0 | 180
N7067 | N7067 - Renewal Of Fire Alarm Panels | HRA | Project - Compliance | Project - Compliance HRA |  |  |  |  | 102000 | 0 | 102000 | 0
N7068 | N7068 - Juniper | HRA | Other Capital Spend | Other Capital Spend HRA |  |  |  |  | 2607000 | 51170 | 0 | -51170
N7070 | N7070 - Major Refurbishment Masons Road | HRA | Other Capital Spend | Other Capital Spend HRA | [6 empty] | 750000 | 0
R0005 | R0005 - MT Vehicles/Plant Replacement Programme. | GF | Rolling Programme | Rolling Programme GF | 4044185 | 1677633.97 | 3265350 | 3276524.2 | 2929845 | 1305231.47 | 4277121 | 184616.28
R0010 | R0010 - Electric Vehicles | GF | Other Capital Spend | Other Capital Spend GF | 293000 | 183442.7 | 507650 | 0 | 424000 | 0
R0011 | R0011 - Grey Fleet | GF | Other Capital Spend | Other Capital Spend GF |  |  | 1800000 | 0
T2273 | T2273 - Car Parks Resurfacing | GF | Rolling Programme | Rolling Programme GF | 416707 | 248476.21 | 324287 | 288423.14 | 468231 | 61797.92 | 335864 | 161317.17
T2277 | T2277 - Food Waste Collection from Flats | GF | Project - Other | Project - Other GF | 0 | -2866.67
T2287 | T2287 - Recycling Transfer Station | GF | #N/A | #N/A | 100000 | 0 | 0 | -752.17 | 0 | 8970.75 | 0 | 234491.36
T2294 | T2294 - Pest Control Equipment | GF | Project - Other | Project - Other GF | 35000 | 27110.01 | 0 | 0
T2299 | T2299 - Controlled Parking Zones | GF | Project - Other | Project - Other GF | 200000 | 0 | 0 | 0 | 400000 | 0 | 250000 | 0
T2301 | T2301 - Depot Rationalisation | GF | Project - Development | Project - Development GF | 486000 | 605821.73 | 2153 | 171005.57 | 700000 | -503566.1 | 996663 | 0
T2302 | T2302 - Redbridge Parking | GF | #N/A | #N/A |  |  | 0 | 0
T2303 | T2303 - Cutteslowe Compactor | GF | Project - Other | Project - Other GF | 39000 | 42228.51
T2304 | T2304 - Redbridge Compactor | GF | Project - Other | Project - Other GF | 23000 | 19750
T2305 | T2305 - Parks Paths | GF | Rolling Programme | Rolling Programme GF | 90690 | 168360 | 77670 | -33840 | 0 | 0
T2306 | T2306 - Mobile Working and Handhelds | GF | Project - ICT | Project - ICT GF | 134000 | 8222.28 | 15000 | 0 | 0 | 0 | 0 | 0
T2307 | T2307 - Transformation Funding | GF | Project - ICT | Project - ICT GF | 800000 | 983132.63 | 400000 | 374569.37 | 400000 | 37075.25 | 130798 | 0
T2308 | T2308 - Additional Technology Requirements | GF | Project - ICT | Project - ICT GF |  |  | 1200000 | 55674.36 | 1464000 | 79913 | 537000 | 0
T2309 | T2309 - Cowley Marsh Extension | GF | Project - Other | Project - Other GF | [6 empty] | 0 | 0

## Budgets & Profiles (hidden)
[14 empty] | 202201 | 202202 | 202203 | 202204 | 202205 | 202206 | 202207 | 202208 | 202209 | 202210 | 202211 | 202212
Costc | Costc(T) | Original Budget 2021/22 | In-Year Adjustments | 2021/22 Latest Budget | Spend to Date | Variance | 2022/23 | 2023/24 | 2024/25 | Total Budget | Agresso Profile Key |  | Profiled? | April | May | June | July | August | September | October | November | December | January | February | March
A4820 | Upgrade Existing Tennis Courts | 35000 | 0 | 35000 | 0 | -35000 | 0 | 0 | 0 | 35000 | 11 | Twelfths Monthly |  | 2915.5 | 2915.5 | 2919 | 2915.5 | 2915.5 | 2919 | 2915.5 | 2915.5 | 2919 | 2915.5 | 2915.5 | 2919
A4833 | Horspath Sports Park | 0 | 0 | 0 | 295.9 | 295.9 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A4845 | CCTV Suite Upgrade | 68688 | 0 | 68688 | 0 | -68688 | 0 | 0 | 0 | 68688 | 11 | Twelfths Monthly |  | 5721.71 | 5721.71 | 5728.58 | 5721.71 | 5721.71 | 5728.58 | 5721.71 | 5721.71 | 5728.58 | 5721.71 | 5721.71 | 5728.58
A4847 | Rose Hill Community Centre - Parking Management | 10000 | 0 | 10000 | 0 | -10000 | 0 | 0 | 0 | 10000 | 11 | Twelfths Monthly |  | 833 | 833 | 834 | 833 | 833 | 834 | 833 | 833 | 834 | 833 | 833 | 834
A4852 | Bodycams for Community Safety Team | 60450 | 0 | 60450 | 0 | -60450 | 0 | 0 | 0 | 60450 | 11 | Twelfths Monthly |  | 5035.48 | 5035.48 | 5041.53 | 5035.48 | 5035.48 | 5041.53 | 5035.48 | 5035.48 | 5041.53 | 5035.48 | 5035.48 | 5041.53
A4853 | City Wide Cycling Infrastructure Contribution | 60000 | 2456 | 62456 | 0 | -62456 | 60000 | 60000 | 60000 | 242456 | 11 | Twelfths Monthly |  | 5202.59 | 5202.59 | 5208.59 | 5202.83 | 5202.59 | 5208.59 | 5202.83 | 5202.59 | 5208.59 | 5202.83 | 5202.83 | 5208.59
B0074 | R & D Feasibility Fund | 325180 | -170595 | 154585 | 0 | -154585 | 150000 | 400000 | 400000 | 1104585 | 11 | Twelfths Monthly |  | -126090.21 | 25504.79 | 25537.31 | 25502.89 | 25504.79 | 25537.31 | 25502.89 | 25504.79 | 25537.31 | 25502.89 | 25502.89 | 25537.31
B0075 | Stage 2 Museum of Oxford Development | 35000 | 1016395 | 1051395 | -191312.25 | -1242707.25 | 0 | 0 | 0 | 1051395 | 11 | Twelfths Monthly |  | 87581.2 | 87581.2 | 87584.7 | 87682.84 | 87581.2 | 87584.7 | 87682.84 | 87581.2 | 87584.7 | 87682.84 | 87682.84 | 87584.7
B0081 | Car Parking Oxpens | 43000 | 192355 | 235355 | 0 | -235355 | 0 | 0 | 0 | 235355 | 11 | Twelfths Monthly |  | 19605.07 | 19605.07 | 19609.37 | 19624.31 | 19605.07 | 19609.37 | 19624.31 | 19605.07 | 19609.37 | 19624.31 | 19624.31 | 19609.37
B0083 | East Oxford Community Centre | 4212439 | 218048 | 4430487 | 0 | -4430487 | 1000000 | 0 | 0 | 5430487 | 11 | Twelfths Monthly |  | 369059.57 | 369059.57 | 369480.81 | 369081.37 | 369059.57 | 369480.81 | 369081.37 | 369059.57 | 369480.81 | 369081.37 | 369081.37 | 369480.81
B0084 | Jericho Community Centre | 200000 | 0 | 200000 | 0 | -200000 | 0 | 0 | 0 | 200000 | 11 | Twelfths Monthly |  | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680
B0086 | Seacourt Park & Ride Extension | 0 | 262499 | 262499 | -313818.88 | -576317.88 | 0 | 0 | 0 | 262499 | 11 | Twelfths Monthly |  | 21866.17 | 21866.17 | 21866.17 | 21892.42 | 21866.17 | 21866.17 | 21892.42 | 21866.17 | 21866.17 | 21892.42 | 21892.42 | 21866.16
B0092 | Cave Street Development (Standingford House) | 1407500 | 68450 | 1475950 | 28607.4 | -1447342.6 | 2755000 | 1277500 | 0 | 5508450 | 11 | Twelfths Monthly |  | 122946.64 | 122946.64 | 123087.39 | 122953.48 | 122946.64 | 123087.39 | 122953.48 | 122946.64 | 123087.39 | 122953.48 | 122953.48 | 123087.39
B0096 | Bullingdon Community Centre | 1481151 | 33427 | 1514578 | 15026.1 | -1499551.9 | 0 | 0 | 0 | 1514578 | 11 | Twelfths Monthly |  | 126164.35 | 126164.35 | 126312.46 | 126167.69 | 126164.35 | 126312.46 | 126167.69 | 126164.35 | 126312.46 | 126167.69 | 126167.69 | 126312.47
B0098 | 1-3 George Street | 1635200 | 291569 | 1926769 | -14930 | -1941699 | 20000 | 0 | 0 | 1946769 | 11 | Twelfths Monthly |  | 160499.86 | 160499.86 | 160663.38 | 160529.02 | 160499.86 | 160663.38 | 160529.02 | 160499.86 | 160663.38 | 160529.02 | 160529.02 | 160663.37
B0100 | Gloucester Green Car Park (H&S) | 74979 | 187144 | 262123 | -23100 | -285223 | 0 | 0 | 0 | 262123 | 687 | B0100 - Gloucester Green Park (H&S) | Y | 15589.09 | 15589.09 | 38450.19 | 38468.91 | 44845.9 | 15589.09 | 15607.81 | 15589.09 | 15589.09 | 15607.81 | 15607.81 | 15589.09
B0101 | Capital works at Covered Market | 1012790 | 36308 | 1049098 | 38580.58 | -1010517.42 | 0 | 0 | 0 | 1049098 | 11 | Twelfths Monthly |  | 87389.87 | 87389.87 | 87491.15 | 87393.5 | 87389.87 | 87491.15 | 87393.5 | 87389.87 | 87491.15 | 87393.5 | 87393.5 | 87491.15
B0102 | Replace or refurbish Lifts | 43294 | 76190 | 119484 | 0 | -119484 | 0 | 0 | 0 | 119484 | 11 | Twelfths Monthly |  | 9953.02 | 9953.02 | 9957.35 | 9960.64 | 9953.02 | 9957.35 | 9960.64 | 9953.02 | 9957.35 | 9960.64 | 9960.64 | 9957.35
B0104 | Old Gas Works Bridges | 0 | 94911 | 94911 | 45534.09 | -49376.91 | 0 | 0 | 0 | 94911 | 11 | Twelfths Monthly |  | 62908.09 | 2908.09 | 2908.09 | 2911.58 | 2908.09 | 2908.09 | 2911.58 | 2908.09 | 2908.09 | 2911.58 | 2911.58 | 2908.09
B0106 | Covered Market Planned Maintenance - Roof | 240000 | 122023 | 362023 | 50585.02 | -311437.98 | 325000 | 325000 | 325000 | 1337023 | 11 | Twelfths Monthly |  | 30156.52 | 30156.52 | 30180.52 | 30168.72 | 30156.52 | 30180.52 | 30168.72 | 30156.52 | 30180.52 | 30168.72 | 30168.72 | 30180.52
B0108 | Floyds Row Refurbishment | 41400 | 0 | 41400 | -123651.16 | -165051.16 | 0 | 0 | 0 | 41400 | 321 | Capital Variable 3 | Y | 0 | 0 | 0 | 0 | 0 | 5477.22 | 5916.06 | 5038.38 | 5257.8 | 5257.8 | 6578.46 | 7874.28
B0110 | Covered Market Vacant Unit Works | 0 | 23938 | 23938 | -26729.29 | -50667.29 | 0 | 0 | 0 | 23938 | 11 | Twelfths Monthly |  | 1994.04 | 1994.04 | 1994.04 | 1996.43 | 1994.04 | 1994.04 | 1996.43 | 1994.04 | 1994.04 | 1996.43 | 1996.43 | 1994.04
B0111 | Town Hall Dry Risers | 37282 | 104191 | 141473 | 81784.85 | -59688.15 | 0 | 0 | 0 | 141473 | 11 | Twelfths Monthly |  | 11784.7 | 11784.7 | 11788.43 | 11795.12 | 11784.7 | 11788.43 | 11795.12 | 11784.7 | 11788.43 | 11795.12 | 11795.12 | 11788.43
B0112 | Cinema Feasibility | 40657 | 20000 | 60657 | 11900 | -48757 | 0 | 0 | 0 | 60657 | 11 | Twelfths Monthly |  | 5052.73 | 5052.73 | 5056.79 | 5054.73 | 5052.73 | 5056.79 | 5054.73 | 5052.73 | 5056.79 | 5054.73 | 5054.73 | 5056.79
B0113 | New Theatre Improvements | 0 | 60657 | 60657 | 0 | -60657 | 0 | 0 | 0 | 60657 | 11 | Twelfths Monthly |  | 5052.73 | 5052.73 | 5052.73 | 5058.79 | 5052.73 | 5052.73 | 5058.79 | 5052.73 | 5052.73 | 5058.79 | 5058.79 | 5052.73
B0114 | Diamond Place Redevelopment | 0 | 0 | 0 | 20680 | 20680 | 0 | 0 | 0 | 0 | 11 | Twelfths Monthly |  | 13360.9 | -1214.1 | -1214.1 | -1215.56 | -1214.1 | -1214.1 | -1215.56 | -1214.1 | -1214.1 | -1215.56 | -1215.56 | -1214.09
B0115 | Covered Market Masterplan | 41560 | 59571 | 101131 | 350 | -100781 | 0 | 0 | 0 | 101131 | 42 | Approved Adjustments - December | Y | 19171.11 | 3671.11 | 3671.11 | 3675.52 | 3671.11 | 3671.11 | 3675.52 | 3671.11 | 14061.11 | 14065.52 | 14065.52 | 14061.12
B0116 | Osney Mead Infrastructure | 900000 | 60000 | 960000 | 0 | -960000 | 4590000 | 540000 | 0 | 6090000 | 11 | Twelfths Monthly |  | 79968 | 79968 | 80058 | 79974 | 79968 | 80058 | 79974 | 79968 | 80058 | 79974 | 79974 | 80058
B0117 | Commercial Property | 20000000 | 0 | 20000000 | 0 | -20000000 | 0 | 0 | 0 | 20000000 | 11 | Twelfths Monthly |  | 1666000 | 1666000 | 1668000 | 1666000 | 1666000 | 1668000 | 1666000 | 1666000 | 1668000 | 1666000 | 1666000 | 1668000
B0118 | Oxford Ice Rink | 32000 | -12100 | 19900 | 5050 | -14850 | 0 | 0 | 0 | 19900 | 11 | Twelfths Monthly |  | 1657.67 | 1657.67 | 1660.87 | 1656.46 | 1657.67 | 1660.87 | 1656.46 | 1657.67 | 1660.87 | 1656.46 | 1656.46 | 1660.87
B0119 | Oxford Station Feasibility | 70000 | 68571 | 138571 | 32688 | -105883 | 0 | 0 | 0 | 138571 | 11 | Twelfths Monthly |  | 11542.96 | 11542.96 | 11549.96 | 11549.82 | 11542.96 | 11549.96 | 11549.82 | 11542.96 | 11549.96 | 11549.82 | 11549.82 | 11549.97
B0120 | Osney Bridge Feasibility | 1100000 | 283745 | 1383745 | 0 | -1383745 | 3500000 | 1340000 | 0 | 6223745 | 11 | Twelfths Monthly |  | 115265.96 | 115265.96 | 115375.96 | 115294.33 | 115265.96 | 115375.96 | 115294.33 | 115265.96 | 115375.96 | 115294.33 | 115294.33 | 115375.96
B0122 | City Cycle Schemes (Growth Deal) | 450000 | 451662 | 901662 | -98337.81 | -999999.81 | 0 | 0 | 0 | 901662 | 11 | Twelfths Monthly |  | 75108.45 | 75108.45 | 75153.45 | 75153.61 | 75108.45 | 75153.45 | 75153.61 | 75108.45 | 75153.45 | 75153.61 | 75153.61 | 75153.44
B0123 | Boswells Feasibility | 0 | 0 | 0 | 4750 | 4750 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B0124 | Port Meadow Moorings | 0 | 50000 | 50000 | -5279.22 | -55279.22 | 0 | 0 | 0 | 50000 | 11 | Twelfths Monthly |  | 14725.38 | 3205.38 | 3205.38 | 3209.23 | 3205.38 | 3205.38 | 3209.23 | 3205.38 | 3205.38 | 3209.23 | 3209.23 | 3205.38
B0125 | City Centre Restart | 0 | 100000 | 100000 | 0 | -100000 | 0 | 0 | 0 | 100000 | 11 | Twelfths Monthly |  | 8330 | 8330 | 8330 | 8340 | 8330 | 8330 | 8340 | 8330 | 8330 | 8340 | 8340 | 8330
B0126 | Asset Surveys | 0 | 300000 | 300000 | 7642.82 | -292357.18 | 0 | 0 | 0 | 300000 | 11 | Twelfths Monthly |  | 24990 | 24990 | 24990 | 25020 | 24990 | 24990 | 25020 | 24990 | 24990 | 25020 | 25020 | 24990
B0127 | ZEZ Phase 1 Feasibility | 0 | 141000 | 141000 | 0 | -141000 | 0 | 0 | 0 | 141000 | 11 | Twelfths Monthly |  | 11745.3 | 11745.3 | 11745.3 | 11759.4 | 11745.3 | 11745.3 | 11759.4 | 11745.3 | 11745.3 | 11759.4 | 11759.4 | 11745.3
B0128 | Greenways Cycling Project | 0 | 106000 | 106000 | 0 | -106000 | 0 | 0 | 0 | 106000 | 11 | Twelfths Monthly |  | 8829.8 | 8829.8 | 8829.8 | 8840.4 | 8829.8 | 8829.8 | 8840.4 | 8829.8 | 8829.8 | 8840.4 | 8840.4 | 8829.8
B0129 | Town Hall Options | 0 | 50000 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 11 | Twelfths Monthly |  | 4165 | 4165 | 4165 | 4170 | 4165 | 4165 | 4170 | 4165 | 4165 | 4170 | 4170 | 4165
B0130 | CIL Feasibility | 200000 | 0 | 200000 | 0 | -200000 | 0 | 0 | 0 | 200000 | 11 | Twelfths Monthly |  | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680 | 16660 | 16660 | 16680
B0131 | Meanwhile In Oxfordshire | 1875000 | -30150 | 1844850 | 54904.17 | -1789945.83 | 0 | 0 | 0 | 1844850 | 11 | Twelfths Monthly |  | 153676.01 | 153676.01 | 153863.51 | 153672.99 | 153676.01 | 153863.51 | 153672.99 | 153676.01 | 153863.51 | 153672.99 | 153672.99 | 153863.51
B0132 | Coach Parking Feasibility | 20000 | 0 | 20000 | 0 | -20000 | 0 | 0 | 0 | 20000 | 11 | Twelfths Monthly |  | 1666 | 1666 | 1668 | 1666 | 1666 | 1668 | 1666 | 1666 | 1668 | 1666 | 1666 | 1668
B0133 | Cemetery Feasibility | 0 | 40000 | 40000 | 0 | -40000 | 0 | 0 | 0 | 40000 | 11 | Twelfths Monthly |  | 3332 | 3332 | 3332 | 3336 | 3332 | 3332 | 3336 | 3332 | 3332 | 3336 | 3336 | 3332
B0134 | Shotover SSI Management Plan | 0 | 20000 | 20000 | 0 | -20000 | 0 | 0 | 0 | 20000 | 11 | Twelfths Monthly |  | 1666 | 1666 | 1666 | 1668 | 1666 | 1666 | 1668 | 1666 | 1666 | 1668 | 1668 | 1666
B0135 | CCTV Gloucester Green Car Park | 0 | 10000 | 10000 | 0 | -10000 | 0 | 0 | 0 | 10000 | 11 | Twelfths Monthly |  | 833 | 833 | 833 | 834 | 833 | 833 | 834 | 833 | 833 | 834 | 834 | 833
B0136 | Covered Market CCTV | 0 | 100000 | 100000 | 0 | -100000 | 0 | 0 | 0 | 100000 | 11 | Twelfths Monthly |  | 8330 | 8330 | 8330 | 8340 | 8330 | 8330 | 8340 | 8330 | 8330 | 8340 | 8340 | 8330
B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | 0 | 26000 | 26000 | 0 | -26000 | 0 | 0 | 0 | 26000 | 11 | Twelfths Monthly |  | 2165.8 | 2165.8 | 2165.8 | 2168.4 | 2165.8 | 2165.8 | 2168.4 | 2165.8 | 2165.8 | 2168.4 | 2168.4 | 2165.8
C3044 | Software Licences | 245000 | 0 | 245000 | 233158.75 | -11841.25 | 245000 | 245000 | 245000 | 980000 | 27 | Annual (October) | Y | 0 | 0 | 0 | 0 | 0 | 0 | 245000 | 0 | 0 | 0 | 0 | 0
C3057 | Housing System Replacement | 0 | 128595 | 128595 | 69636.65 | -58958.35 | 0 | 0 | 0 | 128595 | 11 | Twelfths Monthly |  | 10711.96 | 10711.96 | 10711.96 | 10724.82 | 10711.96 | 10711.96 | 10724.82 | 10711.96 | 10711.96 | 10724.82 | 10724.82 | 10711.96
C3058 | CRM Lagan Replacement | 0 | 120275 | 120275 | 0 | -120275 | 0 | 0 | 0 | 120275 | 11 | Twelfths Monthly |  | 10018.91 | 10018.91 | 10018.91 | 10030.93 | 10018.91 | 10018.91 | 10030.93 | 10018.91 | 10018.91 | 10030.93 | 10030.93 | 10018.9
C3060 | End-Point Devices (Desktops/Laptops) | 60000 | 5775 | 65775 | 17160.53 | -48614.47 | 150000 | 150000 | 150000 | 515775 | 11 | Twelfths Monthly |  | 5479.06 | 5479.06 | 5485.06 | 5479.63 | 5479.06 | 5485.06 | 5479.63 | 5479.06 | 5485.06 | 5479.63 | 5479.63 | 5485.05
C3066 | Telephony Device Refresh | 0 | 9271 | 9271 | 6792.32 | -2478.68 | 60000 | 60000 | 60000 | 189271 | 11 | Twelfths Monthly |  | 772.27 | 772.27 | 772.27 | 773.2 | 772.27 | 772.27 | 773.2 | 772.27 | 772.27 | 773.2 | 773.2 | 772.28
C3067 | Paris Payment System, Replacement / PCI DSS | 17924 | 84760 | 102684 | 0 | -102684 | 0 | 0 | 0 | 102684 | 39 | Approved Adjustments - September | Y | 7060.51 | 7060.51 | 7060.51 | 7068.98 | 7060.51 | 9621.85 | 9630.32 | 9621.85 | 9621.85 | 9630.32 | 9630.32 | 9616.47
C3068 | Windows 2008 Server Replacement | 121128 | 47676 | 168804 | -1140.01 | -169944.01 | 0 | 0 | 0 | 168804 | 40 | Approved Adjustments - October | Y | 3971.41 | 3971.41 | 3971.41 | 3976.18 | 3971.41 | 3971.41 | 24168.22 | 24163.45 | 24163.45 | 24168.22 | 24168.22 | 24139.22
C3070 | Business Process Automation Full Rollout | 0 | 19515 | 19515 | 0 | -19515 | 0 | 0 | 0 | 19515 | 11 | Twelfths Monthly |  | 1625.6 | 1625.6 | 1625.6 | 1627.55 | 1625.6 | 1625.6 | 1627.55 | 1625.6 | 1625.6 | 1627.55 | 1627.55 | 1625.6
C3072 | Council Website Replacement | 0 | 36170 | 36170 | 0 | -36170 | 0 | 0 | 0 | 36170 | 11 | Twelfths Monthly |  | 3012.96 | 3012.96 | 3012.96 | 3016.58 | 3012.96 | 3012.96 | 3016.58 | 3012.96 | 3012.96 | 3016.58 | 3016.58 | 3012.96
C3073 | CorVu Reporting System Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C3078 | Revs and Bens System Replacement | 245000 | 218737 | 463737 | -2.25 | -463739.25 | 0 | 0 | 0 | 463737 | 32 | Annual (March) | Y | 18220.79 | 18220.79 | 18220.79 | 18242.67 | 18220.79 | 18220.79 | 18242.67 | 18220.79 | 18220.79 | 18242.67 | 18242.67 | 263220.79
E3511 | Essential Repair Grants | 24948 | 6572.61 | 31520.61 | 4990 | -26530.61 | 15000 | 15000 | 15000 | 76520.61 | 11 | Twelfths Monthly |  | 2625.66 | 2625.66 | 2628.15 | 2626.32 | 2625.66 | 2628.15 | 2626.32 | 2625.66 | 2628.15 | 2626.32 | 2626.32 | 2628.16
E3521 | Disabled Facilities Grants | 1282378 | 135000 | 1417378 | 95865.62 | -1321512.38 | 1200000 | 1200000 | 1200000 | 5017378 | 11 | Twelfths Monthly |  | 118067.59 | 118067.59 | 118195.83 | 118081.09 | 118067.59 | 118195.83 | 118081.09 | 118067.59 | 118195.83 | 118081.09 | 118081.09 | 118195.83
E3557 | Oxford and Abingdon Flood Alleviation Scheme | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E3558 | Go Ultra Low Oxford - On Street | 4545 | 556605 | 561150 | 49855.86 | -511294.14 | 0 | 0 | 0 | 561150 | 11 | Twelfths Monthly |  | 46743.8 | 46743.8 | 46744.25 | 46799.46 | 46743.8 | 46744.25 | 46799.46 | 46743.8 | 46744.25 | 46799.46 | 46799.46 | 46744.26
E3560 | Go Ultra Low Oxford - Taxis | 0 | 203220 | 203220 | 0 | -203220 | 0 | 0 | 0 | 203220 | 11 | Twelfths Monthly |  | 16928.23 | 16928.23 | 16928.23 | 16948.55 | 16928.23 | 16928.23 | 16948.55 | 16928.23 | 16928.23 | 16948.55 | 16948.55 | 16928.23
E3561 | Additional DFG Funding | 0 | 98682 | 98682 | 25182.55 | -73499.45 | 0 | 0 | 0 | 98682 | 11 | Twelfths Monthly |  | 8220.21 | 8220.21 | 8220.21 | 8230.08 | 8220.21 | 8220.21 | 8230.08 | 8220.21 | 8220.21 | 8230.08 | 8230.08 | 8220.21
E3562 | OxPops (Electric Vehicle Charging) | 35806 | 6349 | 42155 | 0 | -42155 | 0 | 0 | 0 | 42155 | 107 | E3562 - Ox Pops (Electric Vehicle Charging) | Y | 1592.31 | 20687.65 | 528.87 | 529.51 | 528.87 | 528.87 | 529.51 | 15112.65 | 528.87 | 529.51 | 529.51 | 528.87
E3563 | Clean Bus Technology Grants | 0 | 564350 | 564350 | 0 | -564350 | 0 | 0 | 0 | 564350 | 11 | Twelfths Monthly |  | 47010.36 | 47010.36 | 47010.36 | 47066.79 | 47010.36 | 47010.36 | 47066.79 | 47010.36 | 47010.36 | 47066.79 | 47066.79 | 47010.36
E3565 | Decarbonisation Fund - OCC element | 7538547 | -11250 | 7527297 | 438337.56 | -7088959.44 | 0 | 0 | 0 | 7527297 | 11 | Twelfths Monthly |  | 627023.83 | 627023.83 | 627777.69 | 627022.71 | 627023.83 | 627777.69 | 627022.71 | 627023.83 | 627777.69 | 627022.71 | 627022.71 | 627777.69
E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | 3385000 | 0 | 3385000 | 0 | -3385000 | 0 | 0 | 0 | 3385000 | 11 | Twelfths Monthly |  | 281970.5 | 281970.5 | 282309 | 281970.5 | 281970.5 | 282309 | 281970.5 | 281970.5 | 282309 | 281970.5 | 281970.5 | 282309
E3567 | Town Hall Lighting Upgrade (SALIX) | 0 | 90000 | 90000 | 0 | -90000 | 0 | 0 | 0 | 90000 | 11 | Twelfths Monthly |  | 7497 | 7497 | 7497 | 7506 | 7497 | 7497 | 7506 | 7497 | 7497 | 7506 | 7506 | 7497
F7007 | Woodfarm / Headington Community Centre | 8000 | 8397 | 16397 | 0 | -16397 | 0 | 0 | 0 | 16397 | 11 | Twelfths Monthly |  | 1365.87 | 1365.87 | 1366.67 | 1366.71 | 1365.87 | 1366.67 | 1366.71 | 1365.87 | 1366.67 | 1366.71 | 1366.71 | 1366.67
F7011 | Headington Environmental Improvements | 29629 | 1152 | 30781 | 0 | -30781 | 0 | 0 | 0 | 30781 | 11 | Twelfths Monthly |  | 2564.06 | 2564.06 | 2567.02 | 2564.18 | 2564.06 | 2567.02 | 2564.18 | 2564.06 | 2567.02 | 2564.18 | 2564.18 | 2567.01
F7024 | St Clements Environmental Improvements | 20000 | 30000 | 50000 | 0 | -50000 | 0 | 0 | 0 | 50000 | 11 | Twelfths Monthly |  | 4165 | 4165 | 4167 | 4168 | 4165 | 4167 | 4168 | 4165 | 4167 | 4168 | 4168 | 4167
M5019 | Purchase Of Homeless Properties | 0 | 0 | 0 | 17.64 | 17.64 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M5025 | Barton Park - purchase by Council | 5736037 | 2495819 | 8231856 | 0 | -8231856 | 7600000 | 8250000 | 8300000 | 32381856 | 11 | Twelfths Monthly |  | 685713.6 | 685713.6 | 686287.21 | 685963.18 | 685713.6 | 686287.21 | 685963.18 | 685713.6 | 686287.21 | 685963.18 | 685963.18 | 686287.21
M5026 | Housing Company Loans (excl Barton Park) | 32200000 | -5665831 | 26534169 | 305000 | -26229169 | 30200000 | 45500000 | 15000000 | 117234169 | 11 | Twelfths Monthly |  | 2210296.28 | 2210296.28 | 2213516.28 | 2209729.7 | 2210296.28 | 2213516.28 | 2209729.7 | 2210296.28 | 2213516.28 | 2209729.7 | 2209729.7 | 2213516.27
M5031 | Barton Phase 2 - Loan To Housing Company | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M5032 | Barton Park - Loan to OCHL | 5736037 | 2462819 | 8198856 | 0 | -8198856 | 7600000 | 8250000 | 8300000 | 32348856 | 11 | Twelfths Monthly |  | 682964.7 | 682964.7 | 683538.31 | 683210.99 | 682964.7 | 683538.31 | 683210.99 | 682964.7 | 683538.31 | 683210.99 | 683210.99 | 683538.31
M5033 | Blackbird Leys Regeneration (GF element) | 452790 | 1648 | 454438 | 0 | -454438 | 27808162 | 2470344 | 3671682 | 34404626 | 11 | Twelfths Monthly |  | 18927.34 | 18927.34 | 18949.98 | 18927.42 | 18927.34 | 18949.98 | 18927.42 | 18927.34 | 18949.98 | 18927.42 | 18927.42 | 18949.98
M5034 | Affordable Housing Supply | 0 | 3000000 | 3000000 | 0 | -3000000 | 0 | 0 | 0 | 3000000 | 11 | Twelfths Monthly |  | 249900 | 249900 | 249900 | 250200 | 249900 | 249900 | 250200 | 249900 | 249900 | 250200 | 250200 | 249900
M5035 | Growth Deal RP Funding | 6900000 | 347000 | 7247000 | 0 | -7247000 | 0 | 0 | 0 | 7247000 | 11 | Twelfths Monthly |  | 603675.1 | 603675.1 | 604365.1 | 603709.8 | 603675.1 | 604365.1 | 603709.8 | 603675.1 | 604365.1 | 603709.8 | 603709.8 | 604365.1
N6384 | Tower Blocks | 200200 | 798649 | 998849 | -550131.65 | -1548980.65 | 0 | 0 | 0 | 998849 | 521 | N6384 TB | Y | 6991.94 | 6991.94 | 6991.94 | 6991.94 | 6991.94 | 6991.94 | 99884.9 | 319631.68 | 9988.49 | 9988.49 | 9988.49 | 507415.29
N6385 | Adaptations for disabled | 704000 | 0 | 704000 | -13774.16 | -717774.16 | 756000 | 810000 | 810000 | 3080000 | 376 | BS Producitve Per Head | Y | 54700.8 | 48294.4 | 74412.8 | 48505.6 | 61318.4 | 54982.4 | 61459.2 | 71174.4 | 41536 | 54982.4 | 58220.8 | 74412.8
N6386 | Structural | 846600 | 386866.62 | 1233466.62 | 2626.71 | -1230839.91 | 666000 | 232000 | 232000 | 2363466.62 | 467 | Structural N6386 | Y | 102587.71 | 102606.93 | 102691.59 | 102645.41 | 103010.45 | 102730.02 | 102683.84 | 102645.36 | 102864.53 | 102856.78 | 102856.78 | 103287.25
N6387 | Controlled Entry | 312500 | 58583.43 | 371083.43 | 48230 | -322853.43 | 83000 | 87000 | 87000 | 628083.43 | 36 | Approved Adjustments - June | Y | 0.04 | 0.04 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34 | 37108.34
N6388 | Major Voids | 472000 | 0 | 472000 | 14846.88 | -457153.12 | 515000 | 560000 | 560000 | 2107000 | 580 | N6388 Major Voids | Y | 39317.6 | 39317.6 | 39364.8 | 39317.6 | 39317.6 | 39364.8 | 39317.6 | 39317.6 | 39364.8 | 39317.6 | 39317.6 | 39364.8
N6389 | Damp-proof works (K&B) | 119000 | 25006 | 144006 | 14600 | -129406 | 122000 | 137000 | 137000 | 540006 | 11 | Twelfths Monthly |  | 11995.7 | 11995.7 | 12007.6 | 11998.2 | 11995.7 | 12007.6 | 11998.2 | 11995.7 | 12007.6 | 11998.2 | 11998.2 | 12007.6
N6390 | Kitchens & Bathrooms | 0 | 0 | 0 | 0 | 0 | 2695000 | 2905000 | 2905000 | 8505000 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N6391 | Heating | 0 | 0 | 0 | 0 | 0 | 2265000 | 2306000 | 2306000 | 6877000 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N6392 | Roofing | 1040000 | 263521 | 1303521 | -179380.75 | -1482901.75 | 700000 | 700000 | 700000 | 3403521 | 488 | Roofing | Y | 108583.3 | 108583.3 | 108687.3 | 108609.65 | 108583.3 | 108687.3 | 108609.65 | 108583.3 | 108687.3 | 108609.65 | 108609.65 | 108687.3
N6395 | Electrics | 625000 | 635391 | 1260391 | 44016.18 | -1216374.82 | 625000 | 653000 | 653000 | 3191391 | 378 | Electric Rewires N6395 | Y | 104990.57 | 104990.57 | 105053.07 | 105054.11 | 104990.57 | 105053.07 | 105054.11 | 104990.57 | 105053.07 | 105054.11 | 105054.11 | 105053.07
N6434 | Doors and Windows | 579200 | 23923.19 | 603123.19 | 3635.7 | -599487.49 | 500000 | 500000 | 500000 | 2103123.19 | 481 | Doors and Windows | Y | 18093.71 | 18093.71 | 18093.71 | 18093.71 | 18093.71 | 18093.71 | 18093.71 | 30156.17 | 18093.71 | 138718.31 | 138718.31 | 150780.77
N7020 | Extensions & Major Adaptions | 265000 | 159672 | 424672 | -35266.33 | -459938.33 | 278000 | 290000 | 290000 | 1282672 | 583 | N7020 - Extensions & Major Adaptations | Y | 30697.35 | 37709.08 | 33728.88 | 35731.72 | 35705.73 | 35732.23 | 35731.72 | 35705.73 | 35732.23 | 35731.72 | 35731.72 | 36733.9
N7026 | Communal Areas | 198000 | 350889 | 548889 | -1258.89 | -550147.89 | 213000 | 229000 | 229000 | 1219889 | 573 | Communal Areas | Y | 1305.98 | 17302.31 | 1305.98 | 22635.99 | 1305.98 | 11970.2 | 11971.77 | 33298.64 | 1305.98 | 91953.42 | 107949.75 | 246583.04
N7031 | Homes at Barton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N7032 | Great Estates Programme | 1300000 | -73563 | 1226437 | 62633.31 | -1163803.69 | 1109000 | 1163000 | 1163000 | 4661437 | 493 | N7032 Great Estates CP | Y | 24528.74 | 12264.37 | 30660.92 | 49057.48 | 0 | 331137.99 | 0 | 257551.77 | 386327.65 | 134908.07 | 0 | 0
N7033 | Energy Efficiency Initiatives | 1252200 | 300586.04 | 1552786.04 | 33812.41 | -1518973.63 | 1985000 | 2000000 | 2000000 | 7537786.04 | 505 | N7033 Energy Efficiency Initiatives | Y | 0 | 37266.86 | 46583.58 | 55900.3 | 93167.16 | 108695.02 | 15527.86 | 15527.86 | 0 | 310557.2 | 310557.2 | 559002.96
N7040 | Blackbird Leys Regeneration | 209000 | 64166 | 273166 | 3300 | -269866 | 152000 | 3259000 | 296000 | 3980166 | 483 | BBL Regeneration | Y | 0 | 0 | 0 | 54633.2 | 0 | 0 | 0 | 0 | 0 | 54633.2 | 81949.8 | 81949.8
N7041 | Electric Heating Conversion to Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N7042 | Barton Regeneration | 600000 | 28276.92 | 628276.92 | -10720.13 | -638997.05 | 0 | 0 | 0 | 628276.92 | 499 | N7042 Barton Regeneration | Y | -0.03 | 18848.29 | 31413.83 | 43979.39 | 31413.83 | 50262.15 | 50262.16 | 81676.01 | 94241.56 | 75393.25 | 75393.25 | 75393.24
N7044 | Lift Replacement Programme | 306500 | 103686 | 410186 | 4987 | -405199 | 0 | 0 | 0 | 410186 | 31 | Annual (February) | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410186 | 0
N7047 | Social Rented Housing Acquisitions | 2946872 | -852626 | 2094246 | 1126903.96 | -967342.04 | 0 | 0 | 0 | 2094246 | 647 | N7047 - Social Renting Housing Acquisitions | Y | 180105.15 | 686912.7 | 255498 | 0 | 251309.52 | 0 | 251309.52 | 0 | 251309.52 | 0 | 217801.59 | 0
N7048 | Fire doors | 530000 | 338979 | 868979 | -6021.18 | -875000.18 | 580000 | 580000 | 580000 | 2608979 | 699 | N7048 Fire doors | Y | 0 | 0 | 112967.27 | 60828.53 | 69518.32 | 78208.11 | 86897.9 | 95587.69 | 104277.48 | 86897.9 | 86897.9 | 86897.9
N7050 | East Oxford development | 3533000 | -292647 | 3240353 | 0 | -3240353 | 7067000 | 0 | 0 | 10307353 | 696 | N7050 East Oxford development | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810088.25 | 810088.25 | 810088.25 | 810088.25
N7051 | Acquisition of Additional Units | 3103606 | 92475 | 3196081 | -6205.23 | -3202286.23 | 0 | 0 | 0 | 3196081 | 697 | N7051 Acquisition of Additional Units | Y | 0 | 0 | 0 | 95882.43 | 0 | 0 | 0 | 1278432.4 | 0 | 543333.77 | 639216.2 | 639216.2
N7052 | HRA Stock Condition Survey | 169200 | -26471 | 142729 | 0 | -142729 | 0 | 0 | 0 | 142729 | 698 | N7052 HRA Stock Condition Survey | Y | 0 | 0 | 0 | 0 | 0 | 0 | 23792.92 | 23792.92 | 23792.92 | 23792.92 | 23792.92 | 23764.38
N7054 | Properties Purchased From OCHL | 31418629 | 3647432 | 35066061 | 770000 | -34296061 | 46131500 | 45064900 | 69977000 | 196239461 | 32 | Annual (March) | Y | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34296061
N7055 | Use Of Recycled Capital Grants | 0 | 368000 | 368000 | 0 | -368000 | 0 | 0 | 0 | 368000 | 11 | Twelfths Monthly |  | 0 | 0 | -36.8 | 36.8 | 0 | -36.8 | 36.8 | 0 | -36.8 | 36.8 | 36.8 | 367963.2
N7057 | Kitchens | 1228080 | 343096 | 1571176 | -5836.47 | -1577012.47 | 0 | 0 | 0 | 1571176 | 373 | N7057 | Y | 130878.96 | 130878.96 | 131001.77 | 130913.27 | 130878.96 | 131001.77 | 130913.27 | 130878.96 | 131001.77 | 130913.27 | 130913.27 | 131001.77
N7058 | Bathrooms | 907266 | 214400 | 1121666 | 41708.07 | -1079957.93 | 0 | 0 | 0 | 1121666 | 372 | N7058 | Y | 93434.78 | 93434.78 | 93525.5 | 93456.22 | 93434.78 | 93525.5 | 93456.22 | 93434.78 | 93525.5 | 93456.22 | 93456.22 | 93525.5
N7059 | Boilers Only | 1512780 | 0 | 1512780 | 62252.56 | -1450527.44 | 0 | 0 | 0 | 1512780 | 371 | N7059 | Y | 126014.57 | 126014.57 | 126165.85 | 126014.57 | 126014.57 | 126165.85 | 126014.57 | 126014.57 | 126165.85 | 126014.57 | 126014.57 | 126165.85
N7060 | Heating Systems | 272100 | -212100 | 60000 | 19947.11 | -40052.89 | 0 | 0 | 0 | 60000 | 374 | N7060 | Y | 4998 | 4998 | 5025.21 | 4976.79 | 4998 | 5025.21 | 4976.79 | 4998 | 5025.21 | 4976.79 | 4976.79 | 5025.21
N7061 | Northfield Hostel | 7900000 | 0 | 7900000 | 0 | -7900000 | 5600000 | 0 | 0 | 13500000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7900000
N7062 | Lanham Way | 3050000 | 0 | 3050000 | 0 | -3050000 | 2460000 | 459000 | 0 | 5969000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050000
N7064 | Unallocated Site 1 | 5026000 | 0 | 5026000 | 0 | -5026000 | 0 | 0 | 0 | 5026000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5026000
N7065 | Unallocated Site 2 | 4000000 | 0 | 4000000 | 0 | -4000000 | 0 | 0 | 0 | 4000000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000
N7066 | Next Steps Accommodation Programme | 2392000 | 600584.33 | 2992584.33 | 413561.2 | -2579023.13 | 0 | 0 | 0 | 2992584.33 | 32 | Annual (March) | Y | 213000.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 2779584.29
N7067 | Renewal Of Fire Alarm Panels | 102000 | 0 | 102000 | 0 | -102000 | 0 | 0 | 0 | 102000 | 11 | Twelfths Monthly |  | 8496.6 | 8496.6 | 8506.8 | 8496.6 | 8496.6 | 8506.8 | 8496.6 | 8496.6 | 8506.8 | 8496.6 | 8496.6 | 8506.8
N7068 | Tucker/Thomson/Juniper | 2607000 | 0 | 2607000 | 0 | -2607000 | 0 | 0 | 0 | 2607000 | 11 | Twelfths Monthly |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607000
R0005 | MT Vehicles/Plant Replacement Programme. | 2929845 | 1405444 | 4335289 | 98020.48 | -4237268.52 | 3525562 | 2665952 | 2134220 | 12661023 | 11 | Twelfths Monthly |  | 361129.58 | 361129.58 | 361422.56 | 361270.12 | 361129.58 | 361422.56 | 361270.12 | 361129.58 | 361422.56 | 361270.12 | 361270.12 | 361422.57
R0010 | Electric Vehicles | 424000 | -424000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | Twelfths Monthly |  | 0 | 0 | 42.4 | -42.4 | 0 | 42.4 | -42.4 | 0 | 42.4 | -42.4 | -42.4 | 42.4
T2273 | Car Parks Resurfacing | 468231 | 35864 | 504095 | 0 | -504095 | 300000 | 300000 | 300000 | 1404095 | 588 | B1184NE20 – PPJ | Y | 2987.47 | 12352.09 | 109275.91 | 43258.93 | 34358.95 | 32954.25 | 31084.92 | 47937.65 | 31081.33 | 42322.46 | 53560.01 | 62921.04
T2287 | Recycling Transfer Station | 0 | 18752 | 18752 | 8970.75 | -9781.25 | 0 | 0 | 0 | 18752 | 11 | Twelfths Monthly |  | 1562.04 | 1562.04 | 1562.04 | 1563.92 | 1562.04 | 1562.04 | 1563.92 | 1562.04 | 1562.04 | 1563.92 | 1563.92 | 1562.04
T2299 | Controlled Parking Zones | 400000 | -150000 | 250000 | 0 | -250000 | 250000 | 0 | 0 | 500000 | 32 | Annual (March) | Y | -24990 | -24990 | -24990 | -25020 | -24990 | -24990 | -25020 | -24990 | -24990 | -25020 | -25020 | 525010
T2301 | Depot Rationalisation | 700000 | 796663 | 1496663 | 0 | -1496663 | 6000000 | 5179718 | 0 | 12676381 | 11 | Twelfths Monthly |  | 124672.03 | 124672.03 | 124742.03 | 124751.7 | 124672.03 | 124742.03 | 124751.7 | 124672.03 | 124742.03 | 124751.7 | 124751.7 | 124742.02
T2305 | Parks Paths | 0 | 33840 | 33840 | 0 | -33840 | 0 | 0 | 0 | 33840 | 11 | Twelfths Monthly |  | 2818.87 | 2818.87 | 2818.87 | 2822.26 | 2818.87 | 2818.87 | 2822.26 | 2818.87 | 2818.87 | 2822.26 | 2822.26 | 2818.87
T2306 | Mobile Working and Handhelds | 0 | 140778 | 140778 | 0 | -140778 | 0 | 0 | 0 | 140778 | 11 | Twelfths Monthly |  | 11726.81 | 11726.81 | 11726.81 | 11740.89 | 11726.81 | 11726.81 | 11740.89 | 11726.81 | 11726.81 | 11740.89 | 11740.89 | 11726.81
T2307 | Transformation Funding | 400000 | -157702 | 242298 | 0 | -242298 | 0 | 0 | 0 | 242298 | 11 | Twelfths Monthly |  | 20183.42 | 20183.42 | 20223.42 | 20167.65 | 20183.42 | 20223.42 | 20167.65 | 20183.42 | 20223.42 | 20167.65 | 20167.65 | 20223.43
T2308 | Additional Technology Requirements | 1464000 | 1144326 | 2608326 | 0 | -2608326 | 0 | 0 | 0 | 2608326 | 11 | Twelfths Monthly |  | 217273.56 | 217273.56 | 217419.96 | 217387.99 | 217273.56 | 217419.96 | 217387.99 | 217273.56 | 217419.96 | 217387.99 | 217387.99 | 217419.96
|  | 186309148 | 19656312.14 | 205965460.14 | 2811533.07 | -203153927.07 | 172106224 | 140163414 | 123585902 | 641821000.14 |  |  |  | 11717281.23 | 11380020.43 | 11255870.2 | 11060714.01 | 11133778.07 | 11249181.27 | 11462078.14 | 12833821.09 | 12358425.52 | 12954267.6 | 13602339.09 | 74730464.85
| Count | 129 | 129 | 129 | 129 | 129 | [6 empty] | 36

## Profile Data 280621 (hidden)
Cost / Period Ref | Cost Centre | Cost Centre(T) | Account | Period | Batch | Transaction id | Version | Version(T) | Amount | Profile | Profile(T) | Note | User
A4820202201 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202201 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202202 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202202 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202203 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202203 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202204 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202204 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202205 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202205 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202206 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202206 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202207 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202207 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202208 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202208 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202209 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202209 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202210 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202210 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202211 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202211 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4820202212 | A4820 | Upgrade Existing Tennis Courts | Y000 | 202212 | OX-1003076 | 518014 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202201 | A4845 | CCTV Suite Upgrade | Y000 | 202201 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202202 | A4845 | CCTV Suite Upgrade | Y000 | 202202 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202203 | A4845 | CCTV Suite Upgrade | Y000 | 202203 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5728.58 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202204 | A4845 | CCTV Suite Upgrade | Y000 | 202204 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202205 | A4845 | CCTV Suite Upgrade | Y000 | 202205 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202206 | A4845 | CCTV Suite Upgrade | Y000 | 202206 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5728.58 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202207 | A4845 | CCTV Suite Upgrade | Y000 | 202207 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202208 | A4845 | CCTV Suite Upgrade | Y000 | 202208 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202209 | A4845 | CCTV Suite Upgrade | Y000 | 202209 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5728.58 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202210 | A4845 | CCTV Suite Upgrade | Y000 | 202210 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202211 | A4845 | CCTV Suite Upgrade | Y000 | 202211 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5721.71 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4845202212 | A4845 | CCTV Suite Upgrade | Y000 | 202212 | OX-1003076 | 518013 | 2021/22 CAP0 | 2021/22 Capital Original | 5728.58 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202201 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202201 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202202 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202202 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202203 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202203 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 834 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202204 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202204 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202205 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202205 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202206 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202206 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 834 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202207 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202207 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202208 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202208 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202209 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202209 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 834 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202210 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202210 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202211 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202211 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 833 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4847202212 | A4847 | Rose Hill Community Centre - Parking Management | Y000 | 202212 | OX-1003076 | 518012 | 2021/22 CAP0 | 2021/22 Capital Original | 834 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202201 | A4848 | Barton Fit Trail | Y000 | 202201 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202202 | A4848 | Barton Fit Trail | Y000 | 202202 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202203 | A4848 | Barton Fit Trail | Y000 | 202203 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.89 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202204 | A4848 | Barton Fit Trail | Y000 | 202204 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202205 | A4848 | Barton Fit Trail | Y000 | 202205 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202206 | A4848 | Barton Fit Trail | Y000 | 202206 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.89 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202207 | A4848 | Barton Fit Trail | Y000 | 202207 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202208 | A4848 | Barton Fit Trail | Y000 | 202208 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202209 | A4848 | Barton Fit Trail | Y000 | 202209 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.89 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202210 | A4848 | Barton Fit Trail | Y000 | 202210 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202211 | A4848 | Barton Fit Trail | Y000 | 202211 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.18 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202212 | A4848 | Barton Fit Trail | Y000 | 202212 | OX-1003076 | 518011 | 2021/22 CAP0 | 2021/22 Capital Original | 590.89 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4848202201 | A4848 | Barton Fit Trail | Y000 | 202201 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202202 | A4848 | Barton Fit Trail | Y000 | 202202 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202203 | A4848 | Barton Fit Trail | Y000 | 202203 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.89 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202204 | A4848 | Barton Fit Trail | Y000 | 202204 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202205 | A4848 | Barton Fit Trail | Y000 | 202205 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202206 | A4848 | Barton Fit Trail | Y000 | 202206 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.89 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202207 | A4848 | Barton Fit Trail | Y000 | 202207 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202208 | A4848 | Barton Fit Trail | Y000 | 202208 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202209 | A4848 | Barton Fit Trail | Y000 | 202209 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.89 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202210 | A4848 | Barton Fit Trail | Y000 | 202210 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202211 | A4848 | Barton Fit Trail | Y000 | 202211 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.18 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4848202212 | A4848 | Barton Fit Trail | Y000 | 202212 | OX-1003096 | 518590 | 2021/22 CAP0 | 2021/22 Capital Original | -590.89 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4852202201 | A4852 | Bodycams for Community Safety Team | Y000 | 202201 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202202 | A4852 | Bodycams for Community Safety Team | Y000 | 202202 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202203 | A4852 | Bodycams for Community Safety Team | Y000 | 202203 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5041.53 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202204 | A4852 | Bodycams for Community Safety Team | Y000 | 202204 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202205 | A4852 | Bodycams for Community Safety Team | Y000 | 202205 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202206 | A4852 | Bodycams for Community Safety Team | Y000 | 202206 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5041.53 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202207 | A4852 | Bodycams for Community Safety Team | Y000 | 202207 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202208 | A4852 | Bodycams for Community Safety Team | Y000 | 202208 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202209 | A4852 | Bodycams for Community Safety Team | Y000 | 202209 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5041.53 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202210 | A4852 | Bodycams for Community Safety Team | Y000 | 202210 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202211 | A4852 | Bodycams for Community Safety Team | Y000 | 202211 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5035.48 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4852202212 | A4852 | Bodycams for Community Safety Team | Y000 | 202212 | OX-1003076 | 518010 | 2021/22 CAP0 | 2021/22 Capital Original | 5041.53 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202201 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202201 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202202 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202202 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202203 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202203 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202204 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202204 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202205 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202205 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202206 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202206 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202207 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202207 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202208 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202208 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202209 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202209 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202210 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202210 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202211 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202211 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202212 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202212 | OX-1003076 | 518009 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4853202201 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202201 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202202 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202202 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202203 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202203 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202204 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202204 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.83 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202205 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202205 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202206 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202206 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202207 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202207 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.83 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202208 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202208 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202209 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202209 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202210 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202210 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.83 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202211 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202211 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.83 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4853202212 | A4853 | City Wide Cycling Infrastructure Contribution | Y000 | 202212 | OX-1003099 | 518733 | 2021/22 CAPV | 2021/22 Capital Virements | 204.59 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
A4854202201 | A4854 | Coach Parking Feasibility | Y000 | 202201 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202202 | A4854 | Coach Parking Feasibility | Y000 | 202202 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202203 | A4854 | Coach Parking Feasibility | Y000 | 202203 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202204 | A4854 | Coach Parking Feasibility | Y000 | 202204 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202205 | A4854 | Coach Parking Feasibility | Y000 | 202205 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202206 | A4854 | Coach Parking Feasibility | Y000 | 202206 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202207 | A4854 | Coach Parking Feasibility | Y000 | 202207 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202208 | A4854 | Coach Parking Feasibility | Y000 | 202208 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202209 | A4854 | Coach Parking Feasibility | Y000 | 202209 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202210 | A4854 | Coach Parking Feasibility | Y000 | 202210 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202211 | A4854 | Coach Parking Feasibility | Y000 | 202211 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202212 | A4854 | Coach Parking Feasibility | Y000 | 202212 | OX-1003076 | 518008 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
A4854202201 | A4854 | Coach Parking Feasibility | Y000 | 202201 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202202 | A4854 | Coach Parking Feasibility | Y000 | 202202 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202203 | A4854 | Coach Parking Feasibility | Y000 | 202203 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202204 | A4854 | Coach Parking Feasibility | Y000 | 202204 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202205 | A4854 | Coach Parking Feasibility | Y000 | 202205 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202206 | A4854 | Coach Parking Feasibility | Y000 | 202206 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202207 | A4854 | Coach Parking Feasibility | Y000 | 202207 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202208 | A4854 | Coach Parking Feasibility | Y000 | 202208 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202209 | A4854 | Coach Parking Feasibility | Y000 | 202209 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202210 | A4854 | Coach Parking Feasibility | Y000 | 202210 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202211 | A4854 | Coach Parking Feasibility | Y000 | 202211 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
A4854202212 | A4854 | Coach Parking Feasibility | Y000 | 202212 | OX-1003096 | 518589 | 2021/22 CAP0 | 2021/22 Capital Original | -1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202202 | B0074 | R & D Feasibility Fund | Y000 | 202202 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202203 | B0074 | R & D Feasibility Fund | Y000 | 202203 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27120.01 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202204 | B0074 | R & D Feasibility Fund | Y000 | 202204 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202205 | B0074 | R & D Feasibility Fund | Y000 | 202205 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202206 | B0074 | R & D Feasibility Fund | Y000 | 202206 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27120.01 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202207 | B0074 | R & D Feasibility Fund | Y000 | 202207 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202208 | B0074 | R & D Feasibility Fund | Y000 | 202208 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202209 | B0074 | R & D Feasibility Fund | Y000 | 202209 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27120.01 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202210 | B0074 | R & D Feasibility Fund | Y000 | 202210 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202211 | B0074 | R & D Feasibility Fund | Y000 | 202211 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27087.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202212 | B0074 | R & D Feasibility Fund | Y000 | 202212 | OX-1003076 | 518007 | 2021/22 CAP0 | 2021/22 Capital Original | 27120.01 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202202 | B0074 | R & D Feasibility Fund | Y000 | 202202 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202203 | B0074 | R & D Feasibility Fund | Y000 | 202203 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202204 | B0074 | R & D Feasibility Fund | Y000 | 202204 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11926.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202205 | B0074 | R & D Feasibility Fund | Y000 | 202205 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202206 | B0074 | R & D Feasibility Fund | Y000 | 202206 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202207 | B0074 | R & D Feasibility Fund | Y000 | 202207 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11926.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202208 | B0074 | R & D Feasibility Fund | Y000 | 202208 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202209 | B0074 | R & D Feasibility Fund | Y000 | 202209 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202210 | B0074 | R & D Feasibility Fund | Y000 | 202210 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11926.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202211 | B0074 | R & D Feasibility Fund | Y000 | 202211 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11926.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202212 | B0074 | R & D Feasibility Fund | Y000 | 202212 | OX-1003101 | 518830 | 2021/22 CAPV | 2021/22 Capital Virements | -11911.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003122 | 519044 | 2021/22 CAPV | 2021/22 Capital Virements | -91595 | 10 | Annual (April) | P2 Feasibility Adjustments per DB 24.05 | JMARRI
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003123 | 519048 | 2021/22 CAPV | 2021/22 Capital Virements | -60000 | 10 | Annual (April) | P2 Feasibility Adjustments re Pipe Bridge | JMARRI
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202201 | B0074 | R & D Feasibility Fund | Y000 | 202201 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202202 | B0074 | R & D Feasibility Fund | Y000 | 202202 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202202 | B0074 | R & D Feasibility Fund | Y000 | 202202 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202203 | B0074 | R & D Feasibility Fund | Y000 | 202203 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202203 | B0074 | R & D Feasibility Fund | Y000 | 202203 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202204 | B0074 | R & D Feasibility Fund | Y000 | 202204 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10508.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202204 | B0074 | R & D Feasibility Fund | Y000 | 202204 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20850 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202205 | B0074 | R & D Feasibility Fund | Y000 | 202205 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202205 | B0074 | R & D Feasibility Fund | Y000 | 202205 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202206 | B0074 | R & D Feasibility Fund | Y000 | 202206 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202206 | B0074 | R & D Feasibility Fund | Y000 | 202206 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202207 | B0074 | R & D Feasibility Fund | Y000 | 202207 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10508.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202207 | B0074 | R & D Feasibility Fund | Y000 | 202207 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20850 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202208 | B0074 | R & D Feasibility Fund | Y000 | 202208 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202208 | B0074 | R & D Feasibility Fund | Y000 | 202208 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202209 | B0074 | R & D Feasibility Fund | Y000 | 202209 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202209 | B0074 | R & D Feasibility Fund | Y000 | 202209 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202210 | B0074 | R & D Feasibility Fund | Y000 | 202210 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10508.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202210 | B0074 | R & D Feasibility Fund | Y000 | 202210 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20850 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202211 | B0074 | R & D Feasibility Fund | Y000 | 202211 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10508.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202211 | B0074 | R & D Feasibility Fund | Y000 | 202211 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20850 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0074202212 | B0074 | R & D Feasibility Fund | Y000 | 202212 | OX-1003148 | 519476 | 2021/22 CAPV | 2021/22 Capital Virements | -10495.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0074202212 | B0074 | R & D Feasibility Fund | Y000 | 202212 | OX-1003148 | 519479 | 2021/22 CAPV | 2021/22 Capital Virements | 20825 | 11 | Twelfths Monthly | Bring Forward Allocation from 2022/23 | JMARRI
B0075202201 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202201 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202202 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202202 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202203 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202203 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202204 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202204 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202205 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202205 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202206 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202206 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202207 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202207 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202208 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202208 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202209 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202209 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202210 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202210 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202211 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202211 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2915.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202212 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202212 | OX-1003076 | 518006 | 2021/22 CAP0 | 2021/22 Capital Original | 2919 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0075202201 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202201 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202202 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202202 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202203 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202203 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202204 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202204 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84767.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202205 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202205 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202206 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202206 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202207 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202207 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84767.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202208 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202208 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202209 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202209 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202210 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202210 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84767.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202211 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202211 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84767.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0075202212 | B0075 | Stage 2 Museum of Oxford Development | Y000 | 202212 | OX-1003099 | 518732 | 2021/22 CAPV | 2021/22 Capital Virements | 84665.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202201 | B0081 | Car Parking Oxpens | Y000 | 202201 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202202 | B0081 | Car Parking Oxpens | Y000 | 202202 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202203 | B0081 | Car Parking Oxpens | Y000 | 202203 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3586.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202204 | B0081 | Car Parking Oxpens | Y000 | 202204 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202205 | B0081 | Car Parking Oxpens | Y000 | 202205 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202206 | B0081 | Car Parking Oxpens | Y000 | 202206 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3586.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202207 | B0081 | Car Parking Oxpens | Y000 | 202207 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202208 | B0081 | Car Parking Oxpens | Y000 | 202208 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202209 | B0081 | Car Parking Oxpens | Y000 | 202209 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3586.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202210 | B0081 | Car Parking Oxpens | Y000 | 202210 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202211 | B0081 | Car Parking Oxpens | Y000 | 202211 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3581.9 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202212 | B0081 | Car Parking Oxpens | Y000 | 202212 | OX-1003076 | 518005 | 2021/22 CAP0 | 2021/22 Capital Original | 3586.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0081202201 | B0081 | Car Parking Oxpens | Y000 | 202201 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202202 | B0081 | Car Parking Oxpens | Y000 | 202202 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202203 | B0081 | Car Parking Oxpens | Y000 | 202203 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202204 | B0081 | Car Parking Oxpens | Y000 | 202204 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16042.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202205 | B0081 | Car Parking Oxpens | Y000 | 202205 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202206 | B0081 | Car Parking Oxpens | Y000 | 202206 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202207 | B0081 | Car Parking Oxpens | Y000 | 202207 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16042.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202208 | B0081 | Car Parking Oxpens | Y000 | 202208 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202209 | B0081 | Car Parking Oxpens | Y000 | 202209 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202210 | B0081 | Car Parking Oxpens | Y000 | 202210 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16042.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202211 | B0081 | Car Parking Oxpens | Y000 | 202211 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16042.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0081202212 | B0081 | Car Parking Oxpens | Y000 | 202212 | OX-1003099 | 518731 | 2021/22 CAPV | 2021/22 Capital Virements | 16023.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202201 | B0083 | East Oxford Community Centre | Y000 | 202201 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202202 | B0083 | East Oxford Community Centre | Y000 | 202202 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202203 | B0083 | East Oxford Community Centre | Y000 | 202203 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 351317.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202204 | B0083 | East Oxford Community Centre | Y000 | 202204 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202205 | B0083 | East Oxford Community Centre | Y000 | 202205 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202206 | B0083 | East Oxford Community Centre | Y000 | 202206 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 351317.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202207 | B0083 | East Oxford Community Centre | Y000 | 202207 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202208 | B0083 | East Oxford Community Centre | Y000 | 202208 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202209 | B0083 | East Oxford Community Centre | Y000 | 202209 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 351317.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202210 | B0083 | East Oxford Community Centre | Y000 | 202210 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202211 | B0083 | East Oxford Community Centre | Y000 | 202211 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 350896.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202212 | B0083 | East Oxford Community Centre | Y000 | 202212 | OX-1003076 | 518004 | 2021/22 CAP0 | 2021/22 Capital Original | 351317.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0083202201 | B0083 | East Oxford Community Centre | Y000 | 202201 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202202 | B0083 | East Oxford Community Centre | Y000 | 202202 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202203 | B0083 | East Oxford Community Centre | Y000 | 202203 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202204 | B0083 | East Oxford Community Centre | Y000 | 202204 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18185.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202205 | B0083 | East Oxford Community Centre | Y000 | 202205 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202206 | B0083 | East Oxford Community Centre | Y000 | 202206 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202207 | B0083 | East Oxford Community Centre | Y000 | 202207 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18185.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202208 | B0083 | East Oxford Community Centre | Y000 | 202208 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202209 | B0083 | East Oxford Community Centre | Y000 | 202209 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202210 | B0083 | East Oxford Community Centre | Y000 | 202210 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18185.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202211 | B0083 | East Oxford Community Centre | Y000 | 202211 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18185.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0083202212 | B0083 | East Oxford Community Centre | Y000 | 202212 | OX-1003099 | 518730 | 2021/22 CAPV | 2021/22 Capital Virements | 18163.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0084202201 | B0084 | Jericho Community Centre | Y000 | 202201 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202202 | B0084 | Jericho Community Centre | Y000 | 202202 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202203 | B0084 | Jericho Community Centre | Y000 | 202203 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202204 | B0084 | Jericho Community Centre | Y000 | 202204 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202205 | B0084 | Jericho Community Centre | Y000 | 202205 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202206 | B0084 | Jericho Community Centre | Y000 | 202206 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202207 | B0084 | Jericho Community Centre | Y000 | 202207 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202208 | B0084 | Jericho Community Centre | Y000 | 202208 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202209 | B0084 | Jericho Community Centre | Y000 | 202209 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202210 | B0084 | Jericho Community Centre | Y000 | 202210 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202211 | B0084 | Jericho Community Centre | Y000 | 202211 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0084202212 | B0084 | Jericho Community Centre | Y000 | 202212 | OX-1003076 | 518003 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0086202201 | B0086 | Seacourt Park & Ride Extension | Y000 | 202201 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202202 | B0086 | Seacourt Park & Ride Extension | Y000 | 202202 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202203 | B0086 | Seacourt Park & Ride Extension | Y000 | 202203 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202204 | B0086 | Seacourt Park & Ride Extension | Y000 | 202204 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21892.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202205 | B0086 | Seacourt Park & Ride Extension | Y000 | 202205 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202206 | B0086 | Seacourt Park & Ride Extension | Y000 | 202206 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202207 | B0086 | Seacourt Park & Ride Extension | Y000 | 202207 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21892.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202208 | B0086 | Seacourt Park & Ride Extension | Y000 | 202208 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202209 | B0086 | Seacourt Park & Ride Extension | Y000 | 202209 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202210 | B0086 | Seacourt Park & Ride Extension | Y000 | 202210 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21892.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202211 | B0086 | Seacourt Park & Ride Extension | Y000 | 202211 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21892.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0086202212 | B0086 | Seacourt Park & Ride Extension | Y000 | 202212 | OX-1003099 | 518729 | 2021/22 CAPV | 2021/22 Capital Virements | 21866.16 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202201 | B0092 | Cave Street Development (Standingford House) | Y000 | 202201 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202202 | B0092 | Cave Street Development (Standingford House) | Y000 | 202202 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202203 | B0092 | Cave Street Development (Standingford House) | Y000 | 202203 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117385.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202204 | B0092 | Cave Street Development (Standingford House) | Y000 | 202204 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202205 | B0092 | Cave Street Development (Standingford House) | Y000 | 202205 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202206 | B0092 | Cave Street Development (Standingford House) | Y000 | 202206 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117385.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202207 | B0092 | Cave Street Development (Standingford House) | Y000 | 202207 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202208 | B0092 | Cave Street Development (Standingford House) | Y000 | 202208 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202209 | B0092 | Cave Street Development (Standingford House) | Y000 | 202209 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117385.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202210 | B0092 | Cave Street Development (Standingford House) | Y000 | 202210 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202211 | B0092 | Cave Street Development (Standingford House) | Y000 | 202211 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117244.75 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202212 | B0092 | Cave Street Development (Standingford House) | Y000 | 202212 | OX-1003076 | 518002 | 2021/22 CAP0 | 2021/22 Capital Original | 117385.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0092202201 | B0092 | Cave Street Development (Standingford House) | Y000 | 202201 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202202 | B0092 | Cave Street Development (Standingford House) | Y000 | 202202 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202203 | B0092 | Cave Street Development (Standingford House) | Y000 | 202203 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202204 | B0092 | Cave Street Development (Standingford House) | Y000 | 202204 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5708.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202205 | B0092 | Cave Street Development (Standingford House) | Y000 | 202205 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202206 | B0092 | Cave Street Development (Standingford House) | Y000 | 202206 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202207 | B0092 | Cave Street Development (Standingford House) | Y000 | 202207 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5708.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202208 | B0092 | Cave Street Development (Standingford House) | Y000 | 202208 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202209 | B0092 | Cave Street Development (Standingford House) | Y000 | 202209 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202210 | B0092 | Cave Street Development (Standingford House) | Y000 | 202210 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5708.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202211 | B0092 | Cave Street Development (Standingford House) | Y000 | 202211 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5708.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0092202212 | B0092 | Cave Street Development (Standingford House) | Y000 | 202212 | OX-1003099 | 518728 | 2021/22 CAPV | 2021/22 Capital Virements | 5701.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202201 | B0096 | Bullingdon Community Centre | Y000 | 202201 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202202 | B0096 | Bullingdon Community Centre | Y000 | 202202 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202203 | B0096 | Bullingdon Community Centre | Y000 | 202203 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123527.99 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202204 | B0096 | Bullingdon Community Centre | Y000 | 202204 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202205 | B0096 | Bullingdon Community Centre | Y000 | 202205 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202206 | B0096 | Bullingdon Community Centre | Y000 | 202206 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123527.99 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202207 | B0096 | Bullingdon Community Centre | Y000 | 202207 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202208 | B0096 | Bullingdon Community Centre | Y000 | 202208 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202209 | B0096 | Bullingdon Community Centre | Y000 | 202209 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123527.99 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202210 | B0096 | Bullingdon Community Centre | Y000 | 202210 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202211 | B0096 | Bullingdon Community Centre | Y000 | 202211 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123379.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202212 | B0096 | Bullingdon Community Centre | Y000 | 202212 | OX-1003076 | 518001 | 2021/22 CAP0 | 2021/22 Capital Original | 123528 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0096202201 | B0096 | Bullingdon Community Centre | Y000 | 202201 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202202 | B0096 | Bullingdon Community Centre | Y000 | 202202 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202203 | B0096 | Bullingdon Community Centre | Y000 | 202203 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202204 | B0096 | Bullingdon Community Centre | Y000 | 202204 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2787.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202205 | B0096 | Bullingdon Community Centre | Y000 | 202205 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202206 | B0096 | Bullingdon Community Centre | Y000 | 202206 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202207 | B0096 | Bullingdon Community Centre | Y000 | 202207 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2787.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202208 | B0096 | Bullingdon Community Centre | Y000 | 202208 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202209 | B0096 | Bullingdon Community Centre | Y000 | 202209 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202210 | B0096 | Bullingdon Community Centre | Y000 | 202210 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2787.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202211 | B0096 | Bullingdon Community Centre | Y000 | 202211 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2787.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0096202212 | B0096 | Bullingdon Community Centre | Y000 | 202212 | OX-1003099 | 518727 | 2021/22 CAPV | 2021/22 Capital Virements | 2784.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202201 | B0098 | 1-3 George Street | Y000 | 202201 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202202 | B0098 | 1-3 George Street | Y000 | 202202 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202203 | B0098 | 1-3 George Street | Y000 | 202203 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136375.68 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202204 | B0098 | 1-3 George Street | Y000 | 202204 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202205 | B0098 | 1-3 George Street | Y000 | 202205 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202206 | B0098 | 1-3 George Street | Y000 | 202206 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136375.68 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202207 | B0098 | 1-3 George Street | Y000 | 202207 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202208 | B0098 | 1-3 George Street | Y000 | 202208 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202209 | B0098 | 1-3 George Street | Y000 | 202209 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136375.68 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202210 | B0098 | 1-3 George Street | Y000 | 202210 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202211 | B0098 | 1-3 George Street | Y000 | 202211 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136212.16 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202212 | B0098 | 1-3 George Street | Y000 | 202212 | OX-1003076 | 518000 | 2021/22 CAP0 | 2021/22 Capital Original | 136375.68 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0098202201 | B0098 | 1-3 George Street | Y000 | 202201 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202202 | B0098 | 1-3 George Street | Y000 | 202202 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202203 | B0098 | 1-3 George Street | Y000 | 202203 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202204 | B0098 | 1-3 George Street | Y000 | 202204 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24316.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202205 | B0098 | 1-3 George Street | Y000 | 202205 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202206 | B0098 | 1-3 George Street | Y000 | 202206 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202207 | B0098 | 1-3 George Street | Y000 | 202207 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24316.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202208 | B0098 | 1-3 George Street | Y000 | 202208 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202209 | B0098 | 1-3 George Street | Y000 | 202209 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.7 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202210 | B0098 | 1-3 George Street | Y000 | 202210 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24316.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202211 | B0098 | 1-3 George Street | Y000 | 202211 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24316.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0098202212 | B0098 | 1-3 George Street | Y000 | 202212 | OX-1003099 | 518726 | 2021/22 CAPV | 2021/22 Capital Virements | 24287.69 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202203 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202203 | OX-1003076 | 517999 | 2021/22 CAP0 | 2021/22 Capital Original | 22861.1 | 687 | B0100 - Gloucester Green Park (H&S) | App6 Budget Load | AWICKE
B0100202204 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202204 | OX-1003076 | 517999 | 2021/22 CAP0 | 2021/22 Capital Original | 22861.1 | 687 | B0100 - Gloucester Green Park (H&S) | App6 Budget Load | AWICKE
B0100202205 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202205 | OX-1003076 | 517999 | 2021/22 CAP0 | 2021/22 Capital Original | 29256.81 | 687 | B0100 - Gloucester Green Park (H&S) | App6 Budget Load | AWICKE
B0100202201 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202201 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202202 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202202 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202203 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202203 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202204 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202204 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15607.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202205 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202205 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202206 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202206 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202207 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202207 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15607.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202208 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202208 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202209 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202209 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202210 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202210 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15607.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202211 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202211 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15607.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0100202212 | B0100 | Gloucester Green Car Park (H&S) | Y000 | 202212 | OX-1003099 | 518725 | 2021/22 CAPV | 2021/22 Capital Virements | 15589.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202201 | B0101 | Capital works at Covered Market | Y000 | 202201 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202202 | B0101 | Capital works at Covered Market | Y000 | 202202 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202203 | B0101 | Capital works at Covered Market | Y000 | 202203 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84466.69 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202204 | B0101 | Capital works at Covered Market | Y000 | 202204 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202205 | B0101 | Capital works at Covered Market | Y000 | 202205 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202206 | B0101 | Capital works at Covered Market | Y000 | 202206 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84466.69 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202207 | B0101 | Capital works at Covered Market | Y000 | 202207 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202208 | B0101 | Capital works at Covered Market | Y000 | 202208 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202209 | B0101 | Capital works at Covered Market | Y000 | 202209 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84466.69 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202210 | B0101 | Capital works at Covered Market | Y000 | 202210 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202211 | B0101 | Capital works at Covered Market | Y000 | 202211 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84365.41 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202212 | B0101 | Capital works at Covered Market | Y000 | 202212 | OX-1003076 | 517998 | 2021/22 CAP0 | 2021/22 Capital Original | 84466.69 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0101202201 | B0101 | Capital works at Covered Market | Y000 | 202201 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202202 | B0101 | Capital works at Covered Market | Y000 | 202202 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202203 | B0101 | Capital works at Covered Market | Y000 | 202203 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202204 | B0101 | Capital works at Covered Market | Y000 | 202204 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3028.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202205 | B0101 | Capital works at Covered Market | Y000 | 202205 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202206 | B0101 | Capital works at Covered Market | Y000 | 202206 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202207 | B0101 | Capital works at Covered Market | Y000 | 202207 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3028.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202208 | B0101 | Capital works at Covered Market | Y000 | 202208 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202209 | B0101 | Capital works at Covered Market | Y000 | 202209 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202210 | B0101 | Capital works at Covered Market | Y000 | 202210 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3028.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202211 | B0101 | Capital works at Covered Market | Y000 | 202211 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3028.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0101202212 | B0101 | Capital works at Covered Market | Y000 | 202212 | OX-1003099 | 518724 | 2021/22 CAPV | 2021/22 Capital Virements | 3024.46 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202201 | B0102 | Replace or refurbish Lifts | Y000 | 202201 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202202 | B0102 | Replace or refurbish Lifts | Y000 | 202202 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202203 | B0102 | Replace or refurbish Lifts | Y000 | 202203 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3610.72 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202204 | B0102 | Replace or refurbish Lifts | Y000 | 202204 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202205 | B0102 | Replace or refurbish Lifts | Y000 | 202205 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202206 | B0102 | Replace or refurbish Lifts | Y000 | 202206 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3610.72 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202207 | B0102 | Replace or refurbish Lifts | Y000 | 202207 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202208 | B0102 | Replace or refurbish Lifts | Y000 | 202208 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202209 | B0102 | Replace or refurbish Lifts | Y000 | 202209 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3610.72 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202210 | B0102 | Replace or refurbish Lifts | Y000 | 202210 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202211 | B0102 | Replace or refurbish Lifts | Y000 | 202211 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3606.39 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202212 | B0102 | Replace or refurbish Lifts | Y000 | 202212 | OX-1003076 | 517997 | 2021/22 CAP0 | 2021/22 Capital Original | 3610.72 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0102202201 | B0102 | Replace or refurbish Lifts | Y000 | 202201 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202202 | B0102 | Replace or refurbish Lifts | Y000 | 202202 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202203 | B0102 | Replace or refurbish Lifts | Y000 | 202203 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202204 | B0102 | Replace or refurbish Lifts | Y000 | 202204 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6354.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202205 | B0102 | Replace or refurbish Lifts | Y000 | 202205 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202206 | B0102 | Replace or refurbish Lifts | Y000 | 202206 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202207 | B0102 | Replace or refurbish Lifts | Y000 | 202207 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6354.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202208 | B0102 | Replace or refurbish Lifts | Y000 | 202208 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202209 | B0102 | Replace or refurbish Lifts | Y000 | 202209 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202210 | B0102 | Replace or refurbish Lifts | Y000 | 202210 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6354.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202211 | B0102 | Replace or refurbish Lifts | Y000 | 202211 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6354.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0102202212 | B0102 | Replace or refurbish Lifts | Y000 | 202212 | OX-1003099 | 518723 | 2021/22 CAPV | 2021/22 Capital Virements | 6346.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202201 | B0104 | Old Gas Works Bridges | Y000 | 202201 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202202 | B0104 | Old Gas Works Bridges | Y000 | 202202 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202203 | B0104 | Old Gas Works Bridges | Y000 | 202203 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202204 | B0104 | Old Gas Works Bridges | Y000 | 202204 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2911.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202205 | B0104 | Old Gas Works Bridges | Y000 | 202205 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202206 | B0104 | Old Gas Works Bridges | Y000 | 202206 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202207 | B0104 | Old Gas Works Bridges | Y000 | 202207 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2911.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202208 | B0104 | Old Gas Works Bridges | Y000 | 202208 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202209 | B0104 | Old Gas Works Bridges | Y000 | 202209 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202210 | B0104 | Old Gas Works Bridges | Y000 | 202210 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2911.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202211 | B0104 | Old Gas Works Bridges | Y000 | 202211 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2911.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202212 | B0104 | Old Gas Works Bridges | Y000 | 202212 | OX-1003099 | 518722 | 2021/22 CAPV | 2021/22 Capital Virements | 2908.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0104202201 | B0104 | Old Gas Works Bridges | Y000 | 202201 | OX-1003123 | 519049 | 2021/22 CAPV | 2021/22 Capital Virements | 60000 | 10 | Annual (April) | P2 Feasibility Adjustments re Pipe Bridge | JMARRI
B0106202201 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202201 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202202 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202202 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202203 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202203 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 20016 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202204 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202204 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202205 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202205 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202206 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202206 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 20016 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202207 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202207 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202208 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202208 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202209 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202209 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 20016 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202210 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202210 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202211 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202211 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 19992 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202212 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202212 | OX-1003076 | 517996 | 2021/22 CAP0 | 2021/22 Capital Original | 20016 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0106202201 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202201 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202202 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202202 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202203 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202203 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202204 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202204 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10176.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202205 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202205 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202206 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202206 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202207 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202207 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10176.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202208 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202208 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202209 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202209 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202210 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202210 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10176.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202211 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202211 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10176.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0106202212 | B0106 | Covered Market Planned Maintenance - Roof | Y000 | 202212 | OX-1003099 | 518721 | 2021/22 CAPV | 2021/22 Capital Virements | 10164.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0108202206 | B0108 | Floyds Row Refurbishment | Y000 | 202206 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 5477.22 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202207 | B0108 | Floyds Row Refurbishment | Y000 | 202207 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 5916.06 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202208 | B0108 | Floyds Row Refurbishment | Y000 | 202208 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 5038.38 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202209 | B0108 | Floyds Row Refurbishment | Y000 | 202209 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 5257.8 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202210 | B0108 | Floyds Row Refurbishment | Y000 | 202210 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 5257.8 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202211 | B0108 | Floyds Row Refurbishment | Y000 | 202211 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 6578.46 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0108202212 | B0108 | Floyds Row Refurbishment | Y000 | 202212 | OX-1003076 | 517995 | 2021/22 CAP0 | 2021/22 Capital Original | 7874.28 | 321 | Capital Variable 3 | App6 Budget Load | AWICKE
B0110202201 | B0110 | Covered Market Vacant Unit Works | Y000 | 202201 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202202 | B0110 | Covered Market Vacant Unit Works | Y000 | 202202 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202203 | B0110 | Covered Market Vacant Unit Works | Y000 | 202203 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202204 | B0110 | Covered Market Vacant Unit Works | Y000 | 202204 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1996.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202205 | B0110 | Covered Market Vacant Unit Works | Y000 | 202205 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202206 | B0110 | Covered Market Vacant Unit Works | Y000 | 202206 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202207 | B0110 | Covered Market Vacant Unit Works | Y000 | 202207 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1996.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202208 | B0110 | Covered Market Vacant Unit Works | Y000 | 202208 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202209 | B0110 | Covered Market Vacant Unit Works | Y000 | 202209 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202210 | B0110 | Covered Market Vacant Unit Works | Y000 | 202210 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1996.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202211 | B0110 | Covered Market Vacant Unit Works | Y000 | 202211 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1996.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0110202212 | B0110 | Covered Market Vacant Unit Works | Y000 | 202212 | OX-1003099 | 518720 | 2021/22 CAPV | 2021/22 Capital Virements | 1994.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202201 | B0111 | Town Hall Dry Risers | Y000 | 202201 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202202 | B0111 | Town Hall Dry Risers | Y000 | 202202 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202203 | B0111 | Town Hall Dry Risers | Y000 | 202203 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3109.32 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202204 | B0111 | Town Hall Dry Risers | Y000 | 202204 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202205 | B0111 | Town Hall Dry Risers | Y000 | 202205 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202206 | B0111 | Town Hall Dry Risers | Y000 | 202206 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3109.32 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202207 | B0111 | Town Hall Dry Risers | Y000 | 202207 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202208 | B0111 | Town Hall Dry Risers | Y000 | 202208 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202209 | B0111 | Town Hall Dry Risers | Y000 | 202209 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3109.32 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202210 | B0111 | Town Hall Dry Risers | Y000 | 202210 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202211 | B0111 | Town Hall Dry Risers | Y000 | 202211 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3105.59 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202212 | B0111 | Town Hall Dry Risers | Y000 | 202212 | OX-1003076 | 517994 | 2021/22 CAP0 | 2021/22 Capital Original | 3109.32 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0111202201 | B0111 | Town Hall Dry Risers | Y000 | 202201 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202202 | B0111 | Town Hall Dry Risers | Y000 | 202202 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202203 | B0111 | Town Hall Dry Risers | Y000 | 202203 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202204 | B0111 | Town Hall Dry Risers | Y000 | 202204 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1477.68 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202205 | B0111 | Town Hall Dry Risers | Y000 | 202205 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202206 | B0111 | Town Hall Dry Risers | Y000 | 202206 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202207 | B0111 | Town Hall Dry Risers | Y000 | 202207 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1477.68 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202208 | B0111 | Town Hall Dry Risers | Y000 | 202208 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202209 | B0111 | Town Hall Dry Risers | Y000 | 202209 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202210 | B0111 | Town Hall Dry Risers | Y000 | 202210 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1477.68 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202211 | B0111 | Town Hall Dry Risers | Y000 | 202211 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1477.68 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202212 | B0111 | Town Hall Dry Risers | Y000 | 202212 | OX-1003077 | 518096 | 2021/22 CAPV | 2021/22 Capital Virements | 1475.91 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
B0111202201 | B0111 | Town Hall Dry Risers | Y000 | 202201 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202202 | B0111 | Town Hall Dry Risers | Y000 | 202202 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202203 | B0111 | Town Hall Dry Risers | Y000 | 202203 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202204 | B0111 | Town Hall Dry Risers | Y000 | 202204 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7211.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202205 | B0111 | Town Hall Dry Risers | Y000 | 202205 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202206 | B0111 | Town Hall Dry Risers | Y000 | 202206 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202207 | B0111 | Town Hall Dry Risers | Y000 | 202207 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7211.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202208 | B0111 | Town Hall Dry Risers | Y000 | 202208 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202209 | B0111 | Town Hall Dry Risers | Y000 | 202209 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202210 | B0111 | Town Hall Dry Risers | Y000 | 202210 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7211.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202211 | B0111 | Town Hall Dry Risers | Y000 | 202211 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7211.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0111202212 | B0111 | Town Hall Dry Risers | Y000 | 202212 | OX-1003099 | 518719 | 2021/22 CAPV | 2021/22 Capital Virements | 7203.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202201 | B0112 | Cinema Feasibility | Y000 | 202201 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202202 | B0112 | Cinema Feasibility | Y000 | 202202 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202203 | B0112 | Cinema Feasibility | Y000 | 202203 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3390.79 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202204 | B0112 | Cinema Feasibility | Y000 | 202204 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202205 | B0112 | Cinema Feasibility | Y000 | 202205 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202206 | B0112 | Cinema Feasibility | Y000 | 202206 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3390.79 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202207 | B0112 | Cinema Feasibility | Y000 | 202207 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202208 | B0112 | Cinema Feasibility | Y000 | 202208 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202209 | B0112 | Cinema Feasibility | Y000 | 202209 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3390.79 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202210 | B0112 | Cinema Feasibility | Y000 | 202210 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202211 | B0112 | Cinema Feasibility | Y000 | 202211 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3386.73 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202212 | B0112 | Cinema Feasibility | Y000 | 202212 | OX-1003076 | 517993 | 2021/22 CAP0 | 2021/22 Capital Original | 3390.79 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0112202201 | B0112 | Cinema Feasibility | Y000 | 202201 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202202 | B0112 | Cinema Feasibility | Y000 | 202202 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202203 | B0112 | Cinema Feasibility | Y000 | 202203 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202204 | B0112 | Cinema Feasibility | Y000 | 202204 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202205 | B0112 | Cinema Feasibility | Y000 | 202205 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202206 | B0112 | Cinema Feasibility | Y000 | 202206 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202207 | B0112 | Cinema Feasibility | Y000 | 202207 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202208 | B0112 | Cinema Feasibility | Y000 | 202208 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202209 | B0112 | Cinema Feasibility | Y000 | 202209 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202210 | B0112 | Cinema Feasibility | Y000 | 202210 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202211 | B0112 | Cinema Feasibility | Y000 | 202211 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0112202212 | B0112 | Cinema Feasibility | Y000 | 202212 | OX-1003099 | 518718 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202201 | B0113 | New Theatre Improvements | Y000 | 202201 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202202 | B0113 | New Theatre Improvements | Y000 | 202202 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202203 | B0113 | New Theatre Improvements | Y000 | 202203 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202204 | B0113 | New Theatre Improvements | Y000 | 202204 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5058.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202205 | B0113 | New Theatre Improvements | Y000 | 202205 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202206 | B0113 | New Theatre Improvements | Y000 | 202206 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202207 | B0113 | New Theatre Improvements | Y000 | 202207 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5058.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202208 | B0113 | New Theatre Improvements | Y000 | 202208 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202209 | B0113 | New Theatre Improvements | Y000 | 202209 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202210 | B0113 | New Theatre Improvements | Y000 | 202210 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5058.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202211 | B0113 | New Theatre Improvements | Y000 | 202211 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5058.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0113202212 | B0113 | New Theatre Improvements | Y000 | 202212 | OX-1003099 | 518717 | 2021/22 CAPV | 2021/22 Capital Virements | 5052.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202201 | B0114 | Diamond Place Redevelopment | Y000 | 202201 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202202 | B0114 | Diamond Place Redevelopment | Y000 | 202202 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202203 | B0114 | Diamond Place Redevelopment | Y000 | 202203 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202204 | B0114 | Diamond Place Redevelopment | Y000 | 202204 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1215.56 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202205 | B0114 | Diamond Place Redevelopment | Y000 | 202205 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202206 | B0114 | Diamond Place Redevelopment | Y000 | 202206 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202207 | B0114 | Diamond Place Redevelopment | Y000 | 202207 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1215.56 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202208 | B0114 | Diamond Place Redevelopment | Y000 | 202208 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202209 | B0114 | Diamond Place Redevelopment | Y000 | 202209 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202210 | B0114 | Diamond Place Redevelopment | Y000 | 202210 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1215.56 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202211 | B0114 | Diamond Place Redevelopment | Y000 | 202211 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1215.56 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202212 | B0114 | Diamond Place Redevelopment | Y000 | 202212 | OX-1003099 | 518716 | 2021/22 CAPV | 2021/22 Capital Virements | -1214.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0114202201 | B0114 | Diamond Place Redevelopment | Y000 | 202201 | OX-1003122 | 519047 | 2021/22 CAPV | 2021/22 Capital Virements | 14575 | 10 | Annual (April) | P2 Feasibility Adjustments per DB 24.05 | JMARRI
B0115202209 | B0115 | Covered Market Masterplan | Y000 | 202209 | OX-1003076 | 517992 | 2021/22 CAP0 | 2021/22 Capital Original | 10390 | 42 | Approved Adjustments - December | App6 Budget Load | AWICKE
B0115202210 | B0115 | Covered Market Masterplan | Y000 | 202210 | OX-1003076 | 517992 | 2021/22 CAP0 | 2021/22 Capital Original | 10390 | 42 | Approved Adjustments - December | App6 Budget Load | AWICKE
B0115202211 | B0115 | Covered Market Masterplan | Y000 | 202211 | OX-1003076 | 517992 | 2021/22 CAP0 | 2021/22 Capital Original | 10390 | 42 | Approved Adjustments - December | App6 Budget Load | AWICKE
B0115202212 | B0115 | Covered Market Masterplan | Y000 | 202212 | OX-1003076 | 517992 | 2021/22 CAP0 | 2021/22 Capital Original | 10390 | 42 | Approved Adjustments - December | App6 Budget Load | AWICKE
B0115202201 | B0115 | Covered Market Masterplan | Y000 | 202201 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202202 | B0115 | Covered Market Masterplan | Y000 | 202202 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202203 | B0115 | Covered Market Masterplan | Y000 | 202203 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202204 | B0115 | Covered Market Masterplan | Y000 | 202204 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3675.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202205 | B0115 | Covered Market Masterplan | Y000 | 202205 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202206 | B0115 | Covered Market Masterplan | Y000 | 202206 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202207 | B0115 | Covered Market Masterplan | Y000 | 202207 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3675.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202208 | B0115 | Covered Market Masterplan | Y000 | 202208 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202209 | B0115 | Covered Market Masterplan | Y000 | 202209 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202210 | B0115 | Covered Market Masterplan | Y000 | 202210 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3675.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202211 | B0115 | Covered Market Masterplan | Y000 | 202211 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3675.52 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202212 | B0115 | Covered Market Masterplan | Y000 | 202212 | OX-1003099 | 518715 | 2021/22 CAPV | 2021/22 Capital Virements | 3671.12 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0115202201 | B0115 | Covered Market Masterplan | Y000 | 202201 | OX-1003122 | 519045 | 2021/22 CAPV | 2021/22 Capital Virements | 15500 | 10 | Annual (April) | P2 Feasibility Adjustments per DB 24.05 | JMARRI
B0116202201 | B0116 | Osney Mead Infrastructure | Y000 | 202201 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202202 | B0116 | Osney Mead Infrastructure | Y000 | 202202 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202203 | B0116 | Osney Mead Infrastructure | Y000 | 202203 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 75060 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202204 | B0116 | Osney Mead Infrastructure | Y000 | 202204 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202205 | B0116 | Osney Mead Infrastructure | Y000 | 202205 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202206 | B0116 | Osney Mead Infrastructure | Y000 | 202206 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 75060 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202207 | B0116 | Osney Mead Infrastructure | Y000 | 202207 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202208 | B0116 | Osney Mead Infrastructure | Y000 | 202208 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202209 | B0116 | Osney Mead Infrastructure | Y000 | 202209 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 75060 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202210 | B0116 | Osney Mead Infrastructure | Y000 | 202210 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202211 | B0116 | Osney Mead Infrastructure | Y000 | 202211 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 74970 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202212 | B0116 | Osney Mead Infrastructure | Y000 | 202212 | OX-1003076 | 517991 | 2021/22 CAP0 | 2021/22 Capital Original | 75060 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0116202201 | B0116 | Osney Mead Infrastructure | Y000 | 202201 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202202 | B0116 | Osney Mead Infrastructure | Y000 | 202202 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202203 | B0116 | Osney Mead Infrastructure | Y000 | 202203 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202204 | B0116 | Osney Mead Infrastructure | Y000 | 202204 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 5004 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202205 | B0116 | Osney Mead Infrastructure | Y000 | 202205 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202206 | B0116 | Osney Mead Infrastructure | Y000 | 202206 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202207 | B0116 | Osney Mead Infrastructure | Y000 | 202207 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 5004 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202208 | B0116 | Osney Mead Infrastructure | Y000 | 202208 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202209 | B0116 | Osney Mead Infrastructure | Y000 | 202209 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202210 | B0116 | Osney Mead Infrastructure | Y000 | 202210 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 5004 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202211 | B0116 | Osney Mead Infrastructure | Y000 | 202211 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 5004 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0116202212 | B0116 | Osney Mead Infrastructure | Y000 | 202212 | OX-1003099 | 518714 | 2021/22 CAPV | 2021/22 Capital Virements | 4998 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0117202201 | B0117 | Commercial Property | Y000 | 202201 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202202 | B0117 | Commercial Property | Y000 | 202202 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202203 | B0117 | Commercial Property | Y000 | 202203 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1668000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202204 | B0117 | Commercial Property | Y000 | 202204 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202205 | B0117 | Commercial Property | Y000 | 202205 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202206 | B0117 | Commercial Property | Y000 | 202206 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1668000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202207 | B0117 | Commercial Property | Y000 | 202207 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202208 | B0117 | Commercial Property | Y000 | 202208 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202209 | B0117 | Commercial Property | Y000 | 202209 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1668000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202210 | B0117 | Commercial Property | Y000 | 202210 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202211 | B0117 | Commercial Property | Y000 | 202211 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1666000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0117202212 | B0117 | Commercial Property | Y000 | 202212 | OX-1003076 | 517990 | 2021/22 CAP0 | 2021/22 Capital Original | 1668000 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202201 | B0118 | Oxford Ice Rink | Y000 | 202201 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202202 | B0118 | Oxford Ice Rink | Y000 | 202202 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202203 | B0118 | Oxford Ice Rink | Y000 | 202203 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2668.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202204 | B0118 | Oxford Ice Rink | Y000 | 202204 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202205 | B0118 | Oxford Ice Rink | Y000 | 202205 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202206 | B0118 | Oxford Ice Rink | Y000 | 202206 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2668.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202207 | B0118 | Oxford Ice Rink | Y000 | 202207 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202208 | B0118 | Oxford Ice Rink | Y000 | 202208 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202209 | B0118 | Oxford Ice Rink | Y000 | 202209 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2668.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202210 | B0118 | Oxford Ice Rink | Y000 | 202210 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202211 | B0118 | Oxford Ice Rink | Y000 | 202211 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2665.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202212 | B0118 | Oxford Ice Rink | Y000 | 202212 | OX-1003076 | 517989 | 2021/22 CAP0 | 2021/22 Capital Original | 2668.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0118202201 | B0118 | Oxford Ice Rink | Y000 | 202201 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202202 | B0118 | Oxford Ice Rink | Y000 | 202202 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202203 | B0118 | Oxford Ice Rink | Y000 | 202203 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202204 | B0118 | Oxford Ice Rink | Y000 | 202204 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1009.14 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202205 | B0118 | Oxford Ice Rink | Y000 | 202205 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202206 | B0118 | Oxford Ice Rink | Y000 | 202206 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202207 | B0118 | Oxford Ice Rink | Y000 | 202207 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1009.14 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202208 | B0118 | Oxford Ice Rink | Y000 | 202208 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202209 | B0118 | Oxford Ice Rink | Y000 | 202209 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202210 | B0118 | Oxford Ice Rink | Y000 | 202210 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1009.14 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202211 | B0118 | Oxford Ice Rink | Y000 | 202211 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1009.14 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0118202212 | B0118 | Oxford Ice Rink | Y000 | 202212 | OX-1003099 | 518713 | 2021/22 CAPV | 2021/22 Capital Virements | -1007.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202201 | B0119 | Oxford Station Feasibility | Y000 | 202201 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202202 | B0119 | Oxford Station Feasibility | Y000 | 202202 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202203 | B0119 | Oxford Station Feasibility | Y000 | 202203 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5838 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202204 | B0119 | Oxford Station Feasibility | Y000 | 202204 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202205 | B0119 | Oxford Station Feasibility | Y000 | 202205 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202206 | B0119 | Oxford Station Feasibility | Y000 | 202206 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5838 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202207 | B0119 | Oxford Station Feasibility | Y000 | 202207 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202208 | B0119 | Oxford Station Feasibility | Y000 | 202208 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202209 | B0119 | Oxford Station Feasibility | Y000 | 202209 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5838 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202210 | B0119 | Oxford Station Feasibility | Y000 | 202210 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202211 | B0119 | Oxford Station Feasibility | Y000 | 202211 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5831 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202212 | B0119 | Oxford Station Feasibility | Y000 | 202212 | OX-1003076 | 517988 | 2021/22 CAP0 | 2021/22 Capital Original | 5838 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0119202201 | B0119 | Oxford Station Feasibility | Y000 | 202201 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202202 | B0119 | Oxford Station Feasibility | Y000 | 202202 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202203 | B0119 | Oxford Station Feasibility | Y000 | 202203 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202204 | B0119 | Oxford Station Feasibility | Y000 | 202204 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5718.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202205 | B0119 | Oxford Station Feasibility | Y000 | 202205 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202206 | B0119 | Oxford Station Feasibility | Y000 | 202206 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202207 | B0119 | Oxford Station Feasibility | Y000 | 202207 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5718.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202208 | B0119 | Oxford Station Feasibility | Y000 | 202208 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202209 | B0119 | Oxford Station Feasibility | Y000 | 202209 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202210 | B0119 | Oxford Station Feasibility | Y000 | 202210 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5718.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202211 | B0119 | Oxford Station Feasibility | Y000 | 202211 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5718.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0119202212 | B0119 | Oxford Station Feasibility | Y000 | 202212 | OX-1003099 | 518712 | 2021/22 CAPV | 2021/22 Capital Virements | 5711.97 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202201 | B0120 | Osney Bridge Feasibility | Y000 | 202201 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202202 | B0120 | Osney Bridge Feasibility | Y000 | 202202 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202203 | B0120 | Osney Bridge Feasibility | Y000 | 202203 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91740 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202204 | B0120 | Osney Bridge Feasibility | Y000 | 202204 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202205 | B0120 | Osney Bridge Feasibility | Y000 | 202205 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202206 | B0120 | Osney Bridge Feasibility | Y000 | 202206 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91740 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202207 | B0120 | Osney Bridge Feasibility | Y000 | 202207 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202208 | B0120 | Osney Bridge Feasibility | Y000 | 202208 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202209 | B0120 | Osney Bridge Feasibility | Y000 | 202209 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91740 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202210 | B0120 | Osney Bridge Feasibility | Y000 | 202210 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202211 | B0120 | Osney Bridge Feasibility | Y000 | 202211 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91630 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202212 | B0120 | Osney Bridge Feasibility | Y000 | 202212 | OX-1003076 | 517987 | 2021/22 CAP0 | 2021/22 Capital Original | 91740 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0120202201 | B0120 | Osney Bridge Feasibility | Y000 | 202201 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202202 | B0120 | Osney Bridge Feasibility | Y000 | 202202 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202203 | B0120 | Osney Bridge Feasibility | Y000 | 202203 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202204 | B0120 | Osney Bridge Feasibility | Y000 | 202204 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23664.33 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202205 | B0120 | Osney Bridge Feasibility | Y000 | 202205 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202206 | B0120 | Osney Bridge Feasibility | Y000 | 202206 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202207 | B0120 | Osney Bridge Feasibility | Y000 | 202207 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23664.33 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202208 | B0120 | Osney Bridge Feasibility | Y000 | 202208 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202209 | B0120 | Osney Bridge Feasibility | Y000 | 202209 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202210 | B0120 | Osney Bridge Feasibility | Y000 | 202210 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23664.33 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202211 | B0120 | Osney Bridge Feasibility | Y000 | 202211 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23664.33 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0120202212 | B0120 | Osney Bridge Feasibility | Y000 | 202212 | OX-1003099 | 518711 | 2021/22 CAPV | 2021/22 Capital Virements | 23635.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202201 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202201 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202202 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202202 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202203 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202203 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37530 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202204 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202204 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202205 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202205 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202206 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202206 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37530 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202207 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202207 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202208 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202208 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202209 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202209 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37530 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202210 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202210 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202211 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202211 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37485 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202212 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202212 | OX-1003076 | 517986 | 2021/22 CAP0 | 2021/22 Capital Original | 37530 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0122202201 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202201 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202202 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202202 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202203 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202203 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202204 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202204 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37668.61 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202205 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202205 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202206 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202206 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202207 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202207 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37668.61 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202208 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202208 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202209 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202209 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.45 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202210 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202210 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37668.61 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202211 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202211 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37668.61 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0122202212 | B0122 | City Cycle Schemes (Growth Deal) | Y000 | 202212 | OX-1003099 | 518710 | 2021/22 CAPV | 2021/22 Capital Virements | 37623.44 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202201 | B0124 | Port Meadow Moorings | Y000 | 202201 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202202 | B0124 | Port Meadow Moorings | Y000 | 202202 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202203 | B0124 | Port Meadow Moorings | Y000 | 202203 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202204 | B0124 | Port Meadow Moorings | Y000 | 202204 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -960.77 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202205 | B0124 | Port Meadow Moorings | Y000 | 202205 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202206 | B0124 | Port Meadow Moorings | Y000 | 202206 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202207 | B0124 | Port Meadow Moorings | Y000 | 202207 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -960.77 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202208 | B0124 | Port Meadow Moorings | Y000 | 202208 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202209 | B0124 | Port Meadow Moorings | Y000 | 202209 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202210 | B0124 | Port Meadow Moorings | Y000 | 202210 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -960.77 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202211 | B0124 | Port Meadow Moorings | Y000 | 202211 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -960.77 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202212 | B0124 | Port Meadow Moorings | Y000 | 202212 | OX-1003099 | 518709 | 2021/22 CAPV | 2021/22 Capital Virements | -959.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0124202201 | B0124 | Port Meadow Moorings | Y000 | 202201 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202201 | B0124 | Port Meadow Moorings | Y000 | 202201 | OX-1003122 | 519046 | 2021/22 CAPV | 2021/22 Capital Virements | 11520 | 10 | Annual (April) | P2 Feasibility Adjustments per DB 24.05 | JMARRI
B0124202202 | B0124 | Port Meadow Moorings | Y000 | 202202 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202203 | B0124 | Port Meadow Moorings | Y000 | 202203 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202204 | B0124 | Port Meadow Moorings | Y000 | 202204 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202205 | B0124 | Port Meadow Moorings | Y000 | 202205 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202206 | B0124 | Port Meadow Moorings | Y000 | 202206 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202207 | B0124 | Port Meadow Moorings | Y000 | 202207 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202208 | B0124 | Port Meadow Moorings | Y000 | 202208 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202209 | B0124 | Port Meadow Moorings | Y000 | 202209 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202210 | B0124 | Port Meadow Moorings | Y000 | 202210 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202211 | B0124 | Port Meadow Moorings | Y000 | 202211 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0124202212 | B0124 | Port Meadow Moorings | Y000 | 202212 | OX-1003122 | 519043 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | New Feasibility Approval DB 24.05 | JMARRI
B0125202201 | B0125 | City Centre Restart | Y000 | 202201 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202202 | B0125 | City Centre Restart | Y000 | 202202 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202203 | B0125 | City Centre Restart | Y000 | 202203 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202204 | B0125 | City Centre Restart | Y000 | 202204 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202205 | B0125 | City Centre Restart | Y000 | 202205 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202206 | B0125 | City Centre Restart | Y000 | 202206 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202207 | B0125 | City Centre Restart | Y000 | 202207 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202208 | B0125 | City Centre Restart | Y000 | 202208 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202209 | B0125 | City Centre Restart | Y000 | 202209 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202210 | B0125 | City Centre Restart | Y000 | 202210 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202211 | B0125 | City Centre Restart | Y000 | 202211 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0125202212 | B0125 | City Centre Restart | Y000 | 202212 | OX-1003099 | 518708 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202201 | B0126 | Asset Surveys | Y000 | 202201 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202202 | B0126 | Asset Surveys | Y000 | 202202 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202203 | B0126 | Asset Surveys | Y000 | 202203 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202204 | B0126 | Asset Surveys | Y000 | 202204 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 25020 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202205 | B0126 | Asset Surveys | Y000 | 202205 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202206 | B0126 | Asset Surveys | Y000 | 202206 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202207 | B0126 | Asset Surveys | Y000 | 202207 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 25020 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202208 | B0126 | Asset Surveys | Y000 | 202208 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202209 | B0126 | Asset Surveys | Y000 | 202209 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202210 | B0126 | Asset Surveys | Y000 | 202210 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 25020 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202211 | B0126 | Asset Surveys | Y000 | 202211 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 25020 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0126202212 | B0126 | Asset Surveys | Y000 | 202212 | OX-1003099 | 518707 | 2021/22 CAPV | 2021/22 Capital Virements | 24990 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202201 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202201 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202202 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202202 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202203 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202203 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202204 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202204 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5671.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202205 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202205 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202206 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202206 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202207 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202207 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5671.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202208 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202208 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202209 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202209 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202210 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202210 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5671.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202211 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202211 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5671.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202212 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202212 | OX-1003099 | 518706 | 2021/22 CAPV | 2021/22 Capital Virements | 5664.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0127202201 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202201 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202202 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202202 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202203 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202203 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202204 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202204 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6088.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202205 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202205 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202206 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202206 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202207 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202207 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6088.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202208 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202208 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202209 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202209 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202210 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202210 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6088.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202211 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202211 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6088.2 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0127202212 | B0127 | ZEZ Phase 1 Feasibility | Y000 | 202212 | OX-1003101 | 518829 | 2021/22 CAPV | 2021/22 Capital Virements | 6080.9 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0128202201 | B0128 | Greenways Cycling Project | Y000 | 202201 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202202 | B0128 | Greenways Cycling Project | Y000 | 202202 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202203 | B0128 | Greenways Cycling Project | Y000 | 202203 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202204 | B0128 | Greenways Cycling Project | Y000 | 202204 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8840.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202205 | B0128 | Greenways Cycling Project | Y000 | 202205 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202206 | B0128 | Greenways Cycling Project | Y000 | 202206 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202207 | B0128 | Greenways Cycling Project | Y000 | 202207 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8840.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202208 | B0128 | Greenways Cycling Project | Y000 | 202208 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202209 | B0128 | Greenways Cycling Project | Y000 | 202209 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202210 | B0128 | Greenways Cycling Project | Y000 | 202210 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8840.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202211 | B0128 | Greenways Cycling Project | Y000 | 202211 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8840.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0128202212 | B0128 | Greenways Cycling Project | Y000 | 202212 | OX-1003099 | 518705 | 2021/22 CAPV | 2021/22 Capital Virements | 8829.8 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202201 | B0129 | Town Hall Options | Y000 | 202201 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202202 | B0129 | Town Hall Options | Y000 | 202202 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202203 | B0129 | Town Hall Options | Y000 | 202203 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202204 | B0129 | Town Hall Options | Y000 | 202204 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202205 | B0129 | Town Hall Options | Y000 | 202205 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202206 | B0129 | Town Hall Options | Y000 | 202206 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202207 | B0129 | Town Hall Options | Y000 | 202207 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202208 | B0129 | Town Hall Options | Y000 | 202208 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202209 | B0129 | Town Hall Options | Y000 | 202209 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202210 | B0129 | Town Hall Options | Y000 | 202210 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202211 | B0129 | Town Hall Options | Y000 | 202211 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0129202212 | B0129 | Town Hall Options | Y000 | 202212 | OX-1003099 | 518704 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0130202201 | B0130 | CIL Feasibility | Y000 | 202201 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202202 | B0130 | CIL Feasibility | Y000 | 202202 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202203 | B0130 | CIL Feasibility | Y000 | 202203 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202204 | B0130 | CIL Feasibility | Y000 | 202204 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202205 | B0130 | CIL Feasibility | Y000 | 202205 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202206 | B0130 | CIL Feasibility | Y000 | 202206 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202207 | B0130 | CIL Feasibility | Y000 | 202207 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202208 | B0130 | CIL Feasibility | Y000 | 202208 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202209 | B0130 | CIL Feasibility | Y000 | 202209 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202210 | B0130 | CIL Feasibility | Y000 | 202210 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202211 | B0130 | CIL Feasibility | Y000 | 202211 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16660 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0130202212 | B0130 | CIL Feasibility | Y000 | 202212 | OX-1003076 | 517985 | 2021/22 CAP0 | 2021/22 Capital Original | 16680 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202201 | B0131 | Meanwhile In Oxfordshire | Y000 | 202201 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202202 | B0131 | Meanwhile In Oxfordshire | Y000 | 202202 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202203 | B0131 | Meanwhile In Oxfordshire | Y000 | 202203 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156375 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202204 | B0131 | Meanwhile In Oxfordshire | Y000 | 202204 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202205 | B0131 | Meanwhile In Oxfordshire | Y000 | 202205 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202206 | B0131 | Meanwhile In Oxfordshire | Y000 | 202206 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156375 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202207 | B0131 | Meanwhile In Oxfordshire | Y000 | 202207 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202208 | B0131 | Meanwhile In Oxfordshire | Y000 | 202208 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202209 | B0131 | Meanwhile In Oxfordshire | Y000 | 202209 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156375 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202210 | B0131 | Meanwhile In Oxfordshire | Y000 | 202210 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202211 | B0131 | Meanwhile In Oxfordshire | Y000 | 202211 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156187.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202212 | B0131 | Meanwhile In Oxfordshire | Y000 | 202212 | OX-1003076 | 517984 | 2021/22 CAP0 | 2021/22 Capital Original | 156375 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
B0131202201 | B0131 | Meanwhile In Oxfordshire | Y000 | 202201 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202202 | B0131 | Meanwhile In Oxfordshire | Y000 | 202202 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202203 | B0131 | Meanwhile In Oxfordshire | Y000 | 202203 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202204 | B0131 | Meanwhile In Oxfordshire | Y000 | 202204 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2514.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202205 | B0131 | Meanwhile In Oxfordshire | Y000 | 202205 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202206 | B0131 | Meanwhile In Oxfordshire | Y000 | 202206 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202207 | B0131 | Meanwhile In Oxfordshire | Y000 | 202207 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2514.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202208 | B0131 | Meanwhile In Oxfordshire | Y000 | 202208 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202209 | B0131 | Meanwhile In Oxfordshire | Y000 | 202209 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202210 | B0131 | Meanwhile In Oxfordshire | Y000 | 202210 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2514.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202211 | B0131 | Meanwhile In Oxfordshire | Y000 | 202211 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2514.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0131202212 | B0131 | Meanwhile In Oxfordshire | Y000 | 202212 | OX-1003099 | 518703 | 2021/22 CAPV | 2021/22 Capital Virements | -2511.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
B0132202201 | B0132 | Coach Parking Feasibility | Y000 | 202201 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202202 | B0132 | Coach Parking Feasibility | Y000 | 202202 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202203 | B0132 | Coach Parking Feasibility | Y000 | 202203 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202204 | B0132 | Coach Parking Feasibility | Y000 | 202204 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202205 | B0132 | Coach Parking Feasibility | Y000 | 202205 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202206 | B0132 | Coach Parking Feasibility | Y000 | 202206 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202207 | B0132 | Coach Parking Feasibility | Y000 | 202207 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202208 | B0132 | Coach Parking Feasibility | Y000 | 202208 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202209 | B0132 | Coach Parking Feasibility | Y000 | 202209 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202210 | B0132 | Coach Parking Feasibility | Y000 | 202210 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202211 | B0132 | Coach Parking Feasibility | Y000 | 202211 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0132202212 | B0132 | Coach Parking Feasibility | Y000 | 202212 | OX-1003096 | 518588 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202201 | B0133 | Cemetery Feasibility | Y000 | 202201 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202202 | B0133 | Cemetery Feasibility | Y000 | 202202 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202203 | B0133 | Cemetery Feasibility | Y000 | 202203 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202204 | B0133 | Cemetery Feasibility | Y000 | 202204 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3336 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202205 | B0133 | Cemetery Feasibility | Y000 | 202205 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202206 | B0133 | Cemetery Feasibility | Y000 | 202206 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202207 | B0133 | Cemetery Feasibility | Y000 | 202207 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3336 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202208 | B0133 | Cemetery Feasibility | Y000 | 202208 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202209 | B0133 | Cemetery Feasibility | Y000 | 202209 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202210 | B0133 | Cemetery Feasibility | Y000 | 202210 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3336 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202211 | B0133 | Cemetery Feasibility | Y000 | 202211 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3336 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0133202212 | B0133 | Cemetery Feasibility | Y000 | 202212 | OX-1003101 | 518828 | 2021/22 CAPV | 2021/22 Capital Virements | 3332 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202201 | B0134 | Shotover SSI Management Plan | Y000 | 202201 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202202 | B0134 | Shotover SSI Management Plan | Y000 | 202202 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202203 | B0134 | Shotover SSI Management Plan | Y000 | 202203 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202204 | B0134 | Shotover SSI Management Plan | Y000 | 202204 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202205 | B0134 | Shotover SSI Management Plan | Y000 | 202205 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202206 | B0134 | Shotover SSI Management Plan | Y000 | 202206 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202207 | B0134 | Shotover SSI Management Plan | Y000 | 202207 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202208 | B0134 | Shotover SSI Management Plan | Y000 | 202208 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202209 | B0134 | Shotover SSI Management Plan | Y000 | 202209 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202210 | B0134 | Shotover SSI Management Plan | Y000 | 202210 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202211 | B0134 | Shotover SSI Management Plan | Y000 | 202211 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1668 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0134202212 | B0134 | Shotover SSI Management Plan | Y000 | 202212 | OX-1003101 | 518827 | 2021/22 CAPV | 2021/22 Capital Virements | 1666 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202201 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202201 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202202 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202202 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202203 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202203 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202204 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202204 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 834 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202205 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202205 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202206 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202206 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202207 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202207 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 834 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202208 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202208 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202209 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202209 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202210 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202210 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 834 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202211 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202211 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 834 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0135202212 | B0135 | CCTV Gloucester Green Car Park | Y000 | 202212 | OX-1003101 | 518826 | 2021/22 CAPV | 2021/22 Capital Virements | 833 | 11 | Twelfths Monthly | P1 Capital Adjustments & Tidy | JMARRI
B0136202201 | B0136 | Covered Market CCTV | Y000 | 202201 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202202 | B0136 | Covered Market CCTV | Y000 | 202202 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202203 | B0136 | Covered Market CCTV | Y000 | 202203 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202204 | B0136 | Covered Market CCTV | Y000 | 202204 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202205 | B0136 | Covered Market CCTV | Y000 | 202205 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202206 | B0136 | Covered Market CCTV | Y000 | 202206 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202207 | B0136 | Covered Market CCTV | Y000 | 202207 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202208 | B0136 | Covered Market CCTV | Y000 | 202208 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202209 | B0136 | Covered Market CCTV | Y000 | 202209 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202210 | B0136 | Covered Market CCTV | Y000 | 202210 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202211 | B0136 | Covered Market CCTV | Y000 | 202211 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8340 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0136202212 | B0136 | Covered Market CCTV | Y000 | 202212 | OX-1003148 | 519478 | 2021/22 CAPV | 2021/22 Capital Virements | 8330 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202201 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202201 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202202 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202202 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202203 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202203 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202204 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202204 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2168.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202205 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202205 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202206 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202206 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202207 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202207 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2168.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202208 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202208 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202209 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202209 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202210 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202210 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2168.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202211 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202211 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2168.4 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
B0137202212 | B0137 | Court Place Farm and Blackbird Leys Bowling Club Asset Review | Y000 | 202212 | OX-1003148 | 519477 | 2021/22 CAPV | 2021/22 Capital Virements | 2165.8 | 11 | Twelfths Monthly | DB Approved Feasibility Allocations | JMARRI
C3044202207 | C3044 | Software Licences | Y000 | 202207 | OX-1003076 | 517983 | 2021/22 CAP0 | 2021/22 Capital Original | 245000 | 27 | Annual (October) | App6 Budget Load | AWICKE
C3057202201 | C3057 | Housing System Replacement | Y000 | 202201 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202202 | C3057 | Housing System Replacement | Y000 | 202202 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202203 | C3057 | Housing System Replacement | Y000 | 202203 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202204 | C3057 | Housing System Replacement | Y000 | 202204 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10724.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202205 | C3057 | Housing System Replacement | Y000 | 202205 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202206 | C3057 | Housing System Replacement | Y000 | 202206 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202207 | C3057 | Housing System Replacement | Y000 | 202207 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10724.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202208 | C3057 | Housing System Replacement | Y000 | 202208 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202209 | C3057 | Housing System Replacement | Y000 | 202209 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202210 | C3057 | Housing System Replacement | Y000 | 202210 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10724.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202211 | C3057 | Housing System Replacement | Y000 | 202211 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10724.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3057202212 | C3057 | Housing System Replacement | Y000 | 202212 | OX-1003099 | 518702 | 2021/22 CAPV | 2021/22 Capital Virements | 10711.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202201 | C3058 | CRM Lagan Replacement | Y000 | 202201 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202202 | C3058 | CRM Lagan Replacement | Y000 | 202202 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202203 | C3058 | CRM Lagan Replacement | Y000 | 202203 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202204 | C3058 | CRM Lagan Replacement | Y000 | 202204 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10030.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202205 | C3058 | CRM Lagan Replacement | Y000 | 202205 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202206 | C3058 | CRM Lagan Replacement | Y000 | 202206 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202207 | C3058 | CRM Lagan Replacement | Y000 | 202207 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10030.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202208 | C3058 | CRM Lagan Replacement | Y000 | 202208 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202209 | C3058 | CRM Lagan Replacement | Y000 | 202209 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202210 | C3058 | CRM Lagan Replacement | Y000 | 202210 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10030.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202211 | C3058 | CRM Lagan Replacement | Y000 | 202211 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10030.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3058202212 | C3058 | CRM Lagan Replacement | Y000 | 202212 | OX-1003099 | 518701 | 2021/22 CAPV | 2021/22 Capital Virements | 10018.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202201 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202201 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202202 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202202 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202203 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202203 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202204 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202204 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202205 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202205 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202206 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202206 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202207 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202207 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202208 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202208 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202209 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202209 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202210 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202210 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202211 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202211 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 4998 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202212 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202212 | OX-1003076 | 517982 | 2021/22 CAP0 | 2021/22 Capital Original | 5004 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
C3060202201 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202201 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202202 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202202 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202203 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202203 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202204 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202204 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202205 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202205 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202206 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202206 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202207 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202207 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202208 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202208 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202209 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202209 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202210 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202210 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202211 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202211 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.63 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3060202212 | C3060 | End-Point Devices (Desktops/Laptops) | Y000 | 202212 | OX-1003099 | 518700 | 2021/22 CAPV | 2021/22 Capital Virements | 481.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202201 | C3066 | Telephony Device Refresh | Y000 | 202201 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202202 | C3066 | Telephony Device Refresh | Y000 | 202202 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202203 | C3066 | Telephony Device Refresh | Y000 | 202203 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202204 | C3066 | Telephony Device Refresh | Y000 | 202204 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 773.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202205 | C3066 | Telephony Device Refresh | Y000 | 202205 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202206 | C3066 | Telephony Device Refresh | Y000 | 202206 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202207 | C3066 | Telephony Device Refresh | Y000 | 202207 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 773.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202208 | C3066 | Telephony Device Refresh | Y000 | 202208 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202209 | C3066 | Telephony Device Refresh | Y000 | 202209 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202210 | C3066 | Telephony Device Refresh | Y000 | 202210 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 773.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202211 | C3066 | Telephony Device Refresh | Y000 | 202211 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 773.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3066202212 | C3066 | Telephony Device Refresh | Y000 | 202212 | OX-1003099 | 518699 | 2021/22 CAPV | 2021/22 Capital Virements | 772.28 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202206 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202206 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202207 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202207 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202208 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202208 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202209 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202209 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202210 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202210 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202211 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202211 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2561.34 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202212 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202212 | OX-1003076 | 517981 | 2021/22 CAP0 | 2021/22 Capital Original | 2555.96 | 39 | Approved Adjustments - September | App6 Budget Load | AWICKE
C3067202201 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202201 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202202 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202202 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202203 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202203 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202204 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202204 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1230.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202205 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202205 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202206 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202206 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202207 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202207 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1230.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202208 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202208 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202209 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202209 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202210 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202210 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1230.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202211 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202211 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1230.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202212 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202212 | OX-1003099 | 518698 | 2021/22 CAPV | 2021/22 Capital Virements | 1229.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3067202201 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202201 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202202 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202202 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202203 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202203 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202204 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202204 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5838 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202205 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202205 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202206 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202206 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202207 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202207 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5838 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202208 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202208 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202209 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202209 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202210 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202210 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5838 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202211 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202211 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5838 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3067202212 | C3067 | Paris Payment System, Replacement / PCI DSS | Y000 | 202212 | OX-1003120 | 519033 | 2021/22 CAPV | 2021/22 Capital Virements | 5831 | 11 | Twelfths Monthly | Additional Approval re Telephone Payments | JMARRI
C3068202207 | C3068 | Windows 2008 Server Replacement | Y000 | 202207 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20192.04 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202208 | C3068 | Windows 2008 Server Replacement | Y000 | 202208 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20192.04 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202209 | C3068 | Windows 2008 Server Replacement | Y000 | 202209 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20192.04 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202210 | C3068 | Windows 2008 Server Replacement | Y000 | 202210 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20192.04 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202211 | C3068 | Windows 2008 Server Replacement | Y000 | 202211 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20192.04 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202212 | C3068 | Windows 2008 Server Replacement | Y000 | 202212 | OX-1003076 | 517980 | 2021/22 CAP0 | 2021/22 Capital Original | 20167.81 | 40 | Approved Adjustments - October | App6 Budget Load | AWICKE
C3068202201 | C3068 | Windows 2008 Server Replacement | Y000 | 202201 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202202 | C3068 | Windows 2008 Server Replacement | Y000 | 202202 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202203 | C3068 | Windows 2008 Server Replacement | Y000 | 202203 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202204 | C3068 | Windows 2008 Server Replacement | Y000 | 202204 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3976.18 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202205 | C3068 | Windows 2008 Server Replacement | Y000 | 202205 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202206 | C3068 | Windows 2008 Server Replacement | Y000 | 202206 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202207 | C3068 | Windows 2008 Server Replacement | Y000 | 202207 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3976.18 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202208 | C3068 | Windows 2008 Server Replacement | Y000 | 202208 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202209 | C3068 | Windows 2008 Server Replacement | Y000 | 202209 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202210 | C3068 | Windows 2008 Server Replacement | Y000 | 202210 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3976.18 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202211 | C3068 | Windows 2008 Server Replacement | Y000 | 202211 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3976.18 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3068202212 | C3068 | Windows 2008 Server Replacement | Y000 | 202212 | OX-1003099 | 518697 | 2021/22 CAPV | 2021/22 Capital Virements | 3971.41 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202201 | C3070 | Business Process Automation Full Rollout | Y000 | 202201 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202202 | C3070 | Business Process Automation Full Rollout | Y000 | 202202 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202203 | C3070 | Business Process Automation Full Rollout | Y000 | 202203 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202204 | C3070 | Business Process Automation Full Rollout | Y000 | 202204 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1627.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202205 | C3070 | Business Process Automation Full Rollout | Y000 | 202205 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202206 | C3070 | Business Process Automation Full Rollout | Y000 | 202206 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202207 | C3070 | Business Process Automation Full Rollout | Y000 | 202207 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1627.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202208 | C3070 | Business Process Automation Full Rollout | Y000 | 202208 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202209 | C3070 | Business Process Automation Full Rollout | Y000 | 202209 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202210 | C3070 | Business Process Automation Full Rollout | Y000 | 202210 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1627.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202211 | C3070 | Business Process Automation Full Rollout | Y000 | 202211 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1627.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3070202212 | C3070 | Business Process Automation Full Rollout | Y000 | 202212 | OX-1003099 | 518696 | 2021/22 CAPV | 2021/22 Capital Virements | 1625.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202201 | C3072 | Council Website Replacement | Y000 | 202201 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202202 | C3072 | Council Website Replacement | Y000 | 202202 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202203 | C3072 | Council Website Replacement | Y000 | 202203 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202204 | C3072 | Council Website Replacement | Y000 | 202204 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3016.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202205 | C3072 | Council Website Replacement | Y000 | 202205 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202206 | C3072 | Council Website Replacement | Y000 | 202206 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202207 | C3072 | Council Website Replacement | Y000 | 202207 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3016.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202208 | C3072 | Council Website Replacement | Y000 | 202208 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202209 | C3072 | Council Website Replacement | Y000 | 202209 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202210 | C3072 | Council Website Replacement | Y000 | 202210 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3016.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202211 | C3072 | Council Website Replacement | Y000 | 202211 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3016.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3072202212 | C3072 | Council Website Replacement | Y000 | 202212 | OX-1003099 | 518695 | 2021/22 CAPV | 2021/22 Capital Virements | 3012.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202212 | C3078 | Revs and Bens System Replacement | Y000 | 202212 | OX-1003076 | 517979 | 2021/22 CAP0 | 2021/22 Capital Original | 245000 | 32 | Annual (March) | App6 Budget Load | AWICKE
C3078202201 | C3078 | Revs and Bens System Replacement | Y000 | 202201 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202202 | C3078 | Revs and Bens System Replacement | Y000 | 202202 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202203 | C3078 | Revs and Bens System Replacement | Y000 | 202203 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202204 | C3078 | Revs and Bens System Replacement | Y000 | 202204 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18242.67 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202205 | C3078 | Revs and Bens System Replacement | Y000 | 202205 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202206 | C3078 | Revs and Bens System Replacement | Y000 | 202206 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202207 | C3078 | Revs and Bens System Replacement | Y000 | 202207 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18242.67 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202208 | C3078 | Revs and Bens System Replacement | Y000 | 202208 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202209 | C3078 | Revs and Bens System Replacement | Y000 | 202209 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202210 | C3078 | Revs and Bens System Replacement | Y000 | 202210 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18242.67 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202211 | C3078 | Revs and Bens System Replacement | Y000 | 202211 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18242.67 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
C3078202212 | C3078 | Revs and Bens System Replacement | Y000 | 202212 | OX-1003099 | 518694 | 2021/22 CAPV | 2021/22 Capital Virements | 18220.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202201 | E3511 | Essential Repair Grants | Y000 | 202201 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202202 | E3511 | Essential Repair Grants | Y000 | 202202 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202203 | E3511 | Essential Repair Grants | Y000 | 202203 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2080.66 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202204 | E3511 | Essential Repair Grants | Y000 | 202204 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202205 | E3511 | Essential Repair Grants | Y000 | 202205 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202206 | E3511 | Essential Repair Grants | Y000 | 202206 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2080.66 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202207 | E3511 | Essential Repair Grants | Y000 | 202207 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202208 | E3511 | Essential Repair Grants | Y000 | 202208 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202209 | E3511 | Essential Repair Grants | Y000 | 202209 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2080.66 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202210 | E3511 | Essential Repair Grants | Y000 | 202210 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202211 | E3511 | Essential Repair Grants | Y000 | 202211 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2078.17 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202212 | E3511 | Essential Repair Grants | Y000 | 202212 | OX-1003076 | 517978 | 2021/22 CAP0 | 2021/22 Capital Original | 2080.67 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3511202201 | E3511 | Essential Repair Grants | Y000 | 202201 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202202 | E3511 | Essential Repair Grants | Y000 | 202202 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202203 | E3511 | Essential Repair Grants | Y000 | 202203 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202204 | E3511 | Essential Repair Grants | Y000 | 202204 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -595.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202205 | E3511 | Essential Repair Grants | Y000 | 202205 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202206 | E3511 | Essential Repair Grants | Y000 | 202206 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202207 | E3511 | Essential Repair Grants | Y000 | 202207 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -595.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202208 | E3511 | Essential Repair Grants | Y000 | 202208 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202209 | E3511 | Essential Repair Grants | Y000 | 202209 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202210 | E3511 | Essential Repair Grants | Y000 | 202210 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -595.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202211 | E3511 | Essential Repair Grants | Y000 | 202211 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -595.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202212 | E3511 | Essential Repair Grants | Y000 | 202212 | OX-1003099 | 518693 | 2021/22 CAPV | 2021/22 Capital Virements | -594.6 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3511202201 | E3511 | Essential Repair Grants | Y000 | 202201 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202202 | E3511 | Essential Repair Grants | Y000 | 202202 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202203 | E3511 | Essential Repair Grants | Y000 | 202203 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202204 | E3511 | Essential Repair Grants | Y000 | 202204 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1143.46 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202205 | E3511 | Essential Repair Grants | Y000 | 202205 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202206 | E3511 | Essential Repair Grants | Y000 | 202206 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202207 | E3511 | Essential Repair Grants | Y000 | 202207 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1143.46 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202208 | E3511 | Essential Repair Grants | Y000 | 202208 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202209 | E3511 | Essential Repair Grants | Y000 | 202209 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202210 | E3511 | Essential Repair Grants | Y000 | 202210 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1143.46 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202211 | E3511 | Essential Repair Grants | Y000 | 202211 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1143.46 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3511202212 | E3511 | Essential Repair Grants | Y000 | 202212 | OX-1003156 | 519512 | 2021/22 CAPV | 2021/22 Capital Virements | 1142.09 | 11 | Twelfths Monthly | E3511 20/21 Slippage Correction | JMARRI
E3521202201 | E3521 | Disabled Facilities Grants | Y000 | 202201 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202202 | E3521 | Disabled Facilities Grants | Y000 | 202202 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202203 | E3521 | Disabled Facilities Grants | Y000 | 202203 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106950.33 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202204 | E3521 | Disabled Facilities Grants | Y000 | 202204 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202205 | E3521 | Disabled Facilities Grants | Y000 | 202205 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202206 | E3521 | Disabled Facilities Grants | Y000 | 202206 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106950.33 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202207 | E3521 | Disabled Facilities Grants | Y000 | 202207 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202208 | E3521 | Disabled Facilities Grants | Y000 | 202208 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202209 | E3521 | Disabled Facilities Grants | Y000 | 202209 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106950.33 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202210 | E3521 | Disabled Facilities Grants | Y000 | 202210 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202211 | E3521 | Disabled Facilities Grants | Y000 | 202211 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106822.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202212 | E3521 | Disabled Facilities Grants | Y000 | 202212 | OX-1003076 | 517977 | 2021/22 CAP0 | 2021/22 Capital Original | 106950.33 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3521202201 | E3521 | Disabled Facilities Grants | Y000 | 202201 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202202 | E3521 | Disabled Facilities Grants | Y000 | 202202 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202203 | E3521 | Disabled Facilities Grants | Y000 | 202203 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202204 | E3521 | Disabled Facilities Grants | Y000 | 202204 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11259 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202205 | E3521 | Disabled Facilities Grants | Y000 | 202205 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202206 | E3521 | Disabled Facilities Grants | Y000 | 202206 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202207 | E3521 | Disabled Facilities Grants | Y000 | 202207 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11259 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202208 | E3521 | Disabled Facilities Grants | Y000 | 202208 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202209 | E3521 | Disabled Facilities Grants | Y000 | 202209 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202210 | E3521 | Disabled Facilities Grants | Y000 | 202210 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11259 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202211 | E3521 | Disabled Facilities Grants | Y000 | 202211 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11259 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3521202212 | E3521 | Disabled Facilities Grants | Y000 | 202212 | OX-1003099 | 518692 | 2021/22 CAPV | 2021/22 Capital Virements | 11245.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202201 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202201 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202202 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202202 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202203 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202203 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202204 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202204 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202205 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202205 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202206 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202206 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202207 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202207 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202208 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202208 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202209 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202209 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202210 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202210 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202211 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202211 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202212 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202212 | OX-1003099 | 518691 | 2021/22 CAPV | 2021/22 Capital Virements | 192.09 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3557202201 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202201 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202202 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202202 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202203 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202203 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202204 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202204 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.32 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202205 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202205 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202206 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202206 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202207 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202207 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.32 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202208 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202208 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202209 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202209 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202210 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202210 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.32 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202211 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202211 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.32 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3557202212 | E3557 | Oxford and Abingdon Flood Alleviation Scheme | Y000 | 202212 | OX-1003131 | 519076 | 2021/22 CAPV | 2021/22 Capital Virements | -192.09 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
E3558202201 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202201 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202202 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202202 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202203 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202203 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 379.05 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202204 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202204 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202205 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202205 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202206 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202206 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 379.05 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202207 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202207 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202208 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202208 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202209 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202209 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 379.05 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202210 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202210 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202211 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202211 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 378.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202212 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202212 | OX-1003076 | 517976 | 2021/22 CAP0 | 2021/22 Capital Original | 379.06 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3558202201 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202201 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202202 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202202 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202203 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202203 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202204 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202204 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46420.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202205 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202205 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202206 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202206 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202207 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202207 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46420.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202208 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202208 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202209 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202209 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202210 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202210 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46420.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202211 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202211 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46420.86 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3558202212 | E3558 | Go Ultra Low Oxford - On Street | Y000 | 202212 | OX-1003099 | 518690 | 2021/22 CAPV | 2021/22 Capital Virements | 46365.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202201 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202201 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202202 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202202 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202203 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202203 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202204 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202204 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16948.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202205 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202205 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202206 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202206 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202207 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202207 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16948.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202208 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202208 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202209 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202209 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202210 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202210 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16948.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202211 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202211 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16948.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3560202212 | E3560 | Go Ultra Low Oxford - Taxis | Y000 | 202212 | OX-1003099 | 518689 | 2021/22 CAPV | 2021/22 Capital Virements | 16928.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202201 | E3561 | Additional DFG Funding | Y000 | 202201 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202202 | E3561 | Additional DFG Funding | Y000 | 202202 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202203 | E3561 | Additional DFG Funding | Y000 | 202203 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202204 | E3561 | Additional DFG Funding | Y000 | 202204 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8230.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202205 | E3561 | Additional DFG Funding | Y000 | 202205 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202206 | E3561 | Additional DFG Funding | Y000 | 202206 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202207 | E3561 | Additional DFG Funding | Y000 | 202207 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8230.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202208 | E3561 | Additional DFG Funding | Y000 | 202208 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202209 | E3561 | Additional DFG Funding | Y000 | 202209 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202210 | E3561 | Additional DFG Funding | Y000 | 202210 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8230.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202211 | E3561 | Additional DFG Funding | Y000 | 202211 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8230.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3561202212 | E3561 | Additional DFG Funding | Y000 | 202212 | OX-1003099 | 518688 | 2021/22 CAPV | 2021/22 Capital Virements | 8220.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202201 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202201 | OX-1003076 | 517975 | 2021/22 CAP0 | 2021/22 Capital Original | 1063.44 | 107 | E3562 - Ox Pops (Electric Vehicle Charging) | App6 Budget Load | AWICKE
E3562202202 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202202 | OX-1003076 | 517975 | 2021/22 CAP0 | 2021/22 Capital Original | 20158.78 | 107 | E3562 - Ox Pops (Electric Vehicle Charging) | App6 Budget Load | AWICKE
E3562202208 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202208 | OX-1003076 | 517975 | 2021/22 CAP0 | 2021/22 Capital Original | 14583.78 | 107 | E3562 - Ox Pops (Electric Vehicle Charging) | App6 Budget Load | AWICKE
E3562202201 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202201 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202202 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202202 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202203 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202203 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202204 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202204 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 529.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202205 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202205 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202206 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202206 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202207 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202207 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 529.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202208 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202208 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202209 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202209 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202210 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202210 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 529.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202211 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202211 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 529.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3562202212 | E3562 | OxPops (Electric Vehicle Charging) | Y000 | 202212 | OX-1003099 | 518687 | 2021/22 CAPV | 2021/22 Capital Virements | 528.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202201 | E3563 | Clean Bus Technology Grants | Y000 | 202201 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202202 | E3563 | Clean Bus Technology Grants | Y000 | 202202 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202203 | E3563 | Clean Bus Technology Grants | Y000 | 202203 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202204 | E3563 | Clean Bus Technology Grants | Y000 | 202204 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47066.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202205 | E3563 | Clean Bus Technology Grants | Y000 | 202205 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202206 | E3563 | Clean Bus Technology Grants | Y000 | 202206 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202207 | E3563 | Clean Bus Technology Grants | Y000 | 202207 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47066.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202208 | E3563 | Clean Bus Technology Grants | Y000 | 202208 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202209 | E3563 | Clean Bus Technology Grants | Y000 | 202209 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202210 | E3563 | Clean Bus Technology Grants | Y000 | 202210 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47066.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202211 | E3563 | Clean Bus Technology Grants | Y000 | 202211 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47066.79 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3563202212 | E3563 | Clean Bus Technology Grants | Y000 | 202212 | OX-1003099 | 518686 | 2021/22 CAPV | 2021/22 Capital Virements | 47010.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202201 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202201 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202202 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202202 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202203 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202203 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 628714.82 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202204 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202204 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202205 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202205 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202206 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202206 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 628714.82 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202207 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202207 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202208 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202208 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202209 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202209 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 628714.82 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202210 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202210 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202211 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202211 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 627960.96 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202212 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202212 | OX-1003076 | 517974 | 2021/22 CAP0 | 2021/22 Capital Original | 628714.82 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3565202201 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202201 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202202 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202202 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202203 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202203 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202204 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202204 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -938.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202205 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202205 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202206 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202206 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202207 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202207 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -938.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202208 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202208 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202209 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202209 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202210 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202210 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -938.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202211 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202211 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -938.25 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3565202212 | E3565 | Decarbonisation Fund - OCC element | Y000 | 202212 | OX-1003099 | 518685 | 2021/22 CAPV | 2021/22 Capital Virements | -937.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
E3566202201 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202201 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202202 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202202 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202203 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202203 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 282309 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202204 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202204 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202205 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202205 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202206 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202206 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 282309 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202207 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202207 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202208 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202208 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202209 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202209 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 282309 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202210 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202210 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202211 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202211 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 281970.5 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3566202212 | E3566 | Decarbonisation Fund - Low Carbon Hub Loan Element | Y000 | 202212 | OX-1003076 | 517973 | 2021/22 CAP0 | 2021/22 Capital Original | 282309 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
E3567202201 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202201 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202202 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202202 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202203 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202203 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202204 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202204 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202205 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202205 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202206 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202206 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202207 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202207 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202208 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202208 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202209 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202209 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202210 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202210 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202211 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202211 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202212 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202212 | OX-1003120 | 519032 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval | JMARRI
E3567202202 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202202 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202203 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202203 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202204 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202204 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202205 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202205 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 19800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202206 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202206 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202207 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202207 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202208 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202208 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202209 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202209 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 9000 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202210 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202210 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 10800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202211 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202211 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 10800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202212 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202212 | OX-1003124 | 519050 | 2021/22 CAPV | 2021/22 Capital Virements | 28800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202201 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202201 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202202 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202202 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202202 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202202 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202203 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202203 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202203 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202203 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202204 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202204 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202204 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202204 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -900 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202205 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202205 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202205 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202205 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -19800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202206 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202206 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202206 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202206 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202207 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202207 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202207 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202207 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202208 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202208 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202208 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202208 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -2700 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202209 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202209 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202209 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202209 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -9000 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202210 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202210 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202210 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202210 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -10800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202211 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202211 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202211 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202211 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -10800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202212 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202212 | OX-1003125 | 519051 | 2021/22 CAPV | 2021/22 Capital Virements | 7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202212 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202212 | OX-1003125 | 519052 | 2021/22 CAPV | 2021/22 Capital Virements | -28800 | 467 | Structural N6386 | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202201 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202201 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202202 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202202 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202203 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202203 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202204 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202204 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202205 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202205 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202206 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202206 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202207 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202207 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202208 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202208 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202209 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202209 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202210 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202210 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202211 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202211 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7506 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
E3567202212 | E3567 | Town Hall Lighting Upgrade (SALIX) | Y000 | 202212 | OX-1003126 | 519053 | 2021/22 CAPV | 2021/22 Capital Virements | -7497 | 11 | Twelfths Monthly | New Approval Town Hall Lighting Upgrade (SALIX) | JMARRI
F7007202201 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202201 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202202 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202202 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202203 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202203 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 667.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202204 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202204 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202205 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202205 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202206 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202206 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 667.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202207 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202207 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202208 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202208 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202209 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202209 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 667.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202210 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202210 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202211 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202211 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 666.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202212 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202212 | OX-1003076 | 517972 | 2021/22 CAP0 | 2021/22 Capital Original | 667.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7007202201 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202201 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202202 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202202 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202203 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202203 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202204 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202204 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 700.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202205 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202205 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202206 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202206 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202207 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202207 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 700.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202208 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202208 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202209 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202209 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202210 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202210 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 700.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202211 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202211 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 700.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7007202212 | F7007 | Woodfarm / Headington Community Centre | Y000 | 202212 | OX-1003099 | 518684 | 2021/22 CAPV | 2021/22 Capital Virements | 699.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202201 | F7011 | Headington Environmental Improvements | Y000 | 202201 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202202 | F7011 | Headington Environmental Improvements | Y000 | 202202 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202203 | F7011 | Headington Environmental Improvements | Y000 | 202203 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2471.06 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202204 | F7011 | Headington Environmental Improvements | Y000 | 202204 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202205 | F7011 | Headington Environmental Improvements | Y000 | 202205 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202206 | F7011 | Headington Environmental Improvements | Y000 | 202206 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2471.06 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202207 | F7011 | Headington Environmental Improvements | Y000 | 202207 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202208 | F7011 | Headington Environmental Improvements | Y000 | 202208 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202209 | F7011 | Headington Environmental Improvements | Y000 | 202209 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2471.06 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202210 | F7011 | Headington Environmental Improvements | Y000 | 202210 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202211 | F7011 | Headington Environmental Improvements | Y000 | 202211 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2468.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202212 | F7011 | Headington Environmental Improvements | Y000 | 202212 | OX-1003076 | 517971 | 2021/22 CAP0 | 2021/22 Capital Original | 2471.05 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7011202201 | F7011 | Headington Environmental Improvements | Y000 | 202201 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202202 | F7011 | Headington Environmental Improvements | Y000 | 202202 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202203 | F7011 | Headington Environmental Improvements | Y000 | 202203 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202204 | F7011 | Headington Environmental Improvements | Y000 | 202204 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 96.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202205 | F7011 | Headington Environmental Improvements | Y000 | 202205 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202206 | F7011 | Headington Environmental Improvements | Y000 | 202206 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202207 | F7011 | Headington Environmental Improvements | Y000 | 202207 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 96.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202208 | F7011 | Headington Environmental Improvements | Y000 | 202208 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202209 | F7011 | Headington Environmental Improvements | Y000 | 202209 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202210 | F7011 | Headington Environmental Improvements | Y000 | 202210 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 96.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202211 | F7011 | Headington Environmental Improvements | Y000 | 202211 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 96.08 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7011202212 | F7011 | Headington Environmental Improvements | Y000 | 202212 | OX-1003099 | 518683 | 2021/22 CAPV | 2021/22 Capital Virements | 95.96 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202201 | F7024 | St Clements Environmental Improvements | Y000 | 202201 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202202 | F7024 | St Clements Environmental Improvements | Y000 | 202202 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202203 | F7024 | St Clements Environmental Improvements | Y000 | 202203 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202204 | F7024 | St Clements Environmental Improvements | Y000 | 202204 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202205 | F7024 | St Clements Environmental Improvements | Y000 | 202205 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202206 | F7024 | St Clements Environmental Improvements | Y000 | 202206 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202207 | F7024 | St Clements Environmental Improvements | Y000 | 202207 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202208 | F7024 | St Clements Environmental Improvements | Y000 | 202208 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202209 | F7024 | St Clements Environmental Improvements | Y000 | 202209 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202210 | F7024 | St Clements Environmental Improvements | Y000 | 202210 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202211 | F7024 | St Clements Environmental Improvements | Y000 | 202211 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1666 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202212 | F7024 | St Clements Environmental Improvements | Y000 | 202212 | OX-1003076 | 517970 | 2021/22 CAP0 | 2021/22 Capital Original | 1668 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
F7024202201 | F7024 | St Clements Environmental Improvements | Y000 | 202201 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202202 | F7024 | St Clements Environmental Improvements | Y000 | 202202 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202203 | F7024 | St Clements Environmental Improvements | Y000 | 202203 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202204 | F7024 | St Clements Environmental Improvements | Y000 | 202204 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2502 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202205 | F7024 | St Clements Environmental Improvements | Y000 | 202205 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202206 | F7024 | St Clements Environmental Improvements | Y000 | 202206 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202207 | F7024 | St Clements Environmental Improvements | Y000 | 202207 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2502 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202208 | F7024 | St Clements Environmental Improvements | Y000 | 202208 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202209 | F7024 | St Clements Environmental Improvements | Y000 | 202209 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202210 | F7024 | St Clements Environmental Improvements | Y000 | 202210 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2502 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202211 | F7024 | St Clements Environmental Improvements | Y000 | 202211 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2502 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
F7024202212 | F7024 | St Clements Environmental Improvements | Y000 | 202212 | OX-1003099 | 518682 | 2021/22 CAPV | 2021/22 Capital Virements | 2499 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202201 | M5025 | Barton Park - purchase by Council | Y000 | 202201 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202202 | M5025 | Barton Park - purchase by Council | Y000 | 202202 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202203 | M5025 | Barton Park - purchase by Council | Y000 | 202203 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202204 | M5025 | Barton Park - purchase by Council | Y000 | 202204 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202205 | M5025 | Barton Park - purchase by Council | Y000 | 202205 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202206 | M5025 | Barton Park - purchase by Council | Y000 | 202206 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202207 | M5025 | Barton Park - purchase by Council | Y000 | 202207 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202208 | M5025 | Barton Park - purchase by Council | Y000 | 202208 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202209 | M5025 | Barton Park - purchase by Council | Y000 | 202209 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202210 | M5025 | Barton Park - purchase by Council | Y000 | 202210 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202211 | M5025 | Barton Park - purchase by Council | Y000 | 202211 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202212 | M5025 | Barton Park - purchase by Council | Y000 | 202212 | OX-1003076 | 517969 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5025202201 | M5025 | Barton Park - purchase by Council | Y000 | 202201 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202202 | M5025 | Barton Park - purchase by Council | Y000 | 202202 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202203 | M5025 | Barton Park - purchase by Council | Y000 | 202203 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202204 | M5025 | Barton Park - purchase by Council | Y000 | 202204 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 208151.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202205 | M5025 | Barton Park - purchase by Council | Y000 | 202205 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202206 | M5025 | Barton Park - purchase by Council | Y000 | 202206 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202207 | M5025 | Barton Park - purchase by Council | Y000 | 202207 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 208151.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202208 | M5025 | Barton Park - purchase by Council | Y000 | 202208 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202209 | M5025 | Barton Park - purchase by Council | Y000 | 202209 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202210 | M5025 | Barton Park - purchase by Council | Y000 | 202210 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 208151.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202211 | M5025 | Barton Park - purchase by Council | Y000 | 202211 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 208151.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5025202212 | M5025 | Barton Park - purchase by Council | Y000 | 202212 | OX-1003099 | 518681 | 2021/22 CAPV | 2021/22 Capital Virements | 207901.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202201 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202201 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202202 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202202 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202203 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202203 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2685480 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202204 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202204 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202205 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202205 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202206 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202206 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2685480 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202207 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202207 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202208 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202208 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202209 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202209 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2685480 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202210 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202210 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202211 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202211 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2682260 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202212 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202212 | OX-1003076 | 517968 | 2021/22 CAP0 | 2021/22 Capital Original | 2685480 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5026202201 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202201 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202202 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202202 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202203 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202203 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202204 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202204 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -472530.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202205 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202205 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202206 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202206 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202207 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202207 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -472530.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202208 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202208 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202209 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202209 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202210 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202210 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -472530.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202211 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202211 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -472530.3 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5026202212 | M5026 | Housing Company Loans (excl Barton Park) | Y000 | 202212 | OX-1003099 | 518680 | 2021/22 CAPV | 2021/22 Capital Virements | -471963.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202201 | M5032 | Barton Park - Loan to OCHL | Y000 | 202201 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202202 | M5032 | Barton Park - Loan to OCHL | Y000 | 202202 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202203 | M5032 | Barton Park - Loan to OCHL | Y000 | 202203 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202204 | M5032 | Barton Park - Loan to OCHL | Y000 | 202204 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202205 | M5032 | Barton Park - Loan to OCHL | Y000 | 202205 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202206 | M5032 | Barton Park - Loan to OCHL | Y000 | 202206 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202207 | M5032 | Barton Park - Loan to OCHL | Y000 | 202207 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202208 | M5032 | Barton Park - Loan to OCHL | Y000 | 202208 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202209 | M5032 | Barton Park - Loan to OCHL | Y000 | 202209 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202210 | M5032 | Barton Park - Loan to OCHL | Y000 | 202210 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202211 | M5032 | Barton Park - Loan to OCHL | Y000 | 202211 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 477811.88 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202212 | M5032 | Barton Park - Loan to OCHL | Y000 | 202212 | OX-1003076 | 517967 | 2021/22 CAP0 | 2021/22 Capital Original | 478385.49 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5032202201 | M5032 | Barton Park - Loan to OCHL | Y000 | 202201 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202202 | M5032 | Barton Park - Loan to OCHL | Y000 | 202202 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202203 | M5032 | Barton Park - Loan to OCHL | Y000 | 202203 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202204 | M5032 | Barton Park - Loan to OCHL | Y000 | 202204 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205399.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202205 | M5032 | Barton Park - Loan to OCHL | Y000 | 202205 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202206 | M5032 | Barton Park - Loan to OCHL | Y000 | 202206 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202207 | M5032 | Barton Park - Loan to OCHL | Y000 | 202207 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205399.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202208 | M5032 | Barton Park - Loan to OCHL | Y000 | 202208 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202209 | M5032 | Barton Park - Loan to OCHL | Y000 | 202209 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202210 | M5032 | Barton Park - Loan to OCHL | Y000 | 202210 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205399.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202211 | M5032 | Barton Park - Loan to OCHL | Y000 | 202211 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205399.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5032202212 | M5032 | Barton Park - Loan to OCHL | Y000 | 202212 | OX-1003099 | 518679 | 2021/22 CAPV | 2021/22 Capital Virements | 205152.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202201 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202201 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202202 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202202 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202203 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202203 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18881.34 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202204 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202204 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202205 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202205 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202206 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202206 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18881.34 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202207 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202207 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202208 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202208 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202209 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202209 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18881.34 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202210 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202210 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202211 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202211 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18858.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202212 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202212 | OX-1003076 | 517966 | 2021/22 CAP0 | 2021/22 Capital Original | 18881.34 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5033202201 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202201 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202202 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202202 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202203 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202203 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202204 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202204 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202205 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202205 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202206 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202206 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202207 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202207 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202208 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202208 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202209 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202209 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202210 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202210 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202211 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202211 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.72 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5033202212 | M5033 | Blackbird Leys Regeneration (GF element) | Y000 | 202212 | OX-1003099 | 518678 | 2021/22 CAPV | 2021/22 Capital Virements | 68.64 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
M5034202201 | M5034 | Affordable Housing Supply | Y000 | 202201 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202202 | M5034 | Affordable Housing Supply | Y000 | 202202 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202203 | M5034 | Affordable Housing Supply | Y000 | 202203 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202204 | M5034 | Affordable Housing Supply | Y000 | 202204 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 250200 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202205 | M5034 | Affordable Housing Supply | Y000 | 202205 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202206 | M5034 | Affordable Housing Supply | Y000 | 202206 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202207 | M5034 | Affordable Housing Supply | Y000 | 202207 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 250200 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202208 | M5034 | Affordable Housing Supply | Y000 | 202208 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202209 | M5034 | Affordable Housing Supply | Y000 | 202209 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202210 | M5034 | Affordable Housing Supply | Y000 | 202210 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 250200 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202211 | M5034 | Affordable Housing Supply | Y000 | 202211 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 250200 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5034202212 | M5034 | Affordable Housing Supply | Y000 | 202212 | OX-1003120 | 519034 | 2021/22 CAPV | 2021/22 Capital Virements | 249900 | 11 | Twelfths Monthly | 2021 Carry Forward | JMARRI
M5035202201 | M5035 | Growth Deal RP Funding | Y000 | 202201 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202202 | M5035 | Growth Deal RP Funding | Y000 | 202202 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202203 | M5035 | Growth Deal RP Funding | Y000 | 202203 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 575460 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202204 | M5035 | Growth Deal RP Funding | Y000 | 202204 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202205 | M5035 | Growth Deal RP Funding | Y000 | 202205 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202206 | M5035 | Growth Deal RP Funding | Y000 | 202206 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 575460 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202207 | M5035 | Growth Deal RP Funding | Y000 | 202207 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202208 | M5035 | Growth Deal RP Funding | Y000 | 202208 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202209 | M5035 | Growth Deal RP Funding | Y000 | 202209 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 575460 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202210 | M5035 | Growth Deal RP Funding | Y000 | 202210 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202211 | M5035 | Growth Deal RP Funding | Y000 | 202211 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 574770 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202212 | M5035 | Growth Deal RP Funding | Y000 | 202212 | OX-1003076 | 517965 | 2021/22 CAP0 | 2021/22 Capital Original | 575460 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
M5035202201 | M5035 | Growth Deal RP Funding | Y000 | 202201 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202202 | M5035 | Growth Deal RP Funding | Y000 | 202202 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202203 | M5035 | Growth Deal RP Funding | Y000 | 202203 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202204 | M5035 | Growth Deal RP Funding | Y000 | 202204 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28939.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202205 | M5035 | Growth Deal RP Funding | Y000 | 202205 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202206 | M5035 | Growth Deal RP Funding | Y000 | 202206 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202207 | M5035 | Growth Deal RP Funding | Y000 | 202207 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28939.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202208 | M5035 | Growth Deal RP Funding | Y000 | 202208 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202209 | M5035 | Growth Deal RP Funding | Y000 | 202209 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202210 | M5035 | Growth Deal RP Funding | Y000 | 202210 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28939.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202211 | M5035 | Growth Deal RP Funding | Y000 | 202211 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28939.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
M5035202212 | M5035 | Growth Deal RP Funding | Y000 | 202212 | OX-1003077 | 518095 | 2021/22 CAPV | 2021/22 Capital Virements | 28905.1 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6384202201 | N6384 | Tower Blocks | Y000 | 202201 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202202 | N6384 | Tower Blocks | Y000 | 202202 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202203 | N6384 | Tower Blocks | Y000 | 202203 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202204 | N6384 | Tower Blocks | Y000 | 202204 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202205 | N6384 | Tower Blocks | Y000 | 202205 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202206 | N6384 | Tower Blocks | Y000 | 202206 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 1401.4 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202207 | N6384 | Tower Blocks | Y000 | 202207 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 20020 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202208 | N6384 | Tower Blocks | Y000 | 202208 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 64064 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202209 | N6384 | Tower Blocks | Y000 | 202209 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 2002 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202210 | N6384 | Tower Blocks | Y000 | 202210 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 2002 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202211 | N6384 | Tower Blocks | Y000 | 202211 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 2002 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202212 | N6384 | Tower Blocks | Y000 | 202212 | OX-1003076 | 517964 | 2021/22 CAP0 | 2021/22 Capital Original | 101701.6 | 521 | N6384 TB | App6 Budget Load | TCHENG
N6384202201 | N6384 | Tower Blocks | Y000 | 202201 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202202 | N6384 | Tower Blocks | Y000 | 202202 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202203 | N6384 | Tower Blocks | Y000 | 202203 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202204 | N6384 | Tower Blocks | Y000 | 202204 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202205 | N6384 | Tower Blocks | Y000 | 202205 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202206 | N6384 | Tower Blocks | Y000 | 202206 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 5590.54 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202207 | N6384 | Tower Blocks | Y000 | 202207 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 79864.9 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202208 | N6384 | Tower Blocks | Y000 | 202208 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 255567.68 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202209 | N6384 | Tower Blocks | Y000 | 202209 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 7986.49 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202210 | N6384 | Tower Blocks | Y000 | 202210 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 7986.49 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202211 | N6384 | Tower Blocks | Y000 | 202211 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 7986.49 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202212 | N6384 | Tower Blocks | Y000 | 202212 | OX-1003077 | 518091 | 2021/22 CAPV | 2021/22 Capital Virements | 405713.69 | 521 | N6384 TB | 2021/22 Slippage | TCHENG
N6384202201 | N6384 | Tower Blocks | Y000 | 202201 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202202 | N6384 | Tower Blocks | Y000 | 202202 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202203 | N6384 | Tower Blocks | Y000 | 202203 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202204 | N6384 | Tower Blocks | Y000 | 202204 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28410.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202205 | N6384 | Tower Blocks | Y000 | 202205 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202206 | N6384 | Tower Blocks | Y000 | 202206 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202207 | N6384 | Tower Blocks | Y000 | 202207 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28410.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202208 | N6384 | Tower Blocks | Y000 | 202208 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202209 | N6384 | Tower Blocks | Y000 | 202209 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202210 | N6384 | Tower Blocks | Y000 | 202210 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28410.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202211 | N6384 | Tower Blocks | Y000 | 202211 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28410.13 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202212 | N6384 | Tower Blocks | Y000 | 202212 | OX-1003099 | 518668 | 2021/22 CAPV | 2021/22 Capital Virements | 28376.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6384202201 | N6384 | Tower Blocks | Y000 | 202201 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202202 | N6384 | Tower Blocks | Y000 | 202202 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202203 | N6384 | Tower Blocks | Y000 | 202203 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202204 | N6384 | Tower Blocks | Y000 | 202204 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28410.13 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202205 | N6384 | Tower Blocks | Y000 | 202205 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202206 | N6384 | Tower Blocks | Y000 | 202206 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202207 | N6384 | Tower Blocks | Y000 | 202207 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28410.13 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202208 | N6384 | Tower Blocks | Y000 | 202208 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202209 | N6384 | Tower Blocks | Y000 | 202209 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202210 | N6384 | Tower Blocks | Y000 | 202210 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28410.13 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202211 | N6384 | Tower Blocks | Y000 | 202211 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28410.13 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6384202212 | N6384 | Tower Blocks | Y000 | 202212 | OX-1003103 | 518862 | 2021/22 CAPV | 2021/22 Capital Virements | -28376.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6385202201 | N6385 | Adaptations for disabled | Y000 | 202201 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 54700.8 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202202 | N6385 | Adaptations for disabled | Y000 | 202202 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 48294.4 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202203 | N6385 | Adaptations for disabled | Y000 | 202203 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 74412.8 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202204 | N6385 | Adaptations for disabled | Y000 | 202204 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 48505.6 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202205 | N6385 | Adaptations for disabled | Y000 | 202205 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 61318.4 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202206 | N6385 | Adaptations for disabled | Y000 | 202206 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 54982.4 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202207 | N6385 | Adaptations for disabled | Y000 | 202207 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 61459.2 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202208 | N6385 | Adaptations for disabled | Y000 | 202208 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 71174.4 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202209 | N6385 | Adaptations for disabled | Y000 | 202209 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 41536 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202210 | N6385 | Adaptations for disabled | Y000 | 202210 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 54982.4 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202211 | N6385 | Adaptations for disabled | Y000 | 202211 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 58220.8 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6385202212 | N6385 | Adaptations for disabled | Y000 | 202212 | OX-1003076 | 517963 | 2021/22 CAP0 | 2021/22 Capital Original | 74412.8 | 376 | BS Producitve Per Head | App6 Budget Load | AWICKE
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 8466 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 8466 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 8466 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 186252 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 25398 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 25398 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 25398 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 84660 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 101592 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 101592 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003076 | 517962 | 2021/22 CAP0 | 2021/22 Capital Original | 270912 | 467 | Structural N6386 | App6 Budget Load | AWICKE
N6386202201 | N6386 | Structural | Y000 | 202201 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -8466 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70606.44 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -8466 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -8466 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -186252 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70606.44 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -25398 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -25398 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -25398 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70606.44 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -84660 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -101592 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70521.78 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -101592 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003115 | 519009 | 2021/22 CAP0 | 2021/22 Capital Original | 70606.44 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003115 | 519010 | 2021/22 CAP0 | 2021/22 Capital Original | -270912 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 3849.45 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 3849.45 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 3849.45 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 84687.9 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 11548.35 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 11548.35 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 11548.35 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 38494.5 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 46193.4 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 46193.4 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003077 | 518090 | 2021/22 CAPV | 2021/22 Capital Virements | 123182.4 | 467 | Structural N6386 | 2021/22 Slippage | AWICKE
N6386202201 | N6386 | Structural | Y000 | 202201 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.73 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003099 | 518667 | 2021/22 CAPV | 2021/22 Capital Virements | 393.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6386202201 | N6386 | Structural | Y000 | 202201 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.73 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.73 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.25 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.73 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.73 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003103 | 518861 | 2021/22 CAPV | 2021/22 Capital Virements | -393.26 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6386202201 | N6386 | Structural | Y000 | 202201 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -3849.45 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -3849.45 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32104.41 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -3849.45 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -84687.9 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -11548.35 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32104.41 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -11548.35 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -11548.35 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -38494.5 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32104.41 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -46193.4 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32104.41 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -46193.4 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003116 | 519023 | 2021/22 CAPV | 2021/22 Capital Virements | 32065.92 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003116 | 519024 | 2021/22 CAPV | 2021/22 Capital Virements | -123182.4 | 467 | Structural N6386 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6386202202 | N6386 | Structural | Y000 | 202202 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 19.22 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202203 | N6386 | Structural | Y000 | 202203 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 19.22 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202204 | N6386 | Structural | Y000 | 202204 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 19.22 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202205 | N6386 | Structural | Y000 | 202205 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 422.74 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202206 | N6386 | Structural | Y000 | 202206 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 57.65 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202207 | N6386 | Structural | Y000 | 202207 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 57.65 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202208 | N6386 | Structural | Y000 | 202208 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 57.65 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202209 | N6386 | Structural | Y000 | 202209 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 192.16 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202210 | N6386 | Structural | Y000 | 202210 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 230.59 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202211 | N6386 | Structural | Y000 | 202211 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 230.59 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6386202212 | N6386 | Structural | Y000 | 202212 | OX-1003121 | 519042 | 2021/22 CAPV | 2021/22 Capital Virements | 614.89 | 467 | Structural N6386 | P2 HRA Slippage corrections | JMARRI
N6387202203 | N6387 | Controlled Entry | Y000 | 202203 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202204 | N6387 | Controlled Entry | Y000 | 202204 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202205 | N6387 | Controlled Entry | Y000 | 202205 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202206 | N6387 | Controlled Entry | Y000 | 202206 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202207 | N6387 | Controlled Entry | Y000 | 202207 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202208 | N6387 | Controlled Entry | Y000 | 202208 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202209 | N6387 | Controlled Entry | Y000 | 202209 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202210 | N6387 | Controlled Entry | Y000 | 202210 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202211 | N6387 | Controlled Entry | Y000 | 202211 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202212 | N6387 | Controlled Entry | Y000 | 202212 | OX-1003076 | 517961 | 2021/22 CAP0 | 2021/22 Capital Original | 31250 | 36 | Approved Adjustments - June | App6 Budget Load | AWICKE
N6387202203 | N6387 | Controlled Entry | Y000 | 202203 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202204 | N6387 | Controlled Entry | Y000 | 202204 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202205 | N6387 | Controlled Entry | Y000 | 202205 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202206 | N6387 | Controlled Entry | Y000 | 202206 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202207 | N6387 | Controlled Entry | Y000 | 202207 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202208 | N6387 | Controlled Entry | Y000 | 202208 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202209 | N6387 | Controlled Entry | Y000 | 202209 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202210 | N6387 | Controlled Entry | Y000 | 202210 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202211 | N6387 | Controlled Entry | Y000 | 202211 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202212 | N6387 | Controlled Entry | Y000 | 202212 | OX-1003077 | 518089 | 2021/22 CAPV | 2021/22 Capital Virements | 5858.3 | 36 | Approved Adjustments - June | 2021/22 Slippage | AWICKE
N6387202201 | N6387 | Controlled Entry | Y000 | 202201 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202202 | N6387 | Controlled Entry | Y000 | 202202 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202203 | N6387 | Controlled Entry | Y000 | 202203 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202204 | N6387 | Controlled Entry | Y000 | 202204 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4885.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202205 | N6387 | Controlled Entry | Y000 | 202205 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202206 | N6387 | Controlled Entry | Y000 | 202206 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202207 | N6387 | Controlled Entry | Y000 | 202207 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4885.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202208 | N6387 | Controlled Entry | Y000 | 202208 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202209 | N6387 | Controlled Entry | Y000 | 202209 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202210 | N6387 | Controlled Entry | Y000 | 202210 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4885.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202211 | N6387 | Controlled Entry | Y000 | 202211 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4885.91 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202212 | N6387 | Controlled Entry | Y000 | 202212 | OX-1003099 | 518666 | 2021/22 CAPV | 2021/22 Capital Virements | 4880.05 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6387202201 | N6387 | Controlled Entry | Y000 | 202201 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202202 | N6387 | Controlled Entry | Y000 | 202202 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202203 | N6387 | Controlled Entry | Y000 | 202203 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202204 | N6387 | Controlled Entry | Y000 | 202204 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4885.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202205 | N6387 | Controlled Entry | Y000 | 202205 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202206 | N6387 | Controlled Entry | Y000 | 202206 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202207 | N6387 | Controlled Entry | Y000 | 202207 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4885.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202208 | N6387 | Controlled Entry | Y000 | 202208 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202209 | N6387 | Controlled Entry | Y000 | 202209 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202210 | N6387 | Controlled Entry | Y000 | 202210 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4885.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202211 | N6387 | Controlled Entry | Y000 | 202211 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4885.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6387202212 | N6387 | Controlled Entry | Y000 | 202212 | OX-1003103 | 518860 | 2021/22 CAPV | 2021/22 Capital Virements | -4880.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202205 | N6388 | Major Voids | Y000 | 202205 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 84346.4 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202207 | N6388 | Major Voids | Y000 | 202207 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 65608 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202208 | N6388 | Major Voids | Y000 | 202208 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 65608 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202209 | N6388 | Major Voids | Y000 | 202209 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 65608 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202210 | N6388 | Major Voids | Y000 | 202210 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 65608 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202211 | N6388 | Major Voids | Y000 | 202211 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 65608 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202212 | N6388 | Major Voids | Y000 | 202212 | OX-1003076 | 517960 | 2021/22 CAP0 | 2021/22 Capital Original | 59613.6 | 580 | N6388 Major Voids | App6 Budget Load | AWICKE
N6388202201 | N6388 | Major Voids | Y000 | 202201 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202202 | N6388 | Major Voids | Y000 | 202202 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202203 | N6388 | Major Voids | Y000 | 202203 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39364.8 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202204 | N6388 | Major Voids | Y000 | 202204 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202205 | N6388 | Major Voids | Y000 | 202205 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202205 | N6388 | Major Voids | Y000 | 202205 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -84346.4 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202206 | N6388 | Major Voids | Y000 | 202206 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39364.8 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202207 | N6388 | Major Voids | Y000 | 202207 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202207 | N6388 | Major Voids | Y000 | 202207 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -65608 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202208 | N6388 | Major Voids | Y000 | 202208 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202208 | N6388 | Major Voids | Y000 | 202208 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -65608 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202209 | N6388 | Major Voids | Y000 | 202209 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39364.8 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202209 | N6388 | Major Voids | Y000 | 202209 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -65608 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202210 | N6388 | Major Voids | Y000 | 202210 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202210 | N6388 | Major Voids | Y000 | 202210 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -65608 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202211 | N6388 | Major Voids | Y000 | 202211 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39317.6 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202211 | N6388 | Major Voids | Y000 | 202211 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -65608 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202212 | N6388 | Major Voids | Y000 | 202212 | OX-1003115 | 518993 | 2021/22 CAP0 | 2021/22 Capital Original | 39364.8 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202212 | N6388 | Major Voids | Y000 | 202212 | OX-1003115 | 518994 | 2021/22 CAP0 | 2021/22 Capital Original | -59613.6 | 580 | N6388 Major Voids | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6388202201 | N6388 | Major Voids | Y000 | 202201 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202202 | N6388 | Major Voids | Y000 | 202202 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202203 | N6388 | Major Voids | Y000 | 202203 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202204 | N6388 | Major Voids | Y000 | 202204 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16069.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202205 | N6388 | Major Voids | Y000 | 202205 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202206 | N6388 | Major Voids | Y000 | 202206 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202207 | N6388 | Major Voids | Y000 | 202207 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16069.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202208 | N6388 | Major Voids | Y000 | 202208 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202209 | N6388 | Major Voids | Y000 | 202209 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202210 | N6388 | Major Voids | Y000 | 202210 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16069.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202211 | N6388 | Major Voids | Y000 | 202211 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16069.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202212 | N6388 | Major Voids | Y000 | 202212 | OX-1003099 | 518665 | 2021/22 CAPV | 2021/22 Capital Virements | 16049.74 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6388202201 | N6388 | Major Voids | Y000 | 202201 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202202 | N6388 | Major Voids | Y000 | 202202 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202203 | N6388 | Major Voids | Y000 | 202203 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202204 | N6388 | Major Voids | Y000 | 202204 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16069.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202205 | N6388 | Major Voids | Y000 | 202205 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202206 | N6388 | Major Voids | Y000 | 202206 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202207 | N6388 | Major Voids | Y000 | 202207 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16069.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202208 | N6388 | Major Voids | Y000 | 202208 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202209 | N6388 | Major Voids | Y000 | 202209 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202210 | N6388 | Major Voids | Y000 | 202210 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16069.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202211 | N6388 | Major Voids | Y000 | 202211 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16069.01 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6388202212 | N6388 | Major Voids | Y000 | 202212 | OX-1003103 | 518859 | 2021/22 CAPV | 2021/22 Capital Virements | -16049.74 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202201 | N6389 | Damp-proof works (K&B) | Y000 | 202201 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202202 | N6389 | Damp-proof works (K&B) | Y000 | 202202 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202203 | N6389 | Damp-proof works (K&B) | Y000 | 202203 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9924.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202204 | N6389 | Damp-proof works (K&B) | Y000 | 202204 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202205 | N6389 | Damp-proof works (K&B) | Y000 | 202205 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202206 | N6389 | Damp-proof works (K&B) | Y000 | 202206 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9924.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202207 | N6389 | Damp-proof works (K&B) | Y000 | 202207 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202208 | N6389 | Damp-proof works (K&B) | Y000 | 202208 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202209 | N6389 | Damp-proof works (K&B) | Y000 | 202209 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9924.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202210 | N6389 | Damp-proof works (K&B) | Y000 | 202210 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202211 | N6389 | Damp-proof works (K&B) | Y000 | 202211 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9912.7 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202212 | N6389 | Damp-proof works (K&B) | Y000 | 202212 | OX-1003076 | 517959 | 2021/22 CAP0 | 2021/22 Capital Original | 9924.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N6389202201 | N6389 | Damp-proof works (K&B) | Y000 | 202201 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202202 | N6389 | Damp-proof works (K&B) | Y000 | 202202 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202203 | N6389 | Damp-proof works (K&B) | Y000 | 202203 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202204 | N6389 | Damp-proof works (K&B) | Y000 | 202204 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202205 | N6389 | Damp-proof works (K&B) | Y000 | 202205 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202206 | N6389 | Damp-proof works (K&B) | Y000 | 202206 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202207 | N6389 | Damp-proof works (K&B) | Y000 | 202207 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202208 | N6389 | Damp-proof works (K&B) | Y000 | 202208 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202209 | N6389 | Damp-proof works (K&B) | Y000 | 202209 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202210 | N6389 | Damp-proof works (K&B) | Y000 | 202210 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202211 | N6389 | Damp-proof works (K&B) | Y000 | 202211 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202212 | N6389 | Damp-proof works (K&B) | Y000 | 202212 | OX-1003077 | 518088 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N6389202201 | N6389 | Damp-proof works (K&B) | Y000 | 202201 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202202 | N6389 | Damp-proof works (K&B) | Y000 | 202202 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202203 | N6389 | Damp-proof works (K&B) | Y000 | 202203 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202204 | N6389 | Damp-proof works (K&B) | Y000 | 202204 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202205 | N6389 | Damp-proof works (K&B) | Y000 | 202205 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202206 | N6389 | Damp-proof works (K&B) | Y000 | 202206 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202207 | N6389 | Damp-proof works (K&B) | Y000 | 202207 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202208 | N6389 | Damp-proof works (K&B) | Y000 | 202208 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202209 | N6389 | Damp-proof works (K&B) | Y000 | 202209 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202210 | N6389 | Damp-proof works (K&B) | Y000 | 202210 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202211 | N6389 | Damp-proof works (K&B) | Y000 | 202211 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2085.5 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202212 | N6389 | Damp-proof works (K&B) | Y000 | 202212 | OX-1003099 | 518664 | 2021/22 CAPV | 2021/22 Capital Virements | 2083 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6389202201 | N6389 | Damp-proof works (K&B) | Y000 | 202201 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202202 | N6389 | Damp-proof works (K&B) | Y000 | 202202 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202203 | N6389 | Damp-proof works (K&B) | Y000 | 202203 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202204 | N6389 | Damp-proof works (K&B) | Y000 | 202204 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2085.5 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202205 | N6389 | Damp-proof works (K&B) | Y000 | 202205 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202206 | N6389 | Damp-proof works (K&B) | Y000 | 202206 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202207 | N6389 | Damp-proof works (K&B) | Y000 | 202207 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2085.5 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202208 | N6389 | Damp-proof works (K&B) | Y000 | 202208 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202209 | N6389 | Damp-proof works (K&B) | Y000 | 202209 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202210 | N6389 | Damp-proof works (K&B) | Y000 | 202210 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2085.5 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202211 | N6389 | Damp-proof works (K&B) | Y000 | 202211 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2085.5 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6389202212 | N6389 | Damp-proof works (K&B) | Y000 | 202212 | OX-1003103 | 518858 | 2021/22 CAPV | 2021/22 Capital Virements | -2083 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 13624 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 30264 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 30264 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 15080 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 181376 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 362856 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003076 | 517958 | 2021/22 CAP0 | 2021/22 Capital Original | 406536 | 488 | Roofing | App6 Budget Load | AWICKE
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -13624 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202202 | N6392 | Roofing | Y000 | 202202 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202203 | N6392 | Roofing | Y000 | 202203 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86736 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202204 | N6392 | Roofing | Y000 | 202204 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202205 | N6392 | Roofing | Y000 | 202205 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202206 | N6392 | Roofing | Y000 | 202206 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86736 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -30264 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -30264 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86736 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -15080 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -181376 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86632 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -362856 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003115 | 518997 | 2021/22 CAP0 | 2021/22 Capital Original | 86736 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003115 | 518998 | 2021/22 CAP0 | 2021/22 Capital Original | -406536 | 488 | Roofing | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 3452.13 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 7668.46 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 7668.46 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 3821.05 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 45958.06 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 91942.48 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003077 | 518087 | 2021/22 CAPV | 2021/22 Capital Virements | 103010.36 | 488 | Roofing | 2021/22 Slippage | AWICKE
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202202 | N6392 | Roofing | Y000 | 202202 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202203 | N6392 | Roofing | Y000 | 202203 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202204 | N6392 | Roofing | Y000 | 202204 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29100.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202205 | N6392 | Roofing | Y000 | 202205 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202206 | N6392 | Roofing | Y000 | 202206 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29100.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29100.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29100.51 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003099 | 518663 | 2021/22 CAPV | 2021/22 Capital Virements | 29065.62 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202202 | N6392 | Roofing | Y000 | 202202 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202203 | N6392 | Roofing | Y000 | 202203 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202204 | N6392 | Roofing | Y000 | 202204 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29100.51 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202205 | N6392 | Roofing | Y000 | 202205 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202206 | N6392 | Roofing | Y000 | 202206 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29100.51 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29100.51 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29100.51 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003103 | 518857 | 2021/22 CAPV | 2021/22 Capital Virements | -29065.62 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202201 | N6392 | Roofing | Y000 | 202201 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -3452.13 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202202 | N6392 | Roofing | Y000 | 202202 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202203 | N6392 | Roofing | Y000 | 202203 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202204 | N6392 | Roofing | Y000 | 202204 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21977.65 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202205 | N6392 | Roofing | Y000 | 202205 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202206 | N6392 | Roofing | Y000 | 202206 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21977.65 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202207 | N6392 | Roofing | Y000 | 202207 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -7668.46 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202208 | N6392 | Roofing | Y000 | 202208 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -7668.46 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202209 | N6392 | Roofing | Y000 | 202209 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -3821.05 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21977.65 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202210 | N6392 | Roofing | Y000 | 202210 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -45958.06 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21977.65 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202211 | N6392 | Roofing | Y000 | 202211 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -91942.48 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003116 | 519013 | 2021/22 CAPV | 2021/22 Capital Virements | 21951.3 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6392202212 | N6392 | Roofing | Y000 | 202212 | OX-1003116 | 519014 | 2021/22 CAPV | 2021/22 Capital Virements | -103010.36 | 488 | Roofing | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 29875 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 28750 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 17250 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 29312.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 58812.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 88312.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 88437.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 70750 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 41250 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 58937.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 76625 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003076 | 517957 | 2021/22 CAP0 | 2021/22 Capital Original | 36687.5 | 378 | Electric Rewires N6395 | App6 Budget Load | AWICKE
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -29875 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -28750 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52125 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -17250 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -29312.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -58812.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52125 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -88312.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -88437.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -70750 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52125 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -41250 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -58937.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52062.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -76625 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003115 | 518995 | 2021/22 CAP0 | 2021/22 Capital Original | 52125 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003115 | 518996 | 2021/22 CAP0 | 2021/22 Capital Original | -36687.5 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 30371.69 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 29227.99 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 17536.79 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 29799.84 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 59790.29 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 89780.75 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 89907.83 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 71926.26 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 41935.81 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 59917.37 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 77898.94 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003077 | 518086 | 2021/22 CAPV | 2021/22 Capital Virements | 37297.45 | 378 | Electric Rewires N6395 | 2021/22 Slippage | AWICKE
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3681.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3681.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3681.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3681.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003099 | 518662 | 2021/22 CAPV | 2021/22 Capital Virements | 3677.36 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3681.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3681.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3681.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3681.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003103 | 518856 | 2021/22 CAPV | 2021/22 Capital Virements | -3677.36 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202201 | N6395 | Electrics | Y000 | 202201 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -30371.69 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202202 | N6395 | Electrics | Y000 | 202202 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -29227.99 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202203 | N6395 | Electrics | Y000 | 202203 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -17536.79 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52991.61 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202204 | N6395 | Electrics | Y000 | 202204 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -29799.84 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202205 | N6395 | Electrics | Y000 | 202205 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -59790.29 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202206 | N6395 | Electrics | Y000 | 202206 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -89780.75 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52991.61 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202207 | N6395 | Electrics | Y000 | 202207 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -89907.83 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202208 | N6395 | Electrics | Y000 | 202208 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -71926.26 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202209 | N6395 | Electrics | Y000 | 202209 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -41935.81 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52991.61 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202210 | N6395 | Electrics | Y000 | 202210 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -59917.37 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52991.61 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202211 | N6395 | Electrics | Y000 | 202211 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -77898.94 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003116 | 519011 | 2021/22 CAPV | 2021/22 Capital Virements | 52928.07 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6395202212 | N6395 | Electrics | Y000 | 202212 | OX-1003116 | 519012 | 2021/22 CAPV | 2021/22 Capital Virements | -37297.45 | 378 | Electric Rewires N6395 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N6434202201 | N6434 | Doors and Windows | Y000 | 202201 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202202 | N6434 | Doors and Windows | Y000 | 202202 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202203 | N6434 | Doors and Windows | Y000 | 202203 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202204 | N6434 | Doors and Windows | Y000 | 202204 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202205 | N6434 | Doors and Windows | Y000 | 202205 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202206 | N6434 | Doors and Windows | Y000 | 202206 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202207 | N6434 | Doors and Windows | Y000 | 202207 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202208 | N6434 | Doors and Windows | Y000 | 202208 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 28960 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202209 | N6434 | Doors and Windows | Y000 | 202209 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 17376 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202210 | N6434 | Doors and Windows | Y000 | 202210 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 133216 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202211 | N6434 | Doors and Windows | Y000 | 202211 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 133216 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202212 | N6434 | Doors and Windows | Y000 | 202212 | OX-1003076 | 517956 | 2021/22 CAP0 | 2021/22 Capital Original | 144800 | 481 | Doors and Windows | App6 Budget Load | AWICKE
N6434202201 | N6434 | Doors and Windows | Y000 | 202201 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202202 | N6434 | Doors and Windows | Y000 | 202202 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202203 | N6434 | Doors and Windows | Y000 | 202203 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202204 | N6434 | Doors and Windows | Y000 | 202204 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202205 | N6434 | Doors and Windows | Y000 | 202205 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202206 | N6434 | Doors and Windows | Y000 | 202206 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202207 | N6434 | Doors and Windows | Y000 | 202207 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202208 | N6434 | Doors and Windows | Y000 | 202208 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 1196.15 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202209 | N6434 | Doors and Windows | Y000 | 202209 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 717.69 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202210 | N6434 | Doors and Windows | Y000 | 202210 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 5502.29 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202211 | N6434 | Doors and Windows | Y000 | 202211 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 5502.29 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202212 | N6434 | Doors and Windows | Y000 | 202212 | OX-1003077 | 518085 | 2021/22 CAPV | 2021/22 Capital Virements | 5980.75 | 481 | Doors and Windows | 2021/22 Slippage | AWICKE
N6434202201 | N6434 | Doors and Windows | Y000 | 202201 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202202 | N6434 | Doors and Windows | Y000 | 202202 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202203 | N6434 | Doors and Windows | Y000 | 202203 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202204 | N6434 | Doors and Windows | Y000 | 202204 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8913.54 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202205 | N6434 | Doors and Windows | Y000 | 202205 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202206 | N6434 | Doors and Windows | Y000 | 202206 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202207 | N6434 | Doors and Windows | Y000 | 202207 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8913.54 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202208 | N6434 | Doors and Windows | Y000 | 202208 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202209 | N6434 | Doors and Windows | Y000 | 202209 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202210 | N6434 | Doors and Windows | Y000 | 202210 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8913.54 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202211 | N6434 | Doors and Windows | Y000 | 202211 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8913.54 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202212 | N6434 | Doors and Windows | Y000 | 202212 | OX-1003099 | 518661 | 2021/22 CAPV | 2021/22 Capital Virements | -8902.85 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N6434202201 | N6434 | Doors and Windows | Y000 | 202201 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202202 | N6434 | Doors and Windows | Y000 | 202202 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202203 | N6434 | Doors and Windows | Y000 | 202203 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202204 | N6434 | Doors and Windows | Y000 | 202204 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8913.56 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202205 | N6434 | Doors and Windows | Y000 | 202205 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202206 | N6434 | Doors and Windows | Y000 | 202206 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202207 | N6434 | Doors and Windows | Y000 | 202207 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8913.56 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202208 | N6434 | Doors and Windows | Y000 | 202208 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202209 | N6434 | Doors and Windows | Y000 | 202209 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202210 | N6434 | Doors and Windows | Y000 | 202210 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8913.56 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202211 | N6434 | Doors and Windows | Y000 | 202211 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8913.56 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N6434202212 | N6434 | Doors and Windows | Y000 | 202212 | OX-1003103 | 518855 | 2021/22 CAPV | 2021/22 Capital Virements | 8902.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 34450 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 15900 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 26500 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 21200 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003076 | 517955 | 2021/22 CAP0 | 2021/22 Capital Original | 18550 | 583 | N7020 - Extensions & Major Adaptations | App6 Budget Load | AWICKE
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -34450 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -15900 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22101 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -26500 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22101 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22101 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22074.5 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -21200 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003115 | 519007 | 2021/22 CAP0 | 2021/22 Capital Original | 22101 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003115 | 519008 | 2021/22 CAP0 | 2021/22 Capital Original | -18550 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 33779.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 15590.4 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 25984 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 20787.2 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003077 | 518084 | 2021/22 CAPV | 2021/22 Capital Virements | 18188.8 | 583 | N7020 - Extensions & Major Adaptations | 2021/22 Slippage | AWICKE
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12689.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12689.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12689.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12689.23 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003099 | 518660 | 2021/22 CAPV | 2021/22 Capital Virements | -12674.01 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12689.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12689.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12689.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12689.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003103 | 518854 | 2021/22 CAPV | 2021/22 Capital Virements | 12673.98 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -33779.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -15590.4 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -25984 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21670.66 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21670.66 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21670.66 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21670.66 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -20787.2 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003116 | 519021 | 2021/22 CAPV | 2021/22 Capital Virements | 21644.67 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003116 | 519022 | 2021/22 CAPV | 2021/22 Capital Virements | -18188.8 | 583 | N7020 - Extensions & Major Adaptations | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7020202201 | N7020 | Extensions & Major Adaptions | Y000 | 202201 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -13021.79 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202202 | N7020 | Extensions & Major Adaptions | Y000 | 202202 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -6010.06 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202203 | N7020 | Extensions & Major Adaptions | Y000 | 202203 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -10016.76 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202204 | N7020 | Extensions & Major Adaptions | Y000 | 202204 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202205 | N7020 | Extensions & Major Adaptions | Y000 | 202205 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202206 | N7020 | Extensions & Major Adaptions | Y000 | 202206 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202207 | N7020 | Extensions & Major Adaptions | Y000 | 202207 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202208 | N7020 | Extensions & Major Adaptions | Y000 | 202208 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202209 | N7020 | Extensions & Major Adaptions | Y000 | 202209 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202210 | N7020 | Extensions & Major Adaptions | Y000 | 202210 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202211 | N7020 | Extensions & Major Adaptions | Y000 | 202211 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -8013.41 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7020202212 | N7020 | Extensions & Major Adaptions | Y000 | 202212 | OX-1003121 | 519041 | 2021/22 CAPV | 2021/22 Capital Virements | -7011.74 | 583 | N7020 - Extensions & Major Adaptations | P2 HRA Slippage corrections | JMARRI
N7026202202 | N7026 | Communal Areas | Y000 | 202202 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 5940 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202204 | N7026 | Communal Areas | Y000 | 202204 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 7920 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202206 | N7026 | Communal Areas | Y000 | 202206 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 3960 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202207 | N7026 | Communal Areas | Y000 | 202207 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 3960 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202208 | N7026 | Communal Areas | Y000 | 202208 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 11880 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202210 | N7026 | Communal Areas | Y000 | 202210 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 33660 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202211 | N7026 | Communal Areas | Y000 | 202211 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 39600 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202212 | N7026 | Communal Areas | Y000 | 202212 | OX-1003076 | 517954 | 2021/22 CAP0 | 2021/22 Capital Original | 91080 | 573 | Communal Areas | App6 Budget Load | AWICKE
N7026202202 | N7026 | Communal Areas | Y000 | 202202 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 10056.33 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202204 | N7026 | Communal Areas | Y000 | 202204 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 13408.44 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202206 | N7026 | Communal Areas | Y000 | 202206 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 6704.22 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202207 | N7026 | Communal Areas | Y000 | 202207 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 6704.22 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202208 | N7026 | Communal Areas | Y000 | 202208 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 20112.66 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202210 | N7026 | Communal Areas | Y000 | 202210 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 56985.87 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202211 | N7026 | Communal Areas | Y000 | 202211 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 67042.2 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202212 | N7026 | Communal Areas | Y000 | 202212 | OX-1003077 | 518083 | 2021/22 CAPV | 2021/22 Capital Virements | 154197.06 | 573 | Communal Areas | 2021/22 Slippage | AWICKE
N7026202201 | N7026 | Communal Areas | Y000 | 202201 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202202 | N7026 | Communal Areas | Y000 | 202202 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202203 | N7026 | Communal Areas | Y000 | 202203 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202204 | N7026 | Communal Areas | Y000 | 202204 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2456.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202205 | N7026 | Communal Areas | Y000 | 202205 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202206 | N7026 | Communal Areas | Y000 | 202206 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202207 | N7026 | Communal Areas | Y000 | 202207 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2456.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202208 | N7026 | Communal Areas | Y000 | 202208 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202209 | N7026 | Communal Areas | Y000 | 202209 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202210 | N7026 | Communal Areas | Y000 | 202210 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2456.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202211 | N7026 | Communal Areas | Y000 | 202211 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2456.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202212 | N7026 | Communal Areas | Y000 | 202212 | OX-1003099 | 518659 | 2021/22 CAPV | 2021/22 Capital Virements | 2453.27 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7026202201 | N7026 | Communal Areas | Y000 | 202201 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202202 | N7026 | Communal Areas | Y000 | 202202 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202203 | N7026 | Communal Areas | Y000 | 202203 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202204 | N7026 | Communal Areas | Y000 | 202204 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2456.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202205 | N7026 | Communal Areas | Y000 | 202205 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202206 | N7026 | Communal Areas | Y000 | 202206 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202207 | N7026 | Communal Areas | Y000 | 202207 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2456.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202208 | N7026 | Communal Areas | Y000 | 202208 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202209 | N7026 | Communal Areas | Y000 | 202209 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202210 | N7026 | Communal Areas | Y000 | 202210 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2456.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202211 | N7026 | Communal Areas | Y000 | 202211 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2456.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202212 | N7026 | Communal Areas | Y000 | 202212 | OX-1003103 | 518853 | 2021/22 CAPV | 2021/22 Capital Virements | -2453.27 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7026202201 | N7026 | Communal Areas | Y000 | 202201 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202202 | N7026 | Communal Areas | Y000 | 202202 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202203 | N7026 | Communal Areas | Y000 | 202203 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202204 | N7026 | Communal Areas | Y000 | 202204 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1307.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202205 | N7026 | Communal Areas | Y000 | 202205 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202206 | N7026 | Communal Areas | Y000 | 202206 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202207 | N7026 | Communal Areas | Y000 | 202207 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1307.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202208 | N7026 | Communal Areas | Y000 | 202208 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202209 | N7026 | Communal Areas | Y000 | 202209 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202210 | N7026 | Communal Areas | Y000 | 202210 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1307.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202211 | N7026 | Communal Areas | Y000 | 202211 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1307.55 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7026202212 | N7026 | Communal Areas | Y000 | 202212 | OX-1003105 | 518955 | 2021/22 CAPV | 2021/22 Capital Virements | 1305.98 | 11 | Twelfths Monthly | 2021 Capital Carry Forward adj. | JMARRI
N7032202201 | N7032 | Great Estates Programme | Y000 | 202201 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 26000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202202 | N7032 | Great Estates Programme | Y000 | 202202 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 13000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202203 | N7032 | Great Estates Programme | Y000 | 202203 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 32500 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202204 | N7032 | Great Estates Programme | Y000 | 202204 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 52000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202206 | N7032 | Great Estates Programme | Y000 | 202206 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 351000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202208 | N7032 | Great Estates Programme | Y000 | 202208 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 273000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202209 | N7032 | Great Estates Programme | Y000 | 202209 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 409500 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202210 | N7032 | Great Estates Programme | Y000 | 202210 | OX-1003076 | 517953 | 2021/22 CAP0 | 2021/22 Capital Original | 143000 | 493 | N7032 Great Estates CP | App6 Budget Load | AWICKE
N7032202201 | N7032 | Great Estates Programme | Y000 | 202201 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -1935.5 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202202 | N7032 | Great Estates Programme | Y000 | 202202 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -967.75 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202203 | N7032 | Great Estates Programme | Y000 | 202203 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -2419.38 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202204 | N7032 | Great Estates Programme | Y000 | 202204 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -3871 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202206 | N7032 | Great Estates Programme | Y000 | 202206 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -26129.25 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202208 | N7032 | Great Estates Programme | Y000 | 202208 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -20322.75 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202209 | N7032 | Great Estates Programme | Y000 | 202209 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -30484.13 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202210 | N7032 | Great Estates Programme | Y000 | 202210 | OX-1003077 | 518082 | 2021/22 CAPV | 2021/22 Capital Virements | -10645.25 | 493 | N7032 Great Estates CP | 2021/22 Slippage | AWICKE
N7032202201 | N7032 | Great Estates Programme | Y000 | 202201 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202202 | N7032 | Great Estates Programme | Y000 | 202202 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202203 | N7032 | Great Estates Programme | Y000 | 202203 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202204 | N7032 | Great Estates Programme | Y000 | 202204 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59096.07 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202205 | N7032 | Great Estates Programme | Y000 | 202205 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202206 | N7032 | Great Estates Programme | Y000 | 202206 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202207 | N7032 | Great Estates Programme | Y000 | 202207 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59096.07 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202208 | N7032 | Great Estates Programme | Y000 | 202208 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202209 | N7032 | Great Estates Programme | Y000 | 202209 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202210 | N7032 | Great Estates Programme | Y000 | 202210 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59096.07 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202211 | N7032 | Great Estates Programme | Y000 | 202211 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59096.07 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202212 | N7032 | Great Estates Programme | Y000 | 202212 | OX-1003099 | 518658 | 2021/22 CAPV | 2021/22 Capital Virements | -59025.21 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7032202201 | N7032 | Great Estates Programme | Y000 | 202201 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202202 | N7032 | Great Estates Programme | Y000 | 202202 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202203 | N7032 | Great Estates Programme | Y000 | 202203 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202204 | N7032 | Great Estates Programme | Y000 | 202204 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59096.07 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202205 | N7032 | Great Estates Programme | Y000 | 202205 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202206 | N7032 | Great Estates Programme | Y000 | 202206 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202207 | N7032 | Great Estates Programme | Y000 | 202207 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59096.07 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202208 | N7032 | Great Estates Programme | Y000 | 202208 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202209 | N7032 | Great Estates Programme | Y000 | 202209 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202210 | N7032 | Great Estates Programme | Y000 | 202210 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59096.07 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202211 | N7032 | Great Estates Programme | Y000 | 202211 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59096.07 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202212 | N7032 | Great Estates Programme | Y000 | 202212 | OX-1003103 | 518852 | 2021/22 CAPV | 2021/22 Capital Virements | 59025.21 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7032202201 | N7032 | Great Estates Programme | Y000 | 202201 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 464.24 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202202 | N7032 | Great Estates Programme | Y000 | 202202 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 232.12 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202203 | N7032 | Great Estates Programme | Y000 | 202203 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 580.3 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202204 | N7032 | Great Estates Programme | Y000 | 202204 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 928.48 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202206 | N7032 | Great Estates Programme | Y000 | 202206 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 6267.24 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202208 | N7032 | Great Estates Programme | Y000 | 202208 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 4874.52 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202209 | N7032 | Great Estates Programme | Y000 | 202209 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 7311.78 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7032202210 | N7032 | Great Estates Programme | Y000 | 202210 | OX-1003121 | 519040 | 2021/22 CAPV | 2021/22 Capital Virements | 2553.32 | 493 | N7032 Great Estates CP | P2 HRA Slippage corrections | JMARRI
N7033202202 | N7033 | Energy Efficiency Initiatives | Y000 | 202202 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 30052.8 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202203 | N7033 | Energy Efficiency Initiatives | Y000 | 202203 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 37566 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202204 | N7033 | Energy Efficiency Initiatives | Y000 | 202204 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 45079.2 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202205 | N7033 | Energy Efficiency Initiatives | Y000 | 202205 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 75132 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202206 | N7033 | Energy Efficiency Initiatives | Y000 | 202206 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 87654 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202207 | N7033 | Energy Efficiency Initiatives | Y000 | 202207 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 12522 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202208 | N7033 | Energy Efficiency Initiatives | Y000 | 202208 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 12522 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202210 | N7033 | Energy Efficiency Initiatives | Y000 | 202210 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 250440 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202211 | N7033 | Energy Efficiency Initiatives | Y000 | 202211 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 250440 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202212 | N7033 | Energy Efficiency Initiatives | Y000 | 202212 | OX-1003076 | 517952 | 2021/22 CAP0 | 2021/22 Capital Original | 450792 | 505 | N7033 Energy Efficiency Initiatives | App6 Budget Load | TCHENG
N7033202202 | N7033 | Energy Efficiency Initiatives | Y000 | 202202 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 7214.06 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202203 | N7033 | Energy Efficiency Initiatives | Y000 | 202203 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 9017.58 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202204 | N7033 | Energy Efficiency Initiatives | Y000 | 202204 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 10821.1 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202205 | N7033 | Energy Efficiency Initiatives | Y000 | 202205 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 18035.16 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202206 | N7033 | Energy Efficiency Initiatives | Y000 | 202206 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 21041.02 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202207 | N7033 | Energy Efficiency Initiatives | Y000 | 202207 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 3005.86 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202208 | N7033 | Energy Efficiency Initiatives | Y000 | 202208 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 3005.86 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202210 | N7033 | Energy Efficiency Initiatives | Y000 | 202210 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 60117.2 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202211 | N7033 | Energy Efficiency Initiatives | Y000 | 202211 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 60117.2 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202212 | N7033 | Energy Efficiency Initiatives | Y000 | 202212 | OX-1003077 | 518081 | 2021/22 CAPV | 2021/22 Capital Virements | 108210.96 | 505 | N7033 Energy Efficiency Initiatives | 2021/22 Slippage | TCHENG
N7033202201 | N7033 | Energy Efficiency Initiatives | Y000 | 202201 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202202 | N7033 | Energy Efficiency Initiatives | Y000 | 202202 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202203 | N7033 | Energy Efficiency Initiatives | Y000 | 202203 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202204 | N7033 | Energy Efficiency Initiatives | Y000 | 202204 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25068.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202205 | N7033 | Energy Efficiency Initiatives | Y000 | 202205 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202206 | N7033 | Energy Efficiency Initiatives | Y000 | 202206 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202207 | N7033 | Energy Efficiency Initiatives | Y000 | 202207 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25068.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202208 | N7033 | Energy Efficiency Initiatives | Y000 | 202208 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202209 | N7033 | Energy Efficiency Initiatives | Y000 | 202209 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202210 | N7033 | Energy Efficiency Initiatives | Y000 | 202210 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25068.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202211 | N7033 | Energy Efficiency Initiatives | Y000 | 202211 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25068.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202212 | N7033 | Energy Efficiency Initiatives | Y000 | 202212 | OX-1003099 | 518657 | 2021/22 CAPV | 2021/22 Capital Virements | 25038.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7033202201 | N7033 | Energy Efficiency Initiatives | Y000 | 202201 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202202 | N7033 | Energy Efficiency Initiatives | Y000 | 202202 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202203 | N7033 | Energy Efficiency Initiatives | Y000 | 202203 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202204 | N7033 | Energy Efficiency Initiatives | Y000 | 202204 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25068.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202205 | N7033 | Energy Efficiency Initiatives | Y000 | 202205 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202206 | N7033 | Energy Efficiency Initiatives | Y000 | 202206 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202207 | N7033 | Energy Efficiency Initiatives | Y000 | 202207 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25068.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202208 | N7033 | Energy Efficiency Initiatives | Y000 | 202208 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202209 | N7033 | Energy Efficiency Initiatives | Y000 | 202209 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202210 | N7033 | Energy Efficiency Initiatives | Y000 | 202210 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25068.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202211 | N7033 | Energy Efficiency Initiatives | Y000 | 202211 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25068.87 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7033202212 | N7033 | Energy Efficiency Initiatives | Y000 | 202212 | OX-1003103 | 518851 | 2021/22 CAPV | 2021/22 Capital Virements | -25038.81 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202204 | N7040 | Blackbird Leys Regeneration | Y000 | 202204 | OX-1003076 | 517951 | 2021/22 CAP0 | 2021/22 Capital Original | 41800 | 483 | BBL Regeneration | App6 Budget Load | AWICKE
N7040202210 | N7040 | Blackbird Leys Regeneration | Y000 | 202210 | OX-1003076 | 517951 | 2021/22 CAP0 | 2021/22 Capital Original | 41800 | 483 | BBL Regeneration | App6 Budget Load | AWICKE
N7040202211 | N7040 | Blackbird Leys Regeneration | Y000 | 202211 | OX-1003076 | 517951 | 2021/22 CAP0 | 2021/22 Capital Original | 62700 | 483 | BBL Regeneration | App6 Budget Load | AWICKE
N7040202212 | N7040 | Blackbird Leys Regeneration | Y000 | 202212 | OX-1003076 | 517951 | 2021/22 CAP0 | 2021/22 Capital Original | 62700 | 483 | BBL Regeneration | App6 Budget Load | AWICKE
N7040202204 | N7040 | Blackbird Leys Regeneration | Y000 | 202204 | OX-1003077 | 518080 | 2021/22 CAPV | 2021/22 Capital Virements | 12833.2 | 483 | BBL Regeneration | 2021/22 Slippage | AWICKE
N7040202210 | N7040 | Blackbird Leys Regeneration | Y000 | 202210 | OX-1003077 | 518080 | 2021/22 CAPV | 2021/22 Capital Virements | 12833.2 | 483 | BBL Regeneration | 2021/22 Slippage | AWICKE
N7040202211 | N7040 | Blackbird Leys Regeneration | Y000 | 202211 | OX-1003077 | 518080 | 2021/22 CAPV | 2021/22 Capital Virements | 19249.8 | 483 | BBL Regeneration | 2021/22 Slippage | AWICKE
N7040202212 | N7040 | Blackbird Leys Regeneration | Y000 | 202212 | OX-1003077 | 518080 | 2021/22 CAPV | 2021/22 Capital Virements | 19249.8 | 483 | BBL Regeneration | 2021/22 Slippage | AWICKE
N7040202201 | N7040 | Blackbird Leys Regeneration | Y000 | 202201 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202202 | N7040 | Blackbird Leys Regeneration | Y000 | 202202 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202203 | N7040 | Blackbird Leys Regeneration | Y000 | 202203 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202204 | N7040 | Blackbird Leys Regeneration | Y000 | 202204 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5351.53 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202205 | N7040 | Blackbird Leys Regeneration | Y000 | 202205 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202206 | N7040 | Blackbird Leys Regeneration | Y000 | 202206 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202207 | N7040 | Blackbird Leys Regeneration | Y000 | 202207 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5351.53 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202208 | N7040 | Blackbird Leys Regeneration | Y000 | 202208 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202209 | N7040 | Blackbird Leys Regeneration | Y000 | 202209 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202210 | N7040 | Blackbird Leys Regeneration | Y000 | 202210 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5351.53 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202211 | N7040 | Blackbird Leys Regeneration | Y000 | 202211 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5351.53 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202212 | N7040 | Blackbird Leys Regeneration | Y000 | 202212 | OX-1003099 | 518656 | 2021/22 CAPV | 2021/22 Capital Virements | 5345.11 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7040202201 | N7040 | Blackbird Leys Regeneration | Y000 | 202201 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202202 | N7040 | Blackbird Leys Regeneration | Y000 | 202202 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202203 | N7040 | Blackbird Leys Regeneration | Y000 | 202203 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202204 | N7040 | Blackbird Leys Regeneration | Y000 | 202204 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5351.53 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202205 | N7040 | Blackbird Leys Regeneration | Y000 | 202205 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202206 | N7040 | Blackbird Leys Regeneration | Y000 | 202206 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202207 | N7040 | Blackbird Leys Regeneration | Y000 | 202207 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5351.53 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202208 | N7040 | Blackbird Leys Regeneration | Y000 | 202208 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202209 | N7040 | Blackbird Leys Regeneration | Y000 | 202209 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202210 | N7040 | Blackbird Leys Regeneration | Y000 | 202210 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5351.53 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202211 | N7040 | Blackbird Leys Regeneration | Y000 | 202211 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5351.53 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7040202212 | N7040 | Blackbird Leys Regeneration | Y000 | 202212 | OX-1003103 | 518850 | 2021/22 CAPV | 2021/22 Capital Virements | -5345.11 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202202 | N7042 | Barton Regeneration | Y000 | 202202 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 18000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202203 | N7042 | Barton Regeneration | Y000 | 202203 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 30000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202204 | N7042 | Barton Regeneration | Y000 | 202204 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 42000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202205 | N7042 | Barton Regeneration | Y000 | 202205 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 30000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202206 | N7042 | Barton Regeneration | Y000 | 202206 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 48000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202207 | N7042 | Barton Regeneration | Y000 | 202207 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 48000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202208 | N7042 | Barton Regeneration | Y000 | 202208 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 78000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202209 | N7042 | Barton Regeneration | Y000 | 202209 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 90000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202210 | N7042 | Barton Regeneration | Y000 | 202210 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 72000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202211 | N7042 | Barton Regeneration | Y000 | 202211 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 72000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202212 | N7042 | Barton Regeneration | Y000 | 202212 | OX-1003076 | 517950 | 2021/22 CAP0 | 2021/22 Capital Original | 72000 | 499 | N7042 Barton Regeneration | App6 Budget Load | AWICKE
N7042202202 | N7042 | Barton Regeneration | Y000 | 202202 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 1504.2 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202203 | N7042 | Barton Regeneration | Y000 | 202203 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 2507 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202204 | N7042 | Barton Regeneration | Y000 | 202204 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 3509.8 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202205 | N7042 | Barton Regeneration | Y000 | 202205 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 2507 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202206 | N7042 | Barton Regeneration | Y000 | 202206 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 4011.2 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202207 | N7042 | Barton Regeneration | Y000 | 202207 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 4011.2 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202208 | N7042 | Barton Regeneration | Y000 | 202208 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 6518.2 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202209 | N7042 | Barton Regeneration | Y000 | 202209 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 7521 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202210 | N7042 | Barton Regeneration | Y000 | 202210 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 6016.8 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202211 | N7042 | Barton Regeneration | Y000 | 202211 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 6016.8 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202212 | N7042 | Barton Regeneration | Y000 | 202212 | OX-1003077 | 518079 | 2021/22 CAPV | 2021/22 Capital Virements | 6016.8 | 499 | N7042 Barton Regeneration | 2021/22 Slippage | AWICKE
N7042202201 | N7042 | Barton Regeneration | Y000 | 202201 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202202 | N7042 | Barton Regeneration | Y000 | 202202 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202203 | N7042 | Barton Regeneration | Y000 | 202203 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202204 | N7042 | Barton Regeneration | Y000 | 202204 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2642.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202205 | N7042 | Barton Regeneration | Y000 | 202205 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202206 | N7042 | Barton Regeneration | Y000 | 202206 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202207 | N7042 | Barton Regeneration | Y000 | 202207 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2642.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202208 | N7042 | Barton Regeneration | Y000 | 202208 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202209 | N7042 | Barton Regeneration | Y000 | 202209 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202210 | N7042 | Barton Regeneration | Y000 | 202210 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2642.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202211 | N7042 | Barton Regeneration | Y000 | 202211 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2642.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202212 | N7042 | Barton Regeneration | Y000 | 202212 | OX-1003099 | 518655 | 2021/22 CAPV | 2021/22 Capital Virements | 2639.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7042202201 | N7042 | Barton Regeneration | Y000 | 202201 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202202 | N7042 | Barton Regeneration | Y000 | 202202 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202203 | N7042 | Barton Regeneration | Y000 | 202203 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202204 | N7042 | Barton Regeneration | Y000 | 202204 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2642.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202205 | N7042 | Barton Regeneration | Y000 | 202205 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202206 | N7042 | Barton Regeneration | Y000 | 202206 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202207 | N7042 | Barton Regeneration | Y000 | 202207 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2642.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202208 | N7042 | Barton Regeneration | Y000 | 202208 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202209 | N7042 | Barton Regeneration | Y000 | 202209 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202210 | N7042 | Barton Regeneration | Y000 | 202210 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2642.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202211 | N7042 | Barton Regeneration | Y000 | 202211 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2642.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202212 | N7042 | Barton Regeneration | Y000 | 202212 | OX-1003103 | 518849 | 2021/22 CAPV | 2021/22 Capital Virements | -2639.06 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7042202202 | N7042 | Barton Regeneration | Y000 | 202202 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -655.88 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202203 | N7042 | Barton Regeneration | Y000 | 202203 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -1093.14 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202204 | N7042 | Barton Regeneration | Y000 | 202204 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -1530.39 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202205 | N7042 | Barton Regeneration | Y000 | 202205 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -1093.14 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202206 | N7042 | Barton Regeneration | Y000 | 202206 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -1749.02 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202207 | N7042 | Barton Regeneration | Y000 | 202207 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -1749.02 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202208 | N7042 | Barton Regeneration | Y000 | 202208 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -2842.16 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202209 | N7042 | Barton Regeneration | Y000 | 202209 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -3279.41 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202210 | N7042 | Barton Regeneration | Y000 | 202210 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -2623.53 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202211 | N7042 | Barton Regeneration | Y000 | 202211 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -2623.53 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7042202212 | N7042 | Barton Regeneration | Y000 | 202212 | OX-1003121 | 519039 | 2021/22 CAPV | 2021/22 Capital Virements | -2623.53 | 499 | N7042 Barton Regeneration | P2 HRA Slippage corrections | JMARRI
N7044202211 | N7044 | Lift Replacement Programme | Y000 | 202211 | OX-1003076 | 517949 | 2021/22 CAP0 | 2021/22 Capital Original | 306500 | 31 | Annual (February) | App6 Budget Load | AWICKE
N7044202211 | N7044 | Lift Replacement Programme | Y000 | 202211 | OX-1003077 | 518078 | 2021/22 CAPV | 2021/22 Capital Virements | 103686 | 31 | Annual (February) | 2021/22 Slippage | AWICKE
N7044202201 | N7044 | Lift Replacement Programme | Y000 | 202201 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202202 | N7044 | Lift Replacement Programme | Y000 | 202202 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202203 | N7044 | Lift Replacement Programme | Y000 | 202203 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202204 | N7044 | Lift Replacement Programme | Y000 | 202204 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202205 | N7044 | Lift Replacement Programme | Y000 | 202205 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202206 | N7044 | Lift Replacement Programme | Y000 | 202206 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202207 | N7044 | Lift Replacement Programme | Y000 | 202207 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202208 | N7044 | Lift Replacement Programme | Y000 | 202208 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202209 | N7044 | Lift Replacement Programme | Y000 | 202209 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202210 | N7044 | Lift Replacement Programme | Y000 | 202210 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202211 | N7044 | Lift Replacement Programme | Y000 | 202211 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.93 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202212 | N7044 | Lift Replacement Programme | Y000 | 202212 | OX-1003099 | 518654 | 2021/22 CAPV | 2021/22 Capital Virements | -535.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7044202201 | N7044 | Lift Replacement Programme | Y000 | 202201 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202202 | N7044 | Lift Replacement Programme | Y000 | 202202 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202203 | N7044 | Lift Replacement Programme | Y000 | 202203 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202204 | N7044 | Lift Replacement Programme | Y000 | 202204 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.93 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202205 | N7044 | Lift Replacement Programme | Y000 | 202205 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202206 | N7044 | Lift Replacement Programme | Y000 | 202206 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202207 | N7044 | Lift Replacement Programme | Y000 | 202207 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.93 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202208 | N7044 | Lift Replacement Programme | Y000 | 202208 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202209 | N7044 | Lift Replacement Programme | Y000 | 202209 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202210 | N7044 | Lift Replacement Programme | Y000 | 202210 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.93 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202211 | N7044 | Lift Replacement Programme | Y000 | 202211 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.93 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7044202212 | N7044 | Lift Replacement Programme | Y000 | 202212 | OX-1003103 | 518848 | 2021/22 CAPV | 2021/22 Capital Virements | 535.29 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202201 | N7047 | Social Rented Housing Acquisitions | Y000 | 202201 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 253430.99 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202202 | N7047 | Social Rented Housing Acquisitions | Y000 | 202202 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 966574.02 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202203 | N7047 | Social Rented Housing Acquisitions | Y000 | 202203 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 359518.38 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202205 | N7047 | Social Rented Housing Acquisitions | Y000 | 202205 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 353624.64 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202207 | N7047 | Social Rented Housing Acquisitions | Y000 | 202207 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 353624.64 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202209 | N7047 | Social Rented Housing Acquisitions | Y000 | 202209 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 353624.64 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202211 | N7047 | Social Rented Housing Acquisitions | Y000 | 202211 | OX-1003076 | 517948 | 2021/22 CAP0 | 2021/22 Capital Original | 306474.69 | 647 | N7047 - Social Renting Housing Acquisitions | App6 Budget Load | TCHENG
N7047202201 | N7047 | Social Rented Housing Acquisitions | Y000 | 202201 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -73072.74 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202202 | N7047 | Social Rented Housing Acquisitions | Y000 | 202202 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -278696.02 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202203 | N7047 | Social Rented Housing Acquisitions | Y000 | 202203 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -103661.33 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202205 | N7047 | Social Rented Housing Acquisitions | Y000 | 202205 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -101961.96 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202207 | N7047 | Social Rented Housing Acquisitions | Y000 | 202207 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -101961.96 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202209 | N7047 | Social Rented Housing Acquisitions | Y000 | 202209 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -101961.96 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202211 | N7047 | Social Rented Housing Acquisitions | Y000 | 202211 | OX-1003077 | 518077 | 2021/22 CAPV | 2021/22 Capital Virements | -88367.03 | 647 | N7047 - Social Renting Housing Acquisitions | 2021/22 Slippage | TCHENG
N7047202201 | N7047 | Social Rented Housing Acquisitions | Y000 | 202201 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202202 | N7047 | Social Rented Housing Acquisitions | Y000 | 202202 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202203 | N7047 | Social Rented Housing Acquisitions | Y000 | 202203 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202204 | N7047 | Social Rented Housing Acquisitions | Y000 | 202204 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83654.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202205 | N7047 | Social Rented Housing Acquisitions | Y000 | 202205 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202206 | N7047 | Social Rented Housing Acquisitions | Y000 | 202206 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202207 | N7047 | Social Rented Housing Acquisitions | Y000 | 202207 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83654.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202208 | N7047 | Social Rented Housing Acquisitions | Y000 | 202208 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202209 | N7047 | Social Rented Housing Acquisitions | Y000 | 202209 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202210 | N7047 | Social Rented Housing Acquisitions | Y000 | 202210 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83654.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202211 | N7047 | Social Rented Housing Acquisitions | Y000 | 202211 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83654.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202212 | N7047 | Social Rented Housing Acquisitions | Y000 | 202212 | OX-1003099 | 518653 | 2021/22 CAPV | 2021/22 Capital Virements | -83553.9 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7047202201 | N7047 | Social Rented Housing Acquisitions | Y000 | 202201 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202202 | N7047 | Social Rented Housing Acquisitions | Y000 | 202202 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202203 | N7047 | Social Rented Housing Acquisitions | Y000 | 202203 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202204 | N7047 | Social Rented Housing Acquisitions | Y000 | 202204 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83654.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202205 | N7047 | Social Rented Housing Acquisitions | Y000 | 202205 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202206 | N7047 | Social Rented Housing Acquisitions | Y000 | 202206 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202207 | N7047 | Social Rented Housing Acquisitions | Y000 | 202207 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83654.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202208 | N7047 | Social Rented Housing Acquisitions | Y000 | 202208 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202209 | N7047 | Social Rented Housing Acquisitions | Y000 | 202209 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202210 | N7047 | Social Rented Housing Acquisitions | Y000 | 202210 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83654.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202211 | N7047 | Social Rented Housing Acquisitions | Y000 | 202211 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83654.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202212 | N7047 | Social Rented Housing Acquisitions | Y000 | 202212 | OX-1003103 | 518847 | 2021/22 CAPV | 2021/22 Capital Virements | 83553.9 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7047202201 | N7047 | Social Rented Housing Acquisitions | Y000 | 202201 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -253.1 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202202 | N7047 | Social Rented Housing Acquisitions | Y000 | 202202 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -965.3 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202203 | N7047 | Social Rented Housing Acquisitions | Y000 | 202203 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -359.05 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202205 | N7047 | Social Rented Housing Acquisitions | Y000 | 202205 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -353.16 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202207 | N7047 | Social Rented Housing Acquisitions | Y000 | 202207 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -353.16 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202209 | N7047 | Social Rented Housing Acquisitions | Y000 | 202209 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -353.16 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7047202211 | N7047 | Social Rented Housing Acquisitions | Y000 | 202211 | OX-1003121 | 519038 | 2021/22 CAPV | 2021/22 Capital Virements | -306.07 | 647 | N7047 - Social Renting Housing Acquisitions | P2 HRA Slippage corrections | TCHENG
N7048202203 | N7048 | Fire doors | Y000 | 202203 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 68900 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202204 | N7048 | Fire doors | Y000 | 202204 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 37100 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202205 | N7048 | Fire doors | Y000 | 202205 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 42400 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202206 | N7048 | Fire doors | Y000 | 202206 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 47700 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202207 | N7048 | Fire doors | Y000 | 202207 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 53000 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202208 | N7048 | Fire doors | Y000 | 202208 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 58300 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202209 | N7048 | Fire doors | Y000 | 202209 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 63600 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202210 | N7048 | Fire doors | Y000 | 202210 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 53000 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202211 | N7048 | Fire doors | Y000 | 202211 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 53000 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202212 | N7048 | Fire doors | Y000 | 202212 | OX-1003076 | 517947 | 2021/22 CAP0 | 2021/22 Capital Original | 53000 | 699 | N7048 Fire doors | App6 Budget Load | AWICKE
N7048202203 | N7048 | Fire doors | Y000 | 202203 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 44067.27 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202204 | N7048 | Fire doors | Y000 | 202204 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 23728.53 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202205 | N7048 | Fire doors | Y000 | 202205 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 27118.32 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202206 | N7048 | Fire doors | Y000 | 202206 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 30508.11 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202207 | N7048 | Fire doors | Y000 | 202207 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 33897.9 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202208 | N7048 | Fire doors | Y000 | 202208 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 37287.69 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202209 | N7048 | Fire doors | Y000 | 202209 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 40677.48 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202210 | N7048 | Fire doors | Y000 | 202210 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 33897.9 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202211 | N7048 | Fire doors | Y000 | 202211 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 33897.9 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202212 | N7048 | Fire doors | Y000 | 202212 | OX-1003077 | 518076 | 2021/22 CAPV | 2021/22 Capital Virements | 33897.9 | 699 | N7048 Fire doors | 2021/22 Slippage | AWICKE
N7048202201 | N7048 | Fire doors | Y000 | 202201 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202202 | N7048 | Fire doors | Y000 | 202202 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202203 | N7048 | Fire doors | Y000 | 202203 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202204 | N7048 | Fire doors | Y000 | 202204 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.88 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202205 | N7048 | Fire doors | Y000 | 202205 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202206 | N7048 | Fire doors | Y000 | 202206 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202207 | N7048 | Fire doors | Y000 | 202207 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.88 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202208 | N7048 | Fire doors | Y000 | 202208 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202209 | N7048 | Fire doors | Y000 | 202209 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202210 | N7048 | Fire doors | Y000 | 202210 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.88 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202211 | N7048 | Fire doors | Y000 | 202211 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.88 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202212 | N7048 | Fire doors | Y000 | 202212 | OX-1003099 | 518652 | 2021/22 CAPV | 2021/22 Capital Virements | -480.31 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7048202201 | N7048 | Fire doors | Y000 | 202201 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202202 | N7048 | Fire doors | Y000 | 202202 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202203 | N7048 | Fire doors | Y000 | 202203 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202204 | N7048 | Fire doors | Y000 | 202204 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.88 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202205 | N7048 | Fire doors | Y000 | 202205 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202206 | N7048 | Fire doors | Y000 | 202206 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202207 | N7048 | Fire doors | Y000 | 202207 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.88 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202208 | N7048 | Fire doors | Y000 | 202208 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202209 | N7048 | Fire doors | Y000 | 202209 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202210 | N7048 | Fire doors | Y000 | 202210 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.88 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202211 | N7048 | Fire doors | Y000 | 202211 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.88 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7048202212 | N7048 | Fire doors | Y000 | 202212 | OX-1003103 | 518846 | 2021/22 CAPV | 2021/22 Capital Virements | 480.31 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202209 | N7050 | East Oxford development | Y000 | 202209 | OX-1003076 | 517946 | 2021/22 CAP0 | 2021/22 Capital Original | 883250 | 696 | N7050 East Oxford development | App6 Budget Load | AWICKE
N7050202210 | N7050 | East Oxford development | Y000 | 202210 | OX-1003076 | 517946 | 2021/22 CAP0 | 2021/22 Capital Original | 883250 | 696 | N7050 East Oxford development | App6 Budget Load | AWICKE
N7050202211 | N7050 | East Oxford development | Y000 | 202211 | OX-1003076 | 517946 | 2021/22 CAP0 | 2021/22 Capital Original | 883250 | 696 | N7050 East Oxford development | App6 Budget Load | AWICKE
N7050202212 | N7050 | East Oxford development | Y000 | 202212 | OX-1003076 | 517946 | 2021/22 CAP0 | 2021/22 Capital Original | 883250 | 696 | N7050 East Oxford development | App6 Budget Load | AWICKE
N7050202209 | N7050 | East Oxford development | Y000 | 202209 | OX-1003077 | 518075 | 2021/22 CAPV | 2021/22 Capital Virements | -73161.75 | 696 | N7050 East Oxford development | 2021/22 Slippage | AWICKE
N7050202210 | N7050 | East Oxford development | Y000 | 202210 | OX-1003077 | 518075 | 2021/22 CAPV | 2021/22 Capital Virements | -73161.75 | 696 | N7050 East Oxford development | 2021/22 Slippage | AWICKE
N7050202211 | N7050 | East Oxford development | Y000 | 202211 | OX-1003077 | 518075 | 2021/22 CAPV | 2021/22 Capital Virements | -73161.75 | 696 | N7050 East Oxford development | 2021/22 Slippage | AWICKE
N7050202212 | N7050 | East Oxford development | Y000 | 202212 | OX-1003077 | 518075 | 2021/22 CAPV | 2021/22 Capital Virements | -73161.75 | 696 | N7050 East Oxford development | 2021/22 Slippage | AWICKE
N7050202201 | N7050 | East Oxford development | Y000 | 202201 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202202 | N7050 | East Oxford development | Y000 | 202202 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202203 | N7050 | East Oxford development | Y000 | 202203 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202204 | N7050 | East Oxford development | Y000 | 202204 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24406.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202205 | N7050 | East Oxford development | Y000 | 202205 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202206 | N7050 | East Oxford development | Y000 | 202206 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202207 | N7050 | East Oxford development | Y000 | 202207 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24406.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202208 | N7050 | East Oxford development | Y000 | 202208 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202209 | N7050 | East Oxford development | Y000 | 202209 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202210 | N7050 | East Oxford development | Y000 | 202210 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24406.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202211 | N7050 | East Oxford development | Y000 | 202211 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24406.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202212 | N7050 | East Oxford development | Y000 | 202212 | OX-1003099 | 518651 | 2021/22 CAPV | 2021/22 Capital Virements | -24377.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7050202201 | N7050 | East Oxford development | Y000 | 202201 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202202 | N7050 | East Oxford development | Y000 | 202202 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202203 | N7050 | East Oxford development | Y000 | 202203 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202204 | N7050 | East Oxford development | Y000 | 202204 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24406.76 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202205 | N7050 | East Oxford development | Y000 | 202205 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202206 | N7050 | East Oxford development | Y000 | 202206 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202207 | N7050 | East Oxford development | Y000 | 202207 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24406.76 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202208 | N7050 | East Oxford development | Y000 | 202208 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202209 | N7050 | East Oxford development | Y000 | 202209 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202210 | N7050 | East Oxford development | Y000 | 202210 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24406.76 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202211 | N7050 | East Oxford development | Y000 | 202211 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24406.76 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7050202212 | N7050 | East Oxford development | Y000 | 202212 | OX-1003103 | 518845 | 2021/22 CAPV | 2021/22 Capital Virements | 24377.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202204 | N7051 | Acquisition of Additional Units | Y000 | 202204 | OX-1003076 | 517945 | 2021/22 CAP0 | 2021/22 Capital Original | 93108.18 | 697 | N7051 Acquisition of Additional Units | App6 Budget Load | AWICKE
N7051202208 | N7051 | Acquisition of Additional Units | Y000 | 202208 | OX-1003076 | 517945 | 2021/22 CAP0 | 2021/22 Capital Original | 1241442.4 | 697 | N7051 Acquisition of Additional Units | App6 Budget Load | AWICKE
N7051202210 | N7051 | Acquisition of Additional Units | Y000 | 202210 | OX-1003076 | 517945 | 2021/22 CAP0 | 2021/22 Capital Original | 527613.02 | 697 | N7051 Acquisition of Additional Units | App6 Budget Load | AWICKE
N7051202211 | N7051 | Acquisition of Additional Units | Y000 | 202211 | OX-1003076 | 517945 | 2021/22 CAP0 | 2021/22 Capital Original | 620721.2 | 697 | N7051 Acquisition of Additional Units | App6 Budget Load | AWICKE
N7051202212 | N7051 | Acquisition of Additional Units | Y000 | 202212 | OX-1003076 | 517945 | 2021/22 CAP0 | 2021/22 Capital Original | 620721.2 | 697 | N7051 Acquisition of Additional Units | App6 Budget Load | AWICKE
N7051202204 | N7051 | Acquisition of Additional Units | Y000 | 202204 | OX-1003077 | 518074 | 2021/22 CAPV | 2021/22 Capital Virements | 2774.25 | 697 | N7051 Acquisition of Additional Units | 2021/22 Slippage | AWICKE
N7051202208 | N7051 | Acquisition of Additional Units | Y000 | 202208 | OX-1003077 | 518074 | 2021/22 CAPV | 2021/22 Capital Virements | 36990 | 697 | N7051 Acquisition of Additional Units | 2021/22 Slippage | AWICKE
N7051202210 | N7051 | Acquisition of Additional Units | Y000 | 202210 | OX-1003077 | 518074 | 2021/22 CAPV | 2021/22 Capital Virements | 15720.75 | 697 | N7051 Acquisition of Additional Units | 2021/22 Slippage | AWICKE
N7051202211 | N7051 | Acquisition of Additional Units | Y000 | 202211 | OX-1003077 | 518074 | 2021/22 CAPV | 2021/22 Capital Virements | 18495 | 697 | N7051 Acquisition of Additional Units | 2021/22 Slippage | AWICKE
N7051202212 | N7051 | Acquisition of Additional Units | Y000 | 202212 | OX-1003077 | 518074 | 2021/22 CAPV | 2021/22 Capital Virements | 18495 | 697 | N7051 Acquisition of Additional Units | 2021/22 Slippage | AWICKE
N7051202201 | N7051 | Acquisition of Additional Units | Y000 | 202201 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202202 | N7051 | Acquisition of Additional Units | Y000 | 202202 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202203 | N7051 | Acquisition of Additional Units | Y000 | 202203 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202204 | N7051 | Acquisition of Additional Units | Y000 | 202204 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7712.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202205 | N7051 | Acquisition of Additional Units | Y000 | 202205 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202206 | N7051 | Acquisition of Additional Units | Y000 | 202206 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202207 | N7051 | Acquisition of Additional Units | Y000 | 202207 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7712.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202208 | N7051 | Acquisition of Additional Units | Y000 | 202208 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202209 | N7051 | Acquisition of Additional Units | Y000 | 202209 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202210 | N7051 | Acquisition of Additional Units | Y000 | 202210 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7712.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202211 | N7051 | Acquisition of Additional Units | Y000 | 202211 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7712.42 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202212 | N7051 | Acquisition of Additional Units | Y000 | 202212 | OX-1003099 | 518650 | 2021/22 CAPV | 2021/22 Capital Virements | 7703.16 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7051202201 | N7051 | Acquisition of Additional Units | Y000 | 202201 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202202 | N7051 | Acquisition of Additional Units | Y000 | 202202 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202203 | N7051 | Acquisition of Additional Units | Y000 | 202203 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202204 | N7051 | Acquisition of Additional Units | Y000 | 202204 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7712.42 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202205 | N7051 | Acquisition of Additional Units | Y000 | 202205 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202206 | N7051 | Acquisition of Additional Units | Y000 | 202206 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202207 | N7051 | Acquisition of Additional Units | Y000 | 202207 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7712.42 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202208 | N7051 | Acquisition of Additional Units | Y000 | 202208 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202209 | N7051 | Acquisition of Additional Units | Y000 | 202209 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202210 | N7051 | Acquisition of Additional Units | Y000 | 202210 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7712.42 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202211 | N7051 | Acquisition of Additional Units | Y000 | 202211 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7712.42 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7051202212 | N7051 | Acquisition of Additional Units | Y000 | 202212 | OX-1003103 | 518844 | 2021/22 CAPV | 2021/22 Capital Virements | -7703.16 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202207 | N7052 | HRA Stock Condition Survey | Y000 | 202207 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28205.64 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202208 | N7052 | HRA Stock Condition Survey | Y000 | 202208 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28205.64 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202209 | N7052 | HRA Stock Condition Survey | Y000 | 202209 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28205.64 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202210 | N7052 | HRA Stock Condition Survey | Y000 | 202210 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28205.64 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202211 | N7052 | HRA Stock Condition Survey | Y000 | 202211 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28205.64 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202212 | N7052 | HRA Stock Condition Survey | Y000 | 202212 | OX-1003076 | 517944 | 2021/22 CAP0 | 2021/22 Capital Original | 28171.8 | 698 | N7052 HRA Stock Condition Survey | App6 Budget Load | AWICKE
N7052202207 | N7052 | HRA Stock Condition Survey | Y000 | 202207 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4412.72 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202208 | N7052 | HRA Stock Condition Survey | Y000 | 202208 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4412.72 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202209 | N7052 | HRA Stock Condition Survey | Y000 | 202209 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4412.72 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202210 | N7052 | HRA Stock Condition Survey | Y000 | 202210 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4412.72 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202211 | N7052 | HRA Stock Condition Survey | Y000 | 202211 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4412.72 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202212 | N7052 | HRA Stock Condition Survey | Y000 | 202212 | OX-1003077 | 518073 | 2021/22 CAPV | 2021/22 Capital Virements | -4407.42 | 698 | N7052 HRA Stock Condition Survey | 2021/22 Slippage | AWICKE
N7052202201 | N7052 | HRA Stock Condition Survey | Y000 | 202201 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202202 | N7052 | HRA Stock Condition Survey | Y000 | 202202 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202203 | N7052 | HRA Stock Condition Survey | Y000 | 202203 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202204 | N7052 | HRA Stock Condition Survey | Y000 | 202204 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2207.68 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202205 | N7052 | HRA Stock Condition Survey | Y000 | 202205 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202206 | N7052 | HRA Stock Condition Survey | Y000 | 202206 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202207 | N7052 | HRA Stock Condition Survey | Y000 | 202207 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2207.68 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202208 | N7052 | HRA Stock Condition Survey | Y000 | 202208 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202209 | N7052 | HRA Stock Condition Survey | Y000 | 202209 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.03 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202210 | N7052 | HRA Stock Condition Survey | Y000 | 202210 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2207.68 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202211 | N7052 | HRA Stock Condition Survey | Y000 | 202211 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2207.68 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202212 | N7052 | HRA Stock Condition Survey | Y000 | 202212 | OX-1003099 | 518649 | 2021/22 CAPV | 2021/22 Capital Virements | -2205.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7052202201 | N7052 | HRA Stock Condition Survey | Y000 | 202201 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202202 | N7052 | HRA Stock Condition Survey | Y000 | 202202 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202203 | N7052 | HRA Stock Condition Survey | Y000 | 202203 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202204 | N7052 | HRA Stock Condition Survey | Y000 | 202204 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2207.68 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202205 | N7052 | HRA Stock Condition Survey | Y000 | 202205 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202206 | N7052 | HRA Stock Condition Survey | Y000 | 202206 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202207 | N7052 | HRA Stock Condition Survey | Y000 | 202207 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2207.68 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202208 | N7052 | HRA Stock Condition Survey | Y000 | 202208 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202209 | N7052 | HRA Stock Condition Survey | Y000 | 202209 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.03 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202210 | N7052 | HRA Stock Condition Survey | Y000 | 202210 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2207.68 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202211 | N7052 | HRA Stock Condition Survey | Y000 | 202211 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2207.68 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7052202212 | N7052 | HRA Stock Condition Survey | Y000 | 202212 | OX-1003103 | 518843 | 2021/22 CAPV | 2021/22 Capital Virements | 2205.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202212 | N7054 | Properties Purchased From OCHL | Y000 | 202212 | OX-1003076 | 517943 | 2021/22 CAP0 | 2021/22 Capital Original | 31418629 | 32 | Annual (March) | App6 Budget Load | AWICKE
N7054202201 | N7054 | Properties Purchased From OCHL | Y000 | 202201 | OX-1003153 | 519503 | 2021/22 CAP0 | 2021/22 Capital Original | 770000 | 10 | Annual (April) | Reprofile HRA Capital | TCHENG
N7054202212 | N7054 | Properties Purchased From OCHL | Y000 | 202212 | OX-1003153 | 519504 | 2021/22 CAP0 | 2021/22 Capital Original | -770000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7054202212 | N7054 | Properties Purchased From OCHL | Y000 | 202212 | OX-1003077 | 518072 | 2021/22 CAPV | 2021/22 Capital Virements | 3647432 | 32 | Annual (March) | 2021/22 Slippage | AWICKE
N7054202201 | N7054 | Properties Purchased From OCHL | Y000 | 202201 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202202 | N7054 | Properties Purchased From OCHL | Y000 | 202202 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202203 | N7054 | Properties Purchased From OCHL | Y000 | 202203 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202204 | N7054 | Properties Purchased From OCHL | Y000 | 202204 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108241.02 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202205 | N7054 | Properties Purchased From OCHL | Y000 | 202205 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202206 | N7054 | Properties Purchased From OCHL | Y000 | 202206 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202207 | N7054 | Properties Purchased From OCHL | Y000 | 202207 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108241.02 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202208 | N7054 | Properties Purchased From OCHL | Y000 | 202208 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202209 | N7054 | Properties Purchased From OCHL | Y000 | 202209 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202210 | N7054 | Properties Purchased From OCHL | Y000 | 202210 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108241.02 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202211 | N7054 | Properties Purchased From OCHL | Y000 | 202211 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108241.02 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202212 | N7054 | Properties Purchased From OCHL | Y000 | 202212 | OX-1003099 | 518648 | 2021/22 CAPV | 2021/22 Capital Virements | 108111.24 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7054202201 | N7054 | Properties Purchased From OCHL | Y000 | 202201 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202202 | N7054 | Properties Purchased From OCHL | Y000 | 202202 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202203 | N7054 | Properties Purchased From OCHL | Y000 | 202203 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202204 | N7054 | Properties Purchased From OCHL | Y000 | 202204 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108241.02 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202205 | N7054 | Properties Purchased From OCHL | Y000 | 202205 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202206 | N7054 | Properties Purchased From OCHL | Y000 | 202206 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202207 | N7054 | Properties Purchased From OCHL | Y000 | 202207 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108241.02 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202208 | N7054 | Properties Purchased From OCHL | Y000 | 202208 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202209 | N7054 | Properties Purchased From OCHL | Y000 | 202209 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202210 | N7054 | Properties Purchased From OCHL | Y000 | 202210 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108241.02 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202211 | N7054 | Properties Purchased From OCHL | Y000 | 202211 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108241.02 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7054202212 | N7054 | Properties Purchased From OCHL | Y000 | 202212 | OX-1003103 | 518842 | 2021/22 CAPV | 2021/22 Capital Virements | -108111.24 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202201 | N7055 | Use Of Recycled Capital Grants | Y000 | 202201 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202202 | N7055 | Use Of Recycled Capital Grants | Y000 | 202202 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202203 | N7055 | Use Of Recycled Capital Grants | Y000 | 202203 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30691.2 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202204 | N7055 | Use Of Recycled Capital Grants | Y000 | 202204 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202205 | N7055 | Use Of Recycled Capital Grants | Y000 | 202205 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202206 | N7055 | Use Of Recycled Capital Grants | Y000 | 202206 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30691.2 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202207 | N7055 | Use Of Recycled Capital Grants | Y000 | 202207 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202208 | N7055 | Use Of Recycled Capital Grants | Y000 | 202208 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202209 | N7055 | Use Of Recycled Capital Grants | Y000 | 202209 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30691.2 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202210 | N7055 | Use Of Recycled Capital Grants | Y000 | 202210 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202211 | N7055 | Use Of Recycled Capital Grants | Y000 | 202211 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30654.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202212 | N7055 | Use Of Recycled Capital Grants | Y000 | 202212 | OX-1003153 | 519501 | 2021/22 CAP0 | 2021/22 Capital Original | 368000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7055202212 | N7055 | Use Of Recycled Capital Grants | Y000 | 202212 | OX-1003153 | 519502 | 2021/22 CAP0 | 2021/22 Capital Original | -30691.2 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7055202201 | N7055 | Use Of Recycled Capital Grants | Y000 | 202201 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202202 | N7055 | Use Of Recycled Capital Grants | Y000 | 202202 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202203 | N7055 | Use Of Recycled Capital Grants | Y000 | 202203 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202204 | N7055 | Use Of Recycled Capital Grants | Y000 | 202204 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202205 | N7055 | Use Of Recycled Capital Grants | Y000 | 202205 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202206 | N7055 | Use Of Recycled Capital Grants | Y000 | 202206 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202207 | N7055 | Use Of Recycled Capital Grants | Y000 | 202207 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202208 | N7055 | Use Of Recycled Capital Grants | Y000 | 202208 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202209 | N7055 | Use Of Recycled Capital Grants | Y000 | 202209 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202210 | N7055 | Use Of Recycled Capital Grants | Y000 | 202210 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202211 | N7055 | Use Of Recycled Capital Grants | Y000 | 202211 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202212 | N7055 | Use Of Recycled Capital Grants | Y000 | 202212 | OX-1003077 | 518071 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
N7055202201 | N7055 | Use Of Recycled Capital Grants | Y000 | 202201 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202202 | N7055 | Use Of Recycled Capital Grants | Y000 | 202202 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202203 | N7055 | Use Of Recycled Capital Grants | Y000 | 202203 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202204 | N7055 | Use Of Recycled Capital Grants | Y000 | 202204 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202205 | N7055 | Use Of Recycled Capital Grants | Y000 | 202205 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202206 | N7055 | Use Of Recycled Capital Grants | Y000 | 202206 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202207 | N7055 | Use Of Recycled Capital Grants | Y000 | 202207 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202208 | N7055 | Use Of Recycled Capital Grants | Y000 | 202208 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202209 | N7055 | Use Of Recycled Capital Grants | Y000 | 202209 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202210 | N7055 | Use Of Recycled Capital Grants | Y000 | 202210 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202211 | N7055 | Use Of Recycled Capital Grants | Y000 | 202211 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30691.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202212 | N7055 | Use Of Recycled Capital Grants | Y000 | 202212 | OX-1003099 | 518647 | 2021/22 CAPV | 2021/22 Capital Virements | 30654.4 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7055202201 | N7055 | Use Of Recycled Capital Grants | Y000 | 202201 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202202 | N7055 | Use Of Recycled Capital Grants | Y000 | 202202 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202203 | N7055 | Use Of Recycled Capital Grants | Y000 | 202203 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202204 | N7055 | Use Of Recycled Capital Grants | Y000 | 202204 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30691.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202205 | N7055 | Use Of Recycled Capital Grants | Y000 | 202205 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202206 | N7055 | Use Of Recycled Capital Grants | Y000 | 202206 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202207 | N7055 | Use Of Recycled Capital Grants | Y000 | 202207 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30691.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202208 | N7055 | Use Of Recycled Capital Grants | Y000 | 202208 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202209 | N7055 | Use Of Recycled Capital Grants | Y000 | 202209 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202210 | N7055 | Use Of Recycled Capital Grants | Y000 | 202210 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30691.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202211 | N7055 | Use Of Recycled Capital Grants | Y000 | 202211 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30691.2 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7055202212 | N7055 | Use Of Recycled Capital Grants | Y000 | 202212 | OX-1003103 | 518841 | 2021/22 CAPV | 2021/22 Capital Virements | -30654.4 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 41386.3 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 20754.55 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 20754.55 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 46667.04 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 41386.3 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 138036.19 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 138036.19 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 69018.1 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 103527.14 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 138036.19 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003076 | 517942 | 2021/22 CAP0 | 2021/22 Capital Original | 470477.45 | 373 | N7057 | App6 Budget Load | AWICKE
N7057202201 | N7057 | Kitchens | Y000 | 202201 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -41386.3 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102421.87 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -20754.55 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -20754.55 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -46667.04 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102421.87 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -41386.3 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -138036.19 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -138036.19 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102421.87 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -69018.1 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -103527.14 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102299.06 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -138036.19 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003115 | 519005 | 2021/22 CAP0 | 2021/22 Capital Original | 102421.87 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003115 | 519006 | 2021/22 CAP0 | 2021/22 Capital Original | -470477.45 | 373 | N7057 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 11562.33 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 5798.32 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 5798.32 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 13037.65 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 11562.33 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 38563.99 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 38563.99 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 19281.99 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 28922.99 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 38563.99 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003077 | 518070 | 2021/22 CAPV | 2021/22 Capital Virements | 131440.08 | 373 | N7057 | 2021/22 Slippage | AWICKE
N7057202201 | N7057 | Kitchens | Y000 | 202201 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38448.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38448.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38448.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38448.32 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003099 | 518646 | 2021/22 CAPV | 2021/22 Capital Virements | 38402.22 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7057202201 | N7057 | Kitchens | Y000 | 202201 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38448.32 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38448.32 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38448.32 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38448.32 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003103 | 518840 | 2021/22 CAPV | 2021/22 Capital Virements | -38402.22 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7057202201 | N7057 | Kitchens | Y000 | 202201 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202202 | N7057 | Kitchens | Y000 | 202202 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -11562.33 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202203 | N7057 | Kitchens | Y000 | 202203 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -5798.32 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28614.21 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202204 | N7057 | Kitchens | Y000 | 202204 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -5798.32 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202205 | N7057 | Kitchens | Y000 | 202205 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -13037.65 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202206 | N7057 | Kitchens | Y000 | 202206 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -11562.33 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28614.21 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202207 | N7057 | Kitchens | Y000 | 202207 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -38563.99 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202208 | N7057 | Kitchens | Y000 | 202208 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -38563.99 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202209 | N7057 | Kitchens | Y000 | 202209 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -19281.99 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28614.21 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202210 | N7057 | Kitchens | Y000 | 202210 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -28922.99 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28614.21 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202211 | N7057 | Kitchens | Y000 | 202211 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -38563.99 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003116 | 519019 | 2021/22 CAPV | 2021/22 Capital Virements | 28579.9 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7057202212 | N7057 | Kitchens | Y000 | 202212 | OX-1003116 | 519020 | 2021/22 CAPV | 2021/22 Capital Virements | -131440.08 | 373 | N7057 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 26401.44 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 21139.3 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 26401.44 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 53256.51 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 42187.87 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 105515.04 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 105515.04 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 26401.44 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 79113.6 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 105515.04 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003076 | 517941 | 2021/22 CAP0 | 2021/22 Capital Original | 315819.29 | 372 | N7058 | App6 Budget Load | AWICKE
N7058202201 | N7058 | Bathrooms | Y000 | 202201 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -26401.44 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75665.98 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -21139.3 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -26401.44 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -53256.51 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75665.98 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -42187.87 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -105515.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -105515.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75665.98 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -26401.44 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -79113.6 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75575.26 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -105515.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003115 | 519003 | 2021/22 CAP0 | 2021/22 Capital Original | 75665.98 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003115 | 519004 | 2021/22 CAP0 | 2021/22 Capital Original | -315819.29 | 372 | N7058 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 6239.04 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 4995.52 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 6239.04 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 12585.28 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 9969.6 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 24934.72 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 24934.72 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 6239.04 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 18695.68 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 24934.72 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003077 | 518069 | 2021/22 CAPV | 2021/22 Capital Virements | 74632.64 | 372 | N7058 | 2021/22 Slippage | AWICKE
N7058202201 | N7058 | Bathrooms | Y000 | 202201 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31261.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31261.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.34 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31261.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31261.82 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003099 | 518645 | 2021/22 CAPV | 2021/22 Capital Virements | 31224.33 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7058202201 | N7058 | Bathrooms | Y000 | 202201 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31261.82 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31261.82 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.34 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31261.82 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31261.82 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003103 | 518839 | 2021/22 CAPV | 2021/22 Capital Virements | -31224.33 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7058202201 | N7058 | Bathrooms | Y000 | 202201 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202202 | N7058 | Bathrooms | Y000 | 202202 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -6239.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202203 | N7058 | Bathrooms | Y000 | 202203 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -4995.52 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17880.96 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202204 | N7058 | Bathrooms | Y000 | 202204 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -6239.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202205 | N7058 | Bathrooms | Y000 | 202205 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -12585.28 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202206 | N7058 | Bathrooms | Y000 | 202206 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -9969.6 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17880.96 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202207 | N7058 | Bathrooms | Y000 | 202207 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -24934.72 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202208 | N7058 | Bathrooms | Y000 | 202208 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -24934.72 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202209 | N7058 | Bathrooms | Y000 | 202209 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -6239.04 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17880.96 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202210 | N7058 | Bathrooms | Y000 | 202210 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -18695.68 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17880.96 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202211 | N7058 | Bathrooms | Y000 | 202211 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -24934.72 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003116 | 519017 | 2021/22 CAPV | 2021/22 Capital Virements | 17859.52 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7058202212 | N7058 | Bathrooms | Y000 | 202212 | OX-1003116 | 519018 | 2021/22 CAPV | 2021/22 Capital Virements | -74632.64 | 372 | N7058 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7059202201 | N7059 | Boilers Only | Y000 | 202201 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 54611.36 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202202 | N7059 | Boilers Only | Y000 | 202202 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 31163.27 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202203 | N7059 | Boilers Only | Y000 | 202203 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 45383.4 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202204 | N7059 | Boilers Only | Y000 | 202204 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 154757.39 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202205 | N7059 | Boilers Only | Y000 | 202205 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 167162.19 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202206 | N7059 | Boilers Only | Y000 | 202206 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 209671.31 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202207 | N7059 | Boilers Only | Y000 | 202207 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 335383.33 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202208 | N7059 | Boilers Only | Y000 | 202208 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 227068.28 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202209 | N7059 | Boilers Only | Y000 | 202209 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 174726.09 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202210 | N7059 | Boilers Only | Y000 | 202210 | OX-1003076 | 517940 | 2021/22 CAP0 | 2021/22 Capital Original | 112853.39 | 371 | N7059 | App6 Budget Load | AWICKE
N7059202201 | N7059 | Boilers Only | Y000 | 202201 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202201 | N7059 | Boilers Only | Y000 | 202201 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -54611.36 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202202 | N7059 | Boilers Only | Y000 | 202202 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202202 | N7059 | Boilers Only | Y000 | 202202 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -31163.27 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202203 | N7059 | Boilers Only | Y000 | 202203 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126165.85 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202203 | N7059 | Boilers Only | Y000 | 202203 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -45383.4 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202204 | N7059 | Boilers Only | Y000 | 202204 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202204 | N7059 | Boilers Only | Y000 | 202204 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -154757.39 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202205 | N7059 | Boilers Only | Y000 | 202205 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202205 | N7059 | Boilers Only | Y000 | 202205 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -167162.19 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202206 | N7059 | Boilers Only | Y000 | 202206 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126165.85 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202206 | N7059 | Boilers Only | Y000 | 202206 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -209671.31 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202207 | N7059 | Boilers Only | Y000 | 202207 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202207 | N7059 | Boilers Only | Y000 | 202207 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -335383.33 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202208 | N7059 | Boilers Only | Y000 | 202208 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202208 | N7059 | Boilers Only | Y000 | 202208 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -227068.28 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202209 | N7059 | Boilers Only | Y000 | 202209 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126165.85 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202209 | N7059 | Boilers Only | Y000 | 202209 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -174726.09 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202210 | N7059 | Boilers Only | Y000 | 202210 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202210 | N7059 | Boilers Only | Y000 | 202210 | OX-1003115 | 519002 | 2021/22 CAP0 | 2021/22 Capital Original | -112853.39 | 371 | N7059 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202211 | N7059 | Boilers Only | Y000 | 202211 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126014.57 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202212 | N7059 | Boilers Only | Y000 | 202212 | OX-1003115 | 519001 | 2021/22 CAP0 | 2021/22 Capital Original | 126165.85 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7059202201 | N7059 | Boilers Only | Y000 | 202201 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202202 | N7059 | Boilers Only | Y000 | 202202 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202203 | N7059 | Boilers Only | Y000 | 202203 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202204 | N7059 | Boilers Only | Y000 | 202204 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14291.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202205 | N7059 | Boilers Only | Y000 | 202205 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202206 | N7059 | Boilers Only | Y000 | 202206 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202207 | N7059 | Boilers Only | Y000 | 202207 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14291.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202208 | N7059 | Boilers Only | Y000 | 202208 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202209 | N7059 | Boilers Only | Y000 | 202209 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202210 | N7059 | Boilers Only | Y000 | 202210 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14291.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202211 | N7059 | Boilers Only | Y000 | 202211 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14291.17 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202212 | N7059 | Boilers Only | Y000 | 202212 | OX-1003099 | 518644 | 2021/22 CAPV | 2021/22 Capital Virements | 14274.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7059202201 | N7059 | Boilers Only | Y000 | 202201 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202202 | N7059 | Boilers Only | Y000 | 202202 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202203 | N7059 | Boilers Only | Y000 | 202203 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202204 | N7059 | Boilers Only | Y000 | 202204 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14291.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202205 | N7059 | Boilers Only | Y000 | 202205 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202206 | N7059 | Boilers Only | Y000 | 202206 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202207 | N7059 | Boilers Only | Y000 | 202207 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14291.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202208 | N7059 | Boilers Only | Y000 | 202208 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202209 | N7059 | Boilers Only | Y000 | 202209 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202210 | N7059 | Boilers Only | Y000 | 202210 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14291.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202211 | N7059 | Boilers Only | Y000 | 202211 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14291.17 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7059202212 | N7059 | Boilers Only | Y000 | 202212 | OX-1003103 | 518838 | 2021/22 CAPV | 2021/22 Capital Virements | -14274.04 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 14121.99 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 5714.1 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 2884.26 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 5795.73 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 4217.55 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 17359.98 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 2884.26 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 2884.26 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 2884.26 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 2884.26 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003076 | 517939 | 2021/22 CAP0 | 2021/22 Capital Original | 210469.35 | 374 | N7060 | App6 Budget Load | AWICKE
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -14121.99 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -5714.1 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22693.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -2884.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -5795.73 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202205 | N7060 | Heating Systems | Y000 | 202205 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22693.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -4217.55 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -17359.98 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -2884.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22693.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -2884.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -2884.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22665.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -2884.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003115 | 518999 | 2021/22 CAP0 | 2021/22 Capital Original | 22693.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003115 | 519000 | 2021/22 CAP0 | 2021/22 Capital Original | -210469.35 | 374 | N7060 | Delegated ODS HRA budgets reprofile 2 | SHILTO1
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -11007.99 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -4454.1 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -2248.26 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -4517.73 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -3287.55 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -13531.98 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -2248.26 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -2248.26 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -2248.26 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -2248.26 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003077 | 518068 | 2021/22 CAPV | 2021/22 Capital Virements | -164059.35 | 374 | N7060 | 2021/22 Slippage | AWICKE
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19429.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202205 | N7060 | Heating Systems | Y000 | 202205 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19429.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.48 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19429.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19429.78 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003099 | 518643 | 2021/22 CAPV | 2021/22 Capital Virements | 19406.49 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19429.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202205 | N7060 | Heating Systems | Y000 | 202205 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19429.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.48 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19429.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19429.78 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003103 | 518837 | 2021/22 CAPV | 2021/22 Capital Virements | -19406.49 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202201 | N7060 | Heating Systems | Y000 | 202201 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 11007.99 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202202 | N7060 | Heating Systems | Y000 | 202202 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 4454.1 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202203 | N7060 | Heating Systems | Y000 | 202203 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 2248.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17689.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202204 | N7060 | Heating Systems | Y000 | 202204 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 4517.73 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202205 | N7060 | Heating Systems | Y000 | 202205 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202206 | N7060 | Heating Systems | Y000 | 202206 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 3287.55 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17689.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202207 | N7060 | Heating Systems | Y000 | 202207 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 13531.98 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202208 | N7060 | Heating Systems | Y000 | 202208 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 2248.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202209 | N7060 | Heating Systems | Y000 | 202209 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 2248.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17689.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202210 | N7060 | Heating Systems | Y000 | 202210 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 2248.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17689.14 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202211 | N7060 | Heating Systems | Y000 | 202211 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 2248.26 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003116 | 519015 | 2021/22 CAPV | 2021/22 Capital Virements | -17667.93 | 11 | Twelfths Monthly | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7060202212 | N7060 | Heating Systems | Y000 | 202212 | OX-1003116 | 519016 | 2021/22 CAPV | 2021/22 Capital Virements | 164059.35 | 374 | N7060 | Delegated ODS HRA budgets reprofile 3 | SHILTO1
N7061202201 | N7061 | Northfield Hostel | Y000 | 202201 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202202 | N7061 | Northfield Hostel | Y000 | 202202 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202203 | N7061 | Northfield Hostel | Y000 | 202203 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658860 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202204 | N7061 | Northfield Hostel | Y000 | 202204 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202205 | N7061 | Northfield Hostel | Y000 | 202205 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202206 | N7061 | Northfield Hostel | Y000 | 202206 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658860 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202207 | N7061 | Northfield Hostel | Y000 | 202207 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202208 | N7061 | Northfield Hostel | Y000 | 202208 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202209 | N7061 | Northfield Hostel | Y000 | 202209 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658860 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202210 | N7061 | Northfield Hostel | Y000 | 202210 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202211 | N7061 | Northfield Hostel | Y000 | 202211 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658070 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202212 | N7061 | Northfield Hostel | Y000 | 202212 | OX-1003076 | 517938 | 2021/22 CAP0 | 2021/22 Capital Original | 658860 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7061202201 | N7061 | Northfield Hostel | Y000 | 202201 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202202 | N7061 | Northfield Hostel | Y000 | 202202 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202203 | N7061 | Northfield Hostel | Y000 | 202203 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658860 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202204 | N7061 | Northfield Hostel | Y000 | 202204 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202205 | N7061 | Northfield Hostel | Y000 | 202205 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202206 | N7061 | Northfield Hostel | Y000 | 202206 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658860 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202207 | N7061 | Northfield Hostel | Y000 | 202207 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202208 | N7061 | Northfield Hostel | Y000 | 202208 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202209 | N7061 | Northfield Hostel | Y000 | 202209 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658860 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202210 | N7061 | Northfield Hostel | Y000 | 202210 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202211 | N7061 | Northfield Hostel | Y000 | 202211 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658070 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7061202212 | N7061 | Northfield Hostel | Y000 | 202212 | OX-1003153 | 519499 | 2021/22 CAP0 | 2021/22 Capital Original | 7900000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7061202212 | N7061 | Northfield Hostel | Y000 | 202212 | OX-1003153 | 519500 | 2021/22 CAP0 | 2021/22 Capital Original | -658860 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202201 | N7062 | Lanham Way | Y000 | 202201 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202202 | N7062 | Lanham Way | Y000 | 202202 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202203 | N7062 | Lanham Way | Y000 | 202203 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254370 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202204 | N7062 | Lanham Way | Y000 | 202204 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202205 | N7062 | Lanham Way | Y000 | 202205 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202206 | N7062 | Lanham Way | Y000 | 202206 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254370 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202207 | N7062 | Lanham Way | Y000 | 202207 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202208 | N7062 | Lanham Way | Y000 | 202208 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202209 | N7062 | Lanham Way | Y000 | 202209 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254370 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202210 | N7062 | Lanham Way | Y000 | 202210 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202211 | N7062 | Lanham Way | Y000 | 202211 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254065 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202212 | N7062 | Lanham Way | Y000 | 202212 | OX-1003076 | 517937 | 2021/22 CAP0 | 2021/22 Capital Original | 254370 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7062202201 | N7062 | Lanham Way | Y000 | 202201 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202202 | N7062 | Lanham Way | Y000 | 202202 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202203 | N7062 | Lanham Way | Y000 | 202203 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254370 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202204 | N7062 | Lanham Way | Y000 | 202204 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202205 | N7062 | Lanham Way | Y000 | 202205 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202206 | N7062 | Lanham Way | Y000 | 202206 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254370 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202207 | N7062 | Lanham Way | Y000 | 202207 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202208 | N7062 | Lanham Way | Y000 | 202208 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202209 | N7062 | Lanham Way | Y000 | 202209 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254370 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202210 | N7062 | Lanham Way | Y000 | 202210 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202211 | N7062 | Lanham Way | Y000 | 202211 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254065 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7062202212 | N7062 | Lanham Way | Y000 | 202212 | OX-1003153 | 519497 | 2021/22 CAP0 | 2021/22 Capital Original | 3050000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7062202212 | N7062 | Lanham Way | Y000 | 202212 | OX-1003153 | 519498 | 2021/22 CAP0 | 2021/22 Capital Original | -254370 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202201 | N7064 | Unallocated Site 1 | Y000 | 202201 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202202 | N7064 | Unallocated Site 1 | Y000 | 202202 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202203 | N7064 | Unallocated Site 1 | Y000 | 202203 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 419168.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202204 | N7064 | Unallocated Site 1 | Y000 | 202204 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202205 | N7064 | Unallocated Site 1 | Y000 | 202205 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202206 | N7064 | Unallocated Site 1 | Y000 | 202206 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 419168.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202207 | N7064 | Unallocated Site 1 | Y000 | 202207 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202208 | N7064 | Unallocated Site 1 | Y000 | 202208 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202209 | N7064 | Unallocated Site 1 | Y000 | 202209 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 419168.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202210 | N7064 | Unallocated Site 1 | Y000 | 202210 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202211 | N7064 | Unallocated Site 1 | Y000 | 202211 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 418665.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202212 | N7064 | Unallocated Site 1 | Y000 | 202212 | OX-1003076 | 517936 | 2021/22 CAP0 | 2021/22 Capital Original | 419168.4 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7064202201 | N7064 | Unallocated Site 1 | Y000 | 202201 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202202 | N7064 | Unallocated Site 1 | Y000 | 202202 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202203 | N7064 | Unallocated Site 1 | Y000 | 202203 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -419168.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202204 | N7064 | Unallocated Site 1 | Y000 | 202204 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202205 | N7064 | Unallocated Site 1 | Y000 | 202205 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202206 | N7064 | Unallocated Site 1 | Y000 | 202206 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -419168.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202207 | N7064 | Unallocated Site 1 | Y000 | 202207 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202208 | N7064 | Unallocated Site 1 | Y000 | 202208 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202209 | N7064 | Unallocated Site 1 | Y000 | 202209 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -419168.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202210 | N7064 | Unallocated Site 1 | Y000 | 202210 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202211 | N7064 | Unallocated Site 1 | Y000 | 202211 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -418665.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7064202212 | N7064 | Unallocated Site 1 | Y000 | 202212 | OX-1003153 | 519495 | 2021/22 CAP0 | 2021/22 Capital Original | 5026000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7064202212 | N7064 | Unallocated Site 1 | Y000 | 202212 | OX-1003153 | 519496 | 2021/22 CAP0 | 2021/22 Capital Original | -419168.4 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202201 | N7065 | Unallocated Site 2 | Y000 | 202201 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202202 | N7065 | Unallocated Site 2 | Y000 | 202202 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202203 | N7065 | Unallocated Site 2 | Y000 | 202203 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333600 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202204 | N7065 | Unallocated Site 2 | Y000 | 202204 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202205 | N7065 | Unallocated Site 2 | Y000 | 202205 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202206 | N7065 | Unallocated Site 2 | Y000 | 202206 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333600 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202207 | N7065 | Unallocated Site 2 | Y000 | 202207 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202208 | N7065 | Unallocated Site 2 | Y000 | 202208 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202209 | N7065 | Unallocated Site 2 | Y000 | 202209 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333600 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202210 | N7065 | Unallocated Site 2 | Y000 | 202210 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202211 | N7065 | Unallocated Site 2 | Y000 | 202211 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333200 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202212 | N7065 | Unallocated Site 2 | Y000 | 202212 | OX-1003076 | 517935 | 2021/22 CAP0 | 2021/22 Capital Original | 333600 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7065202201 | N7065 | Unallocated Site 2 | Y000 | 202201 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202202 | N7065 | Unallocated Site 2 | Y000 | 202202 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202203 | N7065 | Unallocated Site 2 | Y000 | 202203 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333600 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202204 | N7065 | Unallocated Site 2 | Y000 | 202204 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202205 | N7065 | Unallocated Site 2 | Y000 | 202205 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202206 | N7065 | Unallocated Site 2 | Y000 | 202206 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333600 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202207 | N7065 | Unallocated Site 2 | Y000 | 202207 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202208 | N7065 | Unallocated Site 2 | Y000 | 202208 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202209 | N7065 | Unallocated Site 2 | Y000 | 202209 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333600 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202210 | N7065 | Unallocated Site 2 | Y000 | 202210 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202211 | N7065 | Unallocated Site 2 | Y000 | 202211 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333200 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7065202212 | N7065 | Unallocated Site 2 | Y000 | 202212 | OX-1003153 | 519493 | 2021/22 CAP0 | 2021/22 Capital Original | 4000000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7065202212 | N7065 | Unallocated Site 2 | Y000 | 202212 | OX-1003153 | 519494 | 2021/22 CAP0 | 2021/22 Capital Original | -333600 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003076 | 517932 | 2021/22 CAP0 | 2021/22 Capital Original | 2392000 | 32 | Annual (March) | App6 Budget Load | AWICKE
N7066202201 | N7066 | Next Steps Accommodation Programme | Y000 | 202201 | OX-1003153 | 519491 | 2021/22 CAP0 | 2021/22 Capital Original | 213000 | 10 | Annual (April) | Reprofile HRA Capital | TCHENG
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003153 | 519492 | 2021/22 CAP0 | 2021/22 Capital Original | -213000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003077 | 518067 | 2021/22 CAPV | 2021/22 Capital Virements | 599962 | 32 | Annual (March) | 2021/22 Slippage | AWICKE
N7066202201 | N7066 | Next Steps Accommodation Programme | Y000 | 202201 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202202 | N7066 | Next Steps Accommodation Programme | Y000 | 202202 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202203 | N7066 | Next Steps Accommodation Programme | Y000 | 202203 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202204 | N7066 | Next Steps Accommodation Programme | Y000 | 202204 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50088.71 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202205 | N7066 | Next Steps Accommodation Programme | Y000 | 202205 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202206 | N7066 | Next Steps Accommodation Programme | Y000 | 202206 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202207 | N7066 | Next Steps Accommodation Programme | Y000 | 202207 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50088.71 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202208 | N7066 | Next Steps Accommodation Programme | Y000 | 202208 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202209 | N7066 | Next Steps Accommodation Programme | Y000 | 202209 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202210 | N7066 | Next Steps Accommodation Programme | Y000 | 202210 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50088.71 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202211 | N7066 | Next Steps Accommodation Programme | Y000 | 202211 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50088.71 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003099 | 518642 | 2021/22 CAPV | 2021/22 Capital Virements | 50028.65 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
N7066202201 | N7066 | Next Steps Accommodation Programme | Y000 | 202201 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202202 | N7066 | Next Steps Accommodation Programme | Y000 | 202202 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202203 | N7066 | Next Steps Accommodation Programme | Y000 | 202203 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202204 | N7066 | Next Steps Accommodation Programme | Y000 | 202204 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50088.7 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202205 | N7066 | Next Steps Accommodation Programme | Y000 | 202205 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202206 | N7066 | Next Steps Accommodation Programme | Y000 | 202206 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202207 | N7066 | Next Steps Accommodation Programme | Y000 | 202207 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50088.7 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202208 | N7066 | Next Steps Accommodation Programme | Y000 | 202208 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202209 | N7066 | Next Steps Accommodation Programme | Y000 | 202209 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202210 | N7066 | Next Steps Accommodation Programme | Y000 | 202210 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50088.7 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202211 | N7066 | Next Steps Accommodation Programme | Y000 | 202211 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50088.7 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003103 | 518836 | 2021/22 CAPV | 2021/22 Capital Virements | -50028.64 | 11 | Twelfths Monthly | Remove duplicate HRA Cfwd | JMARRI
N7066202212 | N7066 | Next Steps Accommodation Programme | Y000 | 202212 | OX-1003121 | 519037 | 2021/22 CAPV | 2021/22 Capital Virements | 622.28 | 32 | Annual (March) | P2 HRA Slippage corrections | JMARRI
N7067202201 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202201 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202202 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202202 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202203 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202203 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8506.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202204 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202204 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202205 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202205 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202206 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202206 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8506.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202207 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202207 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202208 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202208 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202209 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202209 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8506.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202210 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202210 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202211 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202211 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8496.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7067202212 | N7067 | Renewal Of Fire Alarm Panels | Y000 | 202212 | OX-1003076 | 517934 | 2021/22 CAP0 | 2021/22 Capital Original | 8506.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202201 | N7068 | Tucker/Thomson/Juniper | Y000 | 202201 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202202 | N7068 | Tucker/Thomson/Juniper | Y000 | 202202 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202203 | N7068 | Tucker/Thomson/Juniper | Y000 | 202203 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217423.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202204 | N7068 | Tucker/Thomson/Juniper | Y000 | 202204 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202205 | N7068 | Tucker/Thomson/Juniper | Y000 | 202205 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202206 | N7068 | Tucker/Thomson/Juniper | Y000 | 202206 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217423.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202207 | N7068 | Tucker/Thomson/Juniper | Y000 | 202207 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202208 | N7068 | Tucker/Thomson/Juniper | Y000 | 202208 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202209 | N7068 | Tucker/Thomson/Juniper | Y000 | 202209 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217423.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202210 | N7068 | Tucker/Thomson/Juniper | Y000 | 202210 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202211 | N7068 | Tucker/Thomson/Juniper | Y000 | 202211 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217163.1 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202212 | N7068 | Tucker/Thomson/Juniper | Y000 | 202212 | OX-1003076 | 517933 | 2021/22 CAP0 | 2021/22 Capital Original | 217423.8 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
N7068202201 | N7068 | Tucker/Thomson/Juniper | Y000 | 202201 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202202 | N7068 | Tucker/Thomson/Juniper | Y000 | 202202 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202203 | N7068 | Tucker/Thomson/Juniper | Y000 | 202203 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217423.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202204 | N7068 | Tucker/Thomson/Juniper | Y000 | 202204 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202205 | N7068 | Tucker/Thomson/Juniper | Y000 | 202205 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202206 | N7068 | Tucker/Thomson/Juniper | Y000 | 202206 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217423.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202207 | N7068 | Tucker/Thomson/Juniper | Y000 | 202207 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202208 | N7068 | Tucker/Thomson/Juniper | Y000 | 202208 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202209 | N7068 | Tucker/Thomson/Juniper | Y000 | 202209 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217423.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202210 | N7068 | Tucker/Thomson/Juniper | Y000 | 202210 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202211 | N7068 | Tucker/Thomson/Juniper | Y000 | 202211 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217163.1 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
N7068202212 | N7068 | Tucker/Thomson/Juniper | Y000 | 202212 | OX-1003153 | 519489 | 2021/22 CAP0 | 2021/22 Capital Original | 2607000 | 32 | Annual (March) | Reprofile HRA Capital | TCHENG
N7068202212 | N7068 | Tucker/Thomson/Juniper | Y000 | 202212 | OX-1003153 | 519490 | 2021/22 CAP0 | 2021/22 Capital Original | -217423.8 | 11 | Twelfths Monthly | Reprofile HRA Capital | TCHENG
R0005202201 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202201 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202202 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202202 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202203 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202203 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244349.07 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202204 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202204 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202205 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202205 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202206 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202206 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244349.07 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202207 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202207 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202208 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202208 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202209 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202209 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244349.07 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202210 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202210 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202211 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202211 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244056.09 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202212 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202212 | OX-1003076 | 517931 | 2021/22 CAP0 | 2021/22 Capital Original | 244349.08 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0005202201 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202201 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202202 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202202 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202203 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202203 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202204 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202204 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81852.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202205 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202205 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202206 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202206 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202207 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202207 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81852.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202208 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202208 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202209 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202209 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202210 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202210 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81852.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202211 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202211 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81852.43 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202212 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202212 | OX-1003099 | 518677 | 2021/22 CAPV | 2021/22 Capital Virements | 81754.29 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
R0005202201 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202201 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202202 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202202 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202203 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202203 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202204 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202204 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202205 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202205 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202206 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202206 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202207 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202207 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202208 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202208 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202209 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202209 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202210 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202210 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202211 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202211 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0005202212 | R0005 | MT Vehicles/Plant Replacement Programme. | Y000 | 202212 | OX-1003120 | 519035 | 2021/22 CAPV | 2021/22 Capital Virements | 35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202201 | R0010 | Electric Vehicles | Y000 | 202201 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202202 | R0010 | Electric Vehicles | Y000 | 202202 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202203 | R0010 | Electric Vehicles | Y000 | 202203 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35361.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202204 | R0010 | Electric Vehicles | Y000 | 202204 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202205 | R0010 | Electric Vehicles | Y000 | 202205 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202206 | R0010 | Electric Vehicles | Y000 | 202206 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35361.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202207 | R0010 | Electric Vehicles | Y000 | 202207 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202208 | R0010 | Electric Vehicles | Y000 | 202208 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202209 | R0010 | Electric Vehicles | Y000 | 202209 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35361.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202210 | R0010 | Electric Vehicles | Y000 | 202210 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202211 | R0010 | Electric Vehicles | Y000 | 202211 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35319.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202212 | R0010 | Electric Vehicles | Y000 | 202212 | OX-1003076 | 517930 | 2021/22 CAP0 | 2021/22 Capital Original | 35361.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
R0010202201 | R0010 | Electric Vehicles | Y000 | 202201 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202202 | R0010 | Electric Vehicles | Y000 | 202202 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202203 | R0010 | Electric Vehicles | Y000 | 202203 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202204 | R0010 | Electric Vehicles | Y000 | 202204 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202205 | R0010 | Electric Vehicles | Y000 | 202205 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202206 | R0010 | Electric Vehicles | Y000 | 202206 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202207 | R0010 | Electric Vehicles | Y000 | 202207 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202208 | R0010 | Electric Vehicles | Y000 | 202208 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202209 | R0010 | Electric Vehicles | Y000 | 202209 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202210 | R0010 | Electric Vehicles | Y000 | 202210 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202211 | R0010 | Electric Vehicles | Y000 | 202211 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35361.6 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
R0010202212 | R0010 | Electric Vehicles | Y000 | 202212 | OX-1003120 | 519036 | 2021/22 CAPV | 2021/22 Capital Virements | -35319.2 | 11 | Twelfths Monthly | P2 Capital Adjustments & Tidy | JMARRI
T2273202202 | T2273 | Car Parks Resurfacing | Y000 | 202202 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 9364.62 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202203 | T2273 | Car Parks Resurfacing | Y000 | 202203 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 106288.44 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202204 | T2273 | Car Parks Resurfacing | Y000 | 202204 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 40267.87 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202205 | T2273 | Car Parks Resurfacing | Y000 | 202205 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 31371.48 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202206 | T2273 | Car Parks Resurfacing | Y000 | 202206 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 29966.78 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202207 | T2273 | Car Parks Resurfacing | Y000 | 202207 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 28093.86 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202208 | T2273 | Car Parks Resurfacing | Y000 | 202208 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 44950.18 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202209 | T2273 | Car Parks Resurfacing | Y000 | 202209 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 28093.86 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202210 | T2273 | Car Parks Resurfacing | Y000 | 202210 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 39331.4 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202211 | T2273 | Car Parks Resurfacing | Y000 | 202211 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 50568.95 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202212 | T2273 | Car Parks Resurfacing | Y000 | 202212 | OX-1003076 | 517929 | 2021/22 CAP0 | 2021/22 Capital Original | 59933.57 | 588 | B1184NE20 – PPJ | App6 Budget Load | AWICKE
T2273202201 | T2273 | Car Parks Resurfacing | Y000 | 202201 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202202 | T2273 | Car Parks Resurfacing | Y000 | 202202 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202203 | T2273 | Car Parks Resurfacing | Y000 | 202203 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202204 | T2273 | Car Parks Resurfacing | Y000 | 202204 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2991.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202205 | T2273 | Car Parks Resurfacing | Y000 | 202205 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202206 | T2273 | Car Parks Resurfacing | Y000 | 202206 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202207 | T2273 | Car Parks Resurfacing | Y000 | 202207 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2991.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202208 | T2273 | Car Parks Resurfacing | Y000 | 202208 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202209 | T2273 | Car Parks Resurfacing | Y000 | 202209 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202210 | T2273 | Car Parks Resurfacing | Y000 | 202210 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2991.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202211 | T2273 | Car Parks Resurfacing | Y000 | 202211 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2991.06 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2273202212 | T2273 | Car Parks Resurfacing | Y000 | 202212 | OX-1003099 | 518676 | 2021/22 CAPV | 2021/22 Capital Virements | 2987.47 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202201 | T2287 | Recycling Transfer Station | Y000 | 202201 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202202 | T2287 | Recycling Transfer Station | Y000 | 202202 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202203 | T2287 | Recycling Transfer Station | Y000 | 202203 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202204 | T2287 | Recycling Transfer Station | Y000 | 202204 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1563.92 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202205 | T2287 | Recycling Transfer Station | Y000 | 202205 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202206 | T2287 | Recycling Transfer Station | Y000 | 202206 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202207 | T2287 | Recycling Transfer Station | Y000 | 202207 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1563.92 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202208 | T2287 | Recycling Transfer Station | Y000 | 202208 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202209 | T2287 | Recycling Transfer Station | Y000 | 202209 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202210 | T2287 | Recycling Transfer Station | Y000 | 202210 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1563.92 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202211 | T2287 | Recycling Transfer Station | Y000 | 202211 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1563.92 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2287202212 | T2287 | Recycling Transfer Station | Y000 | 202212 | OX-1003099 | 518675 | 2021/22 CAPV | 2021/22 Capital Virements | 1562.04 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202212 | T2299 | Controlled Parking Zones | Y000 | 202212 | OX-1003076 | 517928 | 2021/22 CAP0 | 2021/22 Capital Original | 400000 | 32 | Annual (March) | App6 Budget Load | AWICKE
T2299202212 | T2299 | Controlled Parking Zones | Y000 | 202212 | OX-1003077 | 518093 | 2021/22 CAPV | 2021/22 Capital Virements | 150000 | 32 | Annual (March) | 2021/22 Slippage | AWICKE
T2299202201 | T2299 | Controlled Parking Zones | Y000 | 202201 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202202 | T2299 | Controlled Parking Zones | Y000 | 202202 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202203 | T2299 | Controlled Parking Zones | Y000 | 202203 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202204 | T2299 | Controlled Parking Zones | Y000 | 202204 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202205 | T2299 | Controlled Parking Zones | Y000 | 202205 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202206 | T2299 | Controlled Parking Zones | Y000 | 202206 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202207 | T2299 | Controlled Parking Zones | Y000 | 202207 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202208 | T2299 | Controlled Parking Zones | Y000 | 202208 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202209 | T2299 | Controlled Parking Zones | Y000 | 202209 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202210 | T2299 | Controlled Parking Zones | Y000 | 202210 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202211 | T2299 | Controlled Parking Zones | Y000 | 202211 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4170 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202212 | T2299 | Controlled Parking Zones | Y000 | 202212 | OX-1003099 | 518674 | 2021/22 CAPV | 2021/22 Capital Virements | 4165 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2299202201 | T2299 | Controlled Parking Zones | Y000 | 202201 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202202 | T2299 | Controlled Parking Zones | Y000 | 202202 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202203 | T2299 | Controlled Parking Zones | Y000 | 202203 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202204 | T2299 | Controlled Parking Zones | Y000 | 202204 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16680 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202205 | T2299 | Controlled Parking Zones | Y000 | 202205 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202206 | T2299 | Controlled Parking Zones | Y000 | 202206 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202207 | T2299 | Controlled Parking Zones | Y000 | 202207 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16680 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202208 | T2299 | Controlled Parking Zones | Y000 | 202208 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202209 | T2299 | Controlled Parking Zones | Y000 | 202209 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202210 | T2299 | Controlled Parking Zones | Y000 | 202210 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16680 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202211 | T2299 | Controlled Parking Zones | Y000 | 202211 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16680 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202212 | T2299 | Controlled Parking Zones | Y000 | 202212 | OX-1003120 | 519031 | 2021/22 CAPV | 2021/22 Capital Virements | -16660 | 11 | Twelfths Monthly | Remove Carry Forward (CIL Spent) | JMARRI
T2299202201 | T2299 | Controlled Parking Zones | Y000 | 202201 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202202 | T2299 | Controlled Parking Zones | Y000 | 202202 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202203 | T2299 | Controlled Parking Zones | Y000 | 202203 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202204 | T2299 | Controlled Parking Zones | Y000 | 202204 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12510 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202205 | T2299 | Controlled Parking Zones | Y000 | 202205 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202206 | T2299 | Controlled Parking Zones | Y000 | 202206 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202207 | T2299 | Controlled Parking Zones | Y000 | 202207 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12510 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202208 | T2299 | Controlled Parking Zones | Y000 | 202208 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202209 | T2299 | Controlled Parking Zones | Y000 | 202209 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202210 | T2299 | Controlled Parking Zones | Y000 | 202210 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12510 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202211 | T2299 | Controlled Parking Zones | Y000 | 202211 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12510 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2299202212 | T2299 | Controlled Parking Zones | Y000 | 202212 | OX-1003131 | 519077 | 2021/22 CAPV | 2021/22 Capital Virements | -12495 | 11 | Twelfths Monthly | Capital Adjustments | JMARRI
T2301202201 | T2301 | Depot Rationalisation | Y000 | 202201 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202202 | T2301 | Depot Rationalisation | Y000 | 202202 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202203 | T2301 | Depot Rationalisation | Y000 | 202203 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58380 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202204 | T2301 | Depot Rationalisation | Y000 | 202204 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202205 | T2301 | Depot Rationalisation | Y000 | 202205 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202206 | T2301 | Depot Rationalisation | Y000 | 202206 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58380 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202207 | T2301 | Depot Rationalisation | Y000 | 202207 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202208 | T2301 | Depot Rationalisation | Y000 | 202208 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202209 | T2301 | Depot Rationalisation | Y000 | 202209 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58380 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202210 | T2301 | Depot Rationalisation | Y000 | 202210 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202211 | T2301 | Depot Rationalisation | Y000 | 202211 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58310 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202212 | T2301 | Depot Rationalisation | Y000 | 202212 | OX-1003076 | 517927 | 2021/22 CAP0 | 2021/22 Capital Original | 58380 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2301202201 | T2301 | Depot Rationalisation | Y000 | 202201 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202202 | T2301 | Depot Rationalisation | Y000 | 202202 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202203 | T2301 | Depot Rationalisation | Y000 | 202203 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202204 | T2301 | Depot Rationalisation | Y000 | 202204 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 39003.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202205 | T2301 | Depot Rationalisation | Y000 | 202205 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202206 | T2301 | Depot Rationalisation | Y000 | 202206 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202207 | T2301 | Depot Rationalisation | Y000 | 202207 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 39003.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202208 | T2301 | Depot Rationalisation | Y000 | 202208 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202209 | T2301 | Depot Rationalisation | Y000 | 202209 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.83 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202210 | T2301 | Depot Rationalisation | Y000 | 202210 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 39003.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202211 | T2301 | Depot Rationalisation | Y000 | 202211 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 39003.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202212 | T2301 | Depot Rationalisation | Y000 | 202212 | OX-1003077 | 518092 | 2021/22 CAPV | 2021/22 Capital Virements | 38956.82 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2301202201 | T2301 | Depot Rationalisation | Y000 | 202201 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202202 | T2301 | Depot Rationalisation | Y000 | 202202 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202203 | T2301 | Depot Rationalisation | Y000 | 202203 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202204 | T2301 | Depot Rationalisation | Y000 | 202204 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27438.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202205 | T2301 | Depot Rationalisation | Y000 | 202205 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202206 | T2301 | Depot Rationalisation | Y000 | 202206 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202207 | T2301 | Depot Rationalisation | Y000 | 202207 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27438.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202208 | T2301 | Depot Rationalisation | Y000 | 202208 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202209 | T2301 | Depot Rationalisation | Y000 | 202209 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202210 | T2301 | Depot Rationalisation | Y000 | 202210 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27438.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202211 | T2301 | Depot Rationalisation | Y000 | 202211 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27438.1 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2301202212 | T2301 | Depot Rationalisation | Y000 | 202212 | OX-1003099 | 518673 | 2021/22 CAPV | 2021/22 Capital Virements | 27405.2 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202201 | T2305 | Parks Paths | Y000 | 202201 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202202 | T2305 | Parks Paths | Y000 | 202202 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202203 | T2305 | Parks Paths | Y000 | 202203 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202204 | T2305 | Parks Paths | Y000 | 202204 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2822.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202205 | T2305 | Parks Paths | Y000 | 202205 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202206 | T2305 | Parks Paths | Y000 | 202206 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202207 | T2305 | Parks Paths | Y000 | 202207 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2822.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202208 | T2305 | Parks Paths | Y000 | 202208 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202209 | T2305 | Parks Paths | Y000 | 202209 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202210 | T2305 | Parks Paths | Y000 | 202210 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2822.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202211 | T2305 | Parks Paths | Y000 | 202211 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2822.26 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2305202212 | T2305 | Parks Paths | Y000 | 202212 | OX-1003099 | 518672 | 2021/22 CAPV | 2021/22 Capital Virements | 2818.87 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202201 | T2306 | Mobile Working and Handhelds | Y000 | 202201 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202202 | T2306 | Mobile Working and Handhelds | Y000 | 202202 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202203 | T2306 | Mobile Working and Handhelds | Y000 | 202203 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202204 | T2306 | Mobile Working and Handhelds | Y000 | 202204 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11740.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202205 | T2306 | Mobile Working and Handhelds | Y000 | 202205 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202206 | T2306 | Mobile Working and Handhelds | Y000 | 202206 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202207 | T2306 | Mobile Working and Handhelds | Y000 | 202207 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11740.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202208 | T2306 | Mobile Working and Handhelds | Y000 | 202208 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202209 | T2306 | Mobile Working and Handhelds | Y000 | 202209 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202210 | T2306 | Mobile Working and Handhelds | Y000 | 202210 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11740.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202211 | T2306 | Mobile Working and Handhelds | Y000 | 202211 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11740.89 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2306202212 | T2306 | Mobile Working and Handhelds | Y000 | 202212 | OX-1003099 | 518671 | 2021/22 CAPV | 2021/22 Capital Virements | 11726.81 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202201 | T2307 | Transformation Funding | Y000 | 202201 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202202 | T2307 | Transformation Funding | Y000 | 202202 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202203 | T2307 | Transformation Funding | Y000 | 202203 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33360 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202204 | T2307 | Transformation Funding | Y000 | 202204 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202205 | T2307 | Transformation Funding | Y000 | 202205 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202206 | T2307 | Transformation Funding | Y000 | 202206 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33360 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202207 | T2307 | Transformation Funding | Y000 | 202207 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202208 | T2307 | Transformation Funding | Y000 | 202208 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202209 | T2307 | Transformation Funding | Y000 | 202209 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33360 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202210 | T2307 | Transformation Funding | Y000 | 202210 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202211 | T2307 | Transformation Funding | Y000 | 202211 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33320 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202212 | T2307 | Transformation Funding | Y000 | 202212 | OX-1003076 | 517926 | 2021/22 CAP0 | 2021/22 Capital Original | 33360 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2307202201 | T2307 | Transformation Funding | Y000 | 202201 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202202 | T2307 | Transformation Funding | Y000 | 202202 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202203 | T2307 | Transformation Funding | Y000 | 202203 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202204 | T2307 | Transformation Funding | Y000 | 202204 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13152.35 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202205 | T2307 | Transformation Funding | Y000 | 202205 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202206 | T2307 | Transformation Funding | Y000 | 202206 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202207 | T2307 | Transformation Funding | Y000 | 202207 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13152.35 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202208 | T2307 | Transformation Funding | Y000 | 202208 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202209 | T2307 | Transformation Funding | Y000 | 202209 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.58 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202210 | T2307 | Transformation Funding | Y000 | 202210 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13152.35 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202211 | T2307 | Transformation Funding | Y000 | 202211 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13152.35 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2307202212 | T2307 | Transformation Funding | Y000 | 202212 | OX-1003099 | 518670 | 2021/22 CAPV | 2021/22 Capital Virements | -13136.57 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202201 | T2308 | Additional Technology Requirements | Y000 | 202201 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202202 | T2308 | Additional Technology Requirements | Y000 | 202202 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202203 | T2308 | Additional Technology Requirements | Y000 | 202203 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 122097.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202204 | T2308 | Additional Technology Requirements | Y000 | 202204 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202205 | T2308 | Additional Technology Requirements | Y000 | 202205 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202206 | T2308 | Additional Technology Requirements | Y000 | 202206 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 122097.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202207 | T2308 | Additional Technology Requirements | Y000 | 202207 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202208 | T2308 | Additional Technology Requirements | Y000 | 202208 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202209 | T2308 | Additional Technology Requirements | Y000 | 202209 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 122097.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202210 | T2308 | Additional Technology Requirements | Y000 | 202210 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202211 | T2308 | Additional Technology Requirements | Y000 | 202211 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 121951.2 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202212 | T2308 | Additional Technology Requirements | Y000 | 202212 | OX-1003076 | 517925 | 2021/22 CAP0 | 2021/22 Capital Original | 122097.6 | 11 | Twelfths Monthly | App6 Budget Load | AWICKE
T2308202201 | T2308 | Additional Technology Requirements | Y000 | 202201 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202202 | T2308 | Additional Technology Requirements | Y000 | 202202 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202203 | T2308 | Additional Technology Requirements | Y000 | 202203 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202204 | T2308 | Additional Technology Requirements | Y000 | 202204 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 61048.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202205 | T2308 | Additional Technology Requirements | Y000 | 202205 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202206 | T2308 | Additional Technology Requirements | Y000 | 202206 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202207 | T2308 | Additional Technology Requirements | Y000 | 202207 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 61048.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202208 | T2308 | Additional Technology Requirements | Y000 | 202208 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202209 | T2308 | Additional Technology Requirements | Y000 | 202209 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202210 | T2308 | Additional Technology Requirements | Y000 | 202210 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 61048.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202211 | T2308 | Additional Technology Requirements | Y000 | 202211 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 61048.8 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202212 | T2308 | Additional Technology Requirements | Y000 | 202212 | OX-1003077 | 518094 | 2021/22 CAPV | 2021/22 Capital Virements | 60975.6 | 11 | Twelfths Monthly | 2021/22 Slippage | AWICKE
T2308202201 | T2308 | Additional Technology Requirements | Y000 | 202201 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202202 | T2308 | Additional Technology Requirements | Y000 | 202202 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202203 | T2308 | Additional Technology Requirements | Y000 | 202203 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202204 | T2308 | Additional Technology Requirements | Y000 | 202204 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34387.99 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202205 | T2308 | Additional Technology Requirements | Y000 | 202205 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202206 | T2308 | Additional Technology Requirements | Y000 | 202206 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202207 | T2308 | Additional Technology Requirements | Y000 | 202207 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34387.99 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202208 | T2308 | Additional Technology Requirements | Y000 | 202208 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202209 | T2308 | Additional Technology Requirements | Y000 | 202209 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202210 | T2308 | Additional Technology Requirements | Y000 | 202210 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34387.99 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202211 | T2308 | Additional Technology Requirements | Y000 | 202211 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34387.99 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
T2308202212 | T2308 | Additional Technology Requirements | Y000 | 202212 | OX-1003099 | 518669 | 2021/22 CAPV | 2021/22 Capital Virements | 34346.76 | 11 | Twelfths Monthly | 2021 Capital Carry Forward | JMARRI
624618687.14