## Risk Log
Risk Register - Thriving Communities Strategy update report
[9 empty] | Gross |  |  | Current |  |  | Target
Ref | Title | Risk Description | Opp / Threat | Cause | Consequence | Risk Treatment | Date Raised | Owner | P | I | Score | P | I | Score | P | I | Score | Comments | Control / Mitigation Description | Date Due | Action Status | % Progress | Action Owner
1 | Financial | Cost of living or other crisis increases needs beyond available resources | Threat | Wider economic and political climate | Unmet needs - inequalities gaps widen - some communities not thriving | Reduce | 2022-11-02 | Peter Matthew | 4 | 4 | 16 | 3 | 3 | 9 | 4 | 2 | 8 |  | Targeted fundraising and delivery; data and insight informing resource prioritisation; strong partnership networks and collaborative approach; strong engagement with Oxford's diverse community groups |  |  |  | Paula Redway / Hagan Lewisman
2 | Strategy delivery | Tighter budgets lead to insufficient officer/partner capacity/skills to nurture the relationships which are essential to a whole system approach to delivery | Threat | Insufficient capacity | Siloed working; delivery gaps/overlap/failure | Avoid | 2022-11-02 | Peter Matthew | 4 | 4 | 16 | 3 | 3 | 9 | 4 | 2 | 8 |  | Governance, partnership and delivery mechanisms are structured to maintain relationships efficiently with an in-built learning approach. |  |  |  | Hagan Lewisman / Paula Redway
3 | Inclusive access | Facilities/activity programmes ineffective at increasing usage in target groups | Threat | Insufficient EDI awareness/ training/expertise/funding | Unmet needs - inequalities gaps widen - some communities not thriving | Avoid | 2024-10-16 | Peter Matthew | 4 | 4 | 16 | 2 | 3 | 6 | 2 | 2 | 4 |  | EDI training and awareness programme and Equality Impact Assessment in place; services planned to meet community needs and are promoted in an inclusive way; fundraising to increase access for under-represented groups |  |  |  | Paula Redway / Hagan Lewisman
4 | Public health | Tighter budgets lead to insufficient programmes to increase positive mental and physical health and wellbeing | Threat | Insufficient funding for programmes which support mental and physical health | Increased health inequalities | Reduce | 2024-10-16 | Peter Matthew | 4 | 4 | 16 | 2 | 4 | 8 | 2 | 3 | 6 |  | Continue to work in partnership to fundraise and facilitate programmes which support mental and physical health |  |  |  | Hagan Lewisman / Paula Redway
5 | Public safety | Tighter budgets lead to insufficient programmes to increase community cohesion | Threat | Insufficient funding for programmes which support community cohesion | Increased public disorder | Avoid | 2024-10-16 | Peter Matthew | 4 | 4 | 16 | 2 | 3 | 6 | 2 | 3 | 6 |  | Continue to work in partnership to fundraise and facilitate programmes which support community cohesion |  |  |  | Richard Adams / Paula Redway / Hagan Lewisman
Note on C3: Outline the situation or event that exposes the Council to risk
Note on E3: Cause or trigger event: situations or factors which result in risk becoming a reality.
Note on F3: Consequnce or risk effect: likely consequences if the risk materialises (consider worst case scenario)
Note on G3: Select option from Drop-Down
Note on J2: Risk Level if existing controls and mitigations not in place
Note on M2: Risk Level after existing controls and mitigations are taken into account.
Note on P2: Anticipated Risk Level following introduction of planned controls and mitigations