## Risk Log
Risk Register
Proposal for continued investment in Resonance homelessness fund
As at: 21/05/2025
[9 empty] | Gross |  |  | Current |  |  | Target
Ref | Title | Risk Description | Opp / Threat | Cause | Consequence | Risk Treatment | Date Raised | Owner | P | I | Score | P | I | Score | P | I | Score | Comments | Control / Mitigation Description | Date Due | Action Status | % Progress | Action Owner
| Policy or Funding Changes | Changes in national or local housing policy or funding availability | Threat | Central government policy shift or budget cuts | Project delay or cancellation | Reduce | 2025-05-21 | Housing Needs and Strategy Manager | 3 | 3 | 9 | 3 | 3 | 9 | 2 | 2 | 4 |  | Engage with MHCLG on policy developments in sector, lobby against any unhelpful changes and highlight impact |  | Ongoing | 0% | Richard Wood
| Failure to Achieve Cost Avoidance | Projected savings from avoided and reduced nightly paid accommodation not realised | Threat | Units not delivered on time or not occupied quickly | Financial viability of investment questioned | Reduce | 2025-05-21 | Housing Needs and Strategy Manager | 4 | 4 | 16 | 3 | 3 | 9 | 2 | 2 | 4 |  | Prioritise rapid occupancy and keep track of cost avoidance metrics |  | Not yet started | 0% | Richard Wood
| Inability to procure or sustain Leasing Partner | The delivery company may be unable to secure a suitable partner to manage and rent out the acquired dwellings if current provider is not sustained | Threat | Lack of market interest, unattractive leasing terms, or poor location of properties | Properties remain vacant. Oxford City Council does not achieve expected return on investment or cost avoidance | Reduce | 2025-05-21 | Housing Needs and Strategy Manager | 4 | 5 | 20 | 3 | 4 | 12 | 2 | 3 | 6 |  | Implement robust contract management and performance monitoring, develop contingency plan for alternative provider should it be required |  | Not yet started | 0% | Richard Wood
| Ineffectiveness of Property Management Company | The property management company may be ineffective, leading to long void periods, reduced return on investment, increased evictions, and higher repair costs | Threat | Poor performance by the property management company. | Long void periods, reduced return on investment, increased evictions, higher repair costs. | Reduce | 2025-05-20 | Housing Needs and Strategy Manager | 4 | 5 | 20 | 3 | 4 | 12 | 2 | 3 | 6 |  | Fund has implemented robust contract management and performance monitoring developed contingency plan for alternative provider if required. |  | Not yet started | 0% | Richard Wood
| Legislative changes under the Renters’ Rights Bill increasing increase operational complexity. | Abolition of Section 21 “no-fault” evictions, introduction of periodic tenancies, stricter rent increase rules, and expanded tenant rights. | Threat | Government policy change and implementation | Longer tenancy disputes, reduced ability to manage stock effectively, increased legal and administrative costs, and potential delays in regaining possession of properties. | Reduce | 2025-05-20 | Housing Needs and Strategy Manager | 4 | 5 | 20 | 3 | 4 | 12 | 2 | 3 | 6 |  | Monitor the management company ensuring they: Review and update tenancy agreements to align with the new legal framework. Train property management staff on the new legal obligations and tenant rights. Establish clear internal procedures for handling possession claims under the new grounds. Engage legal counsel to ensure compliance and reduce exposure to tribunal challenges. Monitor updates from the Department for Levelling Up, Housing and Communities (DLUHC) and the Private Rented Sector Ombudsman. Develop contingency plans for longer void periods or delayed possession. Enhanced Homeless Prevention activities |  | Not yet started | 0% | Richard Wood
| Drop in investment value | Potential decrease in property values due to market downturns or economic instability | Threat | Market downturns, economic instability. | Reduced asset value, lower return on investment. | Reduce | 2025-05-20 | Housing Needs and Strategy Manager | 4 | 4 | 16 | 3 | 4 | 12 | 2 | 3 | 6 |  | Regularly review property values and market conditions. Adjust investment strategy as needed. Monitor market trends and economic indicators. Long term investment, so more resilient to short term changes in market. Resonance are established in sector so provide expertise |  | Ongoing | 0% | Richard Wood
| Other investors pull out of the fund | Other investors, either the large LAs or other smaller investors pull out of the fund, and can't be replaced | Threat | Investors need to pull out capital, or view fund as lo longer aligned to priorities or a good investment | If investors can be replaced, could resort in selling of some of our match funded units | Reduce | 2025-05-20 | Housing Needs and Strategy Manager | 5 | 4 | 20 | 3 | 4 | 12 | 2 | 4 | 8 |  | The impact of investors pulling out is hard to mitigate against, but we have sought to and will continue to mitigate the chances of it happening. We have been in contact will all other LA investors and clarified their positions. This isn't possible with smaller investors, but have instead been in regular contact with Resonance, and are reassured they are working to either retain all current investors or replace them, and they havent raised any issues yet of needing to sell units. |  | Ongoing | 0% | Richard Wood
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
[11 empty] | 0 |  |  | 0 |  |  | 0
THE RISK REGISTER IS FORMATTED AS A TABLE. PRESS TAB ON THE LAST TABLE CELL TO INSERT A NEW ROW.
Notes
Gross Risk Score
Risk level if existing key controls and mitigations were not in place or not effective.
Current Risk Score
This is the risk score at the time that the risk is reviewed. When the risk is first identified it will be the same as the gross risk score. The current risk score is tracked to ensure that progress is being made to manage the risk and reduce the Council’s exposure.
Target Risk Score
This is the risk score after mitigating actions have taken place. The target risk score shows how effective your action plans are at managing the risk.
Risk Management Approach
See separate tabs for further information:
- | Risk Identification
- | Types of Risk to Consider
- | Risk Evaluation & Prioritisation
- | Risk Treatment
Note on J7: Risk Level if existing controls and mitigations not in place
Note on M7: Risk Level after existing controls and mitigations are taken into account.
Note on P7: Anticipated Risk Level following introduction of planned controls and mitigations
Note on C8: Outline the situation or event that exposes the Council to risk
Note on E8: Cause or trigger event: situations or factors which result in risk becoming a reality.
Note on F8: Consequnce or risk effect: likely consequences if the risk materialises (consider worst case scenario)
Note on G8: Select option from Drop-Down

## Validations (hidden)
| P / I Score | Risk Response | Control Status | Progress
Opportunity | 1 | Reduce | Not yet started | 0%
Threat | 2 | Accept | In Progress | 10%
| 3 | Avoid | Ongoing | 20%
| 4 | Transfer | Completed | 30%
| 5 | Contingency Plans |  | 40%
50%
60%
70%
80%
90%
100%

## Risk ID
Risk Identification
Risks should be identified that may affect the Council’s ability to achieve its business objectives, execute its strategies successfully or limit its ability to exploit opportunities.
Risks can be identified through a number of methods, including:
• A ‘brainstorming’ session or workshop with the whole management team and relevant stakeholders
• Interviews or questionnaires with key stakeholders
• Meetings with smaller groups of people
There are a wide range of methods available that can be used to identify and understand risks. The method that you select will depend upon the type of risk(s) that you are dealing with but typically a management team workshop is the method most commonly used.
Additionally, existing sources of information could help inform this stage. Some examples are listed below:
• Service / corporate plans, strategies and objectives
• Existing risk registers
• Risks or issues raised by internal audit or other scrutiny body
• Risks identified through budget setting processes
• Health & safety risk assessments
• Business continuity risk assessments
• Partnership, programme or project documentation (e.g. business case or project risk register)
• Experience of those participating in the risk identification process
It is the responsibility of those identifying risks to decide which sources of information they should consult. This may be one or more of the sources listed above or it could be something else you think is appropriate.
As well as direct risks to the achievement of our objectives it is important to think broadly about uncertainties that may have an impact on the organisation. The diagram shown below illustrates a variety of different risk themes, expanding on PESTLE prompts, which the organisation could face. Think also in terms of these themes when identifying risks.
Once identified, the risks need to be described in sufficient detail and recorded in a consistent format to support effective decision making on the way that the risk is managed. It is crucial for risks to be defined properly at this stage. Failure to do so can result in confusion about the exact nature of the risk, ineffective risk controls being implemented, or the risk analysis being over or underestimated.
The description of the risk should include the following elements:
• Risk Title – a short and concise header for the risk
• Description – expanding on the risk title outlining the situation or event that exposes us to a risk.
• Risk Cause – also known as the trigger event. Situations or factors which result in the risk becoming a reality.
• Risk Effect – the likely consequences if the risk materialises (The negative impact - consider worst likely scenario)
When describing a risk try not to describe the impact of the risk as the risk itself or define risks with statements which are the converse of objectives. Focus upon the uncertain event that would result in those impacts.

## Types of Risk to Consider
Types of Risk to consider
Strategic / Commercial
1 | Under performance to specification
2 | Management will under perform against expectations
3 | Collapse of contractors
4 | Insolvency of promoter
5 | Failure of suppliers to meet contractual commitments (quality, cost, time)
6 | Insufficient capital
7 | Market fluctuations
8 | Trade/Banking crises
9 | Fraud/theft
10 | Partnership failing to deliver desired outcomes
11 | Situation is not insurable (cost of insurance outweighs the benefit)
Economic / Financial / Market
1 | Exchange rate fluctuation
2 | Interest rate instability
3 | Inflation
4 | Shortage of working capital
5 | Failure to meet projected revenue targets
6 | Market developments will adversely affect plans
Legal and Regulatory
1 | New or changed legislation may invalidate assumptions upon which the activity is based
2 | Failure to obtain appropriate approval e.g. planning consent
3 | Unforseen inclusion of contingent liabilities
4 | Loss of intellectual property rights
5 | Failure to achieve satisfactory contractual arrangements
6 | Unexpected regulatory controls or licencing requirements
7 | Changes in tax or tariff structure
Organisational / Management / Human factors
1 | Management incompetence
2 | Inadequate corporate policies
3 | Inadequate adoption of management practices
4 | Poor leadership
5 | Key personnel have inadequate authority to fulfil their roles
6 | Poor staff selection procedures
7 | Lack of clarity over roles and responsibilities
8 | Vested interests creating conflict and compromising overall aims
9 | Individual or group interests given unwarrented priority
10 | Personality clashes
11 | Indecision or inappropriate decision making
12 | Lack of operational support
13 | Inadequate or inaccurate information
14 | Health and Safety constraints
Political
1 | Change of government policy
2 | Change of government
3 | War and disorder
4 | Adverse public opinion/media intervention
Environmental
1 | Natural disasters
2 | Storms, flooding, tempests
3 | Pollution incidents
4 | Transport problems (including aircraft/vehicle collisions)
Technical / Operational / Infrastructure
1 | Inadequate design
2 | Professional negligence
3 | Human error/incompetence
4 | Infrastructure failure
5 | Operation lifetime lower than expected
6 | Increased dismantling/decommisioning costs
7 | Safety being compromised
8 | Performance failure
9 | Residual maintenance problems
10 | Scope creep
11 | Unclear expectations
12 | Breaches in security/information security
13 | Lack or inadequacy of business continuity

## Risk Eval & Matrix Notes
Risk Evaluation and Prioritisation
Once risks have been identified the risk matrix is the main tool for prioritising risks so we can establish which risks are most significant and therefore are in need of greater attention and resources. It also allows us to compare different types of risk with each other across the council.
Each risk should be analysed using a five by five matrix for (1) the likelihood it will happen and (2) the impact if it did occur. This assessment should be made on three different basis:
• Gross risk – risk level if existing key controls and mitigations were not in place or not effective.
• Current risk – risk level after existing controls and mitigations are taken into consideration.
• Target risk – anticipated risk level following the introduction of planned controls and mitigations.
Assessing the gross risk allows consideration of the dependency the organisation has upon the existing key controls and informs decisions around risk treatment, and selection of an appropriate target risk level, considered in the next section of this toolkit. It is often helpful to consider the Current Risk first, and then ask yourself what the impact and likelihood of the risk might be if the key controls were not in place.
It is the risk owner’s responsibility to ensure the controls they believe are reducing the risk are effective and are working in practice. Controls that are not yet in place should not be considered within the current risk.
Each identified risk should then be plotted onto the risk matrix.
When considering the likelihood of a risk happening you should select the number from 1 to 5 from the risk matrix that you think it will be over the next 12 months (it can be longer or shorter; some risks in the Strategic Risk Register are better considered over 3 to 5 years, some operational risks will be considered over 3 to 6 months). This score will require an element of judgement when considering how likely an event is to occur and you should consider the following:
• Has this event happened before in the Council? (How frequently?) Has this event happened elsewhere? (How frequently?)
• How likely is it that one or more of the causes/ triggers of the event will occur?
• Has anything happened recently that makes the event more or less likely to occur?
The following tables provide some support in quantifying the risk in terms of likelihood and impact.
Risk Probability Assessment Criteria
When you select the impact you should give consideration to the factors outlined in the risk matrix. For example, if the risk you are scoring has a low financial impact but a high impact on our reputation then you would select the most appropriate number between 1 and 5 that relates to the level of reputational impact. Once again, this score will have an element of judgement.
Risk Impact Assessment Criteria

## Risk Treatment Notes
Risk Treatment
Once risks have been identified and scored based on current controls the next step is to decide what action needs to be taken to manage them. Generally speaking, there are four approaches to treating risk: Treat, Tolerate, Terminate or Transfer:
When considering further action required to manage the risk, and indeed the appropriateness of existing controls, an assessment of treatment options should be made alongside a consideration of the Council’s risk appetite and tolerance for the current level of risk.
A further consideration is the efficiency of risk treatment in relation to the cost effectiveness of the proposed actions to be taken. Firstly the cost of implementation has to be considered (time, manpower, budget, etc.). The impact expected if no action is taken, should be weighed against the cost of action and the reduction of the impact. There should be a direct benefit from the cost implementation in terms of the reduction of the level of the risk.
Plans should then be put into place to manage the risk with key milestones identified and clear owners – ensuring that they are ‘SMART’ – Specific, measurable, achievable, realistic, time bound.
Oxford City Council has focused on the Red, Amber, Green status of risks in determining the risk appetite of the organization. Red risks are considered unacceptable and every effort must be made to reduce the risk to the organization.
The risk appetite is reviewed periodically or when there are significant changes to the organisation. Changes to the risk appetite level would require a change to strategy and would therefore require approval of the Cabinet.