## Blank Risk Register
Appendix 2: ASB Policy 2026-29 Risk Assessment
[5 empty] | Date Raised | Owner | Gross |  | Current |  | Residual |  | Comments | Controls
Title | Risk description | Opp/ threat | Cause | Consequence |  |  | I | P | I | P | I | P |  | Control description | Due date | Status | Progress % | Action Owner
ASB Policy | Multi agency enforcement | Lack of enforcement officers | Financial cutbacks in police and council | Ineffective legislation and negative public feedback | 02/09/2025 | Richard Adams | 4 | 2 | 4 | 2 | 2 | 2 | Continued partnership working with the police and other internal Council teams. | Training process in place. Joint working arrangements developed with local neighbourhood policing teams. | 31/10/25 | On-going | 75 | Richard Adams
ASB Policy | Increased demand. | Capacity overstretched. | Inappropriate reporting. | Poor customer service, sign-posting to correct organisation. | 02/09/2025 | Richard Adams | 4 | 2 | 4 | 2 | 2 | 2 | Clear descriptions of types of ASB that Council will not investigate available on the website and in Contact Centre scripts. Data dashboard to monitor adherence to housing regulator standards. | Training process in place. | 31/10/25 | On-going | 75 | Richard Adams
ASB Policy | Not having an ASB Policy | Legal requirement | Policy not approved. | Judical review of cases, poor customer satisfaction, increase in ASB complaints. | 2025-02-09 | Richard Adams | 4 | 1 | 1 | 1 | 1 | 1 | ASB in place for over 10 years. | ASB Policy produced and approved | 31/10/25 | On-going | 90% | Richard Adams