## Risk Register v0.2
Appendix Four: Risk Register - LGR draft Three Unitary Authorities proposal
[5 empty] | Gross |  |  | Current |  |  | Target
Title | Risk Description | Cause | Consequence | Owner | P | I | Score | P | I | Score | P | I | Control Description | Progress | Date Due | Action Status | Action Owner
Financial | Level of net efficiencies not achieved | While a prudent approach has been taken to modelling of costs and savings, there remain uncertainties around overall level of efficiencies that will be delivered: MTFS outturns for each of 7 constituent councils and management of high cost services up to vesting Funding formula changes Future decisions taken by new unitary councils | A lower level of net efficiencies would lead to a longer payback period for transition costs | Transition Director | 3 | 2 |  | 2 | 2 | 4 | 2 | 2 | Detailed financial modelling supported by Pixel Financial, and Inner Circle Consulting Common position on financial data used for modelling among all 7 councils Prudent approach taken, including contingency Projections show all three councils will achieve very strong business growth, that will enable recovery and a business rates position. | 100% | Closed |  | Transition Director
Boundaries | 3UA proposal is taken forward without modification | Government does not grant modification requested to enable boundary changes | If Government accepted 3UA proposal but chose not to grant the modification requested to enable boundary changes: Would significantly reduce opportunity to deliver step change in economic growth Would significantly reduce ability to deliver new housing sufficient to meet Oxford's needs close to city | Transition Director | 2 | 4 |  | 1 | 4 | 4 | 1 | 4 | Regular dialogue with MHCLG officials throughout development of proposal Advice sought from Boundary Commission KC legal advice taken over structuring of proposal and modification request 18 of 21 English county areas undergoing LGR are understood to include proposals involving boundary changes | 100% | Closed |  | Transition Director
Implementation | Implementation of new councils has negative impacts on existing authorities | A lower level of net efficiencies would lead to a longer payback period for transition costs. Additional workload on officers. Uncertainty over future leads to loss of key staff Councils fail to reach agreement on fully collaborative approach to implementation | Transitional and transformational cost savings are delayed Service levels in existing and/ or new councils are negatively impacted Potential delay to implementation | Transition Director | 3 | 3 |  | 2 | 3 | 6 | 1 | 3 | Consistency among outline implementation plans put forward across all three proposals Well understood pathway to creation of new councils with additional support from LGA and MHCLG Strong track record of collaborative working in Oxfordshire | 50% | Open |  | Transition Director
Note on F3: Risk Level if existing controls and mitigations not in place
Note on I3: Risk Level after existing controls and mitigations are taken into account.
Note on B4: Outline the situation or event that exposes the Council to risk
Note on C4: Cause or trigger event: situations or factors which result in risk becoming a reality.
Note on D4: Consequence or risk effect: likely consequences if the risk materialises (consider worst case scenario)

## Validations (hidden)
| P / I Score | Risk Response | Control Status | Progress
Opportunity | 1 | Reduce | Not yet started | 0%
Threat | 2 | Accept | In Progress | 10%
| 3 | Avoid | Ongoing | 20%
| 4 | Transfer | Completed | 30%
| 5 | Contingency Plans |  | 40%
50%
60%
70%
80%
90%
100%