## OFS Project Risk Log
Risk ID | Phase | Description | Impact L/M/H | Probability L/M/H | Proximity | Counter Measures | Prevention/ Reduction/ Acceptance/ Contingency/ Transference | Owner | Author | Date identified/ updated | Current Status | Outcome
CAPITAL PROJECT - Acquisition and Build
1 | Implementation | Contractor not financially stable |  |  |  | Financial monitoring of Contractor continued without any signs of difficult but this risk was realised with Rok entering administration on 8th November 2010. This risk will be also carried for the replacement contractor and supply chain. Monitoring of replacement contractor to be also put in place as well as a new performance bond. | Reduction/ Contingency | Project Team | Paul Quinney | 2011-12-03 |  | Risk realised
1a | Implementation | Contractor not financially stable | High | Low |  | Financial monitoring of Contractor continued without any signs of difficult but this risk was realised with Rok entering administration on 8th November 2010. This risk will be also carried for the replacement contractor and supply chain. Monitoring of replacement contractor to be also put in place as well as a new performance bond. | Reduction/ Contingency | Project Team | Paul Quinney | 2011-02-01 | Current
2 | Implementation | Conditions discharged - Planning permission | Medium | Low |  | Planning Permission with conditions granted by Area Committee. Submission of minor amendments made and agreed. Discharge of conditions submitted and majority approved. Awaiting feedback on last 2 reamining items. | Reduction | Project Team | Nerys Parry/ Paul Quinney | 2011-06-01 | Current
3 | Implementation | Project runs over cost | High | High |  | Main works tender returned and accepted. Risk reduced by 12.5%. Asbestos discovered which has already taken £30k of the risk allowance. Financial implications of Rok entering administration and ability of recovering additional costs from the bond. £200k further VE to be undertaken. Financial uncertainty over full recovery of additional costs arising as a result of ROK entering administration and ability of recovering these costs from the bond. Dialogue to continue with loss adjuster. Additional fees also claimed by Architect and Structural Engineer and others. Impact of 4-week delay by contractor may exceed contract provision. | Prevention | Project Team | Nerys Parry/ Paul Quinney | 2011-06-01 | Current
4 | Implementation | Making building DDA compliant | Medium | Medium |  | Full Building Control application submitted May 2010 and approved 25th June. NOTE: 2 no platform lifts omitted as part of VE accepted by Building Control. 1 no potentially to be added back from client risks. | Reduction | Project Team | Paul Quinney | 2011-06-01 | Current
5 | Implementation | Slippage in project plan |  |  |  | Project Manager to continually review revised programme. Ensure continued comms with HCA. Slippage in Stage E was accomodated by reducing duration of Stage G as agreed with design Team. Regular review of Project Plan. Delay on confirmation of funding to enable contractor appointment and maintain programme. ROK in administration and appointment of Kingerlee resulting in 3 month delay. | Prevention | Project Team | Nerys Parry/ Paul Quinney | 2010-02-04 |  | Risk realised
5a | Implementation | Slippage in project plan | High | High | Reinstate from new date | Regular progress reviews. Delays incurred as a result of further structural works required during opening up. Probability increased to High | Prevention | Project Team | Nerys Parry/ Paul Quinney | 2011-04-01 | Current
ARTS COMPANY - Revenue and On-going Sustainability
6 | Consultation | Unable to identify a core revenue stream to run all Arts services in the building which is sustainable in the short, medium and longer term | High | Medium |  | Reccomendation of establishing Artistic Charitable Trust was supported by CEB on 31/03/10. Arts Company and Charitable status registered, appointed Trustees and Arts Director. Arts Company to review Business Plan. Initial review by Art Director highlight risk of achieving Year 1 revenue target. Seeking additional funding. Initial interest in bookings positive. | Prevention | Project Team | Laura Worsfold | 2011-06-01 | Current
7 | Implementation | Arts Company non-performance | Medium | Medium |  | Working with Trustees to ensure viable Business Plan maintained. Probability remains Medium - To be monitored closely | Prevention | Project Team | Laura Worsfold/ Paul Quinney | 2011-04-01 | Current
8 | Implementation | Limited alcohol licence refused for café, making theatre less commercially viable | Medium | Low |  | Early and ongoing dialogue with licencing officials to understand likely constraints and ensure development is in-line to be submitted early Spring. Initial meetings held and draft application prepared | Prevention | Project Team | Ciara Devlin/ Paul Quinney | 2011-06-01 | Current
CRISIS SKYLIGHT - Revenue and On-going Sustainability
9 | Consultaion | Economic downturn's adverse impact on projected revenue incomes and grant | Medium | Medium |  | Crisis have robust contingency plans. Configuration of building to have maximum flexibility should problems arise and reflected in Design Brief. Early programming and marketing of facilities to be undertaken. CRISIS launching revenue campaign. Fund raising strategy is in place and regional fundraiser appointed. | Prevention | Project Board | Nerys Parry/ Ciara Devlin | 2011-06-01 | Current
10 | Consultation | Collaboration between arts and homelessness provision is not aligned/compatible and cannot be agreed | High | Low |  | A member of Arts & Cultural Development now on project team to shape Arts element. Arts Development Director and Trustees are working with CRISIS' Marketing Team/Head Office | Prevention | Project Team | Nerys Parry/ Ciara Devlin/ Laura Worsfold | 2011-02-01 | Current
11 | Consultation | Voluntary and statutory sector partners do not buy into the project | Medium | Low |  | Ensure they are briefed and part of the consultation process. Set out clearly how OFS fits with other services and how together the map of services meets needs. | Prevention | Project Team | Nerys Parry/ Ciara Devlin | 2008-11-10 | Current
12 | Consultation and on-going | Café is not financially viable | Medium | Low |  | Carry out market research and feasibility study for café/restaurant. Look at other options for a viable social enterprise. Working with commercial partner (Benugo) to develop Business Plan | Acceptance/ Contingency | Project Team | Ciara Devlin | 2011-02-01 | Current
13 | Implementation and on-going | Loss of Political support | High | Low |  | Engaging and communicating with members to ensure understanding to achieve support. | Prevention | Project Board | Nerys Parry | 2009-07-14
14 | Implementation and on-going | CRISIS unable to maintain commitment to Revenue funding | High | Low |  | Ensure dialogue with CRISIS to demonstate funding is being maintained. Regional Fundraiser appointed. | Prevention | Project Board | Ciara Devlin/ Paul Quinney | 2011-06-01 | Current
15 | Implementation and on-going | Oxford City Council unable to maintain commitment to funding | Medium | Low |  | Ensue dialogue maintained with members to maintain support of project. Lease obligation for first 5 years. | Prevention | Project Board | Ciara Devlin/ Paul Quinney | 2011-02-01
Stakeholder Management and Communication
16 | Consultation and on-going | Adverse press coverage which jeopordises any aspect of development | Medium | Medium |  | Development of communication plan with key messages. On-going reinforcement from Project Team to press office. Working with CRISIS Communication Team | Prevention/ Reduction/ Acceptance | Project Team with Press Office | Nerys Parry | 2011-02-01 | Current
17 | Consultation and on-going | HCA (capital funder) not happy with overall direction of project | High | Low |  | HCA have reconfirmed support for scheme. Maintain communications with HCA. Follow up visit on 10th May 2011 | Prevention | Project Team | Nerys Parry | 2011-06-01 | Current
18 | Consultation and on-going | Resistance from residents, businesses and public | Medium | Medium |  | Contractor has registered with Considerate Contractors Scheme. Further communications to be planned. | Prevention/ Reduction | Project Team | Paul Quinney | 2010-08-26 | Current
19 | Consultation and on-going | Input/participation and good relationship with gallery users and wider visual arts sector | Medium | Medium |  | Maintain on-going consultation and comms with current or other potential gallery users to ensure their views are represented. Commitment of gallery provision being established. Following appointment of Arts Director to programming activity has commenced with potential to include shop within Gallery. Probablity of risk being realised remains Medium | Prevention/ Reduction | Project Team | Paul Quinney | 2011-06-01 | Current