CEB Risk Register – Homelessness Revenue Allocation

| No. | Risk Description Link to Corporate Obj | Gross Risk | Cause of Risk | Mitigation | Net Risk | Further Management of Risk: Transfer/Accept/Reduce/Avoid | Monitoring Effectiveness | Current Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Score Impact Score: 1 =Insignificant; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Catastrophic Probability Score: 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost Certain |
| 1. | Reduction in funding to homelessness services due to cuts to the Supporting People budget | 4 | 4 | Cuts to the Supporting People budget | On-going input at SP commissioning body. Withholding a significant allocation of the Preventing Homelessness grant to potentially cover essentially gaps | 2 | 2 | Action: Reduce. Action Owner: Shaibur Rahman Mitigating Control: Reduce Control Owner: Shaibur Rahman | Outcome required: Funding guaranteed. Milestone Date: 1st April 2012 | Q 1 | Q 2 | Q 3 | Q4 | I | P |
| 2. | Inability to spend the large amount of unallocated funding | 3 | 3 | Money is being held back pending SP budget settlement. | Should SP budget not be cut then there is a list of areas of development in the single homeless field that needs addressing | 2 | 2 | Action: Reduce. Action Owner: Shaibur Rahman Mitigating Control: Reduce Control Owner: Shaibur Rahman | Outcome required: Funding allocated. Milestone Date: March 2013 |  |  |  |  |  |  |