## Planned Maintenance Schedule
CORPORATE ASSETS ~ 2012/2013 PLANNED MAINTENANCE PROGRAMME
Scoring
|  |  |  | Critical |  | over £75k |  | 15 |  |  | Grade I | 10
|  |  |  | Essential |  | £50k - £75k |  | 10 |  |  | Grade II* | 7
|  |  |  | High |  | £25k - £50k |  | 7 |  |  | Grade II | 5
|  |  |  | Moderate |  | £10k - £25k |  | 5
|  |  |  | Minimal |  | under £10k |  | 3
UPRN | Repair | Cat'gy | Property | Work Required | Rental Income |  | Asset Management Plan Building Categoisation | Building prioritization | [5 empty] | Project prioritization | [8 empty] | Annual Costs | Five Year Plan - Year and Estimated Cost |  |  |  |  | Year Six and Beyond |  | Backlog - |  | Comments |  |  | Five Year Plan - Year and estimated Cost (From Jan 07) |  |  |  |  | Backlog - |  |  |  | Annual Costs |  | Funding in 2010/11 Capital Programme |  | Capital programme funding | [12 empty] | Comments
[48 empty] | TOTALS | 1122500 | 2000000 |  | 1400000 | 1400000 | 600000 | 600000 | 260500 | 329000 | 330500 | 353500 | 303000 | 269500
| Liability |  |  |  |  | Running Yield |  | Commercial | Civic | Operational | Community | Listed Building | TOTAL | Legal / Statutory / Contractual | Health and safetey | Improvement / Repair | Project importance / Significance | TOTAL | BUILDING & PROJECT TOTAL (Multiplication) | BUILDING & PROJECT TOTAL (Addition) | Building Grading (A-D) | Project Grading (1-4) | (Recurring) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year | Cost | Total Cost | Capital / Revenue |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total Cost | Capital / Revenue | Allocated budget | Cumulative total | Planned | Reactive |  | 6453200 | Year 1 (2011/12) | 2012/2013 | Direct Services work | Year 3 2013/14) | Year 4 (2014/15) | Year 5 (2015/16) | Year 6 (2016/17) | Year 5 (2015/16) | Year 6 (2016/17) | Year 7 (2017/18) | Year 8 (2018/19) | Year 9 (2019/20) | Year 10 (2020/21)
[13 empty] | 0 |  |  |  |  | 0 |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
H187 | CE* | A | Titup Hall Drive (Housing Office) | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 | [5 empty] | 1500 |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 1545 | 1545 | R
| CI | A | Ramsay House | Reactive Maintenance & Minor Repair | [5 empty] | 15 |  |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | B | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
| CI | A | Ramsay House | Replacement Comfort Cooling Plant | [5 empty] | 15 |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | B | 3 | [16 empty] | 30000 |  | 30000 | C |  | 0 | [5 empty] | 175000 | [11 empty] | Part of Office for the Future?
| CI | A | Ramsay House | Services Maintenance | [5 empty] | 15 |  |  | 15 |  |  |  |  | 0 | 0 | 15 | B | 2 | 8000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E036 | C | A | Broad Street, 15 (Tourist Information Centre) | External refurbishments |  |  | A | 3 |  | 7 |  | 5 | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R |  |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 20000 | [6 empty] | 20000 |  |  | 20000 |  | 5000 |  | Recurring cost (Main building) every 5 years Recurring cost (shop front ) every 2/3 years
| C | A | Administration Buildings | Lift Alarms |  |  | A |  |  | 15 |  |  | 15 |  | 7 |  | 7 | 14 | 210 | 29 | ---- | 2 |  | 4000 | [6 empty] | 4000 | R |  |  | 1 | 4120 | 0 | 0 | 0 | 0 | 4120 | R | [5 empty] | 25000 | 20000 | 5000
E220 | C | A | Osney Lane, 14 - Main building | Reactive Maintenance & Minor Repair | [5 empty] | 7 |  |  | 7 | 15 | 15 |  | 15 | 45 | 315 | 52 | B | 2 | 1500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E036 | C | A | Broad Street, 15 (Tourist Information Centre) | Automatic Entrance Doors |  |  | A | 3 |  | 7 |  | 5 | 15 | 7 |  |  | 7 | 14 | 210 | 29 | B | 2 | [15 empty] | 10000 |  |  | 10000 | C | [5 empty] | 15000
R050 |  | A | Cutteslowe Park Offices | Replacement entrance doors |  |  | A |  |  | 10 |  |  | 10 |  |  | 5 | 15 | 20 | 200 | 30 | B | 1 |  | 3000 | [6 empty] | 3000 | R |  |  | 1 | 3090 | 0 | 0 | 0 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  | 3000
E220 | C | A | Osney Lane, 14 - Garages | Replace rainwater goods |  |  | C |  |  | 7 |  |  | 7 |  |  | 10 | 7 | 17 | 119 | 24 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | C |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | C | [5 empty] | 2000 | [5 empty] | 2000
E220 | C | A | Osney Lane, 14 - Main building | External refurbishments |  |  | C |  |  | 7 |  |  | 7 |  |  | 10 | 7 | 17 | 119 | 24 | B | 2 |  | 15000 | [6 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 15450 | 0 | 0 | 0 | 0 | 15450 | R | [5 empty] | 12500 | [5 empty] | 12500 |  |  |  |  | 12500 |  |  | Recurring cost every 5 years
E220 | C | A | Osney Lane, 14 - Main building | Roof Repairs |  |  | C |  |  | 7 |  |  | 7 |  |  | 10 | 7 | 17 | 119 | 24 | B | 1 |  | 10000 | [6 empty] | 10000 | R |  |  | 1 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 | [5 empty] | 2000
E220 | C | A | Osney Lane, 14 - Garages | Door repairs |  |  | C |  |  | 7 |  |  | 7 |  |  | 7 | 7 | 14 | 98 | 21 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000
R050 |  | A | Cutteslowe Park Offices | Reactive Maintenance & Minor Repair | [5 empty] | 10 |  |  | 10 | 15 | 15 |  | 15 | 45 | 450 | 55 | B | 2 | 1500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E220 | C | A | Osney Lane, 14 - Garages | External refurbishments |  |  | C |  |  | 7 |  |  | 7 |  |  | 7 | 7 | 14 | 98 | 21 | B | 2 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2000 | [5 empty] | 2000
E220 | C | A | Osney Lane, 14 - Garages | Replace asbestos cement roof sheets |  |  | C |  |  | 7 |  |  | 7 |  |  | 7 | 7 | 14 | 98 | 21 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 3 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [5 empty] | 5000 | [5 empty] | 5000
E220 | C | A | Osney Lane, 14 - Main building | Masonry repairs |  |  | C |  |  | 7 |  |  | 7 |  |  | 7 | 7 | 14 | 98 | 21 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000
| C | A | Administration Buildings | Signs |  |  | A |  |  | 15 |  |  | 15 |  |  |  | 5 | 5 | 75 | 20 | ---- | 3 |  | 10000 | [6 empty] | 10000 | R |  |  | 4 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 | [6 empty] | 15000
R050 |  | A | Cutteslowe Park Offices | External refurbishments |  |  | A |  |  | 10 |  |  | 10 |  |  |  | 5 | 5 | 50 | 15 | B | 2 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  | 2000 |  |  | 2500 | [6 empty] | Recurring cost every 5 years
E036 | C | A | Broad Street, 15 (Tourist Information Centre) | Reactive Maintenance & Minor Repair |  |  |  | 3 |  | 7 |  | 5 | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | B | 1 | 1500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0
E036 | C | A | Broad Street, 15 (Tourist Information Centre) | Services Maintenance |  |  |  | 3 |  | 7 |  | 5 | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | B | 1 | 2500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0
E027 | C | A | Blue Boar Street Offices | External refurbishments | [5 empty] | 15 |  |  | 15 |  |  |  | 7 | 7 | 105 | 22 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [19 empty] | Recurring cost every 5 years
E027 | C | A | Blue Boar Street Offices | Fire Alarm Alterations | [5 empty] | 15 |  |  | 15 |  |  |  | 5 | 5 | 75 | 20 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R |  |  | 4 | 0 | 0 | 15450 | 0 | 0 | 15450 | R
E027 | C | A | Blue Boar Street Offices | Ground Floor - Staff Access Door | [5 empty] | 15 |  |  | 15 |  |  |  | 3 | 3 | 45 | 18 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 4 | 0 | 0 | 0 | 5150 | 0 | 5150 | R
E027 | C | A | Blue Boar Street Offices | Heating System - Additional Boiler Capacity | [5 empty] | 15 |  |  | 15 |  |  |  | 3 | 3 | 45 | 18 | B | 3 |  |  |  | 12000 |  |  |  |  | 12000 | C |  |  | 3 | 0 | 0 | 15000 | 0 | 0 | 15000 | C
E027 | C | A | Blue Boar Street Offices | Pigeon Netting | [5 empty] | 15 |  |  | 15 |  |  |  | 5 | 5 | 75 | 20 | B | 2 |  | 2000 | [6 empty] | 2000 | R |  |  | 4 | 2060 | 0 | 0 | 0 | 0 | 2060 | R
E027 | C | A | Blue Boar Street Offices | Reactive Maintenance & Minor Repair | [5 empty] | 15 |  |  | 15 |  |  |  |  | 0 | 0 | 15 | B | 2 | 4500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0
E027 | C | A | Blue Boar Street Offices | Roof Access Ladders | [5 empty] | 15 |  |  | 15 |  | 5 |  |  | 5 | 75 | 20 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R
E027 | C | A | Blue Boar Street Offices | Services Maintenance | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 | 4500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0
E027 | C | A | Blue Boar Street Offices | Window Draught Proofing | [5 empty] | 15 |  |  | 15 |  |  |  | 7 | 7 | 105 | 22 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 4 | 0 | 0 | 10300 | 0 | 0 | 10300 | R
H006 | CE* | A | Ashhurst Way, 60 (Housing Office) | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  |  | 5 | 5 | 25 | 10 | B | 3 |  |  |  |  | 5500 |  |  |  | 5500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5665 | 0 | 5665 | R | [5 empty] | 5000 | [6 empty] | 5000 | [6 empty] | Recurring cost every 5 years
| C | A | Administration Buildings | Electrical Testing | [5 empty] | 15 |  |  | 15 |  | 15 |  | 15 | 30 | 450 | 45 | ---- | 1 | 15000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 | 20000
E071 | CI | A | Clarendon House | Lease Termination Dilapidation Claim | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 2 |  |  |  | 100000 |  |  |  |  | 100000 | R |  |  | 1 | 0 | 0 | 103000 | 0 | 0 | 103000 | R
H064 | CE* | A | Cuddesdon Way (Housing Office) | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  |  | 5 | 5 | 25 | 10 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [5 empty] | 1500 |  |  |  |  | 1500 | [8 empty] | Still operational?
| C | A | Administration Buildings | Water Tank Cleaning and Maintenance | [5 empty] | 15 |  |  | 15 |  | 15 |  | 15 | 30 | 450 | 45 | ---- | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 | 10000
|  |  | Miscellaneous Admin Buildings | [41 empty] | 30000 | 0 | 0 | 128000 | 20000 | 180000 |  | 5000 | 1500 | 33500 | 42500 | 0 | 0 | 20000 | 12500 | 5000 | 0
E052 | CE | BKH | Bury Knowle House | Conservatory timberwork repairs | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 15 | 10 | 25 | 500 | 45 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | 10000 | 10000 |  |  |  | 5000 | 5000
E052 | CE | BKH | Bury Knowle House | External refurbishment | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 15 | 10 | 25 | 500 | 45 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 20600 | 0 | 0 | 20600 | R | 10000 | 20000 |  |  |  | 25000 | 30000 | [6 empty] | 25000 |  |  |  | 25000
E052 | CE | BKH | Bury Knowle House | Roof Repairs | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 10 | 15 | 25 | 500 | 45 | B | 2 |  |  | 2000 | [5 empty] | 2000 | C |  |  | 3 | 0 | 10000 | 0 | 0 | 0 | 10000 | C | [5 empty] | 15000 | 15000
E052 | CE | BKH | Bury Knowle House | Replacement rainwater goods | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 10 | 7 | 17 | 340 | 37 | B | 3 |  |  | 7500 | [5 empty] | 7500 | C |  |  | 2 | 0 | 10000 | 0 | 0 | 0 | 10000 | C | [5 empty] | 10000 | 5000
E052 | CE | BKH | Bury Knowle House | External Stonework Repairs | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 10 | 5 | 15 | 300 | 35 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 20600 | 0 | 0 | 20600 | C | [5 empty] | 25000 | 35000
E052 | CE | BKH | Bury Knowle House | Parking Improvements | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 5 | 3 | 8 | 160 | 28 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 4 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 2500 | [5 empty] | 2500
E052 | CE | BKH | Bury Knowle House | Internal refurbishment | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  | 3 | 3 | 6 | 120 | 26 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every7 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 | [6 empty] | 5000 | Recurring cost every7 years
E054 | CE | BKH | Bury Knowle Stables - Barn | Major refurbishment |  |  | D |  |  | 5 |  |  | 5 |  |  | 7 | 5 | 12 | 60 | 17 | C | 1 |  |  |  | 200000 |  |  |  |  | 200000 | C |  |  | 3 | 0 | 0 | 206000 | 0 | 0 | 206000 | C | [5 empty] | 100000 | [6 empty] | 95000
E054 | CE | BKH | Bury Knowle Stables - Stable block | External refurbishments |  |  | D |  |  | 5 |  |  | 5 |  |  | 7 | 5 | 12 | 60 | 17 | C | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 1500 | [6 empty] | 1500 | [6 empty] | Recurring cost every 5 years
E054 | CE | BKH | Bury Knowle Stables - Stable block | Replacement rainwater goods |  |  | D |  |  | 5 |  |  | 5 |  |  | 3 | 3 | 6 | 30 | 11 | C | 3 |  |  |  | 2000 |  |  |  |  | 2000 | C |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | C | [5 empty] | 500 | [6 empty] | 500
E052 | CE | BKH | Bury Knowle House | Reactive Maintenance & Minor Repair | 16300 | 12.07% |  | 5 |  | 10 |  | 5 | 20 | 15 | 15 |  | 15 | 45 | 900 | 65 | B | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E054 | CE | BKH | Bury Knowle Stables - Stable block | Roof repairs |  |  | D |  |  | 5 |  |  | 5 |  |  | 3 | 3 | 6 | 30 | 11 | C | 3 |  |  |  | 3000 |  |  |  |  | 3000 | C |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | C | [5 empty] | 1000 | [6 empty] | 2000
E052 | CE | BKH | Bury Knowle House | Entrance Access Works | 16300 | 12.07% | B | 5 |  | 10 |  | 5 | 20 |  |  |  |  | 0 | 0 | 20 | B | 2 |  |  |  | 30000 |  |  |  |  | 30000 | R |  |  | 3 | 0 | 0 | 30900 | 0 | 0 | 30900 | R | [5 empty] | 50000 | [13 empty] | County County responsibility
E052 | CE | BKH | Bury Knowle House | Services Maintenance | 16300 | 12.07% |  | 5 |  | 10 |  | 5 | 20 | 15 | 15 |  | 15 | 45 | 900 | 65 | B | 2 | 2000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Bury Knowle House | [41 empty] | 0 | 0 | 0 | 240500 | 90000 | 0 |  | 0 | 0 | 7500 | 99000 | 25000 | 0 | 0 | 0 | 25000 | 5000
E298 | C | CC | Barton Centre | Reactive Maintenance & Minor Repair | [5 empty] | 5 | 15 |  | 20 | 15 | 15 |  | 15 | 45 | 900 | 65 | B | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E298 | C | CC | Barton Centre | Services Maintenance | [5 empty] | 5 | 15 |  | 20 | 15 | 15 |  | 15 | 45 | 900 | 65 | B | 2 | 4000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  | CC | Community Centre | Reactive Maintenance & Minor Repair | [6 empty] | 15 |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | ---- | 2 | 100000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  | CC | Community Centre | Services maintenance | [6 empty] | 15 |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | ---- | 2 | 30000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
R098 | CES | CC | Asian Cultural Centre | External refurbishment and repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R |  | 3500 | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [5 empty] | 5000 |  |  | Recurring cost every 5 years
E188 | CES | CC | South Oxford Community Centre | DDA Access lift | [6 empty] | 15 |  | 15 | 15 |  |  | 15 | 30 | 450 | 45 | B | 2 |  |  | 40000 | [5 empty] | 40000 | C |  |  | 4 | 0 | 41200 | 0 | 0 | 0 | 41200 | C |  | 0 |  |  | 67314 | [14 empty] | Order placed
R098 | CES | CC | Asian Cultural Centre | Minor repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 5 | 12 | 180 | 27 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R |  |  | 1 | 0 | 0 | 1545 | 0 | 0 | 1545 | R | [5 empty] | 5000 |  |  |  |  | 5000
R098 | CES | CC | Asian Cultural Centre | Seal main hall floor |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 5 | 12 | 180 | 27 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2500 |  |  |  |  | 2500 | [7 empty] | 2500 | Recurring cost every 7 years
R098 | CES | CC | Asian Cultural Centre | Water storage tank modifications |  |  | A |  |  |  | 15 |  | 15 |  | 7 |  | 7 | 14 | 210 | 29 | B | 3 |  |  | 1500 | [5 empty] | 1500 | R |  |  | 1 | 0 | 1545 | 0 | 0 | 0 | 1545 | R | [5 empty] | 2000 |  |  |  |  | 2000
E298 | C | CC | Barton Centre | Cycle Stands and Car Park Repairs |  |  | A |  |  | 5 | 15 |  | 20 |  |  | 5 | 3 | 8 | 160 | 28 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 3 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 1500 | [6 empty] | 1500
E298 | C | CC | Barton Centre | Entrance Foyer Refurbishment |  |  | A |  |  | 5 | 15 |  | 20 |  |  | 3 | 5 | 8 | 160 | 28 | B | 3 | [5 empty] | 15000 |  |  | 15000 | R |  |  | 3 | 0 | 0 | 0 | 0 | 15450 | 15450 | R | [5 empty] | 15000 | [6 empty] | 15000
E298 | C | CC | Barton Centre | External refurbishments |  |  | A |  |  | 5 | 15 |  | 20 |  |  | 10 | 7 | 17 | 340 | 37 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 10000 | 10000 | [7 empty] | 10000 |  |  |  |  | Recurring cost every 5 years
E298 | C | CC | Barton Centre | Seal hall floor |  |  | A |  |  | 5 | 15 |  | 20 |  |  | 5 | 5 | 10 | 200 | 30 | B | 3 |  |  |  | 4000 |  |  |  |  | 4000 | R |  |  | 1 | 0 | 0 | 4120 | 0 | 0 | 4120 | R | [5 empty] | 3000 | [6 empty] | 3000
E298 | C | CC | Barton Centre | Sports Hall Reglazing |  |  | A |  |  | 5 | 15 |  | 20 |  |  | 5 | 7 | 12 | 240 | 32 | B | 1 |  | 10000 | [6 empty] | 10000 | R |  |  | 3 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 | [6 empty] | 15000
R123 | CES | CC | Bullingdon Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  | 10000 | ü | [7 empty] | 10000 |  |  | Recurring cost every 5 years
R123 | CES | CC | Bullingdon Community Centre | Replace roof covering |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 20000 |  |  |  | 20000 | R |  |  | 3 | 0 | 0 | 0 | 20600 | 0 | 20600 | R | [5 empty] | 20000 |  | 20000 | ü
R123 | CES | CC | Bullingdon Community Centre | Replacement windows |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 3 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  | 10000 | ü
R123 | CES | CC | Bullingdon Community Centre | Reseal floor and replace ceiling in main hall |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  |  | 7500 |  |  |  |  | 7500 | R |  |  | 1 | 0 | 0 | 7725 | 0 | 0 | 7725 | R | [5 empty] | 5000 |  | 5000
R175 | CES | CC | Cheney Community Centre | External refurbishments |  |  | A |  |  |  | 7 |  | 7 |  |  | 3 | 5 | 8 | 56 | 15 | A | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years | 329500 | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 2500 | [6 empty] | 2500 | [6 empty] | Recurring cost every 5 years
R174 | CES | CC | Cutteslowe Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü | [6 empty] | 5000 |  |  |  | Recurring cost every 5 years
R174 | CES | CC | Cutteslowe Community Centre | Repalce roof coverings |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | C |  |  | 3 | 0 | 0 | 0 | 2060 | 0 | 2060 | C | [5 empty] | 3000 |  | 3000 | ü
R174 | CES | CC | Cutteslowe Community Centre | Reseal main hall floor |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 3 | [5 empty] | 1500 |  |  | 1500 | R |  |  | 1 | 0 | 0 | 0 | 0 | 1545 | 1545 | R | [5 empty] | 3000 |  | 3000 | [10 empty] | 3000 | Recurring cost every 7 years
R052 | C | CC | Cutteslowe Park Bowls Pavilion - Community Centre part | Extend at rear to enclose verandah |  |  | A |  |  |  | 15 |  | 15 |  |  | 3 | 5 | 8 | 120 | 23 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 20600 | 0 | 0 | 20600 | C | [5 empty] | 20000 |  |  |  | 20000
R156 | CES | CC | Donnington Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | C | 2 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 | [9 empty] | Recurring cost every 5 years
R156 | CES | CC | Donnington Community Centre | Renew roof coverings |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | C | 2 |  |  | 20000 | [5 empty] | 20000 | C |  |  | 3 | 0 | 20600 | 0 | 0 | 0 | 20600 | C | [5 empty] | 75000 |  |  |  | 75000
R156 | CES | CC | Donnington Community Centre | Replace rainwater goods |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | C | 2 |  |  | 2000 | [5 empty] | 2000 | C |  |  | 3 | 0 | 2060 | 0 | 0 | 0 | 2060 | C | [5 empty] | 2500 |  |  |  | 2500 | [9 empty] | Included with budget for roof replacement
R179 | CES | CC | East Oxford Community Centre | DDA Access lift |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  | 10 | 25 | 375 | 40 | B | 2 |  |  | 30000 | [5 empty] | 30000 | C |  |  | 4 | 0 | 30900 | 0 | 0 | 0 | 30900 | C |  | 0 |  |  |  | 65000 | 115000 | [12 empty] | Included in draft capital programme for 2011/12
R179 | CES | CC | East Oxford Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  |  | 25000 |  |  |  | 25000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 25750 | 0 | 25750 | R | [5 empty] | 25000 |  |  |  |  | 25000 | [6 empty] | 25000 |  | Recurring cost every 5 years
R179 | C | CC | East Oxford Community Centre | Renew heating system |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 | [5 empty] | 30000 |  |  | 30000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 30900 | 30900 | C | [5 empty] | 75000 |  |  |  |  | 75000
R179 | CES | CC | East Oxford Community Centre | Replace windows |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 30000 | 30000 | 30000 |  |  | 90000 | C |  |  | 3 | 0 | 0 | 30900 | 30900 | 30900 | 92700 | C | [5 empty] | 100000 |  |  |  |  | 100000
R179 | CES | CC | East Oxford Community Centre | Rewire building |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 50000 |  |  |  |  | 50000 | C |  |  | 3 | 0 | 0 | 51500 | 0 | 0 | 51500 | C | [5 empty] | 50000 |  |  |  |  | 50000
R035 | C | CC | East Oxford Games Hall | DDA works |  |  | C |  |  |  | 7 |  | 7 | 7 |  |  | 7 | 14 | 98 | 21 | B | 2 |  |  | 18000 | [5 empty] | 18000 | C |  |  | 4 | 0 | 18540 | 0 | 0 | 0 | 18540 | C | [5 empty] | 25000 | [6 empty] | 25000
R035 | C | CC | East Oxford Games Hall | External refurbishments |  |  | A |  |  |  | 7 |  | 7 |  |  | 10 | 7 | 17 | 119 | 24 | C | 2 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 15000 | [6 empty] | 15000 | [6 empty] | Recurring cost every 5 years
R035 | C | CC | East Oxford Games Hall | Masonry repairs |  |  | A |  |  |  | 7 |  | 7 |  |  | 10 | 7 | 17 | 119 | 24 | C | 2 |  |  | 15000 | [5 empty] | 15000 | R |  |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 | [6 empty] | 15000
R035 | C | CC | East Oxford Games Hall | Replace asbestos cement roof sheets |  |  | C |  |  |  | 7 |  | 7 |  |  | 7 | 3 | 10 | 70 | 17 | C | 2 |  |  | 50000 | [5 empty] | 50000 | C |  |  | 3 | 0 | 51500 | 0 | 0 | 0 | 51500 | C | [5 empty] | 50000 | [6 empty] | 50000
R061 | CES | CC | Ferry Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 15 | 25 | 375 | 40 | A | 4 | [5 empty] | 10000 |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 10300 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000 |  |  |  | 10000 |  |  |  |  | Recurring cost every 5 years
R037 | CES | CC | Florence Park Community Centre - All | Alterations to amalgamate with Bowls Club |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  |  | 15000 |  |  |  | 15000 | C |  | 81000 | 3 | 0 | 0 | 0 | 15450 | 0 | 75000 | C | [5 empty] | 50000 | [5 empty] | 50000
R037 | CES | CC | Florence Park Community Centre - All | Replace rainwater goods |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | C |  | 66000 | 3 | 0 | 0 | 0 | 2060 | 0 | 2060 | C | [5 empty] | 3000 | [5 empty] | 3000 | [7 empty] | Included with budget for roof replacement
R037 | CES | CC | Florence Park Community Centre - Bowls Club part | External refurbishments |  |  | A |  |  |  | 5 |  | 5 |  |  | 5 | 15 | 20 | 100 | 25 | C | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 3000 | [5 empty] | 3000 | [5 empty] | 3000 |  | Recurring cost every 5 years
R037 | CES | CC | Florence Park Community Centre - Bowls Club part | Replacement roof |  |  | A |  |  |  | 5 |  | 5 |  |  | 5 | 15 | 20 | 100 | 25 | C | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 50000 | C | [5 empty] | 50000 | [5 empty] | 50000 | [7 empty] | Recurring cost every 5 years
R037 | CES | CC | Florence Park Community Centre - Community Centre part | External refurbishments |  |  | A |  |  |  | 5 |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 3000 | [5 empty] | 3000 | [5 empty] | 3000 |  | Recurring cost every 5 years
R037 | CES | CC | Florence Park Community Centre - Community Centre part | Replace ceiling in main hall |  |  | A |  |  |  | 5 |  | 5 |  |  | 5 | 7 | 12 | 60 | 17 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 3 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 3000 | [5 empty] | 3000
R037 | CES | CC | Florence Park Community Centre - Community Centre part | Replace roof covering |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  |  |  | 15000 |  |  |  | 15000 | C |  | 80000 | 3 | 0 | 0 | 0 | 15450 | 0 | 15450 | C | [5 empty] | 75000 | [5 empty] | 75000
R075 | CES | CC | Headington Community Centre | DDA platform lift |  |  | A |  |  |  | 15 |  | 15 | 10 |  |  | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | C |  |  | 4 | 0 | 0 | 15450 | 0 | 0 | 15450 | C | [5 empty] | 15000 | 15000
R075 | CES | CC | Headington Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 | [5 empty] | 10000 |  |  |  | Recurring cost every 5 years
R075 | CES | CC | Headington Community Centre | Roof repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R |  |  | 3 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 5000 |  |  |  | 5000
R031 | CES | CC | Jericho Community Centre | DDA Improvements |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  |  | 15 | 225 | 30 | C | 2 |  |  | 16500 | [5 empty] | 16500 | C |  | 416000 | 4 | 0 |  | 0 | 0 | 0 | 0 | C
R031 | CES | CC | Jericho Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | C | 3 | [5 empty] | 15000 |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 15450 | 15450 | R | [5 empty] | 15000 |  |  |  |  | 15000 | [6 empty] | 15000 |  | Recurring cost every 5 years
H161 | CES | CC | Jubilee 77 Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 2 |  |  |  |  | 3000 |  |  |  | 3000 | R |  |  | 3 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 2500 |  |  |  | 2500 | [5 empty] | 2500 |  |  |  | Recurring cost every 4 years
H083 | CES | CC | Littlemore Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 3 | [8 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 5000 | 0 | 5000 | R | [5 empty] | 5000 |  |  |  | 5000 | [6 empty] | 5000 |  |  | Recurring cost every 5 years
H118 | CE | CC | Maltfield Road Nursery (Playbase) | Externall repairs and refurbishment |  |  | A |  |  |  | 10 |  | 10 |  |  | 3 | 7 | 10 | 100 | 20 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 | [6 empty] | 10000
H118 | CE | CC | Maltfield Road Nursery (Playbase) | Replacement windows |  |  | A |  |  |  | 10 |  | 10 |  |  | 3 | 7 | 10 | 100 | 20 | B | 2 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 3 | 0 |  | 0 | 0 | 0 | 0 | C
R021 | CES | CC | Blackbird Leys Community Centre | Rewire building | [5 empty] | 5 | 15 |  | 20 |  | 10 |  |  | 10 | 200 | 30 | B | 2 |  |  | 25000 | [5 empty] | 25000 | C |  |  | 3 | 0 | 25750 | 0 | 0 | 0 | 25750 | C |  |  |  |  | 25000 | [14 empty] | Order placed
E219 | CE | CC | Northway Community Centre | External refurbishments |  |  | D |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 7500 | [6 empty] | 7500 |  |  |  |  | 7500 |  | Recurring cost every 5 years
E219 | CE | CC | Northway Community Centre | Platform lift |  |  | D |  |  |  | 15 |  | 15 | 15 |  |  | 15 | 30 | 450 | 45 | B | 2 |  | 17000 | [6 empty] | 17000 | C |  |  | 4 | 17510 | 0 | 0 | 0 | 0 | 15000 | C | 15000 | 15000 |  |  |  | 15000 | [6 empty] | 15000 | [6 empty] | Site to be redeveloped
E219 | CE | CC | Northway Community Centre | Repairs to roof covering |  |  | D |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 3 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 | [6 empty] | 10000
E217 | C | CC | Northway Sports Centre | External refurbishments |  |  | D |  |  |  | 7 |  | 7 |  |  | 3 | 3 | 6 | 42 | 13 | C | 3 |  |  | 7500 | [5 empty] | 7500 | R | Recurring cost every 5 years |  | 1 | 0 | 7725 | 0 | 0 | 0 | 7725 | R | [5 empty] | 7500 | [6 empty] | 7500 | [6 empty] | Recurring cost every 5 years
R130 | CES | CC | Regal Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 7500 |  |  |  | 7500 | [6 empty] | 7500 |  |  | Recurring cost every 5 years
R130 | CES | CC | Regal Community Centre | Replace ceiling in main hall |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | B | 3 |  |  |  |  | 4000 |  |  |  | 4000 | R |  |  | 3 | 0 | 0 | 0 | 4120 | 0 | 4120 | R | [5 empty] | 5000 |  |  |  | 5000
R130 | CES | CC | Regal Community Centre | Replacement doors |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | C |  |  | 3 | 0 | 0 | 0 | 2060 | 0 | 2060 | C | [5 empty] | 5000 |  |  |  | 5000
R093 | CES | CC | Risinghurst Community Centre | Brickwork repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 2 |  |  |  | 1000 |  |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 1000 | [6 empty] | 1000
R093 | CES | CC | Risinghurst Community Centre | DDA Improvements |  |  | A |  |  |  | 15 |  | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 2 |  |  | 8500 | [5 empty] | 8500 | C |  |  | 4 | 0 | 8755 | 0 | 0 | 0 | 8755 | C | [5 empty] | 10000 | 10000
R093 | CES | CC | Risinghurst Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 2 |  |  |  | 15000 |  |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 15000 | 12500 | [8 empty] | 15000 |  |  |  | Recurring cost every 5 years
R093 | CES | CC | Risinghurst Community Centre | Renew roof coverings |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 2 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 1 | 0 | 0 | 20600 | 0 | 0 | 20600 | C | [5 empty] | 50000 | 50000
R093 | CES | CC | Risinghurst Community Centre | Replacement doors and windows |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 2 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 6000 | 60000
R093 | CES | CC | Risinghurst Community Centre | Rewire building |  |  | A |  |  |  | 15 |  | 15 |  | 10 |  | 10 | 20 | 300 | 35 | B | 2 |  |  |  | 12000 |  |  |  |  | 12000 | C |  |  | 3 | 0 | 0 | 12360 | 0 | 0 | 12360 | C | [5 empty] | 15000
R114 | CES | CC | Rose Hill Community Centre | DDA Improvements |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  | 7 | 22 | 330 | 37 | C | 2 |  |  | 6500 | [5 empty] | 6500 | C |  |  | 4 | 0 | 6695 | 0 | 0 | 0 | 6695 | C |  | 0 |  |  |  | 50000 |  | 50000 | [11 empty] | To be included with section 106 refurbishment
E188 | CES | CC | South Oxford Community Centre | Upgrade toilets | [6 empty] | 15 |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | B | 2 |  | 10000 | [6 empty] | 10000 | C |  |  | 3 |  | 0 | 0 | 0 | 0 | 0 | C
R114 | CES | CC | Rose Hill Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  | 15000 | [5 empty] | 15000 | R |  |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | [8 empty] | 15000 |  |  | Recurring cost every 5 years
R114 | CES | CC | Rose Hill Community Centre | Renew ceiling |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | C | 3 |  |  |  | 2500 |  |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 2575 | 0 | 0 | 2575 | R | [5 empty] | 2500 |  | 2500
R114 | CES | CC | Rose Hill Community Centre | Renew roof coverings |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | C | 3 |  |  |  | 17000 |  |  |  |  | 17000 | C |  |  | 3 | 0 | 0 | 17510 | 0 | 0 | 17510 | C | [5 empty] | 30000 |  | 30000
R114 | CES | CC | Rose Hill Community Centre | Repair / overhaul windows |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | C | 3 |  |  |  | 4000 |  |  |  |  | 4000 | R |  |  | 3 | 0 | 0 | 4120 | 0 | 0 | 4120 | R | [5 empty] | 25000 |  | 25000
R114 | CES | CC | Rose Hill Community Centre | Replace heating system |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 3 |  |  |  | 15000 |  |  |  |  | 15000 | C |  |  | 3 | 0 | 0 | 15450 | 0 | 0 | 15450 | C | [5 empty] | 75000 |  | 75000
R114 | CES | CC | Rose Hill Community Centre | Reseal floors |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | C | 3 |  |  |  | 2500 |  |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 2575 | 0 | 0 | 2575 | R | [5 empty] | 2000 |  | 2000
|  | CC | South Oxford Adventure Playground | DDA Improvements |  |  | A |  |  |  | 5 |  | 5 | 5 |  |  | 7 | 12 | 60 | 17 | C | 2 |  |  | 10500 | [5 empty] | 10500 | C |  |  | 4 | 0 | 25000 | 0 | 0 | 0 | 25000 | C | [5 empty] | 25000 | [6 empty] | 25000
E188 | CES | CC | South Oxford Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  | 15000 | [6 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 15450 | 0 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 | [6 empty] | 15000 |  |  |  | 15000 |  |  | Recurring cost every 5 years
E188 | CES | CC | South Oxford Community Centre | Repair stonework and brickwork |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R |  |  | 3 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 5000 |  | 5000 | ü
E188 | CES | CC | South Oxford Community Centre | Replace damaged concrete floors |  |  | A |  |  |  | 15 |  | 15 |  |  | 3 | 5 | 8 | 120 | 23 | B | 2 |  | 7500 | [6 empty] | 7500 | R |  |  | 3 | 7725 | 0 | 0 | 0 | 0 | 7725 | R | [5 empty] | 2500 |  | 2500 | ü
E188 | CES | CC | South Oxford Community Centre | Replace external doors |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü
E188 | CES | CC | South Oxford Community Centre | Replace windows |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 50000 |  | 25000 |  |  | 75000 | C |  |  | 3 | 0 | 0 | 51500 | 0 | 25750 | 77250 | C | [5 empty] | 75000 |  |  |  | 75000
E188 | CES | CC | South Oxford Community Centre | Rewire building |  |  | A |  |  |  | 15 |  | 15 |  | 10 |  | 10 | 20 | 300 | 35 | B | 2 |  |  | 75000 | [5 empty] | 75000 | C |  |  | 3 | 0 | 77250 | 0 | 0 | 0 | 77250 | C | [5 empty] | 75000 |  | 75000
E188 | CES | CC | South Oxford Community Centre | Waterproofing to walls |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 2 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 20600 | 0 | 0 | 20600 | C | [5 empty] | 15000 |  |  |  | 15000
R201 | CES | CC | West Oxford Community Centre | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | A | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years | 10000 | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 | [6 empty] | 5000 |  |  |  |  | 5000 |  | Recurring cost every 5 years
R201 | CES | CC | West Oxford Community Centre | Paving repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | A | 3 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 2500 | [6 empty] | 5000
|  |  | Community Centres | [41 empty] | 0 | 0 | 92314 | 1483500 | 272500 | 343000 |  | 237500 | 289500 | 187000 | 243000 | 0 | 20000 | 32500 | 57500 | 58500 | 5500
T004 | C | CD | All Saints Road Cleansing Depot | Boundary wall repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | 2 |  |  | 500 | [5 empty] | 500 | R |  |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [19 empty] | TO BE SOLD
T004 | C | CD | All Saints Road Cleansing Depot | External brickwork repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | 2 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [19 empty] | TO BE SOLD
T004 | C | CD | All Saints Road Cleansing Depot | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | 2 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [19 empty] | TO BE SOLD
T004 | C | CD | All Saints Road Cleansing Depot | Rainwater goods repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | 2 |  |  | 500 | [5 empty] | 500 | R |  |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [19 empty] | TO BE SOLD
T004 | C | CD | All Saints Road Cleansing Depot | Replace asbestos roof sheets | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | 2 |  |  | 2000 | [5 empty] | 2000 | C |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | C | [19 empty] | TO BE SOLD
|  |  | Cleansing Sub Depot | [41 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
E057 | C | CM | Carfax Tower | Internal refurbishment |  |  | A | 5 | 5 |  | 7 | 5 | 22 |  |  | 15 | 10 | 25 | 550 | 47 | B | 3 | 500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 |  |  |  | 2000 | 2000 |  |  |  | 2000 |  |  | 2000 |  | 2000 |  | 2000 |  | Recurring cost every 2 years
E057 | C | CM | Carfax Tower | Quarter Boys Rrefurbishment |  |  | A | 5 | 5 |  | 7 | 5 | 22 |  |  | 10 | 5 | 15 | 330 | 37 | B | 2 | [16 empty] | 10000 |  | 10000 | R | [5 empty] | 10000 |  | 10000
E057 | C | CM | Carfax Tower | Bell repairs |  |  | A | 5 | 5 |  | 7 | 5 | 22 |  |  | 5 | 7 | 12 | 264 | 34 | B | 2 |  |  |  |  | 15000 |  |  |  | 15000 | R |  |  | 1 | 0 | 0 | 0 | 15450 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000
E209 | C | CM | New Inn Court Yard - Lord Mayor's Garage | External refurbishments |  |  | A |  | 10 | 7 |  |  | 17 |  |  | 7 | 3 | 10 | 170 | 27 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R |  |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
E209 | C | CM | New Inn Court Yard - Lord Mayor's Garage | Replace asbestos cement roof sheets |  |  | A |  | 10 | 7 |  |  | 17 |  |  | 7 | 3 | 10 | 170 | 27 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R |  |  | 3 | 0 | 0 | 1545 | 0 | 0 | 1545 | R | [5 empty] | 2000 |  |  |  |  | 2000
E209 | C | CM | New Inn Court Yard - Parking Spaces | Resurfacing and other repairs |  |  | A |  |  | 7 |  |  | 7 |  |  | 7 | 10 | 17 | 119 | 24 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 7500 | 32500
E057 | C | CM | Carfax Tower | Reactive Maintenance & Minor Repair |  |  |  | 5 | 5 |  | 7 | 5 | 22 | 15 | 15 |  | 15 | 45 | 990 | 67 | B | 2 | 1000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Civic Miscellaneous | [41 empty] | 0 | 0 | 0 | 37000 | 34500 | 25000 |  | 500 | 4000 | 0 | 0 | 2000 | 0 | 2000 | 500 | 2000 | 0
E198 | CE | COV | Covered Market | Reactive Maintenance & Minor Repair | 978484 | 14.83% |  | 15 |  |  | 7 | 5 | 27 | 15 | 15 |  | 15 | 45 | 1215 | 72 | B | 1 | 25000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E198 | CE | COV | Covered Market | Services Maintenance | 978484 | 14.83% |  | 15 |  |  | 7 | 5 | 27 | 15 | 15 |  | 15 | 45 | 1215 | 72 | B | ---- | 15000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E198 | CE | COV | Covered Market | Internal refurbishment | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 15 | 15 | 30 | 810 | 57 | B | 3 |  | 20000 | 20000 | 20000 | 20000 | 20000 |  |  | 100000 | R |  |  | 3 | 20600 | 20600 | 20600 | 20600 | 20600 | 103000 | R | 50000 | 50000 |  |  |  | 25000 | 25000 | 25000 | ü |  | 25000 |  |  |  | 25000 |  | 25000 |  | 25000 | Recurring cost every 2 years
E198 | CE | COV | Covered Market | External Joinery Repairs and refurbishment | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 15 | 10 | 25 | 675 | 52 | B | 2 |  |  | 15000 | 20000 | 20000 |  |  |  | 55000 | R | Recurring cost every 5 years |  | 1 | 0 | 15450 | 20600 | 20600 | 0 | 56650 | R |  | 50000 |  |  |  | 25000 | 25000 | [6 empty] | 25000 |  |  |  | 25000 |  | Recurring cost every 4 years
E198 | CE | COV | Covered Market | Flat Roof Repairs and Resurfacing | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 15 | 10 | 25 | 675 | 52 | B | 2 |  |  | 15000 | [5 empty] | 15000 | C |  |  | 3 | 0 | 15450 | 0 | 0 | 0 | 15450 | C |  | 50000 |  |  | 25000 | 15000 | 15000 |  |  |  | 7500 |  |  | 7500 |  | 7500 |  | 7500 |  | Recurring cost
E198 | CE | COV | Covered Market | Sprinkler System refurbishment and Repair | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 15 | 10 | 25 | 675 | 52 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 3 | 0 | 0 | 3090 | 0 | 0 | 3090 | R |  | 50000 |  |  |  | 10000 | [8 empty] | 10000 |  |  |  | 10000 | Recurring cost every 4 years
E198 | CE | COV | Covered Market | General Roof Repairs | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 15 | 5 | 20 | 540 | 47 | B | 2 |  | 10000 | 10000 | 10000 | 10000 | 10000 |  |  | 50000 | C |  |  | 2 | 10300 | 10300 | 10300 | 10300 | 10300 | 51500 | C |  | 50000 |  |  |  | 10000 | 20000 |  |  | 10000 | 10000 |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | Annual cost
E198 | CE | COV | Covered Market | Avenue Paving Repairs | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 3 | 15 | 18 | 486 | 45 | B | 2 |  |  |  | 20000 | 20000 | 20000 |  |  | 60000 | R |  |  | 3 | 0 | 0 | 20600 | 20600 | 20600 | 61800 | R | [5 empty] | 20000 |  |  |  | 20000
E198 | CE | COV | Covered Market | Market Trader's Toilets Refurbishment | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 3 | 15 | 18 | 486 | 45 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R |  |  | 3 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 5000 |  |  |  | 5000 |  |  |  |  | 5000 |  |  | 5000 |  | Recurring cost every 3 years
E198 | CE | COV | Covered Market | Replace Asbestos Cement Roof Sheets | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 7 | 10 | 17 | 459 | 44 | B | 2 |  | 10000 | 15000 | 15000 |  |  |  |  | 40000 | C |  |  | 3 | 10300 | 15450 | 15450 | 0 | 0 | 41200 | C | [5 empty] | 60000 | 30000
E198 | CE | COV | Covered Market | Security Improvements | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 7 | 10 | 17 | 459 | 44 | B | 3 |  | 10000 | [6 empty] | 10000 | R |  |  | 4 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  | 5000
E198 | CE | COV | Covered Market | Avenue Internal Cleaning | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 5 | 10 | 15 | 405 | 42 | B | 3 | 10000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R | [5 empty] | 10000 | 10000 | 10000 | ü | 10000 | 10000 | 10000 |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | Annual cost
E198 | CE | COV | Covered Market | High Level Louvres Repair / Replacement | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 10 | 5 | 15 | 405 | 42 | B | 3 |  |  |  |  | 30000 |  |  |  | 30000 | R |  |  | 3 | 0 | 0 | 0 | 30900 | 0 | 30900 | R |  | 0 |  |  |  | 30000 |  | 10000 | ü | 10000 | 10000
E198 | CE | COV | Covered Market | High Street Avenue 2 Entrance Re-Roofing | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 10 | 5 | 15 | 405 | 42 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 4 | 0 | 0 | 20600 | 0 | 0 | 20600 | C |  | 0 |  |  |  | 60000 |  | 60000 | ü
E198 | CE | COV | Covered Market | High Street Avenue 3 Entrance Re-Roofing | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 10 | 5 | 15 | 405 | 42 | B | 3 |  |  |  |  | 20000 |  |  |  | 20000 | C |  |  | 4 | 0 | 0 | 0 | 20600 | 0 | 20600 | C |  | 0 |  |  |  | 60000 |  |  |  | 60000
E198 | CE | COV | Covered Market | Repairs to Wall Over Male Trader's Toilet | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 5 | 10 | 15 | 405 | 42 | B | 3 |  |  |  |  | 8000 |  |  |  | 8000 | R |  |  | 3 | 0 | 0 | 0 | 8240 | 0 | 8240 | R | [5 empty] | 7500 |  | 7500 | ü
E198 | CE | COV | Covered Market | Drainage System Repairs | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 7 | 7 | 14 | 378 | 41 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  | 15000 | ü
E198 | CE | COV | Covered Market | Basement Electrical Improvements | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 7 | 5 | 12 | 324 | 39 | B | 2 |  |  | 6000 | [5 empty] | 6000 | C |  |  | 3 | 0 | 6180 | 0 | 0 | 0 | 6180 | C | [5 empty] | 7500 | [5 empty] | 7500
|  |  | Covered Market | Signage | [44 empty] | 20000 | 20000
E198 | CE | COV | Covered Market | High Street Entrance Gates Alterations | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 7 | 5 | 12 | 324 | 39 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | R |  |  | 4 | 0 | 0 | 20600 | 0 | 0 | 20600 | R | [5 empty] | 25000 |  |  |  | 10000 | 25000
E198 | CE | COV | Covered Market | Avenue Lighting Improvements | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 3 | 7 | 10 | 270 | 37 | B | 2 |  | 20000 | 20000 | 20000 | 20000 |  |  |  | 80000 | C |  |  | 3 | 20600 | 20600 |  |  | 0 | 41200 | C | [5 empty] | 10000 |  |  |  | 10000
E198 | CE | COV | Covered Market | Install New Drain to Basement | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 5 | 5 | 10 | 270 | 37 | B | 2 |  |  |  |  | 10000 |  |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 10300 | 0 | 10300 | C | [5 empty] | 15000 | [6 empty] | 15000
E198 | CE | COV | Covered Market | Market Street Entrances Improvements | 978484 | 14.83% | A | 15 |  |  | 7 | 5 | 27 |  |  | 5 | 5 | 10 | 270 | 37 | B | 3 |  |  | 20000 | [5 empty] | 20000 | R |  |  | 4 | 0 | 20600 | 0 | 0 | 0 | 20600 | R | [5 empty] | 20000 |  |  |  | 20000
E198 | CE | COV | Covered Market | Market Street Elevation Masonry Repairs | 978484 | 14.83% |  | 15 |  |  | 7 | 5 | 27 |  |  |  |  | 0 | 0 | 27 | B | 3 |  |  |  | 25000 |  |  |  |  | 25000 | R |  |  | 3 | 0 | 0 | 25750 | 0 | 0 | 25750 | R | [5 empty] | 10000 |  |  |  |  | 10000 | [8 empty] | Budget available
|  |  | Investment ~ Covered Market | [41 empty] | 0 | 0 | 25000 | 450000 | 145000 | 152500 |  | 155000 | 97500 | 17500 | 15000 | 52500 | 60000 | 27500 | 45000 | 57500 | 55000
E315 | C | CP | Westgate Car Park | Deck repair/resurfacing |  |  | B |  |  | 15 |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  | ????????? | [6 empty] | 0 | C |  |  | 3 | ??????? | 0 | 0 | 0 | 0 | 0 | C | [5 empty] | 40000 | 20000 | 20000
T038 | C | CP | Worcester Street Car Park | External repairs |  |  | A |  |  | 15 |  |  | 15 |  | 10 | 5 | 10 | 25 | 375 | 40 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 10000 |  | 10000 | ü
E335 | C | CP | Gloucester Green (Underground) Car Park | Decorate fire exits and repair emergency lights |  |  | A |  |  | 15 |  |  | 15 |  | 10 |  | 10 | 20 | 300 | 35 | B | 2 |  |  | 15000 | [5 empty] | 15000 | R |  |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | ü |  |  |  |  | 15000 |  |  | 15000 |  |  | Recurring cost every 3 years
E335 | C | CP | Gloucester Green (Underground) Car Park | Refurbishment of doors, columns, sprinkler system etc |  |  | A |  |  | 15 |  |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  | 15000 | [5 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
|  |  | Gloucester Green (Underground) Car Park | Repairs & Waterproofing | [44 empty] | 47000
E315 | C | CP | Westgate Car Park | Refurbishment to staircases |  |  | B |  |  | 15 |  |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | C | 3 |  |  |  |  | 20000 |  |  |  | 20000 | R |  |  | 1 | 0 | 0 | 0 | 20600 | 0 | 20600 | R | [5 empty] | 20000 |  | 20000 | ü
E315 | C | CP | Westgate Car Park | Major structural repairs |  |  | B |  |  | 15 |  |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | C | 1 |  | ???????? | [6 empty] | 0 | C |  |  | 3 | ??????? | 0 | 0 | 0 | 0 | 0 | C
E331 | C | CP | Oxpens Road Coach & Car Park | External repairs |  |  | A |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 5000 | [6 empty] | 5000
T042 | C | CP | St. Clements Public Toilets | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [19 empty] | TO BE REDEVELOPED
T042 | C | CP | St. Clements Public Toilets | Minor roof repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 250 | [5 empty] | 250 | R |  |  | 1 | 0 | 257.5 | 0 | 0 | 0 | 257.5 | R | [19 empty] | TO BE REDEVELOPED
T042 | C | CP | St. Clements Public Toilets | Repairs to rainwater goods | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [19 empty] | TO BE REDEVELOPED
T042 | C | CP | St. Clements Public Toilets | Repointing to brickwork | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [19 empty] | TO BE REDEVELOPED
T010 | C | CP | Seacourt Park & Ride Car Park | COUNTY RESPONSIBILITY | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [19 empty] | COUNTY RERSPONSIBILITY
| C | CP | Redbridge Park & Ride Car park | COUNTY RESPONSIBILITY | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R | [19 empty] | COUNTY RERSPONSIBILITY
T030 | C | CP | Pear Tree Park & Ride Car Park | COUNTY RESPONSIBILITY | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [19 empty] | COUNTY RERSPONSIBILITY
T017 | C | CP | Diamond Place Public Toilets | External refurbishments |  |  | A |  |  |  | 10 |  | 10 |  |  | 7 | 10 | 17 | 170 | 27 | B | 3 | [5 empty] | 2000 |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 2060 | 2060 | R | [5 empty] | 5000 | [6 empty] | 5000 |  |  |  |  | 5000 |  | Recurring cost every 5 years
T016 | C | CP | Diamond Place Car Park | External repairs |  |  | A |  |  |  | 10 |  | 10 |  |  | 7 | 5 | 12 | 120 | 22 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 10000 | [6 empty] | 10000
T017 | C | CP | Diamond Place Public Toilets | Tarmac and masonry repairs |  |  | A |  |  |  | 10 |  | 10 |  |  | 5 | 7 | 12 | 120 | 22 | B | 3 | [5 empty] | 2500 |  |  | 2500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 2575 | 2575 | R | [5 empty] | 2500 | [6 empty] | 2500 | [6 empty] | Recurring cost every 5 years
T027 | C | CP | Headington Car Park | External Repairs and Refurbishment |  |  | A |  |  | 15 |  |  | 15 |  |  | 3 | 5 | 8 | 120 | 23 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 2000 | [6 empty] | 2000
E315 | C | CP | Westgate Car Park | Refurbishment to ceilings etc |  |  | B |  |  | 15 |  |  | 15 |  |  | 3 | 5 | 8 | 120 | 23 | C | 3 |  |  |  |  | 20000 |  |  |  | 20000 | R |  |  | 1 | 0 | 0 | 0 | 20600 | 0 | 20600 | R
T005 | C | CP | Barns Road Car Park | Repairs and improvements |  |  | A |  |  | 10 |  |  | 10 |  | 5 |  | 5 | 10 | 100 | 20 | B | 2 |  |  |  |  | 20000 |  |  |  | 20000 | R |  |  | 3 | 0 | 0 | 0 | 20600 | 0 | 20600 | R | [5 empty] | 10000 |  |  |  | 1000
T011 | C | CP | Union Street Car Park | Minor Refurbishment |  |  | A |  |  | 15 |  |  | 15 |  |  | 3 | 3 | 6 | 90 | 21 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 500 | [6 empty] | 500
E299 | C | CP | Union Street Car Park (land adjacent) | Minor Refurbishment |  |  | A |  |  | 7 |  |  | 7 |  |  | 3 | 5 | 8 | 56 | 15 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 500 | [6 empty] | 500
E330 | C | CP | Banbury Road Parking Spaces (Rear of 228-246) | External repairs to masonry & balustrading |  |  | A |  |  |  | 3 |  | 3 |  | 5 |  | 3 | 8 | 24 | 11 | C | 2 |  |  |  | 15000 |  |  |  |  | 15000 | R |  |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 5000 | [6 empty] | 5000
|  |  | Car Parks | [41 empty] | 0 | 0 | 0 | 140500 | 67000 | 80000 |  | 1000 | 0 | 0 | 30500 | 15000 | 0 | 15000 | 15000 | 5000 | 0
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot - Garage buildings | Replace roof sheets |  |  | B |  |  | 15 |  |  | 15 |  |  | 15 | 7 | 22 | 330 | 37 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 20000 | 0 | 20000 | C |  | 0 |  |  |  | 40000 | [5 empty] | 40000 | [7 empty] | Defer subject to depot review
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot - Emergency stores building | External refurbishments |  |  | B |  |  | 15 |  |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 | [5 empty] | 2000 |  |  |  | 2000 |  |  |  | Recurring cost every 5 years
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot - Garage buildings | External refurbishments |  |  | B |  |  | 15 |  |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 | [5 empty] | 2000 |  |  |  | 2000 |  |  |  | Recurring cost every 5 years
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot - Motor Transport workshop | External refurbishments |  |  | B |  |  | 15 |  |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 |  |  |  | 5000 |  |  |  | Recurring cost every 5 years
E144 | C | DSD | Gloucester Lane Cleansing Depot | External refurbishments |  |  | A |  |  | 10 |  |  | 10 |  |  | 7 | 7 | 14 | 140 | 24 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 1500 |  |  |  | 2000 | [5 empty] | 1500 |  |  |  | Recurring cost every 5 years
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot - Admin building | External refurbishments |  |  | B |  |  | 15 |  |  | 15 |  |  |  | 7 | 7 | 105 | 22 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 1500 | [5 empty] | 1500 | [7 empty] | Recurring cost every 5 years
E144 | C | DSD | Gloucester Lane Cleansing Depot | Roof repairs |  |  | A |  |  | 10 |  |  | 10 |  |  | 5 | 5 | 10 | 100 | 20 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  | 1000
T021 | C | DSD | Knights Road Cleansing Depot | External refurbishments |  |  | A |  |  | 7 |  |  | 7 |  |  | 3 | 7 | 10 | 70 | 17 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 1500 | [5 empty] | 1500 | [7 empty] | Recurring cost every 5 years
T023 | C | DSD | Marsh Road (Cowley Marsh ) Depot | Refurbishment to gates |  |  | B |  |  | 15 |  |  | 15 |  |  |  | 3 | 3 | 45 | 18 | B | 3 | [5 empty] | 1000 |  |  | 1000 | R | Recurring cost every 7 years |  | 1 | 0 | 0 | 0 | 0 | 1030 | 1030 | R | [5 empty] | 500 | [5 empty] | 500 | [7 empty] | Recurring cost every 7 years
|  |  | Direct Services Depots | [41 empty] | 0 | 0 | 0 | 55000 | 0 | 0 |  | 3000 | 0 | 52500 | 0 | 0 | 0 | 10500 | 0 | 0 | 0
H219 | CE* | ES | Westlands Drive, 61 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H218 | CE* | ES | Westlands Drive, 59 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H217 | CE* | ES | Westlands Drive, 57 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H216 | CE* | ES | Westlands Drive, 55 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H215 | CE* | ES | Westlands Drive, 53 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H214 | CE* | ES | Westlands Drive, 49/51 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H213 | CE* | ES | Westlands Drive, 47 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H212 | CE* | ES | Westlands Drive, 45 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 750 |  |  |  |  | 750 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H211 | CE* | ES | Westlands Drive, 43 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H198 | CE* | ES | Underhill Circus, Garages to rear | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 4 | 0 | 0 |  | 0 | 0 | 0 | R
H198 | CE* | ES | Underhill Circus, 8 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H197 | CE* | ES | Underhill Circus, 6 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H196 | CE* | ES | Underhill Circus, 4 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H195 | CE* | ES | Underhill Circus, 2 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H194 | CE* | ES | Underhill Circus, 14 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H193 | CE* | ES | Underhill Circus, 10/12 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H182 | CE* | ES | The Oval, 24/25 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H181 | CE* | ES | The Oval, 23 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H169 | CE* | ES | St. Nicholas Road. 69 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H168 | CE* | ES | St. Nicholas Road, 57 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H167 | CE* | ES | St. Nicholas Road, 55 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H166 | CE* | ES | St. Nicholas Road, 53 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H165 | CE* | ES | St. Nicholas Road, 51 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | R |  |  |  | 0 |  | 0 | 0 | 0 | 0 | R
H164 | CE* | ES | St. Nicholas Road, 49 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
|  | HL | Cemetery Lodges & Parks Houses | Reactive Maintenance & Minor Repair | [5 empty] | 5 |  |  | 5 | 15 | 15 |  | 15 | 45 | 225 | 50 | ---- | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
H109 | CE* | ES | Knights Road, 9 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H108 | CE* | ES | Knights Road, 7 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H107 | CE* | ES | Knights Road, 11 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H105 | CE* | ES | Kendall Crescent, 9 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H104 | CE* | ES | Kendall Crescent, 7 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H103 | CE* | ES | Kendall Crescent, 5 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H102 | CE* | ES | Kendall Crescent, 3 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H101 | CE* | ES | Kendall Crescent, 1 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  |  |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H093 | CE* | ES | Grays Road, 4 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H092 | CE* | ES | Grays Road, 2 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H090 | CE* | ES | Gladstone Road, 50 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [19 empty] | Recurring cost every 5 years
H087 | CE* | ES | Girdlestone Road, 7 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H087 | CE* | ES | Girdlestone Road, 7 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 4 | [6 empty] | 2008/9 | 5000 | 5000 | C |  |  | 3 | 0 | 0 | 0 | 0 |  | 0 | C
H086 | CE* | ES | Girdlestone Road, 5 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H086 | CE* | ES | Girdlestone Road, 5 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 4 | [6 empty] | 2008/9 | 5000 | 5000 | C |  |  | 3 | 0 | 0 | 0 | 0 |  | 0 | C
H085 | CE* | ES | Girdlestone Road, 3 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H085 | CE* | ES | Girdlestone Road, 3 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 4 | [6 empty] | 2008/9 | 5000 | 5000 | C |  |  | 3 | 0 | 0 | 0 | 0 |  | 0 | C
H084 | CE* | ES | Girdlestone Road, 1 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H084 | CE* | ES | Girdlestone Road, 1 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 4 | [6 empty] | 2008/9 | 5000 | 5000 | C |  |  | 3 | 0 | 0 | 0 | 0 |  | 0 | C
H042 | CE* | ES | Blackbird Leys Road, 98 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H041 | CE* | ES | Blackbird Leys Road, 96 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H040 | CE* | ES | Blackbird Leys Road, 94 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H039 | CE* | ES | Blackbird Leys Road, 110 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H038 | CE* | ES | Blackbird Leys Road, 108 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H037 | CE* | ES | Blackbird Leys Road, 106 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H036 | CE* | ES | Blackbird Leys Road, 102/104 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H035 | CE* | ES | Blackbird Leys Road, 100 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H033 | CE* | ES | Bellenger Way, 49 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H030 | CE* | ES | Barns Road, 49 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H029 | CE* | ES | Barns Road, 47 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H028 | CE* | ES | Barns Road, 45 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H027 | CE* | ES | Barns Road, 43 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H026 | CE* | ES | Barns Road, 41 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H025 | CE* | ES | Barns Road, 39 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H024 | CE* | ES | Barns Road, 37 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H021 | CE* | ES | Balfour Road, 75 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H020 | CE* | ES | Balfour Road, 73 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H019 | CE* | ES | Balfour Road, 71 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H018 | CE* | ES | Balfour Road, 69 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 |  | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H016 | CE* | ES | Atkyns Road, 9 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H015 | CE* | ES | Atkyns Road, 7 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H014 | CE* | ES | Atkyns Road, 5 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H013 | CE* | ES | Atkyns Road, 3 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H012 | CE* | ES | Atkyns Road, 21 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H011 | CE* | ES | Atkyns Road, 15/19 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 2500 |  |  |  |  | 2500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H010 | CE* | ES | Atkyns Road, 13 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
H009 | CE* | ES | Atkyns Road, 11 | Now HRA property | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 |  | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
|  |  | Estate Shops | [41 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
E339 | CES | HL | Westhill Farmhouse - Outbuildings | External refurbishments | [5 empty] | 5 |  |  | 5 |  |  | 7 |  | 7 | 35 | 12 | B | 3 |  |  |  |  | 1500 |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1545 | 0 | 1545 | R | [19 empty] | Recurring cost every 5 years
E339 | CES | HL | Westhill Farmhouse - House | External refurbishments | [5 empty] | 5 |  |  | 5 |  |  | 7 |  | 7 | 35 | 12 | B | 3 |  |  |  |  | 7500 |  |  |  | 7500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 7725 | 0 | 7725 | R | [19 empty] | Recurring cost every 5 years
E339 | CES | HL | Westhill Farmhouse - House | Rebuild porch | [5 empty] | 5 |  |  | 5 |  |  | 3 |  | 3 | 15 | 8 | B | 1 |  |  | 3000 | [5 empty] | 3000 | C |  |  | 3 | 0 | 3090 | 0 | 0 | 0 | 3090 | C
E339 | CES | HL | Westhill Farmhouse - House | Upgrade to decent homes standard | [5 empty] | 5 |  |  | 5 |  | 15 |  |  | 15 | 75 | 20 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | C |  |  | 4 | 0 | 0 | 0 | 5150 | 0 | 13000 | C
|  | HL | Cemetery Lodges & Parks Houses | Services Maintenance | [5 empty] | 5 |  |  | 5 | 15 | 15 |  | 15 | 45 | 225 | 50 | ---- | 2 | 1000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E078 | CE* | HL | Cowley Road, 50 | Upgrade to decent home standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | C |  |  | 4 | 0 | 0 | 0 | 5150 | 0 | 5150 | C | [5 empty] | 7500 | 7500
E096 | CES | HL | Headington Cemetery Lodge | Upgrade to decent homes standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 4 | 0 | 0 | 0 | 5150 | 0 | 13000 | R | [5 empty] | 7500 | 7500
E193 | CES | HL | Manor Road (South Hinksey), 36 | Upgrade to decent homes standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 4 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [5 empty] | 7500 | 7500
T045 | CES | HL | Marsh Road, 3 | Upgrade to decent homes standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 4 | 0 | 5150 | 0 | 0 | 0 | 13000 | C | [5 empty] | 7500 | 7500
E340 | CES | HL | South Park Bungalow | Upgrade to decent home standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 | [5 empty] | 10000 |  |  | 10000 | C |  |  | 4 | 0 | 0 | 0 | 0 | 10300 | 13000 | C | [5 empty] | 7500 | 7500
E067 | CES | HL | Rose Hill Cemetery Lodge | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 7500 |  |  |  |  | 7500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 7725 | 0 | 0 | 7725 | R | [19 empty] | TO BE SOLD
E067 | CES | HL | Rose Hill Cemetery Lodge | Replace rainwater goods | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [19 empty] | TO BE SOLD
E270 | CE* | HL | St. Marys Road, 87 | Upgrade to decent homes standard |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 15 | 30 | 150 | 35 | B | 3 | [5 empty] | 5000 |  |  | 5000 | C |  |  | 4 | 0 | 0 | 0 | 0 | 5150 | 5150 | C | [5 empty] | 6000 | 6000
E214 | CES | HL | Botley Cemetery Lodge | Decent home standard improvements |  |  | C |  |  | 5 |  |  | 5 |  | 15 |  | 10 | 25 | 125 | 30 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 13000 | R | [5 empty] | 7500 | 7500
E096 | CES | HL | Headington Cemetery Lodge | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 7500 |  |  |  | 7500 | [8 empty] | 7500 | Recurring cost every 7 years
E096 | CES | HL | Headington Cemetery Lodge | Replace flat roof covering |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | C |  |  | 3 | 0 | 0 | 0 | 3090 | 0 | 3090 | C | [5 empty] | 5000 |  |  |  | 5000
E193 | CES | HL | Manor Road (South Hinksey), 36 | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 2 |  | 5000 | [5 empty] | 5000 | 10000 | R |  |  | 1 | 5150 | 0 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 1000 | [7 empty] | 1000
T045 | CES | HL | Marsh Road, 3 | Replacement windows |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 |  |  | 6000 | [5 empty] | 6000 | C |  |  | 3 | 0 | 6180 | 0 | 0 | 0 | 6180 | C | [5 empty] | 5000 |  |  |  | 5000
E340 | CES | HL | South Park Bungalow | Replacement windows and doors |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 | [5 empty] | 10000 |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 10300 | 10300 | C | [5 empty] | 5000 | [5 empty] | 5000
E192 | CE | HL | Manor Road (South Hinksey), 21 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  | 3000 | [5 empty] | 3000 | 6000 | R | Recurring cost every 5 years |  | 1 | 3090 | 0 | 0 | 0 | 0 | 3090 | R | [19 empty] | Recurring cost every 5 years
E192 | CE | HL | Manor Road (South Hinksey), 21 | Masonry repairs and re-pointing | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  | 10000 | [6 empty] | 10000 | C |  |  | 1 | 10300 | 0 | 0 | 0 | 0 | 10300 | C
E192 | CE | HL | Manor Road (South Hinksey), 21 | Replacement rainwater goods | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  | 3000 | [6 empty] | 3000 | C |  |  | 1 | 3090 | 0 | 0 | 0 | 0 | 3090 | C
E342 | CES | HL | Horspath Road, 2 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [19 empty] | TO BE SOLD
E342 | CES | HL | Horspath Road, 2 | Upgrade to decent home standard | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 4 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [19 empty] | TO BE SOLD
E341 | CES | HL | Horspath Road, 1 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [19 empty] | TO BE SOLD
E341 | CES | HL | Horspath Road, 1 | Upgrade to decent home standard | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 4 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [19 empty] | TO BE SOLD
E078 | CE* | HL | Cowley Road, 50 | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 10 | 17 | 85 | 22 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  |  | 3000 | [8 empty] | Recurring cost every 5 years
E193 | CES | HL | Manor Road (South Hinksey), 36 | Roof and chimney repairs |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 10 | 17 | 85 | 22 | B | 2 |  | 1000 | [6 empty] | 1000 | C |  |  | 1 | 1030 | 0 | 0 | 0 | 0 | 1030 | C | [5 empty] | 1500 |  |  |  | 1500
T045 | CES | HL | Marsh Road, 3 | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 10 | 17 | 85 | 22 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 2000 |  |  |  |  | 2000 | [8 empty] | Recurring cost every 5 years
E340 | CES | HL | South Park Bungalow | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 10 | 17 | 85 | 22 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [8 empty] | Recurring cost every 5 years
E152 | CES | HL | Dairy Lodge - The Dairy | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 7500 | [5 empty] | 7500 | R | Recurring cost every 5 years |  | 1 | 0 | 7725 | 0 | 0 | 0 | 7725 | R
E152 | CES | HL | Dairy Lodge - The Dairy | Rainwater good repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R
E152 | CES | HL | Dairy Lodge - The Dairy | Upgrade to decent home standards | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 500 | [5 empty] | 500 | C |  |  | 4 | 0 | 515 | 0 | 0 | 0 | 515 | C
E152 | CES | HL | Dairy Lodge - Barns & garage | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R
E152 | CES | HL | Dairy Lodge - Barns & garage | Masonry repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 7500 | [5 empty] | 7500 | R |  |  | 1 | 0 | 7725 | 0 | 0 | 0 | 7725 | R
E152 | CES | HL | Dairy Lodge - Barns & garage | Rainwater goods repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R
E152 | CES | HL | Dairy Lodge - Barns & garage | Roof repaoirs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R
E270 | CE* | HL | St. Marys Road, 87 | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 10 | 17 | 85 | 22 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 2500 | [5 empty] | 2500 | [7 empty] | Recurring cost every 5 years
E214 | CES | HL | Botley Cemetery Lodge | Minor roof repairs |  |  | C |  |  | 5 |  |  | 5 |  |  | 5 | 10 | 15 | 75 | 20 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 1500 |  |  |  | 1500
E214 | CES | HL | Botley Cemetery Lodge | Replacement rainwater goods |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 5 | 15 | 75 | 20 | B | 3 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 2500 |  |  |  |  | 2500
E096 | CES | HL | Headington Cemetery Lodge | Replacement windows |  |  | C |  |  | 5 |  |  | 5 |  |  | 10 | 5 | 15 | 75 | 20 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | C |  |  | 3 | 0 | 0 | 0 | 515 | 0 | 515 | C | [5 empty] | 1000 |  |  |  |  | 1000
E338 | CES | HL | Brasenose Farmhouse | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  | 5000 | [6 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 5150 | 0 | 0 | 0 | 0 | 5150 | R | [19 empty] | To be sold
E338 | CES | HL | Brasenose Farmhouse | Lintol replacement | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  | 4000 | [6 empty] | 4000 | R |  |  | 1 | 4120 | 0 | 0 | 0 | 0 | 4120 | R | [19 empty] | To be sold
E338 | CES | HL | Brasenose Farmhouse | Replacement doors and windows | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  | 2000 | [6 empty] | 2000 | C |  |  | 1 | 2060 | 0 | 0 | 0 | 0 | 2060 | C | [19 empty] | To be sold
E338 | CES | HL | Brasenose Farmhouse | Upgrade to decent homes standard | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  | 5000 | [6 empty] | 5000 | C |  |  | 4 | 5150 | 0 | 0 | 0 | 0 | 5150 | C | [19 empty] | To be sold
T045 | CES | HL | Marsh Road, 3 | Replacement garage door |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 7 | 14 | 70 | 19 | B | 3 |  |  | 1000 | [5 empty] | 1000 | C |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | C | [5 empty] | 500 | [6 empty] | 500
E214 | CES | HL | Botley Cemetery Lodge | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 5 | 12 | 60 | 17 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [8 empty] | Recurring cost every 5 years
E270 | CE* | HL | St. Marys Road, 87 | Minor masonry repairs |  |  | C |  |  | 5 |  |  | 5 |  |  | 5 | 5 | 10 | 50 | 15 | B | 3 | [5 empty] | 1000 |  |  | 1000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 1030 | 1030 | R | [5 empty] | 1500 | [6 empty] | 1500
H123 | CE* | ES | Masons Road, 23 | External refurbishments |  |  | C | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 | [5 empty] | 1000 |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 1030 | 1030 | R | [5 empty] | 1000 | [6 empty] | 1000 | [6 empty] | Recurring cost every 5 years
|  |  | Houses & Lodges | [41 empty] | 0 | 0 | 0 | 105500 | 51000 | 0 |  | 21500 | 18500 | 7500 | 3000 | 0 | 0 | 0 | 0 | 1000 | 7500
E043 | CE | IBS | Broad Street, 23/25 | External refurbishments | 104000 | 10.95% | A | 15 |  |  |  |  | 15 | 15 |  |  | 15 | 30 | 450 | 45 | B | 3 |  |  |  |  | 15000 |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 15450 | 0 | 15450 | R |  | 0 |  |  | 70000 | 30000 | [8 empty] | 30000 |  |  |  |  | Recurring cost every 5 years
E041 | CE | IBS | Broad Street, 21 | External refurbishments | 52000 | 10% | A | 10 |  |  |  |  | 10 | 15 |  | 10 | 10 | 35 | 350 | 45 | B | 3 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 | 15000 | [6 empty] | 15000 |  |  |  |  | 15000 | Recurring cost every 5 years
E033 | CE | IBS | Broad Street, 12 | External refurbishments | 41750 | 9.71% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  | 12000 | [5 empty] | 12000 | R | Recurring cost every 5 years |  | 1 | 0 | 12360 | 0 | 0 | 0 | 12360 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E033 | CE | IBS | Broad Street, 12 | Roof repairs | 41750 | 9.71% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 | [5 empty] | 15000 |  |  | 15000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 15450 | 15450 | C | [5 empty] | 15000 | 10000 | 5000 | ü
E034 | CE | IBS | Broad Street, 13 | External refurbishments | 61000 | 9.84% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E034 | CE | IBS | Broad Street, 13 | Window repairs | 61000 | 9.84% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 10000 |  | 10000 | ü
E035 | CE | IBS | Broad Street, 14/14a | External refurbishments | 65250 | 10.04% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  | 15000 | [5 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E036 | CE | IBS | Broad Street, 16 (TIC) | External refurbishments |  |  | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E037 | CE | IBS | Broad Street, 17 | External refurbishments | 36450 | 9.11% | A | 7 |  |  |  | 5 | 12 | 10 |  |  | 15 | 25 | 300 | 37 | B | 3 |  | 10000 | [6 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  |  |  | 15000 | [5 empty] | 15000 |  |  |  | Recurring cost every 5 years
E039 | CE | IBS | Broad Street, 19 | External refurbishments | 22000 | 9.52% | A | 7 |  |  |  | 5 | 12 | 10 |  |  | 15 | 25 | 300 | 37 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  |  |  | 15000 | [5 empty] | 15000 |  |  |  | Recurring cost every 5 years
E040 | CE | IBS | Broad Street, 20 | External refurbishments | 31250 | 10.05% | A | 7 |  |  |  | 5 | 12 | 10 |  |  | 15 | 25 | 300 | 37 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  |  |  | 15000 | [5 empty] | 15000 |  |  |  | Recurring cost every 5 years
E042 | CE | IBS | Broad Street, 22 | External refurbishments | 16850 | 7.52% | A | 5 |  |  |  | 5 | 10 | 15 |  |  | 15 | 30 | 300 | 40 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E044 | CE | IBS | Broad Street, 6/7/8 | External refurbishments | 75750 | 9.71% | A | 15 |  |  |  | 5 | 20 | 5 |  |  | 10 | 15 | 300 | 35 | B | 3 |  |  |  |  | 12000 |  |  |  | 12000 | R |  |  | 1 | 0 | 0 | 0 | 12360 | 0 | 12360 | R | [5 empty] | 15000 |  | 15000 | ü | [10 empty] | Recurring cost every 5 years
E044 | CE | IBS | Broad Street, 6/7/8 | Masonry repairs | 75750 | 9.71% | A | 15 |  |  |  | 5 | 20 | 5 |  |  | 10 | 15 | 300 | 35 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 7500 |  | 7500
E044 | CE | IBS | Broad Street, 6/7/8 | Roof repairs | 75750 | 9.71% | A | 15 |  |  |  | 5 | 20 | 5 |  |  | 10 | 15 | 300 | 35 | B | 2 |  |  | 2000 | [5 empty] | 2000 | C |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | C | [5 empty] | 5000 |  | 5000 | ü
E045 | CE | IBS | Broad Street, 7 | External refurbishments | 60885 | 9.59% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  |  | 12000 |  |  |  |  | 12000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 12360 | 0 | 0 | 12360 | R | [5 empty] | 15000 |  | 15000 | ü | [8 empty] | 15000 |  | Recurring cost every 7 years
E046 | CE | IBS | Broad Street, 9/10 | External refurbishments | 69500 | 10.07% | A | 10 |  |  |  | 5 | 15 | 5 |  |  | 15 | 20 | 300 | 35 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 5000 |  | 5000 | ü | [6 empty] | 5000 |  |  |  | Recurring cost every 5 years
E038 | CE | IBS | Broad Street, 18 | External refurbishments | 51125 | 9.83% | A | 10 |  |  |  |  | 10 | 10 |  |  | 15 | 25 | 250 | 35 | B | 3 |  | 15000 | [6 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 15450 | 0 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  | 15000 | ü | [6 empty] | 15000 |  |  |  | Recurring cost every 5 years
E032 | CE | IBS | Broad Street, 11/12 | External refurbishments | 28165 | 10.43% | A | 7 |  |  |  | 5 | 12 | 3 |  |  | 15 | 18 | 216 | 30 | B | 3 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  | 10000 | ü | [5 empty] | 10000 |  |  |  |  | Recurring cost every 5 years
E032 | CE | IBS | Broad Street, 11/12 | Minor stonework repairs | 28165 | 10.43% | A | 7 |  |  |  | 5 | 12 | 3 |  |  | 15 | 18 | 216 | 30 | B | 3 |  |  | 3000 | [5 empty] | 3000 | R |  |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 5000 |  | 5000
E047 | CE | IBS | Boxall Buildings, Broad Street |  |  |  |  | 10 |  |  |  |  | 10 |  |  |  |  | 0 | 0 | 10 | B | ---- | [8 empty] | 0 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
|  |  | Investment ~ Broad Street | [41 empty] | 0 | 0 | 70000 | 267500 | 25000 | 167500 |  | 45000 | 0 | 0 | 0 | 15000 | 40000 | 140000 | 0 | 15000 | 15000
E059 | C | ICC | Castle Street, 30a | Sold | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
E060 | CE | ICC | Castle Street, 31-33 | Sold | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
E061 | CE | ICC | Castle Street, 34 | Sold | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
E058 | CE | ICC | Castle Street, 35 (part) | Sold | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R | [19 empty] | Recurring cost every 5 years
| ----- | ICC | Residential & Commercial Properties | Reactive Maintenance & Minor Repair |  |  |  | 15 |  |  |  |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | ---- | 2 | 35000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
| ----- | ICC | Residential & Commercial Properties | Services Maintenance |  |  |  | 15 |  |  |  |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | ---- | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E406 | CE | ICC | High Street, 139-140 |  | 90000 | 8.57% |  | 15 |  |  |  | 7 | 22 | 10 |  | 3 | 5 | 18 | 396 |  | B | 3 | [19 empty] | R
E211 | CE | ICC | New Road, 11,11a/b & 11c | Chimney Repairs | 74750 | 10.68% | A | 10 |  |  |  |  | 10 |  |  | 7 | 15 | 22 | 220 | 32 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü
E211 | CE | ICC | New Road, 11,11a/b & 11c | External refurbishments | 74750 | 10.68% | A | 10 |  |  |  |  | 10 |  |  | 7 | 15 | 22 | 220 | 32 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  | 2000 | ü | [10 empty] | Recurring cost every 5 years
E145 | CE | ICC | Gloucester Street, 4 | External refurbishments | 42000 | 12.1% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 3 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 | [7 empty] | 10000 |  | Recurring cost every 5 years
E146 | CE | ICC | Gloucester Street, 6 | Damp proofing to basement | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 10000 |  |  |  | 10000
E146 | CE | ICC | Gloucester Street, 6 | External refurbishments | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 | [7 empty] | 10000 |  | Recurring cost every 5 years
E146 | CE | ICC | Gloucester Street, 6 | Masonry cleaning | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  | 1000
E146 | CE | ICC | Gloucester Street, 6 | Masonry repairs | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 2 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  | 2000
E146 | CE | ICC | Gloucester Street, 6 | Repair / replace rainwater goods | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 2500 |  |  |  | 2500
E146 | CE | ICC | Gloucester Street, 6 | Timber repairs | 32000 | 9.14% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 2 |  |  | 500 | [5 empty] | 500 | R |  |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [5 empty] | 1000 |  |  |  | 1000
E384 | CE | ICC | St Ebbes, 12 | External refurbishments | 20000 | 8.66% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000
E384 | CE | ICC | St Ebbes, 12 | Repairs to roof and rainwater good | 20000 | 8.66% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  |  | 1000 |  |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  | 1000
E156 | CE | ICC | High Street, 130 | External refurbishments |  |  | A | 5 |  |  |  | 5 | 10 |  |  | 5 | 7 | 12 | 120 | 22 | B | 3 |  |  |  |  | 7000 |  |  |  | 7000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 7210 | 0 | 7210 | R | [5 empty] | 5000 | [6 empty] | 5000 | [6 empty] | Recurring cost every 5 years
E266 | C | ICC | St. Aldates, Floyds Row | External refurbishments | 150 | 0.02% | A | 3 |  |  |  |  | 3 |  |  | 5 | 5 | 10 | 30 | 13 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [19 empty] | Recurring cost every 5 years
E158 | CE | ICC | High Street, 130a | External refurbishments |  |  | A | 5 |  |  |  | 5 | 10 |  |  | 5 | 7 | 12 | 120 | 22 | B | 3 |  |  |  | 7000 |  |  |  |  | 7000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 7210 | 0 | 0 | 7210 | R | [5 empty] | 5000 | [6 empty] | 5000 | [6 empty] | Recurring cost every 5 years
E068 | CE | ICC | Cornmarket Street, 3 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 5 | 7 | 12 | 36 | 15 | B | 3 |  |  | 12000 | [5 empty] | 12000 | R | Recurring cost every 5 years |  | 1 | 0 | 12360 | 0 | 0 | 0 | 12360 | R | [5 empty] | 15000 | [5 empty] | 10000 | [7 empty] | Recurring cost every 5 years
H201 | CE | ICC | Upper Fisher Row, 9 | External refurbishments | 3500 | 15.91% | A | 3 |  |  |  |  | 3 |  |  | 5 | 7 | 12 | 36 | 15 | B | 4 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000
E301 | CE | ICC | Walton Street, 151 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 | [5 empty] | 7000 |  |  | 7000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 7210 | 7210 | R | [19 empty] | Recurring cost every 5 years
H205 | CE | ICC | Walton Street, 157 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [19 empty] | Recurring cost every 5 years
H305 | CE | ICC | Walton Street, 161 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R
H206 | CE | ICC | Walton Street, 165 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [19 empty] | Recurring cost every 5 years
E303 | CE | ICC | Walton Street, 169 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 2 |  |  |  |  | 15000 |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 15450 | 0 | 15450 | R | [19 empty] | Recurring cost every 5 years
H207 | CE | ICC | Walton Street, 170 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [19 empty] | Recurring cost every 5 years
|  |  | Investement ~ City Centre Misc. | [41 empty] | 0 | 0 | 0 | 79500 | 0 | 7000 |  | 42500 | 0 | 15000 | 10000 | 0 | 0 | 0 | 0 | 20000 | 0
E134 | C | IGG | Gloucester Green Market Square | Upgrade Electrical Supply to Power Bollards |  |  | A |  |  |  | 10 |  | 10 |  |  | 10 | 15 | 25 | 250 | 35 | C | 3 |  |  |  | 11500 |  |  |  |  | 11500 | C |  |  | 4 | 0 | 0 | 11845 | 0 | 0 | 11845 | C | [5 empty] | 25000 |  |  |  | 25000
E134 | C | IGG | Gloucester Green Open Market | Stalls and Covers |  |  | A |  |  |  | 10 |  | 10 |  |  | 10 | 15 | 25 | 250 | 35 | C | 3 | [5 empty] | 10000 |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 10300 | 10300 | C | [5 empty] | 15000 | [5 empty] | 15000
E140 | C | IGG | Gloucester Green Bus Station | Brickwork repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 5 | 12 | 180 | 27 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 500 |  | 500 | ü
E140 | C | IGG | Gloucester Green Bus Station | Repairs and ReRefurbishment of Canopy |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 5 | 12 | 180 | 27 | B | 3 |  |  | 7000 | [5 empty] | 7000 | R |  |  | 3 | 0 | 7210 | 0 | 0 | 0 | 7210 | R | [5 empty] | 5000 |  | 5000 | ü | [5 empty] | 5000 |  |  | 5000 |  | Recurring cost every 3 years
E142 | CE | IGG | Gloucester Green - Old School | External refurbishments | 31500 | 13.82% | A | 7 |  |  |  |  | 7 |  |  | 7 | 15 | 22 | 154 | 29 | C | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 2 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 7500 | [6 empty] | 7500 | [5 empty] | 7500 | Recurring cost every 5 years
E138 | CE | IGG | Gloucester Green, 21 (ground floor) | External refurbishments |  |  | A | 7 |  |  |  |  | 7 |  |  | 7 | 5 | 12 | 84 | 19 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 | [7 empty] | Recurring cost every 5 years
E134 | C | IGG | Gloucester Green | Reactive Maintenance & Minor Repair |  |  | A | [5 empty] | 0 | 15 | 15 |  | 15 | 45 | 0 | 45 | B | 2 | 2000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E139 | C | IGG | Gloucester Green, 21 (upper floor) | External refurbishments |  |  | A | 7 |  |  |  |  | 7 |  |  | 7 | 5 | 12 | 84 | 19 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 | [7 empty] | Recurring cost every 5 years
E139 | C | IGG | Gloucester Green, 21 (upper floor) | Masonry repairs |  |  | A | 7 |  |  |  |  | 7 |  |  | 7 | 5 | 12 | 84 | 19 | B | 3 | [5 empty] | 1000 |  |  | 1000 | C |  |  | 1 | 0 | 0 | 0 | 0 | 1030 | 1030 | C | [5 empty] | 1500 | [5 empty] | 1500
E134 | C | IGG | Gloucester Green | Replace Signs |  |  | A |  |  |  | 5 |  | 5 |  |  | 7 | 5 | 12 | 60 | 17 | B | 3 |  |  |  | 6000 |  |  |  |  | 6000 | R |  |  | 4 | 0 | 0 | 6180 | 0 | 0 | 6180 | R | [5 empty] | 7500 | [5 empty] | 7500
E137 | CE | IGG | Gloucester Green Kiosks | External refurbishments | 22000 | 10.28% | A | 5 |  |  |  |  | 5 |  |  | 5 | 7 | 12 | 60 | 17 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 3000 | [5 empty] | 3000 | [7 empty] | Recurring cost every 5 years
|  |  | Investment ~ Gloucester Green | [41 empty] | 0 | 0 | 0 | 75000 | 0 | 5500 |  | 25000 | 0 | 37000 | 7500 | 0 | 5000 | 0 | 0 | 5000 | 7500
E105 | CE | IGS | George Street, 15-19 | External refurbishments | 142500 | 6.79% | A | 15 |  |  |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  |  | 15000 | [5 empty] | 15000 | R |  |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 20000 | [5 empty] | 5000
E105 | CE | IGS | George Street, 15-19 | Refurbishment of common area | 142500 | 6.79% | A | 15 |  |  |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 | [5 empty] | 15000
E105 | CE | IGS | George Street, 15-19 | Replacement windows | 142500 | 6.79% | A | 15 |  |  |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | C | [5 empty] | 25000 | [5 empty] | 5000
E105 | CE | IGS | George Street, 15-19 | Roof / rooflight repairs | 142500 | 6.79% | A | 15 |  |  |  |  | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | C | [5 empty] | 20000 | [5 empty] | 5000
E108 | CE | IGS | George Street, 24/26 & Gloucester Street, 2 | External refurbishments | 153500 | 7.79% | A | 15 |  |  |  |  | 15 |  |  | 5 | 15 | 20 | 300 | 35 | B | 3 |  |  | 15000 | [5 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 10000 |  |  |  |  | 10000 | [8 empty] | Recurring cost every 5 years
E110 | CE | IGS | George Street, 33/35 | Major refurbishment | 55000 | 3.79% | A | 10 |  |  |  |  | 10 |  |  | 15 | 15 | 30 | 300 | 40 | C | 2 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 50000 | [13 empty] | Capital bid for 2011/12
E115 | CE | IGS | George Street, 42 | External refurbishments | 25000 | 14.04% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000 | [6 empty] | 10000 |  | Recurring cost every 5 years
E115 | CE | IGS | George Street, 42 | Masonry repairs | 25000 | 14.04% | A | 7 |  |  |  |  | 7 |  |  | 10 | 15 | 25 | 175 | 32 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [5 empty] | 3000 |  |  |  |  | 3000 | [6 empty] | 3000
E116 | CE | IGS | George Street, 44 | External refurbishments | 20000 | 9.3% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 12500 |  |  |  |  | 12500 |  |  |  | 12500 |  |  |  |  | Recurring cost every 5 years
E116 | CE | IGS | George Street, 44 | Masonry repairs | 20000 | 9.3% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | C | [5 empty] | 3000 |  |  |  |  | 3000
E358 | CE | IGS | George Street, 46 | External refurbishments | 17900 | 9.68% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000 |  |  |  | 10000
E358 | CE | IGS | George Street, 46 | Internal structural repairs | 17900 | 9.68% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000
E358 | CE | IGS | George Street, 46 | Masonry repairs | 17900 | 9.68% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000
E358 | CE | IGS | George Street, 46 | Replacement rainwater goods | 17900 | 9.68% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 3000 |  |  |  |  | 3000
E364 | CE | IGS | George Street, 46a (included with E358) | External refurbishments | 9600 | 17.78% |  | 3 |  |  |  |  | 3 |  |  | 10 | 15 | 25 | 75 | 28 | B | 2 | [8 empty] | 0 | R |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Investment ~ George Street | [41 empty] | 0 | 0 | 0 | 196500 | 0 | 0 |  | 0 | 66500 | 30000 | 0 | 0 | 22500 | 0 | 0 | 13000 | 0
R015 | CE | IL | Binsey Lane, | [9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R
| ----- | IO | Residential & Commercial Properties | Travellers and Gypsies |  |  | A | 15 |  |  |  |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | ---- | 2 | 1500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E063 | C | IO | Cave Street, Standingford House | Refurbishments and repairs |  |  | A |  |  | 10 | 10 |  | 20 |  |  | 10 | 10 | 20 | 400 | 40 | B | 3 |  |  | 125000 | [5 empty] | 125000 | R | Recurring cost every 5 years |  | 1 | 0 | 128750 | 0 | 0 | 0 | 128750 | R | [5 empty] | 15000 |  | 15000 | ü | [10 empty] | Recurring cost every 5 years
R125 | CE | IO | Princes Street, 44b | External refurbishments | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 7 | 10 | 17 | 170 | 27 | C | 2 |  |  |  |  | 25000 |  |  |  | 25000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 25750 | 0 | 25750 | R | [5 empty] | 25000 | [6 empty] | 25000 | [5 empty] | 25000 | Recurring cost every 5 years
R125 | CE | IO | Princes Street, 44b | Replace windows | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 10 | 7 | 17 | 170 | 27 | B | 3 | [5 empty] | 40000 |  |  | 40000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 41200 | 41200 | C | [5 empty] | 75000 | [6 empty] | 75000
R125 | CE | IO | Princes Street, 44b | Rewire building | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 10 | 7 | 17 | 170 | 27 | B | 3 | [5 empty] | 15000 |  |  | 15000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 15450 | 15450 | C | [5 empty] | 50000 | [6 empty] | 50000
| ----- | IO | Residential & Commercial Properties | Tree Maintenance |  |  | A |  | 7 |  |  |  | 7 | 5 | 7 |  | 10 | 22 | 154 | 29 | ---- | 2 | 2500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
R125 | CE | IO | Princes Street, 44b | Renew roof coverings | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 10 | 5 | 15 | 150 | 25 | B | 3 |  |  |  |  | 25000 |  |  |  | 25000 | C |  |  | 3 | 0 | 0 | 0 | 25750 | 0 | 25750 | C | [5 empty] | 50000
R125 | CE | IO | Princes Street, 44b | Renew rainwater goods | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 7 | 7 | 14 | 140 | 24 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 10300 | 0 | 10300 | C | [5 empty] | 10000
R125 | CE | IO | Princes Street, 44b | Replace heating system | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 3 | 10 | 13 | 130 | 23 | B | 3 |  |  |  |  | 20000 |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 0 | 20600 | 0 | 20600 | C | [5 empty] | 50000
E256 | CE* | IO | St. Clements, 16 | External refurbishments | 11500 | 11.96% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  |  |  | 15000 |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 15450 | 0 | 15450 | R | [5 empty] | 10000 |  |  |  | 10000 |  |  |  |  | 10000 |  |  |  |  | Recurring cost every 5 years
E256 | CE* | IO | St. Clements, 16 | Masonry repairs | 11500 | 11.96% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  |  |  | 2500 |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 0 | 2575 | 0 | 2575 | R | [5 empty] | 2500 |  |  |  | 2500
E256 | CE* | IO | St. Clements, 16 | Replacement windows | 11500 | 11.96% | A | 5 |  |  |  |  | 5 |  |  | 10 | 15 | 25 | 125 | 30 | B | 2 |  |  |  |  | 7500 |  |  |  | 7500 | C |  |  | 3 | 0 | 0 | 0 | 7725 | 0 | 7725 | C | [5 empty] | 7500 |  |  |  | 7500
R125 | CE | IO | Princes Street, 44b | Masonry repairs | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 5 | 7 | 12 | 120 | 22 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 | [6 empty] | 5000
E079 | CE | IO | Cowley Road, 66/66a | External refurbishments | 14500 | 7.32% | A | 5 |  |  |  |  | 5 |  |  | 5 | 15 | 20 | 100 | 25 | B | 2 |  |  |  | 3000 |  |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  | 3000 | [7 empty] | 3000 |  | Recurring cost every 5 years
E077 | CE | IO | Cowley Road, 38 | External refurbishments | 16500 | 11.38% | A | 5 |  |  |  |  | 5 |  |  | 5 | 10 | 15 | 75 | 20 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  |  | 3000 | [8 empty] | Recurring cost every 5 years
E077 | CE | IO | Cowley Road, 38 | Masonry Repairs | 16500 | 11.38% | A | 5 |  |  |  |  | 5 |  |  | 5 | 10 | 15 | 75 | 20 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  |  | 2000
E077 | CE | IO | Cowley Road, 38 | Roof repairs | 16500 | 11.38% | A | 5 |  |  |  |  | 5 |  |  | 5 | 10 | 15 | 75 | 20 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | C |  |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | C | [5 empty] | 1000 |  |  |  |  | 1000
E219 | C | IO | Northway Centre - Workshops | External refurbishments |  |  | D |  |  |  | 7 |  | 7 |  |  | 7 | 3 | 10 | 70 | 17 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1000 | [6 empty] | 1000
E219 | C | IO | Northway Centre - Workshops | Rainwater goods repairs |  |  | D |  |  |  | 7 |  | 7 |  |  | 7 | 3 | 10 | 70 | 17 | B | 2 |  |  | 500 | [5 empty] | 500 | R |  |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [5 empty] | 500 | [6 empty] | 500
E219 | C | IO | Northway Centre - Workshops | Window replacement |  |  | D |  |  |  | 7 |  | 7 |  |  | 7 | 3 | 10 | 70 | 17 | B | 2 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | C | [5 empty] | 5000 | [6 empty] | 5000
R125 | CE | IO | Princes Street, 44b | Reseal floors | 18000 | 8.04% | C | 5 |  |  | 5 |  | 10 |  |  | 3 | 3 | 6 | 60 | 16 | B | 3 |  |  |  |  | 6000 |  |  |  | 6000 | R |  |  | 1 | 0 | 0 | 0 | 6180 | 0 | 6180 | R | [5 empty] | 5000 | [6 empty] | 5000
H002 | CE* | IO | Albert Street, 9 | External refurbishments | 4200 | 11.05% | A | 3 |  |  |  |  | 3 |  |  | 5 | 7 | 12 | 36 | 15 | A | 3 | [5 empty] | 2000 |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 2060 | 2060 | R | [5 empty] | 3000 |  |  |  |  | 3000 | [8 empty] | Recurring cost every 5 years
H005 | CE | IO | Ashhurst Way, 32 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 5 | 3 | 8 | 24 | 11 | A | 3 | [5 empty] | 500 |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 515 | 515 | R | [5 empty] | 1000 | [5 empty] | 1000 | [7 empty] | Recurring cost every 5 years
H099 | CE* | IO | Horspath Road, 96/100 | External refurbishments | 8000 | 12.5% | A | 3 |  |  |  |  | 3 |  |  | 3 | 5 | 8 | 24 | 11 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 | [5 empty] | 500 | [7 empty] | Recurring cost every 5 years
H054 | C | IO | Catherine Street, 1a | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [5 empty] | 1000 | [13 empty] | Recurring cost every 5 years
H054 | C | IO | Catherine Street, 1a | Minor repair to rainwater goods |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 2 | [5 empty] | 1000 |  |  | 1000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 1030 | 1030 | R | [5 empty] | 1000
H058 | CE | IO | Cowley Road, 331 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  |  | 3000 | [8 empty] | Recurring cost every 5 years
H058 | CE | IO | Cowley Road, 331 | Minor external repairs |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 2 |  |  |  | 1000 |  |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  |  | 1000
E082 | CE | IO | Cowley Road, 81 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [8 empty] | Recurring cost every 5 years
E083 | C | IO | Cowley Road, 92 (floors 2/3/4) | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | C | 2 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 | [5 empty] | 10000 | [7 empty] | Recurring cost every 5 years
E084 | CE | IO | Cowley Road, 92 (ground floor) | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | C | 2 |  |  |  | 2500 |  |  |  |  | 2500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2575 | 0 | 0 | 2575 | R | [5 empty] | 2500 | [5 empty] | 2500 | [7 empty] | Recurring cost every 5 years
H081 | CE* | IO | Furlong Close, 1 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1000 | [5 empty] | 1000 | [7 empty] | Recurring cost every 5 years
E161 | CE | IO | Hollow Way, 68 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  |  | 2000 | [8 empty] | Recurring cost every 5 years
H098 | CE* | IO | Horspath Road, 104 | External refurbishments | 5500 | 12.22% | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | A | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 | [5 empty] | 500 | [7 empty] | Recurring cost every 5 years
E190 |  | IO | Magdalen Punt Station | Gate and Fence | 7250 | 10.21% | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 |  | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 4 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 5000 | [5 empty] | 5000
H050 | CE | IO | Bullingdon Road, 78 | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [19 empty] | Recurring cost every 5 years
H145 | CE | IO | Rectory Road, 39/41/42 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000 | [8 empty] | Recurring cost every 5 years
H146 | CE | IO | Regent Street, 2 | External refurbishments |  |  | A | 3 |  |  |  |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 1500 | [5 empty] | 1500 | [7 empty] | Recurring cost every 5 years
|  |  | Investment ~ Outer City | [41 empty] | 0 | 0 | 0 | 203500 | 0 | 15000 |  | 23000 | 30000 | 22000 | 16500 | 0 | 10000 | 0 | 0 | 3000 | 0
E273 | CE | ISMS | Northgate Hall | Reactive Maintenance & Minor Repair |  |  |  | 5 |  |  | 5 | 5 | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | C | 2 | 1000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E273 | CE | ISMS | Northgate Hall | Electrical Inspections and Repairs |  |  | C | 5 |  |  | 5 | 5 | 15 |  | 10 |  | 15 | 25 | 375 | 40 | C | 2 |  | 5000 | [6 empty] | 5000 | R |  |  | 3 | 5150 | 0 | 0 | 0 | 0 | 5150 | R | [5 empty] | 10000 | [5 empty] | 10000
E273 | CE | ISMS | Northgate Hall | External Repairs and Refurbishment |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 3 |  | 15000 | [6 empty] | 15000 | R |  |  | 3 | 15450 | 0 | 0 | 0 | 0 | 15450 | R | [5 empty] | 20000 | [5 empty] | 20000
E273 | CE | ISMS | Northgate Hall | Plaster repairs and Refurbishment |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 2 |  | 4000 | [6 empty] | 4000 | R |  |  | 1 | 4120 | 0 | 0 | 0 | 0 | 4120 | R | [5 empty] | 15000
E273 | CE | ISMS | Northgate Hall | Repair rainwater goods |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 15 | 10 | 25 | 375 | 40 | C | 1 |  | 10000 | [6 empty] | 10000 | R |  |  | 3 | 10300 | 0 | 0 | 0 | 0 | 10300 | R | [5 empty] | 5000 | 5000
E273 | CE | ISMS | Northgate Hall | Renew / repair floor coverings |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 3 |  |  |  |  | 7500 |  |  |  | 7500 | R |  |  | 1 | 0 | 0 | 0 | 7725 | 0 | 7725 | R | [5 empty] | 10000
E273 | CE | ISMS | Northgate Hall | Repair / overhaul windows |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 10 | 7 | 17 | 255 | 32 | C | 2 |  |  | 7500 | [5 empty] | 7500 | R |  |  | 3 | 0 | 7725 | 0 | 0 | 0 | 7725 | R | [5 empty] | 10000
E273 | CE | ISMS | Northgate Hall | Rewire building |  |  | C | 5 |  |  | 5 | 5 | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  | 10000 | [6 empty] | 10000 | C |  |  | 3 | 10300 | 0 | 0 | 0 | 0 | 10300 | C | [5 empty] | 50000
E281 | CE | ISMS | St. Michael Streer, 6 (g. floor & basement) | External refurbishments | 19500 | 8.99% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 10000 |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 10300 | 10300 | R | [5 empty] | 5000 |  |  |  | 5000 |  |  |  |  | 5000 |  |  |  |  | Recurring cost every 5 years
E274 | CE | ISMS | St. Michael Street, 2 | External refurbishments | 19100 | 9.23% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 7000 |  |  | 7000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 7210 | 7210 | R | [5 empty] | 7500 |  |  |  | 7500 |  |  |  |  | 7500 |  |  |  |  | Recurring cost every 5 years
E280 | CE | ISMS | St. Michael Street, 4 | External refurbishments | 11200 | 9.57% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 10000 |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 10300 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 |  |  |  |  | 10000 |  |  |  |  | Recurring cost every 5 years
E278 | CE | ISMS | St. Michaels Street, 26 | External refurbishments | 21000 | 9.81% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | C | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 10000 |  | 10000 | ü | [5 empty] | 10000 |  |  |  |  | Recurring cost every 5 years
E278 | CE | ISMS | St. Michaels Street, 26 | Window repairs / replacement | 21000 | 9.81% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 3000 |  | 3000 | ü | [5 empty] | 3000
E282 | CE | ISMS | St. Michaels street, 6/8 (upper floors) | External refurbishments | 20000 | 11.76% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 10000 |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 10300 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 |  |  |  |  | 10000 |  |  |  |  | Recurring cost every 5 years
E271 | CE | ISMS | St. Michaels Street, 10 | External refurbishments | 500 | 1.47% | A | 3 |  |  |  | 5 | 8 |  |  | 10 | 15 | 25 | 200 | 33 | B | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R | [5 empty] | 2500 |  |  |  |  | 3000
E275 | CE | ISMS | St. Michael Street, 20/22 | External refurbishments |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | C | 3 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 7500 |  |  |  |  | 7500 | [8 empty] | Recurring cost every 5 years
E275 | CE | ISMS | St. Michael Street, 20/22 | Masonry repairs |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | C | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  |  | 2000 | [8 empty] | Recurring cost every 5 years
E275 | CE | ISMS | St. Michael Street, 20/22 | Structural repairs |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | C | 3 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | C | [5 empty] | 10000 |  |  |  |  | 10000
E275 | CE | ISMS | St. Michael Street, 20/22 | Window rpairs / replacement |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | C | 3 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  |  | 3000
E260 | CE | ISMS | St. Michael Street, 28/32 | [9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | [9 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R
E276 | CE | ISMS | St. Michaels Street, 24 (part) | External refurbishments |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [8 empty] | Recurring cost every 5 years
E276 | CE | ISMS | St. Michaels Street, 24 (part) | Minor roof repairs |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 2500 |  |  |  |  | 3000
E276 | CE | ISMS | St. Michaels Street, 24 (part) | Window repairs / replacement |  |  | A | 3 |  |  |  | 5 | 8 |  |  | 7 | 7 | 14 | 112 | 22 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 3 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000
|  |  | Investment ~ St Michael Street | [41 empty] | 0 | 0 | 0 | 207000 | 5000 | 13000 |  | 32500 | 43500 | 30000 | 0 | 0 | 45500 | 0 | 0 | 0 | 0
E239 | CE | ISS | Ship Street, 1 & 2 | External refurbishments | 54000 | 9.39% | A | 10 |  |  |  | 5 | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  | 10000 | ü | [6 empty] | 10000 |  |  |  | Recurring cost every 5 years
E239 | CE | ISS | Ship Street, 1 & 2 | Replace / repair windows | 54000 | 9.39% | A | 10 |  |  |  | 5 | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 2 |  |  |  | 10000 |  |  |  |  | 10000 | C |  |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | C | [5 empty] | 10000 |  | 10000 | ü
E246 | CE | ISS | Ship Street, 5 | External refurbishments | 18500 | 13.7% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 |  |  |  | 15000 |  |  |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 15450 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  |  |  | 15000 |  |  |  |  | 15000 |  |  |  |  | Recurring cost every 5 years
E247 | CE | ISS | Ship Street, 6, 7 & Part 8 | External refurbishments | 21500 | 5.27% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 10000 |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 10300 | 10300 | R | [5 empty] | 10000 |  |  |  | 10000 | [6 empty] | 10000 |  |  | Recurring cost every 5 years
E248 | CE | ISS | Ship Street, 8/9 | External refurbishments | 19250 | 10.41% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 12000 |  |  | 12000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 12360 | 12360 | R | [5 empty] | 12500 |  |  |  | 10000 | [6 empty] | 10000 |  |  | Recurring cost every 5 years
E248 | CE | ISS | Ship Street, 8/9 | Timber repairs | 19250 | 10.41% | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 15 | 25 | 250 | 35 | B | 3 | [5 empty] | 3000 |  |  | 3000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 3090 | 3090 | R | [5 empty] | 3000 |  |  |  | 3000
E240 | CE | ISS | Ship Street, 10 | External refurbishments |  |  | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 10 | 20 | 200 | 30 | B | 3 |  |  |  |  | 7500 |  |  |  | 7500 | R |  |  | 1 | 0 | 0 | 0 | 7725 | 0 | 7725 | R | [5 empty] | 7500 |  |  |  | 7500
E240 | CE | ISS | Ship Street, 10 | Minor roof repairs |  |  | A | 5 |  |  |  | 5 | 10 |  |  | 10 | 10 | 20 | 200 | 30 | B | 3 |  |  |  |  | 1500 |  |  |  | 1500 | R |  |  | 1 | 0 | 0 | 0 | 1545 | 0 | 1545 | R | [5 empty] | 1500 |  |  |  | 1500
|  |  | Investment ~ Ship Street | [41 empty] | 0 | 0 | 0 | 69500 | 0 | 20000 |  | 47000 | 0 | 0 | 0 | 0 | 15000 | 10000 | 20000 | 0 | 0
E294 | CE | ITS | Turl Street, 16 | Structural repairs | 57000 | 9.19% | A | 10 |  |  |  | 5 | 15 |  |  | 10 | 15 | 25 | 375 | 40 | B | 3 | [5 empty] | 15000 |  |  | 15000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 15450 | 15450 | C | [5 empty] | 15000 |  |  |  | 15000
E294 | CE | ITS | Turl Street, 16 | External refurbishments | 57000 | 9.19% | A | 10 |  |  |  | 5 | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 | [5 empty] | 15000 |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 15450 | 15450 | R | [5 empty] | 15000 |  |  |  | 15000 | [6 empty] | 15000 |  |  | Recurring cost every 5 years
E295 | CE | ITS | Turl Street, 17 | External refurbishments | 36500 | 9.76% | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 15 | 25 | 300 | 37 | B | 3 |  |  |  |  | 12000 |  |  |  | 12000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 12360 | 0 | 12360 | R | [5 empty] | 12500 |  |  |  | 12500 |  |  |  |  | 12500 |  |  |  |  | Recurring cost every 5 years
E295 | CE | ITS | Turl Street, 17 | Render repairs | 36500 | 9.76% | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 15 | 25 | 300 | 37 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000
E296 | CE | ITS | Turl Street, 18/19 | External refurbishments | 42000 | 10% | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 15 | 25 | 300 | 37 | B | 3 |  |  | 15000 | [5 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R | [5 empty] | 15000 |  |  |  | 15000 |  |  |  |  | 15000 |  |  |  |  | Recurring cost every 5 years
E296 | CE | ITS | Turl Street, 18/19 | Masonry repairs | 42000 | 10% | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 15 | 25 | 300 | 37 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000
E296 | CE | ITS | Turl Street, 18/19 | Window repairs / replacement | 42000 | 10% | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 15 | 25 | 300 | 37 | B | 3 |  |  | 3000 | [5 empty] | 3000 | R |  |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 5000 |  |  |  | 5000
E297 | CE | ITS | Turl Street, 18a | External refurbishments |  |  | A | 7 |  |  |  | 5 | 12 |  |  | 10 | 10 | 20 | 240 | 32 | B | 3 | [5 empty] | 15000 |  |  | 15000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 15450 | 15450 | R | [5 empty] | 2500 |  |  |  | 2500 | [9 empty] | Recurring cost every 5 years
|  |  | Investment ~ Turl Street | [41 empty] | 0 | 0 | 0 | 75000 | 0 | 0 |  | 75000 | 0 | 0 | 0 | 0 | 27500 | 0 | 15000 | 0 | 0
|  | LA | Allotments | Reactive Maintenance & Minor Repair | [6 empty] | 15 |  | 15 | 10 | 5 | 5 | 5 | 25 | 375 | 40 | ---- | 2 | 11500 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Leisure ~ Allotments | [41 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| C | LC | Cemeteries | Reactive Maintenance & Minor Repair | [5 empty] | 15 | 15 |  | 30 | 15 | 15 |  | 15 | 45 | 1350 | 75 | ---- | 2 | 3000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E213 | C | LC | Botley Cemetery - Chapel | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 10 | 7 | 17 | 425 | 42 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R |  | 0 |  |  |  | 5000 |  | 5000 | ü | [6 empty] | 5000 |  |  |  | Recurring cost every 5 years
E095 | C | LC | Headington Cemetery - Chapel | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 10 | 7 | 17 | 425 | 42 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R |  | 0 |  |  |  | 5000 |  |  |  |  | 5000 | [5 empty] | 5000 |  |  | Recurring cost every 5 years
E095 | C | LC | Headington Cemetery - Chapel | Roof repairs |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 10 | 7 | 17 | 425 | 42 | B | 2 |  |  |  | 2000 |  |  |  |  | 2000 | C |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | C |  | 0 |  |  |  | 20000 |  |  |  |  | 20000
E066 | C | LC | Rose Hill Cemetery - Chapel | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 10 | 7 | 17 | 425 | 42 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R |  | 0 |  |  |  | 5000 |  | 5000 | ü | [6 empty] | 5000 |  |  |  | Recurring cost every 5 years
E312 | C | LC | Wolvercote Cemetery - Chapel | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 10 | 7 | 17 | 425 | 42 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R |  | 0 |  |  |  | 5000 |  |  |  | 5000 | [6 empty] | 5000 |  |  | Recurring cost every 5 years
E213 | C | LC | Botley Cemetery - Mess Room | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 1000 |  | 1000 | ü | [6 empty] | 1000 |  |  |  | Recurring cost every 5 years
E213 | C | LC | Botley Cemetery - Toilet | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 1000 |  | 1000 | ü | [6 empty] | 1000 |  |  |  | Recurring cost every 5 years
E095 | C | LC | Headington Cemetery - Mess Room | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
E095 | C | LC | Headington Cemetery - Mess Room | Masonry repairs |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R |  |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500
E095 | C | LC | Headington Cemetery - Toilets | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
E066 | C | LC | Rose Hill Cemetery - Mess Room | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 500 |  |  |  | 500 | [5 empty] | 500 |  |  |  | Recurring cost every 5 years
E066 | C | LC | Rose Hill Cemetery - Toilets | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [5 empty] | 500 |  |  |  | Recurring cost every 5 years
E066 | C | LC | Rose Hill Cemetery - Toilets | Repairs to roof and rainwater goods |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 1000 |  |  |  | 1000
E312 | C | LC | Wolvercote Cemetery - Chapel | Masonry repairs |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 2 |  | 3000 | [6 empty] | 3000 | R |  |  | 1 | 3090 | 0 | 0 | 0 | 0 | 3090 | R | [5 empty] | 1500 |  |  |  | 1500
E312 | C | LC | Wolvercote Cemetery - Mess Room | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
E312 | C | LC | Wolvercote Cemetery - Toilets | External refurbishments |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 7 | 5 | 12 | 300 | 37 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
E213 | C | LC | Botley Cemetery | Construct Chapel Waiting Room |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | ---- | 3 |  |  |  |  | 20000 |  |  |  | 20000 | C |  |  | 4 | 0 | 0 | 0 | 20600 | 0 | 20600 | C | [5 empty] | 25000
E213 | C | LC | Botley Cemetery | Refurbishment / repair to fences and gates |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 7 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 | [5 empty] | 5000 |  | Recurring cost every 7 years
E095 | C | LC | Headington Cemetery | Refurbishment / repair to fences and gates |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 7 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 | [5 empty] | 2000 | [6 empty] | 2000 | Recurring cost every 7 years
E066 | C | LC | Rose Hill Cemetery | Refurbishment / repair to fences and gates |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 7 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 | [5 empty] | 5000 | [6 empty] | 5000 | Recurring cost every 7 years
E066 | C | LC | Rose Hill Cemetery - Chapel | Replace window guards |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 2 |  |  |  |  | 3000 |  |  |  | 3000 | R |  |  | 3 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 1500 |  | 1500 | ü
E312 | C | LC | Wolvercote Cemetery | Construct Chapel Waiting Room |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | --- | 3 |  | 10000 | [6 empty] | 10000 | C |  |  | 4 | 20600 | 0 | 0 | 0 | 0 | 20600 | C | [5 empty] | 25000
E312 | C | LC | Wolvercote Cemetery | Refurbishment / repair to fences and gates |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 3 |  |  |  |  | 3000 |  |  |  | 3000 | R | Recurring cost every 7 years |  | 1 | 0 | 0 | 0 | 3090 | 0 | 3090 | R | [5 empty] | 3000 | [5 empty] | 3000 | [6 empty] | 3000 | Recurring cost every 7 years
E312 | C | LC | Wolvercote Cemetery - Chapel | Replace window guards |  |  | A |  |  | 15 | 10 |  | 25 |  |  | 5 | 3 | 8 | 200 | 33 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 3 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 1500 |  |  |  | 1500
|  |  | Leisure ~ Cemeteries | [41 empty] | 0 | 0 | 0 | 116000 | 0 | 13500 |  | 12500 | 25000 | 15000 | 0 | 0 | 0 | 13000 | 12000 | 5000 | 10000
| C | LCS | Shotover Country Park | Replacement public toilets |  |  | D |  |  |  | 15 |  | 15 |  |  | 3 | 3 | 6 | 90 | 21 | ---- | 3 |  |  | 50000 | [5 empty] | 50000 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C
| C | LCS | Shotover Country Park | Demolish clcosed public toilets |  |  | D |  |  |  | 3 |  | 3 |  | 5 | 5 | 3 | 13 | 39 |  | D | 2 | [19 empty] | R | [5 empty] | 5000 | [6 empty] | 5000
R026 | C | LCS | Brasenose Farm Depot - Office & Mess Room | External refurbishment and repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R
R026 | C | LCS | Brasenose Farm Depot - Office & Mess Room | Reactive Maintenance & Minor Repair | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 | 5000 |  |  |  | 3000 |  |  |  | 3000 | R |  |  | 2 | 0 | 0 | 0 | 3090 | 0 | 3090 | R
R026 | C | LCS | Brasenose Farm Depot - Barn | Masonry repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | C
R026 | C | LCS | Brasenose Farm Depot - Barn | New doors and external timbers | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  |  | 4000 | [5 empty] | 4000 | R |  |  | 3 | 0 | 4120 | 0 | 0 | 0 | 4120 | R
R026 | C | LCS | Brasenose Farm Depot - Barn | Replacement rainwater goods | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  |  | 2000 | [5 empty] | 2000 | C |  |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | C
R026 | C | LCS | Brasenose Farm Depot - Barn | Roof repairs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | C | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | C
|  |  | Leisure ~ Countryside | [41 empty] | 0 | 0 | 0 | 5000 | 0 | 0 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0
R073 | C | LPD | Florence Park | Automatic gates |  |  | A |  |  | 15 |  |  | 15 |  | 5 | 10 | 10 | 25 | 375 | 40 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1500 | 10000
R050 | C | LPD | Cutteslowe Park Depot - Building 1 | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü | [5 empty] | 5000 |  |  |  |  | Recurring cost every 4 years
R050 | C | LPD | Cutteslowe Park Depot - Building 1 | Replace asbestos cement roof and rainwater goods |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 3 | 0 | 0 | 10000 | 0 | 0 | 10000 | C | [5 empty] | 15000 |  | 15000 | ü
R050 | C | LPD | Cutteslowe Park Depot - Building 2 | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü | [5 empty] | 5000 |  |  |  |  | Recurring cost every 4 years
R050 | C | LPD | Cutteslowe Park Depot - Building 2 | Replace asbestos cement roof and rainwater goods |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 3 | 0 | 0 | 10000 | 0 | 0 | 10000 | C | [5 empty] | 15000 |  | 15000 | ü
R050 | C | LPD | Cutteslowe Park Depot - Building 3 | External refurbishments and masonry repairs repairs |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 2500 |  |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 2575 | 0 | 0 | 2575 | R | [5 empty] | 3000 |  | 3000 | ü | [5 empty] | 3000 |  |  |  |  | Recurring cost every 4 years
R050 | C | LPD | Cutteslowe Park Depot - Building 4 | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü | [5 empty] | 5000 |  |  |  |  | Recurring cost every 4 years
R050 | C | LPD | Cutteslowe Park Depot - Building 4 | Replace asbestos cement roof and rainwater goods |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 3 | 0 | 0 | 10000 | 0 | 0 | 10000 | C | [5 empty] | 15000 |  | 15000 | ü
R050 | C | LPD | Cutteslowe Park Depot - Building 5 | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 1500 |  |  |  | 1500 | R |  |  | 1 | 0 | 0 | 0 | 1545 | 0 | 1545 | R | [5 empty] | 2000 |  | 2000 | ü | [5 empty] | 2000 |  |  |  | 2000 | Recurring cost every 4 years
R143 | C | LPD | South Park Depot - Barn | External refurbishments |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 5000 | [6 empty] | 5000 |  |  |  |  | 5000 |  | Recurring cost every 5 years
R143 | C | LPD | South Park Depot - Barn | Masonry repairs |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | C |  |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | C | [5 empty] | 10000 | [6 empty] | 10000
R143 | C | LPD | South Park Depot - Barn | Replace barn doors |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | C |  |  | 3 | 0 | 0 | 3090 | 0 | 0 | 3090 | C | [5 empty] | 3000 | [6 empty] | 3000
R143 | C | LPD | South Park Depot - Barn | Structural timber repairs |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 20600 | 0 | 0 | 20600 | C | [5 empty] | 20000 | [6 empty] | 20000
R143 | C | LPD | South Park Depot - Garage | Minor repairs |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | C |  |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | C | [5 empty] | 500 | [6 empty] | 500
R143 | C | LPD | South Park Depot - Mess Room | External refurbishments |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2000 | [6 empty] | 1000 | [5 empty] | 2000 | Recurring cost every 5 years
R073 | C | LPD | Florence Park Depot - Garages | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000 | [5 empty] | 5000 |  |  |  | Recurring cost every 5 years
R073 | C | LPD | Florence Park Depot - Mess Room | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2000 |  |  |  | 2000 | [6 empty] | 2000 |  |  | Recurring cost every 5 years
R073 | C | LPD | Florence Park Depot - Mess Room | Replace rainwater goods |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1500 |  |  |  | 1500
R073 | C | LPD | Florence Park Depot - Mess Room | Roof repairs |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1500 |  |  |  | 1500
R083 | C | LPD | Horspath Road RG Parks depot | External refurbishments |  |  | A |  |  | 15 |  |  | 15 |  |  | 3 | 10 | 13 | 195 | 28 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 2500 |  |  |  | 2500 | [6 empty] | 2500 |  |  | Recurring cost every 5 years
R073 | C | LPD | Florence Park Depot - Garages | Replace asbestos cement roof sheets |  |  | A |  |  | 15 |  |  | 15 |  |  | 7 | 5 | 12 | 180 | 27 | B | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 15000 |  |  |  | 15000
R143 | C | LPD | South Park Depot - Office | External refurbishments |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | B | 3 | [5 empty] | 500 |  |  | 500 | R |  |  | 1 | 0 | 0 | 0 | 0 | 515 | 515 | R | [5 empty] | 700 | [6 empty] | 500
R143 | C | LPD | South Park Depot - Office | replacement windows |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 5 | 10 | 150 | 25 | B | 3 | [5 empty] | 500 |  |  | 500 | R |  |  | 1 | 0 | 0 | 0 | 0 | 515 | 515 | R | [5 empty] | 500 | [6 empty] | 500
R050 | C | LPD | Cutteslowe Park Depot - Greenhouses | External refurbishments |  |  | A |  |  | 7 |  |  | 7 |  |  | 5 | 5 | 10 | 70 | 17 | B | 3 |  |  |  |  | 15000 |  |  |  | 15000 | R |  |  | 1 | 0 | 0 | 0 | 15450 | 0 | 15450 | R | [5 empty] | 15000 | [5 empty] | 15000
R196 | C | LPD | Bury Knowle Park Depot - Mess room | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 3 | 10 | 50 | 15 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 1000 | [6 empty] | 1000
R196 | C | LPD | Bury Knowle Park Depot - Store | External refurbishments |  |  | C |  |  | 5 |  |  | 5 |  |  | 7 | 3 | 10 | 50 | 15 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 1500 | [6 empty] | 1500
|  |  | Leisure ~ Depots | [41 empty] | 0 | 0 | 0 | 153200 | 10000 | 65000 |  | 27500 | 0 | 15000 | 43000 | 0 | 20000 | 5000 | 4500 | 5000 | 4000
| C | LPP | Parks Pavilions | Services Maintenance | [5 empty] | 15 | 15 |  | 30 | 15 | 15 |  | 15 | 45 | 1350 | 75 | ---- | 2 | 10000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
R011 | C | LPP | Barton RG Pavilion | DDA Improvements |  |  | D |  |  | 10 | 10 |  | 20 | 15 |  | 15 | 15 | 45 | 900 | 65 | C | 2 |  |  | 20000 | [5 empty] | 20000 | C |  |  | 4 | 0 | 20600 | 0 | 0 | 0 | 20600 | C | [5 empty] | 75000 | [7 empty] | 75000 | [5 empty] | Not required if proposed pavilion replacement goes ahead
R011 | CES | LPP | Barton RG Pavilion | Major refurbishment and re-configuration |  |  | D |  |  | 10 | 10 |  | 20 |  |  | 15 | 15 | 30 | 600 | 50 | C | 2 |  |  | 250000 | [5 empty] | 250000 | R |  |  | 1 | 0 | 257500 | 0 | 0 | 0 | 257500 | R | [5 empty] | 250000 |  |  |  |  | 250000 | [8 empty] | Not required if proposed pavilion replacement goes ahead
R085 | C | LPP | Horspath RG Pavilion | DDA Access lift |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  | 15 | 30 | 450 | 45 | B | 2 |  |  | 30000 | [5 empty] | 30000 | C |  |  | 4 | 0 | 30900 | 0 | 0 | 0 | 30900 | C | 15000 | 15000 |  |  |  | 50000 |  | 100000 | ü | [10 empty] | Subject to pavilion review
| C | LPP | Quarry Fields RG Pavilion | DDA Improvements |  |  | B |  |  |  | 15 |  | 15 | 15 |  |  | 15 | 30 | 450 | 45 | C | 2 |  |  | 24500 | [5 empty] | 24500 | C |  |  | 4 | 0 | 25235 | 0 | 0 | 0 | 25235 | C |  | 15000 |  |  |  | 50000 |  |  |  |  | 50000 | [8 empty] | Subject to pavilion review
| C | LPP | Quarry Fields RG Pavilion | External refurbishments |  |  | B |  |  |  | 15 |  | 15 | 0 |  | 15 | 15 | 30 | 450 | 45 | C | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R |  | 15000 |  |  |  | 7500 |  |  |  |  | 7500 | [8 empty] | Subject to pavilion review
R011 | C | LPP | Barton RG Pavilion | External refurbishments |  |  | D |  |  | 10 | 10 |  | 20 |  |  | 10 | 10 | 20 | 400 | 40 | C | 2 |  | 15000 | [6 empty] | 15000 | R | Recurring cost every 5 years |  | 1 | 15450 | 0 | 0 | 0 | 0 | 15450 | R | [5 empty] | 10000 |  |  |  |  | 10000
R052 | C | LPP | Cutteslowe Park Upper (West) Pavilion | DDA Improvements & internal alterations |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  | 10 | 25 | 375 | 40 | C | 2 |  |  | 24000 | [5 empty] | 24000 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C |  | 0 |  |  |  | 100000 |  |  |  | 100000 | [9 empty] | Subject to pavilion review
R052 | C | LPP | Cutteslowe Park Upper (West) Pavilion | Major internal refurbishment |  |  | A |  |  |  | 15 |  | 15 | 15 |  |  | 10 | 25 | 375 | 40 | C | 2 |  |  | 30000 | [5 empty] | 30000 | C |  |  | 3 | 0 | 30900 | 0 | 0 | 0 | 30900 | C |  | 0 |  |  |  | 50000 |  |  |  | 50000 | [9 empty] | Subject to pavilion review
| C | LPP | Sandy Lane RG Pavilion | DDA Improvements |  |  | A |  |  |  | 15 |  | 15 | 10 |  |  | 15 | 25 | 375 | 40 | C | 2 |  |  | 15000 | [5 empty] | 15000 | C |  |  | 4 | 0 | 15450 | 0 | 0 | 0 | 15450 | C | [5 empty] | 50000 |  |  |  | 50000 | [9 empty] | Subject to pavilion review
| C | LPP | Quarry Fields RG Pavilion | Alterations to incorpoprate disused public toilet |  |  | B |  |  |  | 15 |  | 15 |  |  | 15 | 7 | 22 | 330 | 37 | C | 3 |  |  | 10000 | [5 empty] | 10000 | C |  |  | 4 | 0 | 75000 | 0 | 0 | 0 | 75000 | C | [5 empty] | 50000 |  |  |  |  | 50000 | [8 empty] | Subject to pavilion review
R052 | C | LPP | Cutteslowe Park (East) Pavilion Boiler House | External refurbishments |  |  | C |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000 | [6 empty] | 50000 |  |  | Recurring cost every 5 years Possible redevelopment
R043 | C | LPP | Cowley Marsh RG Pavilion | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 5000 |  |  |  | 5000 | [5 empty] | 5000 |  |  |  | Recurring cost every 5 years
R052 | C | LPP | Cutteslowe Park (East) Pavilion | DDA Improvements |  |  | C |  |  |  | 15 |  | 15 | 7 |  |  | 10 | 17 | 255 | 32 | B | 2 |  | 15000 | [6 empty] | 15000 | C |  |  | 4 | 15450 | 0 | 0 | 0 | 0 | 15450 | C | [5 empty] | 125000 |  |  |  |  | 125000 | [8 empty] | Subject to pavilion review
R052 | C | LPP | Cutteslowe Park (East) Pavilion | External refurbishments |  |  | C |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  | 3000 | [6 empty] | 3000 |  |  | Possible redevelopment
R052 | C | LPP | Cutteslowe Park Upper (West) Pavilion | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | C | 3 | [5 empty] | 5000 |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000 | [6 empty] | 5000 |  |  | Recurring cost every 5 years
| C | LPP | Florence Park Toilets | External refurbishments |  |  | B |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | C | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 1000 |  |  |  |  | 1000 | [6 empty] | 1000 |  | Recurring cost every 5 years
R085 | C | LPP | Horspath RG Pavilion | Brickwork repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  | 5000 | ü
R085 | C | LPP | Horspath RG Pavilion | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 10 | 17 | 255 | 32 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 2500 |  | 2500 | ü | [6 empty] | 2000 |  |  |  | Recurring cost every 5 years
R135 | C | LPP | Rose Hill RG Pavilion | External refurbishment |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  |  | 2500 |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 0 | 2575 | 0 | 2575 | R | [5 empty] | 2500 |  |  |  |  | 2500 | [6 empty] | 2500 |  | Recurring cost every 5 years
R135 | C | LPP | Rose Hill RG Pavilion | Replace rainwater goods |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 2500 |  |  |  |  | 2500
R043 | C | LPP | Cowley Marsh RG Pavilion | Rainwater goods repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 2 |  |  | 500 | [5 empty] | 500 | R |  |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [5 empty] | 5000 |  |  |  | 5000
R052 | C | LPP | Cutteslowe Park Bowls Pavilion - All | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 10 | 15 | 225 | 30 | B | 3 | [5 empty] | 3000 |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 3090 | 3090 | R | [5 empty] | 1500 |  |  |  | 1500 | [5 empty] | 1500 |  |  |  | Recurring cost every 5 years
R135 | C | LPP | Rose Hill RG Pavilion | Replace roof covering |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 2 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 3 | 0 | 5150 | 0 | 0 | 0 | 5150 | C | [5 empty] | 50000 |  |  |  |  | 50000 | [8 empty] | Subject to pavilion review
R135 | C | LPP | Rose Hill RG Pavilion | Window re-glazing |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 1500 |  |  |  |  | 1500
R040 | C | LPP | Court Place Farm Stadium Pavilion | External refurbishments |  |  | Leased |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000 | [6 empty] | 5000 |  |  | Recurring cost every 5 years
R043 | C | LPP | Cowley Marsh RG Pavilion | Roof repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 7 | 7 | 14 | 210 | 29 | B | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 1 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 5000 |  |  |  | 5000
| C | LPP | Alexandra Courts Changing Rooms | External refurbishments |  |  | Leased |  |  |  | 10 |  | 10 |  |  | 10 | 10 | 20 | 200 | 30 | C | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1545 | 0 | 0 | 1545 | R | [5 empty] | 1500 |  | 3000 | ü | [6 empty] | 1500 |  |  |  | Recurring cost every 5 years
R039 | C | LPP | Court Place Farm RG Pavilion | External refurbishments |  |  | A |  |  |  | 10 |  | 10 |  |  | 10 | 10 | 20 | 200 | 30 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 10000 |  |  |  | 10000 | [9 empty] | Recurring cost every 5 years
R039 | C | LPP | Court Place Farm RG Pavilion | External timber repairs |  |  | A |  |  |  | 10 |  | 10 |  |  | 10 | 10 | 20 | 200 | 30 | B | 3 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R | [5 empty] | 7500 |  |  |  | 7500 | [8 empty] | 7500
R072 | C | LPP | Florence Park Pavilion | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000 | [6 empty] | 5000 |  | Recurring cost every 5 years
R072 | C | LPP | Florence Park Pavilion | Replace rainwater goods |  |  | A |  |  |  | 15 |  | 15 |  |  | 5 | 7 | 12 | 180 | 27 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 1000 |  |  |  |  | 1000
| C | LPP | Alexandra Courts Attendants Hut | External refurbishments |  |  | A |  |  | 10 |  |  | 10 |  |  | 10 | 7 | 17 | 170 | 27 | C | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  |  | 1000 | [6 empty] | 1000 |  | Recurring cost every 5 years
| C | LPP | Alexandra Courts Garage | External refurbishments |  |  | A |  |  | 10 |  |  | 10 |  |  | 10 | 5 | 15 | 150 | 25 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 3000 |  |  |  | 3000 | [7 empty] | 3000 |  | Recurring cost every 5 years
R039 | C | LPP | Court Place Farm RG Pavilion | Roof repairs |  |  | A |  |  |  | 10 |  | 10 |  |  | 7 | 7 | 14 | 140 | 24 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 15000 |  |  |  | 15000
R052 | C | LPP | Cutteslowe Park Toilets | External refurbishments |  |  | C |  |  |  | 7 |  | 7 |  |  | 5 | 15 | 20 | 140 | 27 | C | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2500 |  |  |  | 2500 | [6 empty] | 2500 |  |  | Recurring cost every 5 years
R052 | C | LPP | Cutteslowe Park Toilets | Internal refurbishment and alteration |  |  | C |  |  |  | 7 |  | 7 |  |  | 5 | 15 | 20 | 140 | 27 | C | 2 |  |  | 25000 | [5 empty] | 25000 | C |  |  | 1 | 0 |  | 0 | 0 | 0 | 0 | C | [5 empty] | 25000 |  |  |  | 25000
R070 | CE | LPP | Five Mile Drive RG Clubhouse | Major internal refurbishment |  |  | C |  |  |  | 7 |  | 7 | 15 |  |  | 3 | 18 | 126 | 25 | D | 3 | [5 empty] | 30000 |  |  | 30000 | C |  |  | 4 | 0 | 0 | 0 | 0 | 30900 | 30900 | C | [5 empty] | 100000 |  |  |  | 100000 | [9 empty] | Subject to pavilion review
R070 | CE | LPP | Five Mile Drive RG Clubhouse | Replace rainwater goods |  |  | C |  |  |  | 7 |  | 7 |  |  | 15 | 3 | 18 | 126 | 25 | D | 2 |  |  |  | 3000 |  |  |  |  | 3000 | R |  |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 2500 |  |  |  | 2500 | [9 empty] | Buildings future to be considered ~ very poor condition
R070 | C | LPP | Five Mile Drive RG Pavilion | DDA Improvements |  |  | C |  |  |  | 7 |  | 7 | 15 |  |  | 3 | 18 | 126 | 25 | D | 2 |  |  | 25000 | [5 empty] | 25000 | C |  |  | 4 | 0 | 25750 | 0 | 0 | 0 | 25750 | C | [5 empty] | 50000 |  |  |  | 50000 | [9 empty] | Subject to pavilion review
R143 | C | LPP | South Park Pavilion | External refurbishments |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 3 | 8 | 120 | 23 | C | 3 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [19 empty] | Recurring cost every 5 years
R143 | C | LPP | South Park Pavilion | Major internal refurbishment |  |  | C |  |  | 15 |  |  | 15 |  |  | 5 | 3 | 8 | 120 | 23 | C | 3 |  |  | 30000 | [5 empty] | 30000 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C
| C | LPP | Hinksey Park Attendants Hut | External Repairs and Refurbishment |  |  | A |  |  | 7 |  |  | 7 |  |  | 5 | 10 | 15 | 105 | 22 | B | 3 |  |  | 1500 | [5 empty] | 1500 | R |  |  | 1 | 0 | 1545 | 0 | 0 | 0 | 1545 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
| C | LPP | Bury Knowle Park Pavilion | External refurbishments |  |  | B |  |  | 5 |  |  | 5 |  |  | 10 | 10 | 20 | 100 | 25 | B | 3 |  |  | 5000 | [5 empty] | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  | 5000 | [7 empty] | 5000 |  | Recurring cost every 5 years
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | Roof replacement |  |  | C |  |  |  | 7 |  | 7 |  |  | 3 | 10 | 13 | 91 | 20 | C | 1 |  | 20000 | [6 empty] | 20000 | C |  |  | 3 |  | 0 | 0 | 0 | 0 | 0 | C | [5 empty] | 50000 |  |  |  |  | 50000 | [8 empty] | Bowls club only - changing room part condemned
| C | LPP | Headington Hill Park Shelter and Toilets | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  | 4000 | [6 empty] | 4000 | R | Recurring cost every 5 years |  | 1 | 4120 | 0 | 0 | 0 | 0 | 4120 | R
R070 | CE | LPP | Five Mile Drive RG Clubhouse | External refurbishments |  |  | C |  |  |  | 7 |  | 7 |  |  | 10 | 3 | 13 | 91 | 20 | D | 2 |  |  |  | 10000 |  |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 25000 |  |  |  |  | 25000 | [8 empty] | Buildings future to be considered ~ very poor condition
R040 | C | LPP | Court Place Farm Stadium Pavilion | DDA Works |  |  | Leased |  |  |  | 15 |  | 15 | 3 |  |  | 3 | 6 | 90 | 21 | B | 2 |  |  | 23000 | [5 empty] | 23000 | C |  |  | 4 | 0 | 23690 | 0 | 0 | 0 | 23690 | C | [5 empty] | 15000 |  |  |  | 15000
| C | LPP | Alexandra Courts Changing Rooms | Leased to others |  |  | Leased | 7 |  |  | 7 |  | 14 | 3 |  |  | 3 | 6 | 84 | 20 | C | 2 |  |  | 20000 | [5 empty] | 20000 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C
R007 | C | LPP | Banbury Road North RG Garage | External refurbishments |  |  | Leased | 7 |  |  | 7 |  | 14 | 3 |  |  | 3 | 6 | 84 | 20 | C | 2 |  |  |  |  | 5000 |  |  |  | 5000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | [5 empty] | 5000 |  |  |  |  | 5000
R007 | C | LPP | Banbury Road North RG Pavilion | Leased to others |  |  | Leased | 7 |  |  | 7 |  | 14 | 3 |  |  | 3 | 6 | 84 | 20 | C | 2 |  |  | 23500 | [5 empty] | 23500 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C
R007 | C | LPP | Banbury Road North RG Pavilion | Leased to others |  |  | Leased | 7 |  |  | 7 |  | 14 | 3 |  |  | 3 | 6 | 84 | 20 | C | 2 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 |  | 0 | 0 | R
| C | LPP | Alexandra Courts | Paint entrance gates and repair roadway |  |  | A |  |  |  | 10 |  | 10 |  |  | 3 | 5 | 8 | 80 | 18 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R |  | 545500 | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 1000 |  |  |  |  | 1000
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | External refurbishments |  |  | C |  |  |  | 7 |  | 7 |  |  | 7 | 3 | 10 | 70 | 17 | C | 2 |  |  | 10000 | [5 empty] | 10000 | R | Recurring cost every 5 years |  | 1 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 10000 |  |  |  |  | 10000 | [8 empty] | Bowls club only - changing room part condemned
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | Major internal re-configuration |  |  | C |  |  |  | 7 |  | 7 |  |  | 3 | 3 | 6 | 42 | 13 | C | 1 |  | 75000 | [6 empty] | 75000 | C |  |  | 4 | 77250 | 0 | 0 | 0 | 0 | 77250 | C | [5 empty] | 100000 |  |  |  |  | 100000 | [8 empty] | Bowls club only - changing room part condemned
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | Replace external cladding |  |  | C |  |  |  | 7 |  | 7 |  |  | 3 | 3 | 6 | 42 | 13 | C | 2 |  |  | 10000 | [5 empty] | 10000 | R |  |  | 3 | 0 | 10300 | 0 | 0 | 0 | 10300 | R | [5 empty] | 15000 |  |  |  |  | 15000 | [8 empty] | Bowls club only - changing room part condemned
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | Replacement boilers |  |  | C |  |  |  | 7 |  | 7 |  |  | 3 | 3 | 6 | 42 | 13 | C | 1 |  | 15000 | [6 empty] | 15000 | C |  |  | 3 | 15450 | 0 | 0 | 0 | 0 | 15450 | C | [5 empty] | 15000 |  |  |  |  | 15000 | [8 empty] | Bowls club only - changing room part condemned
| C | LPP | Florence Park Bandstand | Repair and Refurbishment |  |  | A |  |  |  | 3 |  | 3 |  |  | 7 | 7 | 14 | 42 | 17 | B | 3 |  |  |  | 3000 |  |  |  |  | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 3090 | 0 | 0 | 3090 | R | [5 empty] | 3000 |  |  |  |  | 3000 | [8 empty] | Recurring cost every 5 years
R052 | C | LPP | Cutteslowe Park Aviary | External refurbishments |  |  | A |  |  |  | 3 |  | 3 |  |  | 5 | 7 | 12 | 36 | 15 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [5 empty] | 1000 |  |  |  |  | 1000 | [8 empty] | Recurring cost every 5 years
R020 | CE | LPP | Blackbird Leys Park Pavilion and Clubhouse | DDA Improvements |  |  | C |  |  |  | 7 |  | 7 |  |  |  |  | 0 | 0 | 7 | C | 2 |  |  | 22000 | [5 empty] | 22000 | C |  |  | 4 | 0 |  | 0 | 0 | 0 | 0 | C | [19 empty] | Bowls club only - changing room part condemned
R039 | C | LPP | Court Place Farm RG Pavilion | DDA Works |  |  | A |  |  |  | 10 |  | 10 |  |  |  |  | 0 | 0 | 10 | B | 2 |  |  | 22000 | [5 empty] | 22000 | C |  |  | 4 | 0 | 22660 | 0 | 0 | 0 | 22660 | C | [5 empty] | 20000 |  |  |  |  | 20000
| C | LPP | South Park Toilets | Building closed | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | D | [9 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Leisure ~ Pavilions | [41 empty] | 0 | 0 | 0 | 1406500 | 0 | 110500 |  | 470500 | 802000 | 0 | 0 | 75000 | 0 | 10000 | 66000 | 17500 | 7500
| C | M | River Banks | Riparian Repairs |  |  |  | 7 | 7 |  |  |  | 14 | 10 | 10 |  | 7 | 27 | 378 | 41 | ---- | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E227 | C | M | Port Meadow | Reactive Maintenance & Minor Repair |  |  |  |  | 7 | 3 | 7 | 5 | 22 | 7 | 5 |  | 5 | 17 | 374 | 39 | A | 2 | 7000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E230 | C | M | Port Meadow (East of Railway) | Reactive Maintenance & Minor Repair |  |  |  |  | 7 | 3 | 7 | 5 | 22 | 7 | 5 |  | 5 | 17 | 374 | 39 | A | ---- | [8 empty] | 0 | R |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R
E150 | C | M | Morrell's Bridge | Repair and Refurbishment |  |  | A |  |  |  | 3 | 5 | 8 |  | 7 | 10 | 10 | 27 | 216 | 35 | C | 3 |  |  |  | 30000 |  |  |  |  | 30000 | R | Recurring cost every 10 years |  | 1 | 0 | 0 | 30900 | 0 | 0 | 30900 | R | [5 empty] | 50000 |  | 75000 | [10 empty] | 50000 | Recurring cost every 7 years
E289 | C | M | The Plain, Victoria Fountain | Masonry repairs and rainwater goods |  |  |  |  | 5 |  | 3 | 5 | 13 |  |  | 3 | 3 | 6 | 78 | 19 | A | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 3 | 0 | 0 | 10300 | 0 | 0 | 10300 | R
R146 | C | M | St. Giles War Memorial | [5 empty] | 7 |  | 7 |  | 14 |  |  | 5 |  | 5 | 70 | 19 | [10 empty] | 0 | R |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | R
| C | M | Gasworks Bridge | Repair and Refurbishment |  |  | A |  |  |  | 5 |  | 5 |  |  | 7 | 5 | 12 | 60 | 17 | B | 3 |  |  |  | 40000 |  |  |  |  | 40000 | R | Recurring cost every 10 years |  | 1 | 0 | 0 | 41200 | 0 | 0 | 41200 | R | [5 empty] | 50000 | [5 empty] | 50000 | [7 empty] | Recurring cost every 10 years
T025 | C | M | Marston Road War Memorial | Minor repairs |  |  | A |  |  |  | 5 |  | 5 |  |  | 5 | 7 | 12 | 60 | 17 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R |  |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 1000 |  |  |  |  | 1000
E228 | C | M | Port Meadow (Walton Well Road Entrance) | Walton Well Road Fencing and Gates |  |  | A |  |  |  | 7 |  | 7 |  |  | 3 | 5 | 8 | 56 | 15 | B | 3 |  |  |  | 10000 |  |  |  |  | 10000 | R |  |  | 4 | 0 | 0 | 10300 | 0 | 0 | 10300 | R | [5 empty] | 10000 | [6 empty] | 10000
| C | M | Quarry School Place | Landscaping and Seating |  |  | A |  |  |  | 5 |  | 5 |  |  | 3 | 3 | 6 | 30 | 11 | ---- | 3 | [5 empty] | 1000 |  |  | 1000 | R |  |  | 4 | 0 | 0 | 0 | 0 | 1030 | 1030 | R | [5 empty] | 1000 | [5 empty] | 1000
| ----- | M | Alhambra Lane | [7 empty] | 3 |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | ---- | [5 empty] | 3000 |  |  |  | 3000 | R |  |  | 4 | 0 | 0 | 0 | 3090 | 0 | 3090 | R
|  | M | Christ Church Meadow Footbridge | Security Improvements |  |  | A |  |  |  | 3 |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  | 3000 | [6 empty] | 3000 | R |  |  | 4 | 3090 | 0 | 0 | 0 | 0 | 3090 | R | [5 empty] | 2500 | [5 empty] | 2500
E216 | C | M | Northfield / Littlemore Brook | Stream clearance |  |  | A |  |  |  | 3 |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | C | 2 |  |  | 2000 | [5 empty] | 2000 | R |  |  | 2 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 2500 |  |  |  |  | 2500
E216 | C | M | Northfield / Littlemore Brook | Tree works |  |  | A |  |  |  | 3 |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | C | 2 |  |  | 1000 | [5 empty] | 1000 | R |  |  | 2 | 0 | 1030 | 0 | 0 | 0 | 1030 | R | [5 empty] | 1500 |  |  |  |  | 1500
E216 | C | M | Northfield / Littlemore Brook - Bridges | Preservative treatment |  |  | A |  |  |  | 3 |  | 3 |  |  | 3 | 3 | 6 | 18 | 9 | B | 3 |  |  |  | 1500 |  |  |  |  | 1500 | R |  |  | 1 | 0 | 0 | 1545 | 0 | 0 | 1545 | R | [5 empty] | 1500 | [5 empty] | 2000
|  |  | Miscellaneous Properties | [41 empty] | 0 | 0 | 0 | 120000 | 0 | 75000 |  | 0 | 5000 | 55500 | 10000 | 0 | 0 | 0 | 0 | 0 | 50000
T043 | C | PC | Market Street Public Toilets | Brickwork parapet repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 15 | 15 | 30 | 450 | 45 | B | 2 |  |  | 5000 | [5 empty] | 5000 | R |  |  | 1 | 0 | 5150 | 0 | 0 | 0 | 5150 | R | [5 empty] | 2500 | 2500
T043 | C | PC | Market Street Public Toilets | External refurbishments |  |  | A |  |  |  | 15 |  | 15 |  |  | 15 | 7 | 22 | 330 | 37 | B | 2 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [5 empty] | 1000 |  |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  | Recurring cost every 4 years
E332 | C | PC | Oxpens Public Toilets | Rainwater goods repairs |  |  | C |  |  |  | 15 |  | 15 |  |  | 10 | 10 | 20 | 300 | 35 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R |  |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 1000 | [5 empty] | 1000
E332 | C | PC | Oxpens Public Toilets | Refurbishment and minor repairs |  |  | C |  |  |  | 15 |  | 15 |  |  | 10 | 7 | 17 | 255 | 32 | B | 3 |  |  |  | 2500 |  |  |  |  | 2500 | R |  |  | 1 | 0 | 0 | 2575 | 0 | 0 | 2575 | R | [5 empty] | 3000 | [5 empty] | 3000 | [5 empty] | 3000 |  | Recurring cost every 5 years
E336 | C | PC | Gloucester Green Public Toilets | Refurbishment and minor repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 2 |  |  | 5000 |  |  | 5000 |  |  | 10000 | R | Recurring cost every 3 years |  | 1 | 0 | 5150 | 0 | 0 | 5150 | 10300 | R | [5 empty] | 5000 |  |  |  | 5000 | [9 empty] | Recurring cost every 3 years
E258 | C | PC | St. Clements Car Park | Minor Refurbishment | [5 empty] | 15 |  |  | 15 |  |  |  |  | 0 | 0 | 15 | B | 3 |  |  |  | 2000 |  |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 2060 | 0 | 0 | 2060 | R | [19 empty] | TO BE REDEVELOPED
E332 | C | PC | Oxpens Public Toilets | Masonry repairs |  |  | A |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R |  |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [5 empty] | 500 | [5 empty] | 1000
T039 | C | PC | St. Giles / Magdalen Street Public Toilets | External refurbishments |  |  | D/C |  |  |  | 15 |  | 15 |  |  | 10 | 5 | 15 | 225 | 30 | B | 3 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [19 empty] | St Giles toilets closed
T022 | C | PC | Bury Knowle Public Toilets | External refurbishments |  |  | A |  |  |  | 10 |  | 10 |  |  | 5 | 10 | 15 | 150 | 25 | B | 3 |  |  | 2000 | [5 empty] | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 2060 | 0 | 0 | 0 | 2060 | R | [5 empty] | 1500 |  |  |  | 1500 |  |  |  |  | 1500 |  |  | 1500 |  | Recurring cost every 3 years
T002 | C | PC | Abingdon Road Public Toilets | External refurbishments |  |  | A |  |  |  | 7 |  | 7 |  |  | 10 | 10 | 20 | 140 | 27 | B | 3 |  |  | 3000 | [5 empty] | 3000 | R | Recurring cost every 5 years |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R | [5 empty] | 2000 |  |  |  | 2000 |  |  |  |  | 2000 |  |  |  |  | Recurring cost every 5 years
T037 | C | PC | Woodstock Road Public Toilets | External refurbishments |  |  | A |  |  |  | 7 |  | 7 |  |  | 5 | 15 | 20 | 140 | 27 | C | 2 |  |  |  | 1000 |  |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 1030 | 0 | 0 | 1030 | R | [19 empty] | Recurring cost every 5 years
T037 | C | PC | Woodstock Road Public Toilets | Masonry repairs |  |  | A |  |  |  | 7 |  | 7 |  |  | 5 | 15 | 20 | 140 | 27 | C | 2 |  |  |  | 7500 |  |  |  |  | 7500 | R |  |  | 1 | 0 | 0 | 7725 | 0 | 0 | 7725 | R
T037 | C | PC | Woodstock Road Public Toilets | Reroof and reconstruct roof light |  |  | A |  |  |  | 7 |  | 7 |  |  | 5 | 15 | 20 | 140 | 27 | C | 2 |  |  |  | 5000 |  |  |  |  | 5000 | C |  |  | 3 | 0 | 0 | 5150 | 0 | 0 | 5150 | C
T044 | C | PC | Knights Road Public Toilets | External refurbishments |  |  | A |  |  | 7 |  |  | 7 |  |  | 5 | 10 | 15 | 105 | 22 | B | 3 |  |  |  | 500 |  |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 515 | 0 | 0 | 515 | R | [5 empty] | 500 |  |  |  | 500 | [6 empty] | 500 |  |  | Recurring cost every 5 years
T007 | C | PC | Barns Road Public Toilets | External refurbishments |  |  | A |  |  |  | 10 |  | 10 |  |  | 5 | 5 | 10 | 100 | 20 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [5 empty] | 1500 |  |  |  | 1500 | [9 empty] | Recurring cost every 5 years
H060 | C | PC | Littlemore Public Toilets | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 |  |  |  |  | 1000 |  |  |  | 1000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 1030 | 0 | 1030 | R | [19 empty] | CLOSED
T033 | C | PC | South Parade Public Toilets | Refurbishments and minor repairs |  |  | A |  |  |  | 10 |  | 10 |  |  | 5 | 3 | 8 | 80 | 18 | B | 3 |  | 2500 | [6 empty] | 2500 | R | Recurring cost every 5 years |  | 1 | 2575 | 0 | 0 | 0 | 0 | 2575 | R | [19 empty] | Recurring cost every 5 years
T062 | C | PC | Speedwell Street Public Toilets | External refurbishments |  |  | A |  |  |  | 7 |  | 7 |  |  | 5 | 5 | 10 | 70 | 17 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 500 |  |  |  |  | 1000 | [8 empty] | Recurring cost every 5 years
T062 | C | PC | Speedwell Street Public Toilets | Replace rainwater goods |  |  | A |  |  |  | 7 |  | 7 |  |  | 5 | 5 | 10 | 70 | 17 | B | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 1 | 0 | 0 | 0 | 2060 | 0 | 2060 | R | [5 empty] | 500 |  |  |  |  | 1000
E309 | C | PC | Castle Street Public Toilets | External refurbishments | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | A | 3 |  |  |  |  | 500 |  |  |  | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 515 | 0 | 515 | R | [19 empty] | CLOSED
T041 | C | PC | St. Bernards Road Public Toilets | External refurbishments |  |  | A |  |  |  | 5 |  | 5 |  |  | 5 | 3 | 8 | 40 | 13 | B | 3 |  |  | 500 | [5 empty] | 500 | R | Recurring cost every 5 years |  | 1 | 0 | 515 | 0 | 0 | 0 | 515 | R | [19 empty] | Recurring cost every 5 years
T013 | C | PC | Cowley Road Public Toilets | Likely redevelopment site |  |  | C | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | B | 3 | [8 empty] | 0 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | R | [19 empty] | TO BE REDEVELOPED
H004 | C | PC | Ashhurst Way Public Toilets | External refurbishments | [6 empty] | 3 |  | 3 |  |  |  |  | 0 | 0 | 3 | D | 3 |  |  | 3000 | [5 empty] | 3000 | R |  |  | 1 | 0 | 3090 | 0 | 0 | 0 | 3090 | R
E333 | C | PC | Westgate Public Toilets |  |  |  | C |  |  |  | 15 |  | 15 |  |  |  |  | 0 | 0 | 15 | B | [9 empty] | 0 | R |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | R
|  |  | Public Toilets | [41 empty] | 0 | 0 | 0 | 19500 | 2500 | 0 |  | 11500 | 2000 | 5000 | 0 | 1000 | 3500 | 0 | 500 | 5500 | 0
E259 | C | SAC | St Aldates Chambers | Decorate Main Staircase | [5 empty] | 15 |  |  | 15 |  |  | 5 |  | 5 | 75 | 20 | B | 3 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [19 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | External refurbishments | [5 empty] | 15 |  |  | 15 |  |  | 10 |  | 10 | 150 | 25 | B | 3 |  |  |  |  | 20000 |  |  |  | 20000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 0 | 20600 | 0 | 20600 | R | [13 empty] | 20000 |  |  |  |  | 20000 | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Hot Water & Heating System Refurbishment and Upgrading | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 3 |  |  | 55000 | [5 empty] | 55000 | C |  |  | 3 | 0 | 75000 | 0 | 0 | 0 | 75000 | C |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Lighting Improvements | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 3 | [5 empty] | 10000 |  |  | 10000 | C |  |  | 3 | 0 | 0 | 0 | 0 | 10300 | 10300 | C |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Main foyer and reception Refurbishment | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 2 | 2000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Reactive Maintenance & Minor Repair | [5 empty] | 15 |  |  | 15 |  |  |  |  | 0 | 0 | 15 | B | 1 | 20000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Repair Felt Roof | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 2 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Replacement Windows and Concrete repairs | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 3 |  |  |  |  | 75000 |  |  |  | 75000 | C |  |  | 3 | 0 | 0 | 0 | 77250 | 0 | 77250 | C |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Repoint Brickwork | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 3 |  |  |  |  | 15000 |  |  |  | 15000 | C |  |  | 3 | 0 | 0 | 0 | 15450 | 0 | 15450 | C |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Second Floor Toilets Refurbishment and Upgrading | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 2 |  |  |  |  | 20000 |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 0 | 25000 | 0 | 25000 | C |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Services Maintenance | [5 empty] | 15 |  |  | 15 | 15 | 15 |  | 15 | 45 | 675 | 60 | B | 1 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R |  | 0 | [17 empty] | Offices for the Future Project
E259 | C | SAC | St Aldates Chambers | Third Floor Toilets Refurbishment and Upgrading | [5 empty] | 15 |  |  | 15 |  |  | 15 |  | 15 | 225 | 30 | B | 2 |  |  |  | 20000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 0 | 25000 | 0 | 0 | 25000 | C |  | #REF! | [17 empty] | Offices for the Future Project
|  |  | St Aldates Chambers | [41 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 20000 | 0 | 0 | 0 | 0 | 20000
E290 | C | TH | Town Hall | Reactive Maintenance & Minor Repair |  |  |  |  | 15 | 15 | 10 | 7 | 47 | 15 | 15 |  | 15 | 45 | 2115 | 92 | A | 2 | 25000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E290 | C | TH | Town Hall | Services Maintenance |  |  |  |  | 15 | 15 | 10 | 7 | 47 | 15 | 15 |  | 15 | 45 | 2115 | 92 | A | 2 | 20000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E290 | C | TH | Town Hall | 1930's Extension - Parapet Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 3 |  |  |  | 8000 |  |  |  |  | 8000 | R |  |  | 1 | 0 | 0 | 8240 | 0 | 0 | 30000 | R | 30000 | 30000 |  |  | 25000
E290 | C | TH | Town Hall | Flagpole Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 3 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 0 | 5150 | 0 | 5150 | R | 5000 | 35000 |  |  |  | 10000 | 10000
E290 | C | TH | Town Hall | Main Hall - Repair and decorate walls, doors windows etc |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 3 |  |  | 100000 | [5 empty] | 100000 | R |  |  | 1 | 0 | 103000 | 0 | 0 | 0 | 103000 | R | 20000 | 55000 |  |  |  | 15000 | 15000 | [7 empty] | 15000 |  |  | 15000 |  | Recurring cost every 3 years
E290 | C | TH | Town Hall | PA System improvements |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 3 |  |  |  | 8000 |  |  |  |  | 8000 | R |  |  | 1 | 0 | 0 | 8240 | 0 | 0 | 8240 | C | 8000 | 63000 |  |  | 30000
E290 | C | TH | Town Hall | Repair / replace Rainwater Goods |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 3 |  |  | 5000 | [5 empty] | 5000 | C |  |  | 1 | 0 | 20000 | 0 | 0 | 0 | 20000 | C | 10000 | 73000 |  |  | 17989 | 10000 |  | 10000 | ü
E290 | C | TH | Town Hall | Roofs - Repair, Recovering and Up-grading |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 15 | 10 | 25 | 1175 | 72 | A | 2 |  |  | 10000 | 10000 |  |  |  |  | 20000 | C |  |  | 3 | 0 | 20000 | 20000 | 0 | 0 | 40000 | C | 10000 | 83000 |  |  |  | 40000 | 20000 | 20000
E290 | C | TH | Museum of Oxford | Reactive Maintenance & Minor Repair |  |  | A |  |  | 10 | 7 | 7 | 24 | 15 | 15 |  | 15 | 45 | 1080 | 69 | B | 2 | 10000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E290 | C | TH | Museum of Oxford | Services Maintenance |  |  | A |  |  | 10 | 7 | 7 | 24 | 15 | 15 |  | 15 | 45 | 1080 | 69 | B | 2 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R
E290 | C | TH | Town Hall | External refurbishment and Masonry Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 7 | 17 | 799 | 64 | A | 3 |  |  |  | 50000 |  |  |  |  | 50000 | R | Recurring cost every 5 years |  | 1 | 0 | 0 | 51500 | 0 | 0 | 51500 | R | 20000 | 20000 |  |  |  | 50000 |  | 50000 | [8 empty] | 50000 |  |  | Recurring cost every 5 years
E290 | C | TH | Town Hall | Main Hall - roof repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 7 | 17 | 799 | 64 | A | 1 |  | 20000 | [6 empty] | 20000 | R |  |  | 3 | 20600 | 0 | 0 | 0 | 0 | 20600 | R |  | 20000 |  |  |  | 20000 |  | 20000
E290 | C | TH | Town Hall | Pigeon Netting |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  | 10 |  | 7 | 17 | 799 | 64 | A | 3 |  |  |  |  | 2000 |  |  |  | 2000 | R |  |  | 4 | 0 | 0 | 0 | 5000 | 0 | 5000 | R | 5000 | 25000 |  |  | 5000
E290 | C | TH | Town Hall | Staff Toilet Refurbishments |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 7 | 17 | 799 | 64 | A | 3 | [16 empty] | 30000 |  | 30000 | R |  | 25000 |  |  |  | 10000 | 10000 |  |  |  |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | Recurring cost every 2 years
E290 | C | TH | Town Hall | Hot Water & Heating Systems - Refurbishment and Upgrading |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 5 | 15 | 705 | 62 | A | 2 |  |  | 60000 | [5 empty] | 60000 | C |  |  | 3 | 0 | 61800 | 0 | 0 | 0 | 61800 | C |  | 25000 |  |  |  | 75000 |  |  |  | 75000
E290 | C | TH | Town Hall | Window and Leaded Light Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 5 | 15 | 705 | 62 | A | 3 |  |  | 10000 | 10000 |  |  |  |  | 20000 | R |  |  | 1 | 0 | 10300 | 10300 | 0 | 0 | 20600 | R | 10000 | 35000 |  |  |  | 5000 |  | 5000 |  |  |  | 5000 |  |  | 5000 |  | 5000 |  | 5000 | Recurring cost every 2 years
E290 | C | TH | Town Hall | Basement Toilet Refurbishment |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 3 | 10 | 13 | 611 | 60 | A | 3 | [5 empty] | 10000 |  |  | 10000 | C |  |  | 4 | 0 | 0 | 0 | 0 | 10300 | 10300 | C | [5 empty] | 15000 | [5 empty] | 15000
E290 | C | TH | Town Hall | Blue Boar Street Toilets - Incorporate into Town Hall |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 10 | 3 | 13 | 611 | 60 | A | 3 |  |  |  | 30000 |  |  |  |  | 30000 | C |  |  | 4 | 0 | 0 | 30900 | 0 | 0 | 30900 | C |  | 0 | [17 empty] | Options appraisal required to define scheme proposals
E290 | C | TH | Town Hall | Kitchen Refurbishments |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 7 | 5 | 12 | 564 | 59 | A | 3 |  |  |  |  | 10000 |  |  |  | 10000 | R |  |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R |  | 0 |  |  |  | 5000 |  | 20000 | ü |  | 5000 |  |  |  | 5000 |  | 5000 |  | 5000 | Recurring cost every 2 years
E290 | C | TH | Town Hall | Lightning Conductor |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  | 7 |  | 5 | 12 | 564 | 59 | A | 2 |  |  |  | 5000 |  |  |  |  | 5000 | R |  |  | 1 | 0 | 0 | 5150 | 0 | 0 | 5150 | R |  | 0 |  |  |  | 5000 | 5000
E290 | C | TH | Town Hall | Council Chamber - Redecorate Ceiling |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 5 | 10 | 470 | 57 | A | 3 | [6 empty] | 2008/09 | 25000 | 25000 | R |  |  | 1 | 0 | 0 | 0 | 0 | 25750 | 25750 | R |  | 0 |  |  |  | 25000 |  | 25000 | ü | [9 empty] | 25000 | Recurring cost every 7 years
E290 | C | TH | Town Hall | Emergency Lighting Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  | 5 |  | 5 | 10 | 470 | 57 | A | 2 |  |  | 15000 | [5 empty] | 15000 | R |  |  | 1 | 0 | 15450 | 0 | 0 | 0 | 15450 | R |  | 0 |  |  |  | 15000 | 15000
E290 | C | TH | Town Hall | Internal refurbishments |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 7 | 3 | 10 | 470 | 57 | A | 3 | 5000 | [7 empty] | 0 | R |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | R | 10000 | 10000 |  |  |  | 10000 | 10000 | 10000 | ü |  | 10000 |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | Annual cost
E290 | C | TH | Town Hall | Old Library - Form Storage Under Balcony |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 7 | 3 | 10 | 470 | 57 | A | 3 |  |  |  |  | 20000 |  |  |  | 20000 | R |  |  | 4 | 0 | 0 | 0 | 25000 | 0 | 25000 | R |  | 10000 |  |  |  | 25000 | [5 empty] | 25000
|  |  | Town Hall | External refurbishment of Courtyards | [45 empty] | 120000
|  |  | Town Hall | Refurbishment / Upgrade of main toilets | [45 empty] | 200000 | ü
|  |  | Town Hall | Heating and Ventilation Improvements | [45 empty] | 100000
|  |  | Town Hall | Fire Risk Assessment Upgrading Works | [45 empty] | 65000 | ü
E290 | C | TH | Town Hall | Alternative fire exit (avoiding Blue Boar Offices) |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  | 5 |  | 3 | 8 | 376 | 55 | A | 3 |  |  |  | 30000 |  |  |  |  | 30000 | C |  |  | 4 | 0 | 0 | 30900 | 0 | 0 | 30900 | C |  | #REF! | [17 empty] | Included as part of Offices for the Future project
E290 | C | TH | Town Hall | Assembly Room - Strip, Sand and Reseal Floor |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 2 |  |  |  |  | 10000 |  |  |  | 10000 | R | Recurring cost every 3 years |  | 1 | 0 | 0 | 0 | 10300 | 0 | 10300 | R |  | #REF! |  |  |  | 10000 |  | 10000 | [5 empty] | 10000 |  |  | 10000 |  |  | Recurring cost every 3 years
E290 | C | TH | Town Hall | Assembly Room Electrical Sockets |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 2 |  |  |  |  | 5000 |  |  |  | 5000 | R |  |  | 4 | 0 | 0 | 0 | 5150 | 0 | 5150 | R |  | #REF! |  |  |  | 2500 |  |  |  | 2500
E290 | C | TH | Town Hall | Basement - Replace Lead Pipes |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  | 5 |  | 3 | 8 | 376 | 55 | A | 3 | [5 empty] | 6000 |  |  | 6000 | R |  |  | 4 | 0 | 0 | 0 | 0 | 6180 | 6180 | R |  | #REF! |  |  |  | 5000 |  | 5000 | ü
E290 | C | TH | Town Hall | Basement Archive Room Refurbishment |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 3 | [5 empty] | 6000 |  |  | 6000 | R |  |  | 4 | 0 | 0 | 0 | 0 | 6180 | 6180 | R |  | #REF! |  |  |  | 7500 |  | 7500 | ü
E290 | C | TH | Town Hall | Blue Boar Street Elevation - Install Exit Door Gates & Masonry Repairs |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 3 |  |  |  |  | 15000 |  |  |  | 15000 | R |  |  | 4 | 0 | 0 | 0 | 15450 | 0 | 15450 | R |  | #REF! |  |  |  | 15000 | [5 empty] | 15000
E290 | C | TH | Town Hall | Main Hall - Repair and Decorate Ceiling |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 3 | 5 | 8 | 376 | 55 | A | 3 |  |  | 100000 | [5 empty] | 100000 | R |  |  | 3 | 0 | 103000 | 0 | 0 | 0 | 103000 | R | [5 empty] | 100000 | 15000 |  |  | 85000
E290 | C | TH | Town Hall | Main hall - Replacement ventilation system |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 3 |  |  | 200000 | [5 empty] | 200000 | C |  |  | 3 | 0 | 206000 | 0 | 0 | 0 | 206000 | C |  | 0 |  |  |  | 100000 | 100000
|  |  | Town Hall | Fire Alarm replacement | [44 empty] | 100000
E290 | C | TH | Town Hall | Removal of Redundant Services |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 5 | 3 | 8 | 376 | 55 | A | 3 | [5 empty] | 10000 |  |  | 10000 | R |  |  | 3 | 0 | 0 | 0 | 0 | 10300 | 10300 | R |  | 0 |  |  |  | 10000 |  | 10000
E290 | C | TH | Town Hall | Blue Boar Street Elevation - Window Grilles Alterations |  |  | A |  | 15 | 15 | 10 | 7 | 47 |  |  | 3 | 3 | 6 | 282 | 53 | A | 3 | [5 empty] | 5000 |  |  | 5000 | R |  |  | 4 | 0 | 0 | 0 | 0 | 5150 | 5150 | R | [5 empty] | 2000 |  |  |  | 2000
|  |  | Town Hall | [41 empty] | 0 | 0 | 77989 | 587000 | 300000 | 677500 |  | 164500 | 15000 | 70000 | 0 | 30000 | 35000 | 20000 | 80000 | 35000 | 45000
|  |  | Old Fire Station |  |  |  |  | 10 |  |  | 10 |  | 20 |  |  | 3 |  | 3 | 60 | [23 empty] | 0 | 0
|  |  | All Properties | Surveys |  |  |  | 15 |  |  |  |  | 15 | 15 | 15 |  |  | 30 | 450 | [22 empty] | R | [5 empty] | 150000 | 100000 | 50000 | [5 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
|  |  | Property Surveys | [41 empty] | 0 | 0 | 0 | 150000 | 100000 | 50000 |  | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 |  |  |  |  | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0